## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | October 2016-October 2017
| Project Title: | Promoting climate resilience in the rice sector through pilot investments in Alaotra-Mangoro Region
| Project Summary: | In the framework of the implementation of its NAPA, the Government of the Republic of Madagascar has recieved support from the Adaptation Fund for the implementation of the project "PROMOTING CLIMATE RESILIENCE IN THE RICE SECTOR THROUGH PILOT INVESTMENTS IN ALAOTRA-MANGORO REGION", which seeks to transform the rice sub-sector towards building resilience to impacts of climate change. The project is comprised of three components: 1) strengthening of technical and scientific capacities, 2) implementation of a rice production cycle that is resilient and adapted, and 3) leveraging policy change in the rice sector. The project is implemented in the Alaotra-Mangoro region, the primary rice production area in Madagascar, in three pilot districts. The project is executed by the Ministry of Environment and Forests, and works at the local level with producers and local partners, along with decentralised ministries and regional technical partners.
|  |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AFB-5060-1111-2G49 | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UN Environment (UNEP) | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | MADAGASCAR | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The Alaotra Mangoro region is located in the Center-East of Madagascar. The region covers 33 054 Km². and is comprised of 5 Districts, which are sub-divided into 79 communes. The regional capital is Ambatondrazaka, approximately 250 Km from Antananarivo. The project is working in the three districts of Andilamena (8 communes), Amparafaravola (20 communes), and Ambatondrazaka (20 communes). The Alaotra-Mangoro region contains many bodies of water and rivers, Lake Alaotra being the most important lake in the region, with an area of 20 000 ha. | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[5 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones |  |  |  | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone | [5 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2011-12-14
IE-AFB Agreement Signature Date: |  | 2012-03-01 |  |  |  | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-10-01 |  |  |  | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | December 2015 - March 2016 (completed)
| Terminal Evaluation Date: | December 2018 (expected)
List documents/ reports/ brochures / articles that have been prepared about the project.
Radio Broadcast (AMOMIX and RDB) and TV Broadcast (TVM Alaotra Mangoro); 1 documentary film on crop rotation (rice and vegetables) with CALA experts; 1 documentary film on sensitizing farmers during the training on compost production by the STOI-MIN expert; Broadcasting programs on MIRR practices on local TV and radio (AMOMIX, RDB) in Ambatondrazaka every Sunday (10mn) and TVM Alaotra Mangoro; Awareness-raising posters, flyers and pamphlets; Panels and displays outlining the general objectives, specific objectives and method of work of the AF RICE project; Website creation and forum; AFRice stand at the International Agricultural Fair
List the Website address (URL) of project.
www.mef.gov.mg
Project contacts:
National Project Manager/Coordinator
| Name: | RAZANAMIHARISOA Jane Alice
| Email: | jrazanamiharisoa@ymail.com
| Date: | 2013-12-10
Government DA
| Name: | Nivoary RAMAROSON
| Email: | nivoohary@yahoo.fr
| Date: | 2016-07-15
Implementing Entity
| Name: | Anna Kontorov, UN Environment (UNEP) Task Manager
| Email: | anna.kontorov@un.org
| Date: | 2017-07-01
Executing Agency
Name:
Email:
Date:
Executing Agency
Name:
Email:
Date:
Executing Agency
Name:
Email:
Date:

## FinancialData
Financial information: cumulative from project start to OCTOBER 2016-OCT 2017
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Cumulative total disbursement as of 30 September 2017 |  | 2546096
Add any comments on AF Grant Funds. (word limit=200)
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period (Oct 2016 - 30 Sept 2017) |  | Output | AMOUNT
|  | Output 1.1.1 Best Available Technologies and Integrated Resilient Rice Model (Modèle Intégré de Riziculture Résiliente - MIRR) selected and publicized | 0
|  | 1.2.1 Crop models are available for rice vulnerability mapping | 3 600
|  | 1.2.2 Updated, dynamic agricultural calendars and climate early warnings taking into account current and projected variability disseminated to local population | 7 029
|  | 1.2.3 Agricultural extension staff trained on climate risk management in an agro-ecosystem context | 22 800
|  | 2.1.1 climate resilient rice varieties selected through participatory field testing | 9 186
|  | 2.1.2 An operational multiplication and dissemination scheme for adapted seed varieties | 36 000
|  | 2.1.3 Updated fertilisation guidelines according to best available standards and taking climate conditions into consideration | 36 987
|  | 2.1.4 Integrated pest management is implemented | 22 400
|  | 2.1.5 Water efficiency, management and conservation technologies and infrastructures are implemented | 56 640
|  | 2.2.1 Best available land preparation, production and harvesting techniques disseminated to reduce deforestation, maintain soil fertility and integrity, and to provide adequate growing conditions | 37 200
|  | 2.2.2 Watershed rehabilitation in productive landscapes introduced, including through reforestation and adaptation of agroforestry practices | 112 300
|  | 2.2.3 Soil conservation and livestock management techniques adapted to topography and landscape in light of future climate conditions | 22 500
|  | 2.2.4 Revitalization of producer’s cooperatives and water user associations for collaborative natural resources allocations (e.g. land and water) and management | 36 300
|  | 2.2.5 Water quality assessments | 5 600
|  | 2.3.1 Increased utilization of rice by-product especially rice straw | -
|  | 2.3.2 Post-harvest storage facilities with phytosanitary control, serving as trading points and markets | 42 555
|  | 3.1.1 gaps and possible maladaptations in the current rice policy are identifed and recommendations on upscaling project outcomes towards rice policy reform are made | 16 800
|  | 3.2.1 a report on best practices and lessons learned for rice adaptation in madagascar | 7 700
|  | 3.2.2 A strategy for communicating information on adaptation techniques to farmers is implemented | 21 478
|  | Cross-cutting costs Component 1 | 9 000
|  | Cross-cutting costs Component 2 | 9 000
|  | Cross-cutting costs Component 3 | 9 931
|  | Project operations/Execution costs | 113 930
|  | TOTAL | 638 936
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | Output | ITEM | PROJECTED COST | Est. Completion Date
1.1.1 Best Available Technologies and Integrated Resilient Rice Model (Modèle Intégré de Riziculture Résiliente - MIRR) selected and publicized
|  | Publication services | 15 000 | Q1 2018
1.2.1 Crop models are available for rice vulnerability mapping
|  | NC for data acquisition to perform rice modelling | 1 000 | Q1 2018
|  | National agriculture modelling expert | 1 000 | Q1 2018
|  | NC expert SIG | 6 400 | Q4 2017
1.2.2 Updated, dynamic agricultural calendars and climate early warnings taking into account current and projected variability disseminated to local population
|  | National Consultant meteorologist | 10 500 | Q4 2017
|  | Sub-contract with National Radio | 18 000 | Q1 2018
| Cross-cutting component costs | Project Coordinator | 4 000 | Q1 2018
1.2.3 Agricultural extension staff trained on climate risk management in an agro-ecosystem context
|  | National agroforestery expert | 45 000 | Q4 2017
|  | Climate Risk Management workshop | 20 000 | Q4 2017
2.1.1 climate resilient rice varieties selected through participatory field testing
|  | Agricultural inputs (seeds, fertilizers, land and tools) | 90 814 | Q1 2018
2.1.2 An operational multiplication and dissemination scheme for adapted seed varieties
|  | Sub-contract with CALA (pre-base seeds) | 45 000 | Q2 2018
2.1.3 Updated fertilisation guidelines according to best available standards and taking climate conditions into consideration
|  | Sub-contract with CALA for soil quality analysis | 16 000 | Q4 2017
|  | National Soil quality Expert | 4 500 | Q4 2017
2.1.4 Integrated pest management is implemented
|  | IPM training workshop | 30 000 | Q1 2018
|  | Aquisition of IPM and phytosanitary equipment | 18 000 | Q1 2018
|  | IPM Expert | 9 600 | Q4 2017
| Cross-cutting component costs | Project Coordinator | 4 000 | Q4 2017
2.1.5 Water efficiency, management and conservation technologies and infrastructures are implemented
|  | Sub-contracts with water engineering firms | 775 000 | Q4 2017
|  | Water management and infrastructure specialist | 37 600 | Q4 2017
2.2.1 Best available land preparation, production and harvesting techniques disseminated to reduce deforestation, maintain soil fertility and integrity, and to provide adequate growing conditions
|  | Local MIRR training | 18 000 | Q1 2018
|  | National riziculture experts | 26 600 | Q4 2017
|  | Training workshops for local leaders | 18 000 | Q1 2018
|  | National agroforestery expert | 40 000 | Q4 2017
|  | Sub-contract with MinAgri - vulgarisation agricole | 21 000 | Q1 2018
| Cross-cutting component costs | Project Coordinator | 4 000 | Q1 2018
2.2.2 Watershed rehabilitation in productive landscapes introduced, including through reforestation and adaptation of agroforestry practices
|  | NC-resilient species study | 6 000 | Q4 2017
|  | Sub-contracts for three NGOs for reforestation work | 63 000 | Q1 2018
|  | Sub-contracts with new NGOs for reforestation for 2018 | 229 230 | Q2 2018
2.2.3 Soil conservation and livestock management techniques adapted to topography and landscape in light of future climate conditions
|  | Sub-contract with NGO MAHARITRA | 52 500 | Q4 2017
|  | Livestock expert | 18 000 | Q1 2018
| Cross-cutting component costs | Project Coordinator | 4 000 | Q1 2018
2.2.4 Revitalization of producer’s cooperatives and water user associations for collaborative natural resources allocations (e.g. land and water) and management
|  | Water user Association training workshop | 20 000 | Q1 2018
|  | Community Based Natural Resources management expert | 11 700 | Q4 2017
|  | Equipment and office supplies for WUG | 10 000 | Q1 2018
2.2.5 Water quality assessments
|  | National water quality expert | 4 400 | Q4 2017
2.3.1 Increased utilization of rice by-product especially rice straw
|  | Workshops on rice by-products | 30 000 | Q1 2018
2.3.2 Post-harvest storage facilities with phytosanitary control, serving as trading points and markets
|  | Civil Engineer | 12 600 | Q4 2017
|  | Sub-contract private sector firm | 100 120 | Q4 2017
|  | Training on community-managed reserves | 10 000 | Q1 2018
|  | National Consultant - Community managed storage | 15 000 | Q1 2018
Cross-cutting component costs
|  | Local Technicians (3) | 6 300 | Q2 2018
|  | Office supplies for Local Technicians (3) | 4 000 | Q2 2018
|  | Operating costs for regional directorates (fuel and expendables) | 3 000 | Q2 2018
|  | Materials and supplies for Local Technicians | 3 000 | Q1 2018
|  | Driver | 1 925 | Q2 2018
|  | Vehicles (incl. 3 motorcycles) and maintenance | 6 200 | Q2 2018
3.1.1 Gaps and possible maladaptations in the current rice policy are identifed and recommendations on upscaling project outcomes towards rice policy reform are made
|  | National agriculture task force consultant | 28 000 | Q1 2018
|  | National rice policy consultant | 22 000 | Q1 2018
|  | Meeting and workshop of upscaling MIRR | 15 000 | Q2 2018
|  | National market analysis consultant | 30 000 | Q1 2018
3.2.1 A report on best practices and lessons learned for rice adaptation in Madagascar
|  | National agriculture policy consultant | 3 670 | Q1 2018
| 3.2.2 A strategy for communicating information on adaptation techniques to farmers is implemented | National Rural communication specialist | 18 000 | Q2 2018
|  | Awareness-raising meetings and workshops | 35 000 | Q2 2018
4. Project/Programme Execution costs
|  | Project Coordinator | 12 000 | Q2 2018
|  | National financial manager | 11 250 | Q2 2018
|  | Administrative support | 7 497 | Q2 2018
|  | Travel for PM | 12500 | Q2 2018
|  | Office equipment and expendables (PCU) | 5000 | Q2 2018
|  | Communication, translation and printing costs | 5000 | Q2 2018
|  | Final evaluation | 35000 | Q2 2018
|  | M&E Officer | 7 497 | Q2 2018
|  | Audit | 7500 | Q2 2018
|  | Inception and steering committee meetings | 9000 | Q2 2018
|  | TOTAL | 2 153 903
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement (hidden)
PROCUREMENT DATA |  |  | 01 Oct 2016 to 30 Sept 2017
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  | 1
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Contract Number | budget code | Payment to Date | Remaining Balance
Long-term Contract | Mme Jane Razanamiharisoa | 91500 | 2012-sep-08 | 01/12 | 1101 | 54000 | 37500
Long-term Contract | Mr. Tahiry Herilalaina | 76250 | 2012-sep-08 | 02/12 | 1102 | 45000 | 31250
Long-term Contract | Mr. Marcellin Lalason | 50813 | 2012-sep-08 | 03/12 | 1301 | 39996 | 10817
Individual Consultancy contract | Mme JOANA Talafré | 120000 | 2013-02-20 | 04/13 | 1212 | 60496 | 59504
Consultancy contract | Gaétan QUESNE and Henri Rakotobe | 35792 | 2013-02-27 | 05/13 | 5501 | 35792 | 0
Consultancy Contract | Madame RAKOTOARISOA Jacqueline and Monsieur Rabeson Raymond | 60000 | 2013-06-26 | 06/13 | 1201 | 60000 | 0
Contract amendment with additional costs | Madame RAKOTOARISOA Jacqueline and Monsieur Rabeson Raymond | 25350 | 2014-09-05 | 06/13 amendment | 1201 | 25350 | 0
Individual Consultancy contract | Madame RASOAFALIMANANA Mbolarinosy | 50000 | 2013-06-26 | 07/13 | 1207 | 50000 | 0
Individual Consultancy contract | Monsieur Rabeson Raymond | 6000 | 2013-09-12 | 07bis/13 | 1201 | 6000 | 0
Individual Consultancy contract | Mr. Ratsimbazafy Tiana | 15000 | 2014-07-23 | 08/14 | 1230 | 15000 | 0
Individual Consultancy contract | Monsieur Andrianirina Michelliarson | 15000 | 2014-07-23 | 09/14 | 1215 | 6000 | 9000
Individual Consultancy contract | Monsieur Rakotoarison Levy | 60000 | 2014-08-20 | 10/13 | 1209 | 60000 | 0
Individual Consultancy contract | Mr. Randrianoro Désiré | 1000 | 2014-02-04 | 11/14 | 5401 | 0 | 1000
Individual Consultancy contract | Mr. Ratsimbazafy Jean-Pierre | 5000 | 2014-03-17 | 12 bis/14 | 1201 | 1620 | 3380
Individual Consultancy contract | Razafindrakoto Helison Romuald | 25000 | 2013-03-07 | 12/14 | 1204 | 25000 | 0
Individual Consultancy contract | Andriamalantomanga Tsiory Dimbimalala | 52600 | 2014-03-07 | 13/14 | 1225 | 14420 | 38180
Individual Consultancy contract | Rabemanantsoa Heritiana Adrianala | 14000 | 2014-03-17 | 14/14 | 1219 | 14000 | 0
Individual Consultancy contract | Ranaivojaona Harinomejanahary Voahanginirina | 9000 | 2014-03-28 | 15/14 | 1227 | 3600 | 5400
Individual Consultancy contract | Rasamison Jules | 9000 | 2014-03-28 | 16/14 | 1227 | 3600 | 5400
Individual Consultancy contract | Randriafiraisampiremena Jules | 9000 | 2014-03-28 | 17/14 | 1227 | 3600 | 5400
MOU | Silo Nationale des Graines Forestieres (SNGF) | 201500 | 2014-04-25 | MOU-1 | 2102 | 80600 | 120900
Long-term Contract | RAMAROSOA Erick Lauret | 11550 | 2014-07-25 | 20/14 | 1228 | 3575 | 7975
MOU | CALA | 180000 | 2014-09-08 | MOU-2 | 2309 | 108000 | 72000
MOU | STOI AGRI (Société Trading de l'Ocean Indien) | 258050 | 2014-11-28 | MOU | 2302 | 77013 | 181037
MOU | International Rice Research Institute | 35000 | 2014-09-22 | MOU-3 | 2204 | 35000 | 0
Individual Consultancy contract | JOELIBARISON | 50000 | 2015-05-18 | 022/15 | 1206 | 35000 | 15000
Individual Consultancy contract | RAZAFINDRAKOTO CHARLOTTE | 74000 | 2015-05-18 | 029/15 | 1213 | 22200 | 51800
Individual Consultancy contract | RAKITRINIAINA Mandarimiorandraibe | 30000 | 2015-05-18 | 024/15 | 1214 | 21000 | 9000
Individual Consultancy contract | RAFALIMANANTSOA JULE | 20000 | 2015-05-18 | 026/15 | 1216 | 14000 | 6000
Individual Consultancy contract | RAKOTOARISOA NY HERY MIANDRAZO | 20000 | 2015-05-18 | 028/15 | 1217 | 14000 | 6000
Individual Consultancy contract | SYLVAIN RODOLPHE Ralaiarimalala | 50000 | 2015-05-20 | 027/15 | 1218 | 35000 | 15000
Individual Consultancy contract | RANAIVOARISOA JOPELANA Toavina | 76000 | 2015-05-18 | 025/15 | 1223 | 53200 | 22800
Individual Consultancy contract | RANDRIANORO DESIRE | 35000 | 2015-05-20 | 023/15 | 1229 | 24500 | 10500
Individual Consultancy contract | RANDRIAMANANAZY GILLES | 68000 | 2015-08-20 | 030/15 | 1226 | 6800 | 61200
Individual Consultancy contract | ANDRIANAHARINOSY Mireille Natacha | 14500 | 2015-11-23 | 031/15 | 1205 | 14500 | 8700
Individual Consultancy contract | ANDRIANASOLO Miravola | 20000 | 2017-03-14 | 033/17 | 1225 | 7000 | 13000
Individual Consultancy contract | RAZAFINDRAKOTO Charlotte | 32000 | 2017-04-03 | 034/17 | 1211 | 22400 | 9600
Individual Consultancy contract | RANDRIAMANARINTSOA Manajaniaina | 28000 | 2017-04-04 | 035/17 | 1224 | 19600 | 8400
Individual Consultancy contract | RALAIARIMALALA Sylvain Rodolphe | 25000 | 2017-05-12 | 036/17 | 1231 | 10000 | 15000
Individual Consultancy contract | ANTILAHY Herimpitia Estelle Rollande | 11000 | 2017-04-27 | 037/17 | 1243 | 4400 | 6600
Individual Consultancy contract | ANDRIANIRINA Michelliarison | 8000 | 2017-04-28 | 038/17 | 1215 | 5600 | 2400
Individual Consultancy contract | RAKITRINIAINA Mandarimiorandraibe | 39000 | 2017-05-12 | 039/17 | 1214 | 27300 | 11700
Individual Consultancy contract | RANDRIAMANANAZY GILLES | 25000 | 2017-07-31 | 40/17 | 1226 | 10000 | 15000
Individual Consultancy contract | RAKOTOARISON Noely Valisoa | 9000 | 2017-04-27 | 41/17 | 1246 | 3600 | 5400
Enterprise contract | SAMAN | 153300 | 2017-09-06 | 42/17 | 2304 | 30660 | 122640
Enterprise contract | BETCP | 121500 | 2017-09-06 | 43/17 | 2304 | 24300 | 97200
Enterprise contract | AAS | 134, 820 | 2017-09-25 | 44/17 | 2304 | 0 | 134820
Individual Consultancy contract | RAMANANKASINA Jacob | 21000 | 2017-04-27 | 45/17 | 1244 | 8400 | 12600
ONG MAHARITRA Contract | ANDRIANANTENAINA Mirindra | 75000 | 2017-08-03 | 46/17 | 2104 | 30000 | 45000
Enterprise contract | EGECA | 240000 | 2017-09-06 | 47/17 | 2304 | 0 | 240000
Individual Consultancy contract | RAFALIMANANTSOA JULES | 9200 | 2017-10-05 | 48/17 | 1216 | 3680 | 5520
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
01/12. Personnel Recruitment - competitive | Mme Jane Razanamiharisoa | 100000 | 90000 | Selection was based on technical merits, experience and expertise. A recruitment panel was launched within the Ministry of Environment for the selection of suitable candidates. No financial offers were required as the salaries were fixed.
| RAMAROVELO Jean Marc | 150000
| HERINIRINA Harisoa Rondro | 120000
02/12 Personnel Recruitment- competitive | Mr. Tahiry Herilalaina | 100000 | 75000 | Selection was based on technical merits, experience and expertise. A recruitment panel was launched within the Ministry of Environment for the selection of suitable candidates. No financial offers were required as the salaries were fixed.
| RASOLOMANDIMBY Tahina Fenosoa | 120000
| RAVOAVY Augustin Bertrand | 145000
03/12 Personnel Recruitment - competitive | Mr. Marcellin Lalason | 50000 | 50000 | Selection was based on technical merits, experience and expertise. A recruitment panel was launched within the Ministry of Environment for the selection of suitable candidates. No financial offers were required as the salaries were fixed.
| RANDRIAMPIERENANA Prisca | 100000
| RAKOTOMAMPIANINA Jean | 80000
04/13. Call for Proposals - international competitive' | Joana Talafré | 150000 | 120000 | Financial bids were requested only for those candidates who fulfilled technical requirements. Contract attributed to highest ranking candidate for both technical and financial proposals. Contract amount revised from 150K to 120K following budget revision and number of days reduced.
| Alexandre Borde | 165000
Shalaby Hani
Olivier Beucher
05/13. Call for Proposals - international competitive | Gaetan Quesne | 35000 | 35000 | Financial bids were requested only for candidates deemed technically qualified to perform the baseline study. A review panel was put together to analyse proposed methodologies and candidates, and a proposal was made to support consortia of international and national consultants. UNEP participated in the recruitment panel. Contract amount was adjusted to account for real hours worked between national and international consultant (a combination of two proposals).
| Henri Rakotobe | 20000
Raparany Serge
Mike Jennings
Narayan Dhital
Kasibothia Sridhar
Corradi Chiara Assunta Riccarda
Barova Harimanga
06/13 (call for proposals) - competitive | Ramangarivelo Lidya Nirina | 45000 |  | After discussion and exchanges and for greater efficiency and complementarity, the Evaluation Committee decided to retain the nominations of Mr. Rabeson and Mrs. Jacqueline Rakotoarisoa consortium. It was deemed that Mr Rabeson by his experiences both in agriculture research and adaptation to climate change, could the lead study in terms of analysis and methodology while Mrs. Rakotoarisoa with her experiences and excellent knowledge of the context and local cultures, could arrange collection and verification of local data. The consultants were encouraged to join forces and present a joint bid. In later months, the contract was expanded to adjust for significantly increased scope of work.
| Rabeson Raymond | 80000 | 60000
| Rakotoarisoa Jacqueline | 85000
07/13- Call for Proposals -competitive | RASOAFALIMANANA Mbolarinosy | 70000 | 50000 | Financial bids required only for those candidates who fulfilled technical requirements. Contract attributed to highest rating candidates for both technical and financial. After discussion and exchanges and for efficiency, the evaluation committee decided to accept the nomination of Ms. Mbolaharinosy Rasoafalimanana based on her experience and excellent knowledge of the local context and culture and her ability to lead the entire study proposals. The contract was negotiated on the basis of the amount available for the work (50K) with a consortium of consultants, based on number of days worked.
| Barova harimanga | 72000
| Rabeson Raymond | 65000
| Ratsimbazafy Jean-Pierre | 75000
| Randrianoro Desire | 80000
| Randriambolamanana Hoby Nantenaina | 90000
07bis/13 - single source | Rabeson Raymond | 6000 | 6000 | Only one candidate was sought out as it was known that he had previously obtained training in DSSAT and ORYZA and was qualified to deliver the required training.
08/13 - competitive | RATSIMBAZAFY Tiana Andrianiaina ( selected canditate) | 37500 | 15000 | After discussion and exchanges and for greater efficiency and complementarity, the evaluation committee decided to accept applications from Mr. Ratsimbafazy Tiana Andrianiaina, through his experiences in agriculture and especially in the use of fertilizer. He also has experiences in collaborations with other agriculture engineers, and NGOs conducting technical tests with farmer. Mr. Tiana has put together a team to address his TORs.
| Randrianasolo Fihevitsoa Rabarijaona | 40000
| Levy Rakotoarison | 50000
| Razafindrabe Manantsoavina Warren | 52000
09/14 - competitive | RAKOTOBE RAHELIARISOA Holinantenaina | 20000 |  | After discussion and exchanges, the evaluation committee decided to accept applications from M. Andrianirina Michelliarson, due to his experiences from the Environment National Reaserch Center (CNRE) and excellent credentials in comparative methodological analysis of water quality and climate change adaptation. He has led the group for the first and second national communications. His team includes an agricultural national expert, who also worked on the development of the national communication.
| Andrianirina Michelliarson (selected candidate) | 17000 | 15000
Ratsimbazafy Jean Pierre
| Rejo robert Andriamananjara | 30000
10/13 - competitive | Levy Rakotoarisoa | 56000 | 60000 | After discussion and exchanges and for greater efficiency, the evaluation committee decided to accept applications from Mr Levy Rakotoarison due to his experience in agriculture research and Climate change Adaptation. He will direct the whole survey in terms of analysis and methodology by his experience and excellent knowledge of the context and the local cultures, will be in charge of the collections and verification of the local data. Contract amount is slightly higher than proposal as consultant missed a few activities of the TOR in his proposal.
Marthe Rafarasoa
| Raminoson Rina | 65000
11/14 - single source | Mr. Randrianoro Désiré |  | 1000 | Due to the low amount, a single candidate, known to be qualified, was sought out. In most recent budget revision, this contract has been cancelled due to non performance and duplication with another consultants' TOR.
12 bis/14 - competitive | Mr. Ratsimbazafy Jean-Pierre | 5000 | 5000 | The evaluation committee decided to accept applications from Mr Ratsimbazafy Jean Pierre due to his experiences in agriculture research and Climate change Adaptation
| Mme Olitina Ratovo | 7500
| Mr RAFALIMANANTSOA Jules | 9000
12/14 - competitive | Rija Fidèle | 30000 |  | The evaluation committee decided to accept applications from Mr Razafindrakoto Helison due to his experiences in agriculture research and climate change adaptation, and knowledge of watershed modeling and experience in software and application of hydrological modeling
| Helison Razafindrakoto ROMUALD | 26000 | 25000
13/14 - competitive | Miharimanana Marie | 20000 |  | After discussion and exchanges and for greater efficiency, the evaluation committee decided to accept applications from Mr Andriamalantomanga Tsiory Dimbimalala through his experiences with farmer communication and climate change impact on agriculture. Contract amount is slightly higher than proposal as consultant missed a few activities of the TOR in his proposal.
| Andriamalantomanga Tsiory Dimbimalala | 17500 | $19,000
| Manampisoa Tanjona | 24000
14/14 - competitive | Heritiana Andrianala Rabemanantsoa | 15000 | 14000 | After discussion and exchanges and for greater efficiency, the evaluation committee decided to accept applications from Mr Rabemanantsoa Heritiana Andrianala through his experiences in agriculture research and Climate change Adaptation as well as experience on the economy and socially.
| Razanakolona Tahina | 165000
| Rakotobe Henri | 18000
15/14 - competitive | RANAIVOJAONA Harinomenjanahary Voahanginirina |  | 9000 | Over 35 candidates were presented for this post of local technician. The top candidates indicated here represent the shortlist, from which the leading candidate was selected. No financial offers were required as the salaries were fixed by the project.
Rabemanda Jean Gabriel
Razafinandrianina Justine
16/14 - competitive | Rasamison Jules |  | 9000
Andry nirina Rakotoarivelo
17/14 - competitive | Randriafiraisampirenena Jules |  | 9000
Razakalanitra Malala Navalona Mariah
022/15 competitive | Joelibarison | 65400 | 50000 | Upon discussion the candidate with the highest number of points (78) was selected
| Ravololomahefa Haritiana | 36700
029/15 competitive LB 1213 | RAZAFINDRAKOTO CHARLOTTE | 134445 | 74000 | The dynamic candidate was selected due to her expertise and experience in the agricultural sectors and AFRICA RICE, which is the only technique known in the Mangoro Alaotra region
| Joelibarison | 16071
024/15 competitive | Andriamihaingo Narivelo | 32143
| Rabemanantsoa Njaratiana | 18705
| Rakitriniaina Mandariniorandraibe | 35850 | 30000 | the candidate was selected due to experience and knowledge in revitalizing association and federations. He has a sound knowledge of the socio-organizational culture of the regions.
| ANDIANIRINA Michelliarson | 25000
026/15 competitive | Rampanjato Andrianantenaina | 16071
| Rakotoarivelo Manitra | 26073
| Ravololomahefa Haritiana | 10583
| Rafalimanantsoa Jules | 22465 | 20000 | The candidate selected had the highest rating (68) and was deemed by the evaluators as having the most merit as per his credentials.
028/15 competitive | Andriamihaingo Narivelo
Rabemanantsoa Andrianala Heritiana
| Rakotoarisoa Ny Hery Miandrazo |  | 20000 | the candidate was selected due to his knowledge and application in the area of macro and micro economics. He has already participated in several projects and is well-experienced in the area of rural economics.
027/15 competitive | Randriamiharisoa Andriamalala Luc | 10740
Rabenarivahiny René
| Sylvain Rodolphe RALAIARIMALALA | 46607 | 50000 | The selected candidate had the highest score and had more experience on issues related to livestock than most candidates.
025/15 competitive | Randriamanantsoa Eric
| Ranaivoarisoa J.Toavina | 79400 | 76000 | The selected candidate has high competence in forestry-related communications and has a forestry engineering background. He has also participated in several agro-forestry projects
Manitrera Safidy
023/15 competitive LB 1229 | Randrianoro Désiré | 36720 | 35000 | This is the only meteorologist that applied for this post; he also has the technical credentials.
| Ratsimbazafy Jean Pierre | 45230
030/15 Competitive LB 1226 | RANDRIAMANANAZY GILLES | 68000 | 68000 | This candidate had the highest score and has the experience in hydraulic infrastructure. He is aware of different systemes such as the (NYCHRI) even if those are not used in Madagascar, and is also knowledgeable on intregated management of water resources used in Madagascar.
| RAKOTOARINARIVO Solonirina | 72000 | 68000
031/15 Competitive LB 1205 | ANDRIANAHARINOSY Mireille Natacha | 14500 | 50000 | This candidate had the highest score and has experience in the management of climate risks. She has field experience in the management of climate data and their use in development planning, in the establishment of risk maps, and in developing early warning systems to climate hazards
| Ratsimbazafy Jean Pierre | 15000
Rakotomalala Naritiana
20/14 - Competitive (driver) | RAMAROSOA Erick Lauret | 12000 | 11550 | The candidate has been selected especially due to his experiences found at the Department of Climate Change: Project driver on the Third of National Communication under the UNFCCC.
| RANDRIANANTOANINA Harinala | 13500
| RANAIVOSON Jean Eric Radonirina | 14800
MOU-1 - Single source | SNGF (Silo National de Grainer et Foresterie) |  | 201500 | The SNGF is a national organization specialized in the research and production of forest seeds. The MOU was negotiated on a non-competitive basis.
MOU-2 - Single source | CALA |  | 180000 | The CALA - Agricultural Center on the Alaotra Lake, is the representative of the FOFIFA on regionally level wich is an institution working in the rice sector, including research on varieties adapted on climate change. MOU was negotiated on a non-competitive basis.
| STOI AGRI (Société Trading de l'Ocean Indien) |  | 258050 | Compost production Company, The MOU was negotiated on a non-competitive basis.
MOU-2 - Single source | IRRI |  | 35000 | IRRI is an internationally recognized rice research center. The MOU was negotiated on a non-competitive basis.
033/17 Competitive LB 1225 | Ravalison Andriatsihoarana Mampionona | 25000
| Andrianasolo Miravola (Selected candidate) | 19000 | 20000 | This candidate received the highest score and has the highest level of experience and skills in communication and climate change.
| Ratefiarivony Romuald | 28000
034/17 Competitive LB 1211 | RAZAFINDRAKOTO CHARLOTTE (selected candidate) | 32000 | 32000 | This candidate received the highest score, has the most appropriate diploma and the highest level of experience in agronomy at the national and international levels.
| Razafindrakotomamonjy Andrianantenaina | 22800
| SERGE Ramparany | 5100
| Razoelina Adeline | 21600
| Rakotondravony Hervé Francis | 8200
035/17 Competitive LB 1224 | Randriamanarintsoa Manajaniaiana | 28032 | 28000 | The candidate is the most qualified in community-based planning for adaptation in the region of Alaotra Mangoro.
| ANDRIANAHARINOSY Mireille Natacha | 10000
036/17 Competitive LB 1231 | Ralaiarimalala Sylvain Rodolphe | 25000 | 25000 | The consultant has the highest level of experience in construction, management and training regarding storage facilities. He also has local knowledge.
| TOANDRO Honoré | 12500
| Randriamanarintsoa Manajaniaiana | 16300
037/17 Competitive LB 1243 | Antilahy Herimpitia Estelle Rollande | 11000 | 11000 | The candidate has a strong experience and skills in conducting household surveys.
| Raveloarison Rindra Nirina | 5000
| Andrianiaina Neila Hanitra | 3220
| Rakotoarisoa Ny Hery Miandrazo | 3900
038/17 Amendment LB 1215 | Andrianirina Michelliarson | 8000 | 8000 | (Contract amendment; original contract 09/14) The candidate has the highest skills and experience in water engeneering and water quality assessment.
039/17 Amendment LB 1214 | Rakitriniaina Mandariniorandraibe | 39000 | 39000 | (Contract amendment; original contract 024/15) The candidate has the most adequate skills and experience in training and strengthening associations and community groups.
40/17 Amendment LB 1226 | RANDRIAMANANAZY GILLES | 25000 | 25000 | (Contract amendment; original contract 030/15) The candidate is the most qualified and experimented in water engineering and water management.
41/17 Competitive LB 1246 | Rakotoarisoa Noely Valisoa (selected candidate) | 17900 | 9000 | (Only one bid received) The candidate has excellent GIS skills and strong experience.
42/17 Competitive LB 2304 | SAMAN (selected candidate) | 153300 | 153300 | The compagny is the most qualifed and experimented in water engineering and water managment
| SYSAME | 154915
| BETCP | 174050
43/17 Competitive LB 2304 | BETCP (selected candidate) | 121500 | 121500 | The compagny is the most qualifed and experimented in water engineering
| SAMAN | 142760
| SYSAME | 142680
44/17 Competitive LB 2304 | AAS (selected candidate) | 134820 | 134820 | The compagny is the most qualifed and experimented in water engineering
| BICKASTYLE | 321700
| EGMP | 169900
45/17 Competitive LB 1244 | RAMANANKASINA Jacob (selected candidate) | 21000 | 21000 | The candidat is the most qualified and experimented in building engineering
| RANDRIARILALAO Heritina Jeannot | 19440
| ROVANARINDRA Soloniary | 20880
46/17 Competitive LB 2104 | ONG MAHARITRA (selected candidate) | 79000 | 75000 | The compagny has the most adequate skills and experience in sustainable land managment and has a multi displinary team sush as soil managment specialist, trainer qualified and communication specialist, etc.
| RANDRIANARY Jean Mario | 33350
| RAIVOSOARIMANANA Marie Delphine | 4000
47/17 Competitive LB 2304 | EGECA (selected candidate) | 515 000 | 240 000 | The compagny is the most qualifed and experimented in water engineering and has the tools and equipments necessary for the work
| BICKA STYLE | 2 217 600
| SARA ET CIE | 1 212 256
| SYSAM ET ECG TIANA | 495 650
48/17 Amendment LB 1216 | RAFALIMANANTSOA Jules | 9 200 | 9 200 | (Contract amendment; original contract 026/15) The candidate is the most qualified and experimented in rural agriculture

## Risk Assesment
RISK ASSESSMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Slow administrative functioning due to lack of human and financial resources | M | This risk has been reduced following the MTR. The roles of each team member have been clarified and better distributed. A new M&E expert was appointed in November 2016. The roles of each team members were redefined accordingly to respective skills.
Frequent political change. This creates a degree of uncertainty | L | Political changes during the third trimester of 2016 resulted in some delays in the project implementation. Although the risk was low in the current reporting period, it will start increasing again as presidential elections are scheduled for late 2018. An effort will be made to close all major project activities by mid-2018, to avoid major impacts of the upcoming elections on implementation progress.
Accesibility of sites during cyclonic/rainy/ flooding period (december-april) could affect inter regional transport and cause delays in performing required field visits and inputs delivery from other regions or from capital | M | Local Technical Staff (LTS) – as local project representatives – are on site and follow the activities. The LTS are very active and competent, and continue to provide progress reports to the PCU on a monthly basis. Therefore, despite inaccessibility of sites around December, the PCU remains abreast of the progress throughout the year, and delays in information transmission are minimized.
Lack of population buy-in on project activities | M | The PCU organises focus groups during the field missions, undertaken approximately every 6 weeks since the MTR was undertaken. During these focus groups, the team investigates the satisfaction of the beneficiairies and grievances of local communities, if any. Additionally, following the MTR recommendations, focus groups have been used to raise awareness of project beneficiaries on the need for them to take full autonomy to enable them to benefit from the project interventions beyond the project. Improvement in communities' understanding of the necessity to become independent of the project has been observed. However, the risk remains rated as Medium, because local communities still regularly raise the continuation of the project as one of their needs and some crucial aspects of the project sustainability (e.g. the production of MIRR rice varieties) are not yet undertaken autonomously by local communities.
There is a risk that the upscaling and replication strategy developed for this project might be insufficient in ensuring uptake of the approach to the rest of the country. Political instability in the country may delay or prevent the adoption of policy recommendations adopted by the project. | M | Since the implementation of the demonstration plots during the first rice cultivation season in 2014-2015, the number of people asking for training on MIRR practices has constantly increased (e.g. approximately 20 times more farmers adopting the MIRR practices in all three sites between season 1 and season 2). Furthermore, other communes are asking for support on these techniques in their own capacity and some other projects have asked CALA for information on these techniques. The upscaling potential is therefore very strong. In addition, upscaling of the project interventions was promoted during the International Fair for Agriculture in Antananarivo in August 2017, which was a very successful event where a high interest for the MIRR techniques was tangible. Representatives of one seed production group and one compost production group per site participated in the Fair, and received requests for seeds which further increased their motivation. Upscaling will also be facilitated by the strengthening of the rice platform. However, the project will end in June 2018, and the time left to advertise the successes of the practices and to transfer knowledge on how to implement it in other areas is limited. This is the reason why this risk is still considered as Medium. No political instability is foreseen until the end of the project.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
There could be project delays due to delays in processing cash advance requests with UNEP, as well as due to change in financial procedures in UNEP or in GoM | Low | A financial report on the remaining budget available on the bank account of the project and expected disbursements within the following three months have been submitted regularly to UNEP Task Manager since January 2017.
Procurement delays | High | Major delays in procurement have been encountered during the reporting period. Several meetings have been organised with the Ministry of Environment to ensure that no further delay is caused by the procurement process during the last year of the project.
The reforestation target of the project might not be met | High | The government partner in charge of the restoration interventions performed very poorly during the first and second planting seasons. Contracts with one experienced NGO per site and with each commune were established to maximise the number of hectares successfully restored during the season 2016-2017, but procurement delays prevented the targets to be met. A fully community-based approach was adopted for the last planting season (2017-2018) for landowners interested in undertaking restoration interventions on their land. The project will provide equipment and plants, while the landowners will participate in the planting interventions and be responsible for maintaining the trees. Many landowners have shown their motivation in undertaking restoration interventions on their land and the establishment of the nurseries was initiated in October 2017. 608 ha are expected to be restored during this last season. A total of 1,800 ha is expected to be restored with a mortality rate lower than 50% by the end of the project.
Lack of financial bids and lack of clarity regarding procurement | High | A more thorough documentation of bids and offers received has been instated within the project management team and the procurement unit of the Ministry of Environment and Forest. The Chief Technical Advisor has participated in the analysis and selection of the candidates to bids since January 2017, and UNEP has been fully informed of the procurement processes underway and their progress. However, full transparency has been difficult to achieve. This was particularly highlighted by the procurement process for the water infrastructure works, which experienced major delays due to the need to address and rectify lack of transparency in the process (which was done in collaboration between UNEP, Ministry of Environment and Forest, and the project team). The open and regular communication on procurement-related issues between the project team, the CTA and UNEP will be continued in the last year of the project, to mitigate this risk.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The improved communication system between the CTA and the PCU continues with regular skype calls for problem solving, technical support, financial reporting, and addressing issues related to the day-to-day management of the project. In addition, the CTA is now an official member of the selection committee for all procurements. MoUs with the project partners were developed to clarify the responsibility of government partners in the project implementation and to increase their involvement in the interventions. For example, the involvement of DREF in the monitoring of reforestation interventions and in awareness raising against bushfires was increased through amending the MoU between DREF and the project for the last planting season, to increase ownership, success rate and sustainability of the interventions.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones | Expected Progress | Progress to Date | Rating
Project Manager/Coordinator: | Outcome 1.1 Knowledge base on best practices for climate resilience in rice, based on existing local knowledge and international research | This outcome should be completed by the end of 2017. | The MIRR guidelines were produced based on the results obtained in the demonstration sites. These guidelines were validated on 13 September 2017 at the regional level in Ambatondrazaka with the presidents of local associations and compost production groups from each site, the president of the national authority for seed production, regional directors of agricultural development, representatives of MEDD, FOFIFA and Met Service, as well as members of the project steering committee. The MIRR guidelines will be validated at the national level by the end of 2017 and will then be published. A training calendar on seed production was developed by DRAE to organise local farmers within groups of 10 for seed production. | M
| Outcome 1.2 Malagasy government, research institutions and local communities have the tools and methods to assess, monitor, and understand climate change impacts on rice. | This outcome should be underway in 2015, with the development of technical capacity for stakeholders at all levels. Estimated completion Q4 2016. | The project provided equipment and materials for the various activities, such as computers and climate monitoring stations. The two climate monitoring stations have been established and training was provided to collect the data. An MoU between Met Services, the commune and the Ministry of Agriculture is under finalisation to enable the maintenance of these stations, collect and interprete climate data beyond the project.Training was provided at the national and regional levels, including the DSSAT model and Oryza, and on the climatic risks, on the interpretation and the communication of the climate reports in clear language for the benefit of the peasants. An expert is currently producing vulnerability maps for different climate scenarios by 2050 and 2100 for use by government authorities. Training on the interpretation of vulnerability maps for rice cultivation will be provided early 2018 at the latest. In addition, training on the use of multivariate models will be provided to GIS staff within all relevant government institutions to enable the update of vulnerability maps based on latest climate and weather data. Up-to-date agricultural calendars and training were completed to increase agricultural productivity under climate change. Finally, training on agroforestry practices will continue until early 2018 to increase the resilience of local communities to climate change. | M
| Outcome 2.1. Sustainable increase in rice yields (using MIRR) | This outcome should be halfway completed in 2015 and completed by the end of the project. | This outcome is completed. The pre-selection of rice and non-rice varieties was undertaken in 2014-2015, followed by some local testing to determine feasibility and adaptability. CALA produced basic seed for the seasons 2015-2016 and 2017-2018 (large-scale application). Soil analyzes were undertaken at the beginning of the project and will be compared to the results obtained at the end of 2017. Regarding the water quality analysis, measures were undertaken before the start of the rehabilitation work for the water infrastructure and will be replicated after completion of the rehabilitation interventions. Fertilization guidelines were developed and the project successfully tested a local compost production program. Training was then provided to enable the farmers produce and use compost. Composting associations have also been formed. The rehabilitation of the water infrastructure began in October 2017 and is expected to enable a significant increase in rice production.The ANCOS (National Agency for Seed Control) through the DRAE (Regional Directorate of Agriculture and Livestock) provides training in groups of 10 people for members of GPS (Seed Production Groups MIRR) and farmers to popularize MIRR seeds. The MIRR Guidelines are validated at the regional level in September and the national in February. | MS
| Outcome 2.2. Ecosystem services maintained | Reforestation targets were designed to be 70% achieved by 2015 (approximately 6000 ha). Other activities under the outcome started in 2015 and will continue until the end of the project | The results of the first reforestation campaign (2014-2015) are not satisfactory (20% success rate). The second season (2015-2016) was not satisfactory either (45% success rate) as measured by the PCU. Based on these results and the experience of other partners (e.g. LIFE model of JICA), the PCU and the CTA have launched a fully community-based approach for the season 2017-2018. This approach is based on communities willingness and commitment to plant and maintain trees. The project will provide small equipment and plants while the beneficiairies will undertake planting interventions and ensure survival. The revitalization activities of Water Users' Associations (WUAs) and the training of members and cooperatives have been completed. These have led to the resolution of various disputes and led to the formation of new associations and members. These new members formulated requests for additional training from the project. It was therefore decided by the PCU and the expert to organise additional training sessions until the end of 2017. Activities such as the dissemination of technological packages, the rehabilitation of lavakas and the various training courses on erosion control, among others, will be carried out during the first quarter of 2017. | MU
| Outcome 2.3. Post Harvest losses reduced | The outcome was designed to be completed in 2015 | Socio-economic analysis of post-harvest losses and rehabilitation options for storage were completed.The construction of three storage rooms has begun in September 2016 but the contracts were ceased because of bad performance. New companies were recruited and the construction work started in October 2017. Training on the management of storage facilities was also provided to local communities. In addition, training on the use of rice by-products such as straws was carried out and the effects of these training interventions are currently been measured. | MU
| Outcome 3.1 Technical norms and standards in rice cultivation reviewed and where necessary modified to take climate change into account | This outcome was designed to be initiated towards the end of the project, once sufficient lessons have been achieved from local activities. It was designed to be finalized in 2017. | This result will be published towards the end of 2017. After the study on the comparative analysis of rice production techniques and technologies at Alaotra Mangoro and other rice granaries and taking into account the recommendations of the Integrated Model Resilient Rice Harvest (Seminar MIRR), demonstration plots have been set up according to the situation of the land: good water control (RBME) and poor water control (RMME). These results made it possible to identify the appropriate seeds and nutrient inputs required for each soil type. Now we are in the phase of large-scale application. To date, 7 seed farmer groups (GPS) have obtained certificates by ANCOS, an authority that gives seed certification according to the necessary standards under climate change. The Regional Directorate for Agriculture and Livestock (DRAE) and ANCOS provided training to the seed production groups to make the production of MIRR varieties and practices viable. A seed bank was established in Ambatondrazaka by DRAE and is aware of the MIRR objectives and principles. The MIRR Guidelines were validated at the regional level in September 2017 and will be published in the first quarter of 2018, after a national validation. The options for the scaling up of MIRR techniques have been initiated at the level of a few regions and will be extended to other regions in the first quarter of 2018.The 3 PCDs of the intervention sites have been updated and validated. The MIRR techniques have been taken into account in the National Strategy for Agricultural Development. strengthened before the end of the first quarter of 2018 | M
|  |  | Overall rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Jane Razanamiharisoa
| Email: | jrazanamiharisoa@ymail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project has encountered delays. However the MTR, which was finalized in March 2016, has helped identify problems and means of improvements. Plans to address these recommendations have been developed by the PCU, UNEP Task manager and CTA. Improvement in management practices and tools were implemented and continue to be rolled-out, including TOR for PCU team members, planning of activities using project monitoring tools, more active monitoring of activities and delivery of outputs and collaboration with other teams working on rice production.
| Progress on Key Milestones | Expected Progress | Progress to Date | Rating
Implementing Agency | Outcome 1.1 Knowledge base on best practices for climate resilience in rice, based on existing local knowledge and international research | The outcome was designed to be completed in 2015. | See above and below from national coordinator and CTA for progress description. The regional validation of MIRR guidelines has been completed, and the national validation and official publication of the guidelines is expected in Q1 2018. | S
| Outcome 1.2 Malagasy government, research institutions and local communities have the tools and methods to assess, monitor, and understand climate change impacts on rice. | The outcome was designed to be completed in 2016. | See above and below from national coordinator and CTA for progress description. Agricultural calendars have been developed, and training on their application will be provided in Q1 2018. Vulnerability maps are currently under development and training will be provided to update and interprete these maps. The arrangements for the maintenance of the weather stations and data use are still to be finalized (MoU with the Met Services). | MS
| Outcome 2.1. Sustainable increase in rice yields (using MIRR) | This outcome should be halfway completed in 2015 and completed by the end of the project. | See above and below from national coordinator and CTA for progress description. Challenges were encountered in the water infrastructure procurement process, which resulted in a delayed start of the activites (now underway). Although good progress with the activities was observed during the Task Manager's field mission in January 2018, the currently-limited onwership, sustainability and upscaling of the MIRR approach and the project interventions more broadly is a concern. This will continue to be focused on in the last year of project implementation. The development of a sustainability strategy is underway, and an upscaling strategy will be developed in Q1 2018. | MS
| Outcome 2.2. Ecosystem services maintained | Reforestation targets were designed to be 70% achieved by 2015 (approximately 6000 ha). Other activities under the outcome were intended to begin in 2015 and to continue until the end of the project | See above and below from national coordinator and CTA for progress description. Reforestation activities have been severely underperforming throughout the project, as a result of non-delivery of partners. In the last planting season, a community-based approach was selected, and good progress with the seedlings in nurseries was observed during the Task Manager's field mission in January 2018. However, even if the 2017-2018 planting season will be successful, the project will fall significantly short of achiving its reforestation targets. | U
| Outcome 2.3. Post Harvest losses reduced | The outcome was designed to have been completed in 2015 | See above and below from national coordinator and CTA for progress description. Following the failed construction of the three post-harvest storage facilites in 2016, the demolishing of the partly-finished buildings and construction of new ones is now finally underway. The construction of the new storage facilites will be completed by Q2 2018. | MU
| Outcome 3.1 Technical norms and standards in rice cultivation reviewed and where necessary modified to take climate change into account | This outcome was designed to be initiated towards the end of the project, once sufficient lessons have been achieved from local activities. It was designed to be finalized in 2017. | See above and below from national coordinator and CTA for progress description. The MIRR principles were integrated in the National Strategy for Rice Cultivation. Much of the upscaling work still remains to be done in Q1 and Q2 2018, including the upscaling of the MIRR approach in three other regions, as well as within the Alaotra-Mangoro region. The implementation of the upscaling strategy will be an important focus of the last year of the project. | MS
|  |  | Overall rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Anna Kontorov
| Email: | anna.kontorov@un.org
| Progress on Key Milestones | Expected Progress | Progress to Date | Rating
Chief Technical Advisor | Outcome 1.1 Knowledge base on best practices for climate resilience in rice, based on existing local knowledge and international research | This outcome should be completed by the end of 2015. | The comparative study of rice production techniques was completed in collaboration with IRRI. A MIRR seminar was organized in September 2014 with IRRI support, which allowed for the consultation of stakeholders from the region (producers, water user associations, ministries, NGOs, organizations and private sector) and the subsequent approval of MIRR guidelines. The MIRR guidelines were produced and are being distributed in Malagasy locally. The MIRR guidelines have not yet been validated officially at the central level. The MoU to maintain the weather stations and integrate the data in the analysis made by Met Services is not yet finalised. | MS
| Outcome 1.2 Malagasy government, research institutions and local communities have the tools and methods to assess, monitor, and understand climate change impacts on rice. | This outcome should be underway in 2015, with the development of technical capacity for stakeholders at all levels. Estimated completion Q4 2016. | The agricultural calendars were updated by CALA based on new climate conditions. However, they have not yet been widely distributed. The vulnerability maps are currently under development and training will subsequently be provided to update and interprate these maps. Climate data is produced and agricultural calendars have been developed but they are not yet accessible to local communities in an open and systematic manner. | MS
| Outcome 2.1. Sustainable increase in rice yields (using MIRR) | This outcome should be halfway completed in 2015 and completed by the end of the project. | Demonstration sites have been implemented and positive results were obtained in all sites. Nevertheless, the knowledge of the MIRR practices and their effects remains very localised at the moment. Little is known at the regional and the central levels on the MIRR. In addition, some crucial aspects of the MIRR (access to MIRR rice varieties, compost production and access to non-rice varieties) is not mastered by local communities yet. A socio-economic assessment of the sustainability of project interventions is underway and additional support will be provided until the end of the project based on the results of this report. The rehabilitation of water infrastructure was initiated in October 2017. Except for some exceptions, beneficiaries still adopt an assisted position and do not take advantage of the project to improve their livelihood sustainably. | MU
| Outcome 2.2. Ecosystem services maintained | Reforestation targets were designed to be 70% achieved by 2015 (approximately 6000 ha). Other activities udner the outcome were intended to begin in 2015 and to continue until the end of the project | Although reforestation work has begun, the project has not been able to achieve with a satisfactory level the reforestation targets, owing to the bad performance of the contracted party (SNGF) and delays in appointing other service providers. The target of 3,900 hectares has defined at MTR will likely not be met by the end of the project. The new expected target is 1,800 ha by the end of the project. In addition, bushfires remains a major threat that the different communes have not yet tackled. DREF will implement a campaign against bushfires in the three sites. This awareness raising campaign should be finalised early 2018. Other trainings are foreseen for the end of 2017 including sustainable land management to control erosion. | U
| Outcome 2.3. Post Harvest losses reduced | The outcome was designed to have been completed in 2015 | Work has begun with the socio-economic analysis of post harvest losses and rehabilitation options for storage. The sites have been identified and procurement for construction was initiated in July 2016. However, the construction did not follow the technicalities of the call for tender and the construction has to be redone. It took a long time to cease the contract. New companies have now been appointed and the work started in October 2017. Activities on the use of rice by products such as straws, have also been provided with the support of livestock experts. However, no concrete results of this training have been monitored to date. | MU
| Outcome 3.1 Technical norms and standards in rice cultivation reviewed and where necessary modified to take climate change into account | This outcome was designed to be initiated towards the end of the project, once sufficient lessons have been achieved from local activities. It was designed to be finalized in 2017. | The MIRR principles were integrated by FOFIFA in the National Strategy for Rice Cultivation. No additional needs for integration of MIRR principles in other strategies or plans have been identified by the project stakeholders to date. | MS
|  |  | TOTAL RATING | MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Lucille Palazy
| Email: | lucille.palazy@gmail.com
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words | Project delivery is slow with changes in senior staff among partner institutions implying the renegotiation of previous agreements and MOUs. Procurement is also slow, and there is often a lack of suitable candidates for consultancies. The quality of some deliverables provided by consultants has often been unsatisfactory thereby leading to delays for revision of documents and reports. Many procurement problems hav ebeen encountered and are responsible for major delays in project implementation. The effects of the project remain at a very small scale and still need to be communicated at a larger scale to have a significant impact in Madagascar. The involvement of the CTA in the project was strengthened since the end of 2016 through an increased number of field missions to support the team in meeting the project targets before the end of the project.
Highly Satisfactory (HS)
Satisfactory (S)
Marginally Satisfactory (MS)
|  | Marginally Unsatisfactory (MU) | The results obtained to date remain far from the expected results. Visible efforts have been made by the project coordination team but a lot still need to be done during the project extension period to enable the benefits of the project to become visible at a larger scale thereby promoting the replication of the interventions.
Unsatisfactory (U)
Highly Unsatisfactory (U)

## Project Indicators
PROJECT Indicators (*as revised following baseline study)
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End | Notes on targets
Outcome 1.1 Knowledge base on best practices for climate resilience in rice, based on existing local knowledge and international research | Percentage of farmers with access to selected and publicized MIRR | There is currently no MIRR available although various ameliorated techniques have been developed in recent decades | Documentary analytical work was undertaken and guidelines on the application of the MIRR were finalized. A workshop was held with all stakeholders to discuss and validate technical findings. MIRR has been tested locally for three seasons (2014-2015, 2015-2016 and 2016-2017) and the upscaling and replication strategy is currently being finalised by FOFIFA (90% completed). To date, 1 495 farmers (336 in Manakambahiny, 754 in Ambohijanahary and 405 in Bemaitso) out of a targeted population of 2 100 farmers (corresponding to 71.2%) have been trained to use the MIRR practices. | Based on existing ameliorated techniques such as SCV, SRI & SRA, and based on new research, 1 Resilient Rice Model is selected and published. At least 90% of farmers targeted by the project has received technical support and has been trained to implement the technique according to technical guidelines. | The number of targeted farmed was not defined at the inception stage. The most logical way of defining it based on the MTR recommendation is to estimate the number of rice cultivation farmers in the targeted sites. The resulting total is 398 in Manakambahiny, 1 034 in Ambohijanahary and 545 in Bemaitso. Based on the project budget, a target of 90% the targeted farmers adopting the MIRR practices is unrealistic, with 80% being a more realistic expectation by project end. However, considering the upscaling potential, the initial target could potentially be met in the near future.
Output 1.1.1 Best Available Technologies and Integrated Resilient Rice Model (Modèle Intégré de Riziculture Résiliente - MIRR) selected and publicized | # and type of technical guidelines for MIRR developed and publicized based on best available technologies and technique | A series of guidelines for rice cultivation techniques, technical guidelines for direct seeding and system of rice intensification, are available from regional directorate of rural development but not yet widely disseminated | Guidelines have been produced in Malagasy and French by the expert from CALA. Three types of guidelines have been developed for different conditions: i) rice cultivation under poor water management conditions; ii) rice cultivation under good water management conditions; and iii) rain-fed rice cultivation on hill sides. Each of these guidelines include the following key techniques: seeding, field preparation, fertilisation, weeding, phytosanitary maintenance and harvest. These guidelines will be validated at the central level towards the end of 2017 and will be published in early 2018. (90% completed) | 1 Recommended Integrated Resilient Rice Model developed and published, including a series of at least 1 technical guidelines with the following key stages/techniques:  Seeding  Planting  Harvest  Post-harvest  Fertilization  Integrated pest management  Water management
Outcome 1.2 Malagasy government, research institutions and local communities have the tools and methods to assess, monitor, and understand climate change impacts on rice. | Level of use of the tools and methods made available to Malagasy government, research institutions and local communities to assess, monitor and understand climate change impacts on rice production | Current tools to address, monitor, and understand climate change impacts on rice are hampered by a lack of data and weak potential to convey information to farmers. Data on observed climate patterns is not being systematically collected at an appropriately local level making it difficult to create models and planting calendars. Dissemination of what information exists is also weak given the limited number of extension staff. While these staff appear to already be trained in climate issues, the information is not being disseminated to farmers. | Awareness raising and information sessions on climate change trends and impacts was organised for 15 representatives of regional extension services, 10 representatives of research institutions including CALA, and 48 farmers. - Training on climate change trends and impacts was provided as part of the MIRR training workshop to 200 government staff. - Awareness-raising on climate change trends and impacts was provided to the public through the development of communication tools such as pamphlets (distribution started but will be expanded by the new communication consultant) and radio talks on local radio by MIRR and compost experts. - Training on the MIRR was provided during several events at the national (Sept 2014), regional (August 2015) and local levels (2014-2016). Technical guidelines have now been finalised and will be validated at the national scale by the end of 2017. - Vulnerability maps are under development by a national expert. A multivariate model was chosen instead of Oryza and DSSAT because of technical problems encountered with these softwares. Training on how to update and interpret the results of the multivariate model will be provided by the consultant before the end of 2017. The MoU with DGM, DRAE and MEDD to maintain the climate monitoring stations, and collect and interpret the climate data is currently being finalised. Negotiations with local radios for the diffusion of 7-day forecast have been initiated but the contract has not yet been finalised. | All regional extension services, research institutions including CALA, and at least 90% of targeted farmers are aware of climate change trends and impacts through awareness raising and information sessions, have access to regular climate forecasts through local communication channels (radio, newspapers), and have been trained and implement MIRR and its technical guidelines, including vulnerability maps.
Output 1.2.1 Malagasy government, research institutions and local communities have the tools and methods to assess, monitor, and understand climate change impacts on rice. REPLACE WITH: Crop models are available for rice vulnerability mapping | Number of rice cropping system models based on expected climate change scenarios, including vulnerability maps of future rice production, and hydrological models developed | Currently, there is no rice cropping system model that includes vulnerability maps of future rice production under potential climate change impacts and hydrological models developed. | A climate-based hydrological model was developed in 2014. The national consultant appointed to build this model first compiled detailed downscaled data on water availability under the climate change scenario, climate risks including those impacting rice cultivation, and pest risk induced by climate change. Gaps filled in or to be filled in: training on meteorological and agricultural data acquisition to perform rice modeling using Oryza and DSSAT; development of four vulnerability maps to guide rice cultivation planning. Corresponding info disseminated: After finalisation of the vulnerability maps, training will be provided at the regional and local levels on the interpretation of the vulnerability maps. The maps will be printed in big format and advertised in public areas. Training on how to update the multivariate model and produce these vulnerability maps will be provided to the relevant staff within government institutions. Training was provided on Oryza and DSSAT models to 15 people (six national and regional staff of MEEMF, two staff from MADR, two from FOFIFA, two from the National Institute of Geography and Hydrography, and three from National Institute of Statistics). A consultant was appointed to collect the required data to build the models. However, several technical problems have been met with the use of DSSAT and Oryza, and it was decided to replace these software by a multivariate spatial model to produce vulnerability maps. The expert was appointed in April 2017. He received the required satellite images to build the four vulnerability maps in October 2017 and started building the multivariate model. | Detailed available downscaled data on expected climate change risks and impacts on rice sector at the local level compiled; identified gaps on available data are filled in; and all data are disseminated to relevant stakeholders at the regional and local levels. 4 rice cropping system models with vulnerability maps developed according to 4 different expected climate change scenarios (driest, low dry, low humid, and most humid scenarios) and 1 hydrological model developed based on available downscaled data on expected climate change risks and impacts.
Output 1.2.2 Updated, dynamic agricultural calendars and climate early warnings taking into account current and projected variability disseminated to local population | Frequency of dissemination of updated dynamic agricultural calendars and climate information, including flood early warnings in the three projected sites | Agricultural calendars under current climate conditions are well defined for all seed varieties developed, yet farmers do not necessarily apply them. The challenge resides in distributing and encouraging the application of established calendars amongst farmers through training and diffusion. Furthermore, new agricultural calendars will need to be developed on the basis of projected future climate trends. With respect to the diffusion of climate information, networks for analyzing and disseminating climate data are also insufficient:  Manakambahiny – In Ambalavato, farmers have access to daily meteorological forecasts in the newspaper and on the Radio Nationale Malgache. In Ambaibo, farmers also have access to daily forecasts. This information, however, is not very useful as it cannot provide longer forecasts that would aid in, for instance, determining seedling date or predicting potential floods.  Bemaintso and Ambohijanahary – Farmers have access to daily forecasts, but the forecasts do not help them adapt their growing calendar with enough forewarning or to choose which seed variety to use. | The MoU with local radio to disseminate the climate forecast over 7 days, early warnings for floods and seasonal forecast information was developed. However, the cost is US$3 per diffusion and the Met Services do not have sufficient budget to cover these costs. The methorological information will therefore be transmitted to the commune vocally (TamTam) during market days. Agricultural calendars have been updated and training on their use was provided in December 2015 to 305 farmers and extension staff. The specific calendars for 2017-2018 were developed and will be validated in February 2018. (50% complete) | Climate information and 3-4 day forecasts, including flood early warnings, made available to farmers through local communication systems. Dynamic agricultural calendars updated and disseminated to at least 80% of targeted farmers. | According the Meteorological Directorate, the duration of the process of data collection, transfer, analysis and climate forecast will not enable the distribution of climate forecasts every 3 or 4 days. They can only be distributed every 7 days.
Output 1.2.3 Agricultural extension staff trained on climate risk management in an agro-ecosystem context | Number of agricultural extension staff in the three districts trained on climate risk management in agro– ecosystem context (gender and district disaggregated) | Extension workers were trained in climate change issues through the BV Lac project, and they do not necessarily lack training. The challenge is disseminating information from extension workers to farmers given how little contact they have with farmers. The presence of extension workers in the project sites is the following:  Manakambahiny – The municipality contains the city Ambatondrazaka, which is the capital of the Alaotra-Mangoro Region. There are 15 to 20 agriculture staff, of which 9 to 11 extension workers cover the 5 districts of the region. Their presence in the field is weak.  Bemaintso – The municipality is part of the Andilamena district where 2 extension workers for rural engineering are located. They use radio to broadcast information to farmers.  Ambohijanahary – The municipality is part of the Amparafaravola district, for which there are 4 extension workers (2 for agriculture and 2 for engineering). | A first training session was organised in April 2016 for 20 people, including staff of extension services and local authority representatives. Training needs for a second training session to extend the number of people trained to the totality of agriculture extension staff were identified. An MoU with the Met Services and the National Office for Risk and Disaster Management to implement these training sessions is under development. | 100 % of staff trained on climate change aspects and how to disseminate new knowledge to farmers, including women.
Outcome 2.1. Sustainable increase in rice yields (using MIRR) | Percentage of change in rice yields in all three project sites | Rice yields in 2012-2013 for irrigated rice in the project areas were:  Manakambahiny – 3.41 tons/ha average (roughly 3 tons/ha for Mk34 and 3.5 tons/ha for Dista and Tsemaka)  Bemaintso – 0.7 tons/ha for MK34 and 1.5 tons/ha for Dista (the low yields observed in Bemaintso are due to floods – care should therefore be taken while analyzing these data)  Ambohijanahary – 2 tons/ha for MK34 and 3 tons for Tsemaka  Tsemaka – Farmers use the variety to increase yields under challenging water conditions; however, farmers report that it does not sell as well at market as MK34.  MKx – Variety developed and distributed by CALA.  Dista – Farmers use the variety in cases where the planting rains start late.  SEBOTA – The variety was developed for the BV Lac project in partnership with CALA and with help from CIRAD. It is designed to tolerate poor water management conditions, but the seed has not been distributed to many farmers due to limited reproduction of the seed and to patent issues.  FOFIFA – This is a group of early maturing varieties that can be produced in the rainy and dry seasons. They are developed by CALA. The last variety developed under this group is FOFIFA 174. | The average rice production among the targeted farmers was 2,15 T/ha in season 2013-2014. It increased to 4,75 T/ha in season 2014-2015, 6,25 T/ha in season 2015-2016 and 5,85 T/ha in 2016-2017 thanks to the adoption of the MIRR practices by trained farmers. The number of people adopting the MIRR practices has significantly increased from one cultivation season to the other. However, it takes a long time and several demonstration seasons for the majority of the farmers to be willing to change their practices. As a result, it has been difficult to implement sustainable systems for compost or rice varieties production, for example. The rehabilitation work for water infrastructure will be completed by January 2018. This is expected to increase rice yields significantly, as it is a major constraint to rice production in the project areas. | Individual rice yields for targeted producers increase by 25% in relation to current averages in each project area.
Output 2.1.1 Climate resilient rice varieties selected through participatory field testing | Number and types of climate resilient rice varieties tested and selected within the three project sites (Municipalities of Manakambahiny, Ambohijanahary and Bemaintso) | Current rice farming is dominated by the seed variety MK34, though it is not necessarily resilient. The next most prominent varieties are Dista and Tsemaka. | The climate-resilient rice varieties created and tested by CALA in the laboratory were presented to the farmers during a workshop in September 2014. Among the varieties presented, the farmers selected three varieties. These varieties were thereafter tested in the field. These varieties are SEBOTA 231, X265 and Madikatra. Based on consultation of CALA, no activities to strengthen their facilities and capacities were deemed necessary. CALA facilities and capacities are sufficient to develop the required varieties. | CALA facilities and capacities are strengthened to develop at least 5 varieties that are tested and proven resilient in both laboratory and field settings in the three project sites. | 3 rice varieties were selected for field-testing.
Output 2.1.2 An operational multiplication and dissemination scheme for adapted seed varieties | Annual quantity and quality of adapted certified seeds produced and distributed in each of the project sites | Seed multiplication appears to be dominated by four main facilities. Challenges include production capacity for CALA and the publication and dissemination of seed-specific planting guidelines. | To date, 439 tons of seeds were distributed for the season 2014-2015 for the three sites, 5,650 tons for the season 2015-2016, and 5,679 tons for the season 2016-2017. Production of adapted seeds is being conducted. During the first years of the project, it has been difficult to identify farmers willing to specificialise in the production of MIRR seeds. Production was therefore done by the CALA. However, local producers in Manakambahiny and Bemaitso have recently received the certification from the National Agency for the Official Control of Seeds and Plants (ANCOS) for the production of rice seeds for the new varieties. As a result, a significant part of the seeds used for the season 2016-2017 were produced by local farmers. The farmers is Ambohijanahary did not receive the certification because they did not meet all the criteria. | At least 5 tons total of seeds for all 5 varieties that were tested and proven resilient are produced annually and distributed in the 3 project sites. | As above: Only 3 rice varieties were selected.
Output 2.1.3 Updated fertilisation guidelines according to best available standards and taking climate conditions into consideration | Number of farmers who apply updated fertilisation guidelines in all three project sites (Municipalities of Manakambahiny, Ambohijanahary and Bemaintso) | Farmers do not appear to follow any specific guidelines for fertilizer application. Farmers vary on how and when they use compost, manure, urea, NPK, and/or DAP. Many farmers do not use any chemical fertilizer practices.fertilisers are not commonly used | To date, a total of 2 438 farmers (569 in Manakambahiny, 904 in Ambohijanahary, 965 in Bemaitso) have received theoretical and practical training on the production and use of organic compost. This figure corresponds to the number of people targeted by the project as well as some from the surrounding communities interested in the training. Training has not been limited to the target population. Among the farmers who received training, 89% are applying the fertilisation guidelines provided. The farmers have been trained by STOI and now produce their compost independently from the project. This production system still has to be strengthened to enable production in the long term. A socio-economic report on the sustainability of the project interventions is underway and will identify the remaining gaps. The priority interventions identified will be covered as much as possible by the project. | 90% of targeted farmers have been trained and/or received technical support and apply fertilisation guidelines updated as part of the development of the MIRR.
Output 2.1.4 Integrated pest management is implemented | Number of farmers trained in integrated pest management in all three project sites (gender and age disaggregated) | In general, farmers had no information or training about the appropriate protocols for using pesticide in pest control. While some used commercial pesticides, they applied them with little knowledge of best practices. | A national IPM expert provided training to 432 farmers including 128 women on integrated pest management during the second trimester of 2017. | 400 farmers trained in integrated pest management, gender and age disaggregated (and among them 50% women and young)
Output 2.1.5a Water efficiency, management and conservation technologies and infrastructures are implemented | Number of Km of rehabilitated irrigation canals and number of reservoirs dredged in all three project sites | Infrastructure in the 3 municipalities was in a state of significant disrepair with damaging siltation and reduced irrigation capacities throughout. There is a large need for rehabilitating canals and dam infrastructure. | A civil engineer was appointed by the project to undertake the feasibility study for the rehabilitation of water management infrastructure, prioritise local communities' needs and develop the calls for tender and technical guidelines. The financial proposal corresponding to the expected rehabilitation targets for the water infrastructures in Ambohijanaharay was two times higher than the available budget. A second prioritisation of the interventions was therefore undertaken with the beneficiaries to align with the budget available. The procurement process was finalised in September 2017, and the rehabilitation interventions were initiated in October 2017 in all sites. | Manakambahiny: 35 km of primary canals cured, dredged, and maintained with norms that take expected climate change impacts into account (future precipitation regimes, drainage and run-off); 4 water intake points along the Ilakana River rehabilitated, strengthened and made more resilient to expected climate change impacts. Bemaitso: The dam is drained and dredged; 14 km of primary canals and 21 km of secondary canals are cured, dredged, and maintained all with norms that take expected climate change impacts into account. Ambohijanahary: The dam at Anony is rehabilitated, primary water control valves are repaired; 13 km of primary canal are drained, dredged, and repaired; and primary canal is extended to irrigate 600 ha of additional rice fields all with norms that take expected climate change impacts into account. | Due to insufficient budget and other factors outlined below, the water infrastructure rehabilitation interventions had to be re-prioritised in consultation with project beneficiaries. The following summarizes the revised activities and their rationale. Manakambahiny: 1 water intake point is sufficient to meet the needs in the site. The main canal is only 4.1 km long. No dredging is planned in the secondary canal because each portion is private and belongs to one farmer. However, some infrastructure that directs the water from the primary to the secondary canals will be rehabilitated. There is a conflict between two water user associations, and some activities are planned to resolve this conflict (e.g. to prevent the watering of the rice field downstream (belonging to WUA 1) to flood the rice field upstream (belonging to WUA 2)). As such, the revised plan includes: 4.1 km of primary canals cured, dredged, and maintained with norms that take expected climate change impacts into account (future precipitation regimes, drainage and run-off) including the construction and rehabilitation of 16 culverts, the rehabilitation of water diverters and regulators, the construction of 2 paths to enable crossing of the canal by people and livestock, and the construction and rehabilitation of secondary water intakes to carry water from the primary to the secondary canals; 1 water intake point along the Ilakana River rehabilitated, strengthened and made more resilient to expected climate change impacts; road going over the canal strengthened to protect it from overflowing and prevent sedimentation in the canals; dike along the river strengthened to prevent flooding of the rice field during intense rains. Bemaitso: The farmers have developed a management plan for the water infrastructure. They have identified problems and presented them to project’s expert. The project addresses the priorities they have identified. The spillway of the dam will be strengthened. However, no dredging of the dam is needed. The Regional Directorate of Agriculture and Livestock Husbandry has worked with a service provider to rehabilitate the L-shaped structure of the dam in November 2016. Some faults have been identified in their work but their intervention is still under warranty and the company committed to undertake the required repairs. The project will therefore focus on another part of the dam, which is the security spillway. Some work will be undertaken on the secondary canals that are not private in this site. Each section affects a group of farmers. The following revised activities are therefore planned: The spillway of the dam is strengthened; 5.3 km of primary canals – including the rehabilitation of a culvert and a small aqueduct – and 3.5 km of secondary canals are cured, dredged, and maintained all with norms that take expected climate change impacts into account. Ambohijanahary: The Regional Directorate of Agriculture has asked for the interventions of AFRice to be clearly differentiated from the interventions of PHART project who will work on improving irrigation systems. The farmers were therefore asked to prioritise, and they chose the canal dredging and the dike as the priorities to be covered by AFRice. Anony dam, including the primary control valves, will therefore be rehabilitated later by PHART project. The rehabilitation of the protection dike replaces the rehabilitation of the dam in the activities. Extending the primary canal to irrigate 600 additional hectares was not prioritized by the farmers in the site; it was therefore not selected. As a result, the following activities are planned: [TBD] km of primary canal are drained, dredged, and repaired; [TBD] km of protection dike are strengthened to prevent flooding of the rice fields during intense rains. It was initially planned to drain 14.2 km of primary canal and strengthen 5.2 km of protection dike in Ambohijanahary. However, the financial proposals of the candidates who replied to the Call for Tender for this work were double the budget available. The civil engineer in charge of designing and monitoring the rehabilitation work is currently reducing the tender for Ambohijanahary to fit under the budget available.
Output 2.1.5b Water efficiency, management and conservation technologies and infrastructures are implemented | Percentage of change in water availability and in water use efficiency in all seasons to water users associations in all three project sites | There is a decrease in water availability during the dry season in all 3 Districts, and water losses reach up to 50 %. | Water losses and availability have been assessed in September 2017 and the same measurements will be undertaken after the water infrastructure rehabilitation works are completed (in Q1 2018). A decrease in water loss and an increase in water availability are expected as soon as the new infrastructure is functional. (20% complete) | 35 % increase in water availability in all seasons in all 3 districts. Water loss estimation decrease from 50% to 25%.
Outcome 2.2. Ecosystem services maintained | Percentage change in land covered by biomass and in overall productivity (rice, vegetables and livestock) in project sites | There is no evidence of activities to increase land covered by biomass such as agro forestry practices, reforestation, or vegetable crop rotations. No farmers use soil quality or water quality improvement techniques. | There has been a significant delay in achieving this outcome, mostly owing to the difficulties encountered by the main service provider, the SNGF. A plan to catch up on the delays was developed (including the creation of a specific bank account for the project funds to facilitate project-related disbursement), and signed by SNGF. However, the second planting season was not successful either. 68 hectares out of 900 were reforested during the first season. 278 out of 1200 were reforested during the second planting season. A high mortality rate (>50%) was recorded among these 346 hectares. As a result, the contract with SNGF was cancelled in December 2016. For the season 2016-2017, one NGO per site was appointed to restore 65 hectares per site. A contract was also signed with each commune to restore 65 additional hectares. However, the procurement and contracting processes were delayed by the cancellation process for the SNGF contract. The planting work could only start in March 2017, which corresponded with the end of the rainy season. Except for Bemaitso, it was too late to plant seeds in nurseries, and seedlings were therefore bought in nearby nurseries and planted directly on site. A high mortality rate was encounted for this 2016-2017 planting season for several reasons, including low rainfall. Based on these results and the experience of other partners (e.g. the LIFE model of JICA), the PCU and the CTA have launched a fully community-based reforestation approach for the 2017-2018 season. This approach is based on communities' willingness and commitment to plant and maintain trees. The project will provide small equipment and sapplings, while the beneficiaries will undertake planting interventions and ensure survival. Regarding the development of agroforestry practices, 257 farmers and extension workers were trained on agroforestry in the project sites during the 2016-2017 season. This included the production of 20 posters and 50 pamphlets, and 28 training sessions. The contract of the national consultant was amended based on additional requests for training from local communities. As part of the amended contract, local communities will be supported by the project to plant agroforestry species over a total of 50 ha per site. The NGO in charge of providing training on land management for upland and lowland communities was appointed in July 2017. A methodology report was submitted in October 2017 and the training activities will be initiated in November 2017. The revitalization activities of Water Users' Associations (WUAs) and the training of members and cooperatives have been completed. These have led to the resolution of various water-use disputes, and led to the formation of new associations and members. These new members formulated requests for additional training from the project. It was therefore decided by the PCU and the expert to organise additional training sessions until the end of 2017. Research on how to value the rice straw has been undertaken, and farmers have been trained on the use of this by-product. A follow-up study is currently being undertaken to measure the qualitative and quantitative effects of these training interventions on changes of practices. Vegetable production has increased from 0.15 tons in 2013 to 01 tons in 2017 following the training provided on off-season cultivation since 2014. Rice production has increased from 2.15 tons in 2013 to 5.85 tons in 2017 following the training on MIRR techniques. | Change in overall land area covered by forests (i.e. net reforestation) of at least 50km2 across the combined 3 municipalities. Data on vegetables and livestock productivity/yields collected by extension services, and increase in overall productivity of rice, vegetables and livestock of 5 % throughout the life of the project and across the project sites. | Due to the significant delays and major challenges in reforestation activities (outlined under "progress"), the reforestation target will not be met. A more realistic target for project end would be a change in overall land area covered by forests (i.e. net reforestation) of 18 km2 across the combined 3 municipalities. As for livestock productivity, because the baseline measurements were very basic, it is unlikely that any significant increase in overall productivity of livestock will be measured. The baseline situation was only measured in terms of number of animals at each site. Negotiations are underway for the expert who undertook the training on the use of rice straw in livestock feeding to go into the field to undertake this measurement again, to compare it to the baseline situation.
Output 2.2.1 Best available land preparation, production and harvesting techniques disseminated to reduce deforestation, maintain soil fertility and integrity, and to provide adequate growing conditions | Percentage application of resilient rice model, including rice–vegetables rotation systems, in all three project sites (gender disaggregated) | Rice/vegetable crop rotations are used on only very small pieces of rice fields. Guidelines for rice/vegetable rotation practices were developed under the BV Lac project, but their dissemination was somewhat limited. | CALA provided training on rice-vegetable crop rotation in 2015 and 2016. In 2015, 65 farmers (13%) cultivated non-rice crops (i.e. carrots, onions, beans, potatoes, cabbage, tomatoes) on an average of 0.06 hectare each. In 2016, 903 farmers (75%) cultivated non-rice crops (i.e. cabbage, courgettes, cucumber, beetroot, cauliflower, pepper, Petsaï, vetch, carrots, onions, beans, potatoes, tomatoes) on an average of 0.17 hectare each. In 2017, 479 farmers (40%) have cultivated non-rice crops (i.e. cabbage, courgettes, cucumber, beetroot, coliflower, pepper, Petsaï, vetch, carrots, onions, beans, potatoes, tomatoes) on an average of 0.16 hectare each. Approximately 80% of this production was for commercial purposes. | At least 75% of targeted farmers practice rice/vegetable crop rotation on an area larger than 0.1 ha and for commercial purposes (and among them at least 50% of women and young).
Output 2.2.2 Watershed rehabilitation in productive landscapes introduced, including through reforestation and adaptation of agro forestry practices | # of ha reforested; # of farmers and land/forest users trained on sustainable agro-forestry and land management in all three project sites (gender and age disaggregated) | some reforestation underway in the broader basin but not in project sites; currently there are no people trained on SLM and agroforestry in the project sites | There have been significant delays in achieving this outcome, mostly owing to the difficulties encountered by the service provider initially appointed, the SNGF. A plan to catch up on the delays was developed (including the creation of a specific bank account for the project funds to facilitate project-related disbursement), and signed by SNGF. However, the second planting season was not successful either. 68 hectares out of 900 were reforested during the first season. 278 out of 1200 were reforested during the second planting season. A high mortality rate (>50%) was recorded among these 346 hectares (20% complete). As a result, the contract with SNGF was cancelled in December 2016. For the season 2016-2017, one NGO per site was appointed to restore 65 hectares per site. A contract was also signed with each commune to restore 65 additional hectares. However, the procurement and contracting processes have been delayed by the cancellation process for SNGF contract. The planting work could only start in March 2017 which corresponded with the end of the rainy season. Except for Bemaitso, it was too late to plant in nurseries, sapplings were therefore bought in nearby nurseries and planted directly on site. A high mortality rate was encounted for this 2016-2017 planting for several reasons, including insufficient rainfall. The results of this latest planting season are as follows: In Ambohijanahary: - Commune contract: 15 ha restored with a mortality rate of ~80% - NGO contract: 49 ha restored with a mortality rate of ~65% In Bemaitso: - Commune contract: 65 ha restored with a mortality rate of ~50% - NGO contract: 65 ha restored with a mortality rate of ~66% In Manakambahiny: - Commune contract: 54 ha restored with a mortality rate of ~60% - NGO contract: 40 ha restored with a mortality rate of ~81,5% Each of these institutions are committed to meet the 65 ha target and replace all the dead plants during the 2017-2018 season. Regarding the poor results of the previous seasons and the fact that successful interventions have been implemented independently by landowners in each site, the new approach selected for the last planting season (2017-2018) is 100% community-based. Local communities have been asked to propose land to be restored by the project. Nursery managers trained by the project during the first planting seasons are responsible for the production of the sapplings. Support will be provided to dig the planting holes and potentially to undertake the planting activities where needed, but no remuneration of land owners will be undertaken in order to ensure that only the most motivated community members benefit from the activities. This approach is expected to enable a high survival rate and the maintenance of the restored sites beyond the project lifespan. A total of 608 hectares have been proposed by local communities for the implementation of the restoration interventions during the 2017-2018 season. Regarding the development of agroforestry practices, 257 farmers and extension workers were trained on agroforestry in the project sites during the season 2016-2017. This includes the production of 20 posters and 50 pamphlets, and 28 training sessions. The contract of the national consultant was amended based on additional requests for training from local communities. As part of the amended contract, local communities will be supported by the project to plant agroforestry species over a total of 50 ha per site. The NGO in charge of providing training on land management for upland and lowland communities was appointed in July 2017. A methodology report was submitted in October 2017 and the training activities will be initiated in November 2017. | In total, at least 50km2 of area distributed in the 3 districts are reforested (5,000 ha). At least 400 farmers trained in sustainable agro forestry and land management (and among them 50% of women and young). | See notes under Outcome 2.2.
Output 2.2.3 Soil conservation and livestock management techniques adapted to topography and landscape in light of future climate conditions | % change in erosion rate | The project PRODAIRE has been training workers for the DREF in monitoring erosion rates. The DREF has therefore the in-house capacities to monitor erosion rates in the project sites. Average erosion rate in the region is 12 mm.yr.1, according to Cox, R. et.al, 2009 “ Erosion Rates and Sediment Contributions in Madagascar Inferred from 10 Analysis of Lavaka, Slope, and River Sediment” | Due to the very limited success of the reforestation efforts during the first two seasons (see under output. 2.2.2), it is unlikely that any significant improvement in erosion rates can be measured before the end of the project, as the trees will still be very small. | 50% reduction in erosion rates | Due to the very limited success of the reforestation efforts during the first two seasons (see under output. 2.2.2), it is unlikely that any significant improvement in erosion rates can be measured before the end of the project, as the trees will still be very small. Based on the estimate received, this study to measure erosion rates would cost approximately US$ 26,000. The project team therefore proposes to not measure progress towards target for this indicator, as this does not seem to be a wise use of funds.
Output 2.2.4 Revitalization of producer’s cooperatives and water user associations for collaborative natural resources allocations (e.g. land and water) and management | Number of members of farmer’s cooperatives and water user associations trained on water management and administrative management within the three project sites | Water user cooperatives exist in the three project areas; however, in all areas members expressed a need for training in administrative management as well as training in water management. | An analysis of the situation regarding Water user associations has been conducted in 2016 and recommendations were made on means to strengthen the WUAs. Thereafter, training was provided to 84 WUA members on water management. Furthermore, additional training for WUAs on administrative and financial management, as well as water management, was initiated in 2017. To date, 269 WUA members (79,5% of the total number of WUA members) have been trained in 2017. | 75 % of the members of water user cooperatives in the project area have been trained on water management and administrative management.
Output 2.2.5 Water quality assessments | Percentage change in water quality (e.g. reduction in turbidity, pollutant content, microbial content, sediment content) in all three project sites | There is currently no water quality analysis conducted in any of the three municipalities | Water losses and availability have been assessed in September 2017 and the same measurements will be undertaken after the rehabilitation work is achieved. A national expert developed the sampling methodology and collected the samples that were thereafter analysed by the National Center for Environmental Research. The water infrastructure will be finalised by January 2018. Decrease in water loss and increase in water availability are expected as soon as the new infrastructure is functional. One technical staff per site was trained on the sampling techniques (20% complete). | Water quality assessment is conducted in all 3 project sites by a national expert and training to the DIREAU to undertake this kind of analysis is provided. Water quality increase by 10 % from the date of the first analysis
Outcome 2.3. Post Harvest losses reduced | Percentage change in post harvest losses | Post–harvest losses are estimated to be between 5 and 10% of total harvest. | The construction of three climate-resilient storage facilities was initiated in July 2016. However, the construction did not follow the technical specifications of the call for tender. The construction was therefore been suspended and the contract was been cancelled, and other companies were contracted to build the three new storage facilities. As soon as the construction will be completed, training on the management of the storage facility and on the conservation of the products will be provided. The consultant in charge of these trainings is also responsible for monitoring the effects of the training and the new infrastructure on harvest losses. | Post-harvest losses are reduced to less than 4%.
Output 2.3.1 Increased utilization of rice by–product especially rice straw | Percentage change in use of rice straws in animal feeding and for briquetting | There are regional variations in the degree to which farmers exploit rice stalks for other uses. In some municipalities, residues are simply burned in the field. | The use of rice straw in the project sites was analysed through the survey of 40 families. Thereafter, 350 farmers were trained on the use and commercialisation of rice straw as a source of energy and other uses. The effects of this training on the use and commercialisation of rice straws will be measured by the end of December 2017. | 75% of farmers use or commercialize rice straws.
Output 2.3.2 Post–harvest storage facilities with phytosanitary control, serving as trading points and markets | Number of renovated storage facilities in all three project sites | Storage facilities in the project sites exist, but they are not in adequate condition | A comprehensive feasibility study was completed and recommendations were made on the rehabilitation and construction of upgraded resilient storage facilities. The construction of three climate-resilient storage facilities was initiated in July 2016. However, the construction did not follow the technical specifications of the call for tender. The contracts were cancelled and three new companies were contracted in October 2017 to build new storage facilities. As soon as the construction will be completed, training on the management of the storage facility and on the conservation of the products will be provided by an expert that has already been appointed. | 75% of existing facilities have been renovated. | Instead of 75% of storage facilities being renovated, the project will be building three new climate-resilient storage facilities. Existing storage facilities were on private land. It was therefore preferred to build new facilities on communal land close to the city hall to avoid conflicts over usage of the facilities and facilitate the guarding of the production.
Outcome 3.1 Technical norms and standards in rice cultivation reviewed and where necessary modified to take climate change into account | Number and types of technical norms and standards in rice cultivation reviewed and modified at the national level to take climate change into account | No recommendation or revision has currently been made to technical norms and standards in rice cultivation. | The MIRR guidelines were developed in Malagasy and French, and have been validated at the local levels. They will be validated at the national level in February 2018. The MIRR principles are integrated in the National Strategy on Rice Cultivation which was validated on 19 December 2016. No additional documents have been identified as priorities for integration of the MIRR principles. The upscaling strategy for the MIRR is under finalisation. A draft action plan for the upscaling of MIRR was developped by CALA and will identify the required interventions to disseminate the MIRR practices, including the complementary documents that should be developed. | At least one national strategy on rice cultivation and at least one technical guideline for the following rice cultivation stages/techniques are revised and updated at the national level: • Seeding • Planting • Harvest • Post–harvest • Fertilization • Integrated pest management • Water management
Output 3 .1.1a Gaps and possible maladaptations in the current rice policy are identified and recommendations on rice policy reform are made | Number and types of activities identified and implemented for up scaling and replication from MIRR application in broader Alaotra basin and in other regions | While there is an Agricultural Development Strategy at the national level, it does not have a true application at the regional level due to financing. There is no specific policy for growing rice. | A workshop between the Ministry of Agriculture, FOFIFA, CALA and other relevant partners was organised to discuss the results of the MIRR, and the development of a replication and upscaling strategy. A draft action plan for the upscaling of MIRR was developped by CALA. This strategy is currently under finalisation by FOFIFA and will be received by the end of 2017. | 1 replication strategy and action plan developed, including at least 5 to 10 operational activities for up scaling and replication of MIRR practices in the broader Alaotra basin and beyond.
Output 3.1.1b Gaps and possible maladaptations in the current rice policy are identified and recommendations on rice policy reform are made | Number and types of recommendations on rice policy reforms made | The National Strategy on Rural Development (SNDR) was completed; however, this strategy has not been published or disseminated. | The MIRR principles were integrated by FOFIFA in the National Strategy for Rice Cultivation. No additional needs for integration of MIRR principles in other strategies or plans have been identified by the project stakeholders to date. | The SNDR is revised with measures to increase climate change resilience of rice production, and then the strategy is published and disseminated. | The revised SNDR will likely not be finalized or published before the end of the project.
Outcome indicator 3.2 Conditions in place for a full adaptation of the rice sub–sector | Number and type of stakeholders to which the report on best practices and lessons learned is distributed | Lessons learned and best practices will be identified and collected during project implementation | The PCU will compile and disseminate the lessons learned and best practices of the project early 2018. | 1 report at end of project.
Output indicator 3.2.1 A report on best practices and lessons learned for rice adaptation in Madagascar | Number and type of stakeholders to which the report on best practices and lessons learned is distributed | None | The report on lessons learned and best practices will be distributed during the second trimester of 2018. | 600 people from the following institutions receive the report on lessons learnt and best practices: Ministry of Environment, Ecology and Forest, Ministry of the Interior and Decentralization, Ministry with the Presidency in charge of Agriculture and Livestock, Ministry of Communication and Relations with Institutions, Ministry of Water, Energy and Hydrocarbures, Ministry of Transport and Meteorology, National Geographic and Hydrographic Institute, National Committee of Climate Change, Cell of Prevention and Emergency Management, National Office of Risk and Disaster Management, FOFIFA/CALA, Deconcentrated Technical Services, Ministerial department at regional level, Ecole Supérieure des Sciences Agronomiques, National Television and Radio.
Output indicator 3.2.2 A strategy for communicating information on adaptation techniques to farmers is implemented | N/A | N/A | Activities began in 2014 and are designed to last until project completion. A rural communication strategy was developed. During the first stage of its implementation, radio talks on MIRR practices were broadcasted locally and pamphlets were developed and distributed. However, because of insufficient performance, the contract with the communication expert was cancelled. A new communication consultant was appointed and is currently developing radio talks, newspaper articles, a web page, a TV documentary, and awareness-raising days in each site. | At least one documentary on MIRR practices developed and broadcasted on national TV and radio talks broadcasted on local and national radio stations. Field visits and training for at least 2 representatives of 4 farmers associations throughout Alaotra-Mangoro to the project sites. 1 field visits and training for Regional Agriculture Delegation and other relevant groups (e.g. Associations Paysannes Régionales, Vulgarisateurs Agricoles, Fédération des AUEs...) of other selected regions.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The project has encountered significant difficulties with some service providers who did not have the required capacity to deliver results. This is the case of the SNGF, as well as some consultants. A more thorough capacity assessment for service providers should be conducted before signing agreements, particularly those that are signed on a non-competitive basis. The project has also encountered significant difficulties in terms of management processes, procurement, etc. In future, comprehensive training and harmonization of procedures should be conducted early on. Based on the experience gained during the project implementation to date, contracting government institutions for the implementation of project activities should preferably be avoided. If a government institutions hired as a service provider does not perform, it is challenging to insist that these institutions apply corrective actions or to break their contracts, because the executing entity needs to maintain good relationships with other government institutions. The fact that local communities asserted their interest to see project activities being implemented is not sufficient to ensure their support in the maintenance of the interventions. It seems necessary to test the motivation of beneficiaires by checking first that they are willing to invest time and energy in the implementation of project activities without being paid for it. This hypothesis will be tested during the last planting season for the restoration interventions.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes. Delays were caused by a variety of reasons: lack of capacity of service providers and low quality of outputs, difficulties in procurement of required expertise and resources, changes in procedures at UNEP and within MEF, changes in personnel in MEF and other key ministries. These have been addressed individually as much as possible, and are being monitored by the CTA and TM. (see risk section for additional mitigation detail)
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Changes to delivery strategies and mechanisms occur on an ongoing basis. Revisions to several project targets were proposed to the AF board earlier this year to account for shortcomings, challenges and delays. In addition, activities were added to promote the sustainability of the project, such as the development of a communication strategy, the certification of seed producers and a socio-economic analysis of the sustainability of project interventions. Further changes are expected in 2018 to increase the capacity of farmers to maintain the use of the entire MIRR practices package beyond the project, based on the socio-economic report that is currently under development. Last, awareness raising on bushfires will be provided by DREF to increase the sustainability of the reforestation interventions.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | During the first couple of years of the project, service providers did not monitor women's participation systematically. Since 2017, this is now clearly specified in the ToRs of the experts to ensure that gender considerations would be systematically integrated in the training and awareness raising interventions.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The high turnover in government staff in Madagascar requires very regular meetings by the PCU with government representatives to make sure that representatives in the key institutions are aware of and fully support the project.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The involvement of the Ministry of Agriculture should have been stronger from the beginning of the project. Additionally, the turnover within all institutions resulted in limited awareness of the Ministry of Agriculture fn the project whose MIRR component falls directly under their mandate. Their involvement will be significantly increased during the last year of the project. For future projects, the key government institutions should be involved in every step of the project design and implementation.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | All partners have the tendancy to implement their interventions without taking climate change into account, despite the emphasise on climate change in the ToRs. Most of the time only past trends and current conditions are considered. A close control of the consideration of future climate conditions by the experts appointed by the project is therefore required for all project activities.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | A replication and upscaling strategy will be developed in 2017 together with an action plan containing concrete on-the-ground interventions. Additionally, field visit to the intervention sites and training will be organised for representatives from other farmers' organisations in the region, as well as selected stakeholders and agriculture extension staff from other selected regions during the last year of the project. Finally, farmers not benefitting from the project have adopted some of the MIRR practices because they learned from the demonstration sites implemented. The project interventions are therefore already being upscaled locally. There is still significant work to be achieved in 2017 to promote maintenance of the interventions but the potential for replication and upscaling is considered as good.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | To date, the most successful interventions for local communities is the introduction of the following practices: production and use of organic compost, use of climate-resilient species, cultivation of counter-season rice and production of non-rice crops. These practices have led to a significant increase in rice and crop yields.
What measures are/have been put in place to ensure sustainability of the project/program results? | One of the recommendations of the MTR was to increase awareness of the beneficiaries on the fact that the funds would stop soon and it was the farmers responsibility to ensure that they would have all the tools and knowledge necessary before the end of the project to be able to continue benefitting from the project outputs beyond its end. As a result, since the beginning of 2016, the sustainability of the interventions were discussed with local communities on a more regular basis. Regarding the MIRR, some aspects still need to be sustained (e.g. rice seed production in Ambohijanahary, non-rice seed production in all sites) but the project beneficiaires can now implement most of the MIRR elements without the project support. For the restoration interventions, long-term management agreements will be developped and awareness-raising campaigns against bushfires will be implemented. These measures will promote the maintenance of the project outputs in the long term.
What measures are being/could have been put in place to improve project/program results? | The development of a communication strategy was added to the project activities to support the upscaling and replication of the interventions. In addition, two new activities will be implemented in 2017 to sustain the project interventions: training on the production of non-rice seeds and awareness-raising against bushfires.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Following the poor results obtained by SNGF during two planting seasons, the PCU is currently identifying potential plant species to be used in the reforestation interventions. To do so, relevant government institutions and NGOs are being consulted to benefit from their experience, and litterature research is underway.
If learning objectives have been established, have they been met? Please describe. | N/A
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | No particular difficulties have been encountered regarding access to existing information relevant to the project.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A

## New Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | AFB-5060-1111-2G49
Implementing Entity | UNEP
Type of implementing entity | MIE
Country | Madagascar
Region | Africa
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 26.264 | 4.538 | 21.726 | Total | 1200 | 200 | 1000 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 33% | 19% | 40% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 43% | 15% | 50% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 10% |  | Agriculture |  | 75 |  | Agriculture |  | 25% |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 0 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 500 | ha rehabilitated | 4: Effective | Cultivated land/Agricultural land | 10 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 0 | ha rehabilitated | 1: Ineffective | Catchment area/Watershed/Aquifer | 4000 | ha rehabilitated | 4: Effective | Forests | 4000 | ha rehabilitated | 1: Ineffective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | N/A | N/A | N/A | 1000 | 35% | From 10% to 20% | Agriculture | 200 | 25% | From 1% to 5% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness

## Old Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 4 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 4.2 | 4 | 2 | TBC
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 4 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 4.2 | Irrigation and drainage infrastructure is improved in 3 sites as follows: Manakambahiny: 35 km of primary canals cured, dredged, and maintained,; Bemaintso: The dam is drained and dredged; 14 km of primary canals and 21 km of secondary canals are cured, dredged, and maintained; Ambohijanahary: The dam at Anony is rehabilitated, primary water control valves are repaired; 13 km of primary canal are drained, dredged, and repaired; and primary canal is extended to irrigate 600 ha of additional rice fields. | 0 physical assets are made resilient to impacts of climate change | TBC
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5 | 4 - Mostly Effective. Change in overall land area covered by forests (i.e. net reforestation) of at least 50km2 across the combined 3 municipalities. | 2 | TBC
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5 | At least 5000 ha reforested across 3 districts | Limited or no reforestation activities in target areas | TBC
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced

## Old Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.