## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 4 March 2020 to 30 December 2020
| Project Title: | Programme Support for Climate Change Adaptation in the vulnerable regions of Mopti and Timbuktu
| Project Summary: | The main objective of the programme is to increase the resilience of vulnerable communities and their adaptive capacity to climate change in the Regions of Mopti and Timbuctu including the Faguibine system zone. The programme has three components with the following specific outcomes: Component 1: Enhanced water control measures in vulnerable water buffer zones. Outcome 1: Increased climate change resilience of local water systems in Mopti and Timbuctu Regions. Component 2: Resilience in subsistence livelihoods of vulnerable communities. Outcome 2: The production of local livelihood systems such as agriculture, fisheries, livestock, and forest enhanced under climate change Component 3: Capacity-building and knowledge generation for adaptation Outcome 3: Enhanced capacity of local institutions and of communities to better adapt to climate change.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PIMS No 4789 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme (UNDP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | UNDP as Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Mali | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Communes of Mopti Region : Bamba, Pelou, Kendé, Tédié, Koubewel-koundia, Gandamia, Dangol-Boré, Pondori and Togoro-Kotia. Communes of Timbuctu Region : Alafia, Hanzakoma, Haribomo, Goundam, Gargando, Bintagoungou, Essakane, Kondi, Arham, Tindirma, and Binga; | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 30/03/2015
IE-AFB Agreement Signature Date: |  | 04 November 2015 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 04 March 2016 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2018-06-01
| Terminal Evaluation Date: | 19 october to 27 november 2020
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Reports: • Program Launch Report • Report on the situation of reference in Mopti and Timbuktu 2016 • PPR 2016, 2017, 2018 and 2019 • Quarterly and annuel Reports 2016, 2017, 2018, 2019 and 2020 to UNDP CO (Progress Report/Financial Reports/Quarterly Work Plan/Annual Work Plan) • Report of the Steering Committee 2016, 2017, 2018 and 2019 • Report of the extraordinary Steering Committee in 2018 • Project Website • Study report on the carbon sequestration rate of agroforestry parks in the project intervention zone. • Photos of construction sites and documentary films from 2017 to 2020 • Revision report on programme indicators and targets 2017 • Monitoring reports of naturally assisted regeneration and training of farmers in Agroforestery parks Of the communities of Bamba, Kendé and Dangol-Boré 2017, 2018 and 2019 • Farmers training report on improved seed cultivation techniques and improved seed monitoring (2017 and 2018 Aand 2019) • Farmers training report on agroforestry techniques adapted to climate change (2017 and 2018 and 2019) • Documentary film of project investments in Mopti in 2019 • Training report for Community counsellors and civil society on the institutional management of climate change (2017) • Report on the training of stae technical agents on the management of climate change and ODD in te cirdle of r Diré, Tombouctou, Bandiagara et Djenné (2019) • Report on the training of farmers and elected officials on climatic and meteorological applications (2018) • Communication Plan Document of the programme 2018 • Work Plans and annual Budgets (2016, 2017, 2018, 2019 and 2020) • Status of implementation of the recommendations of the first, second, third and fourth session of the Programme Steering Committee • Report and Maps on land-use dynamics in relation to climate change in 20 communes • Project brochure for 2019 and 2020 • Report set up and capacity building of investment management structures in the 8 communes of Mopti in 2018 • Mid-term evaluation report for 2018 • Training report of pilot farmers on conservation techniques for improved seed varieties in 2017, 2018 and 2019 • Study reports for 2016, 2017 and 2018 • Control and monitoring of works reports for 2017, 2018 and 2019 • 19 revised municipal PDESC including climate change-related actions and the SDGs • Photo albums of the launch of the project and the steering committees • Assessment report of the 3 years using improved seeds • Reports on capacity building and review of the functionality of investment management committees • 22 Work execution contracts and work acceptance reports • Final evaluation report for 2020 | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.pacvmt-mali.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Balougo TELLY | Dominican Republic
| Email: | balougotelly@yahoo.fr | Ecuador
| Date: | 2020-08-20 | Egypt
| Government DA |  | El Salvador
| Name: | Boureima CAMARA | Equatoral Guinea
| Email: | bouricamara@gmail.com, Tel: +22366805756 | Eritrea
| Date: | 2020-08-20 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | United Nations Development Programme (UNDP) | Fiji
| Email: | oumar.tamboura@undp.org | Finland
| Date: | 2020-08-20 | France
| Executing Agency |  | Gambia
| Name: | Environment and Sustainable Development Agency (AEDD) | Georgia
| Email: | aedd@enironnement.gov.ml | Germany
| Date: | 2020-08-20 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 30 December 2020
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 04/03/2020 | $ 7 823 226,69
Add any comments on AF Grant Funds. (word limit=200) | The project has a cumulative disbursement to date of US$ 7,823,226.69 in December 2020 (4 years and 6 months of implementation) representing 99% of the total funding and 99% of the cumulative disbursed amount (US $ 7,864,838.00) by UNDP from 2015 to 2019. The three disbursements planned in the project proposal were transfered to UNDP (i) in June 2015 at the time of the agreement, (ii) in 2017 and (iii) in November 2019. The project officially ended in September 2020. The final evaluation took place from October 19th to November 27th, 2020.
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT SPENT | AMOUNT COMMITTED | BALANCE
| Outcome 1: Increased climate change resilience of local water systems in Mopti and Timbuctu Regions. | 84390.8354 | 137371.7781 | 52980.9427
| Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 20 km silted channels and obstructed ponds | 0 | 8138.2237 | 8138.2237
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiples users including climate resilient water management systems | 84390.8354 | 129233.5544 | 44842.719
| Outcome 2: The production of local livelihood systems such as agriculture, fisheries, livestock, and forest enhanced under climate change | 212041.9258 | 144298.6993 | -67743.2266
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities | 77888.8048 | 110737.1831 | 32848.3783
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change | 134153.121 | 33561.5161 | -100591.6049
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities | 0 | 0 | 0
| Outcome 3: Enhanced capacity of local institutions and of communities to better adapt to climate change. | 16706.2951 | 62608.4934 | 45902.1982
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) | 5327.2248 | 37290.5735 | 31963.3487
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) | 11379.0703 | 25317.9199 | 13938.8496
| Output 3.3 Local institutional capacity strengthened in 20 communities in establishing micro-credit schemes, cereal banks etc. and in managing | 0 | 0 | 0
| Project Management Costs | 56301.8836 | 66773.2911 | 10471.4075
| TOTAL AF | 369440.9399 | 411052.2619 | 41611.3219 | 0
| COFINANCEMENT UNDP | 468459.01 | 508582.9635 | 40123.9535
| TOTAL AF and UNDP | 837899.9499 | 919635.2254 | 81735.2754
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Outcome 1: Increased climate change resilience of local water systems in Mopti and Timbuctu Regions. | 0
| Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 50 km silted channels and obstructed ponds | 0 | December 2020
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiples users including climate resilient water management systems | 0 | Décember 2020
| Outcome 2: The production of local livelihood systems such as agriculture, fisheries, livestock, and forest enhanced under climate change | 0
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities | 0 | December 2020
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change | 0 | December 2020
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities | 0 | December 2020
| Outcome 3: Enhanced capacity of local institutions and of communities to better adapt to climate change. | 0
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) | 0 | December 2020
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) | 0 | December 2020
| Output 3.3 Local institutional capacity strengthened in 20 communities in establishing micro-credit schemes, cereal banks etc. and in managing | 0 | December 2020
| Project Management Costs | 0
| TOTAL | 0
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | The total co-financing realized during this period is estimated at US$468,459.01 including the US$10,885.63 that should be accounted for in the PPR 2019. The cumulative realized co-financing since the start of the project is estimated at US$ 1,282,922.94 of which U$ 921,922.94 by UNDP and U$ 361,000.00 by the Government (for a total commitment of US$ 1,000,000)
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | The cumulative co-financing as verified during Mid-term Review (MTR) in 2018 is estimated at USS 384,452.00 of which U$134,452.00 by UNDP and U$ 250,000.00 by the Government
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | Thanks to in-kind co-financing from the Government of Mali, a building was made available to the project team. The government also financed the cost of electricity, water and security services. In this reporting period, the Government did not provide any co-financing and all the costs of rent, electricity and security services were covered by UNDP TRAC. The co-financing from UNDP during this reporting period is US$ 457,573.38. An additional US$ 10,885.63 of unrecorded difference in total expenditure from 2016 to 2020 can be accounted for. This gives a total co-financing of US$ 468,459.01 recorded in the final PPR (93,6% of the co-financing planned over the total duration of the project). Cumulatively, at project closure, the total cofinancing realized represents 184.3% of the total planned cofinancing at project proposal approval. UNDP TRAC made a significant contribution to the success of the no-cost extension of the project, with the financing of most of the project management costs during the extension period. At the end of the project, in September 2020, UNDP TRAC resources covered the operation of the office and project staff until November 30, to enable the facilitation of the Terminal Evaluation and activities related to the operational closure of the project.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
L
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Armed conflict that has recently escalated and engulfed the Northern region of Mali | Medium | With the coming of the wintering season, we observe a slight reduction in jihadist attacks against the populations. There were kidnappings of citizens followed by their unconditional release. However, the Armed Forces of Mali and the Minusma are attacked at least once a month. Since July 2020, inter-community meetings for reconciliation between the populations have been underway in the circles of central Mali. Agreements have been signed and many localities have been able to cultivate their fields.
Delays in project inception impacts the achievment of the outputs and outcomes and reduces the scope to deliver the project as outlined in proposal | Low | The project was given an 18-month extension at no additional cost. Thus, the total duration of the project initially planned for 3 years was extended to 4 years and 6 months.This duration was sufficient to carry out the activities planned in the project planning and to cover the delay in starting the project.
A poor collaboration between programme partners | Low | The project collaborated with several partners and obtained their involvement and participation in the implementation of the activities. These actors are in particular: communal authorities (elected officials), regional technical services (Agriculture, Rural Engineering, Hydraulics, Fisheries, Water and Forestry), NGOs, service providers, supervisory authorities, Ministries members of the national steering committee. Translated with www.DeepL.com/Translator (free version)
A poor understanding of the objectives by the programme team | Néant | The project team demonstrated a good understanding of the program's objectives throughout the implementation. This was ensured by the Terms of Reference which clearly stated the need to be familiar with climate change issues in the context of Mali. The different agencies responsible for the project (UNDP and AEDD) also continuously monitored the project to ensure a good management and understanding of the team members and the need for capacity building.
Low mobilization of the target group caused by a poor understanding of climate change issues | Low | The mayors have contributed significantly to the mobilization of local target groups, particularly for activities requiring gatherings. For example, at this time of insecurity, activities such as the revision of the PDESC require the participation of more than twenty people (elected officials and farmers) at the level of the commune's chief town. Farmers take risks in order to move around because the mayors remain their only reliable interlocutors today. The mayors are very well informed and consequently have their own strategy to prevent the farmers invited to the town hall meetings from travelling in case of danger.
Lack of sufficiently qualified partners | Low | Local skills, particularly companies, consulting firms, NGOs and individual service providers, have been prioritized by the project, following the recommendations of the steering committee. This made it possible to implement the project with the involvement of stakeholders familiar with the challenges related to the security situation, local specificities and climate change.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Statement by the Governor of the Mopti Region prohibiting the movement of two-wheeled vehicles from one village to another in the circles of Koro, Bamkass, Douetza and Bandiagara. | Low | This declaration is in force and has no effect on the activities of the project.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Because of the insecurity, in agreement with the Mayors and the technical services, the project has often delocalized the meeting places and this has proven to be a good strategy. In case the insecurity persists, the consultants of the final evaluation will visit some accessible sites which will gather the largest number of beneficiaries.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 50 km silted channels and obstructed ponds |  | Final acceptance of the Kondori and Youmna channels |  | The work on the 2 channels has been definitively accepted. The final payment, was made in November 2020. These 2 channels irrigate by gravity about 200 ha of rice plains. | Satisfactory (S)
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiples users including climate resilient water management systems |  | Consolidation of the Engré micro-dams in the commune of Kendé |  | Small repairs were carried out to consolidate the work. The project supported the commune to purchase the cement and the commune mobilized qualified local labor (masons) and unskilled workers (young people from the village of Engré). | Highly Satisfactory (HS)
|  |  | Final acceptance of the summary water supply systems (AES) of Gomitogo, Mougui-Dembely, Dantiandé, Kel Antessar II and Hanzagoungou. |  | These 5 AESs have been accepted and are functional. The 5% guarantee has been paid to the companies. | Satisfactory (S)
|  |  | Support to the municipality of Alafia for the acquisition of 2 floating cages on behalf of 2 women's associations of 47 members. |  | 2 floating fish cages with a capacity of 20,000 fry were granted to the women's associations "DINE THIERE" and "FABA THIERE" of 47 members in August 2020. The first production cycle will last 6 months. | Satisfactory (S)
|  |  | Completion of development work on the Toupéré pond |  | The work on the Toupéré pond is 100% completed as well as the reforestation of the banks with eucalyptus. The pond has been accepted and the payment of the 5% guarantee for the company is in progress. This pond, in addition to its agro-pastoral vocation, plays an important role in the ecosystem of the Toupéré forest. | Highly Satisfactory (HS)
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities |  | Final acceptance of the market gardening perimeters of Toya, Goundam, Arham, Togor-saré and Sossobé and completion of the development of the market gardening perimeters of Guinédia and Irebane). |  | 5 market gardening perimeters are in place and the payment of the 5% guarantee for the company is made. In spite of the growing insecurity in the circle of Koro, the work on the market gardening perimeters of Guinédia and Irebane has been completed and accepted. | Highly Satisfactory (HS)
|  |  | Granting of 79.9 kg of improved seeds for gardening to 1,305 women in 10 market gardening perimeters in Mopti for the 2020-2021 season. |  | Granting of 79.9 kg of improved seeds (onion, tomato, carrot, potato, apple, beet, lettuce and okra) for 1,318 women | Highly Satisfactory (HS)
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change |  | Assessment of the monitoring of the dynamics of Assisted Natural Regeneration (ANR) in the communes of Bamba, Kendé and Dangol-Boré. |  | An improvement of the ANR in the commune of Bamba and Dangol-Boré and a regression in the commune of Kendé are observed. The lessons of this exercise will be used by the different communes in the 3 agro-ecological zones as a means of sensitizing farmers to develop agroforestry. It remains one of the alternatives to constitute carbon sinks in the fields and to contribute to climate change adaptation and mitigation. | Highly Satisfactory (HS)
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities |  | Closure of the market gardening campaigns in Mopi and Timbuktu |  | In Timbuktu, with the technical support of the NGO ADIL and under the supervision of the Regional Directorate of Agriculture, the campaign report of 3 market gardening perimeters are available. A total of 386.6 tons of vegetables were produced. Part of these products are intended for household consumption and the other part for sale. At the level of each committee, there is a fund which is fed by a contribution from the farmers at the end of the campaign. For example, in Arham, the fund contained 131,000 CFA francs in October 2019 at the time of the NGO ADIL Timbuktu's balance sheet. The Mopti assessment is also available in the DRA-Mopti supervision report. | Satisfactory (S)
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) |  | Multiplication of the 16 CESDP |  | 64 copies of the PDESC were produced and delivered to the 16 municipalities concerned and to the AEDD. | Satisfactory (S)
|  |  | Revision of 4 Mopti communal PDESC by integrating adaptation options |  | 3 communal PDESCs are revised by integrating climate change adaptation actions. A total of 85 people (50 elected officials and 35 farmers), including 17 women, participated in the revision process of the PDESC in the communes of Bamba, Dangol-Boré and Gandamia. Due to insecurity, the PDESC of Togoro-Kotia could not be revised. | Marginaly Satisfactory (MS)
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) |  | Establishment and capacity building of local investment management committees in Mopti and Timbuktu |  | The capacities of 30 management committees (21 in Timbuktu and 9 in Mopti) were strengthened in maintenance and investment management techniques. To date, all the committees are functional (holding meetings, cash in place, good relations with the town hall). These committees are now responsible for maintaining the project's investments in collaboration with the municipal authorities. | Marginally satisfactory (MS)
|  |  | Broadcasting of the 26-minute film on the project's achievements in Mopti and Timbuktu. |  | The film was broadcast by ORTM in 2 sessions in October 2020 on the national TV. | Unsatisfactory (US)
| Project Management Costs |  | Operation of the national office with a staff of 4 agents including 2 drivers |  | The national office operates with a staff of 4 agents including 2 drivers. | Satisfactory (S)
|  |  | Organization of a joint mission to monitor the project's achievements in Mopti. |  | Mission carried out from 12 to 22 March 2020 by the agents of AEED and PACV-MT and which involved the Regional Directorates of Technical Services (DRA, DRGR and DRH) of the Region of Mopti. | Satisfactory (S)
|  |  | Final evaluation of the project |  | The final evaluation took place from October 19 to November 27, 2020. | satisfactory (US)
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Balougo TELLY
| Email: | balougotelly@yahoo.fr
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
At the end of the project, in September 2020, the final evaluation of the project and other closure activities, could not yet be carried out because of COVID-19. In addition, security issues also prevented the revision of the PDESC for the commune of Togoro-Kotia. Apart from these activities, the project was fully implemented by project closure. Considering that project activities were implemented on track (accounting for the extension period) to achieve most of the project's major outcomes with only minor shortcomings, the project can be rated as satisfactory. The project contributed to increasing the resilience of vulnerable populations and their capacity to adapt to climate change through : - Improving access to and control of water for multiple activities through the construction of local water supply systems; - Strengthening the production of local livelihoods such as agriculture, fisheries, livestock and forestry: - Strengthening the capacity of local institutions and communities to better adapt to climate change. In this project my greatest satisfaction was the provision of drinking water supply to the village of Dembeli, which was facing an environmental and climatic migration. Since its creation, this village located on the Dogon plateau of the commune of Koubewel-koundia in the circle of Douentza and Mopti region has never had a reliable drinking water source, with a worsening water access situation caused by climate change and land degradation. Until the project intervened in 2018, no institution or development organization had managed to provide the village with drinking water, with 13 negative boreholes dug. As a consequence, local communities considered relocating the village and many families already had left the village. Remaining women had to walk long distances to fetch water, or men with donkey carts travelled about 8 km to bring water every day. The project, with the commitment of the communal authorities and the population, as well as the conduct of appropriate studies, was able to provide the village with a functional basic drinking water supply - including a channelling sytem. This system now provides a reliable access to basic water needs for the local populations. The commitment of local communities and authorities will ensure the sustainability of the infrastructure.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 50 km silted channels and obstructed ponds |  | Final acceptance of the Kondori and Youmna channels |  | Approximately 200 ha of rice plots in the communes of Kondi and Arham in the Timbuktu region have been secured to improve agricultural production. | Highly Satisfactory (HS)
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiples users including climate resilient water management systems |  | Consolidation of the Engré micro-dams in the commune of Kendé |  | All the water access installations have been fully executed. Some project investments were also consolidated as requested by the steering committee. | Satisfactory (S)
Final acceptance of the summary water supply systems (AES) of Gomitogo, Mougui-Dembely, Dantiandé, Kel Antessar II and Hanzagoungou.
Completion of development work on the Toupéré pond
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities |  | Granting of 79.9 kg of improved seeds for gardening to 1,305 women in 10 market gardening perimeters in Mopti for the 2020-2021 season. |  | Agricultural production in the face of climate change has been improved with the provision of 5,800 kg of improved seeds to 333 farmers. All the market gardening schemes undertaken were 100% implemented and this effectively strengthened the capacities of more than 11,563 women to farm 28.3 ha in order to increase their income and improve family nutrition. | Satisfactory (S)
Final acceptance of the market gardening perimeters of Toya, Goundam, Arham, Togor-saré and Sossobé and completion of the development of the market gardening perimeters of Guinédia and Irebane).
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change |  | Assessment of the monitoring of the dynamics of Assisted Natural Regeneration (ANR) in the communes of Bamba, Kendé and Dangol-Boré. |  | Assisted natural regeneration is the essential basis of farmer agroforestry. It constitutes a system of agricultural production and especially of soil protection and conservation. Trees that grow naturally in agricultural fields are more resilient to climate stress than those that are transplanted. This exercise has allowed farmers and communal authorities to better understand the challenges of this practice in the face of climate changes and the evolution of woody cover in agricultural fields. These field trees compensate for the reduction in forest woodland that is common throughout the Sahel. | Satisfactory (S)
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities |  | Closure of the market gardening campaigns in Mopi and Timbuktu |  | Women have been provided with improved seeds for the 2020-2021 season which starts in September in some localities. The campaign assessment was carried out for 9 market gardening areas in Timbuktu that had benefited from the technical support and guidance of the NGO ADIL under the supervision of the Regional Directorates of Agriculture in Mopti and Timbuktu. | Satisfactory(S)
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) |  | Multiplication of the 16 CESDP |  | The capacities of elected officials and farmers in the communes of Bamba, Gandamia and Dangol-Boré were strengthened to integrate risk management into communal plans. On the other hand, the capacities of elected officials and farmers in the Togor-kotia commune could not be strengthened because of insecurity. | Marginaly Satisfactory
Revision of 4 Mopti communal PDESC by integrating adaptation options
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) |  | Broadcasting of the 26-minute film on the project's achievements in Mopti and Timbuktu. |  | The film on the achievements of the project was broadcasted in 2 sessions by ORTM | Satisfactory(S)
Establishment and capacity building of local investment management committees in Mopti and Timbuktu
| Project Management Costs |  | Operation of the national office with a staff of 4 agents including 2 drivers |  | The joint monitoring mission took place, as planned, from March 12th to 28th 2020. The final evaluation was delayed and took place from October 19th to November 27th, 2020. | satisfactory
Organization of a joint mission to monitor the project's achievements in Mopti.
Final evaluation of the project
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | United Nations Development Programme (UNDP)
Oumar TAMBOURA
| Email: | oumar.tamboura@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project can be rated Satisfactory considering that: All the water access investments under output 1.2 have been completed, accepted and officially handed over to the beneficiaries. At project closure, 17 market gardening areas were developped and 2 existing market gardening areas were supported (i.e. a total of 19 market gardening areas are functional and managed by women under output 2.1), which also supports the capacity building of women, as planned under output 2.3. Under output 3.2, the management committees for all project investments are strengthened and functional despite the insecurity. The number of revised PDESC (output 3.1) is acceptable (95% of revised PDESC) but there is still 1 PDESC to be revised. The film on the achievements of the project was broadcasted in 2 sessions by ORTM. The project achieved the expected results that contribute to the UNDCF/CPD outcomes and national climate change plans, policies and strategies. The communal authorities and the MEADD, which ensures supervision through the AEDD, consider the PACV-MT as one of the best projects which achievements, in terms of adaptation of vulnerable groups to climate change, are to be replicated in several communes in similar regions. Despite the insecurity in all its areas of intervention and throughout its duration, the project has achieved most tangible results in the field across the entire UNDP Environment cluster, and meets the aspirations of the populations who are also committed to consolidating them. All stakeholders appreciate the project and have expressed desire for its scaling-up. The upcoming LDCF project, under formulation, will build on the lessons learned from the project (as observed during the independent Terminal Evaluation) and replicate best practices in the targeted region of Mopti. This will include the strong engagement of local authorities, the contracting of local experts and companies, etc.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 50 km silted channels and obstructed ponds |  | Final acceptance of the Kondori and Youmna channels |  | These over-embanked channels, equipped with regulating gates, will help secure the rice plains of Kondi and Arham against flooding and facilitate gravity-fed irrigation of about 200 ha. This will also improve rice production to contribute to the food self-sufficiency of the populations. | Higtly Satisfactory (HS)
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiples users including climate resilient water management systems |  | Consolidation of the Engré micro-dams in the commune of Kendé |  | On the recommendation of the steering committee, some investments, notably the micro-barrage of Engré, the drilling of nurseries and the water supply of Djera, were consolidated by small repairs. Nowadays, the project has fully executed the investment works and the payments are all made. | Satisfactory (S)
Final acceptance of the summary water supply systems (AES) of Gomitogo, Mougui-Dembely, Dantiandé, Kel Antessar II and Hanzagoungou.
Completion of development work on the Toupéré pond
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities |  | Granting of 79.9 kg of improved seeds for gardening to 1,305 women in 10 market gardening perimeters in Mopti for the 2020-2021 season. |  | The project has 19 market gardening perimeters, all functional and entirely managed by the women's associations of Mopti in Timbuktu. The exploitation of the 28.3 ha of market gardening perimeters will be effective thanks to the provision of improved seeds for the 2020-2021 season that the project initiated before its closure in 2020. It is a good initiative of the project to anticipate the preparation of the market gardening season which starts in September which is also the month of closure of the project. | Higtly Satisfactory (HS)
Final acceptance of the market gardening perimeters of Toya, Goundam, Arham, Togor-saré and Sossobé and completion of the development of the market gardening perimeters of Guinédia and Irebane).
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change |  | Assessment of the monitoring of the dynamics of Assisted Natural Regeneration (ANR) in the communes of Bamba, Kendé and Dangol-Boré. |  | During the three years, an improvement was noted in the natural regeneration park in agricultural fields in the communes of Bamba in the Seno and Dangol-Boré in the flood zone. On the other hand, at the level of Kendé on the Dogon Plateau, a regression was observed that does not favor the dynamics of the agroforestry park. At a time when natural forests are disappearing, the technique of RNA is the only way to reconstitute trees outside the forest. | Higtly Satisfactory (HS)
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities |  | Closure of the market gardening campaigns in Mopi and Timbuktu |  | In Mopti and Timbuktu, the Regional Directorates of Agriculture were strongly involved in the 2019-2020 campaign and provided technical advice to women farmers, especially in the cultivation of improved seeds. More than 300 tons of vegetables were produced for a turnover of more than 50 million CFA francs, therefore improving household nutrition and women's income. | Higtly Satisfactory (HS)
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) |  | Multiplication of the 16 CESDP |  | The revision process of the PDESC was completed in 19 communes out of a total of 20 communes, i.e. 95% of the project target was achieved. Because of the growing insecurity in the center, the PDESC of Togoro-Kotia could not be carried out. | Satisfactory (S)
Revision of 4 Mopti communal PDESC by integrating adaptation options
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) |  | Broadcasting of the 26-minute film on the project's achievements in Mopti and Timbuktu. |  | The film is of good quality. The administrative and communal authorities as well as the beneficiaries have all appreciated the achievements of the project despite the insecurity. The health situation did not allow its diffusion. It will be broadcasted before the final closure of the project. | Unsatisfactory (U)
| Project Management Costs |  | Operation of the national office with a staff of 4 agents including 2 drivers |  | The joint supervision mission of the project realizations took place in the Mopti region. From the mission's observation, the achievements are of good quality, the management committees are set up and their capacity strengthened. | Satisfactory (S)
Organization of a joint mission to monitor the project's achievements in Mopti.
Final evaluation of the project
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Environment and Sustainable Development Agency (AEDD)
Boureima CAMARA
| Email: | bouricamara@gmail.com, Tel: +22366805756
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Despite the insecurity in the entire intervention area, the project was able to develop intervention strategies to achieve its objectives. The recommendations of the national steering committee were instrumental in planning and guiding the project from 2016 to 2020. This team would have been able to do even better had it not been for the insecurity that affected the assumptions of success. The project, after 3 years of initial duration and 18 months of extension, is in its closing phase. However, some major activities including the payment of all commitments and the final evaluation must be completed by its final closure.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Indicators towards Outcome 1 | % increase in functional waterways and channels in the targeted communes | Only about 15% of the waterways and channels are functional or 25 in total | 5 channels (Dialamba, Dialal, Bintagoungou-Essakane, Goundam-TV and Bintagoungou-Issabery in the faguibine sytem) and 3 waterways (water supply waterways of the Boré, Kondori and Youmna pond) are functional; A total of 33 chanels and waterways are now functional, taking into consideration the baseline, reaching 80% of achievement (8 additional channels out of the 10 planned). | Functional waterways and channels increased by about 40 % or 35 in total
| Km increase of cleared water channel | Currently about 50 km of the water channels are cleared | 43.125 km of canals are unblocked by the project, of which 2.9 km irrigate 150 ha of rice fields in the commune of Togoro-Kotia, 12 km supply a chain of ponds including Boré pond and secure certain riverside villages against flooding. 22.025 km feed a series of ponds and lakes in the Faguibine system. 2.4 km from the Kondori channel and 3.8 km from Youmna respectively in the commune of Kondi and Arham protect around 200 ha of rice plains against flooding. A total 93,125 km of unlocked canals are cleared, taking into consideration the baseline, reaching 86.25% of achievement (43.125km out of the additional 50km planned). | 100 km increase of cleared water channel
Indicators towards Outcome 2 | Nombre de périmètres maraîchers aménagés d’au moins 0,5 Ha chacun et gérés par les femmes. | There are presently few market gardens and no community fish farms. | 19 market gardening perimeters (Obè, Saourakom, Adia, Gomitogo, Kande, Déguéré, Dialloubé, Goungoumé, Bougouberi, Bangadria, Toya, Goundam, Arham, Togoro-Sarré, Feindoukaina, Sossobè, Irebane, Guinedia et Issafaye Douekiré), covering at least 30,3 ha, were introduced. This output has been completed at around 95% (19 perimeters out of the 20 planned). | 20 market gardening perimeters of at least 10ha
| Nombre de fermes de poissons aménagées et gérées par la communauté. | There are presently no community fish farms. | 16 fish farms (including 5 fish ponds in the municipalities of Tindirma on behalf of the association ISSABOIREY, 7 fish ponds in Koirabery, Orobane, Pelou , Tabaco, Kondori, Adia and Touperé) were installed and are functional and 4 fish cages are functional. This output has been completed at 80% (16 community fish farms out of the 20 planned). | 6
| Nombre de pépinières communales d’espèces locales foncionnelles. | Few communities benefit from community managed tree nurseries | 15 nurseries including 8 community nurseries in the Mopti region and 7 individual nurseries in the Timbuktu Region have been set up. A total of 231 people, including 176 in Mopti and 55 in Timbuktu, are trained in plant production techniques and equipped with small equipment (pots and watering cans) to encourage community reforestation activities.The final target was achieved (15 nurseries out of the 15 planned). | At least fifteen (15) communal nurseries.
Indicators towards Outcome 3 | Number of local official trained in institutional management of climate change | No local councilors trained to enhance their institutional capacity to adapt to climate change | 274 elected representatives (including 38 women), 40 people from civil society (of which 20 women) and 101 state technical agents are trained on the management of climate change, a total of 415 people, including 58 women. The final target was largely exceeded (274 elected representatives out of the 100 planned). | 100 local councilors and 40 civil society people including 40 women are trained
| Number of PDESC revised in including climate change management | Just about 6 PDESC currently include climate change management | 19 PDESC (communes of Pondori, Pelou, Bamba, Dangol-Boré, Gandamia, Kendé, Koubewel-Koundia, Tédié, Alafia, Goundam, Kondi, Arham, Binga, Tindirma, Essakane, Bintagoungou, Gargando, Hanzakoma and Haribomo) have been revised by integrating CC adaptation concerns. A total of 475 farmers, 126 of whom were women, were trained to better take into account climate change adaptation in the planning and budgeting of development actions. This output has been completed at 95% (19 PDESC out of 20 planned). | 20 local community plans will be developed to include climate change management

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | (i) Faire-faire using local expertise is an effective way to advance the implementation of project activities, especially in times of conflict. (ii) The strong involvement of the communal authorities, especially the Mayors, has given more visibility to the project because all the actions carried out are included in the PDESC. (iii) Clearly define the procurement modalities during the inception workshop, prior to the implementation of project activities.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Insecurity in the commune delayed the completion of market gardening perimeters in Guinédia and Irebane. Following the recommendation of the project team, the company used local masons and village labor to complete the work (digging and installation of 4 wells, fencing of the voltaic fields, fixing the pulleys and repairing the perimeter fence of Irebane).
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | There is no change in the project design except that, due to COVID-19 restrictions, the final evaluation was delayed.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | In addition to the 19 market gardening perimeters of 30.3 ha that are exclusively managed by women, during the last reporting period, the project provided floating cages to 2 women's associations. This action is underway in the commune of Alafia in Timbuktu. The 2 associations total 47 women. It is a tested experience in the management of floating cages by women. In addition, about 386.8 tons of market gardening production were recorded during the 2019-2020 campaign. A part of these products were intended for household consumption and the other part sold to meet the needs of women. The management committees are trained in management techniques and some funds, financed by contributions from women farmers, were created.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The provision of improved seeds to farmers and the strengthening of their capacities on the technical itineraries of these seeds has been very relevant in terms of adaptation to climate change. With the introduction of improved varieties, production almost tripled (5,100 tons of cereals produced annually with the distribution of improved seeds against a baseline of 1,726 tons with local varieties). However, during consultations with farmers at the start of the project, they mentioned they did not appreciate some improved varieties introduced by past partners, such as improved varieties of pearl millet, which taste is less preferred than local variety. Although improved varieties of pearl millet offer shorter cycles and are more resistant to striga (disease) and drought than the local variety, farmers do not want to introduce the improved variety of pearl millet and risk to lose the local variety of pearl millet. Thus, the project used this lesson and provided the farmers only with improved varieties of sorghum (commonly called big millet), maize and cowpea.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Assisted natural regeneration (ANR) to develop agroforestry adapted to climate change is an experiment tested by the project and can be replicated to build carbon sinks in agricultural fields. With the dramatic regression of natural forests and the increasing difficulties of maintenance and watering of plantations by farmers, the adoption of adapted agroforestry on a large scale offers an effective solution for climate change mitigation and adaptation. This can be an entire project to contribute to CDN-Mali
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | The strong involvement of the beneficiaries through the communal authorities gave more visibility to the project's actions. By signing the contracts, the Mayors commit their responsibility in monitoring the implementation of the activities with the beneficiaries. The projects have a short duration and going into the long proedure of state procurement is a major constraint.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | For a better adaptation to climate change of farmers whose survival depends on agricultural production, it is essential to think about a strategy/policy that facilitates the procurement of improved seed varieties. The government, with the support of its partners, should set up a fund to support farmers to access improved seeds. Thus, each season, a subsidy will be provided to agricultural research stations to produce the quality and sufficient quantity of seeds. These seeds will be granted to farmers at a reasonable price according to their purchasing power. Today, farmers have difficult access to seeds because of (i) the non-availability of seeds in remote areas and (ii) the high price of seeds. It will be necessary to set up a marketing unit for improved seeds in each commune under the control of the agents of the agricultural services and the town hall.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | With insecurity, the communes in northern and central Mali are more vulnerable. All the actions carried out by the project are relevant for their adaptation and sustainable revenue generation in such a challenging context. These interventions are pilot measures for climate change adaptation and all the stakeholders agree on their relevance and wish to see a national program with similar projects implemented in each region.
What measures are/have been put in place to ensure sustainability of the project/program results? | The involvement and quality of (i) beneficiaries involvement through local committees, (ii) communal authorities through the the revision of the PDESCs and, especially, (iii) the state technical services during the implementation of the project are expected to ensure the sustainability of the project results.
What measures are being/could have been put in place to improve project/program results? | At the beginning of the project, we should have used the communal contracting authority to give greater responsibility to elected officials and beneficiaries, as well as to recruit local companies for the work in order to complete the construction sites on time. Indeed, under the national procurement procedure, the project had to cancel the contracts of some companies from Bamako due to significant delays in execution.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | In addition to the agro-climatic information provided by Mali-Meteo, the project uses information on security in the communes for the programming of actions. The Mayors regularly report this information to the project level and it is verified at the level of MINUSMA. The project has also made extensive use of the Faguibine System's experiments in channel overburrowing based on labour-intensive work (HIMO).
If learning objectives have been established, have they been met? Please describe. | The results of the three years of monitoring the dynamics of natural regeneration have been returned in five communes to nearly 100 pilot farmers. The results show that the number of young shoots is regressing in the commune of Kendé on the Dogon Plateau and is increasing in the communes of Bamba and Dango-L-Boré in the Seno and the flood zone respectively. The communal authorities, notably those of Kendé, have committed to broadly sensitize the farmers to ensure that the trees are replaced in the agricultural fields. This experience was a school for the farmers during the 3 years.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | None
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | 85 people including 17 women participated in the revision of the PDESCs of 3 communes. They have a good knowledge of climate change and now know how to differentiate adaptation and socio-economic actions.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 81072 (PIMS 4789)
Implementing Entity | PNUD
Type of implementing entity | MIE
Country | Mali
Region | Africa
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion Performance de la cible à l'achèvement |  |  |  | Performance at mid-term |  |  |  | Performance at completion Performance à l'achèvement
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total | 213758 | 140000 | 73758 | Total | 337675 | 214265 | 123410 | Total | 413659 | 290249 | 123410
|  | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries | 51% | 51% | 51%
|  | % of Youth beneficiaries | 49% | 49% | 49% | % of Youth beneficiaries | 49% | 49% | 49% | % of Youth beneficiaries | 49% | 49% | 49% | % of Youth beneficiaries | 49% | 49% | 49%
0
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats. | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis. | Number of targeted stakeholders. |  | Hazards information generated and disseminated. | Overall effectiveness. | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 4: Effective | Total | 0 |  |  | Total | 0 |  |  | Total | 0 | Drought | 4: Effective
|  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted | 0% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated. | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments. | No. of projects/programmes that conduct and update risk and vulnerability assessments. | Sector | Scale. | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems. | Core Indicator 1.2: No. of Early Warning Systems. Nbre système d'alerte precoce | No. of adopted Early Warning Systems | Category targeted | Hazard. |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  |  | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses. | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased. | Number of staff targeted. |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events. | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events. | Total staff trained. | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 10% | Private |  | 400 | 5% | Private |  | 415 | 47.95% | Private |  | 415 | 62.89% | Private
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks. | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Disaster risk reduction | 1: No capacity | Public | Local | Disaster risk reduction | 4: High capacity | Public | Local | Disaster risk reduction | 3: Medium capacity | Public | Local | Disaster risk reduction | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes. | Indicator 3.1: Increase in application of appropriate adaptation responses. | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Disaster risk reduction |  | 30% |  | Disaster risk reduction |  | 25% |  | Disaster risk reduction |  | 34% |  | Disaster risk reduction
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities. | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate . | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0% | 0% | 1: Aware of neither |  | 3000 | 50% | 4: Mostly aware |  | 4210 | 47.7% | 4: Mostly aware |  | 4440 | 48.83% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets. | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate. | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Multi-sector | Local | 2: Partially responsive (Lacks most elements) |  | Multi-sector | Local | 4: Mostly responsive (Most defined elements) |  | Multi-sector | Local | 3: Moderately responsive (Some defined elements) |  | Multi-sector | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened. | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Agriculture | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved |  | Agriculture | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability. | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change. | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 58 | Community |  | Water management | 145 | Community |  | Water management | 146 | Community |  | Water management | 158 | Community |  | Water management
|  | 20 | Community |  | Agriculture | 40 | Community |  | Agriculture | 36 | Community |  | Agriculture | 42 | Community |  | Agriculture
|  | 6 | Community |  | Food security | 11 | Community |  | Food security | 9 | Community |  | Food security | 11 | Community |  | Food security
|  | 67 | Community |  | Multi-sector | 97 | Community |  | Multi-sector | 101 | Community |  | Multi-sector | 101 | Community |  | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress. | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated. | Natural asset or Ecosystem (type). | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets. | No. of targeted households. | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 2: Limited improvement |  | 3000 | 0% | 3: Moderate improvement |  | 20827 | 30% | 3: Moderate improvement |  | 23507 | 34% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods . | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies. | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income. | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agriculture |  |  | 2000 | Agriculture |  |  | 5271 | Agriculture |  |  | 6341 |  | Agriculture
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agribusiness |  |  | 500 | Agribusiness |  |  | 2933 | Agribusiness |  |  | 4283 |  | Agribusiness
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Forestry |  |  | 300 | Forestry |  |  | 11683 | Forestry |  |  | 11683 |  | Forestry
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Fishing |  |  | 200 | Fishing |  |  | 940 | Fishing |  |  | 1200 |  | Fishing
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy. | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 5: All (Fully integrated) |  |  |  | 5: All (Fully integrated) |  |  |  | 5: All (Fully integrated) |  |  |  | 5: All (Fully integrated)
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks. | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 2 | Disaster risk reduction | National | Environmental policy | 3 | Disaster risk reduction | National |  | 2 | Disaster risk reduction | National |  | 2 | Disaster risk reduction | National
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced. | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 22 | 2: Partially not enforced (Most elements not implemented) |  | 1: Ineffective | 22 | 4: Enforced (Most elements implemented) |  | 3: Moderately effective | 18 | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective | 21 | 4: Enforced (Most elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.