## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 30 June 2020 - 30 June 2021
| Project Title: | Promoting Climate Resilience in the Cocoa Rice Sectors as an Adaptation Strategy in Sierra Leone
| Project Summary: | The project proposes the implementation of a set of concrete adaptation options into targeted and profitable agricultural sector (rice and cocoa). A set of enabling actions designed to strengthen national capacities and institutions is interlinked to the concrete adaptation measures which will lead to building the resilience of the cocoa and rice value chains in the most vulnerable areas to climate change in Sierra Leone. Concrete adaptation measures are direct application of integrated climate resilient production, post-harvest and marketing systems. New technologies and best knowledge aim at promoting the paradigm shift and behavioural change in the rice and cocoa production and linkages to markets. To project is structured around three components: Component 1: Climate-proofed agricultural production and post-harvest combined with livelihood diversification; Component 2: Climate resilient rural infrastructures; and Component 3: Institutional capacity building and policy engagement Each component is described in more details below. Component 1: Climate-proofed agricultural production and post-harvest combined with livelihood diversification. This component focuses on household-/village-level interventions in climate resilient and sustainable agriculture in order to reduce the negative impacts from climate change and climate variability, as well as to contribute to agricultural and rural livelihood development through income diversification. Along the agricultural value chain, key vulnerability issues which call for adaptation practices are the low productivity and high vulnerability of the agricultural sector mainly cocoa and rice highly dependent on rainwater, which is the sole water source for a large majority of small farms; the increased recurrence of extreme weather events such as floods, droughts and climate-induced vegetable diseases, which reduce productivity levels; and changes and variations in climate conditions from one year to another. With regards to post harvesting in the cocoa sector, the lack of adequate equipment for drying and processing to maintain a high-quality product of outputs is still a challenge to stabilize and increase farmers’ income in the face of climate change. To support the shift towards climate-resilient production and post-harvest systems combined with livelihood diversification in the targeted areas, the project will focus on the following outputs and activities Output 1.1: Adaptation measures to foster the resilience of cocoa and rice production and post- harvest are implemented Cocoa value Chain: Establishment of cocoa clonal garden at SLARI to facilitate the introduction of drought- and temperature-resistant cocoa seedlings; including resistance to emerging pests and extreme events. Best reforestation and agro-forestry techniques Support to cocoa clonal garden operation. This activity will ensure the long-term functioning of the clonal garden and will also support the establishment of a sustainable business model; Development of cocoa farms, which include resilient practices such as vulnerability-informed land use, tree shading and agroforestry. Climate weather information's to local cocoa producers specifically for droughts, floods and humidity Improvement on crop modelling and assessment of climate vulnerability Use of modern technologies with a particular focus on solar based pumping systems, solar based post-harvest and processing and equipment to attract more youth in agriculture . Under this output, the project will engage with national and Western African expertise on cocoa production, the national expertise of the Sierra Leone Agricultural Research Institute (SLARI) at the Kenema Crop Resource Centre (KFTCRC), and at the regional level, the Ghana Cocoa Board (Cocobod) and the Cocoa Research Institute of Ghana (CRIG). Rice value Chain: Selection of pest resistant varieties and cultural practices (distance between plants, irrigation management, and weeding Support to MAF to run Farmer Field School and provide other technical support. The FFS will showcase specific approaches to facilitate the introduction and uptake of resilient practices for farmers in the cocoa and rice sectors. Bore holes irrigation schemes, to cope with the consequences of drought and heat extreme events, bore holes will be rehabilitated and irrigation schemes will be deployed. The increasing needs for irrigation induced by future climate change will be integrated in the design of the schemes. Development of new Inland Valley Swamps for rice production to increase the production of smallholder farmers and diversify and expand their revenue sources. Watershed rehabilitation, water efficiency and management, Training and extension and infrastructure rehabilitation and construction including drainage systems , Water quality assessment, toilets, sanitation Output 1.2. Income-generating activities (fish farming and gardening) are promoted as livelihood diversification measures 47. The Midterm review of the GEF project recommended using the earth dam reservoirs to develop fish farming activities as alternative adaptation measures. The contribution of fish farming to food and nutrition security in Sierra Leone has been underplayed due to its low priority in the food production systems, however FAO reports that it contributes significantly to national protein intake4 . As a source of irrigation water, pond water is also richer in nutrients than well water as it contains nitrogen-fixing algae, which improve soil fertility . With regard to this output, the actions to be taken include: Construction of 30 earth dams for fish farming activities. Establishment of fish farms, including the creation of value-chain services (fingerling, etc.). Establishment of 100 Community model of integrated vegetable garden of at least 4-5 ha (solar pumps, compost systems, day care facility for women, agro forestry and rotation of crops; transport systems). As a new activity still under development in the country, technical services for the stocking and management of the earth dams and fish farming activities will be provisioned throughout the project. Trained personal will be trained and placed in support to MAFFS regional extensions (depending on the number of communities practising fish farming). The targets are the Farmer-based organizations and directly the smallholder farmers engaging in fish farming. With fingerling production centres in Bo and Makali, the project will work in collaboration with MAFFS, FAO and the Ministry of Fisheries and Marine Resources. Service providers, MAFFS and FAO will support to train farmers through the FFS in fish farming In addition to fish farming, the project will support the establishment of integrated resilient kitchen and community gardens powered by solar applied on integrated resilient farming systems with alternance of climate resilient crops, with high nutritional values. Component 2: Climate resilient rural infrastructure Output 2.1 – Rural transportation and storage infrastructure have been rehabilitated and upgraded to withstand weather extremes . Fostering productivity and production is not sufficient to ensure that smallholder farmers sustain and increase their revenues. Poor road and transportation infrastructure lead to a depreciation of the quality of the production and hence its value on the market therefore smallholders' revenues. The already observed and projected intensification of extreme weather events could lead to more value chain disruptions, affecting the capacity of smallholders to gain sufficient incomes from their production. As a consequence, two key actions will be undertaken by the project: (1) improving the usability of road infrastructure all-year round and for all-weather conditions; (2) in the same areas rehabilitating existing warehouses to withstand wetter climatic conditions will also support the development of the cocoa and rice value chains. With regards to infrastructure, based on the lessons learned exercise from the RCPRP+, road construction has previously overlooked the construction of culverts that enable IVS drainage, resulting in water-logged fields during the rainy season. Depending on the ESIA outcome, this project will help finance culverts that will allow for natural drainage, and it will also support the EPA in its supervision functions. Should the allocated budget permit, the project will support the reinforcing of bridges against increased peak fluvial discharges resulting from increased deforestation, increased surface water runoff and increased rainfall intensity. Activities under this output are: Warehouse rehabilitation to withstand wetter climatic conditions. With an increasing recurrence of extreme wet events, it is essential to ensure that existing warehouses (1) preserve low humidity level to preserve the produce and (2) are rehabilitated outside floodable areas and are not exposed to extreme flood events that could adversely affect the stored produce. Climate-proofing 120 feeder roads and farm tracks to ensure the year-round and all-weather usability. This includes the studies and surveys, the works, the construction of bridges and culverts where necessary, routine and periodic maintenance. To sustain the climate-proofed investment over a longer period of time, activities aiming at their maintenance by local public authorities and Farmer-based organizations will also include: (1) Support to districts for development of Feeder Roads Maintenance Plans and (2) Support to Farmer-based Organizations (Road gangs formation, distribution of maintenance tools, development of Farm Tracks Maintenance Plans) Output 2.2 – Potable water supply increased and sanitation infrastructure built accounting for current and future climate risks . Agricultural and domestic water management in Sierra Leone is becoming more complex due to climate change. Key barriers to agriculture production involve drought (acute and seasonal) and flooding of villages and swamp rice and cocoa fields due to intense periods of rain. In the targeted areas, availability of water, in both quantity and quality, is being severely affected by climate variability and climate change. Constraints identified at the local level include lack of water infrastructure both for agriculture and human consumption. The low productivity in agriculture and livestock is linked to water availability. Addressing the risks of current and future climate change to water supply and agricultural productivity is therefore critical in enhancing resilience. Frequent drought or erratic rainfall results in crop damage, loss of livestock and pastures, water shortage (for humans and livestock), malnutrition (due to lack of food), and migration of households and wild animals. The unsustainable management of water resources is the major factors aggravating the impacts of climate change in the targeted areas. Crop pests and water-borne diseases are common, often caused by poor farm management and the absence of water and sanitation infrastructures. Therefore, the following expected outputs are expected to improve the baseline scenario 56. Based on the lessons learned from the IACCAFPS IFAD/GEF pilot, control and management under climatic stresses remain a big challenge. Activities under this output will improve and upscale water harvesting small earth dams infrastructure with up to 40 new dams (from 4 under GEF) for perennial rice and vegetables in seasonal and climate vulnerable IVSs. The project will also tender a contract for a capable NGO or institution to carryout water quality testing as part of the site selection process to ensure the water is suitable for agriculture. As poor sanitation leads to water borne diseases, which are responsible for all deaths of the labour force, the project will also built latrines in the villages. Activities include: Climate-proofed construction and rehabilitation of drinking water supply and sanitation to withstand the consequences of extreme dry and wet events that could disrupt the quantity and quality of water available to the population and its economic activities. Capacity building for potable water management will complement the construction and rehabilitation. Component 3: Institutional capacity development and policy engagement. Output 3.1: Governmental capacities are strengthened for climate change adaptation. Enabling the implementation of the project will necessitate to further develop the capacities of the relevant government agencies in charge of climate change adaptation from the policy to the implementation levels. The component 3 therefore focuses on strengthening the capacity of key government institutions (3.1) and ensuring the adequate M&E of the project combined with the recruitment and training of the relevant staff to facilitate the implementation of adaptation to climate change activities. The original aim of this activity under the GEF/IACCPFS project, which was significantly hampered by the Ebola Virus Disease outbreak, was to develop the capacity of the Meteorological Department and the Environmental Protection Agency of Sierra Leone to facilitate the implementation of climate change adaptation. This support will consist in targeted capacity development for both institutions and the recruitment and training of key project staff to foster the quality and implementation of climate change adaptation. The activities will consist in: Strengthening of EPA's capacities and staff on climate change adaptation. This could include: Capacity building through technological enhancement, Training to enhance institutional capacity, Exchange visits for EPA staff. The detailed trainings will be decided in collaboration with the staff of the Meteorological Department at project start-up. Strengthening of the Meteorological Department, including capacity building through technology enhancement and training to enhance institutional capacity. The detailed trainings will be decided in collaboration with the staff of the Meteorological Department at project start-up. Technical Assistance for improved policy frameworks to mainstream climate risks in into sectoral strategies and policies. Output 3.2 – Monitoring and Evaluation and Coordination of the Adaptation Activities 60. This final output intends to facilitate the monitoring and evaluation of the project as well as support the project team in accessing the necessary resources to plan and implement adaptation measures. This sub-component supports the critically underfunded Meteorological Department and Environmental Protection Agency, both institutions in charge of climate change adaptation. Under this output, activities to be undertaken are: Support to the development of MRV system of climate response programmes. Support to the improved monitoring & evaluation and knowledge management activities, which will include: Additional baseline survey costs (related to climate change adaptation) and additional terminal survey costs (related to climate change adaptation). Project management and coordination, including the recruitment of Climate change adaptation specialist for the duration of the project and Staff training on adaptation-related issues. The project will leverage climate information's for cropping calendars from existing project that have supported the installation of rain gauges and automatic weather stations in the regions which are functioning.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | International Fund for Agricultural Development | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | International UN organization | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Sierra Leone | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | 15 Agriculture Districts of Sierra leone( Tonkolili, Bombali, Koinadugu, Falaba, Kailahun, Kenema, Kono, Bo, Bonthe, Moyamba, Pujehun, Port Loko, Kambia, Karene and Western Rural Area). | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2019-07-08
IE-AFB Agreement Signature Date: |  | 2019-10-24 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2020-05-06 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
| Original Completion Date: | 2025-09-30
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | 1. Inception Workshop Report dated May, 2020 (copy attached for ease of reference) | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | www.avdp.org.sl | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Abdulrahman Bob Conteh | Dominican Republic
| Email: | bconteh@avdp.org.sl or bobyconteh2019@gmail.com | Ecuador
| Date: | 27th October, 2021 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Environmental Protection Agency (EPA)-Dr Bond Ngevao | Equatoral Guinea
| Email: | bondi.gevao@epa.gov.sl; sheku.kanneh@epa.gov.sl | Eritrea
| Date: | 11th November, 2021 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | International Fund for Agricultural Development (IFAD)- Ann Turinayo | Fiji
| Email: | a.turinayo@ifad.org | Finland
| Date: | 11th November, 2021 | France
| Executing Agency |  | Gambia
| Name: | Ministry of Agriculture- Dr Abdul Karim | Georgia
| Email: | karim@bhbgmbh.com | Germany
| Date: | 11th November, 2021 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 30 June 2021 |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [30 June 2021] | 900000 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | The agreement between the AF and IFAD was signed on the 24th October 2019 and the agreement between the Implementing Entity and Executing Entity was signed on the 20th April 2020. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  |  | INVESTMENT INCOME |  |  |  |  | INVESTMENT INCOME |  |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT (US$) |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Development of Cocoa farms | 35269.78
| Recurrent Costs-Local staff salary | 3279.7
| Grand Total | 38549.48 |  |  | TOTAL | 0 |  |  |  | TOTAL | 0 |  |  |  | TOTAL | 0 |  |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST (US$) | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period |  |  | Est. Completion Date |  | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date |  | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date |  | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
AF Plan ACTIVITIES
| Development of New IVS | 376.645 | 2021-01-08
| Establishment of Cocoa Clonal Garden at SLARI (MOA) | 101.37 | 2021-02-08
| Support to Cocoa Clonal Garden Operation | 56.13 | 2021-03-08
| Development of Cocoa farms | 22.475 | 2022-02-03
| Strengthening of EPA (MOA) | 192.81 | 2022-02-02
| Strengthening of Meteorological Department (MOA) | 105.07 | 2022-03-04
| Local staff salary/Recurrent Cost: Personnel | 26.42 | 2022-01-04
| Execution Cost | 19.18 | 2022-01-01
|  | 900.1 |  |  |  |  | TOTAL | 0 |  |  |  | TOTAL | 0 |  |  |  | TOTAL | 0 |  |  |  | TOTAL | 0
[9 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[9 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[9 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[9 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Insufficient capacities to appropriately manage the day-to-day implementation of the project | Low | MAF and IFAD team have recruited qualified project management team to manage the day to day running of the project. The PMU have been trained and they are using the financial and monitoring software system call Tompro and Tom-monitoring to track expenditures as againt target and equally monitor level of achievement within schedule time as against planned activities. At the start of every year individual staff will set perfarmance target objectives which are use to do the yearly evelaution for contract renewal for the subsequent year.
The project budgeting process doesn’t respect procedures and doesn’t allow for a good implementation of project activities | Low | For every year the PMU and MAF will prepare a budget in line with activities budget schedule in AF PDR which is aligned with AVDP cost tab. These AWBP is share with theNational steering committee (NSC) for comments and approved. The approved AWBP by NSC is sent to IFAD for review and granting of no objections through Notus. Approved AWBP is later uploaded into the Tompro and Tom-montoring system. The PMU do oberve all financial management procedures or processes on momthly basis.
Project financial flows and disbursement processes are not timely and jeopardize the implementation of activities on the ground | Low | After the opening of the designated dollar account, Finance Controller will be convert it to local currency and later transfer to the operations account which is in Leones and use for day to day implementation of activities. Certified statement of expenditure translated into withdrawal application through IFAD through IFAD client potter (ICP) and approve by ministry of finance for onward submission to IFAD. The disbursement to service provider is base contract and payment clauses in the contract for the payment. Subsequent payment are made based on liquidation and certified monitoring report and payment certification. Direct payment is based on the amount of money more than $100,000 and is done by IFAD
Project implementation and financial management procedures do not guarantee sufficient transparency and accountability | Low | The project do ensure three levels of security which include-Adequate segregation of duties in the finance department-one person do the data entry and other person do the posting and finance controller (FC) does the approval.2-Component managers raised request, FC review and Project manager approves PMU conduct two audits, one is the internal done by MAF and External audits done by Audit Sierra Leone and review done by IFAD during implementation support mission and supervision mission. IFAD have in country office headed by program office and supervise by Country manager base in Ivory coast.
The project accounting system and financial procedures are not sufficiently formalized | Low | The PMU is using financial Software called Tompro to monitor the financial commitments including contract and also produces various types of financial reports and taking into account the taxes
The project financial procedures do not allow for proper and regular monitoring | Low | Withdrawal Application is done base cash forecast on the AWBP and monitoring of designated and operation accounts. Account is been monitored base on budget against disbursement. Accountants always prepare quarterly financial and accounting reports (interim financial reports) which will be submitted to the financial controller for signature and to IFAD finance team for approval
Current climate and seasonal variability and/or hazard events result in poor restoration results or agricultural yields. | Low | The SLmet has been providing real time weather information which guide the project to know the appropriate planting time, application of the best agronomic practices and the variety of crop that are drought and flood resilient. Moreover, the project team have trained farmers in adaption and mitigation issues to increased their coping strategies. The project have supported SLARI to develop hybrid cocoa that are drought resilient through the establishment of 15ha cocoa clonal seed garden
Loss of government support may result in lack of prioritisation of AF project activities | Low | The project do have quarterly review meetings with partners ( Environmental Protection Agency (EPA), Sierra Leone meteorological agency (SLmet) and Sierra Leone Agricultural Research Institute (SLARI), service providers and line ministries which include ministry of finance and ministry of agriculture to give update on achievement, challenges and come up with recommendations.
Communities may not adopt activities during or after the AF project | Low | To ensure sustainability of the project activities, the PMU is partnership with government agencies and line ministries. On this note, the project team have trained SLmet, EPA staff and ministry of agriculture technical staff including field staff and have signed MOU with the various departments of ministry of Agriculture for farmer field school facilitation. Environmental protection agency (EPA) and Sierra Leone Meteorological agency (SLmet) are directly involve in implementation of project activities. At community level, youth contractors and facilitators that local residents are trained to transfer knowledge at the farmer field school and to lead on-farm training sessions. This strategy do ensure knowledge sustainability.
Priority interventions implemented are not found to be costeffective. | Low | IFAD consultant and the project have done cost benefit analysis for return on investment for rice and cocoa to guide the project implementation and best strategies are were recommended.
Project Start up and disbursement | low | The IFAD have coordinated through the ministry of agriculture to set up the national steering committee (NSC) and recruited all the support and technical staff both at head office and field officers with well defined roles and responsibilities.All disbursement of fund strictly follow or comply with the finance act of Sierra leones, IFAD finance manual and financial reporting and withdrawal applications are done through NOTUS, Tompro and Tomonitoring software system for transparentcy and accountability.IFAD does regular finance supervision support mission on quarterly basis to keep the system on track.
Increased weather variability related to climate change | very low | The dissemination of real time agromet information to farmers about prolong dry season and rainfall intensity and distribtuion and combine with the supply and delivery of drought resilience crop variety have helped farmers to cope with increased weather variability related to climate change
Availability of appropriately experienced and qualified service providers | very low | The project management Unit (PMU) have been put in place to run the day to day management of the project and equally ensure that due deligent is done by selecting experienced and qualified service provider according to procurement manual or proceedures.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Covid-19- Delayed activities because of the restricted movement of people and closure of borders for vehicular activities | H | The Rural Poor Stimulus Fund (RPSF) was provided by IFAD for farmers to undertake quick farming activities and farmers were supplied seeds and labour saving and gender friendly farming implements.
Catchment area deforestation around IVS | Moderate | Train farmers and service providers on sustainable land development and preparation methods including zero orminimum tillage. Encourage crop intensification and discourage opening of virgin forest for cropping.
Sediment deposition from upland to low land | High | Encourage agronomic practices such as contour ploughing, terraces and bunds in erosion and landslide/mudslide prone hillslope areas. Encourage the planting of cover crops and anchor crops with the main crop.Encourage buffers along stream to prevent erosion
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Yes, the ESMP was used to implement mitigation measures including: erosion control techniques employed in the out-planted cocoa farms and IVS sites during the current reporting period. Other measures include: Zero burning, Zero tillage , Intercropping (groundnuts, rice and plantain suckers) for shade management, Cultivation of cover crops for soil fertility management and prevention of erosion, Mulching for water conservation, Non-use of agrochemicals, and clearing of vegetation at the down streame ends and also extending the drainage 50-100m outside the command to ensure effective conveyance of flood water. These measures drastically reduced the risk of erosion in the farms.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity |  |  | There is a high risk of land tenure issues, with a key role of paramount chiefs in the distribution of land. | Actively involve women and youth in all components and levels of decision-making within the project;  Strive to maintain Project beneficiaries ratio of 40% women and 20% youth (men and women under 35 years old)  Encourage the submission of business proposals from women-only groups (incl. cooperatives);  Ensure women hold at least 30-40% of leadership posts in the farmer apex | Number of women ad youth participating in AVDP (from the project register Number of people without access to land participating in AVDP Secure land access and number of land lease agreement signed with land owners Attendance register of sensitization meetings with Paramount chiefs and other stakeholders | NO. OF Vulnerable people without access to land participating in AVDP | Engage with Paramount Chiefs to secure land for intending beneficiaries with no access and make access to land by women and youth one of the preconditions for a community to participate in the AVDP. Under te elite capture the project remedial actions are to develop Stakeholder engagement plan (SEP) Stakeholder meeting reports, project flyers Complaints register Meeting records, observation, Code of conduct Community meeting Knowledge management materials Number of local CSOs in partner with AVDP | Limited participation of people as a result land tenure issues. | land policy to guarantee land tenure security for beneficiary farmers
3 – Marginalized and vulnerable Groups |  |  | No impact was identified
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | There is a low risk of social exclusion of women and youth due to limited access to land. There is also a risk of low mobilization of women hence a gender inequality in targeting beneficiaries | The project gender target is 40% femalee and 60% youths. Provision gender friendly and labour svaings equiptment for farm operations , Access to land for women and youth should be a precondition for community selection/participation  To avoid obstructionism (‘blocking behaviour’), ensure men are included (‘carried along’) in sensitization activities. Work with locallytrusted CSOs in community sensitization (working towards ‘attitudinal change | No. of female households beneficiaries. Quantity and types of gender friendly and labour svaings equiptment provieded. Provision of short duration food crops intercroped with cocoa and oil palm | The target is stated in the project design document under targeting guidelines | No of female households beneficiaries. Quantity and types of gender friendly and labour svaings equiptment provieded | Exlusion of female participation | The project have ensured full female participation and increase production in activities
Under the elite capture
7 – Indigenous peoples |  |  | No impact was identified
8 – Involuntary resettlement |  |  | Initial screening and compliance assessment is always required during implementation and even though no roads for more that 10 km will not be allocated to my site which may not lead to involuntary resettlements planned. | The PMU will ensure that project-specific ESIA is produce by contractors should be required for all feeder roads construction  Train farmers and service providers on sustainable land development and preparation methods including zero or minimum tillage.  Encourage crop intensification and discourage opening of virgin forest for cropping.Involve partners from the Ministry and research institutes in training farmers on soil conservation techniques | No of people or settlement displaced Production of projectspecific ESIA for feeder road construction  Number of farmers that received training on sustainable land preparation and management  Consummated MOUs with Research Institutes and agencies dealing with soil | no persons placed or resettled, the contractor | Though the project is not anticipating involuntary resettlement,but when limited involuntary resettlement is unavoidable, due process should be observed so that displaced persons shall be informed of their rights, consulted on their options, and offered technically, economically, and socially feasible resettlement alternatives or fair and compensation. | People that will be displaced involuntarily | the due process should be observed so that displaced persons shall be informed of their rights, consulted on their options, and offered technically, economically, and socially feasible resettlement alternatives or fair and compensation.
9 – Protection of natural habitats |  |  | Low risk of wetland (especially mangrove) degradation and removal for rice paddies and vegetable farming | The project is focus in the inland valley swamp and have discouraged removal and draining of mangroves for rice paddies and vegetable farming | Percent decline in wetland | No mongrove intervention except IVS | No conversation of mongrove or manure wetland to farm land | Percent decline in wetland | Continue sensitization of the Ramsar agreement and EPA act on wetland
10 – Conservation of biological diversity |  |  | There is a risk of biodiversity loss (in IVS) caused by bush fires and slash and burn agriculture | The measures taking by the project to prevent biodiversity loss are, to limit cultivation of rice in the mangrove ecosystem to reduce mangrove forest loss, discourage slash and burn and train farmers on sustainable land preparation and development options Avoidance of areas that infringe on known migration patterns of protected, endangered or rare species and maintain known wildlife migration corridor | Percent decline in mangrove forest  Number of farmers that received training on sustainable land preparation and management | No slash and burning in any of the IVS | The project have conducted trainning in sustainable land preparation and on climate change adaptation issues for IVS farmers | Number of farmers that received training on sustainable land preparation and management | The project will continue to follow up and do on farm train+F20:L20nning on sustainable land preparation and managemen
11 – Climate change |  |  | There is a moderate risk of GHG emissions from rice paddies | The project mitigation actions have been: discouraging opening of new virgin forests and coastal mangrove wetlands Trainining of farmers on how to drain rice paddies in mid-season to reduce CH4 emission and improvement in nutrient management including the retention of rice residues  Encouraging the use of clean energy in processing activities | Percent decline in forest and wetland areas  Number of farmers trained in sustainable rice paddies management  Number of processing units using sustainable energy | No use of primary forest | No opening of new virgin forests and coastal mangrove wetlands | Number of hectares of decline forest | No opening of new virgin forests and coastal mangrove wetlands
12 – Pollution prevention and resource efficiency |  |  | There is a risk of water pollution and waste proliferation due to the use of inorganic fertilizer and agrochemicals. | The project do minimized use of inorganic fertilizers and encourage use of biodegradable organic manures (especially in rice, maize and vegetable fields) and agrochemicals in cocoa plantations  The project have trainied youth contractors in sustainable agrochemical application as an enterprise to promote environmental-smart agricultural value chain | Number of farmers that use organic manure instead of inorganic fertilizer  Number of youth engaged in integrated agrochemicals and pesticides application enterprise | Minimal use of agro-chemical according to the application standards | Trainning of youth contractors in sustainable agrochemical application as an enterprise to promote environmental-smart agricultural value chain have been done by the project | No of farmers using the the sustainable agrochemical applications | Promote minimal use of agr-chemicals
13 – Public health |  |  | There is a moderate risk of unsafe and non-healthy working conditions, waterborne diseases and dust from road construction | Efforts to focus on inland valley swamp to protect farmers from schistosomiasis, a waterborne disease in flooded rice fields, with rice boots and medication, Encourage farmers group in the oil palm processing value chain to invest in ‘modern’ mechanical methods of extraction and processing which enhances processing, reduces drudgery and reduces cholesterol levels of palm oil for local consumption | Sensitization materials Number of farmers using rice boots and Number of oil palm processing group that are using modern methods | Focus on inland valley swamp to protect farmers from schistosomiasis, a waterborne disease in flooded rice field | Trainning of youth contractors in IVS development and rehabilitation | No of IVS youth contractors trained | Continue the development of IVS
14 – Physical and cultural heritage |  |  | There is a low risk of loss and disturbance of cultural resources such as sacred forest and archeological site | No approval projects to located in or around sacred forests and community groves and archaeological sites | Inventory of cultural | Focuses on non-forest land or primary faorest | Continue sensitization of the value cultural heritage | No of IVS/tree crop youth contractors trained | Continue sensitization on cultural heritage and sacred placed/bush
15 – Lands and soil conservation |  |  | Deforestation and upland crop production might affect soil quality and conservation, as well as flooding, water logging, soil salinization and alkalization | The project have so far done the, production of project-specific ESIA by contractors should be required for all feeder roads construction  Train farmers and service providers on sustainable land development and preparation methods including zero or minimum tillage.  Encourage crop intensification and discourage opening of virgin forest for cropping.  As much as practicable, encourage mixed cropping of target crops with cover cropsEncourage agronomic practices such as contour ploughing, terraces and bunds in erosion and landslide/mudslide prone hillslope areas  Encourage the planting of cover crops and anchor crops with the main crop  Encourage buffers along river bank to prevent erosion, | No of farmers in erosion/landslide/mudslid e prone areas adopting sound and sustainable agronomic practices, Production of projectspecific ESIA for feeder road construction  Number of farmers that received training on sustainable land preparation and management  Consummated MOUs with Research Institutes and agencies dealing with soil | The project is strictly monitoring the ESIA recommendeations for contructors. The project have also trained farmers are in sustainable land development and preparation methods including zero or minimum tillage. | Continue on farm trainning on sustainable land preparation and management. | umber of farmers that received training on sustainable land preparation and management | Continue trainning farmers and service providers on sustainable land development and preparation methods including zero or minimum tillag
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Joint monitoring on environmentalt and social complaince in the ESMP are conducted quarter and field back or findings are share with the staff, partner, beneficiaries and service providers
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | NA
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The PMU in collaboration wth Environmental Protection Agency (EPA) and Sierra Leone Meteological agency(SLMet) will jointly monitor the project activities using the ESP screening forms that are in line with the AF ESP principles from which the the project ESMP was developed to guide the implementation of AF project. The field data will be collected , collated, analysed and share findings with project stakeholders. With such engagement the team will prepared an emergencey preparedness response plan that will adequately address accidental and emergency situations related to the project that may harm people or the environment.
Have the implementation arrangements been effective during the reporting period? |  | Satisfactory
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | MOA signed with each EE with clear obligations of each EEs
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Satisfactory
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Not applicabe
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | Initially the project anticipated USP and did an assessmentor s reening but with AVDP project, the ESMP of the project is used to monitor the ESP of AF
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | Not applicable because the PMU have not established the grievance redress mechanism.
No grievances and complaints were reported during the period of implementation as a result of the participatory process engaged by the project. |  | Going forward, Not Applicable but the PMU will ensure that all parties involved should recognise the grievance mechanism as legitimate. Particularly, workers should feel that they are able to raise their grievances without fear of victimisation or negative consequences. Th PMU will take into key principles to develope the grievance machanism and these include consultation on the draft mechanism between management, staff, Service providers and beneficiaries, full briefing so everybody is made aware of the procedure, roles, and responsibilities,training, consistency in procrdure, rolling out , confidentiality and publication
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Equal benefit | Households | Number of female households headed beneficiaries that have access to project resources | 2852 | 14000 | Satisfactory (The project achieved 40% target of female headed households).
Participation | Households | Number of female household headed beneficiaries that participated in project intervention at all levels | 2852 | 14000 | Satisfactory (The project achieved 40% target of female headed households).
Access and control | Households | Number of women with access to property right and control over asset. | 2852 | 14000 | Satisfactory (The project achieved 40% target of female headed households).
Representation and Decision making | Households | 1) Number of women that covers managerial position in FFS, ABC and FBO. 2) Number of women and youth that received incentive implement climate adaptation and and mitigation measures along the value change | 10% | 30-40% | Satisfactory (The project achieved target of 15% female headed households).
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | IFAD have hired consultants that work reomtely and often conduct quarterly field technical suppervision of AF gender policy complaince through review of gender segregated gender data base, check the updated gender sensitive indicator in the logframe in relation to progress made and challenges faced, regularly review the gender monitoring tool/checklist and often engage stakeholder and project team about progress made and short falls in line with policy complaince with strong recommendation in mission report.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes. Because the gender policy compalince is rated satisfactory during IFAD suppervision mission rating report.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The PMU have gender and youth targeting team who have developed gender monitor tool/checklist with regular data ( Gender segregated) collect, collate and analyse along side with community gender champions. They do update the data base and the logframe and compare target as against progress and share their report with the project team and community through stake engagement.They team have equally put in place the gender community jounalism program with community base jounalist the effectively sensitize beneficiairie and other stakeholders on AF gender policy. third party monitoring,
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes. Because of the development and implementation of the aforementioned framework
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No. This is because the project have qualified team and have developed gender targeting strategy which is our implementation guide and GALS training done.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | No grievance recceived so far because project beneficiaries were well informed about the project targeting, selection criteria and entitlement. For unforseen grievances, the PMU will ensure that all parties involved should recognise the grievance mechanism as legitimate. Particularly, workers should feel that they are able to raise their grievances without fear of victimisation or negative consequences. Th PMU will take into key principles to develope the grievance machanism and these include consultation on the draft mechanism between management, staff, Service providers and beneficiaries, full briefing so everybody is made aware of the procedure, roles, and responsibilities,training, consistency in procrdure, rolling out , confidentiality and publication
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Component 1: Climate-proofed agricultural production and post-harvest combined with livelihood diversification |  | Outcome 1 | The project is expected to establish 6000 ha of new farms; benefitting 6,000 smallholders farmers . The projected is expected to establish 15 ha of cocoa clonal seed garden |  | IFAD gave no objection to contracts submitted bythe PMU to support the first phase of the development of 1200 ha of IVS (brushing, felling, destumping and clearing). IFAD reviewed and made lot of input into the FFS rice manual to enhance the establishment and running of 30 legacy rice Farmer Field Schools (FFS) benefiting 929 smallholder Inland Valley Swamp (IVS) rice farmers (Female 476 Male 453 Youth…) in 30 communities in 14 Districts with each FFS group establishing 1ha demonstration farm subsequent year. IFAD reviewed and made lot of input into the climate smart manual on cocoa establishment and supported the training of 225 Cocoa youth contractors on climate change adaptation best practices. | S
|  |  |  | The PMU have planned to established 60 fish frams and 60 integrated gardens |  | IFAD proposed the selection of 20 sites for fish farming and profiling of the beneficiaries. | S
| Component 2: Climate-resilient rural transportation and water infrastructure |  | Outcome 2 | The PMU will construct 60 waterpoints, 20 warehouses, 420 km feeder road, 150km trunk roadsand and 350km farm track. |  | IFAD granted No objection to road condition survey and selected road,and verified identified communities for warehouse and water points. | S
| Component 3: Institutional capacity building and policy engagemen |  | Outcome 3 | The project is to strengthening the capacity of three Government Agencies (EPA, MET and SLARI |  | IFAD organized meeting with EPA , SLMet and SLARI to agreed on the role and responsibilities of all partners to AF project | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ann Turinayo
| Email: | a.turinayo@ifad.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Planned activities under the reporting period are largely on track though we are just starting. Some of the actiities such as beneficiary profiling, selection and training of farmer field schools climate demonstration plots have already been completed. The project should expedite the establishment of the remaining climate model farms in the other districts.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Component 1: Climate-proofed agricultural production and post-harvest combined with livelihood diversification |  | Outcome 1 | IVS= The project is expected to develop 4500 ha Inlanding valley swamps, targetting 5625 households. Legacy IVS: The project is expected to provide technical asstance to 4000 farmers of previous IFAD funded projects (RCPRP and SCP-GAFSP) Cocoa= The project is expected to establish 6000 ha of new farms; benefitting 6,000 smallholders farmers . The projected is expected to establish 15 ha of cocoa clonal seed garden |  | The PMU prepared detail annual work plan and budget(AWPB)with implementaion strategies. Profiled beneficiaries in selected communitties and initial the selection of service providers to developed 1200 ha of IVS, established 1500ha of cocoa and 50ha of vegetable. | S
|  |  |  | Fish Farms: 60 fish frams are to be established Integrated Community Garden: 60 gardens are to be established |  | MAF initiated the selection process of consultant do the assessment of earth dam and site selection fo fish farm. | S
| Climate resilient rural infrastructure |  | Outcome 2 | Feeeder Roads: 420 km roads are to be constructed Trunk Roads: 150km of trunk roads are to be rehabilitated Farm Tracks: 350km are to be constrcuted |  | MAF and PMU drafted MOU between the PMU and Sierra road authority (SLRA) to do the road condition survey | S
| Institutional capacity building and policy engagement |  | Outcome 3 | Capacity Building of three Government Agencies (EPA, MET and SLARI |  | MAF organized meeting with partners to review the MOU signed and cleraly explain roles and responsibilities | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dr Abu Bakarr Karim
| Email: | karim@bhbgmbh.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project completed the profiling of 5625 housholds and initiated the recruitment of service providers to kick start the rehabilitation of 1200 ha of IVS; smallholder rice farmers of the previous IFAD projects received training on improved agronomic practices through FFS methodology. The project also organized induction workshop for the the profiling of 6000 cocoa beneficiaries and drafted MOU with SLARI for the establishment of new cocoa farms and cocoa clonal seed garden. The PMU developed training mamnual for the training of cocoa beneficiaries on best agronomic practices through FFS methodology. Recommendation: Viability Test Certification for cocoa from the country of origin must be produced by supplier, followed by robust verification test of the viability of the seeds by the designated instition in country. Given the unpredictable weither pattern, outplanting activities should be initiated earlier.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Core Indicator | Percentage of target population covered by adequate riskreduction systems | 0 | 6000 direct beneficiaries (17.1% of the total target population) | 35,000 direct beneficiaries, including 40% women and 40% youth X indirect beneficiaries
| Number of farmers reporting more diverse income sources. | 0 | 0 | 60% of farming households (in project area
| Number of earth dams constructed | 0 | 0 | 40
| Number of farmers reporting an increase in cocoa productivity. | 0 | 1500 | 85% of farming households (in project area)
| Number of farmers reporting an increase in rice productivity. | 0 | 0 | 85% of farming households (in project area)
| No of target farmers adopting climate resilient farming practices | 0 | 708 | 60% of farming households (in project area)
| Number of cocoa and improved rice nurseries established | 0 | 50 | 100
| Number of cocoa and improved rice seeds distributed | 0 | 1687500 cocoa seeds and no seed supplied for rice | 100
| Number of kilometers or rural roads and feed roads climate proofed | 0 | 0 | 120
| Number of farming households having access to a potable water supply | 0 | 0 | 20000
| Number of hectares of land irrigated from earth dams | 0 | 0 | 1000ha
| Number of water user groups adopting sustainable irrigation practices | 0 | 0 | 100 water user groups cultivating 1000ha
| Number of warehouses rehabilitated | 0 | 0 | 100
| Number of staff of the EPA and meteorological institute trained | 0 | 0 | 2 technicians trained by PY1. 2 meteorologists trained by PY3. 24 staff completed the training (12 by PY 1 and 12 by PY3)
| Number of sectoral policies integrating climate change risks (thanks to the training provided by the project) | 0 | 0 | at least 1
Note on H8: Minjauw, Fanny: We need to enter the final project target in these boxes, so I would enter 35,000
Note on H22: Minjauw, Fanny: This indicator is included below. In this box, it should be a figure related to the # of staff trained
Note on H26: Minjauw, Fanny: This indicator is included below. In this box, it should be a figure related to the # of staff trained

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Moderately unsatisfactory partnership cooperation especially EPA and SLMet. The agencies are technically supporting many MDAs, private companies and other UN agencies in term of climate information, environmental compliance and awareness raising, this is making their time so limited to give full support to the project and the focal persons are frequently travelling for conferences and seminars out of the country. We have proposed quarterly partners coordination meeting and quarterly joint monitoring in the 2022 annual work plan budget to remedy the situation.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes. The target for cocoa(1500 ha) was not achieved due to the non-viability of half of the seeds supplied. The target (15 ha) of the cocoa clonal seed garden establishment could not be achieved this year due to climate variability. Viability Test Certification for cocoa from the country of origin must be produced by supplier, followed by robust verification test of the viability of the seeds by the designated instition in country. Given the unpredictable weither pattern, outplanting activities should be initiated earlier
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No changes have been made to anything since this first report and the PMU have just start implementation
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes. Intrduction of agroforestry practices including intercropping cocoa farms with nitrogen fixing trees, timber trees, plantain etc to reduce CO2 and greenhouse gas emission
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | The 40% female headed households and 40% youth inclusion in project activities have been highly considered. Equal access to productive resources and collective decision making at households level have achived. The intercropping of food crops such as cassava, pinneaple, plantain etc, and also the provision of labour saving tools/equipment for women in vegetable production encouraged high level of female participation as key actors in climate change adaptation
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Not Applicable until Mid-Term
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Not Applicable until Mid-Term
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | Not Applicable until Mid-Term
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | Not Applicable until Mid-Term
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Not Applicable until Mid-Term
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Not Applicable until Mid-Term
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Not Applicable until Mid-Term
What measures are/have been put in place to ensure sustainability of the project/program results? | Not Applicable until Mid-Term
What measures are being/could have been put in place to improve project/program results? | Not Applicable until Mid-Term
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Not Applicable until Mid-Term
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Not Applicable until Mid-Term
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | Not Applicable until Mid-Term
If learning objectives have been established, have they been met? Please describe. | Not Applicable until Mid-Term
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Not Applicable until Mid-Term
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Not Applicable until Mid-Term
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | Not Applicable until Mid-Term
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization. | Not Applicable until Mid-Term
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | 2000003346
Implementing Entity | IFAD
Type of implementing entity | MIE
Country | Sierra Leone
Region | Africa
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 1250 | 750 | 500 | Total | 210000 | 35000 | 175000 | Total |  |  |  | Total
|  | % of female beneficiaries | 40% | 40% | 40% |  | 40% | 40% | 40% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 40% | 40% | 40% | % of Youth beneficiaries | 40% | 40% | 40% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 150 | Drought | 4: Effective | Total | 300 | Drought | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 40% |  |  | % of female targeted | 40% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Agriculture | Regional | 2: Undertaking or updating of assessments in progress | 1 | Agriculture | Regional | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | National | 1 | 3: Dissemination and communication | Geographical coverage | National |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 15 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | National | 1 | 2: Monitoring and warning service | Geographical coverage | National |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 15 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 147 | Agriculture | 3: Medium capacity | Total | 300 | Agriculture | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 17% |  |  | % of female targeted | 40% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 147 | 17% | Public |  | 300 | 40%
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Agriculture | 3: Medium capacity | Public | National | Agriculture | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 3 | National | Agriculture | 3: Medium capacity | 3 | National | Agriculture | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 14% |  | Agriculture |  | 100 |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 5937 | 40% | 4: Mostly aware |  | 35000 | 40% | 5: Fully aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 197 | 40% to 60% | 4: Mostly aware |  | 832 | 40% to 60% | 5: Fully aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 7 | Training manuals | National |  | 7 | Training manuals | National
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Agriculture | National | 3: Moderately responsive (Some defined elements) |  | Agriculture | National | 5: Highly responsive (All defined elements )
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 1 | Community |  | Agriculture | 5 | Community |  | Agriculture
|  | 0 | Multi-community |  | Agriculture | 47 | Multi-community |  | Agriculture
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 3: Moderately effective |  | Agriculture | land | [8 empty] | 5: Very effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 2755 | ha protected | 4: Effective | Cultivated land/Agricultural land | 2755 | ha protected | 4: Effective |  |  |  | 3: Moderately effective | Cultivated land/Agricultural land | 11500 | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1200 | ha protected | 4: Effective | Catchment area/Watershed/Aquifer | 1200 | ha protected | 4: Effective |  |  |  |  | Catchment area/Watershed/Aquifer | 4500 | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1500 | ha protected | 4: Effective | Forests | 1500 | ha protected | 4: Effective |  |  |  |  | Forests | 6000 | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 900 | 40% | 3: Moderate improvement |  | 35000 | 40% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 510 | 40% | From 20% to 30% | Agricultural-related | 1000 | 40% | From 40% to 50% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies | Agriculture | Community-based adaptation | 2 | Adaptation strategies | Agriculture
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 2: Most not integrated |  |  |  | 5: All (Fully integrated)
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
[6 empty] | 1 | Agriculture | National | Environmental Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
[6 empty] | 1 | 5: Fully enforced (All elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
[6 empty] | Inclusion of youth | National | Innovation scaled-up
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
[6 empty] | 2 | Inclusion of youth | Undertaking innovative practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
[6 empty] | 1 | Innovative practice |  | 5: Very effective