## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | January 2022 - December 2022
| Project Title: | An integrated landscape approach to enhancing the climate resilience of smallscale farmers and pastoralists in Tajikistan
| Project Summary: | Tajikistan – An integrated landscape approach to enhancing the climate resilience of smallscale farmers and pastoralists in Tajikistan Implementing Entity: Committee for Environmental Protection under the Government of the Republic of Tajikistan (CEP); United Nations Development Programme (UNDP). Project objective: The project is trying to address the problem of climate change induced negative impacts on livelihoods of small-scale rural farmers and pastoralists in the Kofirnighan River Basin (KRB). The objective of the proposed project is to enhance the livelihoods of the small-scale farmers and pastoralists living in the Kofirnighan River Basin under future climate change conditions. It aims to make rural farmers and pastoralists climate resilient by developing and then implementing a climate-resilient catchment management strategy for the KRB, which will enhance the provision of ecosystem services in the river basin. Component 1: Integrated catchment management to build climate resilience (USD 1,012,000). Outcome 1: Catchment management strategy to manage climate risks operationalised at raion (district) and jamoat (subdistrict)levels in Kofirnighan River Basin (KRB). Component 2: Ecosystem-based Adaptation, including Climate Smart Agriculture and Sustainable Land Management, in agroecological landscapes (USD 7,282,810). Outcome 2: An integrated approach to building climate resilience of agro-ecological landscapes operationalised at a village level. Component 3: Knowledge management on building climate resilience through integrated catchment management and EbA in the KRB (USD 142,500). Outcome 3: Existing knowledge management platforms supported for integrated catchment management and EbA.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | TJK/MIE/Rural/2018/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme (UNDP). | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Tajikistan | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Vahdat District, Varzob District, Faizobod District, Nosiri Khusrav District, Shaartuz District, Kabodiyon District | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | August 27, 2019
IE-AFB Agreement Signature Date: |  | October 21, 2019 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | June 8, 2020 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | N/A
Original Completion Date: |  | June 7, 2025
Revised Completion Date after approval of |  | N/A
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
| Condition or Requirement | N/A
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception report - September 2021 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | N/A | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Giyosiddin Nemonov | Dominican Republic
| Email: | giyosiddin.nemonov@undp.org | Ecuador
| Date: | August, 2020 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Committee for Environmental Protection under the Government of the Republic of Tajikistan | Equatoral Guinea
| Email: | info@tajnature.tj | Eritrea
| Date: | June, 2020 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | United Nations Development Programme (UNDP). | Fiji
| Email: | info@undp.org | Finland
| Date: | June, 2020 | France
| Executing Agency |  | Gambia
| Name: | Committee for Environmental Protection under the Government of the Republic of Tajikistan | Georgia
| Email: | info@tajnature.tj | Germany
| Date: | June, 2020 | Ghana
| Executing Agency |  | Greece
| Name: | N/A | Grenada
| Email: | N/A | Guatemala
| Date: | N/A | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | N/A | Guyana
| Email: | N/A | Haiti
| Date: | N/A | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [31.12.2021] |  |  |  |  | Financial information PPR 2: cumulative from project start to [31.12.2022] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [31.12.2021] | 395294 |  |  |  | Estimated cumulative total disbursement as of [31.12.2022] Note: excluding commitment and IE fee | 1260188 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | Since the beginning of the project one AF tranche was received: in amount of $726,500.00 which includes: $28,893.99 - 2020 expenses $366,400.44* - 2021 expenses&commitment *($278,500.44 actual spendings+$87,900.00 commitment) Total utilization against received tranche is: 54% |  |  |  | Add any comments on AF Grant Funds. (word limit=200) | The project has received tracnhe of USD $4,106,810 from AF. The expenditure in 2022 was USD $952,753.41 which makes 23.23% utilization against received tranche. 9526556,82 TJS = 763838 USD was transferred to the Project Bank account during 2022 |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME |  |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | 2020 Expenses | 2021 Expenses | TOTAL AMOUNT | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Activity 1. Catchment management strategy to manage climate risks operationalised at raion (district) and jamoat (sub-district) levels in Kofirnighan River Basin |  | 51263.2 | 51263.2 |  | Activity 1. Catchment management strategy to manage climate risks operationalised at raion (district) and jamoat (sub-district) levels in Kofirnighan River Basin | 30061.94
| Activity 1.2. Support provided for upgrading automated weather stations in Kofirnighan River Basin watersheds. |  | 15615.44 | 15615.44 |  | Activity 1.2. Support provided for upgrading automated weather stations in Kofirnighan River Basin watersheds. | 48907.54
| Activity 1.3.. Integrated catchment management strategy developed for the Kofirnighan River Basin |  | 17799.65 | 17799.65 |  | Activity 1.3.. Integrated catchment management strategy developed for the Kofirnighan River Basin | 116926.2
| Activity 1.4.. Strengthened coordination and training mechanisms for integrated climate-resilient catchment management. |  | 12327.43 | 12327.43 |  | Activity 1.4.. Strengthened coordination and training mechanisms for integrated climate-resilient catchment management. | 14255.94
| Activity 1.5.Payment for Ecosystem Services models to support the long-term financing of integrated catchment management strategy implementation |  | 440.83 | 440.83 |  | Activity 1.5.Payment for Ecosystem Services models to support the long-term financing of integrated catchment management strategy implementation | 34748.69
| Activity 2.1. Agro-ecological extension services supported at the jamoat level to provide technical support for EbA implementation. |  | 0 | 0 |  | Activity 2.1. Agro-ecological extension services supported at the jamoat level to provide technical support for EbA implementation. | 112453.28
| Activity 2.2. Watershed Action Plans (WAPs) developed that promote climate resilience and enhance economic productivity for target communities. |  | 13847.92 | 13847.92 |  | Activity 2.2. Watershed Action Plans (WAPs) developed that promote climate resilience and enhance economic productivity for target communities. | 89398.52
| Activity 2.3. EbA interventions implemented in target watersheds by local communities |  | 0 | 0 |  | Activity 2.3. EbA interventions implemented in target watersheds by local communities | 334185.6
| Activity 3.1. Existing knowledge management platforms supported for collating information on the planning, implementation and financing of EbA interventions |  | 5185.36 | 5185.36 |  | Activity 3.1. Existing knowledge management platforms supported for collating information on the planning, implementation and financing of EbA interventions | 19940.25
| Activity 3.2. An impact evaluation framework established to enable effective adaptive management of EbA activities. |  | 1520.71 | 1520.71 |  | Activity 3.2. An impact evaluation framework established to enable effective adaptive management of EbA activities. | 20095.18
| Activity 4. Project Management | 28893.99 | 160499.9 | 189393.89 |  | Activity 4. Project Management | 131820.27
| TOTAL | 28893.99 | 278500.44 | 307394.43 |  | TOTAL | 952793.41 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
| Implementing Entity fee per Legal Agreement |  |  | 350304 |  | Implementing Entity fee per Legal Agreement | 209447
| GRAND TOTAL |  |  | 657698.43 |  | GRAND TOTAL | 1162240.41
PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST FOR 2022 | Est. Completion Date |  | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Activity 1.1.Multi-hazard climate risk model developed for vulnerable watersheds in the Kofirnighan River Basin. | 43500 | December 2022 |  |  | Activity 1.1.Multi-hazard climate risk model developed for vulnerable watersheds in the Kofirnighan River Basin. | 24142.45 | December 2023
| Activity 1.2. Support provided for upgrading automated weather stations in Kofirnighan River Basin watersheds. | 250000 | December 2022 |  |  | Activity 1.2. Support provided for upgrading automated weather stations in Kofirnighan River Basin watersheds. | 276981.4 | December 2023
| Activity 1.3. Integrated catchment management strategy developed for the Kofirnighan River Basin | 86300 | December 2022 |  |  | Activity 1.3. Integrated catchment management strategy developed for the Kofirnighan River Basin | 113434.58 | December 2023
| Activity 1.4. Strengthened coordination and training mechanisms for integrated climate-resilient catchment management. | 25000 | December 2022 |  |  | Activity 1.4. Strengthened coordination and training mechanisms for integrated climate-resilient catchment management. | 13757.24 | December 2023
| Activity 1.5. Payment for Ecosystem Services models to support the long-term financing of integrated catchment management strategy implementation | 49500 | December 2022 |  |  | Activity 1.5. Payment for Ecosystem Services models to support the long-term financing of integrated catchment management strategy implementation | 41087.27 | December 2023
| Activity 2.1. Agro-ecological extension services supported at the jamoat level to provide technical support for EbA implementation. | 270000 | December 2022 |  |  | Activity 2.1. Agro-ecological extension services supported at the jamoat level to provide technical support for EbA implementation. | 240000 | December 2023
| Activity 2.2. Watershed Action Plans (WAPs) developed that promote climate resilience and enhance economic productivity for target communities. | 77000 | December 2022 |  |  | Activity 2.2. Watershed Action Plans (WAPs) developed that promote climate resilience and enhance economic productivity for target communities. | 106602.76 | December 2023
| Activity 2.3. EbA interventions implemented in target watersheds by local communities | 2439806.69 | December 2022 |  |  | Activity 2.3. EbA interventions implemented in target watersheds by local communities | 2487500 | December 2023
| Activity 3.1. Existing knowledge management platforms supported for collating information on the planning, implementation and financing of EbA interventions | 20000 | December 2022 |  |  | Activity 3.1. Existing knowledge management platforms supported for collating information on the planning, implementation and financing of EbA interventions | 44874.39 | December 2023
| Activity 3.2. An impact evaluation framework established to enable effective adaptive management of EbA activities. | 22500 | December 2022 |  |  | Activity 3.2. An impact evaluation framework established to enable effective adaptive management of EbA activities. | 27500 | December 2023
| 4. Project Management | 150622.51 | December 2022 |  |  | 4. Project Management | 158775.8 | December 2023
| TOTAL | 3434229.2 |  |  |  | 62040 Foreign exchange currency lost | 50 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
| Implementing Entity fee per Legal Agreement | 209447 |  |  |  | TOTAL | 3534705.89
| GRAND TOTAL | 3643676.2 |  |  |  | Implementing Entity fee per Legal Agreement | 133110
[6 empty] | GRAND TOTAL | 3667815.89
[9 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[9 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[9 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[9 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Capacity constraints of local institutions may limit the ability to undertake the interventions implementation. | Medium | • Human resource capacity will be developed in all targeted regions and villages. • Collaboration and exchange between local institutions and regional/international research institutes will be initiated. • An Integrated Catchment Management Specialist will work closely with the Programme Manager to ensure timely delivery of project outputs.
Priority interventions implemented are not found to be cost-effective. | Low | Detailed analysis of project areas will be conducted to identify particular interventions and ensure their cost-effectiveness. These interventions to be approved by the project steering committee, implementing entities and districts local executive authority.
Lack of commitment/buy-in from local communities may result in failure of intervention sites. | Low | -The detailed analysis of project areas is conducted in consultation with local communities and executive authorities. During these consultations local communities are involved in the process of identification of priority interventions. '-The explanatory activities about the project budget limits to the most vulnerable communities is being explained starting from the district analysis point. '-Stakeholder engagement plan will be developed during the inception phase. Consultations and raising awareness activity on project interventions will be continued during implementation of the project.
Current and predicted climate variability and/or extreme climate events result in poor results for EbA interventions | Medium | Throughout the inception and implementation phase, any changes in the climate will be considered in planning for the implementation of EbA activities. '- Drought and flood-resilient species will be used, as well asindigenousspecies wherever possible. '- Techniques to assist plant growth particularly in the seedling/sapling phases and to reduce risk of damage from extreme climate events will be used.'- Species will be planted in appropriate seasons to reduce risk of hazard impact. '- Ensuring diversity in selected seeds and crops will reduce this risk
Trees and other species planted by the project are cut down by the communities for fuelwood. | Medium | - Community involvement and awareness raising will be undertaken to avoid this risk. '- Species chosen for planting will be beneficial as fruiting trees rather than as fuelwood.
Disagreement amongst stakeholders regarding demonstration of site selection. | Low | -Intervention sites will be selected using an agreed upon list of criteria and the developed shortlist of EbA interventions to ensure the selection is transparent and equitable. -There will be a participatory approach to project activities, particularly with intervention site selection
High turnover of staff members in executing and implementing agencies may negatively impact on project deliverables. | Low-medium | Building partnerships between government and non-government agencies to ensure continuity.
Loss of government support may result in lack of prioritisation of proposed project activities. | Low | -Regular stakeholder consultation and involvement will be undertaken to ensure that government maintains its commitment and considers the project as a support mechanism to its existing climate change adaptation programmes
Institutional capacities and relationships are not sufficient to provide effective solutions to climate problems that are complex and multisectoral. | Medium | -To diffuse this impact, it is necessary for the Project to closely cooperate with the implementing entities (UNDP and CEP) with regards to qualified experts
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
COVID-19 pandemic | Low | Conduction of virtual meetings, preliminary mapping of the target areas. Reaching out to the local authorities to send preliminary data via email. Visits to the project sites shall be conducted maintaining social distancing and use of PPE.
High turnover of staff in UNDP CO | Low | The project experience intermitant and i support during 2021 due to the departure of the UNDP Cluster Manager and a restructuring process.This was addressed in 2022 with a replacement Cluster Manager
Limited availability of technically experienced national consultants on EbA, ESVAL, etc. | High | Addressed through recruitment of an international technical adviser, wider advertizing/networking
Slow processing of administrative procedures by project | Medium | Increased engagement and support by UNDP Cluster manager and UNDP senior management
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
See above mittigating measures taken. Risks partially addressed but delays in implementation progress occurred in 2022.. Further steps are planned based on recommendation of MTR scheduled April 2023

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Low: Necessary monitoring is limited to compliance with related laws and addressing concerns through the grievance mechanism. | Project activities will be undertaken in compliance with the domestic laws of Tajikistan and with all relevant international laws. | monitoring reports | Project design was carried out cognisant with relevant laws of Tajiistan | All field activities undertaken in accordance wit national legislation | NA at this point in implementation | NA at this point in implementation
2 - Access and equity |  |  | Mid: Project activities could temporarily restrict availability and/or quality of, access to, resources where a land use change can displace an economic activity (as rotational grazing control, re-afforestation). Potential impacts will be monitored on a regular basis through participatory representative approach to ensure access and equity is equally provided to all communities and groups. | Project activities will be designed to provide fair and equitable access to benefits in a manner that is inclusive. Activities will not exacerbate existing inequities, particularly with respect to marginalised or vulnerable groups. | monitoring reports | To address short-term restrictions concerning access to pasture lands and forests, the project will promote alternative business opportunities (income generating demonstration activities) and community enterprise developments that will help communities generate compensating incomes. The project is also foreseen introduction of energy-efficient stoves into target communities to compensate for limited access to forest resources | NA at this point in implementation (no significant activities on forest or pasture at this time) | NA at this point in implementation | NA at this point in implementation
3 – Marginalized and vulnerable Groups |  | z | Mid: Vulnerable and marginalized groups may have (i) limited mobility to participate during key stages of project implementation, and (ii) limited access to entitled productive assets (ref. degraded pastures and forests). Stakeholder Engagement Plan developed by the project will guide inclusive participation of such groups in decision making processes. In cases where a land use change can temporarily displace an economic activity (as rotational grazing control, re-afforestation), in accordance with domestic laws and regulations, the project identified compensatory income generating opportunities which will be offered to vulnerable and marginalized groups. Potential impacts will be monitored to ensure such opportunities materialize. | Project activities have taken into account marginalised and vulnerable groups – poor and vulnerable individuals and include those living in places with increased impacts of climate change, food insecure households, households with limited or no productive assets (limited resilience), livestock and/or agricultural land plots. Given the relatively higher rates of labour migration among men, households without manpower, female-headed households, and those with small children and elderly people may also be considered vulnerable. | monitoring reports | UNDP has developed a Stakeholder Engagement Plan, which will guide consultations inclusively during implementation phases, assuring broad representation within existing relevant community based organizations and groups. | All stakeholders at jamoat level consulted through consultative meetings and different groups opinions and inputs assured
4 – Human rights |  |  | Low: Necessary monitoring is limited to compliance with related laws and addressing concerns through the grievance mechanism. | Project activities will respect and, where applicable, promote international human rights. Tajikistan is the most vulnerable country to climate change in Central Asia. Negative effects of climate change on the Tajik population include glacial and permafrost melt, increased rainfall intensity and longer and more frequent dry spells. Together, these effects have increased the rate of topsoil erosion, threatening the livelihoods, health and wellbeing of the population. Losses from natural hazards currently amount to ~20% of the country’s GDP and climate change impacts are predicted to increase the frequency and magnitude of such losses. In the future, loss amounts are expected to rise from ~US$50 million in 2014 to ~US$132 million by 2030. Approximately 33% of all agricultural losses in the country are currently attributable to climate change and variability. Furthermore, it has been projected that crop yields in Tajikistan will decrease by an additional 5–30% by 2050, with the potential for severe negative impacts on the country’s economy. Moreover, by 2050, ~77% of the country’s population will be living in areas most exposed to the impacts of climate change. Tajikistan’s vulnerabilities are attributed to the country’s weak social structures, low adaptive capacity, underdeveloped infrastructure, low income insecurity, poor service provision, strong dependence on agriculture and institutional constraints. To address these challenges, the project will support Tajikistan’s authorities and target population to enhance the climate resilience amongst small-scale farmers and pastoralists of Kofirnighan River basin. Improving the climate resilience of these communities will involve developing a climate-resilient catchment management strategy to inform the planning and development of rural areas in adapting to the increasing impacts of climate change. Interventions will also promote sustainable management of natural resources through an integrated landscape approach to catchment management. The project will directly benefit an estimated 46,000 individuals who are especially vulnerable to the impacts of climate change, through the design and implementation of concrete on-the-ground EbA interventions for more efficient natural resources management. These measures will also provide social and economic benefits to target population in terms of livelihoods, health and wellbeing of the population. In terms of human rights mainstreaming, the impact is multidimensional in nature and addresses the right to food, energy, water, health, etc. In particular, the project’s interventions have the following social and economic benefits for target population: (a) increased profit margins and farm income, (b) reduced loss of crops and land caused by slope instability, drought or dry spells and also caused by ineffective agricultural practices and livestock grazing/breeding; (c) reduced agricultural inputs, water consumption and thus production costs; (d) reduced risk of economic failure due to diversification of production on and off-farm; (e) reduced crops susceptibility to pests; (f) increased nutrition and food security for local communities; (g) increased provision of fuelwood and timber and reduced loss of trees to drought or dry spells; and (h) increased pasture productivity, fodder production and carrying capacity. In addition, the project interventions increase nonmaterial benefits such as ecosystem services such as tourism and recreation, derived from increased conservation value of the landscape. Throughout the project implementation period, the project will seek to ensure that benefits of the project are shared broadly in a non-discriminatory and equitable manner. The project will ensure that all relevant stakeholders participate in decision-making processes and consultations, and that such participatory processes are transparent. Necessary strategies, action plans, site selection criteria and lessons learned will be documented and shared regularly through community driven consultation platforms that the project will seek to facilitate. A wide range of stakeholders were consulted with during the scoping and validation phase of proposed project development. Importantly, the project’s Executing Entity, the Committee for Environmental Protection (CEP), was consulted through the iterative process of refining the project design. As the national organisation responsible for implementing adaptation projects in the country, the CEP is comprised of numerous technical experts. Therefore, the CEP is well-positioned to ensure that the project design is tailored to local requirements, that it benefits vulnerable groups and includes necessary gender considerations. A Validation Workshop was held in Dushanbe on 22 June 2018 that included representatives from relevant Kofirnighan river basin districts, international organisations, academia and partner projects. | monitoring reports | Necessary monitoring is limited to compliance with related laws and addressing concerns through the grievance mechanism. | Local community human rights promoted through jamaot watershed action planning that seek to assure access to critical resources, food security, etc. | NA at this point in implementation | NA at this point in implementation
5 – Gender equality and women’s empowerment |  |  | Mid: Vulnerable women may not be adequately represented in decision-making or participation in the design and implementation of the sub-projects. As a result, they may have limited access to resources, opportunities and benefits. Women’s engagement and participatory mechanisms will be put in place. Dedicated gender focal points will be assigned both at project level and in each target community to proactively identify particularly vulnerable women, including those with restricted mobility and other conditions. Such proactive inclusion approaches will ensure that the project addresses women’s adaptive needs. As part of the project M&E system systematic monitoring will be undertaken to ensure women’s participation, involvement and empowerment. | Project activities will be designed and implemented so that all genders are: i) able to participate fully and equitably; ii) receive comparable social and economic benefits; and iii) do not suffer disproportionate adverse effects as per UNDP Gender Mainstreaming Strategy. A gender analysis will be carried out during the Inception Phase of the proposed project to ensure this. | monitoring reports | Vulnerable women may not be adequately represented in decision-making or participation in the design and implementation of the sub-projects. As a result, they may have limited access to resources, opportunities and benefits. Women’s engagement and participatory mechanisms will be put in place. | Women participation in consultative meetings and training activities assured | NA at this point in implementation | NA at this point in implementation
6 – Core labour rights |  |  | Low: Necessary monitoring is limited to compliance with related laws and addressing concerns through the grievance mechanism. | Project activities will observe the core labour standards of Tajikistan as well as those identified by the International Labour Organisation. | monitoring reports | Necessary monitoring is limited to compliance with related laws and addressing concerns through the grievance mechanism. | All field activities observe national labour rights legislation | NA at this point in implementation | NA at this point in implementation
7 – Indigenous peoples |  |  | N/A | NA | NA | NA | NA | NA | NA
8 – Involuntary resettlement |  |  | Low: Physical resettlements are not necessary for the activities, however, temporary economic displacement (agricultural lands, pastures, forests) are possible due to planned grazing control measures, reforestation activities and introduction of agricultural demonstration plots. Sub-projects will be implemented in such areas where displacement of economic assets is both temporary (short-term) and voluntary. Necessary monitoring will include compliance with related laws, human rights, international provisions and grievance mechanism. | Project activities will not cause any involuntary resettlement of communities. However, sub-projects targeted at pasture grazing control measures, re-forestation, and agricultural demonstration land plots may involve displacement of economic assets (pasture lands, agricultural lands, forests). | monitoring reports | To eliminate or minimize any possible harm to potential incomes, the project will target severely degraded lands (pastures, forests) which are feasibly compensable with alternative income-generating activities targeted to affected communities or groups. | NA | NA at this point in implementation | NA at this point in implementation
9 – Protection of natural habitats |  |  | Low: Project activities will be carried out on areas already under usage, but there is low risk that the construction of EbA interventions could result in the destruction of small areas of natural habitat. Natural habitats are determined and defined by the Government of Tajikistan (Committee for Environmental Protection), and UNDP will monitor project interventions and mitigating measures will be taken in case any sub-projects are selected to be implemented within or relative proximity to such defined natural habitats. | Project activities will not involve any conversion or degradation of critical natural habitats, including those that are: i) legally protected; ii) officially proposed for protection; iii) recognised by authoritative sources for high conservation value, including as critical habitats; or iv) recognised as protected by traditional local communities. | monitoring reports | Project activities will be carried out on areas already under usage, but there is low risk that the construction of EbA interventions could result in the damage of small areas of natural habitat. | NA at this point in implementation as no significant actions impacting habitats have yet been implemented | NA at this point in implementation | NA at this point in implementation
10 – Conservation of biological diversity |  |  | Low: There is a risk that alien and/or invasive alien species are used in reforestation activities. Prior to selection of suitable species, the project Team jointly with Ministry of Agriculture and Forestry Agency will fact check applicability against endorsed inventory of species proven harmless for Kafernigan River Basin. Joint monitoring of flora and fauna changes will also be carried out. The Project will also support the setting up of a procedure for tracking, monitoring and registration of restoration actions implemented. During the last year of the project an ecological and land use assessment will be carried out to evaluate the rate of success of the restoration. | The Project will be supporting activities in environmentally sensitive areas, but this work will aim at reducing impacts in these areas with a net positive impacts. Project activities will be designed and implemented in a way that avoids any significant or unjustified reduction or loss of biological diversity or the introduction of known invasive species. | monitoring reports | Project activities will be designed and implemented in a way that avoids any significant or unjustified reduction or loss of biological diversity or the introduction of known invasive species. | NA at this point in implementation as no significant actions impacting BD have yet been implemented | NA at this point in implementation | NA at this point in implementation
11 – Climate change |  |  | Low: Climate change adaptation of communities will be included in M&E. GHG emissions risk will be monitored and managed. Compliance with related laws will be monitored and concerns through the grievance mechanism addressed in accordance with respective laws and regulations. | Project activities will not result in any significant or unjustified increase in GHG emissions or other drivers of climate change. The project’s designed activities directly support implementation of ecosystem-based adaptation, including climate-smart agriculture and sustainable land management in agro-ecological landscapes. Such actions include rehabilitation and restoration of degraded forest ecosystems, vegetation growth support, water retention measures, establishing saxaul plantations, climate-resilient crop seed planting, and others to prevent and mitigate water related adverse climatic events that have typically posed risks to livelihoods and health of target communities. Current and predicted climatic variability has been taken into account during project design. Throughout the inception and implementation phase, any changes in the climate will be taken into account in planning for the implementation of EbA activities. Drought- and flood-resilient species will be used, as well as indigenous species wherever possible. Techniques to assist plant growth particularly in the seedling/sapling phases and to reduce risk of damage from extreme climate events will be used. Species will be planted in appropriate seasons to reduce risk of hazard impact. The project also aims to build climate resilience through development of a catchment management strategy to manage and operationalize climate risks at district and Jamoat levels in Kofirnighan river basin. The project will develop multi-hazard climate risk models (MHCRM) for vulnerable watersheds in KRB and provide technical support for the modernization of automated weather stations in the most vulnerable districts of KRB. These will help authorities and communities adequately assess risks, climate related projections and incorporate these risks in the Kofirnighan River Basin Management Plans to make informed decisions on EbA activities. | monitoring reports | Project activities will not result in any significant or unjustified increase in GHG emissions or other drivers of climate change. | Field activities (ad-hoc community priority interventions) do not increase GHG or CC vulnerability | NA at this point in implementation | NA at this point in implementation
12 – Pollution prevention and resource efficiency |  |  | Low: Pest control measures and agricultural support may involve potential use of pesticides. Selection and use of suitable pesticides chosen for application will be consulted with the Ministry of Agriculture. Compliance with available Pest Management regulations and manuals endorsed by the Ministry of Agriculture will be duly monitored. | Project activities will be designed and implemented in a way that meets applicable international standards for maximising energy efficiency and minimising material resource use, the production of wastes, and the release of pollutants. Project interventions are not expected to produce any significant amounts of waste or other pollutants. Any potential opportunities identified for improved resource efficiency and pollution reduction during the project development phase will be captured in the project design. The Project will support communities to adopt improved farming techniques (organic agriculture, soil and water conservation, more resilient crop varieties) that would reduce the use of fertilizers and pesticides. Although biological pest control will be preferred, potentially harmful pesticides may be needed for specific use. In this particular case, they will be properly managed, stored, and used in accordance with national and international standards, regulations and procedures. | monitoring reports | Project interventions are not expected to produce any significant amounts of waste or other pollutants | Project interventions are not expected to produce any significant amounts of waste or other pollutants | NA at this point in implementation | NA at this point in implementation
13 – Public health |  |  | Low: Small-scale construction activities (Component 2) may pose safety risks to community members. Regular monitoring will be conducted for compliance with national construction norms and standards, as well as WHO guidelines on Water Safety Plans (drinking water and sanitation). | The Project will follow related environmental impact assessment procedures and ensure compliance with national construction standards and norms, sanitary norms and regulations, and other national laws and regulations (forestry, water, environment, and health). The project will also follow technical guidance and best practices regarding rain-water harvesting systems, drip-irrigation techniques, and micro-reservoirs that are not adequately institutionalized across the country. Other activities may include construction of gabions, terracing, bank enforcement and small dams, the project will assess best practices and lessons learned to address community safety risks from such construction. | monitoring reports | Small-scale construction activities (Component 2) may pose safety risks to community members. Regular monitoring will be conducted for compliance with national construction norms and standards, as well as WHO guidelines on Water Safety Plans (drinking water and sanitation). | Field activities (ad-hoc community priority interventions) implemented within national legislation and controls of dangerous practices | NA at this point in implementation | NA at this point in implementation
14 – Physical and cultural heritage |  |  | Low: Necessary monitoring is limited to compliance with related laws and addressing concerns through the grievance mechanism. | Project activities have been designed so as to avoid the damage to, or removal of, any physical cultural resources, cultural sites, and sites with unique natural values recognized as such at the community, national or international level. | monitoring reports | Necessary monitoring is limited to compliance with related laws and addressing concerns through the grievance mechanism. | No risks identified within current field activities and activities designed with local community participaion. | NA at this point in implementation | NA at this point in implementation
15 – Lands and soil conservation |  |  | Low: Necessary monitoring is limited to compliance with related laws and addressing concerns through the grievance mechanism. | Project activities will be designed and implemented in a way that promotes soil conservation and avoids degradation or conversion of productive lands or land that provides valuable ecosystem services. | monitoring reports | Necessary monitoring is limited to compliance with related laws and addressing concerns through the grievance mechanism. | Field activities (ad-hoc community priority interventions) benefit land and soil conservation | NA at this point in implementation | NA at this point in implementation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | There are no cases of unanticipated ESP risks
Have unanticipated ESP risks been identified during the reporting period?
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Regular monitoring and evaluation of implmentation of activities are carried out to ensure that all activities for implementation are compliant with the ESMP
Have the implementation arrangements been effective during the reporting period? |  | The implementation arrangements have been effective
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Implementing entity is also the executing entity for the project and all the arrangements are in place.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The implementation arrangements have been effective
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
To date no grievances have been received
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal?
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)?
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Catchment management strategy to manage climate risks operationalised at raion (district) and jamoat (sub-district) levels in Kofirnighan River Basin (KRB). | Outcome | Number of staff trained to respond to impacts of climate-related events (gender disaggregated). | 0 | 30% | NA (not yet initiated)
Integrated catchment management strategy developed for the KRB. | Output | Integrated catchment management strategy developed.Number of staff trained (gender disaggregated). Number of community members trained (gender disaggregated) | 0 | 30% 30% | NA (not yet initiated)
An integrated approach to building climate resilience of agro-ecological landscapes operationalised at a village level. | Outcome | Number of people practising climate change adaptation technologies (gender disaggregated). | 0 | 30% | NA (not yet initiated)
.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Implementing Entity has made all necessary efforts to comply with the key concepts of the AF Gender Policy, including gender equity, gender mainstreaming, gender responsiveness, gender sensitivity and women's empowerment. In particular the following aspects have been put in place to ensure compliance with the AF gender policy: 1 - Developing a gender strategy that includes a detailed plan of action necessary for its implementation for the remaining period of the project. Gender Strategy was edited several times taking into account comments and suggestions from the National and Technical Director of the project. 2 - Preparing necessary materials for conducting a gender research in the jamoats of districts involved in the project, namely questionnaires for conducting focus groups. 3 - Conducting of two gender trainings for project employees and trainers, representatives of the Committee of Enviromental Protection, Hydromet and UNDP. The purpose of the trainings was to increase gender sensitivity, clarify the role of gender approaches in the project and methods of their implementation to the variety of projects stakeholders.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Implementation arrangements have been successful to date with adequate representation of women during the inception workshop and consultations.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | Executing Entity provided employees, representatives of all the relevant departments to participate in gender training, and also made everything necessary to assist in the introduction of gender approaches (allocation of funds for the second training, providing of an accomodation for the first training, etc).
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Implementation arrangements have been effective and made the introduction of gender mainstreaming within tha project possible.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | not to date
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
NA |  | NA
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Outcome 1. Catchment management strategy to manage climate risks operationalised at raion (district) and jamoat (sub-district) levels in Kofirnighan River Basin (KRB). |  | Outcome 2 | By the mid of the project, at least 30 staff from local government at raion and jamoat levels (of which at least 30% are women) trained on integrated catchment management. By the end of the project, at least 100 staff from local government at raion and jamoat levels (of which at least 30% are women) trained on integrated catchment management. |  | 1.1) The Project has hired national experts to conducted gap analyses and research to clarify baseline situation, Potential capacity and software to conduct the modeling has been identified. Planning for pilot modelling of MHCRM in 2 pilot watersheds in the upper KBR has been made for 2023 and TOR for additional support of an international consultant to do this developed. 1.2) The Project completed a feasibility analysis of the chosen weather stations for upgrading throughout the reporting period. To modify the operations for modernizing Weather Stations with Hydromet, the Project team has held discussions with the Agency for Hydrometeorology. During the reporting period, the equipment acquisition procedure for modernisation began. 1.3) A review to clarify the baseline situation in terms of Water sector reform progress in the KBR undertaken and revealed assuimptions made in Prodoc. incorrect (i.e. reform progress is not well advanced in terms of RBOs/RBC and other key elements. Additionally, Catchment management strategy is not a priority need (but finalization of KRB Management plan is). Study also revealed widespread lack of understanding or awareness of WSR concept or state policy. 97 representatives of various local governments, the local population, and Water Users Associations in 6 target districts participated in trainings on mainstreaming climate risks for integrated catchment management during the reporting period, which was conducted by the project team in collaboration with local consultants. 1.4) In order to evaluate the existing situation and pinpoint any shortcomings, the Project facilitated a coordination meeting on the water reform sector throughout the reporting period. Participants included representatives from several international organizations and governmental organizations, including the Ministry of Agriculture and the Ministry of Energy and Water Resources. 1.5) The project has hired an international and national expert to undertake a pilot ESV exercise in the upport KBR and capture lessons/make recommendations for future (as an initial basis for future PES modelling if viable). The ESV will be piloted in two target watersheds in 2023. Significant delays in implementation due to difficulties to recruit suitable national consultant. | MS
| Outcome 2. An integrated approach to building climate resilience of agro-ecological landscapes operationalised at a village level. |  | Outcome 5 | At least 600 people (100 per district), of which at least 30% will be women, are implementing EbA interventions for climate risk management. At least 46,000 people, including 25,000 of women, in ~100 villages across 6 districts benefitting from reduced vulnerability to climate change |  | 2.1) During the reporting period the Project identified relevant "immediate support" priority interventions requested by the target population (based on the focus group discussions in 3 target districts in 2021). 9 priority interventions has been implemented ( such as livestock bridge restoration, landslide prevention, and water provision, etc.) . 2.2) The proejct has drafted 14 community Watershed Action Plans during the reporting period which will be finalized in early 2023. The WAPs will provide an agreed planning framework for implementation of IWM using CC resilient EbA at community level. Preparation of WAPs has been constrained / delayed by limited in-country experience and dta collection challenges. 2.3) During the reporting period the planning framework/on-ground implementation mechanism (i.e. WAPs) and the modality for implementing an integrated set of village EbA/SLM/CA interventions via the WAPs have been identified (2 consortiums of mixed national and international service providers). The procurement process for contracting the required services of 3.5 year duration has been initiated (development of 2 TORs and UNDP tender documents for north and south parts of the KBR). Completion of contracting servise providers is envisaged in 1st half of 2023. | MS
| Outcome 3. Existing knowledge management platforms supported for integrated catchment management and EbA. |  | Outcome 3 | By the end of the project at least 1 knowledge centre has been strengthened |  | In 2022, the Project continued to support the web-site of the Committee for Environmental Protection under the Government of the Republic of Tajikistan and subsequent use of the platform to further disseminate information regarding the EbA. The District Analysis and District Profiles have been drafted and submitted to CEP for review and approval for dissemination to the local governments of 6 target districts in 2023. The two documents will be as a reference hand-book for local districts. | S
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Muhiba Rabejanova
| Email: | muhiba.rabejonova@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
In 2022, the Project has initiated considerable advances both in terms of its technical fucus and clarity of direction and it’s on ground impact. Under Component 1 the project has initiated efforts to fill still existing gaps in understanding of the status of water sector reforms in the Kofirnighan river basin and to reach out to key stakeholders. For example a study of the situation was undertaken in order to identify intervention opportunities and a Coordination meeting was held in order to coordinate the activities of the Project with other donors in the field of Water Sector Reform and gain understanding of current trends in this sphere, with participation of 32 (15.6% women) representatives of government, international organizations and NGOs. Activities related to piloting multi hazard climate risk modelling and Ecosystem services valuation, both new approaches in Tajikistan, were initiated. During the reporting period the project team also delivered trainings on building resilience and adapting to the consequences of climate change for small scale farmers and pastoralists at jamoat level in 3 target districts with active participation of 97 people (31.9% women). Two trainings on gender and gender mainstreaming have been conducted by the Project Team. The first round of training has been held for the project staff and trainers who will work in the target jamoats to increase their level of knowledge on gender. The second training was organized for the staff of implementing partners and stakeholders such as Committee for Environmental Protection under the Government of the Republic of Tajikistan, Ministry of Energy and Water Resources, Agency for Land Reclamation and Irrigation. In terms of Component 2, very extensive and in-depth field work has been undertaken to develop 14 jamoat Watershed Action Plans (that include systematic evaluation of threats, root causes, and solutions to watershed management/livelihood issues in a CC context, and subsequent programs to address these both in long term and in short term with project support through EbA interventions) have been drafted. These will be finalized in early 2023 ready to be used by the consortium of organizations which will be recruited in 2023 to initiate implemention of them in target jamoats. TORs and relevant procurement documentation for this purpose have been developed during the reporting period. While the planning for the jamoat / village level has been ongoing, the project has initiated on ground support through 9 priority support interventions that were identified by the communities during previous in-depth consultations by the project national field consultants. The main purpose of these interventions is to build immediate project/community collaboration as a basis in future for more systematic EbA program implementation under the WAPs . The total number of beneficiaries of the interim interventions is 818 (direct) and 15505 (indirect) with an impact on approx. 100 hectares of land. The project team conducted 6 focus group discussions to increase the level of knowledge of project beneficiaries and local activists related to the issues of strengthening resilience to climate change among small farms and pasture users and to determine the initial assessment and to plan practical activities in 6 target jamoats reaching 125 people in total (42.4% women). Under Component 3 the project has continued to support the development and content of the CEP website and development of effective monitoring / impact tools (including a dedicated project GIS desined to support both planning/implementation and impact monitoring). However, the project has faced significant challenges and delays and is behind schedule in terms of meeting its key Component 2 outputs and targets within the duration of the project. The improved technical capacity of the project has shown that past progress of the project was not adequate in terms of providing an sound basis for meeting outputs and targets. As a result extensive works to fill remaining gaps in data and analysis of many key issues (the water sector reform situation, data and analysis of target jamoat need for WAP development, etc). In the context of the water sector reform context, WAP development / EbA , Ecosystem valuation, etc. the project has faced challenges to identify and recruit technically strong national consultant due to the limited in country experience with these issues. Additionally, there have been significant managerial and finance/administrative challenges due to staff capacity constraints, UNDP CO restructuring in 2021/2022, and the limited experience within the Project and UNDP Tajikistan with NIM execution. Thus, in its current timeframe/duration the project is unlikely to meet the outputs and targets under Component 2 which is therefore given an MU rating. For this reason the project has an overall Marginally Satisfactory (MS) rating for the 2022 PPR.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 1. Catchment management strategy to manage climate risks operationalised at raion (district) and jamoat (sub-district) levels in Kofirnighan River Basin (KRB). |  | Outcome 2 | By the mid of the project, at least 30 staff from local government at raion and jamoat levels (of which at least 30% are women) trained on integrated catchment management. By the end of the project, at least 100 staff from local government at raion and jamoat levels (of which at least 30% are women) trained on integrated catchment management. |  | 1.1) The Project has hired national experts to conducted gap analyses and research to clarify baseline situation, Potential capacity and software to conduct the modeling has been identified. Planning for pilot modelling of MHCRM in 2 pilot watersheds in the upper KBR has been made for 2023 and TOR for additional support of an international consultant to do this developed. 1.2) The Project completed a feasibility analysis of the chosen weather stations for upgrading throughout the reporting period. To modify the operations for modernizing Weather Stations with Hydromet, the Project team has held discussions with the Agency for Hydrometeorology. During the reporting period, the equipment acquisition procedure for modernisation began. 1.3) A review to clarify the baseline situation in terms of Water sector reform progress in the KBR undertaken and revealed assuimptions made in Prodoc. incorrect (i.e. reform progress is not well advanced in terms of RBOs/RBC and other key elements. Additionally, Catchment management strategy is not a priority need (but finalization of KRB Management plan is). Study also revealed widespread lack of understanding or awareness of WSR concept or state policy. 97 representatives of various local governments, the local population, and Water Users Associations in 6 target districts participated in trainings on mainstreaming climate risks for integrated catchment management during the reporting period, which was conducted by the project team in collaboration with local consultants. 1.4) In order to evaluate the existing situation and pinpoint any shortcomings, the Project facilitated a coordination meeting on the water reform sector throughout the reporting period. Participants included representatives from several international organizations and governmental organizations, including the Ministry of Agriculture and the Ministry of Energy and Water Resources. 1.5) The project has hired an international and national expert to undertake a pilot ESV exercise in the upport KBR and capture lessons/make recommendations for future (as an initial basis for future PES modelling if viable). The ESV will be piloted in two target watersheds in 2023. Significant delays in implementation due to difficulties to recruit suitable national consultant. | MS
| Outcome 2. An integrated approach to building climate resilience of agro-ecological landscapes operationalised at a village level. |  | Outcome 5 | At least 600 people (100 per district), of which at least 30% will be women, are implementing EbA interventions for climate risk management. At least 46,000 people, including 25,000 of women, in ~100 villages across 6 districts benefitting from reduced vulnerability to climate change |  | 2.1) During the reporting period the Project has initiated on-ground support in target districts through implemention of 9 priority interventions ( such as livestock bridge restoration, landslide prevention, and water provision, etc.) . 2.2) During the reporting perio the proejct has drafted 14 community Watershed Action Plans d which will be finalized in early 2023. The WAPs will provide an agreed planning framework for implementation of IWM using CC resilient EbA at community level. Preparation of WAPs has been constrained / delayed by limited in-country experience and dta collection challenges. 2.3) During the reporting period the planning framework/on-ground implementation mechanism (i.e. WAPs) and the modality for implementing an integrated set of village EbA/SLM/CA interventions via the WAPs have been identified (2 consortiums of mixed national and international service providers). The procurement process for contracting the required services of 3.5 year duration has been initiated (development of 2 TORs and UNDP tender documents for north and south parts of the KBR). Completion of contracting servise providers is envisaged in 1st half of 2023. | MS
| Outcome 3. Existing knowledge management platforms supported for integrated catchment management and EbA. |  | Outcome 3 | By the end of the project at least 1 knowledge centre has been strengthened |  | In 2022, the Project continued to provide support for the Committee for Environmental Protection's website and its subsequent usage as a platform for the wider dissemination of EbA information. For assessment and approval by CEP, the District Analysis and District Profiles have been prepared in preparation for distribution to the local governments of the six target districts in 2023. The two volumes will serve as a manual of references for regional districts. | S
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Giyosiddin Nemonov
| Email: | giyosiddin.nemonov@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
At the end of the previous reporting period the project recruited an international Technical Adviser who undertook a review of the project progress and exist situation in the KBR and, on that basis, has provided a revised and more detailed concept and approach for achieving the project expected results. During the Project reporting period, based on this guidance, the project has initiated significant works under Component 2 to develop 14 jamoat Watershed Action plans (WAPs) in the 6 project target districts which will provide the agreed planning framework for on-ground implementation of integrated watershed management to build CC resilience using EbA interventions at community level. Additionally, in consultation with the UNDP CO, a realistic modality for the implementation of the WAPs has been agree (the recruitment of 2 consortiums made up of national and international service providers) to implement WAPs in northern KBR jamoats and southern KBR jamoats respectively (upper watershed and lower watershed). Consequently, the project national consultants have undertaken extensive field assessment and consultations in order to prepare the jamoat WAPs under the overall technical supervision of the international technical adviser. The consultants completed data collection of three Northern target Districts, Varzob, Vahdat and Faizobod, and started collecting data and conducting gap analysis in three Southern target Districts, Qubodiyon, Shahritus and N. Khusrav. During the analysis, economic, social, hydrological, ecological and climatic data were collected by the specialists in the above-mentioned districts from the main stakeholders, such as district local authorities, pasture users, water users’ associations, dehkan farms and local public organizations. Also, statistical information of Qubodiyon, Shahritus and N. Khusrav districts (population, vulnerable farms, women's farms, labor migrants, animal husbandry, community passports, implemented projects, pasture infrastructure, number of associations of pastures and water users, land and water management, presence of disaster risks, natural and climatic indicators affecting the basin level) were fully analyzed and collected. 14 draft jamoat WAPs were prepared and translated and following detailed review and revision, plus consultation with jamoat stakeholders, are planned to be finalized in the 1st Quarter of 2023. Additionally, draft TORs and relevant procurement documents were developed for the implementation of the WAPs and contracting process is expected to be completed in the 1st half of 2022, and WAP / EbA interventions implementation at village level commencing mid 2022. During the reporting period nine priority interventions identified previously be the project target communities were completed. The interventions include: water provision, bridge renovation and landscape restoration. In the context of Component 1 six trainings were held in March 2022 to increase the knowledge and raise awareness of the population in target communities about the integrated water and land resources management, and to strengthen the cooperation mechanisms with of the working groups of the organizations working in the Kofarnihon River Basin. Total of 97 people (31.9% women) participated in the trainings. On June 23 of this year, within the framework of the project, a round table was held on the topic "Water Sector Reform of the Republic of Tajikistan and management of water resources in the Kofarnihon river basin", in which representatives of ministries and departments, scientific and higher institutions of the Republic of Tajikistan, local executive bodies of state power and international organizations participated. At the round table, the issues of water sector reform in the Republic of Tajikistan and the analysis of the situation of the Kofarnihon river basin, the development and implementation of a water action plan as a water basin management mechanism in the Kofarnihon river basin, as well as the experience, problems and activities of associations of water users and other basin organizations in the management of water resources were discussed locally. Total of 32 people (15.6% women) participated at the round table meeting. Additionally, a review of the current progress and awareness of the water sector reforms in the KBR was undertaken in order to better understand the actual progress in this regard and identify strategic opportunities for the project to target its support most effectively to the practical implementation of these reforms (in collaboration with the key sector actors including Ministry of Energy and Water management and key donor agencies such as WB, USAID, and others). During the reporting period two trainings on gender and gender mainstreaming have been conducted by the Project Team. The first round of training has been held for the project staff and trainers who will work in the target communities to increase their level of knowledge on gender. The second training was organized for the staff of implementing partners and stakeholders such as Committee for Environmental Protection under the Government of the Republic of Tajikistan, Ministry of Energy and Water Resources, Agency for Land Reclamation and Irrigation. The project has faced considerable challenges during 2022. As a result progress has not been according to the expected schedule, particularly in regard to the WAP development. This was largely due to the increased technical needs, very extensive level of fieldworks required, and the difficulty to access data from local authorities. Additionally, there have been administrative and financial constraints and delays due ongoing development of project management experience for implementing nationally executed project modality. The project has also faced significant challenges in the recruitment of technically strong national consultants given the limited in-country experience with the issues involved. This has particularly impacted the timeliness of the water sector reform in the KBR analysis and recruitment of the ESVAL national consultant. It has also impacted the timeliness/quality of the WAP preparation process. Planning to address these limitations and constraints is being undertaken in consultation with the UNDP CO.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1. Catchment management strategy to manage climate risks operationalised at raion (district) and jamoat (sub-district) levels in Kofirnighan River Basin (KRB). | Number of staff trained to respond to impacts of climaterelated events (gender disaggregated). | 0 | 0 | By the end of the project, at least 30 staff (of which at least 30% are women) trained on integrated catchment management. By the end of the project, at least 100 staff (of which at least 30% are women) trained on integrated catchment management.
Output 1.1. Multihazard climate risk models (MHCRMs) developed for target watersheds in the KRB | Number of risk models developed. | 0 | The Watersheds for piloting two MHCRM have been identified. The risk models will be developed in 2023 | Gap analysis conducted for KRB that details climate risks for all watersheds. By the end of the project, at least one MHCRM developed for each watershed in the KRB (and each target district).
Output 1.2. Providing support for establishing automated weather stations in KRB sub-catchments to provide data for refining the multihazard climate models [developed under Output 1.1]. | Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis. | Currently, weather stations do not provide upto-date and relevant information in a timely manner to inform climate risks. There is limited delivery of climate information to local communities. | The procurement for rehabilitation of three weather stations started | Policy- and decisionmakers in KRB receive forecasts from Hydromet. By the end of the project, policy- and decisionmakers in KRB receive forecasts and downscaled national climate information every quarter from Hydromet. By the end of the project, local communities in the project interventions sites receive tailored climate information packages.
Output 1.3. Integrated catchment management strategy developed for the KRB. | Integrated catchment management strategy developed. Number of staff trained (gender disaggregated). Number of community members trained (gender disaggregated). | 0 | No good rationale for development of RB Strategy given this is not part of existing water sector reform and not required by stakeholdes. Focus will be instead on support to KRB Management Plan as this is planning instriment for MEWM, CEP, RBO and RBC. Project will consult with key stakeholders in 2023 and provide agreed support as viable within budget. | By year 3 of the project, at least 30 staff (of which at least 30% are women) trained on integrated catchment management across all target departments. By the end of the project, at least 100 staff (of which at least 30% are women) trained on integrated catchment management across all target departments. At least 100 community members in each district (of which 30% are women) trained on identification of suitable EbA interventions (600 people in total)
Output 1.4. Strengthened coordination and training mechanisms for integrated climate-resilient catchment management. | Number of interactions between relevant stakeholders | 0 | 1 | By the end of the project, at least 2 meetings are held per year between different government sectors, RBOs, district authorities etc.
Output 1.5. Payment for Ecosystem Services (PES) models to support the long-term financing of integrated catchment management strategy implementation | Number of PES models developed for the KRB | 0 | 0 | By the end of the project, at least 1 PES model developed and at least one policy brief submitted to government detailing the model.
Outcome 2. An integrated approach to building climate resilience of agroecological landscapes operationalised at a village level. | Number of people practising climate change adaptation technologies (gender disaggregated). Total number of men and women benefitting from reduced vulnerability to climate change | 0 | XX direct benefitiaries of EbA related interventions (818 direct and 15505 indirect beneficiaries of all "priority support"interventions) | At least 600 people (100 per district), of which at least 30% will be women, are implementing EbA interventions for climate risk management. At least 46,000 people in ~100 villages across 6 districts benefitting from reduced vulnerability to climate change
Output 2.1. Agroecological extension services supported at the jamoat level to provide technical support for EbA implementation. | Number of extension service providers trained. | 0 | 0 | At least 1 private extension service provider in each target KRB district supported
Output 2.2. Watershed Action Plans (WAPs) developed that promote climate resilience and enhance economic productivity for target communities | Number of WAPs developed. | 0 | 14 WAPs drafted (to be finalized in 1Q 2023) | By the end of the project, at least 1 WAP developed in each of the 14 target jamoats.
Outcome 3. Existing knowledge management platforms supported for integrated catchment management and EbA | Knowledge management centre strengthened through the support of project activities | 0 | 1 | By the end of the project at least 1 knowledge centre has been strengthened.
Output 3.1. Existing knowledge management platforms supported for collating information on the planning, implementation and financing of EbA interventions | Existing knowledge centre/ platforms/ hubs in Tajikistan are supported and include information and data on KRB and specifically climate risk information. | Climate change research is not coordinated within the KRB and across Tajikistan. Knowledge generated through projects is not collated, shared | 1 | By the end of the project at least 1 knowledge centre has been strengthened.
Output 3.2. An impact evaluation framework (IEF) to enable effective adaptive management of EbA activities. | Evaluation of EbA interventions in target sites conducted. | Several projects have undertaken activities on climate change adaptation within Tajikistan. However, none of these activities have been evaluated according to their impacts for communities. | Not yet available (pending EbA implementation) | By the end of the project, an IEF will be developed that details the process of evaluating the impact of implemented EbA measures on communities.
Note on G14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In my understanding some of the "priority" interventions are not directly related to demonstration of EbA. For example repair of bridges etc. I think for reporting here you need to sub-divide those interventions (and beneficiaries) with clear EbA relevance and only count them in this cell.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | During 2022 a significant review and adjustment of project technical implementation approaches was made which has positively impacted the oerall strategic approach to achieving overall outputs and targets. However, it has also necessitated the instigation of additional baeline and planning works. An important lesson learned is the need for experienced tehnical input during the project inception phase in order to ensure clear technical implementation strategy and roadmap. A 2nd lesson is the need to realistically budget time when collaborating and supporting rural authorities and communities.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Delays have occured in implementation of a number of key activities, specifically WAP development, water sector reform anaysis, ESVAL / PES, etc. These have been challenging due to limited availability of national technical expertiese in many issues, difficulty of collecting data in rural authorities, etc. The project has faced additional constraints in terms of timely completion of admin/finance procedures and support from UNDP CO during during 2021/22 restructuring. Delays have implications in terms of sufficient time for effective implementation of nature based EbA interventions (that require multiple years/seasons to meaningfully implement). With the support of the scheduled MTR the project and UNDP Co will implement actions needed to address causes of delays and mitigate impact.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No changes have been made to projetc outputs, outcomes or activities. Project Results Framework has not been changed. Significant adjustments have been made to project technical approach and road map to achieving project results
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | N/a
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender equality has been applied in the developed ToRs for recruitment of new staff or procurement purposes. Balanced gender representtion has been assured during community consultation and training activities. A project overall gender strategy has been developed. A gender analysis, and inclusion of gender sensative indicators/expected results, have been incorporated into all 14 draft jamoat Watershed Action Plans
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | TJK/MIE/Rural/2018/1
Implementing Entity | UNDP
Type of implementing entity | MIE
Country | Tajikistan
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 874000 | 46000 | 828000 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 49.73% | 54.35% | 49.47% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage |  | 6 | 3: Dissemination and communication | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total | 100 | Disaster risk reduction | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted | 30% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
[6 empty] | 30 | 30% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 |  |  |  | 1 | Technical guidelines | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer |  |  |  | Catchment area/Watershed/Aquifer | 1500 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
[6 empty] | 600 | Agricultural-related
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
[6 empty] | 46000 | Agricultural-related
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness