Gender and Youth Strategy and Action Plan       for Dairy Modernization and Market                                                     Access Program (DiMMA)2020-2023

2020

Ekaterine Gurgenidze

Gender Specialist

IFAD/AF /Georgia

Contents

Abbreviations and Acronyms	3

1.	Introduction on Project Gender Strategy	4

2.  Overview Georgia Legislation on Gender and Youth	5

3. Gender and Youth   Mainstreaming In IFAD	6

4. Gender Mainstreaming in Adaptation Fund	7

5. DiMMA Project Overview	8

6. Objectives and Activities of the Gender Strategy	11

6.1. Objectives	11

6.2 Rationale:	14

6.3 Gender-Responsive consultations	14

7. Program Overview from the Gender Perspective	16

8. Rationale FOR A YOUTH STRATEGY	19

Representation and engagement of youth in agricultural activities	19

9. Project Implementation Arrangements and	20

Responsibilities of project Gender Specialist	20

9.1 Some Key AF gender considerations during project implementation are:	22

9.2 AF Gender Monitoring Considerations	23

9.3 AF Gender Project Completion Evaluation Considerations	24

Responsibilities and tasks of Gender Specialist	26

Gender and Youth Action Plan	28

ANEXX 1	33

Main Findings from the Project Baseline study	33

1. Gender aspects of target population	33

611 Decision-making process in households	33

1.2 Socio-economic status of women	34

1.3	Distribution of functions in the household	35

1.4 Involvement of women in agriculture	36

1.5  Ownership of household assets and decision-making process	36

1.6 Involvement in various activities and accessibility	37

ANEXX 2	39

ANEXX 3	0

IFAD Gender checklist for programe design	0

# Abbreviations and Acronyms

| ACDA | Agricultural Cooperatives Development Agency |
| --- | --- |
| AMMAR | Agricultural Modernization, Market Access, and Resilience |
| AF | Adaptation Fund |
| AI | Artificial insemination |
| RDA | Rural Development Agency |
| AMP | Agriculture Mechanization Project (USAID) |
| BP | Business Plan |
| CBSP | Capacity building service provider |
| CC | Climate Change |
| CSVC | Climate smart value chain |
| DCFTA | Deep and Comprehensive Free Trade Agreement (EU) |
| DVCF | Dairy Value Chain Development Facility |
| ENPARD | European Neighbourhood Programme for Rural Development |
| EU | European Union |
| FLSP | Farm level service provider |
| FAO | Food and Agriculture Organization of the United Nation |
| FBS | Financial Brokering Specialists |
| FI | Financial Institution |
| GAP | Good agricultural practices |
| GDP | Gross Domestic Product |
| GEF | Global Environment Fund |
| GEL | Georgian Lari |
| GoG | Government of Georgia |
| Ha | Hectare |
| HACCP | Hazardous Analysis and Critical Control Points |
| HH | Household |
| IFAD | International Fund for Agriculture Development |

# DIMMA Gender and Youth Strategy

# Action plan

# Introduction on Project Gender Strategy

Women's role in agriculture worldwide is indisputable. Women produce more than half of all food grown worldwide (FAO updated) and play a fundamental role in the agricultural and rural economies in all developing countries, with the roles varying considerably between and within the regions. Women in Georgia have a specific role in livestock production, focusing on dairy products' milking and processing.

However, women are confronted with specific challenges that limit their ability to thrive in this sector. Development programs need to develop specific opportunities and targeting mechanisms to engage women and ensure their access to the Program's activities and a possibility to share benefits. The gender strategy aims to move women further up the value chain, engaging them in processing products, management and ownership, and marketing. To this end, investing in women’s knowledge development and leadership is crucial.

DiMMA Gender Strategy aims to integrate gender issues in each stage of the project cycle and develop concrete activities to empower women and the young generation. It will demonstrate how the project will meet women's and young people's needs, along with the dairy VC. The detailed targeting mechanism will be developed and determined by this document.

The strategy is aligned with the general framework for gender equality and youth indicated in the project design document. The gender strategy is informed by on DiMMA project design document. On baseline study, Dairy VC analysis from Gender perspective and survey questioner was developed to discover gender-based roles, opportunities, and challenges along the Dairy Value Chain to determine the women's role in the livestock sector and assess their access to information, resources, and new technologies. Identify specific obstacles to the growth of their production and productivity, and define areas where they would need specific support from the Programm to get and develop a grant scheme.

The results and findings from questioners will be reviewed below in this document, and the facts obtained from the baseline study on gender roles along the dairy VC will be reviewed.

# 2.  Overview Georgia Legislation on Gender and Youth

##### Gender

In 1994, Georgia ratified the United Nations Convention on the Elimination of All Forms of Discrimination against Women (CEDAW). Gender equality is reflected in the Georgian Constitution and numerous laws, policies, strategies and action plans. These include, but are not limited to, the Human Rights Strategy, the Gender Equality Law and its action plans, the Anti Domestic Violence Law and its action plans, the Anti Trafficking Law with relevant action plans, the Action Plan on Women, Peace and Security, and finally the Labor Code.

The Gender Equality Council of the Parliament of Georgia, the body authorized to ensure the coordination and monitoring of the implementation of the Gender Equality Law and Action Plan for Gender Equality, has been tasked with performing an analysis of the legislation from a gendered perspective. Parliament should also suggest amendments and actions to accelerate the achievement of gender equality, as well as monitor and evaluate progress towards achieving gender equality.

The 2018-2021 Regional Development Programme of Georgia is based on the EU-Georgia Association Agreement, establishes five priorities, mentions gender equality, and social inclusion as one of its objectives.

The 2016-2020 Small and Medium-sized Enterprises (SME) Development Strategy of Georgia and its Action Plan were adopted, followed by reports on its implementation in 2016, 2017 and 2018.418 The strategy envisages support for vulnerable groups and women. Indeed, special trainings were provided for them, together with establishing a special sub-council to promote women’s entrepreneurship within the Private Sector Development Advisory Council.

Georgia Ministry of Environment and Agriculture (MEPA) has two strategic document, one is The Strategy of Agricultural Development of Georgia 2015-2020 provides a vision for the development of the agricultural sector in Georgia. The strategy mentions gender in two out of seven directions:

Direction 1 – increasing the competitiveness of those employed in the agrarian sector, and Direction 2 – institutional development.

Another document of the MEPA is Rural Development Strategy 2017-2020 Georgia’s was developed with the assistance of ENPARD, UNDP and FAO and includes the improvement of social conditions and living standards as one of its three priorities. Objective #3 of this priority area highlights the increasing involvement of the local population (especially youth and women) in identifying local needs and determining the solutions for said needs. This objective is to be implemented by the LEPL Public Services Development Agency by holding at least six events related to women’s rights and gender equality as well as 10 information meetings.

According to the 2020 Global Gender Gap Report, Georgia ranked 61 (0.70 score) among 153 countries according to how well they use “their female talent pool, based on economic, educational and health.

##### Youth

The Georgian National Youth Policy Document was approved in 2014 year by the parliament of Georgia.

The Youth Policy is a conceptual document. Government of Georgia acknowledges that Gender Equality and human rights are core values underlying young people’s sustainable development, therefore, is committed to mainstream equality principles in each governmental action carried out about the young people. In order to achieve this goal, the Youth Policy encompasses following priorities:

1. Creating opportunities for the youth to be involved in social, economic, cultural and political life;

2. Creating opportunities for appropriate and high quality education, worthy employment and professional growth for the youth;

3. Establishing a healthy lifestyle and improving access to and quality of the healthcare services provided in the youth friendly environment;

4. Increasing awareness among young people on the civil rights and responsibilities, and creating a safe and secure environment for young people, protecting their rights and supporting the young people with special needs.

# 3. Gender and Youth   Mainstreaming In IFAD

The Policy on Gender Equality and Women’s Empowerment will be central to the attainment of the overarching goal of the IFAD Strategic Framework 2011-2015: enabling poor rural women and men to improve their food security and nutrition raise their incomes and strengthen their resilience. This will be achieved through three strategic objectives:

• Strategic objective 1: Promote economic empowerment to enable rural women and men to have equal opportunity to participate in, and benefit from, profitable economic activities.

• Strategic objective 2: Enable women and men to have equal voice and influence in rural institutions and organizations.

• Strategic objective 3: Achieve a more equitable balance in workloads and in the sharing of economic and social benefits between women and men.

Gender Mainstreaming for IFAD projects all over the world are designed according to these three strategic objectives.

“Enhancing impact in the Sustainable Development Goals (SDGs) by empowering rural young women and men” – IFAD’s theory of change.

The First IFAD’s Rural Youth Action Plan (IFAD, 2018c) sets out the framework and guides youth-sensitive agriculture and rural development investments at IFAD. The Rural Youth Action Plan has clear targets that all country strategies and 50 per cent of IFAD new project designs between 2019 and 2021 will be youth-sensitive, and 70 per cent of new project designs are to be youth-sensitive by the end of the Thirteenth Replenishment of IFAD’s Resources in 2027.

IFAD’s pro-youth interventions will foster youth economic empowerment through a comprehensive menu of strategic directions, key themes and action areas. Strategic directions comprise:

(i) business development services; (ii) investments in mechanization and the use of modern technologies, including information and communications technology; (iii) vocational and technical training; (iv) actions targeting youth including credit/equity financing for youth-owned enterprises and start-ups, innovative use of migrants’ remittances to spur investment in rural youth, agricultural risk management and involving youth as stakeholders in farmers organizations, youth associations and cooperatives; and (v) engagement with governments and youth for conducive policy frameworks.

# 4. Gender Mainstreaming in Adaptation Fund

The Adaptation Fund (AF) is an international fund that finances projects and programs aimed at helping developing countries to adapt to the harmful effects of climate change. It is set up under the Kyoto Protocol of the United Nations Framework Convention on Climate Change (UNFCCC). The AF’s principles-based Gender Policy (GP), and Gender Action Plan aims at mainstreaming gender and ensuring that projects and programmes supported by the Fund provide women and men with an equal opportunity to build resilience, address their differentiated vulnerabilities and increase their capability to adapt to climate change impacts.

The Fund’s gender policy has the following objectives:

- To ensure that the Fund will achieve more effective, sustainable and equitable adaptation outcomes and impacts in a comprehensive manner in both its internal and external procedures;

- To provide women and men with an equal opportunity to build resilience, address their differentiated vulnerability, and increase their capability to adapt to climate change impacts; recognizing the need for targeted efforts in order to ensure women’s participation.

- To address and mitigate against assessed potential project/programme risks for women and men in relation to concrete adaptation actions financed by the Fund; and

- To contribute to addressing the knowledge and data gaps on gender-related vulnerabilities and to accelerate learning about effective gender-equal adaptation measures and strategies

- To consult with affected women and men actively, taking into account their experiences capabilities and knowledge throughout Fund processes.

# 5. DiMMA Project Overview

The Dairy Modernization and Market Access (DiMMA) Programme aims at rural economic development and poverty reduction by contributing to the modernization and emergence of a competitive, diversified, resilient and sustainable dairy industry.

Goal: DiMMA’s goal is rural economic development and poverty reduction by contributing to modernization and emergence of a competitive, diversified, resilient and sustainable dairy industry.

Objectives: The development objective is to enhance the livelihoods and resilience of smallholder dairy producers, especially in mountain areas, and improve the management of the natural resources on which they depend.

Project duration: The duration of the programme will be 6 years.

Project outreach: DiMMA will: (i) provide 6,740 target households with better access to services, inputs and markets. Of these, 4,220 will be linked to dairy VCs through profitable partnerships with aggregators, 370 will be employed in new jobs for youth and women in the small enterprises developed in the programme area, 250 youth will start non-extractive livelihood activities and 1,900 will benefit from improved productivity of pastures;

(ii) support the development of 121 small enterprises (75 aggregators and 46 farm level service providers) leading to the capacity to process 240 tons of milk per day in the programme area; and

(iii) bring 9,500 Ha of land under climate resilient management. In addition, DiMMA will have 9,880 indirect beneficiaries. Of these, the rehabilitation of 300 kilometers of pasture roads will indirectly benefit 5,000 households and the small enterprises will provide indirect benefits to 4,880 households.

Key impact indicators: The key impact indicators are: (i) 10% farmers reporting increase in milk production in Georgia; (ii) at least 30% increase in the monthly income of target households by the end of the project; (iii) 90% of the target households reporting increase in productivity and production of dairy products; and (iv) 100% increase in the volume of milk processed by aggregators in the project area.

DiMMA is supported by grant from the Adaptation Fund to help mainstream climate change adaptation into the IFAD project. The goal of the AF financing is to reduce the vulnerability of the dairy value chain to the deleterious impacts of climate change, and with the objective to enhance the resilience to climate change of vulnerable dairy producers.

The programme is to be implemented in six contiguous regions of Georgia :Imereti, Samegrelo-Zemo Svaneti, Samtskhe-Javakheti, Kakheti, Racha-lechkhumi and Qvemo Kartli.

The programme has two principal and inter-related technical components. The first component will target the development of the dairy value chain from production to marketing; the second will support institutional and organizational development.

Component 1: Dairy Value Chain Development with two sub-component:

  - Sub- component- Demand driven demonstrations of dairy production & business models will support partnership between progressive dairy producers and aggregators, linking progressive farmers to aggregators; demonstration and dissemination of technologies and business models; Capacity building of value chain actors by training of small dairy producers, farm level service providers and aggregators, training of AI technicians.

  - Sub-component –Strengthening stakeholder linkages to the dairy value chains will support in selection of innovative technology and business models adopters; Seed capital financing will be extended to assist smallholders who are interested in adopting these improved models and partner in the dairy VCs; under this component project will implement Marketing development support, support in branding and differentiation of premium mountain dairy production;  Business and technical coaching ; Building capacities of specialized privet Capacity Building Service providers; Pasture Development; Marketing infrusturcter development in mountain pastures;

Component 2: Institutional and organizational development with two sub-component:

2.1   Sub-component – Community mobilization and stakeholder organization; DiMMA will form stakeholder platforms comprising representatives of all types of cluster stakeholders with the objectives to suggest and endorse potential beneficiary farmers, processors and service providers who meet the eligibility criteria of the programme, in particular young people and women; DiMMA will also develop FOs with emphasis on strengthening PUAs. The PUAs will be supported to design, develop and implement community-based Pasture Management Plans (PMP) that integrate EU approximation requirements as well as adaptation to climate change and disaster risk-reduction (DRR) measures to increase the resilience of this sector.

2.2    Sub-component – Policy dialogue, DiMMA will support the MEPA to establish a National dairy policy dialogue forum, which will be convened by MEPA, supported, and serviced by the programme. The forum will gather representatives of Government, producers, Georgian Farmers’ Association; national level service providers; processors, research institutions; NGOs and donors.

DiMMA’s benefits will reach three categories of VC actors comprising;

- smallholder dairy producers linked to programme supported dairy VCs and Pasture Users’ Associations (PUA), market vulnerable producers and  progressive producers;

- farm level service providers (FLSPs), assisted to supply the dairy producers with inputs and services required to improve production;

- dairy aggregators, supported to form market linkages with the dairy producers.

Areas of project interventions: a) Matching Grants; b) Trainings and Demo plots; c)

Within each of these categories, DiMMA will have special focus on the inclusion of women and youth and 3,518 (52%) of individual beneficiaries will be youth and 3,370 (50%) will be women. Only one member per household will be eligible for programme support related to seed capital financing.

# 6. Objectives and Activities of the Gender Strategy

### 6.1. Objectives

The project is developing a gender strategy, which is defined by the PDR. This document will guide the project on gender and youth interventions that can increase women's incomes to enhance their decision-making and empowerment. DiMMA Gender Strategy aims to integrate gender issues in each stage of the project cycle and develop concrete activities to empower women and the young generation, to move women further up the value chain. It will demonstrate how the project will meet women's and young people's needs, along with the dairy VC.

DiMMA's benefits will reach three categories of VC actors comprising; below is described the septs project will take for women active participation under each category of the program.

(i) 4,220 smallholder dairy producers linked to programme supported dairy VCs and Pasture Users' Associations (PUA) - consisting of 3,900 (92%) market vulnerable producers and 320 (8%) progressive producers (explained later);

Project intervention:

- Increase women's participation in malty stakeholder meetings in order to raise their voice on specific issues.

- Develop grant program with discount rate to attract women beneficiaries.

- Create and develop a training program according to women and youth's needs. The training should also be conducted in a suitable location for participants (all relevant information on training are in survey reports on VC Analyze from Gender Perspective).

(ii)   46 farm level service providers (FLSPs), assisted in supplying the dairy producers with inputs and services required to improve production;

Project intervention:

- Develop grant program with discount rate to attract women beneficiaries.

- Create and develop a training program according to women and youth's needs. Also, the training should be conducted in a suitable location for participants.

- Seventy-five dairy aggregators supported to form market linkages with the dairy producers. An additional 620 non-commercial rural households will benefit from 250 pilot non-extractive livelihood projects and employment in 370 jobs created by 121 small enterprises supported by the programme. Within each of these categories, DiMMA will focus on the inclusion of women and youth, and 3,518 (52%) of individual beneficiaries will be youth, and 3,370 (50%) will be women. Only one member per household will be eligible for program support related to seed capital financing.

Project intervention

- Develop grant program with discount rate to attract women beneficiaries. Create and develop a training program according to women and youth's needs. Also, the training should be conducted in a suitable location for participants.

Table 1Table 1: Beneficiary outreach table

|  |  | Beneficiary households |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Beneficiary category | Small enterprises supported | New jobs | VC linkage | Non-extractive livelihoods | PUA | Total | Women beneficiaries (number) | Youth beneficiaries (number) |
| Farm level service enterprises | 21 | 21 |  |  |  | 21 | 10 | 21 (100 %) |
| Farm level service providers - Sileage/Hay | 21 | 21 |  |  |  | 21 | 10 | 0 |
| Aggregator enterprises | 75 | 324 |  |  |  | 324 | 162 | 162 |
| Market vulnerable dairy producers |  |  | 3,900 |  |  | 3,900 | 1,950 | 1,950 |
| Progressive dairy producers |  |  | 320 |  |  | 320 | 160 | 160 |
| Non extractive livelihood pilots |  |  |  | 250 |  | 250 | 125 | 250 |
| PUA support |  |  |  |  | 1,900 | 1,900 | 950 | 950 |
| Total | 121 | 370 | 4,220 | 250 | 1,900 | 6,740 | 1,835 | 3,518 |

The table below shows the performance indicators of the project for women’s and youth activities, which is divided by the project components and describes every activity under it.

| Activities | Performance target/Indicators | Responsibility | Timeframe and Deadline |  |  |  |  |  | Budget |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component1. Dairy Value Chain Development with two sub-component |  |  |  |  |  |  |  |  |  |  |
| Outcome 1:Milk production, safety, marketing and profitability of target households improved |  |  |  |  |  |  |  |  |  |  |
| Activity 1.1 |  |  |  | Mid term |  |  |  | End Target |  |  |
|  | Women and youth trained in production practices and /or technologies. | Service Providers | Women 900 Youth 1,800 |  |  |  | 1,500 3,000 |  |  |  |
|  | women trained in income generating activities or business management; | Service Providers | Women 448 Youth 895 |  |  |  | 955 1,910 |  |  |  |
|  | Conduct survey on women’s training needs | Regional Coordinators &Facilitators (in three region) | 60 Interviewer |  |  |  |  |  |  |  |
|  | Analyze grant applications (to underline rejections reasons) In order to take appropriate actions. | GFP | On quarterly Basis |  |  |  |  |  |  |  |
|  | To add precisely steps of action To produce syllabuses with service provider on women’s equality | Service Providers, GFP |  |  |  |  |  |  |  |  |
| Activity 1.2 | women and youth benefiting from seed capital financing; | PIU, RDA | Women 605 Youth 1,210 |  |  |  | 2,235 2,360 |  |  |  |
| Activity 1.3 | Women trained in gender equality issues | PIU, Service providers | Women 605 |  |  |  | 2,235 |  |  |  |
| Component 2. Institutional and organizational development with two sub-component |  |  |  |  |  |  |  |  |  |  |
| Outcome 2. Local dairy initiative cluster and platforms and farmer groups developed/strengthened |  |  |  |  |  |  |  |  |  |  |
| Activity 2.1 | women and youth members in groups supported to sustainable manage natural resources and climate-related risks | Service providers | Women 950 Youth 1,900 |  |  | 1,140 1,900 |  |  |  |  |
| Activity 2.2 | Women trained in gender equality issues | Service provider | Women 950 |  | 1,400 |  |  |  |  |  |
|  | Stakeholder meeting with minimum 30% quarter of women participation | PMU, GFP |  |  |  |  |  |  |  |  |

### 6.2 Rationale:

To rely on the project baseline study, it is evident that there is a real gap in asset ownership, decision-making process, and workload for women in the household. It means that they cannot participate in the business-making process and find financial support from financial institutions. They do not have access to updated information about new agricultural projects in their regions, even in Georgia, and on financial opportunities, such as special grants programs for women.  They spend 25 hours of their time on home activity via a man who spends 10 hours. The central fact is that women think that the distribution of their activity in such a way is quite natural and normal for them.

It is recommended in the first place to start the women empowerment process and create training for gender equality and women's empowerment by the project in all six regions of Georgia.  It helps women and men understand the role gender plays and acquire the knowledge and skills necessary to advance gender equality in their daily lives and work.

With the cooperation of the project Gender Specialist, project service providers will prepare special training courses on women empowerment with relevant curriculum.

According to women's needs, the second level of training will be on knowledge getting in animal husbandry and dairy productions. The questioner survey determined the interesting spheres for women in dairy production.   Service providers should prepare training courses according to the results coming from the questioner.

The third level of training will be designed to develop their agency to find out financial support information. How and where to find relevant information about financial support, loan and grant programs financed by Government and Donor organizations, special programs for women, and s.on. It means creating a database of websites where they will be able to find relevant information.

### 6.3 Gender-Responsive consultations

DiMMA will consult with stakeholders throughout all stages of the project cycle in a gender-responsive And the gender-equal way. Such gender-informed participatory methods are necessary to tackle the critical challenge of underrepresenting either women or men in consultation throughout all stages of the project cycle. Facilitating and actively supporting women's increased participation as essential stakeholders guarantee the inclusion of their often-overlooked needs, concerns, and abilities in project planning, implementation and monitoring, and evaluation.

As both IFAD and the AF's investments are fully integrated, DiMMA will mainstream AF gender consultation requirements to comply with the AF Gender Policy. To help ensure that the project is implemented in a gender-responsive way, the following principles, suggestions, and recommendations on how gender-responsive participation in consultations and training can be ensured:

- Consider consulting with male and female beneficiaries/stakeholders, both separately and in mixed groups. In some cultures, men will not speak about specific issues in front of women and vice versa. When defining priorities or goals for the adaptation intervention, women in meetings or workshops, including both women and men, may defer to men. In women-only groups, women might also have culturally appropriate suggestions on approaching and winning over men to prevent a backlash against women's increased involvement.

- The time and location of consultation meetings is crucial. Women and men might be only available at certain and differing times. The location for meetings should be easy to reach and comfortable for both men and women, some meeting locations might undermine women's participation because they may not be culturally appropriate or women may not be allowed to stay in a public place; transportation and childcare services might have to be provided for women, who are often less mobile, in order to attend meetings.

- Consider appropriate ways of communication. The communication form and media used for information sharing and outreach to both men and women should consider that there are gender differences in access to information technology (availability and use of internet or mobile phones, for example) and literacy. Non-written forms of communication might have to be used (radio, interviewers, picture-based leaflets) to reach the most vulnerable women.

- Consider appropriate meeting formats. Meetings, workshops or trainings may have to be conducted by female staff to increase women's level of comfort to actively participate.

# 7. Program Overview from the Gender Perspective

The program activities, implementation arrangements, and M&E system have been designed in compliance with IFAD Targeting Policy, IFAD policy on gender equality and women's empowerment, and in line with the approaches outlined in the Framework for Gender Mainstreaming in IFAD investment operations.

Support for women engaged in the livestock value chain in Georgia has been provided through different means. Thus, one of women's critical targeting has been through organizing training and awareness for them with HACСP system. Since women play a crucial role in home-based dairy production and processing, it is crucial for those women who would like to continue to be engaged in commercial dairy production to adopt HACCP principles to be able to market, although the investment required for compliance to the new food safety laws will be a significant barrier.

As mentioned earlier, women are mostly engaged in milk processing into yogurt and cheese for their consumption and surplus trade. When household and farm at a larger scale produce milk, it often becomes male-run business. Women often take care of animal health in Georgia, especially in winter. While artificial insemination is still largely men's business, women's role is to recognize when cows are in heat. At the same time, women suffer from lack of knowledge and limited access to veterinary issues, preventive and treatment methods and drugs. There is an overall shortage of veterinarians in Georgia, and especially in remote areas.

Moreover, there are only a few women -veterinarians, who mostly work with pets. That makes women- livestock farmers vulnerable and limits their access to knowledge and skills upgrade. They are rarely engaged in animal health training and programs, which focus mostly on men. Patriarchal traditions often prevent women, especially in remote rural areas to attend such training and to apply to male veterinarians for animal health advice of drug information. At the same time, a growing number of women in Georgia act as de facto para veterinarians. These are women with essential knowledge and skills about animal health, who open simple vet drugs shops from home. They are often a source of information on animal health for other women in the village.

The program will identify such women in target villages and support them, including linking with trained veterinarians and inputs suppliers, engaging them in specialized animal health training and capacity building on business management and financial literacy. These women will be serving as information dissemination agents in target villages. The programme will supply them with informational materials and organize training on issues, which are usually of deep concern for women such as better nutrition, animal health issues, and zoonotic disease prevention. These women para vets will disseminate this information as well as information on food safety requirements and standards.

As discussed earlier, women less often manage and own farms. They often experience various gender-based disadvantages in accessing information, services, and resources, especially financial resources, they need specific targeting efforts within the program to reach and engage them in the livestock value chain.

Women will be encouraged to participate in the VC Clusters to voice women's specific needs and channel concerns to the program. They can form an informal community health sub-committee under the Cluster, which can receive information on food safety, nutrition issues, and prevention of zoonotic diseases. If these issues are identified as a priority in the needs assessment, they will be raised and addressed at the local and regional Clusters.

To attract and support women-led farms and businesses, service provision, and aggregation and processing enterprises, proposals for matching grant support would receive higher scorings in the overall selection process. Since women play an essential role in the livestock sector, the program expects that at least 30 percent of all direct beneficiaries will be women.

Different approaches will be utilized to make the programme's products and services accessible to women farmers and agricultural entrepreneurs. The DiMMA will be utilizing the PMU gender specialist to ensure that gender aspects are reflected in monitoring and evaluation principles that will ensure gender disaggregated data and knowledge will be produced. It is expected that the PMU focal point would dedicate approximately 50 percent of her/his workload to tackle gender-related management aspects in program implementation. Moreover, a gender perspective will be systematically mainstreamed at individual and organizational levels into PMU management from the start via quantitative and qualitative participatory monitoring and evaluation, ad hoc studies, and annual stakeholder review workshops.

The program design document includes all steps to integrate gender issues in the project cycle. The document contains a gender analysis report. The implementation structure of the program includes Gender and Target specialist, with detailed TOR.  In PDR Gender Checklist (see annex 1), exist with detailed objectives.  The project baseline study was developed with sex-disaggregated data.  According to the project, designed document gender perspective will be systematically mainstreamed at individual and organizational levels into PMU management from the start via quantitative and qualitative participatory monitoring and evaluation, ad hoc studies, and annual stakeholder review workshops.

DiMMA Supervisory Mission recommendation

During the first DiMMA supervisory mission in October 2020, introducing more attractive conditions for women were considered. In consideration of the findings of the value chain study and the review of the first round of applications to the grant facility, the supervision mission agreed to lower expected contributions for women in the following categories: MVDPs and PDPs (lowered from 40% to 20%); Non-Extractive Livelihood activities (lowered from 20% to 10%).

These are key to ensure the program can also benefit the most vulnerable beneficiaries such as MVDP, women, and women-headed households and youth.

Targeting of women

According to PDR the program develop a gender strategy regarding interventions that can increase women's incomes, enhance their decision-making and empowerment. Direct targeting and self-targeting measures will be adopted for inclusion of women. Youth (men up to 35 years and women up to 40 years old as it is defined under the on-going AMMAR Programme) will be a target beneficiary in all DiMMA activities.

Table 1: Targeting matrix

|  | Market vulnerable households | Women | Youth |
| --- | --- | --- | --- |
| Geographical targeting | - Programme area with 50% of national cattle herd; above 50% of the national rural population; 99% smallholders as cattle owners; mountainous areas - 50% of target households linked to aggregators & 50% of PUA members must be from vulnerable communities as condition for aggregators and PUAs to receive seed capital and grants. |  |  |
| Self-targeting | - Small size of seed capital financing is attractive only to target households; Labor intensive business models are pertinent to target households; gradual transformation through AI is less attractive to better-off farmers; nearby MCCs, friendly payment system adopted by aggregators suitable for inclusion of target households | - Aggregator level jobs favor employment of women. - FLSP jobs on animal health favor employment of women - Support to niche cheese production will favor self-employment of women. - Adoption of milking machine, etc will reduce drudgery for women. |  |
| Direct targeting | - Aggregators have to develop partnerships with the projected number of target households as committed during BP formulation. | - 30% quota for women for (i) dairy farm-improvement and non-extractive livelihood activities (ii) jobs created by enterprises (iii) (members of) PUAs receiving pasture improvement grants | - 100% youth quota for FLSP entrepreneurs and jobs created by them; non-extractive livelihoods; 50% youth quota for dairy farm improvement; jobs created by aggregators; (members of) PUAs receiving pasture improvement grants |

  - Direct targeting measures for women’s inclusion will involve at least 30% quota reserved for financing women headed households and women managed business out of the total number of: (i) seed capital investments directed to the adoption of improved dairy production systems by target households and adoption of alternative livelihood activities by youth; (ii) jobs created by the small enterprises (aggregators and FLSPs) supported by DiMMA in the programme area; and (iii) PUA members in PUAs selected for grant financing for improving pastures.

  - Self-targeting measures will be driven by the practice of high women’s engagement in milking, processing milk into cheese and other products, local marketing of dairy products and animal care especially when men are in seasonal or long-term migration. DiMMA will provide such women members with technical assistance regarding measures to improve farm level production, adoption of adequate hygienic measures, which will make them more employable in the jobs, created at the aggregator level which generally favor the employment of women. Similarly, training related to animal health improvement will favour women’s employment by the FLSPs. Capacity building for production of niche cheese and dairy products will stimulate higher self-employment of women.

# 8. Rationale for Youth Strategy

# Representation and engagement of youth in agricultural activities

As believed by young people (18-24 years) residing in project target areas, the main field of occupation for rural residents is agriculture. Employment opportunities and types of jobs differ by regions. Employment opportunities are very limited in villages and young people mostly work outside the village, in private businesses and enterprises operating in district centers. The main type of employment is daily jobs at relatively expanded farms. Another type of employment is seasonal work abroad. As noted by young people participating in focus groups, only a handful people work in their chosen professions, and young people with a higher education often fail to get a job.

As noted by focus group participants, the employment rate is higher among middle-aged people than among youth. This can be explained by several factors. First of all, they believe that young people need to accumulate additional experience and knowledge. It is also important that working in agricultural fields is not that appealing for young people.

As believed by focus group participants, the engagement of youth in household chores is quite high, since part of them study. However, despite their involvement, middle-aged people are more actively engaged in household activities than young individuals are.

As for the distribution of functions inside the family, the majority of young people approve of the traditional model and believe that a woman’s duties are cleaning the house, cooking, and household chores, while the man mostly does hard physical labor. Young people are involved in various household activities according to gender.

As for the role of young people in the decision-making process regarding family issues, they assist, and express their opinions, but a head of the household – mostly a middle-aged individual, makes the final decision. It is worth mentioning that for families, in which a middle-aged man (father) is not present, young men lead the household together with mothers and respectively, they make decisions.

The involvement of youth in agricultural activities mostly implies assisting middle-aged people. As declared by young respondents, they are more involved in work that requires more energy and physical force; however, in general, young respondents do not consider their role in agricultural activities to be important.

As for trainings, young people participating in focus groups reported having some experience with trainings, including from their school. Young people believe that they do not have access to trainings and cannot obtain necessary information, however, if needed; the majority expressed a readiness to attend trainings on a topic they are interested in. They named the following topics of interest livestock, breeding new species, diseases, production of organic (bio) products, advertising and branding products. Young people have not participated in trainings held regarding animal husbandry.

In addition, the majority of young people participating in focus groups do not have any experience receiving grants. The main problem related to grant funding is believed to be the accessibility of the grant, and as noted, information is mostly disseminated within a circle of acquaintances.

Young people attending focus group discussions are mostly unaware. NGOs and state institutions/departments working on youth issues cannot assess their work, but there is a youth department in every municipality.

As demonstrated by focus groups, young people mostly have the function of an assistant in the household for both non-agricultural and agricultural activities. As for their civil engagement, part of them reported involvement in a range of discussions and expressing their opinions, but middle-age residents are more involved in civil activities and decision-making processes. It is worth mentioning that the young people who are mostly involved in public discussions are also actively participating in household activities, and are mostly men.

As for the recent tendency in terms of youth engagement, as believed by focus group participants, the involvement of young people at various levels has increased when compared to previous years. Young people are more involved in the decision-making process regarding family or publicly important matters.

# 9. Project Implementation Arrangements and

# Responsibilities of project Gender Specialist

DiMMA project has several tools to implement project activities in rural Georgia. The project has hired regional representatives in 6 regions of Georgia to spread the information on project activities among the rural population, arrange stakeholder meetings, and support farmers to fill in the grant applications. Among project regional representatives/facilitators, out of 12 representatives, five are women.

The project has contracted service providers to implement project activities, and the Agriculture Rural Development Agency (ARDA), responsible for the implementation grant issuing process of the project.  Each service provider has specific tasks for implementation projects, ideas, and activities determined by TOR.

Service Providers for – Civil Works (AF)

Service Providers for- Capacity Building (by regions)

Service Providers for - Climate Change Adaptation Service Provider - Demo Plots and Training (AF)

According to service provider's TOR, each company should have in their team composition the Gender Specialist with the following requirement:

- At least 3 years of progressively responsible professional work experience in gender and development, with proven experience developing training material on gender equality programming;

- A minimum of 3 years of progressively responsible experience in the fields of pedagogy, training/capacity development related to Gender and Development, Education, or other related areas;

- Demonstrated experience conducting training and related capacity building on gender equality (gender mainstreaming and empowerment) programming;

- Experienced in developing an evaluation system for training results;

- Master degree or equivalent in Education, Gender, Social Sciences or other related fields.

- At least three years of progressively responsible professional work experience in gender and development, with proven experience developing training material on gender equality programming;

- A minimum of 3 years of progressively responsible experience in the fields of pedagogy, training/capacity development related to Gender and/or Development, Education, or other related areas;

- Demonstrated experience conducting training and related capacity building on gender equality (gender mainstreaming and empowerment) programming;

- Experienced in developing an evaluation system for training results;

- Gender-responsive consultations and training.

- ensuring women and men being consulted match the project gender and youth targets

The training will be presented in two directions; the first will be in gender mainstreaming tools and the second level of training will be about professional topics in dairy production.

Each service provider will be responsible for presenting the plan in women empowerment directions, with a clear vision on targeting groups. They should analyze the needs of specific women's groups and develop gender mainstreaming training modules, with all relevant components such as gender equality training and gender awareness, which are essential issues in gender mainstreaming and should be developed in three-level: Individual, Institutional and social levels. All these skills are essential to the success of the gender competence development initiative.

The service providers will follow up with the requirements, which is essential for IFAD(and AF) Gender Policy standards in gender empowerment training:

- Understanding gender concepts, issues, and their impact on participants' area of work: training should not be entirely focused on providing participants with practical skills only. In order for the skills to be transformative, they need to be grounded in gender concepts and based on gender theories;

- skills, tools, methods and procedures to mainstream gender and a willingness to 'put on gender glasses';

- Practical examples of how these skills and tools can be applied in participants' everyday practice. Participants should learn to incorporate the gender perspective in their daily work by examining everything from the perspective of women and men, girls and boys, old and young people, etc.;

- Knowledge and practical examples of the relevance of gender equality concern the internal functioning of the organization.

### 9.1 Some Key AF gender considerations during project implementation are:

- Are the presumptions and information regarding the characteristics, needs, and interests of men and women, which informed the initial project/program design, still valid?

- Are adequate provisions for adaptive management and project/programme implementation adjustments based on learning from earlier decisions and interventions and received feedback?

- Have any challenges, barriers or restrictions arisen during project implementation hindered the equal participation of men and women in activities, decision-making processes and the distribution of resources and benefits?

- Are there for example unintended consequences of backlash against women's involvement such as gender-based violence that need mitigation?

- Are partner organizations / service providers aware of and trained to address gender inequalities among beneficiaries?

- Does the project implementation contribute to the sustainability of gender responsiveness and the long-term goal of promoting gender equality, such as the continued integration of gender perspectives within the sector/local context after the intervention ends?

There will be two options in training first is the face-to-face mode and the second one is an online mode.  All training materials will be available online, on service providers' website and on Project FB page.

Professional Trainings

Issues concerning professional trainings in dairy productions the project from its side will present to the service providers all studies and findings concerning women’s role in dairy production. The results of the questioner survey on women’s training needs, which will be core for planning training modules for women farmers. The questioner was developed to understand the women’s obligations along the VC chain. The survey covers the three region of Georgia, where 60 women have been interviewed.  The age range of women who took part in survey are from 20 to 70, 26% present of interviewers are from 20 to 42 age and 43% are from 43 to 61 and up.   The survey participants 37% take care of a small farms (from 2 to 10 cows) and 62% medium size farmers (from 10 to 40 cows). They are not the members of cooperatives or employers of milk companies.  On HH (household) level most of them are involved in animal care (80%) and dairy product preparation (95%) process. Man are active on 100% in transportation of dairy products and milk.

In accordance with AF Gender Policy DiMMA will ensure that all trainings are gender-responsive and where appropriate conduct separate trainings for men and women, with women being trained by women trainers.

The following learning topics were presented for discussion in survey and below are the result of it:

| Cattle Hygienic norms | 19% |
| --- | --- |
| Animal Care | 21% |
| Veterinary | 14% |
| Sales | 7% |
| Basic Principals in Finance | 2% |
| all of them | 37% |

From the table it’s clear that all topic more or less are interesting for them and recommendation will be to prepare training modules for all of them. As for training duration, in the survey questioner the range of training days were proposed from one to one-week training sessions and answer was the following:

| 2 day Training Course | 26% |
| --- | --- |
| 3 day Training Course | 35% |
| One week day Training course | 16% |
| Online Training Course | 28% |

Among the interviews, 3 days training session were most welcome for them like online trainings. Most of the interviewer are ready to attend training sessions in the big cities near their village.

The result of survey will be a good guide for service providers to select learning topics and locations of training sessions according to the regions of Georgia.

### 9.2 AF Gender Monitoring Considerations

As part of their obligation toward the AF, IFAD needs to monitor the implementation of DiMMA on a regular basis and report on their findings to the AFB Secretariat via their annual Project Performance Report (PPR) with the Project Performance Report (PPR) Results Tracker by using gender-disaggregated data. The AF Gender Action Plan (GAP) mandates also an update to the PPR Template that would, for example, introduce a default reporting requirement on actions targeting gender equality and women’s empowerment in the template’s spreadsheets on risk assessment on project indicators, on lessons learned (through qualitative assessment questions on gender) and on results tracked.

A focus on qualitative assessment of gender lessons learned is also particularly important for the mid-term and completion report of projects/programmes. Such qualitative assessments should focus on highlighting the role of women as key actors with experiences and knowledge crucial to the successful implementation of the adaptation project/programme.

### 9.3 AF Gender Project Completion Evaluation Considerations

In line with the AF’s evaluation framework, IFAD is required to commission an independent evaluator to conduct terminal evaluations of regular completed projects and programmes that include an assessment of the project/programme’s contribution to gender equality and women’s empowerment. To that purpose, the IFAD should select an independent evaluator with adequate gender knowledge. There fore IFAD needs to ensure that gender considerations are sufficiently integrated in setting the terms of reference (ToRs) for the evaluator and the evaluation process. For example, the IE should specify in the ToRs for the evaluators that gender expertise is required and that the evaluation team should be gender- diverse with a demonstrated commitment to gender equality and women’s empowerment. The ToR for the evaluation process could also stipulate the involvement of men and women from diverse stakeholder groups (for example both implementing partners and beneficiaries), for example through interviews or focus groups, as well as detailed and specific evaluation questions addressing gender concerns. Particularly for marginalized stakeholders, the literacy level, language skills and time and logistical constraints to participation in the evaluation need to be kept in mind. Part of the evaluation question catalogue should be the elaboration of recommendations on how to strengthen the participation of women or bring about a more gender- equitable distribution of benefits in the specific sector of the adaptation intervention.

For the Adaptation Fund some of the questions the evaluation should attempt to answer in order to assess the success or failure of integrating gender considerations into the project/programme may include:

- Did the project/programme bring about adaptation and reduced vulnerability for both women and men?

- To what extent was the project/programme aligned with the specific adaptation needs and priorities of both women and men?

- Has the project/programme led to more equal opportunities for men and women or did women suffer any detriment as a result of the intervention (with respect to division of labor and care-burden, time poverty or access and control of resources)?

- Have men’s and women’s perceptions (norms, stereotypes, values) been altered during the course of the project/programme implementation

- Were benefits and results distributed equally between men and women and equitably between targeted stakeholder groups?

- Was a gender-responsive results framework incorporated into the project design setting gender-disaggregated targets and using gender-disaggregated indicators?

- Was gender mainstreaming expertise an explicit requirement in all job descriptions, job responsibilities and terms of reference for the project/programme implementation, studies, consulting work, capacity building and training exercises?

- Were gender-related resources (capacities, personnel, budget) suitable and sufficient for gender mainstreaming the project/programme?

- Have the selected executing entities demonstrated sufficient capacities or even strengthened their capacities to carry out gender-responsive activities?

Which of the lessons learned and good practices related to mainstreaming gender in this sector/region can be scaled up or replicated and should be documented and reported?

##### The Role and Responsibilities of the program Gender Specialist

Programm Gender Specialist is the change agent who is overriding role advocates for increased attention to and integration of gender equality and women's empowerment in programming.

She/he is responsible for ensuring that gender aspects are reflected in monitoring and evaluation principles to ensure gender disaggregated data and knowledge will be produced.

TOR of PMU Gender Specialist

- Support the service providers / implementing partners (SPs) to integrate cross-cutting issues into program activities to ensure that correct targeting is done (focusing on gender mainstreaming).

- Identify gender and targeting issues in implementing each program component and design strategies and tools for addressing them through regular field visits for meetings with women and men in villages, SP, and local staff.

- Take Part in preparation of TOR for project baseline study concerning gender issues.

- Prepare project Gender Strategy and Gender Action Plan to effectively integrate gender concerns into the implementation of project activities, including strategies to ensure women's participation in the implementation of various project components and activities.

- Develop Value Chain Analysis from a Gender perspective for specific agriculture products;

- Facilitate communities' consultations in all project target municipalities and document gender considerations, ensuring women's equal participation in those communities.

- Document gender considerations from community consultations and lead in prioritizing and implementing gender-equitable project interventions. In collaboration with the project team, development, and dissemination outreach materials such as brochures, fact sheets, and presentations, ensuring they are gender sensitive and promote gender equality.

### Responsibilities and tasks of Gender Specialist

DiMMA project has several service providers responsible for implementing project activities on various filed of the project.

Responsibilities under Program Service Providers:

- To ensure that the syllabus on gender empowerment is in line with the international standards, IFAD, and AF requirements.  It should include all the necessary aspects of the women empowerment process need.

- To develop a report form for each service provider on their activities.

- To take part in training sessions to make clear for participants the overall program goals;

- To ensure that The training sessions will be prepared in two directions: face to face and online;

- The place of training (location) should be acceptable for all participants;

- Service providers must ensure the attendance of participants in line with project targets;

- The list of attended participants should be recorded according to project M&E standards and send to the project.

- Trainings and exchange visits should be incompliant with Service Providers TOR, and the gender participation quote must be followed.

Responsibilities under Rural Development Agency ( RDA )

- Monitoring of received applications. To analyses applications in time and to find out the reason of rejection.

- Ensure amendments to the grant manual agreed upon during the mission are effectively put in place by RDA to favour women's access to grants;

- On regular basis meet RDA Gender Specialist to ensure that, the organization meet IFAD and AF criteria.

Responsibilities under project regional coordinators and facilitators

- Define coordination mechanisms with field staff and service providers;

- On regular basis, arrange meetings to find out are all target groups participating equally (according to IFAD,AF requirements) and get benefits from the project.

- To spread information on women's access to grants along 6 regions of Georgia;

- Establish a reporting system on women's and youth activity along with the project component;

- With the help of  the project regional representatives monitoring project service providers activities;

Detailed project activities are listed in the Action Plan with targets and responsible persons. (Please see Action Plan).

# Gender and Youth Action Plan

The action plan spell out for two years period until the end of 2022 year. All activities listed under the action plan will be  reviewed after 2022 year and recorded accordingly.

| Activity (organized by project components) | Key milestones/outputs | Indicators | Budget | Target | Deadline | Responsible Person |
| --- | --- | --- | --- | --- | --- | --- |
| Take part in preparation Base line survey questionnaire for focus groups for women’s and youths. | To be sure all aspects will take into consideration |  |  |  | May 2020 | Gender Specialist M&E, ACT |
| Produce the scope of work for Gender specialist of Service Providers’ TOR | To hire Professional Gender Specialist on board | 3 Service Provides TOR |  | 3 TOR of Service Providers | August 2020 | PIU, Gender Specialist |
| Conduct survey on women’s role in dairy VC. Pprepare questioner on identification gaps under the six domain of women empowerment and make assessment of their need in trainings. | Include all aspects concerning training needs of women and youth | Maximum 100 interviewers in three regions of Georgia |  |  | June 2020 | Gender Specialist |
| With the help of projects regional coordinators and facilitators take survey in three regions of Georgia (Samtkhe-kavakheti, Imereti and Samegrelo) |  |  |  | Minimum 20 women interviewer from each region. Total 60 interview. | Due to Pandemic, interviews were conducted by phone | Project Regional Coordinators and Facilitators,Gender Specialist |
| Prepare Dairy VC analyze from Gender Perspective. | To identify gaps for women interventions |  |  | One study | July 2020 | Gender Specialist |
| On quarterly bases meet with regional coordinator and discuss with them problems concerning women’s and youth participation in grant program. Create short reports on Identification of the main problems and present the ways of problem solution. | To analyze program participation patterns. |  |  | On Quarterly base, one visit in each region. Total 6 visit in six regions of Georgia. | on regular base |  |
| On quarterly base, analyze rejected grant application. | To identify the real reason of rejection. Inform the project management on it and make appropriate steps. |  |  | Once in each quartier | on regular base |  |
| Organize dedicated information sessions and outreach activities to reach out to MVDP, women, women-headed households and youth. | It is essential for program to reach the women headed households and find out the ways of their involvement in the program. |  |  |  | on regular base | Gender Specialist |
| Participate in preparation of Stakeholder Mapping in order to identify women, youth farmers and women headed household on DiMMA project areas. | Women headed household are the most vulnerable segment of the project. To identify, reach and make them project beneficiaries are the target of the DiMMA project. |  |  |  | April-May 2021 |  |
| Survey on para vet women’s activity along the 6 regions of Georgia | To develop questioner in order to analyze their current situation. | Survey will cover 6 regions of Georgia |  |  | 2021 Marc-April | Gender Specialist & Regional Representatives |
| Develop a reporting format for gender and youth to be included in the project periodic progress report |  |  |  | For progress reports | on regular base | Gender Specialist |
| To launch Active advertising campaign of the project through women project beneficiaries about new grant composition. | To rise project visibility. On a regular base Update, project FB page and web site on women’s and youth active participation. |  |  | 6 Region of Georgia | April 2021 (duration 1 month) | Gender Specialist , KM &Communication specialist |
| Monitoring training session organized by the project Service Providers in gender mainstreaming, with all relevant component. | They should conduct a gender-learning needs assessment aimed at assessing participants’ knowledge of gender issues and concepts, to better tailor training to their identified needs. Gender-learning needs assessment should focus on assessing the ‘problems’, such as individual resistance. | 6 training sessions in six regions (Imereti, Samegrelo, Samtskhe-Javakheti, Kakheti, Kvemo Kartli, Racha) , once in every three month. |  | 15 women from each region. | December 2020 | Gender Specialist & Service Provider |
| Ensure the participation of women and youth in community mobilization process, stakeholders’ platforms comply with Dimma project targets. Adaptation Fund will be completed - , in PUAs. | Women and youth should be informed properly on PUA organization process. Their active participation and opinions should be taken into account | Minimum 30% women 50 %youth |  |  | on regular base | Gender Specialist, Service Provider, Regional Representatives |
| Ensure that the participation of women and youth in the Training sessions and exchange visits organized by service providers are according to Dimma target. | Projects should reach its target of women’s and youth participation. | 50 % women 52 % youth |  |  |  | Gender Specialist & Service Provider |
| Use women’s empowerment Agriculture Index (WEAI) for midterm and and-line surveys to fine tune project activities and for advocacy. | To see the full picture in women empowerment process on every stage of project life. |  |  | Project mid-term survey |  | Gender Specialist & Research company |
| Training session in women’s empowerment | It is obligatory to provide training course in gender equality principles. | Depends on women activity. Two session in each region. (7-8 women per group) |  |  | Pending | Gender Specialist & Service Provider |
| Professional Training sessions | Two project service providers | 50 % women 52 % youth |  |  | Pending | Gender Specialist & Service Provider |
| Professional trainings | AF service provider | 30% women |  |  | Pending | Gender Specialist & Service Provider |

# ANEXX 1

# Main Findings from the Project Baseline study

Women and men are equally involved in farming, with men spending 98.1 days and women 84.3 days per year in the crops value chain, while men spend 165.8 days and women 259.9 days in the animal husbandry value chain. Taking care of domestic animals and producing dairy products heavily depend on problematic water and gas supplies; this is probably one of the reasons for the long hours spent on animal husbandry.

Based on the project goal and objectives, the research design was developed through tight and active collaboration with the client. The survey was conducted in rural areas throughout Georgia, including the following target regions: Imereti, Samegrelo-Zemo Svaneti, and Samtskhe-Javakheti; and control regions: Kakheti, Kvemo Kartli, Shida Kartli, Racha-Lechhkhumi – Kvemo Svaneti, Guria, and Adjara.

The given study consisted of both quantitative and qualitative components, during the base line study 1,600 household was interviewed and among 8 focus groups discussions one was women and one young focus groups.   Here is the summery of main findings according to baseline study on several domains.

### 1. Gender aspects of target population

### 611 Decision-making process in households

According to the study results, every adult family member equally contributes in making decisions on investments and business startups. The share of households in which male members make such decisions (27%) is almost two times higher than the share of families in which women make decisions (15%).

As demonstrated by the study results, every adult member of the family equally makes decisions when planning expenses in 57% of inquired households throughout Georgia. The share of HHs where male members make a decision on this matter is 24%, while female members are decision-makers in 20% of households.

In 64% of households, decisions on family members’ work and education are made equally by all adult members. In total, the share of respondents who declare that male (18%) or female (18%) members make a decision on these matters is equal.

In 52% of households, every adult member is equally involved in making decisions on agricultural activities. In 29% of families, male members make such decisions, while in 19% of cases, females are the decision-makers.

Involvement of household members in the decision-making process

### 1.2 Socio-economic status of women

As demonstrated by the study results, there are minor differences between the genders in terms of the status of obtained education in the target population (rural settlements of Georgia). Citizens mostly have a complete secondary education (38%). The share of men with a complete secondary education (41%) is slightly higher than that of women with this level of education (36%). The share of women with a vocational education (22%) is slightly higher than that of men (18%) with the same status. Only 16% of women and men have a higher education.

However, despite equality between genders in terms of education level, the employment rate of women is significantly lower than the employment rate of men. Only 20% of adult women are employed, while the employment rate is 32% among men.

Speaking of cases in which the respondent is the manager, the gender distribution is as follows: 58 men and 30 women. For cases in which someone else manages the enterprise/business, 7 are men and 5 are women.

Level of education and employment status by gender

As for employment opportunities for women and men, the majority of women mostly consider a man’s labor as hard physical labor both in agricultural and non-agricultural fields. On the other hand, a woman’s labor mostly implies activities requiring less physical force. However, respondents believe that women do not face any particular barriers in terms of employment, and that men and women have almost equal opportunity from this point of view. It is worth mentioning that women rarely consider household chores (for example, taking care of children) when speaking about employment, before they begin speaking about the distribution of household chores and having limited time due to the current distribution.

When speaking about non-agricultural fields, women mostly see job opportunities at shops and markets, and sometimes in tourism facilities and restaurants, but these are often available outside their village. Focus group participants declare that they mostly have a chance to be involved in large productions, hazelnut picking, and various factories if there are any. Employment opportunities vary by region.

### Distribution of functions in the household

When speaking about employment, the majority of women reported being a housewife and being mostly responsible for household chores. A small portion of them also have a job alongside household chores, but most women still have to refuse an additional job for a variety of reasons including: a lack of time due to having a lot to do at home, insufficient salary, and age. The majority of women agree, however, that considering the household’s financial needs, the more members who are employed, the better.

According to focus group discussion participants, women are generally responsible for household chores such as cleaning the house, laundry, cooking, and bringing up children. It is worth mentioning that men are involved in a certain part of taking care of children, but this is mostly just as assistance. House refurbishment or repair is mostly perceived as the man’s responsibility. Women believe that such distribution of functions is natural, and we often had to explain what was meant by ‘distribution of household functions’ during focus groups or interviews. As for decisions, elder members of the family mostly make joint decisions; however there are cases in which women are more informed on a range of topics such as expenses related to child care, expenses of primary consumption items and food. Respectively, women are more involved in managing finances and making respective decisions.

As noted above, because of household responsibilities, women often cannot do whatever they are interested in, but this is mostly perceived as natural, as they believe that functions are fairly distributed and everyone has to work hard for the family.

Regardless of the fact that the majority of women noted that everyone in the family has his/her function and no one is without a function, they still believe that household work – unpaid labor is not properly appreciated.

### 1.4 Involvement of women in agriculture

As noted by female participants of focus groups, women and men are actively involved in agricultural activities. Women and men distribute functions when carrying out agricultural activities. As believed by female participants of discussions, the main factor when distributing activities is physical force.

When carrying out agricultural activities, what defines the distribution of functions is whether the family consists of only women or we if there are mixed genders. Namely, in families consisting of only women, agricultural activities are fulfilled by women, while functions are distributed between men and women in mixed gender households. Focus group discussion participants noted that in the process of cultivating annual and perennial crops, the main function of women is to cultivate and take care of crops – or gardening, while the main responsibility of men is to harvest other crops (corn, vine). Women are also involved in the harvesting process.

When discussing agricultural activity in general, women believe animal husbandry is mostly a man’s responsibility. However, when discussing direct functions, it turned out that women spend double the amount of time on livestock activities as men. The main function of men is to bring animal feed and in regions where cattle is taken to pastures and when family members do it themselves, keeping an eye on cattle and in rare cases, cleaning the barn. Taking care of animals, cleaning the barn, milking, and making dairy products are a woman’s responsibilities.

Respectively, in terms of the distribution of work, a woman spends 25 hours on this activity per week, while a man spends 10 hours.

### 1.5  Ownership of household assets and decision-making process

Both parties are generally involved in making decisions about agricultural issues. Animals are believed to be jointly owned by a family, but there are exceptions when animals are owned by a man and he makes decisions on these issues.

As for the ownership of various assets, land parcels are mostly owned by men, and women own land manage their assets only in cases when they don’t have a husband.

As declared by female participants of focus groups, mostly women are involved in the process of selling produce.

There are differences in terms of the ownership of real estate by women and men. Namely, regardless of the fact that the shared ownership of a residential house is quite a prevalent practice (23% on average), men are typically the official owners of residential houses in all regions (Imereti – 46%, Samegrelo-Zemo Svaneti – 50%, Samtskhe-Javakheti – 43%). The number of cases in which women are the owners is relatively smaller. The gender imbalance is even more noticeable in terms of owning agricultural land – 66%-71% of rural land parcels are registered to men in target regions. This factor can be explained by a tradition, according to which property is automatically inherited by men.

Land ownership rate by gender

As declared by focus group representatives, land is mostly owned by men, implying both formal and informal ownership.

### 1.6 Involvement in various activities and accessibility

In the majority of families of women involved in the study, they did not carry out business activity, and respectively it was difficult for them to discuss this topic. In addition, hardly any participants had experience starting a business, or receiving any type of grant or loan. In most cases, focus group participants do not have any experience in completing grant proposals or taking business loans.

A major part of the focus group discussion participants did not participate in any type of trainings. In most cases, they reported on attending work-training courses. Many of them have never heard of anyone being involved in any type of trainings and respectively, could not assess the effectiveness of the trainings. As for the desire to participate in trainings, focus group participants are ready to become involved and make time for trainings, mostly on agricultural topics, and they would love to learn some craft work. There are exceptions, however, who believe that they would not be able to attend trainings. Female participants of the study have not participated in trainings related to animal husbandry.

As demonstrated by the qualitative study, women are not informed about NGOs operating in their region or departments of state bodies working on women’s’ issues. It is worth mentioning that departments focusing on women’s issues function in every municipal center.

Women are actively involved in the management of household issues. As for civil activity, their involvement in various public activities differ – some women reported attending a discussion of village problems and based on their observation, women are more involved in discussions than men. Some women do not participate in civil activities at all and note that mostly men are involved in this kind of activity.

Regardless of the quality of public activism of female participants, they believe that women are more active when compared to recent years at both the public and household level, and that they are more actively engaged in the decision-making process.

# ANEXX 2

| Results | Indicators |  |  |  |  |  | Means of Verification |  |  | Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hierarchy | Name | Unit | Baseline | Mid- Term | End Target | Source |  | Frequency | Responsibility |  |  |
| Outreach | Number of persons receiving services promoted or supported by the programme (Core indicator outreach 1) | Men | 0 | 1,953 | 3,370 | M&E system |  | Semi-annually | M&E officer |  |  |
|  |  | Women | 0 | 1,953 | 3,370 |  |  |  |  |  |  |
|  |  | Young | 0 | 2,105 | 3,518 |  |  |  |  |  |  |
|  |  | Non-young | 0 | 1,801 | 3,222 |  |  |  |  |  |  |
| Goal: Rural economic development and poverty reduction by contributing to the modernization and emergence of a competitive, diversified, resilient and sustainable dairy industry | Increase (international standards ‘compliant) milk production in Georgia | % | 604 million ton/ year | - | 10% 664 million ton/ year | Geostatic Baseline and completion surveys |  | Baseline and completion | PMU | - Political stability - Marco-economic conditions remain stable or improve - Major milk processors maintain local sourcing policy on milk produce |  |
|  | Number of households experiencing economic mobility (IFAD impact assessment indicator) | Number | 0 | - | 3,514 |  |  |  |  |  |  |
| Development Objective: Enhance the livelihoods and resilience of smallholder dairy producers, especially in mountain areas, and improve the management of the natural resources | Percentage increase in average monthly income of supported dairy smallholders over baseline | % | TBD | - | 30% |  |  |  |  |  |  |
| Outcome 1 Milk production, safety, marketing and profitability of target households improved | Increase in volume of processed milk in milk collection centers/ processing enterprises | Litres/ day | TBD | 50% | 100% | Enterprise records |  | Baseline and annually | PMU/ M&E officer | - Livestock epidemic disease (R) - Various dairy value chain actors are willing to participate in the programme - Dairy value chain actors are willing to invest in development of the farm production capability - Availability of qualified service providers for group facilitation, training and extension activities |  |
|  | Percentage reduction in volumes of milk rejected by milk collection centers | % | 0 | 10% | 30% | Annual outcome survey |  | Annually | M&E officer |  |  |
|  | Number of new jobs created (core indicator 2.2.1) | Number | 0 | 129 | 370 | Enterprise records |  | Annually | PMU/M&E officer |  |  |
| Output 1.1 Value chain actors capacitated | Number of persons trained in production practices and/or technologies (core indicator 1.1.4) | Total | 0 | 3,600 | 6,000 | Training reports |  | Semi-annually | M&E officer Component officer |  |  |
|  |  | Men | 0 | 900 | 1,500 |  |  |  |  |  |  |
|  |  | Women | 0 | 900 | 1,500 |  |  |  |  |  |  |
|  |  | Youth | 0 | 1,800 | 3,000 |  |  |  |  |  |  |
|  | Number of persons trained in income-generating activities or business management (core indicator 2.1.2) | Total | 0 | 1,790 | 3,820 | Training reports |  | Semi-annually | M&E officer Component officer |  |  |
|  |  | Men | 0 | 448 | 955 |  |  |  |  |  |  |
|  |  | Women | 0 | 448 | 955 |  |  |  |  |  |  |
|  |  | Youth | 0 | 895 | 1,910 |  |  |  |  |  |  |
| Output 1.2 Seed capital financing provided through DVCF | Number of persons benefitting from seed capital financing | Total | 0 | 2,420 | 4,470 | APMA reports |  | Semi-annually | M&E officer Component officer |  |  |
|  |  | Men | 0 | 605 | 2,235 |  |  |  |  |  |  |
|  |  | Women | 0 | 605 | 2,235 |  |  |  |  |  |  |
|  |  | Youth | 0 | 1,210 | 2,360 |  |  |  |  |  |  |
| Output 1.3 Pasture lands developed | Number of hectares of land brought under climate-resilient management (core indicator 3.1.4) | ha | 0 |  | 9,500 | Component reports |  | Semi-annually | M&E officer Component officer |  |  |
| Output 1.4 Marketing infrastructure developed | Number of kilometers of roads constructed, rehabilitated, or upgraded (core indicator 2.1.5) | KM | 0 | 300 | 300 | construction contracts/ progress reports |  | Semi-annually | M&E officer Component officer |  |  |
| Outcome 2: Sustainable institutional and organisational development | Number of existing/new regulations, policies, or strategies supporting pasture management and growth of dairy subsector proposed to policy makers for approval, ratification, or amendment (Core indicator policy 3) | Number | 0 | 1 | 2 | MSP proposals |  | Annually | KM officer | - Interest and motivation among community members - PUAs |  |
| Output 2.1. local dairy initiative clusters and platforms and farmer groups developed/strengthened | Number of groups supported to sustainably manage natural resources and climate- related risks (core indicator 3.1.1) | PUA | 0 | 76 | 76 | PUA meetings |  | Annually | M&E officer Component officer |  |  |
|  | Number of members in groups supported to sustainably manage natural resources and climate- related risks | Total | 0 | 3,800 | 3,800 |  |  |  |  |  |  |
|  |  | Men | 0 | 950 | 2,660 |  |  |  |  |  |  |
|  |  | Women | 0 | 950 | 1,140 |  |  |  |  |  |  |
|  |  | Youth | 0 | 1,900 | 1,900 |  |  |  |  |  |  |
| Output 2.2. Dialogue between dairy sector stakeholders strengthened. | Number of functioning multi-stakeholder platforms supported (Core indicator policy 2) | MSP | 0 | 3 | 3 | M&E system MSPs meetings |  | Semi-annually | M&E officer Component officer |  |  |

Confidance

# ANEXX 3

### IFAD Gender checklist for programe design

| Gender checklist | Comments |
| --- | --- |
| 1. The programme design report contains – and programme implementation is based on - sex-disaggregated poverty data and an analysis of gender differences in the activities or sectors concerned, as well as an analysis of each programme activity from a gender perspective to address any unintentional barriers to women’s participation. | Yes. The programme design contains and based on sex disaggregated data on agricultural production, poverty from the Geostat, ASP impact assessment. Design has analysis of gender differences with regards to livestock VC in terms of roles of women in the livestock sub sector, access to loans, technical support and matching grants. Measures are prescribed how to address limitations. For details see Annex 2: Poverty, targeting and gender |
| 2. The programme design report articulates – or the programme implements – actions which aim to: Expand women’s economic empowerment through access to and control over productive and household assets; | Yes. The Programme intends to mainstream gender and provide women service providers, especially para vets, as well as women livestock farmers and women heads of farms with the following: capacity building activities targeted at women engaged in services provision (inputs suppliers, vets and para vets), linkages to the inputs suppliers for para vets, diversification from livestock production and accessing jobs in newly created or expanded enterprises; agricultural production; small matching grants, including to women producers of premium quality cheese with financial products without requiring collateral or on a preferential matching grant ration of 70/30. |
| Strengthen women’s decision-making role in the household and community, and their representation in membership and leadership of local institutions; | Yes. The Programme will support women’s engagement in local and regional value chain clusters to voice their needs and concerns to the Programme and policy makers. Programme will cooperate with the UN Women program on women’s empowerment and channel lessons learned to policy Women para vets will be trained on issues of nutrition and animal zoonotic diseases prevention to disseminate knowledge further in the communities |
| Achieve a reduced workload and equitable workload balance between women and men. | Yes The Programme will facilitate increase of dairy livestock productivity and link producers to markets. Women will be able to market fresh milk instead of producing cheese and would benefit in terms of increased income, saved time and decreased workload. |
| 3. The programme design report includes one paragraph in the targeting section that explains what the programme will deliver from a gender perspective. | Yes |
| 4. The programme design report describes the key elements for operationalizing the gender strategy, with respect to the relevant programme components. | Partially. The DiMMA Programme will have to develop Gender Strategy to reflect all targeting measures |
| 5. The design document describes - and the programme implements - operational measures to ensure gender- equitable participation in, and benefit from, programme activities. These will generally include: |  |
| Allocating adequate human and financial resources to implement the gender strategy | Yes. DiMMA will have to employ at least part time Gender Focal Point and allocate funding for Gender Strategy implementation |
| 5.2 Ensuring and supporting women’s active participation in programme-related activities, decision-making bodies and committees, including setting specific targets for participation | Yes. Programme sets target of at least 30 percent being female participants NGO will need to facilitate brokerage with financial institutions to allow women to access loans without collateral. If such product will not be offered by the participating financing institutions, women will be treated on a preferential basis during scoring in selection of the BPs and 70/30 matching grant ration, where 30 percent is contribution from women farmers. |
| 5.3 Ensuring that programme management arrangements (composition of the programme management unit, terms of reference for programme staff and implementing partners, etc.) reflect attention to gender equality and women’s empowerment | Yes. The existing PMU has a capable Gender Focal Point in charge of gender mainstreaming. TORs of the PMU staff have provisions on gender mainstreaming and sensitivity. |
| 5.4 Ensuring direct programme outreach to women (for example through appropriate numbers and qualification of field staff), especially where women’s mobility is limited | Yes. TORs for local NGO to implement Components 1 and 2 will require proven experience in working with gender issues |
| 5.5 Identifying opportunities to support strategic partnerships with government and other development organizations for networking and policy dialogue | Yes. Programme will contribute to livestock and pasture management policy development. It will be also support through local and national Livestock Platforms for local and national level dialogue. |
| 6. The programme’s logical framework, M&E, MIS and learning systems specify in design – and programme M&E unit collects, analyses and interprets sex- and age-disaggregated performance and impact data, including specific indicators on gender equality and women’s empowerment. | Yes. M&E staff of the PMU will be monitoring targeting performance and beneficiary tracking. All reports will be sex disaggregated and against specific gender indicators. |

DiMMA PDR-Appendix4: Detailed Programme Description

Gender-responsive: refers to the consideration of gender norms, roles, and relations and to addressing inequality generated by unequal norms, roles and to the goal of having the same number of women and relations through changes within a given social setting through remedial action.

. Women's economic empowerment includes women's ability to participate equally in existing markets; their access to and control over productive resources, access to decent work, control over their own time, lives and bodies; and increased voice, agency, and meaningful participation in economic decision-making at all levels from the household to international institutions

The total number of targeted households is 6740? on the assumption that there will only one beneficiary per household as per the economic and financial analysis

Baseline figures to be updated based on the baseline survey.

Baseline figures to be updated based on the baseline survey. The estimated capacity of the supported processing units/ milk collection centers is 121,300 litres/day. The current volume of processed milk will be estimated during the baseline survey