| Mid-Term Review AF-financed project | Project: Dairy modernization and market access: adaptation component (DIMMAdapt) Prepared by Joris Oele |
| --- | --- |

Table of Contents

1.	Executive summary	5

1.1.	Project information summary	5

1.2.	Project description	5

1.3.	Summary of conclusions, lessons learned and recommendations	6

2.	Introduction and background	11

2.1.	Evaluation features	11

2.2.	Report introduction	11

2.3.	Object of evaluation	11

2.4.	Implementation context	12

3.	Evaluation scope and objectives	14

3.1.	Evaluation scope	14

3.2.	Evaluation criteria	14

3.3.	Evaluation questions	15

3.4.	Evaluation matrix	16

4.	Evaluation approach and methods	17

4.1.	Evaluation principles	17

4.2.	Data sources	17

4.3.	Data collection methods	17

4.4.	Data analysis	18

4.5.	Evaluation stakeholder engagement	18

4.6.	Ethical considerations related to data collection and use	18

4.7.	Methodological limitations	18

5.	Evaluation findings and conclusions	19

6.	Evaluation lessons learned	24

7.	Evaluation recommendations	27

8.	Annexes	31

8.1.	Project results framework and analysis of performance until MTR	31

8.2.	Details of results until MTR	35

8.3.	Summary of budget and analysis of budget spent until MTR	37

8.4.	Data collection tools	41

8.5.	Evaluation timeline	41

8.6.	Evaluation Inception Report	41

Acronyms and abbreviations

AF		Adaptation Fund

AC		Acre

AMMAR	Agriculture Modernization, Market Access and Resilience

DIMMAdapt 	Dairy modernization and market access: adaptation component

ESMP		Environmental and Social Management Plan

FtF		Farmer-to-Farmer

GHG 		Greenhouse Gas

GIS 		Geographic Information System

KG 		Kilogram

HA		Hectare

M		Metre

M2		Square metre

IFAD		International Fund for Agriculture Development

MEPA		Ministry of Environmental Protection and Agriculture

MTR		Mid-Term Review

NASLM	National Agency for Sustainable Land Management and Land use monitoring

PMP 		Pasture Management Plan

PMU		Project Management Unit

PUA		Pasture User Associations (at district level)

PUU		Pasture User Unions (at village level)

RECC 		Regional Environmental Center for the Caucasus

Currency equivalents

Monetary Unit 		= 	Georgian Lari (GEL) 
USD 1 			= 	GEL 3.12 (as per AF proposal)

USD 1			=	GEL 2.95 (as per August 2024)

Weights and measures

1 kilogram (kg) 	= 	2.204 pounds (lb)

1000 kg 		= 	1 metric tonne (t)
1 metre (m) 		= 	1.09 yards (yd)
1 square metre (m2)	= 	10.76 square feet (ft2)

1 acre (ac) 		= 	0.405 ha
1 hectare (ha) 		= 	2.47 acres

Project target area

Figure 1 Map of project area

The region of Samtskhe-Javakheti is the most developed of the three regions of the project.

Situated in the southwest of the country, the region is mainly constituted of high plateaus with most of the land (80 percent) considered as high mountain (above 1500m) and with an average altitude of 1865 meters above sea level. The dairy market in this region was particularly improved during the last decade, supported by the government and private investments and the unemployment rate is the lowest of the three regions (5.9 percent in 2017) even though there is a large variation of poverty level within the region. The region is divided in the following municipalities: Adigeni, Akhaltsikhe, Borjomi, Aspindza, Akhalkalaki, Ninotsminda.

The Imereti region is situated in the west part of the country, in the mountainous chain between the Greater and the Lesser Caucasus mountains. The region is composed of high mountains in the east and lower plains in the east. The Imereti region is the most populated of the three project regions, with 507.000 people but is also the region with the highest unemployment rate, around 14 percent in 2017. The potential of development is quite high with great demand in dairy products at national and international level and the highest number of cattle heads in the country with the Samegrelo Zveno-Svaneti region. The region is divided in the following municipalities: Khoni, Tskaltubo, Samtredia, Tkibuli, Kutaisi, Terjola, Chiatura, Sachkere, Zestafoni, Vani, Baghdati, Kharagauli.

The Samegrelo Zveno-Svaneti region has both high mountains in the Greater Caucasus and low plains facing the Black Sea. With more than 50 percent of its territory with high slopes (above 10 degrees) and more heavy rainfall events in summer over the past 40 years, this region is subject to an increase in erosion. The high number of cattle heads could worsen the situation if adequate pasture management is not established rapidly. The region is divided into the following municipalities: Mestia, Tsalenjikha, Chkorotsku, Martvili, Zugdidi, Senaki, Khobi, Poti, Abasha.

# Executive summary

## Project information summary

Table 1 Project information summary table

| Project Title: | Dairy modernization and market access: adaptation component (DIMMAdapt) |  |  |
| --- | --- | --- | --- |
| IFAD Project ID: | 2000001393 (as part of Dairy Modernisation and Market Access Project) |  |  |
| Country: | Republic of Georgia |  |  |
| Region: | Near East and North Africa (NEN) and Europe Division |  |  |
| Objective: | Enhance the resilience to climate change of vulnerable dairy producers |  |  |
| Implementing agency | International Fund for Agriculture Development (IFAD) |  |  |
| Executing Agency: | Ministry of Environmental Protection and Agriculture (MEPA) |  |  |
| Budget in USD | 4,644,794 |  |  |
| Duration | 4 years |  |  |
| Key dates |  |  |  |
| AF approval |  | Effectiveness | Mid-term Review |
| 11 September 2019 |  | 16 April 2021 | Sept 2024 |

## Project description

This is the Mid-Term Review (MTR) covering the Adaptation Fund (AF) project ‘Dairy modernization and market access: adaptation component (DIMMAdapt), implemented by the International Fund for Agricultural Development and executed by the Ministry of Environmental Protection and Agriculture (MEPA) The MTR was prepared in line with AF evaluation policies.

Project goal: Reduce the vulnerability of the dairy value chain to the deleterious impacts of climate change.

Project objective: Enhance the resilience to climate change of vulnerable dairy producers.

Project components: Table 2 provides an overview of the project components, outcomes, outputs and budget

Table 2 AF project components as per initial project proposal

| Project/Programme Components | Expected Outcomes | Expected Outputs | Amount (USD) |
| --- | --- | --- | --- |
| 1. Climate-proofing pastoral ecosystem services (water management, pasture regeneration, and disaster risk reduction). | Outcome 1.1 An enabling environment developed through training and capacity building. | Output 1.1.1: Climate resilient and DRR solutions for pasture rehabilitation and increased productivity promoted. | 1,691,047 |
|  | Outcome 1.2. Pasture Management Plans Implemented | Output 1.2.1: Climate resilient and ecosystem-based adaptive pastoral investments implemented. | 1,103,064 |
|  |  | Output 1.2.2: A management mechanism is in place to screen and offset any potential cattle number increases from DiMMA | 40,000 |
| 2. Supporting the climate resilience of market vulnerable smallholders. | Outcome 2.1 Climate-smart technology demonstrations and livelihood diversification. | Output 2.1.1 Climate-smart technologies and alternative livelihood measures promoted. Output 2.1.2 Alternative, complementary, non-competitive, non-extractive livelihood jobs created. | 1,128,080 |
| Total |  |  | 3,922,191 |
| Project/Programme Execution Cost (9.1%) |  |  | 358,727 |
| Total Project Cost |  |  | 4,280,918 |
| Project Cycle Management Fee Charged by the Implementing Entity (8.5%) |  |  | 363,876 |
| Amount of Financing Requested |  |  | 4,644,794 |

## Summary of conclusions, lessons learned and recommendations

High priority recommendations

- Update and request DiMMAdapt restructuring proposal with the project extension till June 2026, incorporating the new output focused on the identification, categorization, and registration of pastures, as proposed by the National Agency for Sustainable Land Management and Land Use (Lang Agency) within the Ministry of Environmental Protection and Agriculture (MEPA) and increasing the budget for Component 2 activities.

- Timely launch procurement process for two separate service providers to implement PMPs

- Ensuring adequate / timely state (ministry of finance) allocation to secure timely payments for project activities (esp. 4th grant calls)

- Prepare action plans / guidelines / clear maps and exit strategy for PMPs / villagers (in Georgian) combined with building capacity of pastoralist and municipality to collectively implement PMPs in a sustainable and climate change resilient way

- Ensure all villagers of target villages are involved in land inventory and categorization process under the newly proposed output by the Land Agency and that there is consensus on categorization and ownership.

Medium priority recommendations

- Prioritize / maximize the implementation of PMPs, water management activities and greenhouses for the remainder of the project and consider redistribution of budget to these activities

- Safeguard AF targets

- Analyse and prioritize project activities that prepare for and complement the future DiMMAdapt+ project

- Ensure capacity building activities take place on time to support effective implementation concrete activities

- Maximize the trainees per trainings

- Review / develop (tradition sensitive) targeting strategy for further involvement of females and shepherds in trainings and implementation of PMPs.

- Ensure project beneficiaries are aware of the grievance mechanism

Low priority recommendations – see Evaluation recommendations

Table 3 Recommendations for the remainder of the project (linked to conclusions and lessons learned)

| Evaluation criteria | Conclusions | Main lessons | Recommendations for the remainder of the project | Justification | Respon-sible | priority | Time-frame |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Relevance | - Most activities are relevant from a climate change perspective. The development / implementation of PMPs, water conservation / management and grants for greenhouses stand out as most relevant. Not all activities as anticipated during project design will be implemented (such as planting of trees / wind breaks). All interventions are relevant in general for project beneficiaries, except perhaps reducing CO2 emissions. Solar energy has great benefits for beneficiaries, but not perse from a climate change adaptation perspective. The project is in alignment with national, municipal and community priorities. The focus on the Samtskhe-Javakheti (for implementing PMPs) is justified. M & E: - It is not clear why demos and trainings are sometimes reported / budgeted under 2.1.1 instead of 1.1.1 - Monitoring against all AF indicators could be stronger | - The development / implementation of PMPs, water management / conservation activities and grants for greenhouses stand out as the most relevant activities from a climate change perspective in the project | - Prioritize / maximize the implementation of PMPs, water management activities and greenhouses for the remainder of the project and consider redistribution of budget to these activities | Most relevant, and impactful | IFAD and PMU | Medium | Remainder of the project |
|  |  |  | - Improve monitoring against all relevant AF indicators as suggested in Table 15 | Supports improved reporting to the AF | PMU | Low | Remainder of the project |
| Coherence | - DiMMA and DIMMAdapt are complementary, but the complementarity / linkage of climate proofing DIMMA activities could have been stronger. Trainings support implementation of concrete activities, but the timing of capacity strengthening activities could have been better in some cases | - Complementarity of projects need to be ensured while also safeguarding separate project targets - Capacity building activities need to support the effective implementation of concrete interventions and be timely | - Safeguard AF targets | To maximize results under DiMMAdapt | AF coordinator PMU | Medium | Remainder of the project |
|  |  |  | - Analyse and prioritize project activities that prepare for and complement the future DiMMAdapt+ project | To ensure sustainability, efficiency and avoid duplication |  |  |  |
|  |  |  | - Ensure capacity building activities take place on time to support effective implementation concrete activities | To maximize effectiveness |  |  |  |
| Effective-ness | - Project results under outcome 1 are limited, while progress under outcome 2 is better. Overall, project results are off-track due to project delays (caused by non-adoption / delayed pasture law) and too ambitious targets set during project design and perhaps some limitations to technical expertise to reach targets considering above. There is a need to extend the project to reach adjusted targets Grants: - There seem to be a slight mismatch between initial targets set and budget spent / remaining (which could be due to timing reporting) - There seem to be a slight mismatch between initial targeting strategy (20 cows) and actual number of cows present (higher) | - Targets set during project design were too ambitious and the main mitigation measures for the main potential risk of delays were not in place. Related future project need to better assess feasibility of targets and potential delay risks at design and inception phase | - Update and request DiMMAdapt restructuring proposal with the project extension till June 2026. This proposal should incorporate the new output on identification, categorization and registration of pastures in the new municipality as proposed by the Land Agency. | Without some activities will not be implemented and targets reached limited | IFAD and PMU | High | By Mid Oct 2024 latest |
|  |  |  | - Review the targets for grants and review the targeting strategy for beneficiaries with correct number of cattle | Risk of non-feasible targets and inappropriate targeting | PMU | Low | Before next grant call |
| Efficiency | - Spending under component 1 is off-track. Spending under component 2 is on-track. The project activities are less cost-efficient than anticipated during project design, but this is due to targets set to ambitiously during project design. The number of trainees per training is not high. Some delays can be attributed to some capacity limitations (incl. former AF coordinator and PMU sometimes flagging potential issues a bit late) and slow fund release from the ministry of finance The remaining budget under execution costs could support project extension. The budget presented under evaluation / MTR may be incorrect / too high and should be corrected. | - Potential delay risks should also be assessed / monitored and quickly responded to during project implementation and | - Timely launch procurement process for two separate service providers to implement PMPs | To avoid delay and lack of capacity one service provider | PMU | High | By end Nov 2024 latest |
|  |  |  | - Ensuring adequate / timely state (ministry of finance) allocation to secure timely payments for project activities (esp. 4th grant calls) | To avoid delays | PMU | High | By end Nov 2024 latest |
|  |  |  | - Maximize the trainees per trainings | To reach more beneficiaries | PMU | Medium | Remainder of the project |
|  |  |  | - Review and update reporting on PMU / evaluation spending to fix previous errors) | Current spending on evaluation is reporting inaccurately | PMU | Low | Before end of the project |
| Impact | - The beneficiaries met during the MTR are generally very happy with the results so far and planned actions. The implementation of the PMP has a potentially large impact on the way pastures are managed. Trainings for pastoralists to implementing the PMPs / manage pastures collectively in 15 villages are wanted by villagers Controlled grazing and water management is anticipated to increase the sustainability / climate change resilience of pastures PV and greenhouses have a big impact on beneficiaries with improved production and income | - Beneficiaries seem to be happy with all project activities leading to increased production and income. - The implementation of the PMPs has a potentially large impact on the way pastures will be managed (sustainably or not) - PV and greenhouses have a big impact on beneficiaries with improved production and income | - Prepare action plans / guidelines / clear maps and exit strategy for PMPs / villagers (in Georgian) combined with building capacity pastoralist and municipality to collectively implement PMPs in a sustainable and climate change resilient way | Pastoralists need concrete and simple tools to manage pastures (as current PMPs read as long assessments | PMU | High | During implementation PMPs |
|  |  |  | See 1.1.1. Prioritize greenhouses |  |  |  |  |
| Equity | - The number of beneficiaries in Imeriti could have been higher but the targeting strategy can be justified. The involvement of females and shepherds in trainings and the implementation of PMPs is limited Females benefit relatively most from grants for PV and greenhouses. Youth benefits relatively most from grants for greenhouses. | - Females benefit relatively most from grants for PV and greenhouses, while youth relatively benefit most from grants for grants for greenhouses. | - Review / develop (tradition sensitive) targeting strategy for further involvement of females and shepherds in trainings and implementation of PMPs. | Limited involvement so far | PMU | Medium | During implementation PMPs |
|  |  |  | See 1.1.1. Prioritize greenhouses |  |  |  |  |
| Adaptive manage-ment | - The response to the implication of the pasture law not being in place came quite late, not helping reducing delays. (Proposed) changes are relevant and can mostly be justified. | - See 3.1. and 4.1. | See 2.1.2 and 3.1.1 and 3.1.2 | Maximize results / impacts for the remainder of the project |  |  |  |
| Scalability | - Scaling of investment in greenhouses seems most relevant from climate change perspective and beneficial to females and youth Scaling of investment in land categorization and registration is a pre-condition for the future sustainable / climate change resilient management of pastures. Scaling of investments in fodder conservation is relevant from climate change perspective and beneficiary perspective, but cost-effectivenss needs to be proven | - Replication / scale-up of grants for greenhouses seems most relevant from climate change perspective and beneficial to females and youth. | - Analyse feasibility of a business model / financial mechanism to replicate / scale-up greenhouses e.g. with loans (+see also 1.1.1. Prioritize greenhouses) | To ensure sustainability (in future development) | PMU | Low | Before end of the project |
|  |  |  | - Analyse cost-effectiveness of fodder conservation |  |  |  |  |
| Human and ecological sustain-ability and security | - It is not clear if most project beneficiaries are aware of the existing grievance mechanism. Negative project impacts seem to be limited as activities are very localised. However, a potential issue could arise over land ownership / conflict as result of land categorization and registration | - Awareness raising of the grievance mechanism may be important for its effectiveness | - Ensure project beneficiaries are aware of the grievance mechanism | To ensure no grievances are missed | PMU | medium | Remainder of the project |
|  |  |  | - Ensure all villagers of target villages are involved in land inventory and categorization process under the newly proposed output by the Land Agency and that there is consensus on categorization and ownership. | To avoid any potential conflict | PMU | High | From start of process |

# Introduction and background

## Evaluation features

This is the Mid-Term Review (MTR) covering the Adaptation Fund (AF) project ‘Dairy modernization and market access: adaptation component (DIMMAdapt), implemented by the International Fund for Agricultural Development and executed by the Ministry of Environmental Protection and Agriculture (MEPA) The MTR was prepared in line with AF evaluation policies.

Purpose: the AF Evaluation Policy requires AF projects with a duration >4 years to conduct a MTR. According to the AF Evaluation Policy, the objective of the MTR is to compare baseline results to MTR findings to assess progress and achievement. The MTR means to serve as an opportunity to critically assess administrative and technical issues and constraints and recommend a way forward in the project. Findings may also feed into the final evaluation.

Scope

- Time period being evaluated: 16 April 2021 until 16 September 2024. The MTR is submitted past halfway of the project due to execution delays and AF rejection of the previously submitted MTR.

- Target beneficiaries:

  - 6000 smallholder farmers, of which 30 percent female and 50 percent youth

  - 3900 market-vulnerable dairy producers

- Geographic coverage: The regions of Samtskhe-Javakheti, Imereti and Samegrelo Zveno (see Figure 1), with focus on Samtskhe-Javakheti region

- Baseline compared to MTR results: extent of the achievement of the project results in accordance with the original project results framework

Audience and intended use: Implementing entity, executing entity and other relevant stakeholders to consider recommendations made in the MTR for project way forward. Besides that, the MTR is required by the AF.

The MTR was prepared by an independent evaluator with the support of the project team and IFAD. A MTR mission was conducted 8-14 September 2024.

## Report introduction

This MTR covers the following:

- Executive summary

- Introduction and background

- Evaluation scope and objectives

- Evaluation approach and methods

- Evaluation findings and conclusions

- Lessons learned

- Evaluation recommendations

## Object of evaluation

This is the Mid-Term Review (MTR) covering the Adaptation Fund (AF) project ‘Dairy modernization and market access: adaptation component (DIMMAdapt), implemented by the International Fund for Agricultural Development and executed by the Ministry of Environmental Protection and Agriculture (MEPA). The MTR was prepared in line with AF evaluation policies.

Project goal: Reduce the vulnerability of the dairy value chain to the deleterious impacts of climate change.

Project objective: Enhance the resilience to climate change of vulnerable dairy producers.

Project components: Table 4 provides an overview of the project components, outcomes, outputs and budget

Table 4 AF project components as per initial project proposal

| Project/Programme Components | Expected Outcomes | Expected Outputs | Amount (USD) |
| --- | --- | --- | --- |
| 1. Climate-proofing pastoral ecosystem services (water management, pasture regeneration, and disaster risk reduction). | Outcome 1.1 An enabling environment developed through training and capacity building. | Output 1.1.1: Climate resilient and DRR solutions for pasture rehabilitation and increased productivity promoted. | 1,691,047 |
|  | Outcome 1.2. Pasture Management Plans Implemented | Output 1.2.1: Climate resilient and ecosystem-based adaptive pastoral investments implemented. | 1,103,064 |
|  |  | Output 1.2.2: A management mechanism is in place to screen and offset any potential cattle number increases from DiMMA | 40,000 |
| 2. Supporting the climate resilience of market vulnerable smallholders. | Outcome 2.1 Climate-smart technology demonstrations and livelihood diversification. | Output 2.1.1 Climate-smart technologies and alternative livelihood measures promoted. Output 2.1.2 Alternative, complementary, non-competitive, non-extractive livelihood jobs created. | 1,128,080 |
| Total |  |  | 3,922,191 |
| Project/Programme Execution Cost (9.1%) |  |  | 358,727 |
| Total Project Cost |  |  | 4,280,918 |
| Project Cycle Management Fee Charged by the Implementing Entity (8.5%) |  |  | 363,876 |
| Amount of Financing Requested |  |  | 4,644,794 |

## Implementation context

Agriculture / pastures: One in seven Georgians works in agriculture, forestry or related fields. Almost half of the rural households are working in agriculture-related fields. There are approximately 1 million heads of cattle in Georgia, of which about 50 percent dairy cows. Pastures can be divided into summer pastures and communal (lowland) pastures. The AF project proposal aims to address one of the main issues impacting pastures: degradation. Degradation happens due to lack of pasture management (e.g. managing overgrazing) and climate change impacts. As there is no pasture law / policy being implemented yet, sustainable management of pastures is lacking.

Climate change: The historical climate trend has been one of longer dry periods and more intense rainfall leading to increased pasture vulnerability through increased flooding, soil erosion, mudslides and landslides that have adversely impacted the pastoral ecosystem services which the rural poor, including women, youth and the landless poor depend on for their livelihoods. In the future, the agriculture sector is expected to have to further adapt to increasing temperatures and changing rainfall patterns that will increase the prevalence of periods of drought and intense rainfall.

Climate change impacts in Georgia include:

- Reducing water supply for animals due to increasing temperatures

- Reducing production livestock and agriculture due to droughts and heat waves.

- Loss of vegetation and biodiversity due to changing temperatures

Project complementarity: DiMMAdapt (especially component 1) aims to upscale in part the successful IFAD AMMAR project with GEF co-financing that successfully planted 40,000 trees for a length of 26 km x 20 meters wide. This project has protected around 1330 ha of land from erosion. DiMMAdapt aims to build on this success to support the design and development of climate resilient pastoral ecosystem services to reduce the negative impacts from climate change and climate variability on agricultural and rural livelihood development.

The AF project is part of the IFAD Dairy Modernization and Market Access (DiMMA) Programme in Georgia with two components:

- Component 1: Dairy Value Chain Development

- Component 2: Institutional and organisational development

Table 5 DiMMA project financing components

Developments during project implementation / execution

Originally the project proposal was designed and approved with the assumption that the Pasture Law would be adopted and enacted during project implementation. However, the Pasture Law has not been adopted yet. Due to parliamentary elections scheduled to take place on 26 October 2024, it is now anticipated that the pasture law will be submitted for approval in March / April 2025. This presented challenges for the implementation of the project, especially activities under component 1, which were supposed to ‘test’ the implementation of the pasture law. Besides that, initial targets were too ambitious.

For this reason and as part of redesign during the project implementation, 15 villages in one municipality in the Samtskhe-Javakheti were selected to test / anticipate for the pasture law, with a more informal approach to organizing villages / pastoralists for managing pasturelands, even though without formal pastureland registration yet. The reason for this push is that local pasture ownership / responsibility is seen as the only way to ensure future sustainable / climate change resilient management of these pasturelands.

To support this process, the subcontractor, the Regional Environmental Center for Caucasus (RECC) with the Ministry of Environmental Protection and Agriculture (MEPA), in close cooperation with the National Agency of Sustainable Land Management and Land Use Monitoring have been involved in the process of identification, surveying and registration of non-registered or uncategorized pastures and to develop PMPs for 15 villages.

Given these challenges and project time remaining, initial targets will not be reached and should be adjusted to focus on what is still relevant, feasible and impactful, also in line with the forthcoming DiMMAdapt+ project.

# Evaluation scope and objectives

## Evaluation scope

The AF Evaluation Policy requires AF projects with a duration longer than 4 years to conduct a MTR. According to the AF Evaluation Policy, the objective of the MTR is to compare baseline results to MTR findings to assess progress and achievement. The MTR means to serve as an opportunity to critically assess administrative and technical issues and constraints. Findings may also feed into the final evaluation.

- Time period being evaluated: 16 April 2021 until 16 September 2024. The MTR is submitted past halfway of the project due to execution delays and AF rejection of the previously submitted MTR.

- Target beneficiaries:

  - 6000 smallholder farmers, of which 30 percent female and 50 percent youth

  - 3900 market-vulnerable dairy producers

- Geographic coverage: The regions of Samtskhe-Javakheti, Imereti and Samegrelo Zveno (see Figure 1), with focus on Samtskhe-Javakheti region, as the project prioritized activities in this region.

- Baseline compared to MTR results: extent of the achievement of the project results in accordance with the original project results framework. The MTR focuses most on project component 1 as limited progress has been made under this component

MTR Findings should:

- Identify what works and why and what isn’t working and why to timely inform project implementation, course correction, and strategic decision making

- Recognition of successes and best practices, as well as areas with potential for upscaling or replication.

- Identify challenges or problems before they worsen and reveal good practices and strengths for that implementing entities to expand their successes.

- Improve project performance and bolster its impact and sustainability of results over the remainder of the project’s life.

- Organize and synthesize experiences and lessons. As the MTR involves learning during project implementation, experiences and lessons identified can be readily acted upon to improve project impacts and outcomes. Lessons also help to improve and instruct future climate change adaptation interventions.

## Evaluation criteria

The MTR sets about attempting to provide answers to the following questions (evaluation criteria):

- Relevance: Is the intervention doing the right thing?

- Coherence: How well does the intervention fit?

- Effectiveness: Is the intervention achieving its objectives?

- Efficiency: How well are resources being used?

- Impact: What difference does the intervention make?

- Equity: Are the benefits of the intervention shared fairly between groups and geographies?

- Adaptive management: Does the intervention make evidence-based decisions?

- Scalability: Can the intervention be replicated at a greater scale?

- Human and ecological sustainability and security: Does the intervention affect the ability of human and natural systems to support the equitable life of all species on the planet? Is the intervention sensitive to conflict and fragility?

## Evaluation questions

Table 6 Evaluation criteria and specific questions

| Criteria | Specific questions |
| --- | --- |
| Relevance: Is the intervention doing the right thing? | - Climate change: Are the project interventions helping project beneficiaries to adapt to droughts, heat waves, torrential rains? - Priorities: Are the project intervention in line with national and local priorities? - Geography: Is the focus on the Samtskhe-Javakheti region justified? |
| Coherence: How well does the intervention fit? | - How well do the activities fit together? |
| Effectiveness: Is the intervention achieving its objectives? | - Targets as set in the results framework reached and justification why yes or no? |
| Efficiency: How well are resources being used? | - Targets reached with available budget and timeline? |
| Impact: What difference does the intervention make? | - What is the impact / change for beneficiaries and are they satisfied with the result |
| Equity: Are the benefits of the intervention shared fairly between groups and geographies? | - Are the gender targets reached as per the results framework and gender action plan? Why yes / no? |
| Adaptive management: Does the intervention make evidence-based decisions? | - Are changes in implementation justified and relevant? |
| Scalability: Can the intervention be replicated at a greater scale? | - What interventions can be replicated and why yes / no? |
| Human and ecological sustainability and security: Does the intervention affect the ability of human and natural systems to support the equitable life of all species on the planet? Is the intervention sensitive to conflict and fragility? | - ESMP implemented properly (without negative effects)? |

## Evaluation matrix

Table 7 project evaluation matrix

| Question | Evaluation criteria | Indicators | Data source | Data collection techniques | Rationale for selection |
| --- | --- | --- | --- | --- | --- |
| - Climate change: Are the project intervention helping project beneficiaries to adapt to droughts, heat waves, torrential rains? | Relevance | Alignment with climate change adaptation needs as per national strategies; Key stakeholders and % beneficiaries responding positively | National climate change strategies Project beneficiaries | Analysis and interviews | To match criteria for evaluation Feasibility within MTR assignment |
| - Priorities: Is the project in line with national and local priorities? |  | Relevant ministries and municipalities confirming | Ministries Municipality | Interviews |  |
| - Geography: Is the focus on the Samtskhe-Javakheti (for implementing PMPs) region justified? |  | Climate change vulnerability of regions; justifications from key stakeholders | Climate change Vulnerability profile; key stakeholders | Data analysis and interviews |  |
| - How well do the activities fit together? | Coherence | Key stakeholders Match trainings and interventions | Project beneficiaries | Data analysis and interviews |  |
| - Targets as set in the results framework reached and justification why yes or no? | Effectiveness | See results framework | Results reporting, images, etc. | Analysis |  |
| - Targets reached with available budget and timeline? | Efficiency | See budget | Expenditure reporting | Analysis |  |
| - What is the impact / change for beneficiaries and are they satisfied with the result | Impact | Key stakeholders and % beneficiaries responding positively | Project beneficiaries | Data analysis and interviews |  |
| - Are the benefits of the intervention shared fairly between groups and geographies? Are gender targets reached as per the results framework and gender action plan? | Equity | See results framework | Results reporting, images, etc. | Analysis |  |
| - Are changes in implementation timely, justified and relevant? | Adaptive management | Positive impact changes Timely adaption of changes | Docs showing amendments | Analysis |  |
| - What interventions can be replicated and why yes / no? | Scalability | Identified replicable actions | Key stakeholders and beneficiaries | Data analysis and interviews |  |
| - ESMP implemented properly (without negative effects)? | Human and ecological sustainability and security | Risks and negative effects identified | Key stakeholders, site visits | Data analysis and interviews |  |

# Evaluation approach and methods

## Evaluation principles

Figure 2 AF Evaluation principles

## Data sources

- Primary data collection:

  - Questionnaires

  - Interviews

  - Data

  - Observations

  - Pictures

  - Maps

- Secondary data:

  - Project proposal and results framework

  - DiMMA Gender and youth strategy / plan

  - Environmental and Social management Plan (ESMP)

  - Project baseline / inception report

  - PPR 1, 2 and 3

  - Project implementation supervision mission reports

  - RECC reports

  - DiMMA MTR

  - Survey report in women’s empowerment in DiMMA project

## Data collection methods

See Table 7 section 3.4.

## Data analysis

The MTR will be conducted in line with AF policies and guidelines for evaluation. A mixed-methods approach will be used, including: (i) a desk review of project documents available, (ii) online interviews with the project team and relevant stakeholders; and (iii) face-to-face interviews with project beneficiaries in Samtskhe-Javakheti.

## Evaluation stakeholder engagement

Table 8 Evaluation stakeholder engagement

| Stakeholder | Level | Type of engagement |
| --- | --- | --- |
| IFAD | Project team and regional office | Online and in-person |
| PMU | Project team | In-person |
| MEPA-NASLM | Responsible for the project | In-person |
| RECC (Service provider) | Responsible for the project | In-person |
| Individual farmers / pastures | Individual | In-person |
| Women and youth farmers | Individual | In-person |

## Ethical considerations related to data collection and use

The Reviewer / evaluator respected the right of institutions and individuals to provide information in confidence; the sources of specific information and opinions in this report are not disclosed except where necessary and then only after confirmation with the consultee.

## Methodological limitations

Table 9 Methodological limitations

| Methodological limitations | Implications | Mitigation measures |
| --- | --- | --- |
| Limited time and feasibility for questionnaires with project beneficiaries | Limited reach / only sample which may not fully represent reality | To be covered by final evaluation |
| Focus mostly on Samtskhe-Javakheti region and related interventions | Limited review / evaluation of other regions due to strategic refocus on the project | Data analysis and online interviews about interventions in other regions |

# Evaluation findings and conclusions

Table 10 Evaluation findings and conclusions responding to evaluation questions and criteria

| Question | Nr | Evaluation criteria | Findings |  | nr | Conclusions |
| --- | --- | --- | --- | --- | --- | --- |
| Climate change: Are the project intervention helping project beneficiaries to adapt to droughts, heat waves, torrential rains? | 1 | Relevance | Output 1.1.1: Climate resilient and DRR solutions for pasture rehabilitation and increased productivity promoted |  | 1 | See also Table 11. Most activities are relevant from a climate change perspective. The development / implementation of PMPs, water conservation / management and grants for greenhouses stand out as most relevant. Not all activities as anticipated during project design will be implemented (such as planting of trees / wind breaks). All interventions are relevant in general for project beneficiaries, except perhaps reducing CO2 emissions. Solar energy has great benefits for beneficiaries, but not perse from a climate change adaptation perspective. The project is in alignment with national, municipal and community priorities. The focus on the Samtskhe-Javakheti (for implementing PMPs) is justified. M & E: - It is not clear why demos and trainings are currently reported / budgeted under 2.1.1 instead of 1.1.1 - Monitoring against all AF indicators could be stronger |
|  |  |  | Demos: fodder conservation | Reduces overgrazing and dependence on dry lands (+ presents alternative/affordable feeding options for farmers, reduces food loss and waste thus, reducing food-borne pathogens and release) |  |  |
|  |  |  | Demos: manure management | Not implemented yet |  |  |
|  |  |  | Trainings | Trainings support implementation of concrete activities. |  |  |
|  |  |  | Development / implementation PMPs | Ownership / responsibility for pastures is critical for its sustainable management / climate change resilience. This should also support adaptation efforts at village level |  |  |
|  |  |  | Output 1.2.1: Climate resilient and ecosystem-based adaptive pastoral investments implemented. |  |  |  |
|  |  |  | Controlled grazing / electric fencing | Reduces erosion (human and climate change – caused by droughts) (+helps to reduce carbon dioxide by conversion of carbon dioxide to soil organic carbon) |  |  |
|  |  |  | Water management (water points) | Support water conservation (responding to droughts / water scarcity) |  |  |
|  |  |  | Output 1.2.2: A management mechanism is in place to screen and offset any potential cattle number increases from DiMMA |  |  |  |
|  |  |  | Reducing CO2 emissions | No climate change adaptation benefit |  |  |
|  |  |  | Output 2.1.1 Climate-smart technologies and alternative livelihood measures promoted. |  |  |  |
|  |  |  | Animal feed processing equipment | Good benefit for beneficiaries |  |  |
|  |  |  | Solar energy-based alternative system | Justified when electricity is used for cooling at remote locations (to adapt to changing temperatures) but seems not always the case. |  |  |
|  |  |  | Output 2.1.2 Alternative, complementary, non-competitive, non-extractive livelihood jobs created. |  |  |  |
|  |  |  | Greenhouses | Support adaptation to changing temperatures |  |  |
| Priorities: is the project in line with national and local priorities? |  |  | Priorities: is the project in line with national and local priorities? | At national level, the project informs and prepares for the anticipated pasture law. The municipality of Akhaltsikhe visited during the MTR mission worked with RECC on the village-level PMPs, while the villages stress the need for sustainable / resilient pasture management |  |  |
| Geography: Is the focus on the Samtskhe-Javakheti (for implementing PMPs) region justified? |  |  | Geography: Is the focus on the Samtskhe-Javakheti (for implementing PMPs) region justified? | Among the AF target regions, Samtskhe-Javakheti is a region with a relative high share of pasture lands and livestock farming population. Like the other regions, these lands and people are impacted by climate change. The selection can be justified from a pasture management need and climate change perspective but could also have been a political decision. |  |  |
| How well do the activities fit together? | 2 | Coherence | DiMMA and DiMMAdapt | The DiMMAdapt project was designed to climate proof DiMMA project activities. In practice most of the project activities are the same or different. There is complementarity, but that does not necessarily mean DiMMAdapt activities climate proof DiMMA activities. | 2 | DiMMA and DIMMAdapt are complementary, but the complementarity / linkage of climate proofing DIMMA activities could have been stronger. Trainings support implementation of concrete activities, but the timing of capacity strengthening activities could have been better in some cases |
|  |  |  | Concrete and supporting / soft activities | Trainings support implementation of concrete activities. In some cases, as observed during the MTR field visit, trainings came a bit later than the concrete activities. |  |  |
| Targets as set in the results framework reached and justification why yes or no? | 3 | Effective-ness | Output 1.1.1: Climate resilient and DRR solutions for pasture rehabilitation and increased productivity promoted |  | 3 | See also Table 15 for details Project results under outcome 1 are limited, while progress under outcome 2 is better. Overall, project results are off-track due to project delays (caused by non-adoption / delayed pasture law), too ambitious targets set during project design with blended results frameworks, and perhaps some limitations to technical expertise to reach targets considering above. There is a need to extend the project to reach adjusted targets. Grants: - There seem to be a slight mismatch between initial targets set and budget spent / remaining (which could be due to timing reporting) - There seem to be a slight mismatch between initial targeting strategy (20 cows) and actual number of cows present (some 30) |
|  |  |  | Demos: fodder conservation | - 4 out of 10 planned (with initially higher target to support reaching 6000 farmers. The Project Management Unit (PMU) found a solution to deliver fodder processing training through ACDI-VOCA Farmer-to-Farmer (FtF) project. |  |  |
|  |  |  | Demos: manure management | 0 out of 6 planned (with initially higher target to support reaching 6000 farmers |  |  |
|  |  |  | Trainings | 51 beneficiaries out of 870 planned (with initially higher target to support reaching 6000 farmers). |  |  |
|  |  |  | Development / implementation PMPs | 15 PMPs / villages covering 500ha categorised pastureland out of 1000 ha of rehabilitated / 3800 improved management of pastureland (with initial target of 9500ha of pastureland rehabilitated) |  |  |
|  |  |  | Output 1.2.1: Climate resilient and ecosystem-based adaptive pastoral investments implemented. |  |  |  |
|  |  |  | Controlled grazing / electric fencing | 0 |  |  |
|  |  |  | Water management (water points) | 0 |  |  |
|  |  |  | Output 1.2.2: A management mechanism is in place to screen and offset any potential cattle number increases from DiMMA |  |  |  |
|  |  |  | Reducing CO2 emissions | 0 |  |  |
|  |  |  | Output 2.1.1 Climate-smart technologies and alternative livelihood measures promoted. |  |  |  |
|  |  |  | Animal feed processing equipment | 6 (not anticipated initially) |  |  |
|  |  |  | Solar energy-based alternative system | 75 with initially higher target to support reaching 3900 households. Some beneficiaries targeted have more cows than in targeting strategy. |  |  |
|  |  |  | Output 2.1.2 Alternative, complementary, non-competitive, non-extractive livelihood jobs created. |  |  |  |
|  |  |  | Greenhouses | 45 with initially higher target to support reaching 3900 households |  |  |
| Targets reached with available budget and timeline? | 4 | Efficiency |  | As of 31 August 2024, actual cumulative expenditures were USD 1.632 million (38%) (while it was 26% six months ago). Spending under component 1 is off-track. Spending under component 2 is on-track. Good progress has been observed for grants disbursements. Number of trainees per training is not high. The development of PMPs seems quite expensive. The proposed water interventions are not cheap but can be justified for pilots The amount per grant for PV is quite high considering the anticipated number of individual grants (households) targeted, but having lower amounts for PV does not make sense. The option of recruiting individual experts instead of capacity building service providers (CBSPs) seems to bear positive results both in terms of quality of training and value for money. The budget under execution costs is used efficiently and could support project extension (considering there were ineligible expenses first and the initial AF coordinator was not effective and resigned). Fund release from the ministry of finance has been slow, impacting grant calls | 4 | See also Table 19 for details Spending under component 1 is off-track. Spending under component 2 is on-track. The project activities are less cost-efficient than anticipated during project design, but this is due to targets set to ambitiously during project design. The number of trainees per training is not high. Some delays can be attributed to some capacity limitations (incl. former AF coordinator and PMU sometimes flagging potential issues a bit late) and slow fund release from the ministry of finance The remaining budget under execution costs could support project extension. Budget used for MTR is too high / not correct. should be corrected (see Table 19) |
| What is the impact / change for beneficiaries and are they satisfied with the result? | 5 | Impact | Output 1.1.1: Climate resilient and DRR solutions for pasture rehabilitation and increased productivity promoted |  | 5 | The beneficiaries met during the MTR are generally very happy with the results so far and planned actions. The implementation of the PMP has a potentially large impact on the way pastures are managed. Trainings for pastoralists to implementing the PMPs / manage pastures collectively in 15 villages are wanted by villagers Controlled grazing and water management is anticipated to increase the sustainability / climate change resilience of pastures PV and greenhouses have a big impact on beneficiaries with improved production and income |
|  |  |  | Demos: fodder conservation | Although demos are limited so far, the demos established will increase productivity per cow. Beneficiary met is satisfied with demo established so far |  |  |
|  |  |  | Demos: manure management | Not implemented yet |  |  |
|  |  |  | Trainings | Beneficiaries met are satisfied so far although some trainings came late or are still needed. Pastoralists met during the MTR stressed the need for trainings to implement PMP / manage pastures. |  |  |
|  |  |  | Development / implementation PMPs (potentially) | Although the PMPs are not implemented with the pastoralists / farmers yet, this could have a big impact, and beneficiaries stressed the need for the implementation / sustainable / cc resilient pasture management |  |  |
|  |  |  | Output 1.2.1: Climate resilient and ecosystem-based adaptive pastoral investments implemented. |  |  |  |
|  |  |  | Controlled grazing / electric fencing (potentially) | Although this is not implemented yet, it should have positive impacts on the sustainability / cc resilience of pastures and beneficiaries agree with the need |  |  |
|  |  |  | Water management (water points) potentially) |  |  |  |
|  |  |  | Output 1.2.2: A management mechanism is in place to screen and offset any potential cattle number increases from DiMMA |  |  |  |
|  |  |  | Reducing CO2 emissions | Although it is important the project does not lead to additional GHG emissions, this may not be relevant for beneficiaries at local level |  |  |
|  |  |  | Output 2.1.1 Climate-smart technologies and alternative livelihood measures promoted |  |  |  |
|  |  |  | Animal feed processing equipment | This supports the efficiency of local production |  |  |
|  |  |  | Solar energy-based alternative system | This has a high impact on beneficiaries as some had no electricity before and PV use reduces costs and supports productivity. Beneficiaries met are very satisfied – See also Table 11. |  |  |
|  |  |  | Output 2.1.2 Alternative, complementary, non-competitive, non-extractive livelihood jobs created. |  |  |  |
|  |  |  | Greenhouses | This has a high impact on beneficiaries as productivity and income increase. Beneficiaries met are very satisfied – See also Table 11. |  |  |
| Are the benefits of the intervention shared fairly between groups and geographies? Are gender targets reached as per the results framework and gender action plan? | 6 | Equity | Geographies | As per Table 17, most of the grant beneficiaries have been in the region of Samegrelo and Zemo Svaneti. Irmereti benefited the least (although budget per grant was higher) due to 1) share of poor population; 2) concentration of livestock production, 3) first come first serve system for grant applications. The region of Samtskhe-Javakheti will benefit the most for the remainder of the project with the PMPs and related concrete interventions being piloted there. | 6 | See also Table 15 for details The number of beneficiaries in Emeriti could have been higher but the targeting strategy can be justified. The involvement of females and shepherds in trainings and the implementation of PMPs is limited. This is due to a shift from pasture management activities to grants. This resulted in fewer opportunities for women to take on technical or leadership roles. Females benefit relatively most from grants for PV and greenhouses. Youth benefits relatively most from grants for greenhouses. |
|  |  |  | Gender | - Trainings: the share of females benefitting is lacking - PMPs: females participated in planning but targeting strategy for share is not clear - PV grants: share of female beneficiaries is very high while youth beneficiaries are lacking - Greenhouse grants: share of female beneficiaries is high and for youth very high. Certain areas show less involvement from women due to traditional gender roles. Some sheppards afraid of losing their job due to changes in pasture management and e.g. use of electric fensing. |  |  |
| Are changes in implementation timely, justified and relevant? | 7 | Adaptive management |  | The response to the implication of the pasture law not being in place came quite late. Also at national level, flexibility for alternative interventions seemed quite limited. Besides that, COVID restrictions also delayed activities (especially demos). The proposed new activity (1.1.2) to increase inventory and categorization of pasture lands anticipating the adoption of the pasture law is relevant and justified as this is a pre-condition for the sustainable management pastures / implementation PMPs. Considering the existing experience in RDA of issuing grants, it was decided to be more efficient to issue grants rather than establish demos and carry out trainings. | 7 | See also Table 19 for details The response to the implication of the pasture law not being in place came quite late, not helping reducing delays. (Proposed) changes are relevant and can mostly be justified. |
| What interventions can be replicated and why yes / no? | 8 | Scalability |  | Investments in greenhouses because of positive benefits/impact: climate control against heat, temperature changes and hailstones and improved productivity / income, especially benefitting females and youth Land categorization and registration is needed before pastures can be managed sustainability and in a climate change resilient way (through PMPs). This could potentially have a very big impact on pasture management practices in Georgia Investments in fodder conservation could reduce overgrazing and dependence on dry lands, while Improving productivity, but cost-effectivenss needs to be proven | 8 | See also Table 11 Scaling of investment in greenhouses seems most relevant from climate change perspective and beneficial to females and youth Scaling of investment in land categorization and registration is a pre-condition for the future sustainable / climate change resilient management of pastures. Scaling of investments in fodder conservation is relevant from climate change perspective and beneficiary perspective, but cost-effectivenss needs to be proven |
| ESMP implemented properly (without negative effects)? | 9 | Human and ecological sustain-ability and security |  | A grievance mechanism is functional via project regional representatives (RDA office) and FB page. However, it was not implemented at the start of the project Interventions have been screened against a national list of protected areas, critical biodiversity heritage sites. Negative project impacts seem to be limited as activities are very localised. A potential issue could arise over land ownership / conflict as result of land categorization and registration | 9 | It is not clear if most project beneficiaries are aware of the existing grievance mechanism. Negative project impacts seem to be limited as activities are very localised. However, a potential issue could arise over land ownership / conflict as result of land categorization and registration |

Table 11 Evaluation of project activities visited during mission

| Date | Location | Beneficiary | Project intervention | Proof of visit | Focus of intervention | Relevance (climate change) | Coherence | Effectiveness | Efficiency | Impact | Equity | Scalability | Adaptive management | Sustainability | Beneficiary satisfaction | Main issue / comment | Main benefit / comment | Recommendation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 11 Sept 2024 | Akhaltsike Village Kheoti | Nikoloz Zazadze | Fodder conser-vation demo |  | Mix fodder with brew: should lead to extra 2l milk / cow / day; trainings for multiple pastoralists |  |  |  |  |  |  |  |  |  |  | -Cost-effectiveness of buying brew not clear | -Reduces overgrazing and dependence on dry lands -Improves productivity | -Organize pasturalists to buy brew toghether |
| 11 Sept 2024 | Akhaltsikhe Village minadze | Vepkhia Tabatadze / Maia Inasaridze | Solar panels grants |  | No electricity before; electricity used for general purpose + some cooling milk |  |  |  |  |  |  |  |  |  |  | -Limited cc adaptation benefit -Targetting strategy to many cows? | -Big improvement for pasturalsist | -Ensure milk cooling benefit and focus on remote pasturalists -Prioritize greenhouse -Ensure proper targetting strategy |
| 11 Sept 2024 | Akhaltsikhe Village Greli | Giorgi Londaridze | Green-houses grants |  | Strawberries; improved productvity limited so far |  |  |  |  |  |  |  |  |  |  | -Capacity support was a bit late; some seedlings not of good quality -Strawbarries need shading in summer | -Climate control against heat, temperature changes and hailstones -Improved productivty / income -Benefits women and youth -Wish to expand | -Replicate / scale-up (with financial mechanism to replicate without grants) -Ensure capacity support from beginning -Provide shading equipment for crops that need this. |
| 13 Sept 2024 | Adigeni Village Benara | Lela Chilashvili |  |  | Various crops; improved producton and income |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13 Sept 2024 | Akhaltsikhe Vale | Ana Chitashvili |  |  | Mostly tomatoes; improved producton and income |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 Sept 2024 | Akhaltsikhe Village Tkemlana | 20 pastoralists present | Pasture Management Plans (PMPs) |  | Proposed pasture management intervention: controlled grazing (electric fensing), water conservation (water points) and seedlings |  |  |  |  |  |  |  |  |  |  | -Misses clear action plan / guidelines for pasturalist, incl; clear map and translation -Some water interventions bit expensive but justified as pilot -Some sheppards afraid of losing job | -Controled grazing against degradation / erosion; water conservation against reducing water availability Potentially big impact | - Prepare clear action plan / guidelines / map in Georgian; - Have capacity support for pasturalists and municipality for implenentation PMPs for after project - Guide how electric fensing can be used most effieciently by e.g. moving between pasture areas -Ensure role sheppard secured from beginning |
| 12 Sept 2024 | Akhaltsikhe Village Mugareti | 15 pastoralists present |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 Sept 2024 | Akhaltsikhe Village Andriacminda | 4 pastoralists present |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Table 12 Summary of the main issues identified during MTR

| Issue | Specifics | Root cause | Other cause | Mitigation measures so far |
| --- | --- | --- | --- | --- |
| Delays project implementation / execution | Mostly component 1 and related to pasture management / restoration interventions | - Absence of legal framework for sustainable management pastures (i.e. pasture law not adopted yet) - Initial targets too ambitious for budget and capacity | - Lengthy process land categorization and registration - Former AF coordinator not effective and resigned - Adaptive management slow and some technical capacity limitations - PMU not flagging issues on time - Delays fund release from ministry of finance | - Pilot PMPs anticipating adoption of law - Redesigns and redistributions |
| Targets not reached |  |  |  | - Proposed reduction targets and redistribution to outcome 2 |
| Some interventions have limited relevance / coherence | PV and CO2 reduction do not necessarily support climate change adaptation | - Blended project with blended results framework | - Preference beneficiaries - Limited awareness adaptation needs / technical expertise | - New AF coordinator |
| Ineligible expenses | AF funds used for PMU too high | - PMU mismanagement funds | - Initially approved by IFAD | - Redistributed funds back to AF |

# Evaluation lessons learned

Table 13 Lessons learned until MTR

| Evaluation criteria | Conclusions | Main lessons |
| --- | --- | --- |
| Relevance | - Most activities are relevant from a climate change perspective. The development / implementation of PMPs, water conservation / management and grants for greenhouses stand out as most relevant. Not all activities as anticipated during project design will be implemented (such as planting of trees / wind breaks). All interventions are relevant in general for project beneficiaries, except perhaps reducing CO2 emissions. Solar energy has great benefits for beneficiaries, but not per se from a climate change adaptation perspective. The project is in alignment with national, municipal and community priorities. The focus on the Samtskhe-Javakheti (for implementing PMPs) is justified. M & E: - It is not clear why demos and trainings are sometimes reported / budgeted under 2.1.1 instead of 1.1.1 - Monitoring against all AF indicators could be stronger | - The development / implementation of PMPs, water management / conservation activities and grants for greenhouses stand out as the most relevant activities from a climate change perspective in the project |
| Coherence | - DiMMA and DIMMAdapt are complementary, but the complementarity / linkage of climate proofing DIMMA activities could have been stronger. Trainings support implementation of concrete activities, but the timing of capacity strengthening activities could have been better in some cases | - Complementarity of projects need to be ensured while also safeguarding separate project targets - Capacity building activities need to support the effective implementation of concrete interventions and be timely |
| Effective-ness | - Project results under outcome 1 are limited, while progress under outcome 2 is better. Overall, project results are off-track due to project delays (caused by non-adoption / delayed pasture law) and too ambitious targets set during project design and perhaps some limitations to technical expertise to reach targets considering above. There is a need to extend the project to reach adjusted targets Grants: - There seem to be a slight mismatch between initial targets set and budget spent / remaining (which could be due to timing reporting) - There seem to be a slight mismatch between initial targeting strategy (20 cows) and actual number of cows present (higher) | - Targets set during project design were too ambitious and the main mitigation measures for the main potential risk of delays were not in place. Related future project need to better assess feasibility of targets and potential delay risks at design and inception phase |
| Efficiency | - Spending under component 1 is off-track. Spending under component 2 is on-track. The project activities are less cost-efficient than anticipated during project design, but this is due to targets set to ambitiously during project design. The number of trainees per training is not high. Some delays can be attributed to some capacity limitations (incl. former AF coordinator and PMU sometimes flagging potential issues a bit late) and slow fund release from the ministry of finance The remaining budget under execution costs could support project extension. Budget used for MTR is too high / not correct. should be corrected (see Table 19) – In this regard, as reported in the PPR3, costs previously charged against the AF budget for MTR have been declared ineligible expenditures thereunder and action has been taken by the Implementing Agency (IFAD) to reverse these charges through a compensation exercise involving the IFAD loan funding for the DiMMA programme, which will result in offsetting the relevant amount. The amount incurred for the DiMMAdapt MTR will be well below the budgeted amount in line with the AF policy (USD 23,000) and the combined costs of the MTR and the completion evaluation of DiMMAdapt will remain within the USD 46,000 limit. | - Potential delay risks should also be assessed / monitored and quickly responded to during project implementation |
| Impact | - The beneficiaries met during the MTR are generally very happy with the results so far and planned actions. The implementation of the PMP has a potentially large impact on the way pastures are managed. Trainings for pastoralists to implementing the PMPs / manage pastures collectively in 15 villages are wanted by villagers Controlled grazing and water management is anticipated to increase the sustainability / climate change resilience of pastures PV and greenhouses have a big impact on beneficiaries with improved production and income | - Beneficiaries seem to be happy with all project activities leading to increased production and income. - The implementation of the PMPs has a potentially large impact on the way pastures will be managed (sustainably or not) - PV and greenhouses have a big impact on beneficiaries with improved production and income |
| Equity | - The number of beneficiaries in Imereti could have been higher but the targeting strategy can be justified. The involvement of females and shepherds in trainings and the implementation of PMPs is limited Females benefit relatively most from grants for PV and greenhouses. Youth benefits relatively most from grants for greenhouses. | - Females benefit relatively most from grants for PV and greenhouses, while youth relatively benefit most from grants for greenhouses. |
| Adaptive manage-ment | - The response to the implication of the pasture law not being in place came quite late, not helping reducing delays. (Proposed) changes are relevant and can mostly be justified. | - See 3.1. and 4.1. |
| Scalability | - Scaling of investment in greenhouses seems most relevant from climate change perspective and beneficial to females and youth Scaling of investment in land categorization and registration is a pre-condition for the future sustainable / climate change resilient management of pastures. Scaling of investments in fodder conservation is relevant from climate change perspective and beneficiary perspective, but cost-effectivenss needs to be proven | - Replication / scale-up of grants for greenhouses seems most relevant from climate change perspective and beneficial to females and youth. |
| Human and ecological sustain-ability and security | - It is not clear if most project beneficiaries are aware of the existing grievance mechanism. Negative project impacts seem to be limited as activities are very localised. However, a potential issue could arise over land ownership / conflict as result of land categorization and registration | - Awareness raising of the grievance mechanism may be important for its effectiveness |

# Evaluation recommendations

Table 14 Recommendations for the remainder of the project (linked to conclusions and lessons learned)

| Evaluation criteria | Conclusions | Main lessons | Recommendations for the remainder of the project | Justification | Respon-sible | priority | Time-frame |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Relevance | - Most activities are relevant from a climate change perspective. The development / implementation of PMPs, water conservation / management and grants for greenhouses stand out as most relevant. Not all activities as anticipated during project design will be implemented (such as planting of trees / wind breaks). All interventions are relevant in general for project beneficiaries, except perhaps reducing CO2 emissions. Solar energy has great benefits for beneficiaries, but not perse from a climate change adaptation perspective. The project is in alignment with national, municipal and community priorities. The focus on the Samtskhe-Javakheti (for implementing PMPs) is justified. M & E: - It is not clear why demos and trainings are currently reported / budgeted under 2.1.1 instead of 1.1.1 - Monitoring against all AF indicators could be stronger | - The development / implementation of PMPs, water management / conservation activities and grants for greenhouses stand out as the most relevant activities from a climate change perspective in the project | - Prioritize / maximize the implementation of PMPs, water management activities and greenhouses for the remainder of the project and consider redistribution of budget to these activities | Most relevant, and impactful | IFAD and PMU | Medium | Remainder of the project |
|  |  |  | - Improve monitoring against all relevant AF indicators as suggested in Table 15 | Supports improved reporting to the AF | PMU | Low | Remainder of the project |
| Coherence | - DiMMA and DIMMAdapt are complementary, but the complementarity / linkage of climate proofing DIMMA activities could have been stronger. Trainings support implementation of concrete activities, but the timing of capacity strengthening activities could have been better in some cases | - Complementarity of projects need to be ensured while also safeguarding separate project targets - Capacity building activities need to support the effective implementation of concrete interventions and be timely | - Safeguard AF targets | To maximize results under DiMMAdapt | AF coordinator PMU | Medium | Remainder of the project |
|  |  |  | - Analyse and prioritize project activities that prepare for and complement the future DiMMAdapt+ project | To ensure sustainability, efficiency and avoid duplication |  |  |  |
|  |  |  | - Ensure capacity building activities take place on time to support effective implementation concrete activities | To maximize effectiveness |  |  |  |
| Effective-ness | - Project results under outcome 1 are limited, while progress under outcome 2 is better. Overall, project results are off-track due to project delays (caused by non-adoption / delayed pasture law) and too ambitious targets set during project design and perhaps some limitations to technical expertise to reach targets considering above. There is a need to extend the project to reach adjusted targets Grants: - There seem to be a slight mismatch between initial targets set and budget spent / remaining (which could be due to timing reporting) - There seem to be a slight mismatch between initial targeting strategy (20 cows) and actual number of cows present (sometimes 30) | - Targets set during project design were too ambitious and the main mitigation measures for the main potential risk of delays were not in place. Related future project need to better assess feasibility of targets and potential delay risks at design and inception phase | - Update and request DiMMAdapt restructuring proposal with the project extension till June 2026 This proposal should incorporate the new output on identification, categorization and registration of pastures in the new municipality as proposed by the Land Agency. | Without some activities will not be implemented and targets reached limited | IFAD and PMU | High | By Mid Oct 2024 latest |
|  |  |  | - Review the targets for grants and review the targeting strategy for beneficiaries with correct number of cattle | Risk of non-feasible targets and inappropriate targeting | PMU | Low | Before next grant call |
| Efficiency | - Spending under component 1 is off-track. Spending under component 2 is on-track. The project activities are less cost-efficient than anticipated during project design, but this is due to targets set to ambitiously during project design. The number of trainees per training is not high. Some delays can be attributed to some capacity limitations (incl. former AF coordinator and PMU sometimes flagging potential issues a bit late) and slow fund release from the ministry of finance The remaining budget under execution costs could support project extension. Budget used for MTR is too high / not correct. should be corrected (see Table 19). – In this regard, as reported in the PPR3, costs previously charged against the AF budget for MTR have been declared ineligible expenditures thereunder and action has been taken by the Implementing Agency (IFAD) to reverse these charges through a compensation exercise involving the IFAD loan funding for the DiMMA programme, which will result in offsetting the relevant amount. The amount incurred for the DiMMAdapt MTR will be well below the budgeted amount in line with the AF policy (USD 23,000) and the combined costs of the MTR and the completion evaluation of DiMMAdapt will remain within the USD 46,000 limit. | - Potential delay risks should also be assessed / monitored and quickly responded to during project implementation and | - Timely launch procurement process for two separate service providers to implement PMPs | To avoid delay and lack of capacity one service provider | PMU | High | By end Nov 2024 latest |
|  |  |  | - Ensuring adequate / timely state (ministry of finance) allocation to secure timely payments for project activities (esp. 4th grant calls) | To avoid delays | PMU | High | By end Nov 2024 latest |
|  |  |  | - Maximize the trainees per trainings | To reach more beneficiaries | PMU | Medium | Remainder of the project |
|  |  |  | - Review and update reporting on PMU / evaluation spending to fix previous errors) | Current spending on evaluation is reporting inaccurately | PMU | Low | Before end of the project |
| Impact | - The beneficiaries met during the MTR are generally very happy with the results so far and planned actions. The implementation of the PMP has a potentially large impact on the way pastures are managed. Trainings for pastoralists to implementing the PMPs / manage pastures collectively in 15 villages are wanted by villagers Controlled grazing and water management is anticipated to increase the sustainability / climate change resilience of pastures PV and greenhouses have a big impact on beneficiaries with improved production and income | - Beneficiaries seem to be happy with all project activities leading to increased production and income. - The implementation of the PMPs has a potentially large impact on the way pastures will be managed (sustainably or not) - PV and greenhouses have a big impact on beneficiaries with improved production and income | - Prepare action plans / guidelines / clear maps and exit strategy for PMPs / villagers (in Georgian) combined with building capacity pastoralist and municipality to collectively implement PMPs in a sustainable and climate change resilient way | Pastoralists need concrete and simple tools to manage pastures (as current PMPs read as long assessments | PMU | High | During implementation PMPs |
|  |  |  | See 1.1.1. Prioritize greenhouses |  |  |  |  |
| Equity | - The number of beneficiaries in Emeriti could have been higher but the targeting strategy can be justified. The involvement of females and shepherds in trainings and the implementation of PMPs is limited Females benefit relatively most from grants for PV and greenhouses. Youth benefits relatively most from grants for greenhouses. | - Females benefit relatively most from grants for PV and greenhouses, while youth relatively benefit most from grants for grants for greenhouses. | - Review / develop (tradition sensitive) targeting strategy for further involvement of females and shepherds in trainings and implementation of PMPs. | Limited involvement so far | PMU | Medium | During implementation PMPs |
|  |  |  | See 1.1.1. Prioritize greenhouses |  |  |  |  |
| Adaptive manage-ment | - The response to the implication of the pasture law not being in place came quite late, not helping reducing delays. (Proposed) changes are relevant and can mostly be justified. | - See 3.1. and 4.1. | See 2.1.2 and 3.1.1 and 3.1.2 | Maximize results / impacts for the remainder of the project |  |  |  |
| Scalability | - Scaling of investment in greenhouses seems most relevant from climate change perspective and beneficial to females and youth Scaling of investment in land categorization and registration is a pre-condition for the future sustainable / climate change resilient management of pastures. Scaling of investments in fodder conservation is relevant from climate change perspective and beneficiary perspective, but cost-effectivenss needs to be proven | - Replication / scale-up of grants for greenhouses seems most relevant from climate change perspective and beneficial to females and youth. | - Analyse feasibility of a business model / financial mechanism to replicate / scale-up greenhouses e.g. with loans (+see also 1.1.1. Prioritize greenhouses) | To ensure sustainability (in future development) | PMU | Low | Before end of the project |
|  |  |  | - Analyse cost-effectiveness of fodder conservation |  |  |  |  |
| Human and ecological sustain-ability and security | - It is not clear if most project beneficiaries are aware of the existing grievance mechanism. Negative project impacts seem to be limited as activities are very localised. However, a potential issue could arise over land ownership / conflict as result of land categorization and registration | - Awareness raising of the grievance mechanism may be important for its effectiveness | - Ensure project beneficiaries are aware of the grievance mechanism | To ensure no grievances are missed | PMU | medium | Remainder of the project |
|  |  |  | - Ensure all villagers of target villages are involved in land inventory and categorization process under the newly proposed output by the Land Agency and that there is consensus on categorization and ownership. | To avoid any potential conflict | PMU | High | From start of process |

# Annexes

## Project results framework and analysis of performance until MTR

Table 15 Project results framework as per initial proposal, achievement by MTR, findings / conclusions and recommendations

| Objective, outcome and output | Indicator | Target | Achieved by MTR | Planned total | Findings / conclusion | Recommendation |
| --- | --- | --- | --- | --- | --- | --- |
| Overall objective: Enhancing the resilience to Climate Change of vulnerable dairy producers. | Number of hectares of pasture rehabilitated, restored or protected | 9500 ha | 0 (500 ha categorised under PMPs) | 1000 ha rehabilitated 3,800 hectares pastures under improved management (through PMPs preparation and Field mobilization and training of de-facto pasture users on rotational grazing) | Results off track Target off track Initial target was too ambitious with available budget. Even with no delay reaching this target was not feasible | Request approval for revised target |
|  | Number of households benefitting from climate resilient improvements Suggest aligning M & E with AF core indicator: No of beneficiaries - Total - % female - % youth | 3900 households (12870 people) | 177 (81+45+51) - Grants: 126 - PMP users: 0 - Trained: 51 - 65 % female - 38 % youth | 1,313 households will benefit from climate resilient improvements. (1136 remaining) Grants: 443 (317 remaining) - PMP users: 590 (40 per villages - Trained: 280 (229 remaining) - 30 % female - 30 % youth | Results off track Target off track Initial target was too ambitious with available budget. Even with no delay reaching this target was not feasible. | Request approval for revised target Consider reallocating budget for more grants focused on greenhouses Suggest reaching more beneficiaries trained Suggest aligning M & E with AF indicator (see indicator column) |
| Component 1: Climate-proofing pastoral ecosystem services (water management, pasture regeneration, and disaster risk reduction) |  |  |  |  |  |  |
| Outcome 1.1 An enabling environment developed through training and capacity building. | Suggest aligning M & E with AF Indicator 3.1: Increase in application of appropriate adaptation responses (% and sector) |  |  |  |  | Suggest aligning M & E with AF indicator (see indicator column) |
| Output 1.1.1. Climate change resilient and DRR solutions for pasture rehabilitation and increased productivity promoted | Number of farmers receiving pasture management, silage and fodder conservation demonstrations Suggest aligning M & E with AF Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | 6000 farmers - 30 % female - 50 % youth Awareness raising demonstrations | 51 - 14% female - 29% youth Trainings: 4 Exchange visits: 1 International exchange visits: 1 Demos: 4 4 fodder conservation 0 manure management | 870 (819 remaining) - 30% female - 30% youth - Trained on fodder conservation and energy saving: 280 - PMP users: 590 Demos: 16 (12 remaining) - 10 fodder conservation - 6 manure management PMPs - 15 of which - 4 targeted for physical interventions | Results off track Target off track Initial target was too ambitious with available budget. Females reached for trainings is limited Without delay there could have been more demos 10 trainees per demo Preparation of PMP was expensive (28k per PMP) | Request approval for revised target Focus on trainings for pastoralists / farmers informally organised (+ municipality) for implementing the PMPs (15 villages), including trainings on controlled grazing (electric fencing, fodder conservation and manure management Maximize trainees per training Ensure participation women (and youth) Suggest aligning M & E with AF indicator (see indicator column |
|  | Number of PUA’s receiving training | 76 PUA’s to receive capacity building in pasture management | 0 | 15 villages | Results off track Target off track Due to absence legal framework working officially with PUA/PUUs is impossible | Work with target municipality, villages and with pastoralists / farmers informally organised |
| Outcome 1.2. Pasture management plans implemented | Suggest aligning M & E with AF indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress (from ineffective to very effective) |  |  |  |  | Suggest aligning M & E with AF indicator (see indicator column |
| Output 1.2.1. Climate resilient and ecosystem-based adaptive pastural investments implemented | Number of ha of pastureland rehabilitated, improved or protected Suggest aligning M & E with AF Core Indicator 5.1: Natural Assets protected or rehabilitated (nr ha and from ineffective to very effective) | 9500 ha | 0 (500 ha categorised under PMPs) | 1000 ha rehabilitated (with electric fencing for controlled grazing, water management interventions and seedlings) 3800 ha pastures under improved management (covering 1000 ha of rehabilitated pastures / 15 villages using PMPs) At least 15,900 ha (15% of 106,163 ha) pastures are registered | Results off track Target off track Initial target was too ambitious with available budget. 1000ha rehabilitation and 3800 ha under improved management seems maximum possible (when project is extended) Interventions are relevant and costs are reasonable. Water interventions are not cheap but can be justified for pilots | Request approval for revised target Extend project with one year to reach revised target |
|  | Number of households benefitting from pasture rehabilitation | 3900 households (12870 people) | 177 (75+45+6+51) - Grants: 126 - PMP users: 0 - Trained: 51 - 65% female - 38% youth | 1,313 households will benefit from climate resilient improvements. (1136 remaining) Grants: 443 (317 remaining) - PMP users: 590 (40 per villages - Trained: 280 (229 remaining) - 30 % female - 30 % youth | Results off track Target off track Initial target was too ambitious with available budget. Even with no delay reaching this target was not feasible. Remaining grant target of 215 may not be feasible with remaining budget. With current budget 190 seems feasible | Request approval for revised target Consider reallocating budget for more grants Suggest reaching more beneficiaries trained |
| Output 1.2.2. A management mechanism is in place to screen and offset any potential cattle number increases from DiMMA (GHG) | tCO2eq resulting from DiMMA cattle numbers | A max of 0 tCO2eq will result from DiMMA cattle numbers | Initial assessment by FAO showing reduced emission | Ex-act planned for Q1 2025 Offsetting of 150,000 tCO2eq from DiMMA | Still feasible | Continue as planned |
| Component 2: Supporting the climate resilience of market vulnerable smallholders |  |  |  |  |  |  |
| Outcome 2.1 Climate smart technology demonstrations and livelihood diversification. | Suggest aligning M & E with AF Indicator 6.1: Increase in households and communities having more secure access to livelihood assets (no HH, % female and from no improvement to high improvement) |  |  |  |  | Suggest aligning M & E with AF indicator (see indicator column |
| Output 2.1.1 Climate-smart technologies and alternative livelihood measures promoted. | Number of farmers exposed to climate smart technology demonstrations in milk-precooling, AI and crossbreeding and solar power. Suggest aligning M & E with AF Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies (no and type of asset and adaptation strategy) Consider AF Core Indicator 6.1.2: Increased income, or avoided decrease in income (nr HH, income source and income level | 3,900 market vulnerable farmers to receive climate-smart demonstrations. - 30 % female - 50 % youth | 75 Solar energy-based alternative system: 75 - 90% female - 12% youth | Approx. 138 (63 remaining with proposed new budget - 90% female - 30% youth | Target off track but spending on track Price per grant is reasonable but impossible to reach initial target beneficiaries. This means initial design / targeting strategy was wrong or grants should have been much smaller. For PV this is difficult. Female beneficiaries of grants is high but low for youth. It is not feasible to reach target for youth | Request approval for revised target Consider reallocating remaining budget for greenhouses Suggest aligning M & E with AF indicator (see indicator column |
| Output 2.1.2 Alternative, complementary, non-competitive, non-extractive livelihood jobs created. | Number of households benefitting from alternative non-extractive industry activities. Suggest also M & E for AF Indicator 6.1.1 and 6.1.2 | 250 jobs - 30% female - 50% youth will be created for the market vulnerable beneficiaries. | 45 Greenhouse construction - 62% female - 100% youth | Approx 299 (254 remaining) with proposed new budget - 60% female - 100% youth | Target off track but spending on track Price per grant is reasonable but impossible to reach initial target beneficiaries, which means initial design / targeting strategy was wrong or grants should have been much smaller. For Greenhouses this is difficult. With proposed new budget initial target should be reached Female and youth beneficiaries of grants is high | Request approval for revised target Consider reallocating budget for more grants for greenhouses Suggest aligning M & E with AF indicator (see indicator column |

## Details of results until MTR

Exchange visits (under output 1.1.1)

- Farmers from the Samegrelo-Zemo Svaneti region visited an animal fodder conservation farm in the Shida Kartli region (Gori municipality);

- Farmers (pasture users) from the Samtskhe-Javakheti region traveled to the Kakheti region to observe rehabilitated pastures under the project "Achieving Land Degradation Neutrality (LDN)," implemented by the Food and Agriculture Organization of the United Nations (FAO).

- Study Tours to Switzerland with delegation members from MEPA, NASLM, RECC, PIU, Including Deputy Minister of MEPA. The key objective of the Study Tour was to become familiar to the experience and lessons learnt by Swiss colleagues.

Pasture rehabilitation (under output 1.1.1)

- 15 Pasture Management Plans (PMPs) developed

- 4 Detailed PMPs where physical interventions are planned covering 1000 ha (in villages Mugareti, Khaki, Tkemplana and Andriatsminda – in one municipality

Demo Plots (reported under 2.1.1 but should perhaps been under 1.1.1)

4 'Fodder Conservation' demonstration plots

Trainings (reported under 2.1.1 but should perhaps been under 1.1.1)

Table 16 Training activities under AF component

| Activities | Number of trained individuals | Male | Female |
| --- | --- | --- | --- |
| Training (4) on animal fodder conservation | 35 | 30 | 5 |
| Exchange visit – rehabilitated pasture | 13 | 13 |  |
| Exchange visit - animal fodder conservation | 3 | 1 | 2 |
| Total | 51 | 44 | 7 |

Grants (under output 2.1.1 and 2.2.1.)

Table 17 Disbursed grants disaggregated by Type of investment and Region

| Type Of Investment | Imereti | Samegrelo and Zemo Svaneti | Samtskhe-Javakheti | Total |
| --- | --- | --- | --- | --- |
| Animal feed processing equipment | 4 | 0 | 2 | 6 |
| Greenhouse construction | 5 | 29 | 11 | 45 |
| Solar energy-based alternative system | 2 | 64 | 9 | 75 |
| Total | 11 | 93 | 22 | 126 |

*Reasons for geographical distribution: 1) poor population; 2) concentration of livestock production, 3) first come first serve system for grant applications

Summary results until MTR

Table 18 Summary results until MTR

| Components | Units | Planned 2024 | Actual by MTR | Appraisal Target (without proposed changes | % Cumu-lative Actual |
| --- | --- | --- | --- | --- | --- |
| AF output 1.1.1. |  |  |  |  |  |
| Manure Management demos | demo | 6 | 0 | 20 | 0% |
| Training support and Exchange visits on pasture management and fodder conservation | visit | 2 | 2 | 4 | 50% |
| International exchange visits on pasture management | lump sum | 0 | 1 | 2 | 50% |
| AF output 2.1.1. |  |  |  |  |  |
| Fodder conservation demos | demo | 6 | 4 | 10 | 40% |
| Field trainings session demo sites (4 demos and on exchange visit) | session | 34 | 5 | 71 | 7% |
| Animal feed processing equipment | Grants | 0 | 6 | na | % |
| Solar energy-based alternative | Grants | 42 | 75 | 90 | 80% |
| AF output 2.2.1 |  |  |  |  |  |
| Greenhouse construction | Grants | 82 | 45 | 125 | 36% |

## Summary of budget and analysis of budget spent until MTR

Table 19 Budget spent until MTR and findings / comments

| Original Item/activity | Original Amount (USD) | Revised Item/activity | Amount actual Spent (USD) |  |  | Spent + planned. /committed USD) | Cost-effectiveness / efficiency analysis |  |  | Findings / Conclusions / Recommendations |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1: Climate-proofing pastoral ecosystem services (water management, pasture regeneration, and disaster risk reduction) |  |  |  |  |  |  |  |  |  |  |  |
| Outcome 1.1. An enabling environment developed through training and capacity building. |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1.1: Climate resilient and DRR solutions for pasture rehabilitation and increased productivity promoted. |  |  |  |  |  |  |  |  |  |  |  |
| Training support and exchange visits for the development of Pasture Management Plans by the PUA’s and smallholder and progressive farmers (GIS mapping, PMP format, threat analysis, adaptation strategy, adaptation activities, management plan, fees and revenue generation, business plan for PAF grant, herd and grazing management). | $475,403 | Exchange visits for the development of Pasture Management Plans by the PUA’s and smallholder and progressive farmers, herd and grazing management | $51,135 |  |  | $51,135 | Most of the budget used for international exchange training |  |  | Spending off track Some trainings are not cost-efficient due to limited participants per training Suggest allocating enough budget for trainings for pastoralists / farmers informally organised (+ municipality) for implementing the PMPs (15 villages), including on controlled grazing (electric fencing, fodder conservation, manure management, etc. |  |
| Silage production (fodder conservation) demonstrations (including the production and dissemination of awareness raising and visual learning materials). | $358,856 | 6 Silage production (fodder conservation) demonstrations (including the production and dissemination of awareness raising and visual learning materials). | $0 |  |  | $12,000 | USD 2000 / fodder demo USD 2000 / direct beneficiary, while assuming 20 more benefitting = USD 100 pp |  |  | Spending off track |  |
| Manure composting demonstrations (including the production and dissemination of awareness raising and visual learning materials). | $34,464 | Manure composting demonstrations (including the production and dissemination of awareness raising and visual learning materials). | $0 |  |  | $0 | $0 |  |  | Spending off track |  |
| Development of Pasture Management Plans | $140,119 | Development of Pasture Management Plans (RECC) | $278,682 |  |  | $426,384 | 28k / PMP |  |  | Overspent Price per PMP seems quite expensive. |  |
| Pasture adaptation demonstrations for PUA farmers (including the restoration of degraded pastures; water management measures; soil conservation; mudslide and flood mitigation measures; riverine vegetation promotion). | $472,000 | cancelled | $0 |  |  | $0 |  |  |  | Spending off track Will be no results |  |
| Pasture management demonstrations for private pasture farmers (including the production and dissemination of awareness raising and visual learning materials). | $149,643 | cancelled | $0 |  |  | $0 |  |  |  | Spending off track Will be no results |  |
| On-demand demonstrations (including the production and dissemination of awareness raising and visual learning materials). | $60,562 | cancelled | $0 |  |  | $0 |  |  |  | Spending off track Will be no results |  |
| Sub-total | $1,691,047 | Sub-total | $341,817 |  |  | $489,519 |  |  |  |  |  |
| Output 1.1.2 (NEW): Inventory and Registration of Pasturelands. |  |  |  |  |  |  |  |  |  |  |  |  |
| newly proposed activities | $0 | Purchase of Equipment and Goods | $0 |  |  | $167,860 |  |  |  |  |  |
|  | $0 | Purchase of 2 field vehicles | $0 |  |  | $74,000 |  |  |  |  |  |
|  | $0 | Operating expenses | $0 |  |  | $24,000 |  |  |  |  |  |
|  | $0 | Identification, categorization and surveying of pasturelands and hayfields in target areas | $0 |  |  | $316,568 |  |  |  |  |  |
|  | $0 | Assessment of pasture vegetation types and their condition | $0 |  |  | $59,480 |  |  |  |  |  |
|  | $0 | Mobilization of communities for identification and mapping of users. | $0 |  |  | $58,400 |  |  |  |  |  |
|  | $0 | Submission for registration. | $0 |  |  | $93,812 |  |  |  |  |  |
| Sub-Total | $0 | Sub-total | $0 |  |  | $794,120 |  |  |  |  |  |
| Outcome 1.2. Pasture Management Plans Implemented. |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.1: Implementation of climate resilient and ecosystem-based adaptive pastoral grants. |  |  |  |  |  |  |  |  |  |  |  |
| Restoration of degraded pastures, reforestation and wind breaks. | $1,103,064 | Restoration of degraded pastures - to fund water management, controlled grazing and seedling interventions in 4 villages | $0 |  |  | $244,552 | 1000 ha = USD1100 ha |  |  | Spending off track but still feasible Interventions are relevant and costs are reasonable. Water interventions are not cheap but can be justified for pilots |  |
| Water management measures to favour pasture resilience. |  |  |  |  |  |  |  |  |  |  |  |
| Measures to prevent soil erosion, mudslides and floods. |  |  |  |  |  |  |  |  |  |  |  |
| Restoration of riverine vegetation for better water management as barriers against floods, to improve water quality and as a source of fodder. |  |  |  |  |  |  |  |  |  |  |  |
| Fodder production (seed capital financing). |  | Fodder production (seed capital financing). | $195,322 |  |  | $0 | 6 grants for Animal feed processing equipment = 40692 / grantee |  |  | Spending on track Price per grant too large to reach initial target beneficiaries. This means initial design / targeting strategy was wrong or grants should have been much smaller. |  |
| Silage production (fodder conservation). |  | Silage production (fodder conservation). | $48,830 |  |  | $0 |  |  |  |  |  |
| Output 1.2.2: Consultancy services for GHG emission calculations. | $40,000 | Output 1.2.2: Consultancy services for GHG emission calculations. | $0 |  |  | $40,000 |  |  |  | Still feasible Planned for early 2025 |  |
| Sub-total | $1,143,064 | Sub-total | $244,152 |  |  | $288,552 |  |  |  |  |  |
| Cost for Component 1 | $2,834,111 | Cost for Component 1 | $573,969 |  |  | $1,568,191 |  |  |  |  |  |
| Component 2: Supporting the climate resilience of market vulnerable smallholders. |  |  |  |  |  |  |  |  |  |  |  |
| Outcome 2.1 Climate smart technology demonstrations and livelihood diversification. |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1.1 Climate-smart technologies promoted though on-farm demonstrations. |  |  |  |  |  |  |  |  |  |  |  |
| Energy efficient milk pre-cooling heat exchangers and renewable energy. | $774,080 | Energy efficient renewable energy support through matching grants | $761,558 |  |  | $1,407,040 | 75 grants for PV USD = 10154 / grantee Approx 63 grants left under new proposed budget |  |  | Spending on track Price per grant is reasonable but impossible to reach initial target beneficiaries. This means initial design / targeting strategy was wrong or grants should have been much smaller. For PV this is difficult. |  |
| Output 2.2.1: Alternative non-extractive livelihoods. |  |  |  |  |  |  |  |  |  |  |  |
| Non-extractable livelihood support (Beekeeping, mushroom production, greenhouses and orchards). | $354,000 | Non-extractable livelihood support through matching grants (Beekeeping, greenhouses). | $148,226 |  |  | $986,960 | 45 grants for greenhouses = 3294 / grantee Approx 254 grants left under new proposed budget |  |  | Spending on track Price per grant is reasonable (also compared to PV grants) but impossible to reach initial target beneficiaries, which means initial design / targeting strategy was wrong or grants should have been much smaller. For Greenhouses this is difficult |  |
| Cost for Component 2 | $1,128,080 | Cost for Component 2 | $909,784 |  |  | $2,394,000 |  |  |  |  |  |
| Total Project | $3,962,191 | Total Project | $1,483,753 |  |  | $3,962,191 |  |  |  |  |  |
| Project Execution Costs |  |  |  |  |  |  |  |  |  |  |  |
| Recruitment of a Climate Change Specialist | $63,858 | Recruitment of a Climate Change Specialist | $33,009 |  |  | $75,009 |  |  |  | Enough for extension |  |
| Facilitator Salaries | $163,968 | Facilitator Salaries | $69,189 |  |  | $197,089 |  |  |  | Enough for extension |  |
| Facilitator Incentives | $90,901 | Cancelled | $0 |  |  | $90,901 |  |  |  | Enough for extension |  |
| MTR and Final Evaluation | $46,000 | MTR and Final Evaluation | $38,760 |  |  | $49,744 |  |  |  | Budget used for MTR is too high / not correct. should be corrected |  |
| (New) Finance Manager salary | $0 | Salaries |  |  |  | $24,750 |  |  |  |  |  |
| (New) M&E Specialist salary | $0 | Salaries |  |  |  | $18,135 |  |  |  |  |  |
| Total Project Execution Costs | $364,727 | Total Project Execution Costs | $140,958 |  |  | $364,727 |  |  |  | Spending on track Feasible to extend |  |
| Total Project Costs | $4,326,918 | Total Project Costs | $1,624,711 |  |  | $4,326,918 |  |  |  |  |  |
| Project Cycle Management Implementing Entity Fee |  |  |  |  |  |  |  |  |  |  |  |
| Operational and Financial Management | $100,000 | Operational and Financial Management | $100,000 |  |  | $0 |  |  |  |  |  |
| Project Development and implementation support | $117,876 | Project Development and implementation support | $117,876 |  |  | $0 |  |  |  |  |  |
| Technical support and supervision | $100,000 | Technical support and supervision | $100,000 |  |  | $0 |  |  |  |  |  |
| Total Project Cycle Management Implementing Entity Fee | $317,876 | Total Project Cycle Management Implementing Entity Fee | $317,876 |  |  | $0 |  |  |  | Spending on track |  |
| Amount of Financing Requested | 4,644,794 | Amount Total | $1,624,711 |  |  | $4,644,794 |  |  |  |  |  |

## Data collection tools

See 8.6 Evaluation Inception Report – 7.2. data collection tools

## Evaluation timeline

The evaluation took take place between 8 September and 31 October, including a mission between 14-18 September 2024.

Table 20 Evaluation deliverables and milestones

| Deliverable | Milestones |
| --- | --- |
| Inception report (in English) on proposed MTR methodology, work plan, stakeholder engagement list, and proposed structure of the MTR report | End of August 2024 |
| MTR mission findings, to be presented and discussed (in English) at mission wrap-up meeting with IFAD (PDT) | Mid-September 2024 |
| Draft MTR report (in English) to be submitted for PDT’s, PMU and AF NDA review. | End of September |
| Lead a validation meeting of the MTR report, once comments received have been addressed. | Early October |
| Final MTR report (in English) to be submitted, including a 2–3-page executive summary, a set of limited and strategic recommendations (not to exceed 10 recommendations total), and response addressing issues raised during presentation of draft. The suggested template for the report will be provided. | Mid-October |

## Evaluation Inception Report

- Executive summary

  - Introductory overview

Table 21 Project information summary table

| Project Title: | Dairy modernization and market access: adaptation component (DIMMAdapt) |  |  |
| --- | --- | --- | --- |
| IFAD Project ID: | 2000001393 (as part of Dairy Modernisation and Market Access Project) |  |  |
| Country: | Republic of Georgia |  |  |
| Region: | Near East and North Africa (NEN) and Europe Division |  |  |
| Objective: | Enhance the resilience to climate change of vulnerable dairy producers |  |  |
| Implementing agency | International Fund for Agriculture Development (IFAD) |  |  |
| Executing Agency: | Ministry of Environmental Protection and Agriculture (MEPA) |  |  |
| Key dates |  |  |  |
| AF approval |  | Effectiveness | Mid-term Review |
| 11 September 2019 |  | 16 April 2021 | Aug-Sept 2024 |

This is the inception report of the independent Mid-Term Review (MTR) covering the Adaptation Fund (AF) project ‘Dairy modernization and market access: adaptation component (DIMMAdapt), implemented by the International Fund for Agricultural Development and executed by the Ministry of Environmental Protection and Agriculture (MEPA) The MTR will be prepared in line with AF evaluation policies.

The AF Evaluation Policy requires AF projects with a duration longer than 4 years to conduct a MTR. According to the AF Evaluation Policy, the objective of the MTR is to compare baseline results to MTR findings to assess progress and achievement. The MTR means to serve as an opportunity to critically assess administrative and technical strategies, issues and constraints. Findings may also feed into the final evaluation.

The inception report of the MTR is being prepared by an independent evaluator with the support of the project team and IFAD. A MTR mission is planned for 8-14 September 2024.

Time period being evaluated: 16 April 2021 until 16 September 2024. The MTR is submitted past halfway of the project due to execution delays and rejection previously submitted MTR.

Audience and intended use: Implementing entity, executing entity and other relevant stakeholders to use recommendations made in the MTR for project way forward.

  - Summary of the report and contents

This report is a preparation report for the MTR report. The following is discussed:

- Evaluation background

- Evaluation criteria and questions

- Evaluation approach and methods

- Evaluation work plan and management

- Evaluation background

  - Object of evaluation

The MTR will evaluate the AF project ‘Dairy Modernization and Market Access: Adaptation Component (DiMMAdapt)’ The project has the following goal, objective and components.

Goal: Reduce the vulnerability of the dairy value chain to the deleterious impacts of climate change.

Objective: Enhance the resilience to climate change of vulnerable dairy producers.

Table 22 Components AF project as per initial proposal

| Project/Programme Components | Expected Outcomes | Expected Outputs | Amount (USD) |
| --- | --- | --- | --- |
| 1. Climate-proofing pastoral ecosystem services (water management, pasture regeneration, and disaster risk reduction). | Outcome 1.1 An enabling environment developed through training and capacity building. | Output 1.1.1: Climate resilient and DRR solutions for pasture rehabilitation and increased productivity promoted. | 1,691,047 |
|  | Outcome 1.2. Pasture Management Plans Implemented | Output 1.2.1: Climate resilient and ecosystem-based adaptive pastoral investments implemented. | 1,103,064 |
|  |  | Output 1.2.2: A management mechanism is in place to screen and offset any potential cattle number increases from DiMMA | 40,000 |
| 2. Supporting the climate resilience of market vulnerable smallholders. | Outcome 2.1 Climate-smart technology demonstrations and livelihood diversification. | Output 2.1.1 Climate-smart technologies and alternative livelihood measures promoted. Output 2.1.2 Alternative, complementary, non-competitive, non-extractive livelihood jobs created. | 1,128,080 |
| Total |  |  | 3,922,191 |
| Project/Programme Execution Cost (9.1%) |  |  | 358,727 |
| Total Project Cost |  |  | 4,280,918 |
| Project Cycle Management Fee Charged by the Implementing Entity (8.5%) |  |  | 363,876 |
| Amount of Financing Requested |  |  | 4,644,794 |

  - Implementation context

Development: Georgia is classified as an upper middle-income country. Poverty was estimated at 32 percent in 2016, decreasing from a peak of 46.7 percent in 2010.

Agriculture / pastures: Since 2010 Georgian agriculture has been reversing its long-term decline. Today, agriculture in Georgia accounts for 45 percent of rural household income. There are approximately 1 million head of cattle in Georgia, about 50 percent of which are producing dairy cows. Pastures can be divided into summer pastures and communal (lowland) pastures. Pastures in Georgia are included under agricultural lands.

Climate change: The historical climate trend has been one of longer dry periods and more intense rainfall leading to increased pasture vulnerability through increased flooding, soil erosion, mudslides and landslides that have adversely impacted the pastoral ecosystem services which the rural poor, including women, youth and the landless poor depend on for their livelihoods. In the future, the agriculture sector is expected to have to further adapt to increasing temperatures and changing rainfall patterns that will increase the prevalence of periods of drought and intense rainfall.

Climate change impacts in Georgia include:

- Reducing water supply for animals due to increasing temperatures

- Reducing production livestock and agriculture due to drought and heat waves.

- Loss of vegetation and biodiversity due to changing temperatures

Other projects: DiMMAdapt (especially component 1) aims to upscale in part the successful IFAD AMMAR project with GEF co-financing that successfully planted 40,000 trees for a length of 26 km x 20 meters wide. This project has protected around 1330 ha of land from erosion. DiMMAdapt will build on this success to support the design and development of climate resilient pastoral ecosystem services to reduce the negative impacts from climate change and climate variability on agricultural and rural livelihood development.

The AF project is part of the IFAD Dairy Modernization and Market Access (DiMMA) Programme in Georgia with two components:

- Component 1: Dairy Value Chain Development

- Component 2: Institutional and organisational development

Table 23 DiMMA project financing components

  - Stakeholder analysis

Table 24 Key stakeholders, needs, expectations, evaluation focus and potential risks

| Stakeholder | Needs and expectations | Evaluation focus | Potential risks |
| --- | --- | --- | --- |
| In Tbilisi |  |  |  |
| IFAD regional and country office | Identify project issues, solutions / way forward and progress | Activities with issues / delays and progress so far |  |
| Project Management Unit (PMU) |  | Root causes execution issues and progress so far |  |
| Ministry of Environmental Protection and Agriculture (MEPA) – National Agency for Sustainable Land Management and Land use monitoring (NASLM) |  |  | Potential conflicting priorities ministries and municipality |
| Regional Environmental Center for the Caucasus (RECC) (Service provider) | Guidance on further execution | Activities with issues / delays; capacity issues to execute | Limited capacity and insight in data |
| In the field |  |  |  |
| Municipality / villages | How to manage pastures when responsibility is hand-over from ministry of economy to municipalities |  | Potential conflicting priorities ministries and municipality |
| Project beneficiaries: Individual pastoralists | To receive project support | Identify if project interventions are helping project beneficiaries to adapt to droughts, heat waves, torrential rains; Identify if project interventions respond to the specific needs of the project beneficiaries | Not meeting best representatives |
| Project beneficiaries: Women and youth |  |  | Limited response with male present |

- Evaluation criteria and questions

  - Purpose and scope

The AF Evaluation Policy requires AF projects with a duration longer than 4 years to conduct a MTR. According to the AF Evaluation Policy, the objective of the MTR is to compare baseline results to MTR findings to assess progress and achievement. The MTR means to serve as an opportunity to critically assess administrative and technical strategies, issues and constraints. Findings may also feed into the final evaluation.

MTR Findings should:

- Identify what works and why and what isn’t working and why to timely inform project implementation, course correction, and strategic decision making

- Recognition of successes and best practices, as well as areas with potential for upscaling or replication.

- Identify challenges or problems before they worsen and reveal good practices and strengths for that implementing entities to expand their successes.

- Improve project performance and bolster its impact and sustainability of results over the remainder of the project’s life.

- Organize and synthesize experiences and lessons. As the MTR involves learning during project implementation, experiences and lessons identified can be readily acted upon to improve project impacts and outcomes. Lessons also help to improve and instruct future climate change adaptation interventions

The MTR will focus on:

- Identifying main project issues and make recommendations to address these or refocus

- The implementation of the DiMMA Gender and youth strategy / plan

- The implementation of the project Environmental and Social policy / ESMP

- Consulting relevant stakeholders

The MTR will focus most on project component 1 as limited progress has been made under this component and on the Samtskhe-Javakheti region, as the project prioritized activities in this region.

Time period of project reviewed: 16 April 2021 until 16 September 2024

Audience and intended use: Implementing entity, executing entity and other relevant stakeholders to use recommendations made in the MTR for project way forward.

  - Criteria

The MTR sets about attempting to provide answers to the following questions (evaluation criteria):

- Relevance: Is the intervention doing the right thing?

- Coherence: How well does the intervention fit?

- Effectiveness: Is the intervention achieving its objectives?

- Efficiency: How well are resources being used?

- Impact: What difference does the intervention make?

- Equity: Are the benefits of the intervention shared fairly between groups and geographies?

- Adaptive management: Does the intervention make evidence-based decisions?

- Scalability: Can the intervention be replicated at a greater scale?

- Human and ecological sustainability and security: Does the intervention affect the ability of human and natural systems to support the equitable life of all species on the planet? Is the intervention sensitive to conflict and fragility?

  - Questions

Table 25 Evaluation criteria and specific questions

| Criteria | Specific questions |
| --- | --- |
| Relevance: Is the intervention doing the right thing? | - Climate change: Are the project intervention helping project beneficiaries to adapt to droughts, heat waves, torrential rains? - Priorities: Are the project interventions in line with national and local priorities? - Geography: Is the focus on the Samtskhe-Javakheti region justified? |
| Coherence: How well does the intervention fit? | - How well do the activities fit together? |
| Effectiveness: Is the intervention achieving its objectives? | - Targets as set in the results framework reached and justification why yes or no? |
| Efficiency: How well are resources being used? | - Targets reached with available budget and timeline? |
| Impact: What difference does the intervention make? | - What is the impact / change for beneficiaries and are they satisfied with the result |
| Equity: Are the benefits of the intervention shared fairly between groups and geographies? | - Are the gender targets reached as per the results framework and gender action plan? Why yes / no? |
| Adaptive management: Does the intervention make evidence-based decisions? | - Are changes in implementation justified and relevant? |
| Scalability: Can the intervention be replicated at a greater scale? | - What interventions can be replicated and why yes / no? |
| Human and ecological sustainability and security: Does the intervention affect the ability of human and natural systems to support the equitable life of all species on the planet? Is the intervention sensitive to conflict and fragility? | - ESMP implemented properly (without negative effects)? |

- Matrix

Table 26 project evaluation matrix

| Question | Evaluation criteria | Indicators | Data source | Data collection techniques | Rationale for selection |
| --- | --- | --- | --- | --- | --- |
| - Climate change: Are the project interventions helping project beneficiaries to adapt to droughts, heat waves, torrential rains? | Relevance | Alignment with climate change adaptation needs as per national strategies; Key stakeholders and % beneficiaries responding positively | National climate change strategies Project beneficiaries | Analysis and interviews | To match criteria for evaluation Feasibility within MTR assignment |
| - Priorities: Is the project in line with national and local priorities? |  | Relevant ministries and municipalities confirming | Ministries Municipality | Interviews |  |
| - Geography: Is the focus on the Samtskhe-Javakheti (for implementing PMPs) region justified? |  | Climate change vulnerability of regions; justifications from key stakeholders | Climate change Vulnerability profile; key stakeholders | Data analysis and interviews |  |
| - How well do the activities fit together? | Coherence | Key stakeholders Match trainings and interventions | Project beneficiaries | Data analysis and interviews |  |
| - Targets as set in the results framework reached and justification why yes or no? | Effectiveness | See results framework | Results reporting, images, etc. | Analysis |  |
| - Targets reached with available budget and timeline? | Efficiency | See budget | Expenditure reporting | Analysis |  |
| - What is the impact / change for beneficiaries and are they satisfied with the result | Impact | Key stakeholders and % beneficiaries responding positively | Project beneficiaries | Data analysis and interviews |  |
| - Are the benefits of the intervention shared fairly between groups and geographies? Are gender targets reached as per the results framework and gender action plan? | Equity | See results framework | Results reporting, images, etc. | Analysis |  |
| - Are changes in implementation timely, justified and relevant? | Adaptive management | Positive impact changes Timely adaption of changes | Docs showing amendments | Analysis |  |
| - What interventions can be replicated and why yes / no? | Scalability | Identified replicable actions | Key stakeholders and beneficiaries | Data analysis and interviews |  |
| - ESMP implemented properly (without negative effects)? | Human and ecological sustainability and security | Risks and negative effects identified | Key stakeholders, site visits | Data analysis and interviews |  |

- Evaluation approach and methods

  - Evaluation principles

Figure 3 AF Evaluation principles

  - Evaluation data sources

- Primary data collection:

  - Questionnaires

  - Interviews

  - Data

  - Observations

  - Pictures

  - Maps

- Secondary data:

  - Project proposal and results framework

  - DiMMA Gender and youth strategy / plan

  - Environmental and Social management Plan (ESMP)

  - Project baseline / inception report

  - PPR 1, 2 and 3

  - Project implementation supervision mission reports

  - RECC reports

  - DiMMA MTR

  - Survey report in women’s empowerment in DiMMA project

  - Evaluation data collection methods

See Table 7 section 3.4.

  - Evaluation data analysis

The MTR will be conducted in line with AF policies and guidelines for evaluation. A mixed-methods approach will be used, including: (i) a desk review of project documents available, (ii) online interviews with the project team and relevant stakeholders; and (iii) face-to-face interviews with project beneficiaries in Samtskhe-Javakheti.

  - Evaluation stakeholder engagement

Table 27 Evaluation stakeholder engagement

| Stakeholder | Level | Type of engagement |
| --- | --- | --- |
| IFAD | Project team and regional office | Online and in-person |
| PMU | Project team | In-person |
| MEPA-NASLM | Responsible for the project | In-person |
| RECC (Service provider) | Responsible for the project | In-person |
| Individual farmers / pastures | Individual | In-person |
| Women and youth farmers | Individual | In-person |

  - Ethical considerations related to data collection and use

The Reviewer / evaluator will respect the right of institutions and individuals to provide information in confidence; the sources of specific information and opinions in this report are not disclosed except where necessary and then only after confirmation with the consultee.

  - Methodological limitations

Table 28 Methodological limitations

| Methodological limitations | Implications | Mitigation measures |
| --- | --- | --- |
| Limited time and feasibility for questionnaires | Limited reach | To be covered by final evaluation |
| Focus mostly on Samtskhe-Javakheti region and related interventions | Limited review / evaluation of other regions due to strategic refocus on the project | Data analysis and online interviews about interventions in other regions |

- Evaluation work plan and management

  - Evaluation work plan

Table 29 Evaluation work plan

| Tasks | Deliverable |
| --- | --- |
| Desk research Online interviews | Inception report (in English) on proposed MTR methodology, work plan, stakeholder engagement list, and proposed structure of the MTR report |
| Mission to the field including interviews | MTR mission findings, to be presented and discussed (in English) at mission wrap-up meeting with IFAD (PDT) |
| Draft MTR report based on findings above | Draft MTR report (in English) to be submitted for PDT’s, PMU and AF NDA review. |
| Prepare validation meeting | Lead a validation meeting of the MTR report, once comments received have been addressed. |
| Draft final MTR report based on above | Final MTR report (in English) to be submitted, including a 2–3-page executive summary, a set of limited and strategic recommendations (not to exceed 10 recommendations total), and response addressing issues raised during presentation of draft. The suggested template for the report will be provided. |

Table 30 Draft mission agenda

| Date | Time (Tbilisi) | Event | Participants | Comments |
| --- | --- | --- | --- | --- |
| Sunday 8 September |  | Part of Mission team arrives in Georgia | In-country IFAD team | Night in Tbilisi |
| Monday 9 September | 9:45 | Enrico arrives in Georgia |  | Night in Tbilisi |
|  | 10:00-11:15 | Mission internal brief at hotel Document review | In-country IFAD team |  |
|  | 12:00-19:00 | Briefing and discussion with PMU on DiMMA Progress to date, status of last agreed actions, etc. Review of the agenda and One-to-one discussions Document review | In-country IFAD team + PMU team |  |
| Tuesday 10 September | 10:00-12:30 | Discussion with REC Caucasus on Pasture Management Plans (include NALSM representatives if possible) | In-country IFAD team + PMU team | Night in Tbilisi |
|  | Time TBD | Discussion with RDA on DiMMA/DiMMAdapt grants |  |  |
|  | 13:00-17:00 | One-to-one discussions with PMU counterparts |  |  |
| Wednesday 11 September Group 1 | 07:00-11:00 | Travel to Samtskhe-Javakheti region | GROUP 1 : Khafiz + Joris + Gizo + Dito + Ilia | Night in Akhaltsikhe (Hotel Almi) |
|  | 11:00-18:00 | Field Visits to PMP villages and beneficiaries of other DiMMA/DiMMAdapt interventions (fodder conservation, barn renovation, small/medium scale processing, training, AI, silage/hay service providers, greenhouses, etc.) – Whenever possible, combine these visits in locations nearby the PMP villages to save transport time |  |  |
|  | 18:00 | Check-in Hotel Almi |  |  |
| Wednesday 11 September Group 2 | 10:00-17:30 | One-to-one discussions with PMU counterparts re: procurement, grant process, project management, targeting, project extension, partnerships, new financing, etc. | GROUP 2 : Enrico + Isabelle + Youssef + PMU team PMU team for the SECAP demo: Katie, Tamuna, Yana, Alexander, Eka + RDA staff | Night in Tbilisi |
|  | Day and time TBD | Demonstration by Youssef on how to fill the SECAP checklist on a sample nearby grant beneficiary – e.g., barn renovation/construction grant in Kvemo Kartli or Kakheti (close to Tbilisi) |  |  |
|  | 17:30-19:00 | Document review |  |  |
| Thursday 12 September Group 1 | 09:00-18 :00 | Field Visits to PMP villages and beneficiaries of other DiMMA/DiMMAdapt interventions (fodder conservation, barn renovation, small/medium scale processing, training, AI, silage/hay service providers, greenhouses, etc.) – Whenever possible, combine these visits in locations nearby the PMP villages to save transport time | GROUP 1 : Khafiz + Joris + Gizo + Dito+ Ilia | Night in Akhaltsikhe (Hotel Almi) |
|  | 18:00 | Check-in Hotel Almi |  |  |
| Thursday 12 September Group 2 | 10:00-17:30 | One-to-one discussions with PMU counterparts re: procurement, grant process, project management, targeting, project extension, new financing, etc. | GROUP 2 : Enrico + Isabelle + Youssef + PMU team PMU team for the SECAP demo: Katie, Tamuna, Yana, Alexander, Eka + RDA staff | Night in Tbilisi |
|  | Day and time TBD | Demonstration by Youssef on how to fill the SECAP checklist on a sample nearby grant beneficiary – e.g., barn renovation/construction grant in Kvemo Kartli or Kakheti (close to Tbilisi) |  |  |
|  | 17:30-19:00 | Document review |  |  |
| Friday 13 September Group 1 | 09:00-13:00 | Field Visits to beneficiaries of other DiMMA/DiMMAdapt interventions (fodder conservation, barn renovation, small/medium scale processing, training, AI, silage/hay service providers, greenhouses, etc.) – Whenever possible, combine these visits in locations nearby the PMP villages to save transport time | GROUP 1 : Khafiz + Joris + Gizo + Dito+ Ilia | Night in Tbilisi |
|  | 14:00-18:00 | Travel back to Tbilisi |  |  |
| Friday 13 September Group 2 | 10:00-17:30 | One-to-one discussions with PMU counterparts re: procurement, grant process, project management, targeting, project extension, new financing, etc. | GROUP 2 : Enrico + Isabelle + Youssef + PMU team | Night in Tbilisi |
|  | 17:30-19:00 | Document review |  |  |

Mission dates: 		8-14 September

Days in Tblisi: 		3

Days in the field:		3

IFAD Mission composition:

- Isabelle Lagaillarde: Rural Development and Agribusiness specialist (consultant) – IFAD mission team leader

- Enrico Protomastro: IFAD Programme Officer

- Khafiz Atymtay: IFAD Environment and Climate Officer

- Youssef Saad: Procurement specialist (consultant)

- Joris Oele (AF MTR consultant)

DiMMA PMU:

- Lali Durmishidze: Project Director

- Katie Sharabidze: Dty Project Director and VC Specialist

- Tamuna Tsintsadze: M&E specialist

- Eka Gurgenidze: Gender and KM Focal Point

- Dito Kvirikhashvili: Livestock Specialist (field)

- Gizo Chelidze: AF Coordinator (field)

- Ilia Mchelidze: Agronomist consultant supporting greenhouse beneficiaries (field)

- Zura Kuljanishvili: Regional Coordinator for Samtskhe-Javakheti region (field)

Table 31 Planned interviews

| Actor | Name | Function | Objective |
| --- | --- | --- | --- |
| IFAD |  | Environment and Climate Officer | - Identify project issues, solutions / way forward - Details project progress and proposed adjustments - Justification focus on the Samtskhe-Javakheti region (from a vulnerability, agriculture / pastures and feasibility perspective? - Identify appropriate content PMPs - Identify interventions that can be replicated and why yes / no? - ESMP implemented properly (without negative effects)? |
|  |  | Rural development and agribusiness specialist |  |
| PMU |  | Project director | - Root causes execution issues - System to monitor the herd numbers and net GHG emissions. |
|  |  | AF coordinator |  |
|  |  | M & E specialist | - Review results framework and targets |
|  |  | KM and gender specialist | - Review gender targets and issues |
| MEPA-NASLM |  |  | - Identify how to address issue of PUUs not being eligible to receive grants? - Identify if project interventions are in line with national priorities |
| RECC |  |  | - Identify progress and proof, incl. data and maps - Progress 5-month action plan - Pastures categorised (ha) and villages covered, incl. PMPs developed) - Identify challenges and solutions grants - Identify municipalities involved in PMPs (15 done) developed by RECC |
| Municipality |  |  | - How to address issue of PUUs not being eligible to receive grants? Through municipality and ministry of economy with right to use land 5-8 years. Alternatives? - Identify how Involved in development PMPs |
| Individual pasturalists |  |  | - Identify if project interventions are helping project beneficiaries to adapt to droughts, heat waves, torrential rains - Identify if project interventions respond to the needs of the project beneficiaries |
| Women and youth |  |  |  |

Table 32 Main issues identified so far and status / possible solutions

| Main issues identified so far | Status / possible solution |
| --- | --- |
| Lack of progress due to absence of roadmap guided by pasture policy and law | Status guidance from policy and law? |
| Pasture User Unions can’t receive grants as they are not recognised as legal entities | Status? Alternatives? |

  - Evaluation timeline, milestones, and deliverables

The evaluation will take place between 8 September and 31 October, including a mission between 14-18 September 2024.

Table 33 Evaluation deliverables and milestones

| Deliverable | Milestones |
| --- | --- |
| Inception report (in English) on proposed MTR methodology, work plan, stakeholder engagement list, and proposed structure of the MTR report | End of August 2024 |
| MTR mission findings, to be presented and discussed (in English) at mission wrap-up meeting with IFAD (PDT) | End of September 2024 |
| Draft MTR report (in English) to be submitted for PDT’s, PMU and AF NDA review. | Mid-October 2024 |
| Lead a validation meeting of the MTR report, once comments received have been addressed. | End of October 2024 |
| Final MTR report (in English) to be submitted, including a 2–3-page executive summary, a set of limited and strategic recommendations (not to exceed 10 recommendations total), and response addressing issues raised during presentation of draft. The suggested template for the report will be provided. | End of October 2024 |

  - Roles and responsibilities

The reviewer / evaluator will be responsible for the evaluation process and required reports. The reviewer / evaluator will be supported by the project supervision team (same mission) and IFAD regional office.

  - Quality assurance

The MTR aims to be credibility, independent and impartiality. Gender and Environmental and Social Policies will be considered and appropriately reflected in the findings and recommendations. The reviewer / evaluator will interview relevant stakeholders and beneficiaries to ensure their perspectives are incorporated into findings. Initial findings will be shared with stakeholders and feedback and recommendations will be incorporated into the final MTR report.

  - Risk management and mitigation measures

Table 34 Potential evaluation risks per key stakeholder and mitigation measures

| Stakeholder | Potential risks | Mitigation measures |
| --- | --- | --- |
| MEPA - NASLM | Conflicting priorities with ministry of agriculture | Interview with MEPA reps only |
| Municipality | Conflicting priorities with ministry of agriculture | Interview with municipal reps only |
| RECC (Service provider) | Limited capacity | Checking capacity and conduct interviews about this from secondary sources |
| Individual pastoralists | Not meeting best representatives | Request associations to meeting appropriate reps |
| Women and youth farmers | Limited response with male present | Interview women and / or youth only |

Table 35 Identified risks and mitigation measures as per PPR 1

| Identified Risk | Current Status | Steps Taken to Mitigate Risk | MTR assessment |
| --- | --- | --- | --- |
| Low interest and capacity of smallholder dairy producers to adopt new climate smart approaches and technologies. | Low | The programme will pay attention to technical and environmental capacity building and training as a key factor in the upgrading process. It will carry out demonstrations and raise general environmental and climate change awareness and train farmers on the economic and environmental benefits for the adoption of systems and new technologies. | - Status low interest and capacity - Implementation of capacity building |
| The current policy and regulatory environment for pasture does not encourage the sustainable management of collective pasture, leading to degradation of this resource. | High | The current policy and regulatory environment for pasture does not encourage the sustainable management of collective pasture, leading to degradation of this resource. It was decided to carry out inventory of pasturelands in one of the target regions (Samtskhe-Javkheti), create PMPs for targeted 9500 ha of land and further implement several PMPs as funds and project timeframe allows | - Check if PMU aims to overcome this through an inventory of pasturelands to identify user groups and pasture areas subject to climate-resilient measures - How can policy support encourage the sustainable management of collective pastures? If not, what are the alternatives within the project? |
| Climatic shock: the main effect of climate change on weather patterns is the increased occurrence of extreme weather events: droughts and flooding in particular. These weather shock can have a direct impact on animals but also contribute to the emergence of diseases | Low | The programme will introduce climate smart infrastructure and will ensure that climate adaptation measures are implemented. It will in particular ensure that breeds used in crossbreeding strategies are resilient to climate shocks (utilization of rustic breeds); Promotion of fodder conservation and of use of concentrate feeds will contribute to improving resilience; to drought; Surveillance of emerging diseases will be addressed as mentioned above. | - Check feasiblity of crossbreading leading to more resilient / rustic breeds - Check promotion of fodder conservation and surveillance emerging diseases - Why limited flood risk reduction measures? |
| Insufficient capacities to appropriately manage the day-to-day implementation of the project | Low | The DiMMAdapt project coordinator is supported by the DiMMA project technical and administrative staff. | - Check capacity staff to manage the project |

  - Outreach and dissemination plan

Initial findings to be shared with key stakeholders and feedback and recommendations incorporated into the final MTR report.

- Annexes

  - Evaluation’s ToR

Consultant ☒	Intern ☐	Fellow ☐	Conference Service ☐

Minimum number of years of relevant experience required (consultants only):

1yr ☐	3yr ☐	8yrs ☒	12+yrs ☐

| Full Name: | Joris Oele |  |
| --- | --- | --- |
| Specialization: | Monitoring & Evaluation |  |
| Expected Start Date of Assignment: | 8 September 2024 |  |
| Expected End Date of Assignment: | 31 October 2024 |  |
| Total number of working days (max. 240 in a 12-month period): | 20 (7 days in Georgia). |  |
| Division/Department: | ECG/NEN |  |
| Location: | Home Based with with a mission to Georgia for 7 days |  |
| Reports to (name and title): | Mr Walid Nasr/Mr Liam Chicca |  |
| GENERAL DESCRIPTION OF TASK(S) AND OBJECTIVES TO BE ACHIEVED |  |  |
| Technical Focus This document features the terms of reference (TOR) for the mid-term review of the DIMMAdapt project in Georgia. Description of the project: objectives, components, current situation Mid-Term review purpose In accordance with the Funded Activity Agreement between IFAD and the AF, IFAD is required to deliver to the AF Secretariat an independent mid-term review report. The Mid Term review (MTR) has two purposes. First, it will provide accountability to the AF and to the national government (GoG). Second, it will have a critical learning purpose, since in the process of assessing progress towards the results and contribution to the objectives set by the project to date, measures will be identified to improve the implementation, such as lessons learned and recommendations to take corrective action as necessary during the second half of the project. The evaluation will be conducted by an independent consultant who will assess if the implementation of the Project (including its progress, performance, overall management, contribution to and achievement of expected results, behavioral changes, etc.) is aligned with the project’s obligations (agreement between AF and IFAD) and IFAD’s (being the Implementing Entity for the project) project document. The evaluation will be guided by the AF Evaluation criteria in accordance with following criteria: impartiality, objectivity, independence; relevance, utility, credibility, measurability, transparency, ethics, and partnerships. The consultant will work in close coordination with IFAD’s project delivery team (PDT) and the Project Management Unit (PMU) who will provide key project documentation prior to fieldwork and assist the consultant in developing a detailed mission programme to facilitate consultations with key stakeholders and beneficiaries. Tasks and responsibilities - Collect and verify primary and secondary data in order to assess project progress, performance and quality of implementation in line with the defined objectives, and legal and financial agreement; - Identify barriers, challenges and bottlenecks during implementation of the project; - Identify potential solutions, strategies and action plans to address challenges and speed up project implementation; - Review and suggest revisions as necessary to the current implementation plans, AWPBs and procurement plans; - Undertake interviews, surveys, community consultations, transect walks, and focus group discussions with relevant stakeholders, beneficiaries, EE’s, possibly national and or local Governments, and where relevant other development partners in order to capture varying perspectives and to evaluate the project’s relevance, efficiency and effectiveness; - Collect data as needed (government data/records, field observation visits, public expenditure reporting, GIS data, etc.) to validate evidence of results and assessments (including but not limited to: assessment of TOC, activities delivery, and results/changes occurred); - Liaise with key implementing partners and stakeholders, which include IFAD (as IE), AF NDA, etc; - Liaise with and coordinate inputs from other mission members who will participate in the MTR mission. - Lead the discussions on the MTR report and mission findings with PDT and AF NDA to validate the findings of the evaluation, and address any comments received, as well as lead a validation meeting for the MTR final report. Expected deliverables The independent consultant will produce the following outputs: - Inception report (in English) on proposed MTR methodology, work plan, stakeholder engagement list, and proposed structure of the MTR report - MTR mission findings, to be presented and discussed (in English) at mission wrap-up meeting with IFAD (PDT) - Draft MTR report (in English) to be submitted for PDT’s, PMU and AF NDA review. - Lead a validation meeting of the MTR report, once comments received have been addressed. - Final MTR report (in English) to be submitted, including a 2–3-page executive summary, a set of limited and strategic recommendations (not to exceed 10 recommendations total), and response addressing issues raised during presentation of draft. The suggested template for the report will be provided. Minimum requirements - University degree in natural resource management, climate adaptation, environmental economics, agri-sciences, information management, or any related topics; - Minimum 5 years (with master’s degree) or 8 years (with bachelor’s degree) of relevant experience with results-based planning, monitoring, evaluation and reporting of development sector projects. - Fluency in English. - Proficiency with office software packages (MS Word, Excel, etc.), and other web-based management systems. - Prior experience with the UN system and development programmes is required. - Prior M&E experience in an AF funded project will be an asset. |  |  |
| KEY PERFORMANCE INDICATORS |  |  |
| Expected Outputs (please include any travel if applicable): |  | Required Completion Date: |
| Lead the write up of DiMMAdapt report delineating the main findings and an action plan for the adjustment of the component, to the extent needed by 31st October. |  | 31 October 2024 |

7.2. Data collection tools

Table 36 Key questions (questionnaire) per stakeholder

| Actor | Questions | Answers |
| --- | --- | --- |
| IFAD | Project issues, solutions / way forward - What are the key issues and why (root causes)? - How can these be addressed? - What cannot be addressed and why? - Is it feasible to extend the project and for how long? |  |
|  | Relevance - Climate change: How are the project intervention helping project beneficiaries to adapt to droughts, heat waves and intense rainfall (leading to increased flooding, soil erosion, mudslides and landslides)? - How to justify focus on renewable energy (PV) / energy efficiency from climate change adaptation perspective - How to justify focus on greenhouses from climate change adaptation perspective - Geography: How to justify the focus on the Samtskhe-Javakheti region? - PMPs: Is the content of the PMPs relevant (and does it contain below as per design)? Why yes /no? - Disaster risks analysis and climate change impacts / vulnerability - Adaptation strategy (and DRR strategy) - Investment plan (also targeting most vulnerable people) - Mapping of protected areas, critical biodiversity, heritage sites - Maps of pasture lands showing |  |
|  | Coherence - Is there any disconnection / mismatch between project activities (e.g. relation between trainings and concrete interventions and / or DiMMA - DiMMAdapt)? Why yes / no? - AF logframe: - Why is Fodder conservation DEMO under AF Component 2.1.1 and not under 1.1.1? - Why are field training sessions demo sites under AF Component 2.1.1 and not under 1.1.1? |  |
|  | Effectiveness - Please highlight the main reasons / justifications for delays / not reaching results - Is there enough capacity to manage the project (incl. PMU)? Why yes / no? |  |
|  | Efficiency - How well (i.e. efficient) are resources being used? Are the targets reached with available budget? Why yes / no? |  |
|  | Impact - What are the main impacts of the project? |  |
|  | Equity - Are the benefits of the intervention shared fairly between groups and geographies? Are the gender targets reached as per the results framework and gender action plan? Why yes / no? |  |
|  | Adaptive management / revisions - How are the proposed changes in implementation relevant and justified? |  |
|  | Scalability - What interventions can be replicated or scaled-up and why yes / no? - What are the main lessons learned? |  |
|  | Human and ecological sustainability and security - Is the ESMP being implemented properly (without negative effects)? Why yes /no? |  |
| PMU | Project issues, solutions / way forward - What are the main issues and why (root causes)? - How can these be addressed? - What cannot be addressed and why? |  |
|  | Relevance - Climate change: How are the project intervention helping project beneficiaries to adapt to droughts, heat waves and intense rainfall (leading to increased flooding, soil erosion, mudslides and landslides)? - How to justify focus on renewable energy (PV) / energy efficiency from climate change adaptation perspective - How to justify focus on greenhouses from climate change adaptation perspective - Geography: How to justify the focus on the Samtskhe-Javakheti region? - PMPs: Is the content of the PMPs relevant (and does it contain below as per design)? Why yes /no? - Disaster risks analysis and climate change impacts / vulnerability - Adaptation strategy (and DRR strategy) - Investment plan (also targeting most vulnerable people) - Mapping of protected areas, critical biodiversity, heritage sites - Maps of pasture lands showing |  |
|  | Coherence - Is there any disconnection / mismatch between project activities (e.g. relation between trainings and concrete interventions and / or DiMMA - DiMMAdapt)? Why yes / no? - AF logframe: - Why is Fodder conservation DEMO under AF Component 2.1.1 and not under 1.1.1? - Why are field training sessions demo sites under AF Component 2.1.1 and not under 1.1.1? |  |
|  | Effectiveness - Please highlight the main reasons / justifications for delays / not reaching results - Is there enough capacity to manage the project? Why yes / no? |  |
|  | Efficiency - How well (i.e. efficient) are resources being used? Are the targets reached with available budget? Why yes / no? |  |
|  | Impact - What are the main impacts of the project? |  |
|  | Equity - Are the benefits of the intervention shared fairly between groups and geographies? Are the gender targets reached as per the results framework and gender action plan? Why yes / no? |  |
|  | Adaptive management / revisions - How are the proposed changes in implementation relevant and justified? |  |
|  | Scalability - What interventions can be replicated or scaled-up and why yes / no? - What are the main lessons learned? |  |
|  | Human and ecological sustainability and security - Is the ESMP being implemented properly (without negative effects)? - Who is responsible? - Have the project sites been screened against: - List of national protected areas - Critical biodiversity risks - Heritage sites - Is a Grievances and Redress mechanism in place? - Any issues reported? |  |
| MEPA- NASLM | Project issues, solutions / way forward - What are the key issues and why (root causes)? - How can these be addressed? |  |
|  | Relevance - National priorities: Are the project intervention in line with national priorities? Why yes / no? |  |
| RECC (service provider) | Project issues, solutions / way forward - What are the key issues and why (root causes)? - How can these be addressed? - What cannot be addressed and why? |  |
|  | Relevance - PMPs: Is the content of the PMPs relevant (and does it contain below as per design)? Why yes /no? - Disaster risks analysis and climate change impacts / vulnerability - Adaptation strategy (and DRR strategy) - Investment plan (also targeting most vulnerable people) - Mapping of protected areas, critical biodiversity, heritage sites - Maps of pasture lands |  |
|  | Coherence - Is there any disconnection / mismatch between project activities (e.g. relation between trainings and concrete interventions)? Why yes / no? |  |
|  | Effectiveness - Are the targets as set in the contract reached and justification why yes / no? |  |
|  | Efficiency - How well (i.e. efficient) are resources being used? Are the targets reached with available budget? Why yes / no? |  |
|  | Impact - What are the main impacts of the project? |  |
|  | Equity - Are the benefits of the intervention shared fairly between groups and geographies? Why yes / no? |  |
|  | Scalability - What interventions can be replicated or scaled-up and why yes / no? - What are the main lessons learned? |  |
| Municipality / villages | Project issues, solutions / way forward - What are the key issues and why (root causes)? - How can these be addressed? - What cannot be addressed and why? |  |
|  | Relevance - Climate change: How are the project intervention helping project beneficiaries to adapt to droughts, heat waves and intense rainfall (leading to increased flooding, soil erosion, mudslides and landslides)? - National priorities: Are the project intervention in line with national and municipal priorities? Why yes / no? - PMPs: was the municipality / villages involved with the development? Are the PMPs good? Why yes / no? Anything missing? How to implement it? |  |
| Individual pasturalists | Project issues, solutions / way forward - What are the main issues and why (root causes)? - How can these be addressed? |  |
|  | Relevance - Climate change: How are the project intervention helping project beneficiaries to adapt to droughts, heat waves and intense rainfall (leading to increased flooding, soil erosion, mudslides and landslides)? - Priorities: what are your main needs / priorities? PMPs: Were farmers involved? How? Are the PMPs good? Why yes / no? Anything missing? |  |
|  | Effectiveness - What project interventions are effective and which not? Why? Please show results - Is crossbreading leading to more resilient / rustic breeds? Why yes / no? - Which trainings did you get? Were these good / relevant? Why yes / no? - Is fodder conservation effective? Why yes / no? Please show results - Is manure composting effective? Why yes / no? Please show results - Is energy saving / use of renewable energy effective? Why yes / no? Please show results. What do you do with savings from lower energy bill? - Is there any restoration of degraded pastures? Is it effective? Why yes / no? Please show results - Is there any water management measure (in barns)? Is it effective? Why yes / no? Please show results - Is there any restoration riverine vegetation (to reduce flood risks)? Is it effective? Why yes / no? Please show results - Are greenhouses effective? Why yes / no? please show results - Is there any mushroom production, orchards production, drying of medicinal plants or agric-tourism? Why yes / no? - Is there any surveillance of emerging diseases? |  |
|  | Equity - Are the benefits of the intervention shared fairly between groups and geographies? Why yes / no? |  |
| Women and youth | Project issues, solutions / way forward - What are the main issues and why (root causes)? - How can these be addressed? |  |
|  | Relevance - Climate change: How are the project intervention helping project beneficiaries to adapt to droughts, heat waves and intense rainfall (leading to increased flooding, soil erosion, mudslides and landslides)? - Priorities: what are your main needs / priorities? - PMPs: Were women / youth involved? How? Are the PMPs good? Why yes / no? Anything missing? |  |
|  | Effectiveness - What project interventions are effective and which not? Why? Please show results - Is crossbreading leading to more resilient / rustic breeds? Why yes / no? - Which trainings did you get? Were these good / relevant? Why yes / no? - Is fodder conservation effective? Why yes / no? Please show results - Is manure composting effective? Why yes / no? Please show results - Is energy saving / use of renewable energy effective? Why yes / no? Please show results. What do you do with savings from lower energy bill? - Is there any restoration of degraded pastures? Is it effective? Why yes / no? Please show results - Is there any water management measure (in barns)? Is it effective? Why yes / no? Please show results - Is there any restoration riverine vegetation (to reduce flood risks)? Is it effective? Why yes / no? Please show results - Are greenhouses effective? Why yes / no? please show results - Is there any focus on energy efficient milk pre-cooling heat exchangers and renewable energy? Is it effective? Why yes / no? Please show results - Is there any mushroom production, orchards production, drying of medicinal plants or agric-tourism? Why yes / no? - Is there any surveillance of emerging diseases? |  |
|  | Equity - Are the benefits of the intervention shared fairly between groups and geographies? Why yes / no? |  |

7.1. Detailed Results Framework

Table 37 Project results framework as per the original proposal

7.3. Project budget

Table 38 Project budget as per the proposal

| Item/activity | Amount (USD) |
| --- | --- |
| Component 1: Climate-proofing pastoral ecosystem services (water management, pasture regeneration, and disaster risk reduction) |  |
| Outcome 1.1. An enabling environment developed through training and capacity building. |  |
| Output 1.1.1: Climate resilient and DRR solutions for pasture rehabilitation and increased productivity promoted. |  |
| Training support and exchange visits for the development of Pasture Management Plans by the PUA’s and smallholder and progressive farmers (GIS mapping, PMP format, threat analysis, adaptation strategy, adaptation activities, management plan, fees and revenue generation, business plan for PAF grant, herd and grazing management). | 475,403 |
| Development of Pasture Management Plans | 140,119 |
| Pasture adaptation demonstrations for PUA farmers (including the restoration of degraded pastures; water management measures; soil conservation; mudslide and flood mitigation measures; riverine vegetation promotion). | 472,000 |
| Pasture management demonstrations for private pasture farmers (including the production and dissemination of awareness raising and visual learning materials). | 149,643 |
| Silage production (fodder conservation) demonstrations (including the production and dissemination of awareness raising and visual learning materials). | 358,856 |
| Manure composting demonstrations (including the production and dissemination of awareness raising and visual learning materials). | 34,464 |
| On-demand demonstrations (including the production and dissemination of awareness raising and visual learning materials). | 60,562 |
| Sub-total | 1,691,047 |
| Outcome 1.2. Pasture Management Plans Implemented. |  |
| Output 1.2.1: Implementation of climate resilient and ecosystem-based adaptive pastoral grants. |  |
| Restoration of degraded pastures, reforestation and wind breaks. | 885,000 |
| Water management measures to favour pasture resilience. |  |
| Measures to prevent soil erosion, mudslides and floods. |  |
| Restoration of riverine vegetation for better water management as barriers against floods, to improve water quality and as a source of fodder. |  |
| Fodder production (seed capital financing). | 109,032 |
| Silage production (fodder conservation). | 109,032 |
| Output 1.2.2: Consultancy services for GHG emission calculations. | 40,000 |
| Sub-total | 1,143,064 |
| Cost for Component 1 | 2,834,111 |
| Component 2: Supporting the climate resilience of market vulnerable smallholders. |  |
| Outcome 2.1 Climate smart technology demonstrations and livelihood diversification. |  |
| Output 2.1.1 Climate-smart technologies promoted though on-farm demonstrations. |  |
| Energy efficient milk pre-cooling heat exchangers and renewable energy. | 774,080 |
| Output 2.2.1: Alternative non-extractive livelihoods. |  |
| Non-extractable livelihood support (Beekeeping, mushroom production, greenhouses and orchards). | 354,000 |
| Cost for Component 2 | 1,128,080 |
| Total Project | 3,962,191 |
| Project Execution Costs |  |
| Recruitment of a Climate Change Specialist | 63,858 |
| Facilitator Salaries | 163,968 |
| Facilitator Incentives | 90,901 |
| MTR and Final Evaluation | 46,000 |
| Total Project Execution Costs | 364,727 |
| Total Project Costs | 4,326,918 |
| Project Cycle Management Implementing Entity Fee |  |
| Operational and Financial Management | 100,000 |
| Project Development and implementation support | 117,876 |
| Technical support and supervision | 100,000 |
| Total Project Cycle Management Implementing Entity Fee | 317,876 |
| Amount of Financing Requested | 4,644,794 |

7.4. MTR report template

- Title page

- Optional front material

  - Preface

  - Acknowledgements

- Table of contents

- Acronyms

- Executive summary

  - Introductory overview of the evaluation’s purpose, scope, audience, intended use, time period, geographic coverage, and target population groups.

  - Summary of the report and contents (to assist readers to navigate the document)

- Introduction and background

  - Evaluation features – provides an introductory overview of the evaluation’s purpose, scope, audience, intended use, time period, geographic coverage, and target population groups.

  - Report introduction – introduces the report structure and contents

  - Object of evaluation – describes the intervention being evaluated (e.g., project, programme, or strategy)

  - Implementation context – describe the larger context in which the intervention is being implemented

- Evaluation scope and objectives

  - Evaluation scope clearly delineating what is and is not to be included in the evaluation

  - Evaluation criteria that specify the standards that provide the basis for evaluative judgment.

  - Evaluation questions that elaborate the evaluation criteria, specifying what is to be assessed

  - Evaluation Matrix that details how each evaluation is answered, what indicators to measure and which data collection tool will be applied – see Annex 4.

- Evaluation approach and methods

  - Evaluation principles – the Fund’s seven evaluation principles are identified in its Evaluation Policy and elaborated in its Evaluation Principles Guidance Note

  - Evaluation data sources – primary and secondary information sources for the evaluation

  - Evaluation data collection methods – quantitative and qualitative collection methods and their procedures, including a discussion of the rational for their selection

  - Evaluation data analysis – the analytical framework or approach that will be used to synthesize and interpret evaluation findings

  - Evaluation stakeholder engagement, including the level and type of engagement

  - Ethical considerations related to data collection and use

  - Methodological limitations –, their implications for the evaluation, and any mitigation measures taken in response.

- Evaluation findings and conclusions

  - Findings and conclusions should respond to the evaluation criteria and questions.

  - Findings and conclusions should provide insights to inform solution analysis and recommendations

  - Findings should include unanticipated outcomes and impacts.

  - Findings and conclusions should be presented in a logical, coherent format

  - The logical relationship between findings and conclusions should be reinforced

  - Findings and conclusions should be individually numbered, so they can be readily cross-referenced elsewhere

- Optional lessons learned

  - Lessons should be concise and presented in a logical, coherent manner, individually numbered for cross-referencing

  - Clearly identify the relevance of the lesson and intended audience/use

  - If appropriate, explain how and why the lesson was learned.

- Evaluation recommendations

  - Recommendations should respond to the evaluations intended purpose and use, written to support management response and other evaluation follow-up and learning

  - Recommendations should be supported by evidence linked to the evaluation’s findings and conclusions that substantiates the proposed actions

  - Recommendations should be specific, practical, and feasible for implementation

  - Recommendations should identify who is responsible for follow-up and by when.

  - Additional information can be used to elaborate recommendations, such as prioritizing recommendations or the resources and budget required to achieve a recommendation.

  - Recommendations should be presented in a logical, coherent manner, individually numbered for cross-referencing. Consider using a table to format and present recommendations, as illustrated below

- Annexes

  - Evaluation Terms of Reference

  - Additional methodological information

  - Results framework

  - Stakeholder or landscape analysis / mapping

  - Summary of performance data to date

  - Summary of budget data to date

  - List of secondary data sources consulted

  - List of primary data sources

  - Data collection tools

  - Evaluation timeline

AF proposal Dairy Modernization and Market Access: Adaptation Component (DiMMAdapt), page 12.

AF proposal Dairy Modernization and Market Access: Adaptation Component (DiMMAdapt), page 2.

AF proposal Dairy Modernization and Market Access: Adaptation Component (DiMMAdapt), page 16.

AF proposal Dairy Modernization and Market Access: Adaptation Component (DiMMAdapt), page 11.

AF proposal Dairy Modernization and Market Access: Adaptation Component (DiMMAdapt), page 2.

AF proposal Dairy Modernization and Market Access: Adaptation Component (DiMMAdapt), page 16.

AF proposal Dairy Modernization and Market Access: Adaptation Component (DiMMAdapt), page 11.