## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 16 April 2021 - 16 April 2022
| Project Title: | Diary Modernisation and Market Access project: Adaptation component (DiMMAdapt)
| Project Summary: | Goal: The overall goal of the project is to reduce the vulnerability of the dairy value chain to the deleterious impacts of climate change. Objective: The project objective is to enhance the resilience to climate change of vulnerable dairy producers. The project will achieve the stated goal and objective through three outcomes: - Outcome 1.1 An enabling environment developed through training and capacity building. - Outcome 1.2 Pasture Management Plans Implemented - Outcome 2.1 Climate-smart technology demonstrations and alternative livelihood diversification.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | GEO/MIE/Agric/2019/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | IFAD | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity (MIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Georgia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Samtskhe-Javakheti, Samegrelo-Zemo-Svaneti and Imereti regions | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | October 11, 2019
IE-AFB Agreement Signature Date: |  | October 16, 2020 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | April 16, 2021 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
| Original Completion Date: | March 31, 2025
Revised Completion Date after approval of |  | N/A
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
| Category of condition | Environmental and Social Safeguards
| Condition or Requirement | Prior to signing the agreement, IFAD will submit the Environmental and Social Management Framework (ESMF) for each unidentified sub-project (USP) and relevant knowledge management outputs under Component 1 to the secretariat
| Current Status | Condition met but clearance pending by AFB Sec
| Planned actions, including a detailed time schedule | In the reporting period, the USPs are still unknown, hence no ESMFs were submitted to the secretariat
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | www.mepa.gov.ge | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Ms. Lali Durmishidze | Dominican Republic
| Email: | Lali.Durmishidze@mepa.gov.ge | Ecuador
| Date: | February 4, 2020 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Ms. Nino Tandilashvili | Equatoral Guinea
| Email: | Nino.Tandilashvili@mepa.gov.ge | Eritrea
| Date: | February 4, 2020 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Mr. Fidy Rajaonson | Fiji
| Email: | f.rajaonson@ifad.org | Finland
| Date: | November 1, 2021 | France
| Executing Agency |  | Gambia
| Name: | Nino Kizikurashvili | Georgia
| Email: | Nino.Kizikurashvili@mepa.gov.ge | Germany
| Date: | February 4, 2020 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from 16.04.2021 to 16.04.2022 |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 16.04.2022 | 351826.03 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | In accordance with the AF Guidance, the figure above is provided excluding the IE fee and reflects the amount of money disbursed from the implementing entity to the executing entity to date. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
Component 1: Climate-proofing pastoral ecosystem services (water management, pasture regeneration, and disaster risk reduction)
Outcome 1.1. An enabling environment developed through training and capacity building.
Output 1.1.1: Climate resilient and DRR solutions for pasture rehabilitation and increased productivity promoted.
| Training support and exchange visits | 0
| Development of Pasture Management Plans | 33730.86
| Pasture adaptation demonstrations for PUA farmers | 0
| Pasture management demonstrations for private pasture farmers | 0
| Silage production (fodder conservation) demonstrations | 0
| Manure composting demonstrations | 0
| On-demand demonstrations | 0
Outcome 1.2. Pasture Management Plans Implemented.
Output 1.2.1: Implementation of climate resilient and ecosystem-based adaptive pastoral grants.
| Restoration of degraded pastures, reforestation and wind breaks | 0
| Water management measures to favour pasture resilience. | 0
| Measures to prevent soil erosion, mudslides and floods. | 0
| Restoration of riverine vegetation for better water management as barriers against floods, to improve water quality and as a source of fodder. | 0
| Fodder production (seed capital financing) | 227063.99
| Silage production (fodder conservation) | 0
| Output 1.2.2: Consultancy services for GHG emission calculations. | 0
Component 2: Supporting the climate resilience of market vulnerable smallholders
Outcome 2.1 Climate smart technology demonstrations and livelihood diversification.
Output 2.1.1 Climate-smart technologies promoted though on-farm demonstrations.
| Energy efficient milk pre-cooling heat exchangers and renewable energy | 0
Output 2.1.2: Alternative non-extractive livelihoods
| Non-extractable livelihood support (Beekeeping, mushroom production, greenhouses and orchards). | 0
Project execution costs
| Recruitment of a Climate Change Specialist | 9224.08
| Facilitator Salaries | 81807.1
| Facilitator Incentives | 0
| MTR and Final Evaluation | 0
| IE fee | 62918.8
| TOTAL | 414744.83
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
Component 1: Climate-proofing pastoral ecosystem services (water management, pasture regeneration, and disaster risk reduction)
Outcome 1.1. An enabling environment developed through training and capacity building
Output 1.1.1: Climate resilient and DRR solutions for pasture rehabilitation and increased productivity promoted
| Training support and exchange visits | 0 | 2023-04-16
| Development of Pasture Management Plans | 90000 | 2023-04-16
| Pasture adaptation demonstrations for PUA farmers | 0 | 2023-04-16
| Pasture management demonstrations for private pasture farmers | 0 | 2023-04-16
| Silage production (fodder conservation) demonstrations | 0 | 2023-04-16
| Manure composting demonstrations | 0 | 2023-04-16
| On-demand demonstrations | 0 | 2023-04-16
Outcome 1.2. Pasture Management Plans Implemented
Output 1.2.1: Implementation of climate resilient and ecosystem-based adaptive pastoral grants
| Restoration of degraded pastures, reforestation and wind breaks | 0 | 2023-04-16
| Water management measures to favour pasture resilience. | 0 | 2023-04-16
| Measures to prevent soil erosion, mudslides and floods. | 0 | 2023-04-16
| Restoration of riverine vegetation for better water management as barriers against floods, to improve water quality and as a source of fodder. | 0 | 2023-04-16
| Fodder production (seed capital financing) | 0 | 2023-04-16
| Silage production (fodder conservation) | 0 | 2023-04-16
| Output 1.2.2: Consultancy services for GHG emission calculations. | 0 | 2023-04-16
Component 2: Supporting the climate resilience of market vulnerable smallholders
Outcome 2.1 Climate smart technology demonstrations and livelihood diversification.
Output 2.1.1 Climate-smart technologies promoted though on-farm demonstrations.
| Energy efficient milk pre-cooling heat exchangers and renewable energy | 0 | 2023-04-16
Output 2.1.2: Alternative non-extractive livelihoods
| Non-extractable livelihood support (Beekeeping, mushroom production, greenhouses and orchards). | 0 | 2023-04-16
Project execution costs
| Recruitment of a Climate Change Specialist | 18000 | 2023-04-16
| Facilitator Salaries | 0 | 2023-04-16
| Facilitator Incentives | 0 | 2023-04-16
| MTR and Final Evaluation | 0 | 2023-04-16
| IE fee | 63575 | 2023-04-16
| TOTAL | 171575 | [6 empty] | TOTAL | #REF! |  |  | TOTAL | #REF! |  |  | TOTAL | #REF!
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Formulas:
Est. Completion Date = [Est. Completion Date, row above]

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Management risks
Low interest and capacity of smallholder dairy producers to adopt new climate smart approaches and technologies. | Low | The programme will pay attention to technical and environmental capacity building and training as a key factor in the upgrading process. It will carry out demonstrations and raise general environmental and climate change awareness and train farmers on the economic and environmental benefits for the adoption of systems and new technologies.
The current policy and regulatory environment for pasture does not encourage the sustainable management of collective pasture, leading to degradation of this resource. | High | The current policy and regulatory environment for pasture does not encourage the sustainable management of collective pasture, leading to degradation of this resource. It was decided to carry out inventory of pasturelands in one of the target regions (Samtskhe-Javkheti), create PMPs for targeted 9500 ha of land and further implement several PMPs as funds and project timeframe allows
Climatic shock: the main effect of climate change on weather patterns is the increased occurrence of extreme weather events: droughts and flooding in particular. These weather shock can have a direct impact on animals but also contribute to the emergence of diseases | Low | The programme will introduce climate smart infrastructure and will ensure that climate adaptation measures are implemented. It will in particular ensure that breeds used in crossbreeding strategies are resilient to climate shocks (utilization of rustic breeds); Promotion of fodder conservation and of use of concentrate feeds will contribute to improving resilience; to drought; Surveillance of emerging diseases will be addressed as mentioned above.
Insufficient capacities to appropriately manage the day-to-day implementation of the project | Low | The DiMMAdapt project coordinator is supported by the DiMMA project technical and administrative staff.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
(1) Under the Component 1 (Climate-proofing pastoral ecosystem services) at the request of MEPA it was decided to allocate funds for pasture demos and relevant trainings on carrying out the inventory of pastures in one pilot region of Samtskhe-Javakheti, preparation of PMPs for target 9500 ha of inventored pastures, and further implementation of several PMPs as resources and project time-frame allows. (2) Under the Component 2 (Supporting the climate resilience of market vulnarable smallholders), at the request of MEPA and based upon desition that there is enough capacity with regard to energy efficient coollers/heaters on the one hand and on the other hand there is an existing experience in RDA of issuing grants in this direction, it was considered to be more efficient to issue grants rather than establish demos and carry out trainings (many donors, NGOs and private companies worked in this direction for years now); promotion of alternative livelihood measures will also be channeled through RDA matching grants.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity |  |  | There may be a slight risk that some project activities may exacerbate existing inequalities, through targeting some support to "lead farmers", generally better off than their peers. | Project planning and designing is done in consultation and agreement with vulnerable groups. The project will ensure the selection process will be conducted without discrimination nor favouritism. It will focus on targeting the most vulnerable categories in society with quotas ensuring women participation across all activities as well as youth participation. The project will also directly target those climate vulnerable regions that are identified as being inhabited only by rural poor smallholder farmers | Farmers (number of women, and youth) | 0 | No safeguard measure implemented during the reporting period | There may be a slight risk that some project activities may exacerbate existing inequalities, through targeting some support to "lead farmers", generally better off than their peers. | The selection will be done without discremination and favouritism ensuring quotas for women and youth. The project will target the most climate vulnerable regions and communities.
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights |  |  | Beneficiaries may be exposed to the risk of accidents while engaging in project implementation activities. | Activities under project will create employment enabling marginalized and vulnerable groups including unemployed youth and women to raise their income. - The relevant national labour laws guided by the ILO labour standards will be followed throughout project implementation. - Positive discrimination in favour of women will be used to provide fair and equal opportunity to women who seek employment as labour and gain from wages earned. - The project will not engage child labour in any of its activities. The prohibition of child labour will be part of the agreement with the beneficiaries and will be a nonnegotiable provision of the agreement. | No of women beneficiaries; % of agreements with beneficiaries that exclude child labour | 0 0 | No safeguard measures implemented during the reporting period | Beneficiaries may be exposed to the risk of accidents while engaging in project implementation activities. | The project will abide by the national labour laws and ILO labour standards. The project will undertake positive discremination in favor of women and will not engage child labour (will be specificied in the provisions of the agreements).
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats |  |  | There is a low risk that Project activities may be conducted in protected natural habitats. | Screen the project areas against the list of national protected areas to ensure there is no overlap and for each affected critical natural habitat in the project areas (if any), the PMU will provide an analysis on the nature and the extent of the impact including direct, indirect, cumulative, or secondary impacts; theseverity or significance of the impact; and a demonstration that the impact is consistent with management plans. | % of project areas screened against the list of natural protected areas; % of analysis on the tature and the extent of the impact for each affected natural protected habitats in the project area | 0 0 | No safeguard measures implemented during the reporting period | There is a low risk that Project activities may be conducted in protected natural habitats. | Screen the project areas against the list of national protected areas to ensure there is no overlap and for each affected critical natural habitat in the project areas (if any), the PMU will provide an analysis on the nature and the extent of the impact including direct, indirect, cumulative, or secondary impacts; theseverity or significance of the impact; and a demonstration that the impact is consistent with management plans.
10 – Conservation of biological diversity |  |  | There is a low risk that Project activities may have an adverse impact on critical biodiversity in the project areas. | The project will screen the project areas for critical biodiversity risks to ensure there is no overlap and the PMU will identify and exclude protected areas as detailed in Principle 9 and will furthermore only utilise indegenious species, hereby mitigating any risk of species invasion. | % of project areas screened against the list of critical biodiversity areas; % of analysis on the tature and the extent of the impact for each affected critical biodiversity areas in the project area | 0 0 | No safeguard measures implemented during the reporting period | There is a low risk that Project activities may have an adverse impact on critical biodiversity in the project areas. | The project will screen the project areas for critical biodiversity risks to ensure there is no overlap and the PMU will identify and exclude protected areas as detailed in Principle 9 and will furthermore only utilise indegenious species, hereby mitigating any risk of species invasion.
11 – Climate change |  |  | There is no risk associated with DiMMAdapt, but with DiMMA activities, which may result in increase of GHG emissions. | DiMMAdapt has developed a EMSP (in output 1.2.2 and ESP11 in annex 3) to monitor and report on any changes in GHG emissions and take corrective action should they be seen to increase | Herd numbers; Net GHG emissions in tCO2-eq | 0 0 | No safeguard measures implemented during the reporting period | There is no risk associated with DiMMAdapt, but with DiMMA activities, which may result in increase of GHG emissions. | Set up a system to monitor the herd numbers and net GHG emissions.
12 – Pollution prevention and resource efficiency
13 – Public health
14 – Physical and cultural heritage |  |  | There is a low risk that Project activities may be conducted in cultural heritage sites. | The project will ensure whether there will be any national cultural heritage sites in the project areas and propose measures to avoid any alteration, damage, or removal of physical cultural resources, cultural sites, and sites with unique natural values | % of project areas screened against the list of cultural heritage sites; % of analysis on the tature and the extent of the impact for each affected clutural heritage sites in the project area | 0 0 | No safeguard measures implemented during the reporting period | There is a low risk that Project activities may be conducted in cultural heritage sites. | The project will ensure whether there will be any national cultural heritage sites in the project areas and propose measures to avoid any alteration, damage, or removal of physical cultural resources, cultural sites, and sites with unique natural values
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | The GRM is the main mechanism to monitor unanticipated ESP risks.
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The Implementing Entity used the ESMP developed at design to implement the ESP safeguard measures.
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The PMU AF coordinator has the overall responsibility for ESMP implementation. She is supported by technical specialists (e.g. the livestock specialist). All contracts are scereend against the 15 AF ESP principles.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes, the arrangements have been effective.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | The PMU AF coordinator has the overall responsibility for ESMP implementation. She is supported by technical specialists (e.g. the livestock specialist). All contracts/activities are secreend against the 15 AF ESP principles. IFAD assesses ESMP implementation at least once per year during supervision missions by a team of international experts. The climate and NRM consultant leads the assessment.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | No USPs have been identified during the reporting period. Once identified, the ESMP will be updated.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP] | NA
USP 2: [name the USP] | NA
USP 3: [name the USP] | NA
USP 4: [name the USP] | NA
USP 5: [name the USP] | NA
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | The gender analyses of the sector was developed during the project preparation phase and it is the part of the project design document.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | The project result framework include gender-responsive indicators and it is broken down at the different levels.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Enhancing the resilience to Climate Change of vulnerable dairy producers. | Output 1.2.1: Climate resilient and ecosystem-based adaptive pastoral investments implemented. | Number of hectares of pasture rehabilitated, restored or protected | 0 | 9,500 ha of pastures rehabilitated, restored or protected. 6,000 farmers (1,800 women, 4,200 men and 3,000 youth) are to receive awareness raising demonstrations | N/A (activities not started yet)
Alternative, complementary, non-competitive, non-extractive livelihood jobs created. | Output 2.1.2 Alternative, complementary, non-competitive, non-extractive livelihood jobs created. | Number of households benefitting from alternative non-extractive industry activities. | 0 | 250 jobs (75 women, 175 men and 125 youth) will be created for the market vulnerable beneficiaries. | N/A (activities not started yet)
Climate-smart technologies and alternative livelihood measures promoted. | Output 2.1.1 Climate-smart technologies and alternative livelihood measures promoted. | Number of farmers exposed to climate smart technology demonstrations in milk-precooling, AI and crossbreeding and solar power. | 0 | 3,800 market vulnerable farmers to receive climate-smart demonstrations. 30 % women, 50% youth. | N/A (activities not started yet)
Climate resilient and DRR solutions for pasture rehabilitation and increased productivity promoted. | Output 1.1.1: Climate resilient and DRR solutions for pasture rehabilitation and increased productivity promoted. | Number farmers receiving pasture management, silage and fodder conservation demonstrations. | 0 | 6,000 farmers (1,800 women, 4,200 men and 3,000 youth) are to receive awareness raising demonstrations | N/A (activities not started yet)
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
Women inclusion will involve at least 30% quota in seed capital investment
Women inclusion will involve at least 30% quota in demo plot establishment
Set 30% quota for: a) the adoption of alternative livelihood activities by youth and b) PUA members in PUAs selected for grant financing for improving pastures.
Lower expected grant contributions for women - MVDPs and PDPs (lowered from 40% to 20%);
Lower expected grant contributions for women - Non-Extractive Livelihood activities (lowered from 20% to 10%).
Training on milk management hygiene should target almost exclusively women, since they are the ones involved in milking activities. It is therefore essential that these training sessions are organized as “women-friendly”. This implies that the trainer is a woman (systematic). Note: men are welcome to attend if they wish, but really the primary target group for this particular training is women.
Conduct training in women's empowerment and equality issues
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | IFAD employs a gender and social inclusion specialist during annual supervision missions to assess the project's performance on targeting and gender mainstreaming, and provide guidance to the project on improving its gender outreach. Assessments and recommended actions are reported in Aide Memoires to the Executing Agency and in the Supervision mission reports.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes. The IE’s supervision mission in November 2021 rated the project’s performance on gender as moderately satisfactory. The IE’s gender expert recommended a number points to finalize the gender strategy, and explicitly encouraged the EE to find ways to encourage women, youth and women-headed households to partake in the grant schemes.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The DiMMA project has a dedicated gender focal point and developed a gender and youth strategy and action plan. Gender perspectives are reflected in the value chain analysis. The gender focal point supports the project M&E officer in capturing gender-disaggregated data. The project’s service providers have also hired gender specialists and their syllabuses include gender empowerment. A training needs assessment for women was developed.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes. The established monitoring system collected gender-disaggregated data and captured the involvement of women's and youth's activity in the project. Further analysis revealed the gaps along the dairy value chain that need to be addressed and what kind of training should be provided especially for women and youth. Recommendations provided by the IE during the supervision mission are being addressed.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No capacity gaps were identified during the reporting period that affected GP compliance.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | It was noted that participants of the training sessions of milk management and hygiene were men in most cases. The project made the decision to target almost exclusively women, since they are the ones involved in milking activities. It is therefore essential that these training sessions are organized as “women-friendly”.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Component 1: Climate-proofing pastoral ecosystme services |  | Outcome 3 | Demo plots and PUAs identified for capacity building and training plan developed |  | Lacking regulation on pasture tenure/management and lacking data on pastures presents a hurdle to intervene on pastures. The PMU aims to overcome this through an inventory of pasturelands to identify user groups and pasture areas subject to climate-resilient measures. Manure demo plots are going to be established and relevant trainings to be carried out. Respective changes are done in the contract of SP (CBSP) | MS
|  |  | Outcome 2 | Pasture areas pre-selected, participatory engagement modalities determined, and template for pasture management plans developed |  | Lacking regulation on pasture tenure/management and lacking data on pastures presents a hurdle to intervene on pastures. The PMU aims to overcome this through an inventory of pasturelands to identify user groups and pasture areas subject to climate-resilient measures. Inventory of pasturelands in planning to identify user groups and pasture areas subject to climate-resilient measures through pasture management plans | MS
|  |  | Outcome 5 | None, as pasture management plans first need to be set up to determine climate resilient measures that then will be implemented |  | N/A | MS
| Component 2: Supporting the climate resilience of market vulnerable smallholders |  | Outcome 6 | Delivery mechanisms via Rural Development Agency and service providers laid out |  | Preliminary delivery mechanisms laid out for further implementation in the next reporting period. | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Renaud Colmant
| Email: | r.colmant@ifad.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
(1) Demonstration Plots (DPs). DP owners need to be better identified/selected right from the beginning and in line with the DP methodology established under the contracts of the Capacity Building Service Providers (CBSPs). Applicants who do not meet the criteria, esp. in terms of technical capacity, representativity of the target community, should not be validated. (2) Pasture management interventions under DiMMA are still at a standstill since the Government has not yet issued a regulation/law on communal pasture lands. This prevents the project from implementing its activities as per design. After intensive brainstorming within the executing entity, it was decided to propose some changes during implementation. In particular, it was decided to tackle first the main problem for the quick proceed with the relevant legislation, that is the absence of inventory of pastures: MEPA does not possess information on pastures, on their condition, their sizes, etc. It was agreed to conduct a full inventory of pastures in the Samtskhe-Javakheti region, that is among the most promising for improved pasture management. Based on the results of the inventory, the project will engage in the preparation of pasture management plans for the targeted 9,500 ha. The current service provider contract will be amended to reflect above two activities. (3) Non-extractive livelihood activities (target = 250 youth, 50% youth, with grant of 4,000 GEL). Potential activities have been defined as small greenhouses (for the production of vegetables, berries, flowers, etc.), agro-tourism, collection/drying of medicinal plants (to be linked with GeoFlower company), beekeeping (provided that they are properly monitored, for instance by using the GPS system piloted by Elkana), etc.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Component 1: Climate-proofing pastoral ecosystme services |  | Outcome 3 | Training on manure management and energy efficiency |  | Service providers have been contracted under the IFAD DiMMA proejct who will also provide training on manure management and energy efficiency. Trainings will take during the next reporting period. | MS
|  |  | Outcome 2 | First batch of pasture management plans developed |  | Lacking regulation on pasture tenure/management and lacking data on pastures presents a hurdle to intervene on pastures. The PMU aims to overcome this through an inventory of pasturelands to identify user groups and pasture areas subject to climate-resilient measures | MS
|  |  | Outcome 5 | None, as pasture management plans first need to be set up to determine climate resilient measures that then will be implemented |  | N/A | MS
| Component 2: Supporting the climate resilience of market vulnarable smallholders |  | Outcome 6 | Establsih several demos and grants on energy efiicient technologies; and grants for small greenhouses |  | Grants manual has been developed that includes enegy efficiency technologies and small greenhouses. Grants to be disbursed in next reporting period together with technical assistance for greenhouses. | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | nino.kizikurashvili
| Email: | Nino.Kizikurashvili@mepa.gov.ge
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
(1) Under the component 1 (Climate-proofing pastoral ecosystem services) at the request of MEPA it was decided to allocate funds for pasture demos and relevant trainings on carrying out the inventory of pastures in one pilot region of Samtskhe-Javakheti, preparation of PMPs for target 9500 ha of inventoried pastures, and further implementation of several PMPs as resources and project time-frame allows. (2) Under the component 2 (Supporting the climate resilience of market vulnerable smallholders), at the request of MEPA and based upon decision that there is enough capacity with regard to energy efficient coolers/heaters on the one hand and on the other hand there is an existing experience in RDA of issuing grants in this direction, it was considered to be more efficient to issue grants rather than establish demos and carry out trainings (many donors, NGOs and private companies worked in this direction for years now); promotion of alternative livelihood measures will also be channelled through RDA matching grants.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Negative: (1) Abcence of effective legal framework on pastures put under threat sustainabiity of investent in the direction of establishment of either private demos or PUAs. Positive: (1) experience, training materials and established manure management demos (compost, vermi-compost) are planned to be used in DiMMA target regions with respect of capacity building in manure management direction. (2) based upon desition that there is enough capacity with regard to energy efficient coollers/heaters on the one hand and on the other hand there is an existing experience in RDA of issuing grants in this direction, it was considered to be more efficient to issue grants rather than establish demos and carry out trainings (many donors, NGOs and private companies worked in this direction for years now).
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There were delays with implementation of demo plots due to COVID situation in the country. Policy paper entitled "Feasibility study of intergrated pastureland and livestock development in Georgia including cost-benefit analysis for currebt and future scenarios" is considered to be a measure aimed at reduction of delays. this Feasibility study is going to become a part of the forthcoming National Pastureland Management Policy Document (NPMPD), which will provide a good enabling framework to empower these pasture organizations, and on the other hand, inform the service providers assisting the DiMMA supported pasture organizations so that their support is aligned with eventual legal or other requirements
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | (1) Under the component 1 (Climate-proofing pastoral ecosystem services) at the request of MEPA it was decided to allocate funds for pasture demos and relevant trainings on carrying out the inventory of pastures in one pilot region of Samtskhe-Javakheti, preparation of PMPs for target 9500 ha of inventoried pastures, and further implementation of several PMPs as resources and project time-frame allows. (2) Under the component 2 (Supporting the climate resilience of market vulnerable smallholders), at the request of MEPA and based upon decision that there is enough capacity with regard to energy efficient coolers/heaters on the one hand and on the other hand there is an existing experience in RDA of issuing grants in this direction, it was considered to be more efficient to issue grants rather than establish demos and carry out trainings (many donors, NGOs and private companies worked in this direction for years now); promotion of alternative livelihood measures will also be channelled through RDA matching grants.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Keeping in mind that field activities have not started yet, no unwanted negative impacts have been identified or reported via the Grievance Redress Mechnaim of the project in the reporting period.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Contracted Service providers are requested to ensure women inclusion with at least 30% quota in demo plot establishment.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | NA
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A
What measures are being/could have been put in place to improve project/program results? | N/A
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | N/A
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | N/A
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | N/A
If learning objectives have been established, have they been met? Please describe. | N/A
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | N/A
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization. | N/A
Yes
No

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Overall objective: Enhancing the resilience to Climate Change of vulnerable dairy producers. | Number of hectares of pasture rehabilitated, restored or protected | 0 | 0 | 9,500 ha of pastures rehabilitated, restored or protected.
| Number of households benefitting from climate resilient improvements | 0 | 0 | 3,900 households (12,870 people) will benefit from climate resilient improvements.
Outcome 1.1 An enabling environment developed through training and capacity building.
Output 1.1.1: Climate resilient and DRR solutions for pasture rehabilitation and increased productivity promoted. | Number farmers receiving pasture management, silage and fodder conservation demonstrations. | 0 | 0 | 6,000 farmers (1,800 women, 4,200 men and 3,000 youth) are to receive awareness raising demonstrations
| Number of PUA’s receiving training | 0 | 0 | 76 PUA’s to receive capacity building in pasture management.
Outcome 1.2. Pasture Management Plans Implemented.
Output 1.2.1: Climate resilient and ecosystem-based adaptive pastoral investments implemented. | Number of hectares of pasture land rehabilitated, improved or protected. | 0 | 0 | 9,500ha of pasture land will be rehabilitated, improved or protected.
| Number of households benefitting from pasture rehabilitation. | 0 | 0 | 3,900 households will benefit from Climate resilient and ecosystem-based adaptive pastoral investments
Output 1.2.2 GHG from DiMMA cattle increases offset | tCO2eq resulting from DiMMA cattle numbers | 0 | 0 | A maximum of 0 tCO2eq will result from the DiMMA cattle numbers.
Outcome 2.1 Climate smart technology demonstrations and livelihood diversification.
Output 2.1.1 Climate-smart technologies and alternative livelihood measures promoted. | Number of farmers exposed to climate smart technology demonstrations in milk-precooling, AI and crossbreeding and solar power. | 0 | 0 | 3,800 market vulnerable farmers to receive climate-smart demonstrations
Output 2.1.2 Alternative, complementary, non-competitive, non-extractive livelihood jobs created. | Number of households benefitting from alternative non-extractive industry activities. | 0 | 0 | 250 jobs (75 women, 175 men and 125 youth) will be created for the market vulnerable beneficiaries.
Note on E7: Renaud: Tamuna

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | IFAD
Type of implementing entity | Multilateral Implementing Entity (MIE)
Country | Georgia
Region | Eastern Europe
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  | 0 |  | Total |  | 6000 |  | Total |  |  |  | Total
|  | % of female beneficiaries |  | 0% |  | % of female beneficiaries |  | 30% |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  | 0% |  | % of Youth beneficiaries |  | 50% |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Disaster risk reduction | 2: Low capacity | Total | 3900 | Disaster risk reduction | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 30% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Agriculture |  | 50% |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 2: Partially not aware |  | 3000 | 30% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 0 | 20% to 39% | 2: Partially not aware |  | 76 | 20% to 39% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Agriculture | land | 3: Moderately effective | 1 | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 9500 | ha rehabilitated | 1: Ineffective | Rangelands | 9500 | ha rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 2: Limited improvement |  | 3800 |  | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agriculture |  | 252 | 6000 | Agriculture |  | 30%
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
Note on I54: თამარ ცინცაძე: benefited from pasture rehabilitation, from 9500 ha rehabilitated pasture.
Note on H108: თამარ ცინცაძე: market vulnerable farmers to receive climate-smart demonstrations.
Note on I108: თამარ ცინცაძე: We don’t have such target
Note on K120: თამარ ცინცაძე: NA