## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | June 2021 to June 2022
| Project Title: | Enhancing climate resilience of rural communities and ecosystems in Ahuachapán Sur, El Salvador.
| Project Summary: | The main project objective is reducing the vulnerability of communities and productive ecosystems in the Municipality of San Francisco Menendez to drought risk, soil erosion, and flash floods due to climate change and climate variability. The project will integrate forest landscape restoration as a climate change adaptation strategy targeted towards increasing forest cover, improving the hydrological cycle, increasing the amount of available water, and regulating surface and groundwater flows, while maintaining and improving water supply and quality. The project landscape approach will ensure that land degradation is reduced (or reversed) and that productivity is maintained and made resilient to climate change impact, thus contributing to better food security and community resilience. By ensuring and enabling institutional and governance environment, the project will generate coordinated and informed actors with the capacity to address appropriate adaptation measures in the medium and long term thus resulting in a genuine local resilience to climate change.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Ministry of environment and natural resources (MARN) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | El Salvador | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Ahuachapán Sur: Municipalities San Francisco Menéndez, Municipio de Jujutla; Municipio de Guaymango; Municipio de San Pedro Puxtla; Municipio de Tacuba.m Department de Ahuachapán, El Salvador. El Department of Ahuachapán has the following coordinates: 14 02 56" LN North ; 13 52 43" LN South; 89 45 22" LWGo East y 89 58 18" LWG e East. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2019-10-11
IE-AFB Agreement Signature Date: |  | June 5, 2020 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | June 16, 2021 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | August 10, 2023
February 10, 2026 : Expected Date of Operational Closure
| Original Completion Date: | August 10, 2026: Expected Date of Financial Closure
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
| Category of condition | Other
| Condition or Requirement | UNDP will submit an assessment of potential complementarities with the project “Upscaling climate resilience in the dry corridor agroecosystems of El Salvador” (RECLIMA) with any necessary updates.
| Current Status | Condition met and cleared by the AFB Sec
Planned actions, including a detailed time schedule
| Category of condition | Budget
| Condition or Requirement | Resubmit a revised proposal with an amendment of the disbursement schedule to display whole numbers.
| Current Status | Condition met and cleared by the AFB Sec
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://www.adaptation-fund.org/project/enhancing-climate-resilience-of-rural-communities-and-ecosystems-in-ahuachapan-sur-el-salvador/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Maritza Guido Martínez | Dominican Republic
| Email: | maritza.guido@undp.org y mguido@marn.gob.sv | Ecuador
| Date: | 2021-06-11 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Ryna Avila | Equatorial Guinea
| Email: | ryna.avila@undp.org | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ministry of Environment and Natural Resources (MARN) / Eva Colorado | Fiji
| Email: | Eva Maria Colorado Panameño: eva.colorado@marn.gob.sv | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Ministry of Environment and Natural Resources (MARN) | Georgia
| Email: | Miguel Alberto Gallardo Meléndez mgallardo@marn.gob.sv | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [from 1 july 2021 to 30 june 2022] |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [30/06/2022] | 443493.56 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | For this reporting period, UNDP received a first tranche from the AF for a total of USD 1,718,487.00. UNDP as Implementing Entity deducted an amount of USD 336,362.00 as Management Fee from the total amount of the Grant in accordance with the terms set forth in Clause 8.01 of the AF Legal Agreement. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 16868.91 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1 Landscape planning through community restoration plans for ecosystem based adaptation and landscape management | 68823
| Output 1.2 Forest landscape restoration is implemented to meet climate adaptation needs and improve ecosystem services | 25600
| Output 1.3 Promotion of Sustainable and Resilient Agriculture to Climate Change in critical ecosystems | 1504
| Output 1.4. Integrated Watershed Management within Community Restoration Plans | 258053.83
| Output 2.1 Identification and promotion of climate resilient products to enhance rural livehoods | 1668
| Output 2.2 Adapted livehood s introduced to new hight value markets to generate economic alternatives in the region | 7196.49
| Output 3.1 Generated the capacity and knowledge to monitor EBA and restoration interventions in South Ahuachapán | 0
| Output 3.2. Improved production and utilization of hydrological and climate information applied to decision-making by stakeholders and local development agents | 0
| Output 4.1. Establishment technical capacities in municipal governance to integrate information and promote concerted action for adaptation | 3500 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
| Output 4.2 Local adaptation plans designed and included in the municipality´s territorial planning | 0
| Output 4.3 Enhanced capacities in local organizations to articulate actions and mobilize financing for Ecosystem-based Adaptation | 0
| Project Execution Costs | 77148.24
| Implementing Management Fee | 336362
| TOTAL | 779855.56
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1 Landscape planning through community restoration plans for ecosystem based adaptation and landscape management | 64568.84 | 2023-05-01
| Output 1.2 Critical ecosystem are restored to meet climate adaptation needs and improve ecosystem | 8786.07 | 2023-05-01
| Output 1.3 Promotion of Sustainable and Resilient Agriculture to Climate Change in critical ecosystems | 1292669.06 | 2023-05-01
| Output 1.4 Integrated Watershed Management within community Restoration Plans | 0 | 2023-06-01
| Output 2.1 Identification and promotion of climate resilient products to enhance rural livehoods | 137182.4 | 2023-05-01
| Output 2.2 Adapted livehood s introduced to new hight value markets to generate economic alternatives in the region | 72100 | 2023-05-01
| Output 3.1 Generating the capacity and knowledge to monitor EBA and restoration interventions in South Ahuachapán | 107400 | 2023-05-01
| Output 3.2 Improved production and utilization of hydrological and climate information applied to decision-making by stakeholders and local development agents | 201400 | 2023-05-01
| Output 4.1. Establishment technical capacities in municipal governance to integrate information and promote concerted action for adaptation | 97160 | 2023-05-01
| Output 4.2 Local adaptation plans designed and included in the municipality´s territorial planning. | 15000 | 2023-04-01
| Output 4.3 Enhanced capacities in local organizations to articulate actions and mobilize financing for Ecosystem-based Adaptation | 89300 | 2023-06-01
| Project Execution Costs | 110400 | 2023-06-01
| Implementing Management Fee (for deduction per Legal Agreement) | 89194 | 2023-01-23 |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
| TOTAL | 2285160.37
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: insertar la fecha del periodo de reporte del 1 de Julio 2021 al 30 de junio 2022

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
There is uncertainty regarding the local political will to incorporate adaptation measures into planning instruments. | Political/ Low | As a mitigation measure in the face of the uncertainty of the municipal governments to include an adaptation plan as a local planning tool, the project will establish a technical advisory committee with the staff of the environmental units and other key actors, which will guarantee an adaptation strategy. management and adaptation.
Institutional and policy changes related to change of government delay project implementation | Political/Medium | Currently the central government has not presented changes and is promoting adaptation and restoration plans through MARN, which favors the project.
Security issues in the region slow the implementation of project activities | Operational / Low | The project team and MARN are coordinating with municipal authorities, local police and producer associations in planning and developing field visits, capacity building events and technical assistance activities.
Limited engagement of the local actors in the implementation of the project activities which leads to a lack of appropriation of the adaptation measures affecting project sustainability in the long term. | Operational/ Low | In its initial document, the project proposes the microregion of Ahuachapan Sur as territorial actors, which currently does not exist. Today the platform that MARN has established is the COAL, which is made up of all the sectors and actors of Ahuachapán Sur. The project has looked to engage the COAL actively
Extreme weather events affect the projects outputs that are sensible to the occurrence of extreme weather events. | Operational/ Financial/Low | The climate event mitigation process will consist of establishing community restoration areas and also having seeds that are resistant to climate events. An extreme event would affect the local economy, so work will be done to have a tool that allows monitoring the economic and climatic impact to measure vulnerability and take action.
Conflicting interests among stakeholders with respect to land use and access to and use of natural resources impact project results and activities. | Institutional/Medium | The mitigation measures for the use of the land in the project will be established through the different agroforestry or silvopastoral systems and their techniques to restore the soil, which will be identified with the diagnosis of farms. Field visits to plots will be made in order to define each diagnosis and define the landscape. During this time the project has looked to provide socialization in the area on the project's approach and theory of change.
Delays in executing project funding at the local level | financial / potential impact is Medium | In the face of internal administrative delays, the project has been able to work through local processes with the support from FIAES including in some cases its own resources. This was the case in initial training and first call for proposals. FIAES is the delegate to work on community restoration plans, in case of delays in administrative processes they can operate with their own resources to ensure there is little impact in execution. This was the case in the first transfer from project resources which was delayed due to an initial lengthy internal administrative process.
2) Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The watershed approach in decision-making for community restoration plans must consider the communities of the upper basin of Ahuachapán Sur corresponding to the Municipality of Tacuba, which is not included among the Municipalities affected by the Project. . | Social and Environmental | The project will include the communities of the basin above San Francisco Menéndez, which are from the municipality of Tacuba.
Hiring staff for the project takes longer than expected and delays the execution associated with the monitoring of components 2 and 4 of the project. The transition of the centralized services offered by UNDP, the GSSU, has affected. | Operational | UNDP is making the necessary arrangements with the GSSU to support the project in contracting. As it is a Support to NIM project, MARN will use its national regulations to hire the rest of the technical staff.
Current mapping of the project has identified a self-designated indigenous population in the municipality of Tacuba in the Upper Basin of "Cara Sucia - San Pedro de Belén" that should be included within the framework of the project to ensure that they are not excluded from the benefits of the project. | Social and substantial | In the project, if these groups were identified at the Inception Workshop, then appropriate steps will be taken for their participation in accordance with the Project's Environmental and Social Management Plan and UNDP policies. An Integration Plan of the Indigenous Peoples Plan (PIIC) and a legal analysis will be carried out on the issues of land tenure in indigenous peoples and the legal framework for the certification of native seeds.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Whether risk mitigation measures were employed during the reporting period. They are summarized below: • Identification of indigenous peoples in the upper area of ​​Tacuba. These were not contemplated in the ProDoc and were identified in the initial workshop, which is why they are being included in the intervention zone. • In this period, the micro-assessment to MARN (required by UNDP's HACT policies), expired and took longer than expected (scheduled for 2 months and was carried out in 4 months), these delays due to multiple causes, including staff with Covid. The mitigation measure taken was that UNDP El Salvador authorized the use of a ceiling of $150,000

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE - Cumplimiento de la política ambiental y social
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity |  |  | Marginalized groups of women, the elderly and youth could be excluded from participating. | A series of meetings were held at the local level with stakeholders from different municipalities, involving women, youth, and agricultural, livestock, and water boards and fishermen community associations to produce a list of stakeholders. | 65 community restoration plans established: signed and monitored | Calls for proposals and evaluation commission to ensure that the allocation is fair and without discrimination. | Consultation processes with local actors by communities
3 – Marginalized and vulnerable Groups |  |  | Restoration activities may restrict access to resources affecting the livelihoods of marginalized individuals or groups | Consultations were held with organized women's groups from the municipalities of Ahuachapán Sur to socialize the Project and their participation in the implementation of the gender action plan. | Number of groups: productive, associations, youth, women, that participate in workshops and training (lists). | Field surveys and report, as well as workshops. | Capacity building and knowledge dissemination activities will be developed in the 4 components of the Project.
4 – Human rights |  |  | The right to health, water, and food security may be affected if climate risks are not anticipated | Restoration activities will be implemented in accordance with the restoration and lan use guidelines established by MARN. | Monitoring and tracking of restorarion activities are done systematically | Community restoration plans will include provisions to ensure that activities will not cause adverse impacts on critical habitats. | Community members accept and engage into restoration activities | No further assessment required for compliance
5 – Gender equality and women’s empowerment |  |  | Women may have unequal access to resources or opportunities and benefits of the Project. | Include young women in decision-making processes and in the different activities of the Project | At least 1,152 female households are interested in adopting income diversification models. | A market study aimed at women producers, associations and organization | There were informative meetings with women's organizations about the components of the Project and their way of participating.
6 – Core labour rights |  |  | No further assessment required for compliance. |  |  |  |  | No further assessment required for compliance
7 – Indigenous peoples |  |  | Indigenous peoples are excluded from the activities and benefits of the Project. | An Indigenous Integration Plan (PIIC) will be included in the Project activities. Socialization and coordination meetings have been held with the council of indigenous peoples of Tacuba. | Members of the indigenous community accept and participate in restoration activities, seed banks, diversify agriculture, improve livelihoods and generate income. | Analysis of adequate participation with the indigenous peoples of Tacuba | Informative meetings on the project and measures for the participation of the indigenous peoples of Tacuba | None identified. The project will promote the participation of indigenous peoples and provide inputs to he development of the productive and establishment of seedbanks. identifyin seeds used in ancestral and taditional practices. | Social and environmental screening will take place in this area prior to activities taking place within the ESMF guidelines. Funds allocated per outputs are considered appropriate to work with these communities.
8 – Involuntary resettlement |  |  | The project will not implement or support any activities that result in involuntary resettlment. No further assessment is required.
9 – Protection of natural habitats |  |  | Restoration activities may not result in maintenance of ecosystem functionality that may affect critical habitats. | Restoration areas for conservation and production purposes will be defined in the community restoration plans. | 3,864 hectares of landscape will be under restoration. | Support conservation efforts in El IMPOSIBLE and Barra de Santiago | Species studies, economic valuation of wetlands and water monitoring will begin. | None identified. The project includes restoration activities to restore ecosystem functions and cecrease degradation in the areas nature and The community restoration plans. | The municipalities of San Francisco Menendez, Jujutla, Guaymango, San Pedro Puxtla, Tacuba, where a wide range of ecosystems are presente, cinluding coastal-marine; mangroves, dry tropical forests; and agroecosystems.
10 – Conservation of biological diversity |  |  | There is a risk in the use of exotic species in restoration activities | Local knowledge of climate-resilient crops and native species will give access to native seeds and they will be stored in seed banks. Informative meetings have been held with community leaders convened by CENTA. | Development of Seed Banks and 3 market studies and production value chains to diversify livelihoods | Local and traditional knowledge, promoted and shared. | Adopt organic farming techniques, soil and water conservation | None identified, the restoration guidelines identify the use of native species | Training will be provided around the project's ESMF to make the guideline explicit to all actors.
11 – Climate change |  |  | The project will not result in an increase in greenhouse gas emissions or other drivers of climate change. The project is directly supporting the implementation of ecosystem-based adaptation measures at the local and landscape levels, including the reforestation of degraded areas, natural forest systems, and agricultural areas. The ecosystem-based adaptation measures proposed in the project are expected to generate climate change mitigation benefits through increased carbon sequestration and have been targeted to the landscape where these measures are most needed. No further assessment required for compliance.
12 – Pollution prevention and resource efficiency |  |  | During the implementation of agroforestry systems, pesticides that affect the environment could be used. | All the components of the Project include activities to improve capacities and disseminate knowledge aimed at community leaders, farmers, and municipal governments. | Restoration techniques and land use according to the guidelines of the MARN Restoration Program. | Identification and systematization of productive technological packages that consider climate-resilient crops and species. | Support the monitoring of species carried out by the MARN in biodiversity of wetlands and species of protected natural areas to corroborate their presence and impact of other external agents. | None identified, the project's ESMF includes use of pesticide as an exclusionary criteria. | Training will be provided around the project's ESMF to make the guideline explicit to all actors.
13 – Public health
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | A follow-up has been carried out, mainly as a result of the inception workshop at a national and local level that deemed the importance of including the area of Tacuba. The actions were to include the indigenous peoples in the beneficiary actors of the Ahuachpán Sur Project and also to prepare an integration plan.
Have unanticipated ESP risks been identified during the reporting period? |  | Yes, the project was able to verify the presence of indigenous populations within the project beneficiary area as the municipality of Tacuba was included in the project. Climate change risks where also identified mainly in terms of the impact of extreme weather to project investments (landscape restoration activities)
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | Safeguard measures: a) include them as local actors who will benefit from the 4 components of the Project. b) Develop a plan for the integration of indigenous peoples. The project will take into account existing climate information as well as that developed by the project to guide project actions (See Risk Assessment tab cell E14)
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The first year of execution has been to establish the operational structure that, in conjunction with FIAES, would work with the organizations selected to receive grants. For the time being, induction workshops have been held on the application of ESP safeguards to FIAES, to ensure their application.
Have the implementation arrangements been effective during the reporting period? |  | We cannot verify it at this time, because we are laying the foundations to start operating.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The project team an MARN will coordinate with municipal authorities, local police and producer associations in planning and developing field visits, capacity building events and technical assistance activities. Equally, FIAES in component 1 of the project, has locally implemented calls for local organizations to actively participate.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The implementation activities during year 1 of the project, if they have been effective because the coordination with the different actors of the COAL and its governance (operational plans and operating-regulatory structure) have been developed.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | There is installed capacity in the MARN that supports the different processes, but the hiring of the personnel that will follow up the different stages of the Project in the territory of Ahuachapán Sur is pending.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | Not applicable as community restoration plans (UPS) have yet to be enacted, the project during this reporting period began with socialization and on the ground scoping.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Has not been received
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Households in San Francisco Menendez that are resilient to climate-related events, disaggregated by those headed by women to ensure that women headed household are benefited by the program throughout its various strategies and based on the indicators at output level. | Objective | Number of Households | 0 | 6,396 households of which approximately 1152 are headed by women | Satisfactory
Local livelihood diversification and income generation models systematized and consolidated for use by producers, a focus of these models will include those that are relevant to women producers | Objective | Small holder cooperatives that have been transmitted local livelihood and diversification and income generation models | 0 | 80 small holder cooperatives of which 16 are women cooperatives | Satisfactory
Productive groups (cooperatives and associations those favoring women producers) in San Francisco Menendez that benefit from the introduction of diversified agriculture, livelihood strategies and options. Women based cooperatives and associations will be targeted to ensure that capacities are provided to women producers | Outcome | Number of productive groups | 0 | 83 cooperatives (of which 16 favor women) will benefit from enhanced capacities generated by the extension support provided as a result of the project | Satisfactory
Local livelihood diversification and income generation models systematized and consolidated for use by producers | Output | Number of climate resilient products/practices | 0 | 6 of which one will favor women | Satisfactory
High value market chains identified for diversified livelihoods strategies | Output | Number of high value market chains identified for diversified livelihoods strategies | 0 | 3 market studies. From these, 1 market study is developed to target women producers, organizations and associations. | Satisfactory
Enhanced capacity to generate relevant climate and hydrological information to address the impact of climate change on natural resources in South Ahuachapán | Outcome | The generation of improved climate products relevant at the local level | 0 | 5 new climate products developed by the Observatorio Ambiental targeted to South Ahuachapán. 1 knowledge product targeted to women | Satisfactory
Uptake of generated hydro meteorological information | Output | % of the rural population using CI | 0 | At least 40% of the rural population (51% of which are women) in the four municipalities in South Ahuachapán make use of the climate information being provided to the region | Satisfactory
Planning tools developed to address climate vulnerabilities of Ahuachapán Sur | Output | Planning tools | 0 | One climate vulnerability assessment of south Ahuachapán that considers how climate change impacts women. | Satisfactory
Enhanced capacity to capture climate finance from diverse sources and to identify adaptation investments | Output | Organizations with enhanced capacity to attract climate finance and identify adaptation projects | 0 | 5 local organizations and one local organization will target women. | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Individual Consulting on Gender will be carried out for year 2.
Have the implementation arrangements at the IE been effective during the reporting period? |  | In year 2 it will define
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | During the first year, the following has been developed: a) Socialization of the Project to women's organizations in the different municipalities of Ahuachapán Sur. b) Participation of women in the different COAL workshops. c) Collection of information on the capacities of women's groups in their territories.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | It has been partially effective, in the work meetings with the women of the different municipalities, progress has been made, but the hiring of the personnel in charge of making the project's gender plan operational in year two is pending
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Pending the hiring of personnel for component 4 and component 2 of the project. Only the socialization process and the capture of information from women's organizations have been carried out.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
OBJECTIVE | Number of households in San Francisco Menendez that are vulnerable to climate-related events (disaggregated by those headed by women) | 6,396 rural households | In year 1 of the project, two calls for proposals have been for the participation of local organizations. The characterization of the community restoration plans, key areas for productive development will be identified by community and using existing land use mapping ensuring that productive restoration in these areas support the sustainable management of the landscape. | By the end of the project, 6,396 households (100% of rural households of which approximately 1152 are headed by women) in San Francisco Menendez benefitted from the project therefore, reducing vulnerability and increasing resilience of communities and natural ecosystems to climate variability and change
| Number of local livelihood diversification and income generation models systematized and consolidated for use by producers | 0 | The period of year 1 developed coordination actions with MAG-CENTA to incorporate the project in the agricultural committees of the Municipality. | At least 6 technological packages and 3 market studies have generated local diversification models that have been transmitted to at least 80 small holder cooperatives, of which 16 are women cooperatives.
| Development of climate information products that enhances adaptive capacities of communities | 0 | The MARN-DOA has prepared the TDR of the personnel to be hired and the technical specifications of the equipment to be purchased. It has also carried out consultations with organized women with basic knowledge of data recording of rainfall and flows of rivers and streams. | 5 products based on improved capacity to measure and produce locally specific hydro meteorological alert products
| Access to adaptation planning instruments for municipalities | 0 | The environmental units of the municipal governments have participated in the workshops and working meetings. These meeting have allowd to present the focus of the project and begin to discuss oon adaptation planning. | 1 local adaptation plan developed and streamlined into municipal planning instruments.
OUTCOME 1 | Hectares of land under restoration, helping reduce vulnerability to climate variability and change | 23,635 ha | Work has begun with the communities to establish restoration plans and locate degraded areas that require restoration under the community plans. | By the end of the project implementation cycle, 3,864 ha of forest landscape will be under restoration.
| Community restoration plans established for sustainable landscape management of 3,864 Ha of forest landscape | 0 | The characterization of the areas to be restored in the upper basin of the municipality of San Francisco Menéndez, which corresponds to the Cara Sucia-San Pedro basin, has begun. | 65 community restoration plans establisher with management agreements documented for sustainable landscape management.
| Restoration of critical ecosystems within forest landscapes to improve ecosystem services for landscape climate resilience | 0 | Monitoring and tracking of restoration activities is done systematically. With the upper part of the basin is being covered in this period. It will start with 50 hectares of riparian forest in the upper basin. | Restoration of 284.52 ha of riparian forests and restoration of 141 ha of mangrove forest.
| Critical forest landscape transition areas under sustainable productive management for enhanced climate resilience | 0 | During this period, 67 hectares of silvopastoral systems and 141 hectares of agroforestry for basic grains has been started by identifying potential areas. This will continue in year two of the project. | 2,708 ha of agroforestry for basic grains established, and 664 ha of silvopastoral systems established and 67 has of agroforestry systems for coffee and cacao established
| Enhanced water flow regulation in the intervention areas as measured through community governance mechanisms | 0 | This will begin once the communities that will have restoration areas are established. It is considered that by the end of year two and the beginning of year three the process will begin. | All community restoration plans will have improved water management and monitoring practices.
OUTCOME 2 | Number of productive groups (cooperatives and associations those favoring women producers) in San Francisco Menendez that benefit from the introduction of diversified agriculture, livelihood strategies and options | 0 | In this period, the coordination and definition of activities with agricultural extension offices of MAG-CENTA have been established. In this period, the coordination and definition of activities with agricultural extension offices of MAG-CENTA have been established. The project has been socialized at the level of directors and managers and heads of extension offices. | By the end of the project, 83 cooperatives (of which 16 favor women) will benefit from enhanced capacities generated by the extension support provided as a result of the project
| Establishment of a local seed bank for access to locally appropriate seeds resilient to drought and flooding | 0 | During this period, it has coordinated with MAG-CENTA, with the germplasm bank to coordinate the training process for community seed banks and also the collection of climate-resilient native seeds in Ahuachapán Sur. | 1 local seed bank will be established in San Francisco Menendez to provide access to locally appropriate seeds resilient to drought and flooding
| Number of alternative crops/practice s introduced as result of project interventions | 0 | In this period, with MAG-CENTA, farmers who carry out successful practices in their crops have been sought. The hiring of the technician for component 2 of the project with their respective consultants is pending. | At least 6 climate resilient products/practices have been identified and packaged into technological packages. From these 1 favors women.
| Number of high value market chains identified for diversified livelihoods strategies | 0 | In year two, market studies will begin on products that are resilient to the climate or other products that generate income and diversify livelihoods. | 3 market studies (are produced systemizing information on diversified livelihood are produced identifying entry points into new markets, increasing livelihood diversification in the intervention areas. From these, 1 market study is developed to target women producers, organizations and associations.
OUTCOME 3 | Enhanced capacity of Observatorio Ambiental measured by the generation of improved climate products relevant at the local level | 0 | During this period, the TDR of the field technical personnel to be hired has been prepared and have been sent to UNDP for hiring. Year two begins without this staff | 5 new climate products developed by the Observatorio Ambiental targeted to Ahuachapán Sur. 1 knowledge product targeted to women.
| Geographical area with access to improved climate information services | 0 | During this period, the communities that already have a network of climate observers receive information from MARN on measurements and forecasts. | 98,016 people (disaggregated by gender) within the four municipalities of South Ahuachapán have access to climate information services
| Capacity to identify and monitor the impact of restoration actions in Ahuachapán Sur as effective EBA actions | 0 | This year, the local actors who will monitor the impact on the family economy and soil loss have been identified | 1 Completed conceptual model of the ESA-01 aquifer, including hydric balances and aquifer recharge capacity 1 Hydrological flow assessment of the Rio Paz Establishment of indicators to monitor the impact of restoration interventions as EBA (impact on aquifer and flow assessment)
| Uptake of generated hydro meteorological information | 0 | Component 3 technical team is required to complete the conceptual model. TORs have been prepared. | At least 40% of the rural population (of which 51% is women) in the municipalities in Ahuachapán Sur make use of the climate information being provided to the region.
OUTCOME 4 | The incorporation of adaptation measures as identified by the local adaptation plan into municipal planning instruments. | 0 | Pending the hiring of the person in charge of governance of component 4 of the project. The process begins in year 1 of the project. | Incorporation of climate adaptation measures into at least 1 municipal planning instrument in 4 municipalities located in Ahuachapán Sur
| Number of municipalities with capacity to assess technical information and promote measures to manage climate change at a territorial level | 0 | Pending the hiring of the person in charge of governance of component 4 of the project. The process begins in year 1 of the project. | 4 municipalities benefiting from a TAC to assess and disseminate information (clearing house) for managing climate change at a territorial level
| Planning tools developed to address climate vulnerabilities of Ahuachapán Sur | 0 | The TDR for the climatic vulnerability study of the municipalities of Ahuachapán Sur are prepared with DOA. | 1 climate vulnerability assessment of the four municipalities in Ahuachapán Sur. Vulnerability assessment considers how climate change impacts women. One local climate adaptation plan of the four municipalities in Ahuachapán Sur
| Enhanced capacity to capture climate finance from diverse sources and to identify adaptation investments | 0 | Pending the hiring of the person in charge of governance of component 4 of the project. | 5 local organizations with enhanced capacity to attract climate finance and identify adaptation projects. One local organization will target women.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Critical ecosystem services in forest landscapes are restored and enhanced to better manage climate change impacts |  | Outcome 5 | By the end of the project implementation cycle, 3,864 ha of forest landscape will be under restoration 100% of productive area being managed through community restoration plans will have agro- silvopastoral practices implemented. |  | In the first year of execution, the Project has prepared the logistics to identify the organizations that will receive donations, so MARN together with FIAES are beginning to identify these organizations on the ground. | Marginally Satisfactory (MS)
| Local livelihood diversification n and income generation models are implemented building local resilience to climate change |  | Outcome 6 | By the end of the project, 83 cooperatives (of which 16 favor women) will benefit from enhanced capacities generated by the extension support provided as a result of the project 1 local seed bank will be established in San Francisco Menendez to provide access to locally appropriate r seeds resilient to drought and flooding |  | Process begins in year 2 with the hiring of personnel in charge of component 2. Progress has been made in year 1 with coordination with MAG-CENTA and project socialization meetings as well as in the bases for the creation of community seed banks. | Satisfactory (S)
| Enhanced capacity to generate relevant climate and hydrological information to address the impact of climate change on natural resources in South Ahuachapán |  | Outcome 3 | 5 new climate products developed by the Observatorio Ambiental targeted to South Ahuachapán. 1 knowledge product targeted to women. 98,016 people (disaggregated by gender) within the four municipalities of South Ahuachapán have access to climate information services |  | The MARN Threat Observatory ("Observatiorio de Amenazas") has been constantly generating climatic information. In the first year of the project, a rain event already occurred at the beginning of June 2022, where a Red Alert was decreed. The San Francisco Menendez area and the COAL representatives received timely information via WhatsApp and Twitter. The project has the challenge of measuring and improving this communication for the second year of the project | Satisfactory (S)
| Local institutions and governance mechanisms with enhanced capacities to implement adaptation measures and manage climate change. |  | Outcome 7 | Incorporation of climate adaptation measures into at least 1 municipal planning instrument in 4 municipalities located in South Ahuachapán |  | The project has done a lot of territorial work, although the team is still being formed, together with FIAES they have managed to bring together local government leaders and representatives of local organizations in workshops | Satisfactory (S)
[6 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Ryna Avila
| Email: | ryna.avila@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The Project is in its first year of execution, its main challenge is ambitious and it needs to generate a territorial lobby to be able to generate conditions and place grants in local organizations that allow the generation of climate-resilient crops and the generation of subsistence measures. Despite administrative delays in hiring the technical team, the Project Manager and the FIAES support technicians have carried out important territorial work, reaching out to local bases and strategic actors such as CENTA of the Ministry of Agriculture, to work on the seed bank. climate resilient. Another important achievement is the identification of a small organized group of native peoples located in Tacuba, a municipality adjacent to San Francisco Menendez. This work carried out will lay the foundations for an execution with greater incidence at the local level for the second year.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Critical ecosystem services in forest landscapes are restored and enhanced to better manage climate change impacts |  | Outcome 5 | By the end of the project implementation cycle, 3,864 ha of forest landscape will be under restoration 100% of productive area being managed through community restoration plans will have agro- silvopastoral practices implemented. |  | The process of identifying community plans for restoration in the upper basin of San Francisco Menendez has begun | Satisfactory
| Local livelihood diversification and income generation models are implemented building local resilience to climate change |  | Outcome 6 | By the end of the project, 83 cooperatives (of which 16 favor women) will benefit from enhanced capacities generated by the extension support provided as a result of the project 1 local seed bank will be established in San Francisco Menendez to provide access to locally appropriate r seeds resilient to drought and flooding |  | Process begins in year 2 with the hiring of personnel in charge of component 2. Progress has been made in year 1 with coordination with MAG-CENTA and project socialization meetings. | Satisfactory
| Enhanced capacity to generate relevant climate and hydrological information to address the impact of climate change on natural resources in South Ahuachapán |  | Outcome 3 | 5 new climate products developed by the Observatorio Ambiental targeted to South Ahuachapán. 1 knowledge product targeted to women. 98,016 people (disaggregated by gender) within the four municipalities of South Ahuachapán have access to climate information services |  | The process begins in year 2 with the hiring of personnel in charge of component 2. In year 1, the entire process of technical specifications for personnel and purchases was carried out hence providing an important foundations for the work that will be developed. This has resulted in the purchasing of hydromet equipment through an existing UNDP LTA. | Satisfactory
| Local institutions and governance mechanisms with enhanced capacities to implement adaptation measures and manage climate change. |  | Outcome 7 | Incorporation of climate adaptation measures into at least 1 municipal planning instrument in 4 municipalities located in South Ahuachapán |  | During this period, progress has been made with the dissemination of the project to the municipalities. The hiring of personnel in charge of component 4 of the project is currently underway. | Marginally Satisfactory
[6 empty] | Overall Rating | Satisfactory
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Martiza Guido
| Email: | mguido@marn.gob.sv
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The progress of the project has been in the participatory inclusion of the different actors and sectors of the COAL in the different components of the Project. This has made it possible to establish shared operational activities, as well as coordination with local government institutions and with external cooperation present in the territory, defining joint actions so as not to duplicate efforts. The administrative processes of UNDP to recruit personnel have limited the progress of components 2 and 4. The transfer of funds to FIAES limited its start but did not limit its activity of convening and coordinating and explanatory meetings of the processes.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
MARN: de Proyecto | Critical ecosystem services in forest landscapes are restored and enhanced to better manage climate change impacts |  | Outcome 5 | By the end of the project implementation cycle, 3,864 ha of forest landscape will be under restoration 100% of productive area being managed through community restoration plans will have agro- silvopastoral practices implemented. |  | The process of identifying community plans has begun | Satisfactory
| Local livelihood diversification n and income generation models are implemented building local resilience to climate change |  | Outcome 6 | By the end of the project, 83 cooperatives (of which 16 favor women) will benefit from enhanced capacities generated by the extension support provided as a result of the project 1 local seed bank will be established in San Francisco Menendez to provide access to locally appropriate r seeds resilient to drought and flooding |  | We know that this activity begins in year 2, as reported by the project. Progress has been made in year 1 with coordination with MAG-CENTA, with the aim of socializing the project. | Satisfactory
| Enhanced capacity to generate relevant climate and hydrological information to address the impact of climate change on natural resources in South Ahuachapán |  | Outcome 3 | 5 new climate products developed by the Observatorio Ambiental targeted to South Ahuachapán. 1 knowledge product targeted to women. 98,016 people (disaggregated by gender) within the four municipalities of South Ahuachapán have access to climate information services |  | This process begins in year 2 and the hiring of personnel in charge of the component as planned. As reported by the project, in year 1 the entire process of technical specifications for personnel and purchases was carried out. | Satisfactory
| Local institutions and governance mechanisms with enhanced capacities to implement adaptation measures and manage climate change. |  | Outcome 7 | Incorporation of climate adaptation measures into at least 1 municipal planning instrument in 4 municipalities located in South Ahuachapán |  | During this period, progress has been made with the dissemination of the project to the municipalities and the hiring of personnel in charge of component 4 of the project is pending. | Marginally Satisfactory
[6 empty] | Overall Rating | Satisfactory
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Eva Maria Colorado Panameño
| Email: | eva.colorado@marn.gob.sv
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | The Project began with a delay of approximately one year, but this has not been an impediment to advance in the delayed activities. Component 1 has began and its first disbursement has been made, its execution percentages have begun to rise and the work in the communities is quite considerable, it is necessary to accelerate the hiring of specialized personnel to contribute to the achievement of the proposed objectives of the project. It is necessary to advance forward, if not we should not obtain the expected results.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies
Note on J27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Maritza Guido Sugiero escribir los avances que realiza el Observatorio de amenazas en la generaciòn de informaciòn que ya realiza. Visibilicemos que ya hay una plataforma para comunicar y sobre eso el proyecto medirà que tanto funciona

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The delays in the implementation of year 1 of the project were due to external administrative processes, such as the case of the hiring of personnel under a new UNDP recruitment and the other limitation was the transfer of funds to FIAES due to an audit process (HACT).
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There were delays mainly as a result of long administrative processes, these included screening and hiring and procurement processes that where prolongued. The measures that were taken were to continue the work on Component 1 with FIAES' own resources and initiate several socialization processes with local actors with a very small project team and strengthen the governance processes with MARN support.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | During the inception workshop it was made clear that the Microregion figure for the area had been recently eliminitated. However the role of Comites de Asosor Local (COAL) remained. The COAL groups the 4 municipalities within Ahuachapan Sur for the purposes of sustainable land management within areas next to and in the conservation area. Hence working through the COAL was considered to be an appropriate option considering its mandate and the presence of all municipalities. There were no other changes in the Project in this period
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | They have been effective, particularly the Project's Stakeholder Analysis. The project has ensured that the measures for the project have been included in the proposals of the community plans of component 1 of the project.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Meetings were held with organized women from the different municipalities of Ahuachapán Sur; to socialize the Project and their interest in participating. Women's organizations are focusing their efforts on guaranteeing food for their families and water quality. Organized women show interest in owning the land under their name and not under the man's name.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc.) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what channels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever possible (e.g. project videos, project stories, studies and technical reports, case studies, training manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | 111194
Implementing Entity | Ministry of Environment and Natural Resources (MARN)
Type of implementing entity | MIE
Country | El Salvador
Region | Latin America and Caribbean
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: number of households (baseline: 3,396 rural households) |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 98016 | 30211 | 67805 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 40% | 59% | 30.86% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 1: Ineffective | Total | 30211 | Drought | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 51% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems (Número de Sistemas de Alerta Temprana) | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 2: Partially not aware |  | 98016 | 51% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | technical guidelines | Local |  | 5 | Technical guidelines | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Multi-sector | land | 4: Effective |  | Multi-sector | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated (bienes naturales protegidos y rehabilitados) | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 23635 | ha rehabilitated | 2: Partially effective | Forests | 27499 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households* | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 6396 | 18% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% |  | Agriculture | 6396 | 18% |  | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
0
| Core Indicator 6.1.2: Increased income, or avoided decrease in income (aumento de los ingresos o reducción de los ingresos) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agriculture |  |  | 6396 | Agricultural-related
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
* of total households int the project area 18% are femelae headed as speciefied in the project's logframe
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | Local | Domestic policy | 4 | Multi-sector | Local | Domestic policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
Note on E21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: baseline cannot be the same as the target at completion
Note on E27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: baseline cannot be the same as target at completion
Note on D67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: baseline cannot be the same as target at completion