## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 01/13/2022 - 01/13/2023
| Project Title: | Enhancing Climate Change Resilience of Coastal Communities of Zanzibar
| Project Summary: | Zanzibar is one of the two countries that form the United Republic of Tanzania (URT). Located in the Indian Ocean, just south of the Equator, the Zanzibar archipelago comprises two major islands - Unguja and Pemba - and more than 50 other small and remote islets. In the last census, of 2012, Zanzibar had 1,303,569 inhabitants. The population had increased by 33% since the previous census of 2002, with an average annual growth rate of 2.8. Population growth rates are projected to be high. The economy of the islands is very dependent on climate with reliance on agriculture, natural resources and ecosystems exploitation. Agriculture sector has direct contribution to the livelihoods of many people, providing more than 75% of the foreign exchange earnings. However, the coastal climate regime of Zanzibar is changing, and increasing wave activity and wave heights are a factor in recent increase in salt water intrusion on the islands. In recent decades, Zanzibar has seen rising temperature, increased rainfall variability, higher wind speed and extreme weather events. Around 150 sites on the islands have been identified as being affected by salt water intrusion and are now not suitable for agriculture. This has contributed to food insecurity whereby 26% of Zanzibaris are food insecure and 3.6% are facing chronic food insecurity. Overall, the frequency and intensity of extreme events (e.g. drought and floods) are expected to increase. Negative impacts will include reduced water availability, vegetation and land degradation, and ecosystem and biodiversity destruction, as well as negative impacts on poverty eradication, economic development, food production and health. The project will progress activities geared towards enabling climate resilient livelihoods in climate impacted areas of Zanzibar. Thus, the project’s main objective is to build the capacity of smallholder farmers in tackling climate change impacts through practical and innovative solutions; that have concrete and tangible outputs. Specifically, the project envisages achieving the following: (i) Constructing water harvesting infrastructures for supplying water throughout the year in selected sites (ii) Promoting soil and water conservation techniques for improved water protection and crop productivity (iii) Developing integrated climate resilient livelihoods diversification systems in selected sites (iv) Institutional capacity building of local government authorities and communities in planning , implementation of climate change adaption actions and dissemination of project results and lessons learnt
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | National Environment Management Council | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Tanzania | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Dar es Salaam | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2020-01-06
IE-AFB Agreement Signature Date: |  | 2020-09-09 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2022-01-13 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | N/A
| Original Completion Date: | 2025-01-12
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception Report 12th January 2022 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Saida Issa Omar | Dominican Republic
| Email: | siosam2002@gmail.com | Ecuador
| Date: | 2023-02-04 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Dr. Switbert Mukama | Equatoral Guinea
| Email: | switbert.mukama@vpo.go.tz | Eritrea
| Date: | 2023-02-06 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Fredrick Mulinda | Fiji
| Email: | nieaf@nemc.or.tz / kasigazi.koku@gmail.com | Finland
| Date: | 2023-02-04 | France
| Executing Agency |  | Gambia
| Name: | Dr.Omar D. Shajak | Georgia
| Email: | odshajak61@hotmail.com | Germany
| Date: | 2023-02-06 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from 01/13/2022 to 01/31/2023 |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31/01/2023 | 243023 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 360102 |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1 Water reservors constructed | 82334
| Output 1.2 Water efficient irrigation schemes established | 7000
| Output 2.1 Improved land management for improved crop yield | 46089
| Output 2.2 Improved water resources management | 2000
| Output 3.1 Tree nurseries promoted | 6000
| Output 3.2 Poultry farming improved | 4500
| Output 3.3 Aquaculture improved | 6000
| Output 3.4 Beekeeping production improved | 4500
| Output 3.5 Production of high value horticultural crops increased | 5000
| Output 4.1 Capacity of local government authorities strengthened | 7000
| Output 4.2 Capacity of farmers associations and communities strengthened | 0
| EXECUTION FEE | 31900
| IMPLEMENTING ENTITY FEEs | 40700
| TOTAL | 243023 | [5 empty] | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1 Water reservors constructed | 8000 | 2024-06-30 |  | Output 1.1 Water reservors constructed | 8000
| Output 1.2 Water efficient irrigation schemes established | 96800 | 2024-06-30 |  | Output 1.2 Water efficient irrigation schemes established | 96800
| Output 2.1 Improved land management for improved crop yield | 228977 | 2024-11-30 |  | Output 2.1 Improved land management for improved crop yield | 228977
| Output 2.2 Improved water resources management | 7500 | 2024-03-30 |  | Output 2.2 Improved water resources management | 7500
| Output 3.1 Tree nurseries promoted | 11000 | 2024-12-31 |  | Output 3.1 Tree nurseries promoted | 11000
| Output 3.2 Poultry farming improved | 31500 | 2024-12-10 |  | Output 3.2 Poultry farming improved | 31500
| Output 3.3 Aquaculture improved | 28800 | 2024-12-20 |  | Output 3.3 Aquaculture improved | 28800
| Output 3.4 Beekeeping production improved | 20000 | 2024-06-30 |  | Output 3.4 Beekeeping production improved | 20000
| Output 3.5 Production of high value horticultural crops increased | 37000 | 2024-10-31 |  | Output 3.5 Production of high value horticultural crops increased | 37000
| Output 4.1 Capacity of local government authorities strengthened | 33000 | 2024-12-15 |  | Output 4.1 Capacity of local government authorities strengthened | 33000
| Output 4.2 Capacity of farmers associations and communities strengthened | 16000 | 2024-12-02 |  | Output 4.2 Capacity of farmers associations and communities strengthened | 16000
| EXECUTION FEES | 17000 | 2024-12-20 |  | EXECUTION FEES | 17000
| IMPLEMENTING ENITY FEE | 20000 | 2024-12-23 |  | IMPLEMENTING ENITY FEE | 20000
| TOTAL | 555577 |  |  | TOTAL | 555577 |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[7 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[7 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[7 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[7 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Late disbursement of funds | Low | The executing entity prepared all requests and progress reports timely and has improved its financial and banking procedures to easy fund disurbement and speed the implementation of project activities. Also, the executing entity used special template for quartely and annual report
Financial control | Low | The executing entity observed and followed the existing government structure, accounting and procurement standards and principles to meet all accounting requirements related to reporting, control and transparency and auditing.
Project performance | Low | All members of project team have adequate academic knowledge and skills to manage the project. The project team is working smoothly to deliver the expected project outputs through the guidance of the developed work plan approved by both Project Steering Committee and NEMC.
Participation of stakeholders | Low | All key stakeholders are well imvolved in all stages of project implementation
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
There was no direct access to the reservoir site for transporting construction materials. Through active involvement and participation of communities and other project stakeholders, proper site was provided to easily access the reservoir site.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Risk: Low Potential impact: High -Workplace Accidents -Child labor and women empowerment | The project activities strongly comply with all relevant national laws including international standard. They do not conflict with any domestic laws and policies, but they strongly support implementations of those laws and policies as indicated at Part II E of the approved project document. Respective Site Engineer of the construction activities of the tasked to control all risk and accident of Dikes and Reservoir respectively. Furthermore, the Coordinator and Monitoring Office among others were tasked to carryout regular environmental monitoring in collaboration with the Zanzibar Environmental Management Authority (ZEMA) to ensure environmental and social compliance of the project and construction activities in accordance with environmental and social management plan and environmental monitoring plan of the project. Different types of trainings on Health, Safety and Environment, relevant Policies and Acts were conducted regularly for the people engaged in project activities including construction activities. | Number of national laws with which the project must comply | The project is compliant with all relevant national laws and regulation including the bylaws set by North B district, Wete district and project sites. | The project has continued to adhere to existing laws | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
2 - Access and equity |  |  | Risk: Low Potential impact: Low -Misunderstanding can arises during member selection of committee or employment | The project activities being implemented do not reduce or prevent communities at the sites in all villages from accessing basic health services, clean water and sanitation, energy, education, housing, safe and decent working conditions and land right. Communities and beneficiaries will be highly sensitized to enhance priorities of the most vulnerable communities while ensuring benefits to reach further communities for scaling up and replications. In addition, measures have been put in place to able this project to closely monitor all targeted beneficiaries to assure equal access of men, women, youth and the most vulnerable. The management of project involved local community from the beginning of the site selection of the site for construction of the reservoir. 65 participated in the site section visit, which make the decision for the area of the construction of the reservoir, out of that, 30 participants were from local community, and District. There was a monthly site meeting during the whole period of construction, which constituted of 12 members, out of the 5 members were from the community. The site meeting helped to enforce quality standards such as developing a reservoir quality control plan, assess workmanship during construction, increases communication in the construction team and communities of the project areas, assess the specification used and requires a competent construction manager. | Number of people with reduced access to basic social services as a result of the project | No reported case of reduced access to basic social services as a result of the project | The project interventions promote equitable access to basic social services | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
3 – Marginalized and vulnerable Groups |  |  | Risk: Moderate Potential impact: Moderate/High -Misunderstanding and discrimination may arise | Marginalized and poor vulnerable village groups especially women have been widely involved during implemenation of this project. This project ensures that all components enhance the adaptive capacity of marginalized and vulnerable groups including transforming their social life to better levels especially for women and girls. | Number of marginilized and vulnerable groups negatively impacted by the project | No reported case of marginalized and vulnerable groups being negatively affected by the project | The project continues to observe that no marginalized and vulberable group is negatively affected by the project | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
4 – Human rights |  |  | Risk: Low Potential impact: Moderate/High | The project will respect and adhere to all relevant conventions on human rights, national and local laws in relation to human rights. | Number of cases from the project that demonstrate violation of human rights | No reported case from the project that demonstrate violation of human rights | The project has contunied to ensure that its interventions promotes basic human rights for equitable access to service and clean and safe drinking water, access to food, information, and quality and health environment. | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
5 – Gender equality and women’s empowerment |  |  | Risk: Moderate Potential impact: Moderate/High -Failure to involve women in project implementations and decision making as well | From the beginning, the project has ensured inclusion of gender particularly on rights, responsibilities, opportunities, and access to resources allocated to improve their resilience to the current and future climate change effects. Representatives of all genders have participated in all implemented project activities so far. | Number of women in the project villages benefiting from the project | About 30% of women in the project villages participate and benefit from project activities | Since inception of the project, inclusion of gender equality and women empowerment issues has been signdicantly considered | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
6 – Core labour rights |  |  | Risk: Low Potential impact: Moderate/High -Recurrence of Incidents & Accidents -Misunderstanding between employee and employer -Workplace hazards -Child labor | Core labour rights are respected and considered in the project implementation. The Employment Act No. 11 of 2005 of Zanzibar provides the restriction on employment of children of less than 18 years of age, stipulated different types of contracts of service that can be entered with employees. During the whole period of the construction activities of the project, the project observed all safety measures required to avoid accidents, including wearing of personal protective equipment (PPE) e.g. helmets, safety glasses, earplugs, dust masks, tough boats (safety shoes), correct work clothing, right gloves, and therefore, they were mandatory for all workers to use PPE in all working place. Precaution signs (pictograms) and first aids kits were introduced and placed in all project areas. Furthermore, before started working, the workers were trained on how to use PPE and to take care themselves. This type of training was conducted regularly to keep the knowledge of the workers up to date. Through these initiatives there were no serious accident observed during the whole period of construction. | The number of cases from the project that demonstate violation of core labour rights | No violation of core labour rights | The project has continued to ensure that there is no violation of core labour rights | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
7 – Indigenous peoples |  |  | Risk: Moderate Potential impact: Moderate/High -Destruction of the project due to lack of awareness and involvement, strike and insecurity because they are skipped | All project interventions ensure equitable access to project benefits and resources by local peoples and to most extent communities at grass-root level are included in community consultation and during participatory planning of activities. The project ensured that all stakeholders consultation and sensitization meetings are inclusive. | Number of cases from the project that demonstrate exclusion of the local people in project execution | Local people are fully engaged in the project | The project has continued to ensure that local people benefit from project interventions | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
8 – Involuntary resettlement |  |  | Risk: Low Potential impact: High | The project implementation does not include voluntary or any involuntary resettlement. | Number of cases from the project that demonsrtate voluntary or involuntary resettlement | Involunatry resettlement does not exist in the project | No involunatry settlement | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
9 – Protection of natural habitats |  |  | Risk: Low Potential impact: Moderate/High | By implementing conservation measures linked to economic benefits to the people to tackle climate change in North 'B' District, the project contributes to improved management of natural ecosystems, particularly in the context of future climate change. | Number of project activities that demonstrate protection of natural habitats | The natural habitats are highly degraded due to unsustainable human activities in the past. The project has started interventions towards restoration of natural habitats | The project continues to promote interventions that contribute towards protection and restoration of natural habitats | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
10 – Conservation of biological diversity |  |  | Risk: Low Potential impact: High -Introduction of trees can alter behavior of microorganisms, reptiles, and birds life adaptation hence lead to loss of biodiversity | The project implementation has been keen not to cause any risk to biological diversity. Tree planting has involved local species only. no exotic trees have been planted. None of the activities involved clearing of natural vegetation. Among the criteria that was used for selection of proper site for construction of the reservoir is the site that has less biodiversity. Therefore, the site that was selected contains less biodiversity. | Number of project activities that contribute to conservation of biological activities | No project activity that may cause any significant risk to biological diversity. Components 2 and 3 of the project enhances biological diversity. | The project continues to promote interventions that contribute towards conservation of biological diversity | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
11 – Climate change |  |  |  | Through the Four (4) components, this project improve climate resilience of agro-pastoral rural communities in North 'B' District, facilitate transfer of climate adaptation technologies to local communities in rural villages, and promote innovations development for climate solutions in rural villages and communities | Number of project activities that contribute to climate change adaptation | No concrete measures to address climate change impacts in the project area existed before. No solution for salt water inundation due to sea level rise and water shortage due to long dry spells. | The project has continued to progress activities that contribute to enhancement of climate change resilience by coastal communities in the project villages | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
12 – Pollution prevention and resource efficiency |  |  | Risk: Low Potential impact: High -Waste generation causing disease eruption -Oil Spills leads to hydrocarbons pollution | The proposed project is visualized to cause no any harm or pollution. The project employed proper waste management techniques including techniques related to re-use and recycling of waste. 2 places were located in the construction sites for sorting of waste to enhance re-use and recycling; 1 site used to put the organic waste, second one for re use and recyclable waste. Most of the construction wastes were taken by the local communities through proper directives for re-use. Proper maintenance and machineries of the contract vehicles was done regularly in an authorized place outside of the project site to avoid any risk project on oil spillage. | Number of reported cases of pollution emanating from project activities | No pollution cases exist | The project continues to observe that no siginicant environmental pollution emante from project activities | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
13 – Public health |  |  | Risk: Low Potential impact: High -Emerge of respiratory diseases -Sexitiual Transmitted Disease outbreaks -Water born diseases | The proposed project enhances the quality of public health. Indeed, through component 1, 2 and 3 contribution of the project to the general public health is clear. During the whole period of the construction activities of the project, the project observed all health and safety measures required to avoid accidents, including wearing of personal protective equipment (PPE) e.g. helmets, safety glasses, earplugs, dust masks, tough boats (safety shoes), correct work clothing, right gloves, and therefore, they were mandatory for all workers to use PPE in all working place. Precaution signs (pictograms) and first aids kits were introduced and placed in all project areas. Furthermore, before started working, the workers were trained on how to use PPE and to take care themselves and HIV/AID awareness programmes. This types of training were conducted regularly to keep the knowledge of the workers up to date. Through these initiatives there were no serious accident observed during the whole period of construction. | Number of project activities that contibute to public health | In project villages, sanitation and hygiene is poor due to limited access to water | The project has continued to progress activities that contributes to public health. In particular, project activities in components 1 and 2 contribute to public health. | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
14 – Physical and cultural heritage |  |  | Risk: Low Potential impact: Moderate/High -Deterioration of archeological site Without thorough and careful site selection especially during construction of water infrastructures | There are no archaeological and cultural heritage sites which exists in the project sites. The Environmental and Social Impact Assessment (ESIA) Report does not indicate the any impact of the archaeological and cultural sites as there is no existence. | Number of cases from the project related to destruction of physical and cultural heritage | No physical and cultural heritage sites in the project villages | The project contunues to observe that no physical and cultural heritage sites exist in the project villages | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
15 – Lands and soil conservation |  |  | Risk: Low Potential impact: Moderate/High -Alteration and modification of soil profile and structure -Soil and land pollution/degradation | This project is design to enhance and promote conservation of soil and land resources. The project activities under components 2 and 3 contribute into increased soil stability, rehabilitate the degraded contour bands/windrows and reduced runoff of nutrients from top soil, promote improved soil fertility and productivity, improve the hard pan soils and waste land to productive lands. | Number of project activities contributing to lands and soil conservation | The status of land and soil health in some project villages is poor. Soil erosion has destroyed roads and some farming land. | The project has continued to progress activities that contribute to land and soil protection. he project activities under components 2 and 3 contribute into increased soil stability | Residual impact is not yet experienced as the safeguard measures are still being implemenetd | No remedial action for residual impacts for now as there is no residual impact identified yet
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | No unanticipated risk in the reporting period
Have unanticipated ESP risks been identified during the reporting period? |  | No unanticipated risk in the reporting period
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | No unanticipated risk in the reporting period
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The IE had regular visits to the project sites and had instructed the EE to submit the quarterly reports that integrate ESP safeguard measures
Have the implementation arrangements been effective during the reporting period? |  | Yes. The IE has conducted several monitoring visits to ensure that the project is on track
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The EE has a monitoring and evaluation plan that integrates ESP safeguard measures
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes. The EE has been able to carry out most of the activities planned for Year 1. The EE has been submitting the quarterly to the IE
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievance recived during the reporting period
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Improved access to water for various uses such as irrigation farming, livestock and domestic use | Increased water supply leading to improved production in various sub sectors | Number of men , women and most vulnerable groups with access to freshwater. | 400 women and 300 men | 1,650 women and 1,455 men have access to freshwater. Al least 50 % of most vulnerable groups such as children, orphans, widows disabled individuals and the elderly have access to freshwater. | 1,700 women and 1,500 men have access to freshwater (good succes). 56% of most vulnerable group (children, orphans, widows disables inviduals and elders) have access to freshwater (good performance)
Improved crop yield and water resources protection | Increased agricultural production | Number of bags/kgs produced from a farm under soil and water conservation interventions | The crop yield was 200kg of rice per farmer. 571 female farmers and 400 male farmers used their affected arable land before construction of dikes | Crop yield increase by at least 10% in farms under soil and water conservation. 4851 female farmers and 4159 male farmers reclaim their arable land following construction of dikes for preventing saltwater inundation | The current crop yield was recorded as 300 kg of rice per farmer. This yield is 50% recorded (Good). 680 female farmers and 541 reclaim their arable land following construction of dikes for preventing saltwater inundation (Good)
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The monitoring team of the IE comprised of at least 2 female members
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes. The IE has been keen in ensuring project monitoring data are disaggregated by sex
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The project management unit of the EE comprises of 3 females
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes. The project interventions take into account men, women and youth . Furthemore, the project monitoring data are disaggregated by sex
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | No grievance reported yet
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Increased water supply leading to improved production in various sub sectors |  | Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  | The adaptive capacity of communities have been enhanced through construction of rain water harvesting reservoir and selection of sites for establishment of drip irrigation systems | S
| Promoting soil and water conservation techniques for improved water protection and crop productivity |  | Outcome 4 | Increased adaptive capacity within relevant development and natural resource sectors |  | The adaptive capacity of communities have been enhanced through dike construction for prevention salt water intrusion in the agricultural land | MS
|  |  | Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  | The ecosystem resilience have been incresed by planting of trees including Mangrove in a degraded ecosytemsn for restoration | MS
| Developing integrated climate resilient livelihoods diversification systems in selected sites |  | Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  | Training of community members on various climate resilient livelihoods are conducted. This is evisaged to strengthen capacity of communities in project areas in adoption of intergrated climate resilient livelihoods activities and improve their income | S
| Institutional capacity building of local government authorities and communities in planning, implementation of climate change adaption actions and dissemination of project results and lessons learn |  | Outcome 2 | Strengthened Institutional capacity to reduce risks associated with climate induced |  | Training materials for district oficers were developed. Furthermore, a training for trainers for commmunity memberes was connducted. This is envisaged to strenghten the institutional capacity to reduce climate risks at village level | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Fredrick Mulinda
| Email: | nieaf@nemc.or.tz/kasigazi.koku@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Based on the quarterly reports submmited by the EE and site visits conducted by NEMC (NIE) monitoring team, we are of the view that most of project activities are on track. Therefore, the overall project perfromance is sastifactory
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Increased water supply leading to improved production in various sub sectors |  | Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  | The adaptive capacity of communities have been enhanced through construction of rain water harvesting reservoir and selection of sites for establishment of drip irrigation systems | S
| Promoting soil and water conservation techniques for improved water protection and crop productivity |  | Outcome 4 | Increased adaptive capacity within relevant development and natural resource sectors |  | The adaptive capacity of communities have been enhanced through dike construction for prevention salt water intrusion in the agricultural land | S
|  |  | Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  | The ecosystem resilience have been increased by planting of trees including Mangrove in a degraded ecosytems for restoration | S
| Developing integrated climate resilient livelihoods diversification systems in selected sites |  | Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  | Training of community members on various climate resilient livelihoods are conducted. This is evisaged to strengthen capacity of communities in project areas in adoption of intergrated climate resilient livelihoods activities and improve their income | S
| Institutional capacity building of local government authorities and communities in planning, implementation of climate change adaption actions and dissemination of project results and lessons learn |  | Outcome 2 | Strengthened Institutional capacity to reduce risks associated with climate induced |  | Training materials for district officers were developed. Furthermore, a training for trainers for commmunity members was conducted. This is envisaged to strenghten the institutional capacity to reduce climate risks at the village level | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Saida Issa Omar
| Email: | siosam2002@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
During Year 1 of project implementation, the project has been on track. With exception of few cases whereby the project activities were delayed, the project implementation has been successful.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator |  | Baseline | Progress since inception | Target for Project End
Output 1.1 | Number of water reservoirs |  | 0 | 1 water reservoir constructed | 2 water reservoirs
Output 1.2 | Number of drip irrigation systems installed |  | 0 | 2 drip irrigation system installed | 2 drip irrigation system
Output 2.1 | Length of dikes constructed |  | 0 | 400m dike constructed | 1350m dikes constructed
Output 2.1 | Number of Drainage canal constructed |  | 0 | 1 drainage canal constructed | 1 drainage canal
Output 2.1 | Area covered by formation of plot bund |  | 0 | not yet done | 2 acres
Output 2.1 | Number of Community Based Trainers trained |  | 0 | 60 Community Based Trainers trained | At least 60 Community Based Trainers trained
Output 2.1 | Number of hectar planted Mangrove |  | 0 | 5 hectar planted by Mangrove | 15 hectar
Output 2.1 | Number of hectar planted Coastal Vegetation |  | 0 | 1 hectar planted by coastal vegetation | 5 hectar
Output 2.1 |  | Area of Rice farm recovered from intrusion of salt water | 0 | 60 acres of rice farm recovered | 183 acres of rice
Output 3.1 |  | Number of trees nurseries groups supported | 0 | not yet done | 9 tree nursery group supported (6 in Unguja; 3 in Pemba)
Output 3.2 | Number of poultry production group supported |  | 0 | not yet done | 8 poultry production group (6 poultry groups in Unguja and 2 poultry groups in Pemba)
Output 3.3 | Number of fish pond constructed |  | 0 | not yet done | 2 fish ponds constructed
Output 3.3 |  | Number of fish farmers supported | 0 | not yet done | 180 fish farmers supported
Output 3.4 | Number of modern beehives provided |  | 0 | not yet done | 200 beehive boxes provided (100 in each district)
Output 3.4 |  | Number of centrifuge machine Provided | 0 | not yet done | 2 centrifuge machine provided
Output 3.5 | Number of greenhouses with drip constructed |  | 0 | not yet done | 4 greenhouse with drip irrigation constructed
Output 4.1 |  | Number of Taining Modules Developed | 0 | not yet done | 2 training module developed
Output 4.1 |  | Number of staff trained | 0 | not yet done | 30 staff trained
Output 4.2 |  | Number of community based Trainers supported | 0 | not yet done | 90 community Based Trainers supported
Output 4.2 | Number of study tours conducted |  | 0 | not yet done | 2 exchange visit conducted
Output 4.2 |  | Number of project documentaries prepared | 0 | 1 project documentary created | at least 3 documentaries created

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1. At the beginning of the project, the Communities at Bumbwini requested the fund for the construction of Dikes in their community to be transferred directly to them. This was solved through awareness of the community members on the modality and procedures of funds and roles for each actor in the project. 2. Changed of Focal Persons and Leaders of the community. Some of the Focal persons of the partner institutions and local leaders were often changed and replaced by new ones. The old focal person and local leaders were trained and familiarized with the entire project objectives and document. The new ones who came into the project need more time to familiarise themselves with the project. This was solved through the section of the alternative member.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Fund disbursement delays from IE to EE due to internal processes of the bank. This was addressed by changing the system of receiving the fund from the exchequer to a direct EE Bank Account.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No changes was made
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes, The Environmental and Social Impact Assessment for the construction of a water reservoir at Bumbwini Mafufuni was conducted and an EIA certificate was issued. The environmental and Social Management Plan and Environmental and Social Monitoring Plan were executed and compliance was ensured.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | All activities and progress reports include the beneficiaries in terms of gender. For example, in the construction of the dike, beekeeping, and coastal vegetation training; men and women participated in nearly equal amounts (51.33% for men and 48.67% for women), and progress reports of these indicated data. The lessons learned for the inclusion of gender include the creation of ownership for all genders and therefore, reduced unnecessary conflict. Women play a significant role in the dikes and water reservoirs that were constructed for the project particularly in supplying construction materials, site clearance, excavation, and refilling of the core trench. Furthermore, women play a key role in mobilizing men to participate in the construction of dikes, reservoirs, and trenches. Through this, we discovered that the project's success actually depended on gender inclusion, given the kind of activities were carried out and the specific roles played by each.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | TZA/NIE/Water/2019/2
Implementing Entity | National Environment Management Council
Type of implementing entity | NIE
Country | Tanzania
Region | Africa
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 5300 | 300 | 5000 | Total | 18938 | 1525 | 17413 | Total |  |  |  | Total
|  | % of female beneficiaries | 10% | 10% | 10% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 5% | 5% | 5% | % of Youth beneficiaries | 8% | 8% | 8% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 10000 | Coastal flooding | 1: Ineffective | Total | 18938 | Coastal flooding | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 20% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Multi-sector | Local | 1: No plans conducted or updated | 1 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Local | 1 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 1 |  |  | Number of municipalities | 1 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Salinization | No. of adopted Early Warning Systems | Category targeted | Hazard | Salinization | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Local | 1 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 1 |  |  | Number of municipalities | 1 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 5 | Multi-sector | 2: Low capacity | Total | 30 | Multi-sector | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 10% |  |  | % of female targeted | 20% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 10 | 5% | Public |  | 30 | 20% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Multi-sector | 1: No capacity | Public | Local | Multi-sector | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 3 | Local | Multi-sector | 2: Low capacity | 6 | Local | Multi-sector | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 10% |  | Multi-sector |  | 90% |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 2500 | 20% | 3: Partially aware |  | 4500 | 50% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 1 | 20% to 39% | 3: Partially aware |  | 2 | 40% to 60% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 1 | Training manuals | Local |  | 4 | Training manuals | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Agriculture | Local | 3: Moderately responsive (Some defined elements) |  | Agriculture | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 1 | Community |  | Agriculture | 3 | Community |  | Agriculture
|  | 1 | Community |  | Water management | 3 | Community |  | Water management
|  | 0 | Community |  | Food security | 2 | Community |  | Food security
|  | Baseline information |  |  |  | Target Performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 10 | ha rehabilitated | 1: Ineffective | Mangroves | 15 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 10 | ha rehabilitated | 1: Ineffective | Forests | 5 | ha protected | 4: Effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 50 | 5% | 2: Limited improvement |  | 200 | 10% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 50 | 10% | From 1% to 5% | Agribusiness | 200 | 10% | From 10% to 20% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 50 | 10% | From 1% to 5% | Agriculture | 200 | 10% | From 10% to 20% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 50 | 10% | From 1% to 5% | Livestock production | 200 | 10% | From 10% to 20% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households |  | Alternate Source
|  | 50 | 10% | From 1% to 5% | Agribusiness | 200 | 10% | From 10% to 20% | Agribusiness
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 3 | Adaptation strategies | Food security | Supporting livelihoods | 7 | Adaptation strategies | Multi-sector | Soil water conservation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 200 | Agriculture |  | 1 | 200 | Agriculture |  | 2
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 200 | Agriculture |  | 0.5 | 200 | Agriculture |  | 1.5
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 200 | other |  | 0.5 | 200 | other |  | 2
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 200 | Agriculture |  | 0.5 | 200 | Agriculture |  | 1.5
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 4 | Multi-sector | National | Environmental policy | 6 | Multi-sector | National | Environmental Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 2 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective | 5 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Food Security | Community | Innovation rolled out |  | Food Security | Community | Innovation rolled out
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 0 | Food Security | No innovative practices | 1: Ineffective | 3 | Food Security | Completed innovation practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  | 1: Ineffective | 4 | Innovative practice |  | 4: Effective