## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 22 March 2021-21 March 2022
| Project Title: | Talent Retention for Rural Transformation - Adapt (TART-Adapt)
| Project Summary: | The project objective is to “strengthen the agro-ecological and social resilience to climate change in the climate vulnerable areas of Moldova, by enhancing water availability, water use efficiency, and promoting adaptive agriculture production systems and technologies for improved livelihoods and food security of rural households”. The project is structured around 3 components: i. Capacity development to integrate CC adaptation into agricultural production systems ii. Climate-resilient Agricultural Investments. iii. Development of a National Framework for Conservation Agriculture supported.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | International Fund for Agricultural Development (IFAD) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Republic of Moldova | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The project has a national coverage and is implemented in the areas controlled by the Government of Moldova (GoM) except the entities registered in Chisinau and Balti. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2019-11-10
IE-AFB Agreement Signature Date: |  | 2020-05-06 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 03/22/2021 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
| Original Completion Date: | 03/30/2025
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception report submitted to the AF on 20 May 2021 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | http://www.ucipifad.md/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Samir Bejaoui, Country Director (Kyrgyz Republic and Republic of Moldova) Near East, North Africa, Europe and Central Asia Division (NEN), IFAD | Dominican Republic
| Email: | s.bejaoui@ifad.org | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Mr. Viorel Gherciu, Minister, Ministry of Agriculture and Food Industry | Equatoral Guinea
| Email: | viorel.gherciu@maia.gov.md | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Mr. Samir Bejaoui, Country Director (Kyrgyz Republic and Republic of Moldova) Near East, North Africa, Europe and Central Asia Division (NEN), IFAD | Fiji
| Email: | s.bejaoui@ifad.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Mr. Sergiu Gherciu, State Secretary, Ministry of Agriculture and Food Industry | Georgia
| Email: | sergiu.gherciu@maia.gov.md | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Director, Consolidated Programmes Implementation Unit (CPIU IFAD) | Grenada
| Email: | vacant position | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [insert date] |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [March 2022] | 17594 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | USD 787,085 were at the project's disposal for this reporting period (excluding IE fees) |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | n/a |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA* |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Project Execution Cost: (Adaptation Fund Specialist & Irrigation engineer for infrastructure/ Employment/annual Operating costs annual) | 6266.57
| Output 1.1.1 A Training of Trainers (ToT) programme designed and implemented | 0
| Output 1.1.2 Demo plots identified and set up | 0
| Output 1.1.3 Beneficiaries trained in groups of around 20 on climate resilient techniques and approaches to adapt to weather extremes and water efficient irrigation. | 0
| Output 1.2.1 Professionals trained in gender awareness, CA, and CA technical and service provision to smallholder farmers. | 0
| Output 1.3.1. Knowledge management and climate change awareness raising system established and implemente (Climate vulnerability Baseline Survey for TRTP) | 1500
| Output 2.1.1: Annual mobilisation campaign delivered and beneficiaries supported in making grant applications | 0
| Output 2.1.2 Beneficiary applications screened by CPIU for compliance to criteria. | 0
| Output 2.2.1: Improved smallholder access to water from rivers and rainwater reservoirs (Service provider for feasibility study of investment proposals) | 0
| Output 2.3.1 Households to received climate smart irrigation and support for banking fees for pro-poor escrow account. | 0
| Output 2.3.2 Climate adaptive techniques implemented | 0
| Output 3.1.1. National survey and CA White Paper produced | 0
| Output 3.1.2 National convention on CA | 0
| Output 3.1.3 Conservation Agriculture mainstreamed into the national higher-level educational system. | 0
| Output 3.2.1 CA research grants, demo sites, equipment, soil laboratory supported. | 0
| IE Fees | 9827
| TOTAL | 17593.57 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Project Execution Cost: (Adaptation Fund Specialist & Irrigation engineer for infrastructure/ Employment/annual Operating costs annual) | 21588 | 2027
| Output 1.1.1 A Training of Trainers (ToT) programme designed and implemented | 0 | 2026
| Output 1.1.2 Demo plots identified and set up | 0 | 2025
| Output 1.1.3: FFS set up and 5000 beneficiaries trained in groups of around 20 on climate resilient techniques and approaches to adapt weather extremes of which at least 400 on water efficient irrigation | 30000 | 2027
| Output 1.2.1 Professionals trained in gender awareness, CA, and CA technical and service provision to smallholder farmers. | 0 | 2025
| Output 1.3.1. Knowledge management and climate change awareness raising system established and implemente (Climate vulnerability Baseline Survey for TRTP) | 13080 | Q2 2022
| Output 2.1.1: Annual mobilisation campaign delivered and beneficiaries supported in making grant applications | 31000.5 | 2027
| Output 2.1.2 Beneficiary applications screened by CPIU for compliance to criteria. | 0 | 2024
| Output 2.2.1: Improved smallholder access to water from rivers and rainwater reservoirs (Service provider for feasibility study of investment proposals) | 12000 | 2026
| Output 2.1.1: Annual mobilisation campaign delivered and beneficiaries supported in making grant applications | 31000.5 | 2027
| Output 1.1.3: FFS set up and 5000 beneficiaries trained in groups of around 20 on climate resilient techniques and approaches to adapt weather extremes of which at least 400 on water efficient irrigation | 30000 | 2027
| Output 2.3.1 Households to received climate smart irrigation and support for banking fees for pro-poor escrow account. | 0 | 2026
| Output 2.3.2 Climate adaptive techniques implemented | 0 | 2026
| Output 3.1.1. National overview of CA adoption to inform policy and the development of a national CA curriculum (recruiting team of experts and enumerators conducting nationwide survey, producing report of findings and White Paper on recommendations for CA in Moldova) | 51000 | Q1 2023
| Output 3.1.2 National convention on CA | 0 | 2025
| Output 3.1.3 Conservation Agriculture mainstreamed into the national higher-level educational system. | 0 | 2026 |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
| Output 3.2.1 CA research grants, demo sites, equipment, soil laboratory supported. | 0 | 2026
| IE Fees | 94136 | 2027
| TOTAL | 219669 | [5 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Low interest and capacity of smallholder to adopt new climate smart approaches and technologies. | L | The steps aimed to mitigete this risk will be taken when the awareness and mobilisation campaign targeting the potential beneficiaries will start (planned in Q4 2022). Since this activity hasn't been started yet, no such steps have been undertaken.
Water is a scarce resource the use of which is heavily regulated. There is a risk that the institutional process of requesting and issuing permits is long and laborious leading to delays in project implementation. | L | IFAD has developed over the course of several projects an application approval framework in partnership with the Ministry of Agriculture and Food Industry (MAFI). Through the Selection Committee set up by MAFI decree, the application review and approval process is mainstreamed and integrated into the project structure. It hereby fast-tracks the approval process mitigating any delays due to slow and is proven to review applications and issue permits within 30 days.
Climatic shock: the main effect of climate change on weather patterns is the increased occurrence of extreme weather events: droughts and flooding in particular. These climatic shocks can have a direct impact on crop production | M | The programme has prepared a set of measures to mitigate this risk that have to be implemented durig the active phase of the project. However, since this phase hasn't started yet, no such steps have been undertaked so far.
Insufficient capacities to appropriately manage the day-today implementation of the project | L | It was decided that IFAD will participate as an observer in all stages of the recruitment process and the staff of the CPIU will be linked to the project by renewable annual contracts based on a performance evaluation.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
None
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
None

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats |  |  | Low riks. The project is highly unlikely to pose a risk to critical natural habitats, however as the project activity areas has not yet been defined it is not possible to make a definitive assessment. | For the reporting period: - Inclusion of AF safeguards in the Project Implementation Manual (PIM) and the Annual Work Plan and Budget (AWPB) - All protected areas identified and mapped in all the country - Setting up of screening panel and screening requirements. Ongoing: - Inclusion in public tenders that the GPS locations of project activities need to be provided and a mapping of project locations vis-à-vis protected areas. - Screening of proposals and grants for funding to ensure that project activities will not operate in or near protected areas. - Should proposals be received within or near identified protected areas they will need to include: i. an analysis on the nature and the extent of the impact including direct, indirect, cumulative, or secondary impacts; the severity or significance of the impact; and a demonstration that the impact is consistent with management plans and affected area custodians. ii. Describe the location of the critical habitat in relation to the project and why it cannot be avoided, as well as its characteristics and critical value. - The screening panel should assess whether ESP compliance and proposed mitigations measures are sufficient. | 1- Reviewing the geo-referenced locations of project activities against the map of natural habitats 2- Reviewing the screening checklist for grants against the map of natural habitats | The baseline is zero | During the full IFAD/AF project design IFAD carried out a SECAP and ESA that identified and excluded national parks ensuring that the project will not directly or indirectly impact protected areas or high value conservation areas. | Not identified | Not applciable
10 – Conservation of biological diversity |  |  | Low risk. At project design the project is not able to determine the project areas and conduct a full risk assessment. | For the reporting period: - Inclusion of AF safeguards in the Project Implementation Manual (PIM) and the Annual Work Plan and Budget. - Conduct an assessment and mapping of the national of threatened flora and fauna species (if any). - Setting up of screening panel and screening requirements. Ongoing: - Include in the screening matrix of the proposal screening panel to assess whether proposed activities are within areas identified as containing threatened flora and fauna species. - Inclusion in public tenders that project activities need to be screened for threatened flora and fauna. - Screen and assess whether project activities are a potential threat to threatened species. - Should threatened flora and fauna be identified proposals: i. Describe the elements of known biological diversity importance in the project area, using any relevant sources of information, such as protection status, status on the IUCN Red List of Threatened Species and other inventories, recognition as a UNESCO Man and the Biosphere Programme reserve, Ramsar site. ii. Describe why the biological diversity cannot be avoided and what measures will be taken to minimize impacts. - The screening panel should assess whether mitigations measures are sufficient. | 1- Reviewing the geo-referenced locations of project activities against the map of national thretened flora and fauna 2- Reviewing the screening checklist for grants against the map of national thretened flora and fauna | The baseline is zero | No measures implemented during the reporting period | Not identified | Not applciable
11 – Climate change
12 – Pollution prevention and resource efficiency |  |  | Possible risk for outcome 2.2: - There is a risk that project activities will add extraction pressures on a limited resource. - There is a risk that water used as a result of the outcome 2.2 tertiary canals (through the TRTP programme) from rivers or rain water reservoirs is not used efficiently. | For the reporting period: - Assess whether the proposed water permit framework in the project proposal is still relevant - The CPIU will hire a consultant to work with MARDE to explore ways within the national legal and procedural framework to streamline the national water permit approval process and requirements for simple investment proposals for the grants. - Update the PIM and ESMP with revised safeguard guidelines - Based on the revised guidelines screen grant proposals to ensure that they have the required water permits to ensure grant approval. | 1- Availability of the water permit 2- Reviewing the screening checklist for grants | The baseline is zero | No measures implemented during the reporting period | Not identified | Not applciable
13 – Public health
14 – Physical and cultural heritage |  |  | Low risk. At project design the project is not able to determine the project areas and conduct a full risk assessment. | For the reporting period: - Inclusion of AF safeguards in the Project Implementation Manual (PIM) and the Annual Work Plan and Budget. - All physical and cultural areas identified and mapped in all the country - Setting up of screening panel and screening requirements. Ongoing: - Inclusion in public tenders that the GPS locations of project activities need to be provided and a mapping of project locations vis-à-vis protected areas. - Screening of proposals and grants for funding to ensure that project activities will not operate in or near protected cultural areas. - Should proposals be received within or near identified cultural areas proposals for screening and review will need to include: i. Provide an inventory of the physical and cultural heritage present in the wider project area that enjoys recognition at community, national, or international levels. Describe the cultural heritage, the location and the results of a risk assessment analysing the potential for impacting the cultural heritage; and ii. Describe the measures to be taken to ensure that cultural heritage is not impacted, and if it is being accessed by communities, how this access will continue. - The screening panel should assess whether mitigations measures are sufficient. | 1- Reviewing the geo-referenced project activities against the map of cultural heritage sites 2- Reviewing the screening checklist for grants against the map of cultural heritage sites | The baseline is zero | No measures implemented during the reporting period | Not identified | Not applciable
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | No monitoring has been carried out as the project is in the implementation preparatory stage (staff recruitment, ToR development etc)
Have unanticipated ESP risks been identified during the reporting period?
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | No arrangements have been put in place as the project is in the implementation preparatory stage (staff recruitment, ToR development etc)
Have the implementation arrangements been effective during the reporting period?
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures?
Have the implementation arrangements at the EEs been effective during the reporting period?
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Strengthen the agro-ecological and social resilience to climate change in the climate vulnerable areas of Moldova, by enhancing water availability, water use efficiency, and promoting adaptive agriculture production systems and technologies for improved livelihoods and food security of rural households | Objective | No. of smallholder households benefitting from climate resilient improvements. | n/a | 5,000 households (11,665 people, 40% - 4666 women) will benefit from climate resilient improvements. | Satisfactory
|  | No. of people with improved awareness about the impacts of climate change and basic measure that can be taken to adapt. | n/a | 15,000 households (35,000 people, 40% - 14,000 women) will receive improved climate change awareness. | Satisfactory
Beneficiaries trained in groups of around 20 on climate resilient techniques and approaches to adapt to weather extremes and water efficient irrigation. | Output 1.1.3. | No. of beneficiaries trained | n/a | At least 400 beneficiaries (40% - 160 women ) trained on on-farm irrigation techniques | Satisfactory
|  |  | n/a | Around 4,600 farmers (40% - 1840 women) trained on climate resilient techniques. | Satisfactory
Professionals trained in gender awareness, CA, and CA technical and service provision to smallholder farmers. | Output 1.2.1. | No. of professionals trained | n/a | Around 40 professionals including recent university graduates and experienced professionals trained as service providers. (40% - 16 women) | Satisfactory
Knowledge management and climate change awareness raising system established and implemented. | Output 1.3.1. | Knowledge products produced and disseminated | n/a | Around 10,000 people (40% - 4,000 women) will receive improved climate change awareness through video clips broadcast on the AgroTV channel as well as social media (Facebook, Instagram and YouTube). Other outputs include radio programmes and the printed media including posters and leaflets. | Satisfactory
Improved smallholder access to water from rivers and rainwater reservoirs. | Output 2.2.1. | No. of beneficiaries benefitting from improved access to water | n/a | Around 400 smallholders (40% -160 women) benefit from water access. | Satisfactory
Households to received climate smart irrigation and support for banking fees for pro-poor escrow account | Output 2.3.1. | No. of smallholders to receive on-farm water-efficient irrigation technology | n/a | At least 400 households (40% -160 women) will benefit from technology that reduces irrigation water consumption, reduces production costs and increases yields and product quality. | Satisfactory
|  | No. of farmers benefitting from escrow account | n/a | Up to 400 farmers (40% – 160 women) benefitted from escrow account. | Satisfactory
Climate adaptive techniques implemented | Output 2.3.2. | No. of climate vulnerable smallholders supported to implement climate adaptive training. | n/a | Around 4,600 farmers (40% – 1,840 women) will receive demand-driven equipment to help farms apply training in adapting to increased drought and flooding. | Satisfactory
Conservation Agriculture mainstreamed into the national higher-level educational system. | Output 3.1.3. | Scholarships supported | n/a | One male and one female scholarships supported. | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
Not applicable (as the active imlementation phase of the project has not started yet)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | A TRTP Targeting and Gender strategy has been drafted.
Have the implementation arrangements at the IE been effective during the reporting period?
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5]
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5]
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented?
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Component 1 Capacity development to integrate CC adaptation into agricultural production systems
| Outcome 1.1 Climate resilient training programme established. |  | Outcome 3 | A service provider (SP) is contracted to develop and implement the training programme. SP will provide practical and theoretical training through FFS using demo plots to grant and non-grant beneficiaries, which implies that in the first year of training, all participants will be non-grant beneficiaries according to the selection criteria. Sequencing of training before lauching grants call is presented in the Project Implementation Manual. |  | A draft ToR is under development to start the procurement process for the selection of a service provider | S
| Outcome 1.2 Conservation agriculture (CA) professional service provider capacity built with a focus on smallholders |  | Outcome 4 | A ToR is developed and procurement process is initiated to select and contract a service provider to be in charge of CA capacity building |  | A ToR is not developed and procurement process is not initiated | U
| Outcome 1.3 Knowledge management |  | Outcome 3 | Knowledge management plan established. A service provider is contracted and the Baseline Survey is ongoing. |  | A Knowledge Management Plan identifies TRTP key knowledge themes, goal and objectives. A 18 months’ KM plan was developed, whose activities are adequately integrated in the AWPB and monitored by the M&E system. Creation of an on-line repository. A service provider is contracted and the Baseline Survey is ongoing | MS
Component 2: Climate-resilient Agricultural Investments
| Outcome 2.1 Community mobilisation undertaken with a focus on women and youth in the most climate-vulnerable areas |  | Outcome 3 | SP in charge of supporting the implementation of TRTP-Adapt interventions. This SP will be involved among others in the annual mobilisation campaigns to raise awareness and generate interest in the project and ensure equal access to project activities for the most vulnerable. This will be reflected in the PIM. A service provider is contracted to undertake community mobilisation |  | A draft ToR is under development to start the procurement process for the selection of a service provide | S
| Outcome 2.2 Climate resilient off-farm access to water secured from tertiary canals from rivers and water harvesting ponds |  | Outcome 4 | A Call for applications for climate resilient off-farm access to water secured from tertiary canals from rivers and water harvesting ponds is launched and applications received |  | A Call for applications for climate resilient off-farm access to water secured from tertiary canals from rivers and water harvesting ponds is launched and extended twice, while only one application was received | S
| Outcome 2.3 Demand-driven and beneficiary co-financed on-farm water conservation management and climate adaptive techniques supported |  | Outcome 6
Component 3: Development of the national framework for CA supported
| Outcome 3.1: CA mainstreamed into the national higher-level educational system |  | Outcome 4 | The CPIU will work with relevant research institutes to build on the information available in TRTP-Adapt and the PIM on defining the criteria for the CA research grants; strengthening the soil lab capacity; and development of demo plots and procurement of CA machinery specific for academic research in CA. This will be reflected in the PIM. A ToR is developed and a procurement process is launched to select a service provider to be in charge of CA mainstreaming into the national higher-level educational system |  | A Tor is not developed and a procurement process is not yet launched. | U
| Outcome 3.2 Research into CA supported with a focus on smallholders and women |  | Outcome 4 | No progress expected |  | No progress to date | n/a
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Renaud Colmant
| Email: | r.colmant@ifad.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project had a slow start due to the requcrutiemnts within the Project Implementation Unit. The progress to date is only related to some of the terms of reference that pave the way for the procurement processes. However, the project looks set to kicking off next year and meeting its disbursement target.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Component 1 Capacity development to integrate CC adaptation into agricultural production systems
| Outcome 1.1 Climate resilient training programme established. |  | Outcome 3 | A service provider is contracted to develop and implement the training programme |  | A draft ToR is under development to start the procurement process for the selection of a service provider | MS
| Outcome 1.2 Conservation agriculture (CA) professional service provider capacity built with a focus on smallholders |  | Outcome 4 | A ToR is developed and procurement process is initiated to select and contract a service provider to be in charge of CA capacity building |  | A ToR is not developed and procurement process is not initiated | U
| Outcome 1.3 Knowledge management |  | Outcome 3 | A service provider is contracted and the Baseline Survey is ongoing |  | A service provider is contracted and the Baseline Survey is ongoing | S
Component 2: Climate-resilient Agricultural Investments
| Outcome 2.1 Community mobilisation undertaken with a focus on women and youth in the most climate-vulnerable areas |  | Outcome 3 | A service provider is contracted to undertake community mobilisation |  | A draft ToR is under development to start the procurement process for the selection of a service provide | MS
| Outcome 2.2 Climate resilient off-farm access to water secured from tertiary canals from rivers and water harvesting ponds |  | Outcome 4 | A Call for applications for climate resilient off-farm access to water secured from tertiary canals from rivers and water harvesting ponds is launched and applications received |  | A Call for applications for climate resilient off-farm access to water secured from tertiary canals from rivers and water harvesting ponds is launched and extended twice, while only one application was received | S
| Outcome 2.3 Demand-driven and beneficiary co-financed on-farm water conservation management and climate adaptive techniques supported |  | Outcome 6
Component 3: Development of the national framework for CA supported
| Outcome 3.1: CA mainstreamed into the national higher-level educational system |  | Outcome 4 | A ToR is developed and a procurement process is launched to select a service provider to be in charge of CA mainstreaming into the national higher-level educational system |  | A Tor is not developed and a procurement process is not yet launched. | U
| Outcome 3.2 Research into CA supported with a focus on smallholders and women |  | Outcome 4 | No progress expected |  | No progress to date | n/a
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Elena Burlacu, CPIU IFAD, interim director
| Email: | elena.burlacu@ucipifad.md
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project has a slow start due to needed preparatory work (i.e. implementation staff recruitment, development of ToRs for the selection of service providers, procurement process to be conducted for the identification, selection and contracting of service providers, launching of call for proposals for off-farm Climate resilient off-farm access to water infrastructure, on-farm water management and CA research grant beneficiaries)
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline* | Progress since inception** | Target for Project End
Overall objective: strengthen the agro ecological and social resilience to climate change in the climate vulnerable areas of Moldova, by enhancing water availability, water use efficiency, and promoting adaptive agriculture production systems and technologies for improved livelihoods and food security of rural households | Ha of smallholder agricultural land made climate resilient | 0 | 0 | 25,000 ha of smallholder agricultural land that has benefitted from improved access to water, climate-smart irrigation systems and improved adaptive agricultural techniques
| No. of smallholder households benefitting from climate resilient improvements | 0 | 0 | 5,000 households (11,665 people, 40% - 4666 women, 50% 5,383 youth) will benefit from climate resilient improvements
| No. of people with improved awareness about the impacts of climate change and basic measure that can be taken to adapt | 0 | 0 | 35,000 people (15,000 households), 40% - 14,000 women, 50% - 17,500 youths, will receive improved climate change awareness
Component 1 Capacity development to integrate CC adaptation into agricultural production systems
Outcome 1.1 Climate resilient training programme established.
Output 1.1.1 A Training of Trainers (ToT) programme designed and implemented | Training programme designed | 0 | 0 | Training programme designed and implemented
Output 1.1.2 Demo plots identified and set up | No. of demo plots set up | 0 | 0 | 10 demo plots locations have been successfully identified, screened and implemented
Output 1.1.3 Beneficiaries trained in groups of around 20 on climate resilient techniques and approaches to adapt to weather extremes and water efficient irrigation | No. of beneficiaries trained | 0 | 0 | At least 400 beneficiaries (40% - 160 women 50% - 200 youth) trained on onfarm irrigation techniques
|  | 0 | 0 | Around 4,600 farmers (40% - 1840 women 50% - 2,300 youth) trained on climate resilient techniques
Outcome 1.2 Conservation agriculture (CA) professional service provider capacity built with a focus on smallholders
Output 1.2.1 Professionals trained in gender awareness, CA, and CA technical and service provision to smallholder farmers | No. of professionals trained | 0 | 0 | Around 40 professionals including recent university graduates and experienced professionals trained as service providers (40% - 16 women)
Outcome 1.3 Knowledge management
Output 1.3.1 Knowledge management and climate change awareness raising system established and implemented | Knowledge products produced and disseminated | 0 | 0 | Around 10,000 people (40% - 4,000 women, 50% 5,000 youth) will receive improved climate change awareness through video clips broadcast on the AgroTV channel as well as social media (Facebook, Instagram and YouTube). Other outputs include radio programmes and the printed media including posters and leaflets
| No. of knowledge generating studies / research produced. | 0 | 0 | Baseline, studies on effectiveness of outcome 2.3 and impact assessment produced
Component 2: Climate-resilient Agricultural Investments
Outcome 2.1 Community mobilisation undertaken with a focus on women and youth in the most climate-vulnerable areas
Output 2.1.1 Annual mobilisation campaign delivered and beneficiaries supported in making grant applications | No. of smallholders receiving information about the project | 0 | 0 | At least 11,665 people (5,000 households), 40% - 4666 women, 50% 5,383 youth, will benefit from climate resilient improvements
Output 2.1.2 Beneficiary applications screened by CPIU for compliance to criteria | No. of applications received that have successfully been granted water permits | 0 | 0 | At least 400 smallholders (40% - 160 women 50% - 200 youth) successfully applied for water efficient irrigation
| No. of demo plot applications received | 0 | 0 | Around 4,600 smallholders (40% - 1,840 women 50% - 2,300 youth) successfully applied for climate adaptive training
Outcome 2.2 Climate resilient off-farm access to water secured from tertiary canals from rivers and water harvesting ponds
Output 2.2.1 Improved smallholder access to water from rivers and rainwater reservoirs | Ha. with improved access to water | 0 | 0 | 2,000 ha. of smallholder land has improved water access
| No. of beneficiaries benefitting from improved access to water | 0 | 0 | Around 400 smallholders (40% - 160 women, 50% 200 youth) benefit from water access
Outcome 2.3 Demand-driven and beneficiary co-financed on-farm water conservation management and climate adaptive techniques supported
Output 2.3.1 Households received climate smart irrigation and support for banking fees for pro-poor escrow account | No. of smallholders to receive on-farm water efficient irrigation technology | 0 | 0 | At least 400 smallholders (40% -160 women, 50% - 200 youth) will benefit from technology that reduces irrigation water consumption, reduces production costs and increases yields and product quality
| No. of farmers benefitting from escrow account | 0 | 0 | Up to 400 farmers (40% – 160 women, 50% - 200 youth) benefitted from escrow account
Output 2.3.2 Climate adaptive techniques implemented | No. of climate vulnerable smallholders supported to implement climate adaptive training | 0 | 0 | Around 4,600 farmers (40% – 1,840 women, 50% 2,300 youth) will receive demand-driven equipment to help farms apply training in adapting to increased drought and flooding
Component 3: Development of the national framework for CA supported
Outcome 3.1: CA mainstreamed into the national higher-level educational system
Output 3.1.1 National survey and CA White Paper produced | A national CA survey conducted and White Paper produced | 0 | 0 | A survey is conducted and a White Paper produced making recommendations for the future of CA in Moldova
Output 3.1.2 National convention on CA. | At least one convention on CA is held | 0 | 0 | At least one convention is held and consensus reached on a national strategy for CA in Moldova
Output 3.1.3 CA mainstreamed into the national higher-level educational system. | A curriculum on CA is designed and textbooks and journals translated | 0 | 0 | A higher-level educational curriculum is designed on CA including translating textbooks and research papers
| Scholarships supported | 0 | 0 | One male and one female scholarships supported
Outcome 3.2 Research into CA supported with a focus on smallholders and women
Output 3.2.1 CA research grants, demo sites, equipment, soil laboratory supported | A research institute is supported in CA | 0 | 0 | Demo plots, equipment, soil laboratory provided
|  | 0 | 0 | Gender and smallholder-focused research is produced
| 1.b Estimated corresponding total number of households members | 0 | 0 | 33997
| 1.a Corresponding number of households reached | 0 | 0 | 11723
| 1 Persons receiving services promoted or supported by the project | 0 | 0 | 11723
| Number of households that report an increase in income | 0 | 0
| Percentage reduction in the number of households reporting about their intentions and plans to migrate from their community due to the project (%) | 0 | 0 | 20%
| Percentage increase in average monthly income of supported smallholders over baseline (%) | 0 | 0 | 30%
| IE.2.1. Perecentage of persons reporting an improvement in empowerment (the means of verification pro-WEAI) | 0 | 0 | >= 20%
| 3.2.2 Percentage of households reporting adoption of environmentally sustainable and climate-resilient technologies and practices | 0 | 0 | 70%
| 1.2.1 Households reporting improved access to land, forests, water or water bodies for production purposes | 0 | 0 | 2085
| 2.2.3 Rural producers’ organizations engaged in formal partnerships/agreements or contracts with public or private entities | 0 | 0 | 10
| 2.2.1 New jobs created | 0 | 0 | 1000
| 2.1.5 Roads constructed, rehabilitated or upgraded (Km) | 0 | 0 | 3
| 1.1.2. Farmlands under water-related infrastructures (Ha) | 0 | 0 | 2800
| Number of farmers provided with water saving technologies and trained in practices which are climate resilient | 0 | 0 | 440
| Number of persons trained in water and soil conservation agriculture which promotes CA | 0 | 0 | 5000
| 2.1.3. Rural producers' organizations supported | 0 | 0 | 10
| Numbers of Market Facilitation meetings organized | 0 | 0 | 32
| Number of business ideas/plans supported and mentored which assist in diversification of product | 0 | 0 | 10
| Number of institutions that have introduced CA in their curricula | 0 | 0 | 4
| 1.2.5 Households reporting using rural financial services | 0 | 0 | 182
| 1.1.5 Persons in rural areas accessing financial services | 0 | 0 | 260
| Number of SCAs whose savings are protected by the Deposit insurance fund | 0 | 0 | 60
| Policy-relevant knowledge products completed (MoF and NCFM policy) | 0 | 0 | 1
* The baseline indicators are set at 0.
**Considering the delay in hiring the adaptation fund specialis the active phase of the project implementation has not started yet and there is no progress since inception

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The project has a slow start due to needed preparatory work (i.e. implementation staff recruitment, development of ToRs for the selection of service providers for the implementation of particular activities, procurement processes to be conducted for the identification, selection and contracting of service providers, launching of call for applications for off-farm climate resilient off-farm access to water infrastructure, on-farm water management and CA research grant beneficiaries.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The project records some delays in implementation. The delay is caused by the fact that the Adaptation Fund Senior Specialist quitted the project implementation after three months. Another procurement process to select an Adaptation Fund Specialist was initiated. Moreover, the selection of the irrigation engineer for infrastructure development lasted longer than expected..
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No changes in project design were undertaken.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | No environmental and social safeguard measures were undertaken yet as the project is in the implementation preparatory stage (staff recruitment, ToR development etc.)
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | A TRTP Targeting and Gender strategy has been drafted.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | ???
Implementing Entity | International Fund for Agricultural Development (IFAD)
Type of implementing entity | MIE
Country | Moldova
Region | Eastern Europe
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 11665 | 5000 | 6665 | Total |  |  |  | Total
|  | % of female beneficiaries | 40% | 40% | 40% | % of female beneficiaries | 40% | 40% | 40% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 40% | 40% | 40% | % of Youth beneficiaries | 40% | 40% | 40% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness