## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | March 15th,2022 to March 31st ,2023
| Project Title: | RESILIENCE BUILDING AS CLIMATE CHANGE ADAPTATION IN DROUGHT-STRUCK SOUTH-WESTERN AFRICAN COMMUNITIES ANGOLA AND NAMIBIA
| Project Summary: | Angola and Namibia are experiencing severe food and water insecurity due to high drought occurrence. Increasing temperatures and rainfall variability have led to more frequent occurrences of floods and droughts resulting in negative effects on populations and ecosystems. The climate change (CC) impacts that both Angola and Namibia are experiencing are significant and include changing weather patterns, drops/rises in water levels, and increased frequency of extreme weather events such as droughts and floods, whose socio-economic repercussions are making communities even more vulnerable. The transboundary area of Cuando-Cubango and Kavango faces environmental stress in meeting the livelihood needs of the increasing human population leading to food insecurity; water pollution from fertilizer and pesticide application upstream along the Cuito, Cubango and Okavango rivers; soil erosion and siltation of rivers; unsustainable subsistence fishing; uncontrolled harvesting of forest resources for timber, charcoal and fuelwood energy causing deforestation with minimal replanting; and uncontrolled anthropogenic fires. Under projected CC in the two countries, it is inevitable that such environmental stresses render the communities in the transboundary area highly vulnerable to floods and droughts. Human land use activities such as crop and livestock farming are increasingly placing the river basin under environmental stress, raising concerns about its future sustainability. The long-term fate of the Cubango-Okavango Basin (CORB) and its delta depends upon the sustainable management of its water resources. As the populations in the area suffer from impacts induced by CC, most notably in the form of prolonged dry spells, long periods of drought conditions, and floods, prospects will not improve without interventions to build resilience to CC impacts. Deliberate efforts aimed at enhancing the resilience of communities and ecosystems to such impacts are imperative. A unified cross-border approach will not only help the populations to adapt to changing conditions but also encompass a key contribution to avoid further natural resource degradation such as encroachment of the protected areas. Sustainable utilization and ecosystem services provision of agricultural soils, surface and groundwater resources, forests and other terrestrial ecosystems will be achieved. Financed by the Adaptation Fund, the overall objective of the ADSWAC Project is to enhance the adaptation capacity and resilience of communities to climate change impacts and variability in the transboundary region between Angola and Namibia. The specific objectives are to: •Enhance local, sub-national and regional capacities to adapt and respond to climate change risks in the cross-border area of Angola and Namibia; •Build organizational and technical capacity for climate-resilient production and water management; •Improve food security in response to climate change impacts amongst rural and vulnerable communities in Cuando Cubango Province and the Regions of Kavango East and Kavango West.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AFR/RIE/Rural/2019/PPC/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Sahara and Sahel Observatory (OSS) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Regional Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Angola & Namibia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | •Angola : Cuando Cubango province (Cuangar; Calai; Dirico and Rivungo) •Namibia: Kavango East and Kavango West | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date:
IE-AFB Agreement Signature Date: |  | July 2021 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | March 15 2022 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | November 15 2024
| Original Completion Date: | March 01 2027
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception workshop report (March 15th, 2022) submited on May 11th, 2022 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
Implementing Project Manager/Coordinator
| Name: | Mrs. Khaoula Jaoui
| Email: | khaoula.jaoui@oss.org.tn
| Date: | July 1st, 2021
| Regional Project Manager/Coordinator |  | Dominican Republic
| Name: | Mr.Valente cangengo | Ecuador
| Email: | valente.cangengo@adpp-angola.org | Egypt
| Date: | February 2nd, 2023
| National Project Manager/Coordinator |  | El Salvador
| Name: | Mr. Eurico Virgilio (Angola) | Equatoral Guinea
| Email: | eurico.virgilio@adpp-angola.org | Eritrea
| Date: | January 12th, 2023 | Estonia
Ethiopia
| Name: | Mrs. Lynnety Sinalumbu | Fiji
| Email: | lynnety@dapp-namibia.org | Finland
| Date: | March 1st, 2023 | France
| Implementing Entity |  | Ethiopia
| Name: | SAHARA AND SAHEL OBSERVATORY | Fiji
| Email: | boc@oss.org.tn | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | ADPP (Ajuda de Desenvolvimento de Povo para Povo) | Georgia
| Email: | adpp@adpp-angola.org | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | DAPP NAMIBIA(DEVELOPMENT AID FROM PEOPLE TO PEOPLE NAMIBIA) | Grenada
| Email: | dappnamibia@iway.na | Guatemala
| Date: |  | Guinea
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to March 31st 2023 |  |  |  |  | Financial information PPR 2: cumulative from April 1st 2023 to March 31st 2024 |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of March 31st 2023 |  | 856618.2 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) |  | As of this reporting period, a total cumulative disbursement of USD 856,618.20 to the EEs has been recorded from the received amount of USD 4,868,000 from the AF. this is 17% of the funds received. This is due to the lengthy operationalization of the project taking into account the initial COVID pandemic and the setting up of the management units. Following the above, the RIE has put in place measures to support the EEs to fast track the execution of activities as well as developing a Rapid Response Initiative (RRI) which is expected to deliver results in a timely manner. The RIE has also initiated activities related to capacity building and working sessions to the EEs to support the financial management approaches and sessions related to con tinuous development of operational documents. This will support the results based reporting using the No-objection process to monitor coupled with M&E missions as well as supervision missions. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME |  |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
|  | Output 1.1.1 Communities and populations in the targeted areas have participated in climate change adaptation and risk reduction awareness activities | 2689.2985
|  | Output 1.1.2 Climate change awareness and sensitization to the communities | 0
|  | Output 1.2.1 National and regional centers and networks to respond to extreme weather events have been established, reinforced and supported in their operation | 0
|  | Output 2.1.1 Capacities of extension services and institutions needs are assessed and strengthened | 0
|  | Output 2.1.2 Communities are organized and adopt and mainstream to climate resilience practices (160 POs and 160 WUAs) | 40386.0949
|  | Output 2.2.1 160 model plots (Farmer Field Schools) for climate-resilient and water-efficient agriculture practices (Conservation Agriculture (CA) and Agroforestry Systems (AFS)) are established | 0
|  | Output 3.1.1 Target farmers’ and populations’ access to and use of water during the dry season are increased | 89481.9485
|  | Output 3.1.2 Agriculture resilient practices are adopted and promoted | 0
|  | Output 3.1.3 Sustainable fisheries are supported | 0
|  | Output 3.1.4Improved livestock production is supported | 0
|  | Output 3.2.1Production of 6,500 targeted farmers (50% women) is diversified (crop diversification, beekeeping, fishing) | 0
|  | Total of Activities | 132557.3419 |  |  | Total of Activities | 0
|  | Executing Entity Fees | 72690.0261 |  |  | Executing Entity Fees
|  | TOTAL | 205247.3679 |  |  | TOTAL | 0
|  | Implementing Entity Fees | 96957.26 |  |  | Implementing Entity Fees
|  | TOTAL | 302204.6279 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST (USD) | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
|  | Output 1.1.1 Communities and populations in the targeted areas have participated in climate change adaptation and risk reduction awareness activities | 370299.67 | 31/03/2024
|  | Output 1.1.2 Climate change awareness and sensitization to the communities | 200702.73 | 31/03/2024
|  | Output 1.2.1 National and regional centers and networks to respond to extreme weather events have been established, reinforced and supported in their operation | 117466.24 | 31/03/2024
|  | Output 2.1.1 Capacities of extension services and institutions needs are assessed and strengthened | 195834.35 | 2024-01-31
|  | Output 2.1.2 Communities are organized and adopt and mainstream to climate resilience practices (160 POs and 160 WUAs) | 423679.95 | 2024-02-29
|  | Output 2.2.1 160 model plots (Farmer Field Schools) for climate-resilient and water-efficient agriculture practices (Conservation Agriculture (CA) and Agroforestry Systems (AFS)) are established | 565294.22 | 2023-12-17
|  | Output 3.1.1 Target farmers’ and populations’ access to and use of water during the dry season are increased | 2061837.99 | 2024-02-29
|  | Output 3.1.2 Agriculture resilient practices are adopted and promoted | 688538.62 | 2024-02-29
|  | Output 3.1.3 Sustainable fisheries are supported | 159566.97 | 2023-11-30
|  | Output 3.1.4Improved livestock production is supported | 209056.9 | 2024-02-29
|  | Output 3.2.1Production of 6,500 targeted farmers (50% women) is diversified (crop diversification, beekeeping, fishing) | 448578.35 | 31/03/2024
|  | Total of Activities | 5440855.99
|  | Executing Entity Fees | 110032
|  | TOTAL (actvities+EE) [a] | 5550887.99
|  | IMPLEMENTING ENTITY FEES [b] | 135000
|  | TOTAL[a+b] | 5685887.99
| ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
| How much of the total co-financing as committed in the Project Document has actually been realized? |  | N/A |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
| Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  | 0 |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
| Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  | N/A |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The Covid-19 virus or other pandemic outbreaks hinder the implementation of activities | Low | ◘ Follow up closely on and adhere to any national regulations regarding hygienic measures, permitted behaviour in terms of meetings and travel restrictions; ◘ Continue having good contingency plans in place for potential new outbreaks of the virus, including guidelines for project staff, access to and use of hygiene provisions, etc.; ◘ Assure continuous communication with staff in the field regarding the situation; ◘ Hold meetings virtually when the situation requires;
Low collaboration amongst the relevant technical institutions | Medium | ◘ The involved institutions have been identified, consulted and engaged and will be further involved within the project activites; ◘ Institutions will be engaged and brought together during the project implementation
Lack of political will to implement the project at local or national level | Low | ◘ Authorities have demonstrated commitment to the projects during several meeting at diffrent levels; ◘ Continuous consultations, involvement and reporting with relevant institutions during the entire project cycle; ◘ The EEs have been working in the targeted areas for over 20 years, and are trusted organizations amongst government and local leaders;
GoA or GoN departments that are involved are understaffed and can’t reach the requirements | Medium | ◘The Project has been allocated focal points in the Ministries and included in the fiscal year work planning ◘ Draft Agreements, MoUs have been developed with various Ministries and departments towards their scope of activities and will be signed ◘GoA and GoN departments will be consulted and involved in the planning phases of specific activities and activity clusters; ◘As applicable, project staff will attend to some departments’ responsibilities; ◘Representatives from GoA and GoN has been appointed and are part of the project's steering committee in order to ensure their involvement within the decision making process and within the project activities;
Insufficient resources locally to duplicate models (rainwater harvesting, solar irrigation technology) | Low | ◘ Where possible, low-cost models will be promoted (in situ systems, farm ponds, etc.) ◘ POs and WUAs are in the process of establishment which will include ToTs and the CNA is being elaborated to take into account the human capacities as well. ◘POs and WUAs will be formalized institutions, and access to credit will be facilitated for investing in technologies
Language difference between the countries affects the communication and implementation | Low | ◘ Build on the EEs’ experience in cross-border projects and communication as members of the same network; ◘ Translation is provided during meetings that involve participants from both sides of the border; ◘ Project manuals, documents and tools are translated in English and Portuguese; ◘ Although national languages are different, local languages spoken are similar across the border, ◘The NPMU and project field staff will be sourced from the project areas and will ensure the involvement of the local and traditional authorities for fluidity of local spoken language
Insufficient interest in the project among the target population and local governments | Low | ◘Local leaders are backing the project, and will be continuously be involved ◘The EEs have built a good reputation with the stakeholders at different levels ◘Sensitization at community-level and with community leaders is inherent to the project’s approach ◘PMUs support and engaging directly in undertaking KAP survey to understand better the needs and practices of the communities so as to execute and align activities
Insufficient interest in the project among youth | Low | ◘Emphasize youth involvement especiallywomen in all activities ◘ Initial engagement of youth through sensitization and awareness campaigns of the NEEs ◘Engaging the women and youth in the project activity teams in preparation for project activities' execution
Established POs, WUAs or CCACs collapse | Low | ◘Technical and management training and mentorship of organizations ◘Ensure community structures have viable constitutions, organizational structures and sufficient extension support within and beyond the project
Conflicts between transhumance pastoralists and smallholder farmers, and among fishermen across the border | Low | ◘Involvement of traditional leaders in planning, implementation, monitoring and evaluation processes of the project ◘Mass sensitization on the relevance of the project at the project initiation stage ◘Adherence to all local formal and informal regulations ◘Trainings provided in conflict management
Greater awareness and increased capacities don’t lead to positive change | Low | ◘Project methodologies and capacity building sessions selected are the result of many experiences in similar target areas; ◘Close monitoring of results and progress on indicators to be able to adjust in good time ◘ Promote flexibility among staff to adjust to new approaches when and where necessary ◘Contrast traditional/cultural practices to new technologies and approaches ◘CNA being elaborated to understand the capacity gaps and how to address them through the training plan ◘Draft communication plan on sensitization and awareness campaigns to be valorised
Poor monitoring and evaluation and delayed delivery of outputs | Low | ◘The project will develop a detailed participatory M&E framework with the key project partners ◘Regular follow-ups and timely continuous monitoring and evaluation ◘Onboarding of an M&E assistant at the PMU level to support monitoring of activities ◘ The use of weekly meetings has been explored to include the EEs by the RIE ◘ The application of supervision missions to the entities is programmed as a countinous process to ensure first hand monitoring of all project aspects
Project financial management | Medium | ◘ The RIE has engaged a finacial specialist dedicated to the ADSWAC project to support, monitor and train the EEs in financial management ◘ The project has developed Financial reporting templates and tools to be applied by the EEs ◘ The Financial managers have been trained in the use of these tools and are reporting on a monthly, quarterly, semi annual and annually basis with the use of supporting documents ◘ The EEs are supported on a day to day basis by the fiduciary unit of OSS when required ◘ The establishment of the PMUs with the inclusion of finance and procurement support ensures that all procedures that were provided are been implemented and align with AF and OSS regulations and standards
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Delays in establishment of Project Management Units and execution of project activities by NEE | Medium | ◘ The RIE has assisted in development of draft ToRs and transmitted to the EEs to fast track of the actvities. ◘ The RIE has assisted the EEs in the finanicial mangement of the budget dedicated to the PMUs salaries. ◘ The RIE has assisted the EEs in the process of the recuitment of the PMUs members and was present as observer during the interviews. ◘ The RIE has expedited the NO process to ensure timely submissions of the decisions.
Delays in execution of project activities by EEs | Medium | ◘ The RIE has assisted the EEs in integration of some year one project activities in the second-year annual work planning and fast track preparation of AWP and PP ◘ The annual wok plans and budgets have been revised to take into account the activities to be executed through an action plan linking the REE and NEEs to work in tandem where some activities will be undertaken jointly. ◘ The use of inhouse expertise provided by EEs has been proposed to facilitate fast tracking of activities as well as taking into account limited expetise in such cases. ◘A Rapid Results Initiative has been proposed to enable some activities to be result based within a 90 day period
Inadequate capacity in populating project documents e.g. No-objection tracker and limited capacity of PMUs to provide high quality documents e.g. No objections to the RIE | Medium | ◘ RIE provided technical assistance to the EEs when and where necessary in order to facilitate the process and meet the project requirements. ◘ RIE Organised a technical working sessions that enabled the Executing Entities to discuss project-related documents. ◘ RIE has proposed capacity building sessions with the EEs on technical and financial aspects.
Management of funds by EEs- accountability etc. | Low | ◘The RIE has developed tools and has taken the EEs through a training on how to use and apply the financial monitoring tools with the fiduciary units which include procurement and accounting with the coordinators, non-finance personnel and project managers in the within the EEs and PMUs
Limited capacity, especially in areas of SWLM , CRA practices and CC impacts in the targeted sites | Low | ◘ The KAP survey is being undertaken in collaboration between the EEs to understand the schematics of the communities and their perceived expectations of the ADSWAC Project. ◘ A CNAis been undertaken to identify the capacity building needs within the target sites. ◘ Training manuals will be elaborated based on the CNA to conceptualise the needs of the stakeholders in relation to project interventions. ◘ A training plan will be developed to identify relevant additional training modules. ◘ The establishment of the National Steering Committees has been undertaken. It includes representatives from local goverments, and NGOs. They will establish the linkages with the project beneficiaries to on-going capacity development efforts of resilience building in the two countries which will also ensure synergies.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
With regards to the risk mitigation, the project team embarked on undertaking knowledge management which focused on capacity building and empowerement of community members. The risks have been managed through: (i) The Organization of clinic sessions and project philosophy understanding to facilitate the activities progress in a regional dimension (ii) The elaboration of concrete action plans for the second year detailing the actions, responsibilities and deadlines, and fastracking of project activites that would bring a better dynamism to the project and reduce the delays experienced (iii) The creation of a sharing platform (sharepoint) to act as a repository for all the Project related documents, ToRs, CNs, reports developed which is continuously being updated by all EEs to ensure alignment and promote the regional dimension of the project not forgeting communication and lessons learnt (iv) The constant engagement and monitoring of project partners has been enhanced to promote knowledge management and ensure delivery of project outcomes (v) Weekly meetings and technical assistance/support to the EEs is a constant day to day of the RIE to enable alignment of all entities to achieve globally Above that, community and stakeholder participation at the centre has been pivotal towards risk mitigations, of which ADSWAC project is employing participatory approaches through its identification, planning for solutions/interventions, implementation, monitoring and evaluation of interventions. Therefore, all these project approaches have significantly contributed towards risk mitigations. Overall, the risks identified above are manageable during this reporting period.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | NTR | NTR | NTR | NTR | ◘ Currently no risk has been identified regarding conformity with the law | NTR | NTR
2 - Access and equity |  |  | ◘ Women and youth are characterized by poor access to land and related resources over agricultural production and finance. These findings imply that there is limited capacity to cope due to high levels of poverty and dependency among the women and youth and may limit their opportunities to benefit from projects outcomes requiring access to land. ◘ Rural people (pastoralists, fishers and smallholder farmers) and marginalized poor families targeted by the project are not often integrated in the local politics and decision-making processes. This may limit their opportunities to be part of the decision-making bodies such as the WUAs and POs and to benefit the project outcomes. | Project beneficiaries will be selected through few phases, including (1) Screening of potential beneficiaries during the community consultation meetings, (2) Recommendations by the municipalities and the final beneficiaries will be selected as a result of (3) Face-to-face meeting and visit to the farm of the beneficiary in order to assess her/his skills of farming and readiness to accept the project terms. ◘ To ensure the equal participation of women, youth, elderly and other potentially vulnerable groups, dedicated consultations and working groups with these groups will be organized to provide ample space for the consideration of the specific needs of these stakeholder groups. ◘ Close monitoring of the project beneficiaries to assure equal access of men; women, youth and the most vulnerable; ◘ A grievance redress mechanism would support community members and stakeholders to submit any complaint. | ◘ Selection criteria agreed on ◘ Nb of workshops ◘ Nb of participants to these workshops and gender distribution ◘ Nb of complaints | NTR | ◘ Initial consultations of some potential project beneficiaries within the project area were held for more understanding of the communities needs and daily challenges, women, youth, elderly was also part of the meetings, the FPIC process was applied during the consultation process. ◘ The selection criteria of the project beneficiaries are being developed together with the different stakeholders within the project area, this will be part of the consultations during the execution of the baseline study taken into consideration gender equality access, this includes also the indigenous groups within the project sites. | NTR | NTR
3 – Marginalized and vulnerable Groups |  |  | ◘Lack of land ownership may affect negatively some vulnerable groups | ◘Marginalized people who do not have land will be given priority for access to other project activities such as IGAs, fishing, etc. The project will also closely monitor the targeting of all project beneficiaries to ensure equal access of men, women youth and the most vulnerable. ◘ Community selection criteria to avoid exclusion and inequity ◘ The project activities do not require full time labour. Full time labour of communities can be directed to other activities including agricultural crop farming in other areas. ◘ KAP surveys will be conducted at the local level to collect feedback from the population including marginalized groups ◘ Grievance mechanism ◘To avoid the exclusion of marginalized and vulnerable communities in order to disseminate and broadcast the information in local radio channels and traditional practices such as speakers to reach them. Visual learning and awareness materials will be included to avoid exclusion of illiterate groups | ◘ Nb/ Frequency of radio awareness campaigns per day (in local language) | 0
4 – Human rights |  |  | ◘ The project activities do not generate risks related to human rights. | ◘The project activities do not generate risks related to human rights so there are no mitigation measures to plan. ◘ Grievance mechanism
5 – Gender equality and women’s empowerment |  |  | ◘ Women’s status and representation may limit their meaningful participation in project activities and benefiting it outcomes. ◘ The majority of those involved and benefiting from the project’s field agricultural activities will be men who are mostly land owners | ◘ Ensure the presence of women and young people in workshops and trainings; ◘ A Gender Assessment Action Plan have been developed to ensure that women are meaningfully engaged in project activities and realize an equitable share of project benefits ◘ Communication and sensitization of the population on the gender issue to ensure gender parity in USPs; ◘ Grievance mechanism. Women will be specifically targeted to benefit from activities primarily animal raising loans and the agro-processing activities. This will enhance their access to finance and enable them to generate income, contributing directly to their financial empowerment. | ◘% of women and youth participating in workshops and trainings ◘ % of women beneficiaries of USPs ◘ % of women in the POs and WUAs ◘ % of women leading POs and WUAs ◘ Nb of complaints ◘% of women beneficiaries’ micro credit | NTR | NTR | NTR | NTR
6 – Core labour rights |  |  | ◘ Construction/Rehabilitation planned under the project may lead to accidents and occupational hazards during the project preparation and implementation. ◘ In rural areas where the presence of the state is not very strong, late or unpaid salaries or remuneration non- compliant with the countries labour legislations and laws may occurs as well as Children’s labour. | ◘ Sensitize workers and populations to the risks related to the undertaken activities; ◘ Design and implement safety measures and emergency plans to contain accidents risks and ensure the application of safety standards by companies (equipment, signs, training, etc.) ◘ Provide workers with protective clothing (nose and mouth masks, ear muffs, overalls, industrial boots and gloves) and helmets as applicable ◘ Salaries in line with the best common practices in the districts and villages; ◘ Close follow-up and monitoring of the worksites by the national executing entities including schedules, activities progress, respect of the labour and safety rights of workers and conformity with national labour codes. | ◘ Nb of training sessions on the risks related to construction sites ◘ Nb of participants to these sessions and gender distribution ◘ % of companies that comply with safety standards ◘ % workers equipped with protective clothing ◘ Signature of people involved in works; ◘% of spot checks validated | NTR | NTR | NTR | NTR
7 – Indigenous peoples |  |  | Although indigenous people have formal right to participate, they have no influence over national issues and rarely consulted on issues affecting them directly and therefore special consideration of empowering. Changes in San and Khoisan lifestyle due to the type of activities promoted in the project | ◘Involvement of indigenous people representatives at all project stages (development, implementation, monitoring and decision-making process) ◘ Ongoing consultation process to adapt the project activity (USP) to their needs. ◘The implementation of the activities under Component 3 that involve indigenous peoples will align with the seasonal calendar of the indigenous peoples. | ◘% indigenous people involved | NTR | NTR | NTR | NTR
8 – Involuntary resettlement |  |  | ◘The construction of water solution and demonstration plots will occupy spaces and may affect private lands or related activities | ◘The choice of these areas will include strict criteria to be agreed with traditional and local authorities that stipulate no population resettlement through giving priority to communal-owned lands. ◘ Sensitization and awareness sessions will be organized to explain the potential impact of such an activity and its added value. | ◘ Nb of beneficiaries affected by the project activities ◘ Nb of sensitization session | NTR | NTR | NTR | NTR
9 – Protection of natural habitats |  |  | ◘The presence of labour and construction equipment, if this is necessary for carrying out the works or activities planned by the project such as boat loading sites could have an impact on the fauna and flora of certain intervention sites. ◘ The implementation of water solution may result in the vegetation and wildlife habitats destabilization in the implantation site | ◘ Follow-up of the implementation of all activities related to the protection and management of ecosystems and natural habitats; ◘ Establishment of E&S Impact Assessment Studies; ◘ Sensitization sessions to local populations on good environmental practices and the protection of natural habitats. | ◘ Nb of monitoring reports including specific section on activities related to the protection and management of ecosystems ◘ Nb of E&S impacts assessments ◘ Nb of awareness sessions on the protection of the ecosystems ◘ Nb of participants to these session | NTR | NTR | NTR | NTR
10 – Conservation of biological diversity |  |  | ◘ The promoted drought resilient species and seeds may represent a form of disturbance for the flora. ◘ Vegetation clearance for water harvesting and storage sites construction may represent a form of disturbance for fish habitats and wildlife. | ◘ Organize consultations meetings with forest officer and communities to agree on the suitable seeds ◘ Species introduced in the communities are not alien to the area. ◘ Follow-up and monitor the implementation of all activities related to the protection and management of ecosystems; ◘ Minimize vegetation clearance as Low as Reasonably Practical (ALARP); ◘ Avoid cutting large trees with a diameter >20cm; ◘ Promote planning for activities of biodiversity conservation such as Compensatory reforestation; ◘ Pre-survey the proposed construction site areas to avoid sensitive habitats that have high diversity of indigenous plants; ◘ Promote awareness sessions, capacity building and peer learning to strengthen the efficient management of natural resources, including aquatic species, animals and forests | ◘ Nb of meetings organized ◘ Nb of monitoring reports including specific section on activities related to the protection and management of ecosystems ◘ % reforested land in relation to deforested land ◘ Nb surveys established ◘ % of surveys indicating that the area has high diversity of indigenous plants ◘ Nb of awareness sessions on the protection of the ecosystems ◘ Nb of participants in these sessions and gender distribution | NTR | NTR | NTR | NTR
11 – Climate change |  |  | ◘ The project activities do not generate risks related to climate change | ◘ The project activities do not generate risks related to climate change so there are no mitigation measures to plan; ◘ A small positive impact is expected from the use of solar energy for water pumping and irrigation, reducing the use of diesel pumps; ◘ Agriculture practices mainstreamed can be expected to have a positive impact as carbon sequestering. |  | NTR | NTR | NTR | NTR
12 – Pollution prevention and resource efficiency |  |  | ◘ Potential contamination of water reservoir through introduction of impurities, wastewater and solid waste | ◘ Conduct regular water quality monitoring and maintenance of the water supply system as well as ensure the monitoring of water quality by chemical analysis; ◘ Awareness improvement on water Resource management and conservation through consultation workshop ◘ Irrigation system installed, fully monitored and schedule controlled | ◘ Nb of conformity certificates issued; ◘ Nb of awareness sessions on water Resource management and conservation ◘ Nb of frauds and irregularities | NTR | NTR | NTR | NTR
13 – Public health |  |  | Water storage constructions may lead to water- or vector-borne diseases (such as cholera or Malaria) increase, and the proliferation of insects near the water points. The presence of workers at construction sites near the project beneficiary villages could increase the risk of spread of sexually transmitted diseases (STD) especially that most vulnerable members of communities. Risk of persons safety in maintaining the tanks or dams (in particular risk of fall of man or cattle. | ◘Raise awareness and support mechanisms to prevent and control spread of water related diseases such as Malaria and Bilharzia among the program workers and local communities ◘ Implement disease awareness and management programme for Malaria and Bilharzia ◘ Provide family sanitary kits (filters and disinfectants) ◘ Conduct community campaigns on safe water use, and improved hygiene and sanitation practices; ◘ Prevent and control spread of HIV/AIDS among the program workers and local communities, by organizing sensitization sessions and distributing prevention kits. ◘ Recruitment of the project labour force among the targeted area Ensure security at the reservoirs especially at the dams’ area by providing adequate protective equipment (e.g., protective mesh). | ◘ Nb of participants in these sessions and gender distribution ◘ Nb of families provided with sanitary kits for water purification ◘Nb of awareness sessions on diseases ◘ Nb of workers provided by prevention kits ◘ % of the labour force from the targeted area ◘ % reservoirs equipped with security measures ◘ Nb of security measures set up at each reservoir | NTR | NTR | NTR | NTR
14 – Physical and cultural heritage |  |  | ◘ The new agricultural practices and water solutions may affect local and indigenous people’s knowledge | ◘ Awareness raising sessions with to local populations on the project activities | ◘ Nb of sessions organized | NTR | NTR | NTR | NTR
15 – Lands and soil conservation |  |  | ◘ Some activities such as agriculture and construction may lead to soil erosion and compaction | ◘ Instruction of sustainable soil and water conservation measure ◘ Refreshment of the deteriorate land ◘ Raise the local population awareness to strengthen the effective management of soil and land | ◘ Nb of soil and water conservation measures ◘ % refreshed land in relation to compacted land ◘ Nb of awareness sessions on the effective management of soil and land | NTR | NTR | NTR | NTR
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes and this is on going. The tools for periodic monitoring of project interventions and ESMPs implementation provides for capturing any unanticipated ESP risks and is schedulled during implementation extensively to ensure compliance. Yes , ununanticipated ESP risks will be carried out by the RIE and PMU M&E responsible at the regional and local level when activities will be executed.
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The RIE provided technical support to the project team to build its capacity of employing community based participatory planning approached which was very key in preparation of project related documents such as the workplans, and procurment plans. Furthermore, in its capacity as RIE provided various reference materials to support project off-take and ongoing implementation. Additionally, technical backstopping services were made available in implementation of the ADSWAC project activities to ensure adherance to standards and minimise the identified risks. In order to implement the required ESP safeguard measures the IE has put in place the following arrangements: ◘ Review of reports on project progress that include MIFs and project tracker and quartaly reports; ◘ Review of ToRs, CNs through a No - Objection process in order to ensure that the ESP safeguards have been taken into consideration.
Have the implementation arrangements been effective during the reporting period? |  | Yes, the implementation arrangements continue to be effective however through a lengthy process which has now been addressed to support the next period.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | In order to implement the required ESP safeguard measures, the RIE with EEs have put in place the following arrangements: ◘ Recruitment of the PMUs staff at regional and national levels (project coordinator, Financial manager, procurement officer, accountant technical and M&E officer); ◘ Involvement of technical and financial staff from the RIE to the PMUs in the understanding and execution of activities as part of the EEs support and facilitation; ◘ Organizing of frequent consultation and sensitization sessions with all actors and stakeholders such as local communities; ◘ The matter of ESP is discussed with the EEs during planning of each project activity and compliance is observed
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes. The arrangements were implemented by the EEs throughout the project in a continuous process as well as the onboarding of the M&E responsible and ensueing their undertstanding towards the ESMP requirements.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Yes. The required capacity for ESMP implementation is present and effective with both IE and EEs. The IE is responsible for monitoring implementation progress of the ESMPs and also provision of technical support. The IE has designated technical focal persons for all the project components i.e. soil and water conservation, crop insurance, smallholder agriculture produce marketing and Village savings and loans. On the other hand, the EE is responsible for disclosure of the ESMPs to the project beneficiaries and all relevant stakeholders. Furthemore, the EE is responsible for actual implementation of the ESMP and reporting of the progress. The EE has appropriate structures in place at all levels to foste implementation of the ESMPs and the organization level. At National level the EE has the National Project Management Unit (NPMU) which amongst others comprises, the National project coordinator, project component leads (Soil and Water Conservation, Crop Insurance, Smallholder Agriculture Produce Marketing and M&E). The NPMU works hand in hand with the local governments and administrators in execution of the project activities. Furthermore, the local governments and administrators work in close collaboration with frontline workers in all the project impact areas, who spearhead activity execution at community level. Adequate orientation/sensitisations have ben done at all levels on the ESMPs.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | No, the ESMP is still as is and shall be updated accordingly during the execution.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, during the preparation of the full proposal a Gender Assessment and Action Plan for ADSWAC Project (Angola and Namibia) was carried out
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes, the results framework include gender-responsive indictors broken down at the outcome and output levels
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Output 1.1.1 Communities and populations in the targeted areas have participated in climate change adaptation and risk reduction awareness activities | Output | ◘Number of consultative workshops dedicated to women ◘Number of capacities-building activities dedicated to women ◘% of women participants in development of CAAPs |  | ◘3 consultative workshops dedicated to women ◘4 capacities-building activities dedicated to women ◘40 % of women participants in development of CAAPs ◘4 capacities-building activities dedicated to women ◘40 % of women participants in development of CAAPs | poor
Output 1.1.2 Climate change awareness and sensitization to the communities | Output | ◘% of women reached by the communication strategy ◘Number of CC awareness campaigns dedicated to women ◘Number of CC awareness campaigns organized for girls in schools ◘% of women/ girls accessing project results ◘Number of written and non-written knowledge products e.g., documents on lessons and best practices from project interventions ◘Number of case studies and lessons learned documented and shared |  | ◘50% of women reached by the communication strategy ◘At least 1 CC awareness campaigns per CCAC per year organized for women in each targeted community ◘30 CC awareness campaigns organized for girls in schools ◘50% women accessing project results ◘4 brochures, 4 publication (documents), 4 non-written forms of communication on lessons and best practices from project intervention ◘At least 8 case studies /lessons learned shared | poor
Output 1.2.1 National and regional centres and networks to respond to extreme weather events have been established,reinforced and supported in their operation | Output | ◘% of women reached by the communication strategy ◘Number of CC awareness campaigns dedicated to women ◘Number of CC awareness campaigns organized for girls in schools ◘% of women/ girls accessing project results ◘Number of written and non-written knowledge products e.g., documents on lessons and best practices from project interventions ◘Number of case studies and lessons learned documented and shared |  | ◘50% of women reached by the communication strategy ◘At least 1 CC awareness campaigns per CCAC per year organized for women in each targeted community ◘30 CC awareness campaigns organized for girls in schools ◘50% women accessing project results ◘4 brochures, 4 publication (documents), 4 non-written forms of communication on lessons and best practices from project intervention ◘At least 8 case studies /lessons learned shared | poor
Output 2.1.1 Capacities of extension services and institutions needs are assessed and strengthened | Output | ◘Number of training sessions dedicated to women ◘Number of women attending farmer field days ◘Number of training sessions dedicated to women ◘Number of women attending farmer field days ◘Number of women accessing FFS methodology |  | ◘5 training sessions per year dedicated to women ◘3,250 women attending farmer field days ◘3,250 women access FFS methodology | poor
Output 2.1.2 Communities are organized to adopt and mainstream to climate resilience practices (160 POs and 160 WUAs) | Output | ◘Number of women integrated in POs and WUAs ◘% of women members of WUAs and POs board ◘Number of information forums dedicated to women |  | ◘50% women integrate POs and WUAs ◘50% of women members of WUAs and POs board ◘2 information forums are dedicated to women (1 in Angola, 1 in Namibia) | poor
Output 2.2.2 160 model plots (Farmer Field Schools) for climate-resilient and water-efficient agriculture practices (Conservation Agriculture (CA) and Agroforestry Systems ( | Output | ◘Number of women that partake in FFS model plots establishment ◘Number of female Lead Farmers trained ◘Number of training sessions dedicated to women |  | ◘650 women partake in FFS model plots establishment ◘350 female Lead Farmers trained ◘160 training sessions dedicated to women | poor
Output 3.1.1 Target farmers and population access and use of water during the dry season are increased | Output | Attending participatory processes ◘Number of women accessing irrigation technology ◘Number of sensitization campaigns dedicated to women |  | Participatory processes ◘3,250 women accessing irrigation technology ◘At least 30 sensitization campaigns dedicated to women | poor
Output 3.1.2 Agricultural resilient practices are adopted and promoted | Output | ◘Number of trainings dedicated to women ◘Number of nurseries and seed banks established and managed by women ◘Number of women using drought-resistant crops and seeds ◘Number of women beneficiaries from resilient cropping practices ◘Number of women beneficiaries from horticulture and horticulture sites ◘Number of nurseries and seed banks established and managed by women |  | ◘160 trainings dedicated to women ◘80 nurseries and seed banks established and managed by women ◘3,250 women using drought-resistant crops and seeds ◘3,250 women beneficiaries from resilient cropping practices ◘3,250 women beneficiaries from horticulture and horticulture sites | poor
Output 3.1.3 Sustainable fisheries are supported | Output | ◘Number of women accessing fishing sites ◘Number of trainings dedicated to women ◘Number of women equipped with fishing material and tools |  | ◘100 women accessing fishing sites ◘10 trainings dedicated to women ◘100 women equipped with fishing material and tools | poor
Output 3.1.4 Improved livestock production is supported | Output | ◘Number of women accessing veterinary services for various livestock owned (poultry to ruminants) ◘Number of women beneficiaries from small short-cycle livestock production ◘Number of trainings dedicated to women |  | ◘1,500 women accessing veterinary services for various livestock owned (poultry to ruminants) ◘3,250 women benefit from small short-cycle livestock production ◘160 trainings dedicated to women | poor
Output 3.2.2 Production of 6,500 targeted farmers (50% women) is diversified (crop diversification, beekeeping, fishing) | Output | ◘Number of farmer exchange visits between POs across the border dedicated to women ◘Number of women accessing diversified production activities ◘Number of women beneficiaries from processing equipment ◘Number of women accessing all stages of value chain ◘Number of training sessions dedicated to women |  | ◘10 farmer exchange visits between POs across the border dedicated to women ◘160 training sessions dedicated to women 3,250 women accessing diversified production activities ◘350 women benefit from processing equipment ◘3,250 women accessing all stages of value chain | poor
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | In order to ensure that the GP safeguards are addressed, the IE conducted: ◘Reviewing the terms of reference, the no-objection mechanism, concept notes, etc. to ensure the gender lense is considered ◘Engaged with the EE during sensitization of the actors on the respect of the parity between men and women during the consultation meetings ◘Monitored that Field visits to assess the implementation of GP actions were considered ◘Developed and disseminated tools that included gender and age pyramid identification in reporting
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes but with some challenges due to capacity needs of the EEs
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | During the different sensitization and awareness workshops and sessions, the EE required the participation of different categories of the local population, including women, young, aged people, PLWD etc. using a selection criteria where necessary to identify and ensure cross-cutting participation.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | During the different sensitization and awareness workshops and sessions, the EE required the participation of different categories of the local population, including women, young, aged people, PLWD etc using a selection criteria to identify and ensure cross-cutting participation i.e., 1. the project targets to achieve at least 40% women beneficiaries in each intervention through engendering the project 2. the project has ensured solid participation and benefit on the part of youth particularly girls 3. gender-transformative approach has been mainstreamed in implementation 4. Mechanisms to manage potential risks to the promotion of gender equality and the empowerment of women as well are also identified
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No, during the reporting period no capacity gaps have been identified to hinder execution. To note, the baseline and KAP survey are underway and the findings shall be included in the next PPR.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances have been received and recorded during this reporting period. According to OSS processes, identified and substansive grievances will be reported when they occur and the applicable procedures undertaken to address and resolve the grievance.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Outcome 1.1. Enhanced awareness and ownership of adaptation and climate risk reduction processes of the targeted populations |  | Outcome 3 |  | ◘Rehabilitation or construction of the CCACs ◘Establishment of institutional capacities to manage the CCACs ◘Development of Community Adaptation Action Plans (CAAPs) |  | ◘Identification and agreement on land for setting up of the CCACs demonstration plots is ongoing with land for 3 CACCS identified. ◘Concept note for CAAPs has been developed and is being finalized. | S
| Outcome1.2. Enhanced capacity at sub-national, national and regional level to adapt to climate change risks and variability inthe agriculture and water sectors |  | Outcome 2 |  | ◘Development of a communication strategy for CC information and dissemination ◘Organize climate change awareness campaigns in target communities ◘Organize climate change awareness campaigns in schools through the Green School Programme ◘Disseminate project results, best practices and lessons learned |  | ◘Concept note for the communication strategy has been drafted and is being finalized ◘Climate change awareness campaigns in target communities will follow the setting up of Activity teams, which is ongoing ◘Identification of the schools to undertake the GSP is underway within the project sites and identification of Climate champions teachers is underway | S
| Outcome 2.1. Established and strengthened community-based and farmer-based organizations for agricultural production and water management |  | Outcome 4 |  | ◘Conduct baseline and capacity needs assessment of all actors ◘Development of a training plan and training modules for all topics ◘Establishing partnership and Memorandum of Understanding (MoU) with the subnational extension services ◘Train the extension agents and field instructors to ensure farmer trainings ◘Conduct KAP surveys |  | ◘The baseline and capacity needs assessment of all actors has been initiated and will be followed by the CNA and this will allow for the development of a training plan and training modules for all topics. | MS
| Outcome 2.2. Enhanced technical capacity of smallholder farmers and technical staff to adopt and mainstream climateresilient agricultural practices |  | Outcome 4 |  | ◘Training and sensitization of the lead farmers in each of 160 POs ◘Organize with the support of the extension services sensitization sessions ◘Set up the demonstration plots and procure inputs for their establishment and management |  | ◘The process of identifying and recruiting the POs has been initiated | MS
| Outcome 3.1. Resilience of populations and ecosystems improved through concrete adaptation measures |  | Outcome 6 |  | ◘Identify and select the most viable water solutions for production ◘Provide inputs to farmers to implement infrastructure for production, water capture and retention systems at farmers’ fields ◘Establish models for water collection for human consumption ◘Promote solar powered water pumps and small-scale irrigation systems ◘Conduct community campaigns for safe water use and water demand management |  | This has not been intitiated | U
| Outcome 3.2. Resilience of populations' livelihoods is increased and sustained through Income Generating Activities (IGAs) |  | Outcome 6 |  | ◘Development and promotion of non-agricultural sources of income ◘Facilitate access to micro-credits for farmers and POs to adopt new IGAs ◘Development of public private partnerships (PPPs) to improve links to the market ◘Organize exchange visits between POs across the border to facilitate experience sharing |  | This has not been intitiated | U
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mrs. Khaoula JAOUI
| Email: | khaoula.jaoui@oss.org.tn
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
In its first year, the project can be considered Marginally Satisfactory. The project regional kick-off workshop was held on March 15th, 2022, and the project execution commenced Given that this is a regional project, the delay has been recorded at all levels, some highlights for this period are summarized and presented below: • Establishing a common understanding of the project philosophy between the Executing Entities was the first challenge during this period. This included the establishment of an agreement towards the roles and responsibilities as well as the renumeration of the PMUs members. It also constitutes a challenge during the recruitment process to get the right candidate for these positions due to different aspects including the country's context. • The participatory approach was adopted to allow the PMUs to agree on a common understanding of the project philosophy to guide their operations and to strengthen their capacities towards the project ownership using formulas such as bi-weekly meetings and other reporting avenues such as monthly interim financial reports, technical back stoppers inter alia • Based on the recorded project activities’ execution delays, project relevant measures have been put in place such as the engaging and onboarding multilingual members to the PMUs, in order to facilitate the fast tracking of activities and to align the two national entities as well as the Regional PMU to be able to coordinate and move at par. As a general recommendation to clear the backlog it was agreed on the development of a rapid response initiatve and a fast tracked option for all year one activities.The entities developed action plans with guidance from the RIE covering year 1 and year 2 activities for fast tracking. Project Coordination and Management: The PMUs has effectively started the execution on the ground and the RIE has provided them with an additional capacity building through technical and financial sessions. This is expected to accelerate the progress of project activites execution.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
REE Regional Coordinator: | Outcome 1.1. Enhanced awareness and ownership of adaptation and climate risk reduction processes of the targeted populations; |  | Outcome 3 |  | ◘Rehabilitation or construction of the CCACs ◘Establishment of institutional capacities to manage the CCACs ◘Development of Community Adaptation Action Plans (CAAPs) |  | ◘Land for the Construction of the Calai CCAC is identified and tehcnical drawings are being taken. ◘Recruitment process is set to start as soon as the ToR of the activity team is approved by OSS. ◘Community Adaptation Action Plans (CAAPs) are set to be developed after the baseline and KAP | Satisfactory (S)
| Outcome1.2. Enhanced capacity at sub-national, national and regional level to adapt to climate change risks and variability inthe agriculture and water sectors; |  | Outcome 2 |  | ◘Development of a communication strategy for Cc information and dissemination ◘Organize climate change awareness campaigns in target communities ◘Organize climate change awareness campaigns in schools through the Green School Programme ◘Disseminate project results, best practices and lessons learned |  | ◘The communication strategy is being developed in-house by ADPP. ◘107 communities have being identified out of 120 communities originally intended in Angola. ◘The green school program is also being developed in-house by ADPP. | Marginally unsatisfactory (MU)
| Outcome 2.1. Established and strengthened community-based and farmer-based organizations for agricultural production and water management; |  | Outcome 4 |  | ◘Conduct baseline and capacity needs assessment of all actors ◘Development of a training plan and training modules for all topics ◘Establishing partnership and Memorandum of Understanding (MoU) with the subnational extension services ◘Train the extension agents and field instructors to ensure farmer trainings Conduct KAP surveys |  | ◘Baseline ToR and CN was sent to OSS. Waiting for approval in order to carry out these activities. ◘Training plan will start with the baseline training. MoU are being developed and will be shared as soon as it is completed. ◘KAP survey is expected to be taken alongside with the baseline. | Satisfactory (S)
| Outcome 2.2. Enhanced technical capacity of smallholder farmers and technical staff to adopt and mainstream climateresilient agricultural practices; |  | Outcome 4 |  | ◘Training and sensitization of the lead farmers in each of 160 Pos ◘Organize with the support of the extension services sensitization sessions ◘Set up the demonstration plots and procure inputs for their establishment and management |  | ◘Training will start as soon as the ToR of activity team and the CN of activity 2.1.2.1-2.1.2.2 are approved by OSS. Demontrations plots will be set up after the estblishement of the CCACs | Marginally unsatisfactory (MU)
| Outcome 3.1. Resilience of populations and ecosystems improved through concrete adaptation measures |  | Outcome 6 |  | ◘Identify and select the most viable water solutions for production ◘Provide inputs to farmers to implement infrastructure for production, water capture and retention systems at farmers’ fields ◘Establish models for water collection for human consumption Promote solar powered water pumps and small-scale irrigation systems ◘Conduct community campaigns for safe water use and water demand management |  | ◘This Outcome relies on the identifictation and establishment of PO and WUA. Results can be fast tracked as soon as the CN of activity 2.1.2.1-2.1.2.2 are approved by OSS | Satisfactory (S)
| Outcome 3.2. Resilience of populations' livelihoods is increased and sustained through Income Generating Activities (IGAs) |  | Outcome 5 |  | ◘Development and promotion of non-agricultural sources of income ◘Facilitate access to micro-credits for farmers and POs to adopt new IGAs ◘Development of public private partnerships (PPPs) to improve links to the market ◘Organize exchange visits between POs across the border to facilitate experience sharing |  | No actions were taken under this component | Unsatisfactory (U)
[7 empty] | Overall Rating | Marginally unsatisfactory (MU)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Valente Sabino
| Email: | valente.cangengo@adpp-angola.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
My rate was based in what we realistically managed to achieve. There are still a couple of activities waiting for approval in order to commence. If the ToRs and CN sent so far are approved as soon as possible, we can say that it is possible to have a better progress to achieve the desired outcomes during year 2. The positive progress is that we achieved to set up a great partnership with stakeholders, the negative impact is the slow progress the project is taking (delays in approvals). My recommendation is, as we agreed to fast track certain activities, in collaboration with the RIE which has to fast track their approval as well. Since we agreed to do so, the RIE has given us opportunities to progress through a participatory approach which can be sped up thinking of the progress to be achieved in the coming time.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
NEE Angola Coordinator: | Outcome 1.1. Enhanced awareness and ownership of adaptation and climate risk reduction processes of the targeted populations; |  | Outcome 3 |  | ◘Rehabilitation or construction of the CCACs ◘Establishment of institutional capacities to manage the CCACs ◘Development of Community Adaptation Action Plans (CAAPs) |  | We met with local government entities from 4 municipalities Cuangar, Calai, Dirico and Rivungo. we have identified the land for the construction of the CCAC in Calai and for the remains of the municipalities, this is in process and we believe that as soon as the team is installed on the land, we will conclude. slow due to the weak presence of the team on the ground. The design of the CCAC is in the finalization phase, the recruitment process is set to start once the activity team's ToR are approved. Community Adaptation Action Plans (CAAPs) should be developed after the baseline and CAP. | Unsatisfactory (U)
| Outcome1.2. Enhanced capacity at sub-national, national and regional level to adapt to climate change risks and variability inthe agriculture and water sectors; |  | Outcome 2 |  | ◘Development of a communication strategy for Cc information and dissemination ◘Organize climate change awareness campaigns in target communities ◘Organize climate change awareness campaigns in schools through the Green School Programme ◘Disseminate project results, best practices and lessons learned |  | ◘The communication strategy for CCAC information and dissemination is being developed by the executing entity. We identified 107 villages from the 120 communities initially planned for Angola, of which we approved 25 villages with the desired profile. ◘The green school program is also being developed internally by ADPP. | Satisfactory (U)
| Outcome 2.1. Established and strengthened community-based and farmer-based organizations for agricultural production and water management; |  | Outcome 4 |  | ◘Conduct baseline and capacity needs assessment of all actors ◘Development of a training plan and training modules for all topics ◘Establishing partnership and Memorandum of Understanding (MoU) with the subnational extension services ◘Train the extension agents and field instructors to ensure farmer trainings ◘Conduct KAP surveys |  | ◘This is in process, at the moment, ToR and CN of the baseline will be sent to OSS. Awaiting approval to carry out these activities. The training plan will start with baseline training. ◘The MoU is being developed and will be shared once it is completed. It is expected that the CAP survey will be carried out in conjunction with the baseline. | Unsatisfactory (U)
| Outcome 2.2. Enhanced technical capacity of smallholder farmers and technical staff to adopt and mainstream climateresilient agricultural practices; |  | Outcome 4 |  | ◘Training and sensitization of the lead farmers in each of 160 Pos ◘Organize with the support of the extension services sensitization sessions ◘Set up the demonstration plots and procure inputs for their establishment and management |  | The training ptograms, POS and WUA training strategy was created and the assembly of the demonstration plots will be done after the ToR of the activity team and the CN of activity 2.1.2.1-2.1.2.2 are approved by the OSS. | Unsatisfactory (U)
| Outcome 3.1. Resilience of populations and ecosystems improved through concrete adaptation measures |  | Outcome 6 |  | ◘Identify and select the most viable water solutions for production◘ ◘Provide inputs to farmers to implement infrastructure for production, water capture and retention systems at farmers’ fields ◘Establish models for water collection for human consumption ◘Promote solar powered water pumps and small-scale irrigation systems ◘Conduct community campaigns for safe water use and water demand management |  | After the mapping done in November to October of the year 2022 in 25 villages, the executing entity is in the process of developing strategies and systems that can promote water solutions for producers and families in the communities. CN and No were sent to the OSS for activities 2.1.2.1 and 2.1.2.2 with the aim of being approved. we believe we are ready to start and as soon as the teams are in the field and the activities are approved, we will make good progress in the second quarter of 2023. | Unsatisfactory (U)
| Outcome 3.2. Resilience of populations' livelihoods is increased and sustained through Income Generating Activities (IGAs) |  | Outcome 5 |  | ◘Development and promotion of non-agricultural sources of income ◘Facilitate access to micro-credits for farmers and POs to adopt new IGAs ◘Development of public private partnerships (PPPs) to improve links to the market ◘Organize exchange visits between POs across the border to facilitate experience sharing |  | No action was taken on this component | Unsatisfactory (U)
[7 empty] | Overall Rating | Unsatisfactory (U)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Eurico L.Virgilio
| Email: | Euricco.virgilio@adpp-angola.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
My ranking was based on the current state of activities, most of the activities that should have been done in the first year were not done, it still seems like we have a lot to do. I believe that the second year will be different but we have to join efforts to make reality the wish of the families that suffer and need to learn more about climate change and make them resilient and for this, we need to employ the work teams in the field, approvals of the activities in the right time. The positive point is that we have a close collaboration with the Angolan government, local entities and the interested parties are motivated for the work and also the regional, national launch was made, and the identification of 107 possible Producer Organization in the communities for the project. The negative point is the accentuated bureaucracy of the approval process for the team, activities and others, which can compromise other activities that depend on the seasons, as in the case of agricultural production and school programs. We need to find a means to start with the activities in practice and that is up to the implementing and executing entity to make them happen.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
NEE Namibia Coordinator: | Outcome 1.1. Enhanced awareness and ownership of adaptation and climate risk reduction processes of the targeted populations; |  | Outcome 3 |  | ◘Rehabilitation or construction of the CCACs ◘Establishment of institutional capacities to manage the CCACs ◘Development of Community Adaptation Action Plans (CAAPs) |  | ◘Two sites for the establishment of the CCACs has been endorsed by Traditional Athorities and Political leadership including key stakeholders in the Kavango East and West regions. ◘Institutional capacities with Regional councils, Traditional Authorities and key stakeholders has already been established as we await the recruitment of the activity staffs to manage the CCACs. ◘Development of CAAPs was not done , due to the fact that the activity staffs are not yet recruited. | Satisfactory (S)
| Outcome1.2. Enhanced capacity at sub-national, national and regional level to adapt to climate change risks and variability inthe agriculture and water sectors |  | Outcome 2 | Outcome 2 | ◘Development of a communication strategy for Cc information and dissemination ◘Organize climate change awareness campaigns in target communities ◘Organize climate change awareness campaigns in schools through the Green School Programme ◘Disseminate project results, best practices and lessons learned |  | ◘The communication strategy is being developed in-house by DAPP Namibia. 25 communities have being identified out of 40 communities originally intended for Namibia. ◘The green school program is also being developed in-house by DAPP Namibia. ◘8 schools have been identified, 3 in Kavango East and 5 in Kavango West regions. To be implemented at the end of the project. | Satisfactory (S)
| Outcome 2.1. Established and strengthened community-based and farmer-based organizations for agricultural production and water management; |  | Outcome 4 |  | ◘Conduct baseline and capacity needs assessment of all actors ◘Development of a training plan and training modules for all topics ◘Establishing partnership and Memorandum of Understanding (MoU) with the subnational extension services ◘Train the extension agents and field instructors to ensure farmer trainings ◘Conduct KAP surveys |  | ◘Baseline ToR and CN was sent to OSS waiting for approval . ◘Training plan will start with the baseline training. ◘MoU are being developed and will be shared as soon as it is completed. ◘KAP survey is expected to be undertaken alongside with the baseline. | Satisfactory (S)
| Outcome 2.2. Enhanced technical capacity of smallholder farmers and technical staff to adopt and mainstream climateresilient agricultural practices |  | Outcome 4 |  | ◘Training and sensitization of the lead farmers in each of 160 Pos ◘Organize with the support of the extension services sensitization sessions ◘Set up the demonstration plots and procure inputs for their establishment and management |  | ◘Training will start as soon as the ToR of activity team and the CN of activity 2.1.2.1-2.1.2.2 are approved by OSS. ◘Demontrations plots will be set up after the estblishement of the CCACs. | Marginally satisfactory (MS)
| Outcome 3.1. Resilience of populations and ecosystems improved through concrete adaptation measures |  | Outcome 6 |  | ◘Identify and select the most viable water solutions for production◘ ◘Provide inputs to farmers to implement infrastructure for production, water capture and retention systems at farmers’ fields ◘Establish models for water collection for human consumption ◘Promote solar powered water pumps and small-scale irrigation systems ◘Conduct community campaigns for safe water use and water demand management |  | ◘This Outcome relies on the identifictation and establishment of PO and WUA. ◘Results can be fast tracked as soon as the CN of activity 2.1.2.1-2.1.2.2 are approved by OSS | Marginally satisfactory (MS)
| Outcome 3.2. Resilience of populations' livelihoods is increased and sustained through Income Generating Activities (IGAs) |  | Outcome 5 |  | ◘Development and promotion of non-agricultural sources of income ◘Facilitate access to micro-credits for farmers and POs to adopt new IGAs ◘Development of public private partnerships (PPPs) to improve links to the market ◘Organize exchange visits between POs across the border to facilitate experience sharing |  | Activities not implemented because the activity staffs are not yet recruited to carry out the activities. | Marginally satisfactory (MS)
[7 empty] | Overall Rating | Marginally satisfactory (MS)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Lynnety Sinalumbu
| Email: | lynnety@dapp-namibia.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | My rate was based in what we reallistic managed to achieve. There is still a couple of activity waiting for OSS approval in order to start. If the ToRs and CN sent so far are approved as soon as possible, we can say that it is possible to have a better progress to achieve the desired outcomes during year 2. The positive progress is that we achieved to set up a great partnership with stakeholders, the negative impact is the slow progress the projet is taking (delays in approvals). My recommendation is, as we agreed to fast track certain activities through a conceited approval process.
| AF Outcomes |  |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective 1. To enhance capacities to adapt and respond to climate change risks in the crossborder area of Angola and Namibia; local, subnational and regional | ◘Percentage of the targeted population aware of the adverse impacts on climate change. | 0 |  | ◘At least 90% of the target population is aware of the adverse impacts on climate change ◘At least 80% of the targeted actors participating in regional information sharing platforms ◘ At least 70% of targeted smallholder farmers and pastoralists access and integrate EW information into seasonal calendars
Outcome 1.1 Awareness and ownership of adaptation and climate risk reduction processes of the target populations are enhanced. | ◘Number of operational CCACs ◘Number of schools integrated in the Green Schools Programme (GSP) ◘Number of Community Adaptation Action Plans (CAAPs) developed. | 0 | ◘CCAC sites identified: 2 Angola, 2 Namibia | ◘6 functional/ operational CCACs (4 in A; 2 in N) ◘40 schools integrated in the GSP (20 in A; 20 in N) ◘140 Community Adaptation Action Plans established (105 in A; 35 in N)
Output 1.1.1 Communities and local and district level stakeholders in the target area have participated in climate change adaptation and risk reduction awareness activities | ◘Number of Capacity building/trainings conducted ◘Number of Training manuals developed ◘Number of stakeholders trained | 0 | ◘Draft training manuals developed | ◘5 Annual Capacity building held /training reports produced. ◘1 training manual developed ◘90 staff trained (assuming same staff trained multiple times). ◘16 trainings conducted (4 dedicated to women)
Output 1.1.2 Climate change awareness and sensitization to communities | ◘Number of awareness campaigns in communities and schools ◘Number of students reached with the GSP ◘Number of knowledge products ◘Number of case studies and lessons learnt, documented, packaged and shared | 0 | ◘Draft communication plan elaborated | ◘At least 16 campaigns in 70% of targeted communities and schools ◘Students in 38 schools reached with the GSP (19 in A; 19 in N) (50% girls/women) ◘4 brochures, 4 publications (documents) developed on lessons and best practices from project interventions ◘At least 8 case studies/lessons learned shared.
Outcome 1.2 Capacity at subnational, national and regional level to adapt to climate change risks and variability in the agriculture and water sectors is enhanced. | ◘Proportion of institutions with enhanced capacity in food and water security and management | 0 |  | ◘At least 80% of targeted institutions at sub-national, national and regional level actively participate in the implementation of the project in climate responsive agriculture and water management.
Output 1.2.1 National and regional centresand networks to respond to extreme weather events have been established, reinforced and supported in their operation | ◘Number of transboundary mechanisms established ◘Number of meetings of transboundary mechanism that have taken place ◘Number of coordination meetings among 6 CCACs that have ◘Proportion of targeted farmers and pastoralists reached with conflict management trainings regarding transhumance ◘Number of of farmers that have accessed climate information | 0 |  | ◘1 transboundary mechanism established and operational ◘At least 8 meetings of transboundary mechanism have taken place ◘At least 8 meetings ◘At least 60% of targeted farmers and pastoralists reached with trainings ◘At least 5,000 farmers have accessed climate information (3,750 in A; 12,50 in N).
Objective 2 : To strengthen organizational and technical capacities for climate-resilient production and water management | ◘Number of community-based organizations with increased capacities for climate-resilient water management and agriculture production | 0 |  | ◘360 Organizations (240 in A; 120 in N) established and members trained in climate-resilient water management and agriculture production. ◘160 POs (120 in A; 40 in N) have gained access to model plots for CRA and CRA extension services ◘ At least 90% of targeted farmers and pastoralists trained
Outcome 2.1: Community- based and farmer based organizations for production and water management have been established and strengthened | ◘Number of Producer Organizations (POs) established and operational ◘Number of Water User Associations (WUAs) in the target areas that are operational ◘Proportion of targeted farmers with increased knowledge and skills in opportunities for agriculture and water management ◘Proportion of farmers engaged in productive agriculture and water management | 0 | ◘107 pre-selected POs in Angola and 24 have been engaged | ◘160 POs are operational (120 in A; 40 in N) ◘160 Water User Associations (WUAs) are operational in the target area representing 95 % of target population (120 in A; 40 in N) ◘At least 90% of targeted farmers have increased knowledge and skills in opportunities for agriculture and water management. ◘At least 80% of farmers engaged in productive agriculture and water management (50% women)
Output 2.1.1: Capacities of extension services and institutions needs are strengthened | ◘Number of partnership or MOUs developed with subnational extension services ◘Number of training plans developed ◘Number of extension agents and Farming instructors trained in CRA practices ◘Number of Farmer Field days conducted ◘Change in Knowledge, Attitudes and Practices |  |  | ◘1 partnership agreements/MOU per country ◘1 training plan developed per country ◘40 extension agents (20 in each country) and 34 Farming instructors trained. ◘At least 4 Farmer Field days per PO per year conducted. ◘There is significant change in Knowledge, Attitudes and Practices
Output 2.1.2: Communities are organized to adopt and mainstream climate-resilient agricultural practices (Conservation Agriculture and Agroforestry Systems) are established practices. | ◘Number of POs established ◘Number of POs participating/engaged in climate resilient agricultural (CRA) production ◘Number of POs governance structures supported Number of ◘Number of POs trained (storage facilities, business, and climate adaptive agriculture) ◘Number of legal and functional WUAs in place. ◘Number of WUAs participating/engaged in climate resilient water management ◘Number of WUAs trained (field level water management, water infrastructure, usage, equitable access etc.) | 0 | ◘107 pre-selected POs in Angola and 24 have been engaged | ◘160 POs established and supported (120 in A; 40 in N) ◘160 POs participating/ engaged in CRA production (120 in A; 40 in N) ◘160 POs governance structures supported (120 in A; 40 in N) ◘160 POs (120 in A; 40 in N) have completed training programmes in (storage facilities, business, and climate adaptive agriculture) ◘160 WUAs established/supported (120 in A; 40 in N) ◘160 WUAs functional (120 in A; 40 in N) ◘160 WUAs participating/engaged in climate resilient water management (120 in A;40 in N) ◘160 WUAs are fully operational in all trained aspects (120 in A; 40 in N).
Outcome 2.2 6,500 Smallholder farmers (50% women) have been trained and technically supported to adopt and mainstream climate-resilient agriculture practices | ◘ Proportion of smallholder farmers undertaking climate resilient agricultural practices (disaggregated by sex) ◘ Proportion of extension services engaged in dissemination of climate resilient agricultural practices | 0 |  | ◘At least 90% of smallholder farmers trained and supported of which 50% are women ◘At least 90% of extension staff engaged in training smallholder farmers.
Output 2.2.1 160 model plots (Farmer Field Schools) for climate-resilient and water efficient agriculture practices (Conservation Agriculture and Agroforestry Systems) are established | ◘ # of model field plots established ◘ # of lead farmers trained (disaggregated by sex) ◘ Proportion of targeted farmers applying new resilient practices (disaggregated by sex) ◘ # of model plots supported with inputs | 0 |  | ◘ 160 model plots/FFS established (120 in A; 40 in N) ◘ 700 lead farmers trained, of which 50% are women (525 in A; 175 in N) ◘ At least 80% of targeted farmers (50% women) applying new resilient practices ◘ 160 model plots (120 in A; 40 in N) supported with inputs
Objective 3. To improve food security in response to climate change impacts in rural and vulnerable communities in Cuando Cubango Province and the Regions of Kavango East and Kavango West; | ◘Proportion (%) of food secure households (HHs). ◘Proportion (%) of small-scale farmers with average >20% increased income. | 0 |  | ◘At least a 70% increase in the number of targeted HHs (50% women) that are food secure ◘3,900 HHs (50% women) with average >20% increase in income.
Outcome 3.1: Resilience of populations and ecosystems is improved through concrete adaptation measures | ◘Percentage (%) of targeted farmers accessing and using efficient water for production ◘Percentage (%) of targeted farmers with diversified farming systems ◘Number of farmers that have increased production of cereals, legumes and vegetables by at least 30% ◘Percentage (%) increase of targeted farmers owning small animals. | 0 |  | ◘At least 60% of targeted farmers accessing and using efficient water for production technologies ◘At least 60% of targeted farmers have diversified their farming systems to include at least one legume or vegetable crop ◘4,500 farmers have increased their crop production by at least30%; (3,375 in A; 1,125 in N). ◘30% increase in the number of cereals, legume and vegetable crops grown by targeted farmers. ◘40% increase in the number of small animals owned by targeted smallholder farmers.
Output 3.1.1: Target farmers and population access and use of water during the dry season are increased. | ◘Number of model water capture and retention systems established at farmers’ fields ◘Number of model water collection facilities for human consumption established ◘Number of solar powered water pumps and small-scale irrigation systems provided ◘Number of community campaigns for safe water use and water demand management ◘Proportion (%) of farmers undertaking safe water use and water demand management | 0 |  | ◘160 model water capture and retention systems at farmers’ fields established (120 in A; 40 in N) ◘6 model water collection facilities for human consumption per country. ◘160 solar powered water pumps and small-scale irrigation systems provided (120 in A; 40 in N) ◘At least 10 community campaigns for safe water use and water demand management are conducted in 70% of targeted communities. ◘At least 60% of targeted farmers undertaking safe water use and water demand management
Output 3.1.2: Climate resilient agriculture practices are promoted and adopted. | ◘Number of farmers practicing/adopted CA practices ◘Number of POs undertaking cropping practices resilient to climate change ◘Proportion (%) of farmers using drought resistant crops and seeds ◘Number of seed collection and multiplication centres developed ◘Number of horticulture production communal plots established | 0 |  | ◘At least 6,000 farmers (50% women) practicing/adopted CA practices (4,500 in A;1,500 in N). ◘160 POs undertaking cropping practices resilient to climate change (120 in A; 40 in N). ◘At least 40% of farmers using of a range of drought-resistant crops and seeds. ◘160 seed collection and multiplication schemes developed and functional (120 in A; 40 in N). ◘120 horticulture and horticulture production communal plots established (90 in A; 30 in N).
Output 3.1.3 Sustainable fisheries are supported | ◘Extent (%) to which community members have gained access to fishing sites. ◘Number of fisherwomen/men that have participated in trainings on sustainable fishing methods ◘Proportion (%) of targeted HHs that have gained access to improved equipment and materials. | 0 |  | ◘Community members have gained access to fishing sites ◘500 fisherwomen/men have participated in trainings on sustainable fishing methods (250 in each country) ◘30% increase among target HHs has gained access to improved fishing equipment and materials.
Output 3.1.4: Improved livestock production is supported | ◘Proportion (%) of farmers accessing veterinary services ◘Number of farmers engaged in short cycle livestock production ◘Proportion (%) of farmers supported in production of fodder for short cycle livestock ◘Number of sensitization campaigns to prevent potential conflicts arising from transhumance | 0 |  | ◘At least 70% of farmers accessing veterinary services and 60 % of targeted farmers vaccinate short-cycle livestock ◘60 % of targeted farmers vaccinate short-cycle livestock.(50% women engaged in short cycle livestock production ◘At least 60% of all PO member farmers engaged in short-cycle livestock production. ◘At least 40% of targeted farmers supported in production of fodder for short-cycle livestock. ◘20 sensitization campaigns to prevent potential conflicts arising from transhumance per country.
Outcome 3.2: Resilience of populations’livelihoods is increased and sustained through climate-resilient Income Generating Activities (IGAs) | ◘Percentage (%) of targeted HHs that have gained at least 1 additional climate resilient income stream ◘Percentage (%) of targeted HHs that has gained access to village loans or formal microcredits. | 0 |  | ◘50% of targeted HHs have at least 1 additional income stream. ◘75% of targeted HHs is accessing village loans or formal micro-credits.
Output 3.2.1: Income generating options of 6,500 farmers are diversified | ◘Proportion (%) of targeted farmers engaged in nonagricultural sources of income ◘Number of saving groups among farmers ◘Proportion (%) of farmers accessing micro-credits to adopt new income generating activities ◘Proportion (%)of farmers practicing post-harvest techniques, processing and good storage practices. ◘Number of public-private partnerships (PPPs) to improve links to the markets ◘Number of farmer exchange visits between POs across the border to facilitate experience sharing | 0 |  | ◘At least 40% of targeted farmers (of which 50% women) engaged in nonagricultural sources of income. ◘160 saving groups among farmers (120 in A; 40 in N). ◘At least 40% of farmers are accessing microcredits for farmers to adopt new IGAs. ◘At least 60% of farmers practicing post-harvest techniques, processing and good storage practices. ◘6 PPPs to improve links to the markets. ◘20 farmer exchange visits between POs across the border to facilitate experience sharing.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | •Early capacity building of the executing parties is critical. This enables teams to understand the project philosophy. •The involvement of stakeholders from different EEs requires proper coordination and support in terms of defining proper roles and responsibilities to each of them.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes, there was. Delays: •Understanding of concrete interventions on climate change-related activities. •Institutional arrangements related to EE operationalization •Development of detailed and itemized work plan and procurement plan Measures: •Development of project philosophy documentation as well as work sessions was initiated and is a continuous process. •Development of TORs and identification of relevant PMU members related to climate projects and occasions was undertaken •Approved work plan and procurement plan were developed and are living documents for execution of activities.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No changes were undertaken given that the concrete actions had not yet commenced.but there has been concerted engagement of the EEs to enhance the execution processes
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes. Up to date, the environmental and social safeguards have been adequate as no concrete actions have been undertaken and thus no negative impacts have emerged as of this reporting period.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Yes. •The project made deliberate efforts to ensure gender inclusion in the various levels of stakeholders during this reporting period where a selection criteria guide as well as the AF15 principles and FPIC process was taken into account to ensure engendering of the project implementation towards fostering equal participation of men and women in institutions and decision-making processes related to the project.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A - to be filled at mid-term and project completion.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A - to be filled at mid-term and project completion.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A - to be filled at mid-term and project completion.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A - to be filled at mid-term and project completion.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A - to be filled at mid-term and project completion.
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A - to be filled at mid-term and project completion.
What measures are being/could have been put in place to improve project/program results? | N/A - to be filled at mid-term and project completion.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | N/A - to be filled at mid-term and project completion.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | N/A - to be filled at mid-term and project completion.
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | N/A - to be filled at mid-term and project completion.
If learning objectives have been established, have they been met? Please describe. | N/A - to be filled at mid-term and project completion.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A - to be filled at mid-term and project completion.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A - to be filled at mid-term and project completion.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | N/A - to be filled at mid-term and project completion.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | AFR/RIE/Rural/2019/PPC/1
Implementing Entity | Sahara and Sahel Observatory
Type of implementing entity | RIE
Country | Angola | Namibia
Region | Africa
Sector | Food security
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
|  |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 182500 | 42500 | 140000 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 53.1% | 54% | 52.8% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 13.1% | 14% | 12% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
|  | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 2: Partially effective | Total | 182500 | Drought | 4: Effective | Total |  |  |  | Total
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | % of female targeted | 0% |  |  | % of female targeted | 53.1% |  |  | % of female targeted |  |  |  | % of female targeted
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  |  | Food security | Regional | 2: Undertaking or updating of assessments in progress |  | Food security | Regional | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Regional |  | 3: Dissemination and communication | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | National |  | 3: Dissemination and communication | Geographical coverage | National |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 15 |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | National |  | 3: Dissemination and communication | Geographical coverage | National |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 15 |  |  | Number of municipalities | 15 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
|  | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
|  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks
|  | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality
|  | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
|  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses
|  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | 0 | 0% | 2: Partially not aware |  | 182500 | 53% | 4: Mostly aware
|  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | 0 | 20% to 39% | 2: Partially not aware |  |  | 40% to 60% | 4: Mostly aware
|  | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | Training manuals | National |  | 4 | Training manuals | National
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
|  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Food security | Regional | 2: Partially responsive (Lacks most elements) |  | Food security | Regional | 4: Mostly responsive (Most defined elements)
|  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Water management | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Other | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Other | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change
|  | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
|  | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
|  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies
|  | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
Core Indicator 6.1.2: Increased income, or avoided decrease in income
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
|  | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks
|  | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced
|  | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
Select | 5: All |  |  |  |  | 3: Some |  |  | Fishing | Personal capital
1 | 4: Almost all | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
2 | 3: Half | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
3 | 2: Some | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
4 | 1: None | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
[6 empty] | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
Asia-Pacific | NIE | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Latin America and Caribbean | RIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Africa | MIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Eastern Europe |  |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
| ha protected |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha rehabilitated | [6 empty] | Training Centres
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Angola | km rehabilitated | [5 empty] | Policy/regulatory reform | Drinking water systems
Albania |  | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Argentina |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Armenia | Forests | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Antigua and Barbuda | Mangroves | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Azerbaijan | Coasts |  |  |  |  | Education policy | Mangrove reforestation
Burundi | Rangelands |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Benin | Cultivated land/Agricultural land |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Bangladesh | Protected areas/National parks |  | From 5% to 10% |  |  | Health policy | Erosion control
Bulgaria | Other |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bahrain |  |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahamas, The |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bosnia and Herzegovina |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Belarus |  |  | Above 50% |  |  | Monetary policy | Water storage
Belize | [5 empty] | Population policy | ICT and information dissemination
Bolivia | [5 empty] | Private policy
Brazil | [5 empty] | Public policy
Barbados | [5 empty] | Science policy
Bhutan | [5 empty] | Social policy
Botswana |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Central African Republic |  | describe |  |  |  | Urban policy
Chile |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
China, People's Republic of |  | describe |  |  |  | Other policy
Cote d'Ivoire |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cameroon |  | describe
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
|  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated
|  | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated
|  | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness