## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | April 2021 to March 2022
| Project Title: | Adapting to Climate Change through Sustainable Integrated Watershed Governance in Indigenous People of Ammatoa Kajang Customary Area in Bulukumba Regency, South Sulawesi Province, Indonesia
| Project Summary: | The overall main objective is to enhance climate resilience and build adaptive capacity toward climate change for vulnerable community through sustainable integrated watershed governance in Indigenous People of Ammatoa Kajang Customary Area in Bulukumba, South Sulawesi Province yang berfokus pada empat tujuan; 1) Reduced climate change vulnerability and risk by improving management and governance of watersheds in Indigenous People of Ammatoa Kajang customary area in Bulukumba, 2) Enhanced resilience of people in Indigenous People of Ammatoa Kajang customary area with climate adaptive sustainable livelihood development and climate mitigation actions, 3) Advanced Sustainable Integrated Watershed Governance adaptive to Climate Change on regency development planning and development budgeting in Bulukumba regency, 4) Raising awareness and Increased knowledge of local people on the importance of watershed and climate change impact. During a year of the project, it has succeeded in establishing a Watershed Management Coordination Forum in Bulukumba Regency with 50 parties involved (Provincial government agencies, related Ministries offices, Regency Governments, Academics, Business Actors, Community members and representatives, Non-Governmental Organizations. The structure of the DAS Forum consists of the Council of Trustees/gurantee, Experts, Technical Coordinators, Field Coordinators and Governing Councils. There are 46 board members with a presentation of 74% male and 26% female. In addition, currently, the process of drafting RP-DAS (watershed management plan document) in the Apparang, Raowa and Baonto watersheds is planned to be completed in June-July 2022. At the village level, agroforestry nurseries are underway in 11 villages with a total of 110,000 seeds of trees, with 10,000 trees per village. The types of plants that are planted are adjusted to the needs of the community. The seeds will be planted in the Agroforestry demonstration plots in 11 project villages, the rest will be distributed to the community. The planting is planned to be carried out at the end of April to May 2022. Climate Resilient Women Groups have been formed in 14 project villages (one women group in each village with 25 women members). Currently, women's groups have been practicing house yard gardening as an initiative of building family food self-sufficiency and food resilience. The RPJMDes (village development planning) revision has been implemented in two villages namely Pantama Village and Dwi Tiro Village and is currently in the process of revising the RPJMDes in the three other villages namely Bonto Baji Village, Lolisang Village and Tugondeng Village. Other villages are waiting for the election of village heads. The RPJMDes revision process is in collaboration with the Bulukumba District Environment and Forestry Service, the Village and Community Empowerment Service (DPMD), and the Village Facilitator from the Bulukumba District P3MD (village empowerment program). In addition, there has also been a public consultation on the development planning of the Pro-Climate Change Adaptation Village (RPJMDes) in Dwi Tiro Village.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | KEMITRAAN | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Indonesia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Target sites 14 villages in 4 Sub-districts: 1. Sub-district Bulukumpa (Villages: Kambuno, Jawi-Jawi, and Jojjolo) 2. Sub-district Kajang ( Villages: Desa Pattiroang, Tanah Towa, Batunilamung, Malleleng, Bonto Baji, Possi Tanah, Tambangan, Pantama dan Lolisang) 3. Sub-district Herlang (Tugondeng Village) 4. Aub-district Bonto Tiro (Dwi Tiro Village) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2020-09-23
IE-AFB Agreement Signature Date: |  | 2020-12-21 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2021-04-01 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2022-04-01
2023-04-01
Original Completion Date:
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | - | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Dewi Rizki | Dominican Republic
| Email: | dewi.rizki@kemitraan.or.id | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Ir. Laksmi Dhewanthi, M.A. | Equatoral Guinea
| Email: | ldhewanthi@menlhk.go.id | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Laode M. Syarif, PhD | Fiji
| Email: | laode.syarif@kemitraan.or.id | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Karno B. Batiran | Georgia
| Email: | karnobatiran@payopayo.or.id | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [insert date] |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [March 31, 2022] | 342847 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | Uncommitted figures not yet disbursed to executing entities to date = USD 772,676 (exclude budget audit in PEC ) |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Activity 1.1.1.1 Project Team Orientation | 731.4556
| Activity 1.1.1.2 Program socialization & Kickoff | 1337.0493
| Activity 1.1.1.3 Series of multi stakeholder workshop for establishing watershed management coordination forum and formulating forum workplan | 4942.4963
| Activity 1.1.1.4 Watershed management multistakeholder coordination forum legalization | 1234.7421
| Activity 1.1.2.1 Workshop on preparation for study for formulating integrated watershed management plan and climate adaptation action plan | 1308.1211
| Activity 1.1.2.2 Workshop for making instrument for study for formulating integrated watershed management plan and climate adaptation action plan | 3921.1882
| Activity 1.1.2.3 Etnography, institutional analisys, Policy Analysis, Sustainable livelihood analysis, secondary data study on watershed area | 3921.1882
| Activity 1.1.2.4 Conservation and biodiversity study on the Watershed area | 3921.1882
| Activity 1.1.2.5 Assesment PES (payment ecosystem services) | 4222.818
| Activity 1.1.2.6 Resilience, vulnerability assesment on disaster and climate change impact | 4222.818
| Activity 1.1.2.7 Land use assesmnet (FGD on land use history of village and watershed area) | 3921.1882
| Activity 1.1.2.8 Establishment of participatory land use mapping team | 5136.5272
| Activity 1.1.2.9 Participatory mapping training | 5531.6447
| Activity 1.1.2.10 Land use participatory mapping | 48404.5015
| Activity 1.1.2.11 Area and village land use map making | 16067.0641
| Activity 1.1.2.12 Workshop on land use mapping result | 2569.6747
| Activity 1.1.2.13 Workshop on preparation of integrated watershed management plan document framework and climate adaptarion action plan formulation | 1582.5866
| Activity 1.1.2.14 Series of workshop on formulating integrated watershed management plan and climate change adaptation action plan | 2685.3877
| Activity 1.1.2.15 Public consultation integrated watershed management and climate change adaptation action plan document | 0
| Activity 1.1.2.16 Evaluation | 0
| Activity 2.1.1.1 Agroforestry field school | 28483.7367
| Activity 2.1.1.2 Agroforestry Demonstration plot making | 34925.5627
| Activity 2.1.1.3 Establishment of Climate resilience women group (14 villages) | 5136.5272
| Activity 2.1.1.4 Series of FGD with climate resilience women group at 14 villages (3 times each village) | 15409.5816
| Activity 2.1.1.5 Yard gardening field school | 27263.1059
| Activity 2.1.1.6 Yard gardening implementation by climate resilience women group at 14 villages | 24694.8423
| Activity 2.1.1.7 Biomass stove procurement for women group at 14 villages | 0
| Activity 2.1.1.8 Training on using biomass stove for women group at 14 villages | 0
| Activity 2.1.1.9 Goat Livestock field school | 0
| Activity 2.1.1.10 Goat procurement for farmer group | 0
| Activity 2.1.1.11 Goat stall/shelter making | 0
| Activity 2.1.1.12 Training on making organic fertilizer from goat dunk | 0
| Activity 2.1.1.13 Field School on System of Rice Intensification (SRI) | 0
| Activity 2.1.1.14 SRI Practicing/implementation | 0
| Activity 2.1.1.15 FGD with farmers for Seed bank preparation | 0
| Activity 2.1.1.16 Seed bank development | 0
| Activity 2.1.1.17 Field school banana cultivation | 0
| Activity 2.1.1.18 Banana cultivation | 0
| Activity 2.1.1.19 Series of integrated pest management (6x) | 0
| Activity 2.1.2.1 Soil and water conservtion training | 0
| Activity 2.1.2.2 Terasering demonstration plot for soil and water conservation | 0
| Activity 2.1.2.3 Evaluation | 0
| Activity 3.1.1.1 Series of discussion of multisatkeholders watershed management coordination forum to formulate and finalizing regent regulation on integrated watershed management and climate adaptation action plan(10 times) | 0
| Activity 3.1.1.2 Public consultation of regent regulation on integrated watershed management and climate adaptation action plan of Bulukumba regency | 0
| Activity 3.1.1.3 legalization of Regent regulation on Integrated watershed management and climate adaptation action plan | 0
| Activity 3.1.2.1 Formation of revision team / draft maker of Pro Climate Change Adaptation Village development planning (RPJMDes) at 14 villages. | 1104.9178
| Activity 3.1.2.2 Series of discussions and finalization of revision / drafting of Pro Climate Change Adaptation Village development planning (RPJMDes) at 14 villages. | 6771.3258
| Activity 3.1.2.3 Public consultation of Pro Climate Change Adaptation Village development planning (RPJMDes) | 698.5113
| Activity 3.1.2.4 Roadshow to internalize the integrated watershed management framework to the provincial government development plan (Governor, Bappeda, DLHK, BP-DAS LH) | 0
| Activity 3.1.2.5 Evaluation | 0
| Activity 4.1.1.1 KAP Baseline and end line survey | 15058.2093
| Activity 4.1.1.2 Awareness rising campaign | 0
| Activity 4.1.1.3 Academic writing and project lesson learnd book | 0
| Activity 4.1.2.1 villagers discussion forum on watershed management and climate change | 0
| Activity 4.1.2.2 project dissemination seminar | 0
| Activity 4.1.2.3 Evalualuation | 0
| A. Project/Program Excecution Cost | 40779.788
| B. Project Cycle Managemet Services | 26858.9586
| TOTAL | 342846.7069 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Activity 1.1.1.1 Project Team Orientation | -0.1123 | 2023-03-31
| Activity 1.1.1.2 Program socialization & Kickoff | 1527.5029 | 2023-03-31
| Activity 1.1.1.3 Series of multi stakeholder workshop for establishing watershed management coordination forum and formulating forum workplan | 807.5037 | 2023-03-31
| Activity 1.1.1.4 Watershed management multistakeholder coordination forum legalization | 71.228 | 2023-03-31
| Activity 1.1.2.1 Workshop on preparation for study for formulating integrated watershed management plan and climate adaptation action plan | 75.461 | 2023-03-31
| Activity 1.1.2.2 Workshop for making instrument for study for formulating integrated watershed management plan and climate adaptation action plan | 545.2297 | 2023-03-31
| Activity 1.1.2.3 Etnography, institutional analisys, Policy Analysis, Sustainable livelihood analysis, secondary data study on watershed area | 545.2297 | 2023-03-31
| Activity 1.1.2.4 Conservation and biodiversity study on the Watershed area | 545.2297 | 2023-03-31
| Activity 1.1.2.5 Assesment PES (payment ecosystem services) | 243.5999 | 2023-03-31
| Activity 1.1.2.6 Resilience, vulnerability assesment on disaster and climate change impact | 243.5999 | 2023-03-31
| Activity 1.1.2.7 Land use assesmnet (FGD on land use history of village and watershed area) | 545.2297 | 2023-03-31
| Activity 1.1.2.8 Establishment of participatory land use mapping team | 296.3086 | 2023-03-31
| Activity 1.1.2.9 Participatory mapping training | 319.1016 | 2023-03-31
| Activity 1.1.2.10 Land use participatory mapping | 4282.0656 | 2023-03-31
| Activity 1.1.2.11 Area and village land use map making | 1820.9956 | 2023-03-31
| Activity 1.1.2.12 Workshop on land use mapping result | 260.176 | 2023-03-31
| Activity 1.1.2.13 Workshop on preparation of integrated watershed management plan document framework and climate adaptarion action plan formulation | 94.6522 | 2023-03-31
| Activity 1.1.2.14 Series of workshop on formulating integrated watershed management plan and climate change adaptation action plan | 57288.866 | 2023-03-31
| Activity 1.1.2.15 Public consultation integrated watershed management and climate change adaptation action plan document | 3215.2985 | 2023-03-31
| Activity 1.1.2.16 Evaluation | 343.2836 | 2023-03-31
| Activity 2.1.1.1 Agroforestry field school | 22165.517 | 2023-03-31
| Activity 2.1.1.2 Agroforestry Demonstration plot making | 10223.691 | 2023-03-31
| Activity 2.1.1.3 Establishment of Climate resilience women group (14 villages) | 296.3086 | 2023-03-31
| Activity 2.1.1.4 Series of FGD with climate resilience women group at 14 villages (3 times each village) | 888.9259 | 2023-03-31
| Activity 2.1.1.5 Yard gardening field school | 1572.715 | 2023-03-31
| Activity 2.1.1.6 Yard gardening implementation by climate resilience women group at 14 villages | 1424.5607 | 2023-03-31
| Activity 2.1.1.7 Biomass stove procurement for women group at 14 villages | 19589.5522 | 2023-03-31
| Activity 2.1.1.8 Training on using biomass stove for women group at 14 villages | 7235.0746 | 2023-03-31
| Activity 2.1.1.9 Goat Livestock field school | 104138.0597 | 2023-03-31
| Activity 2.1.1.10 Goat procurement for farmer group | 77940.2985 | 2023-03-31
| Activity 2.1.1.11 Goat stall/shelter making | 33380.597 | 2023-03-31
| Activity 2.1.1.12 Training on making organic fertilizer from goat dunk | 8358.209 | 2023-03-31
| Activity 2.1.1.13 Field School on System of Rice Intensification (SRI) | 58550.3731 | 2023-03-31
| Activity 2.1.1.14 SRI Practicing/implementation | 2942.9104 | 2023-03-31
| Activity 2.1.1.15 FGD with farmers for Seed bank preparation | 2085.8209 | 2023-03-31
| Activity 2.1.1.16 Seed bank development | 6791.0448 | 2023-03-31
| Activity 2.1.1.17 Field school banana cultivation | 42582.0896 | 2023-03-31
| Activity 2.1.1.18 Banana cultivation | 20320.8955 | 2023-03-31
| Activity 2.1.1.19 Series of integrated pest management (6x) | 45578.3582 | 2023-03-31
| Activity 2.1.2.1 Soil and water conservtion training | 10231.3433 | 2023-03-31
| Activity 2.1.2.2 Terasering demonstration plot for soil and water conservation | 2552.2388 | 2023-03-31
| Activity 2.1.2.3 Evaluation | 343.2836 | 2023-03-31
| Activity 3.1.1.1 Series of discussion of multisatkeholders watershed management coordination forum to formulate and finalizing regent regulation on integrated watershed management and climate adaptation action plan(10 times) | 7919.403 | 2023-03-31
| Activity 3.1.1.2 Public consultation of regent regulation on integrated watershed management and climate adaptation action plan of Bulukumba regency | 3177.9851 | 2023-03-31
| Activity 3.1.1.3 legalization of Regent regulation on Integrated watershed management and climate adaptation action plan | 652.9851 | 2023-03-31
| Activity 3.1.2.1 Formation of revision team / draft maker of Pro Climate Change Adaptation Village development planning (RPJMDes) at 14 villages. | 1621.9479 | 2023-03-31
| Activity 3.1.2.2 Series of discussions and finalization of revision / drafting of Pro Climate Change Adaptation Village development planning (RPJMDes) at 14 villages. | 43362.2563 | 2023-03-31
| Activity 3.1.2.3 Public consultation of Pro Climate Change Adaptation Village development planning (RPJMDes) | 9644.7723 | 2023-03-31
| Activity 3.1.2.4 Roadshow to internalize the integrated watershed management framework to the provincial government development plan (Governor, Bappeda, DLHK, BP-DAS LH) | 2791.0448 | 2023-03-31
| Activity 3.1.2.5 Evaluation | 343.2836 | 2023-03-31
| Activity 4.1.1.1 KAP Baseline and end line survey | 16285.0743 | 2023-03-31
| Activity 4.1.1.2 Awareness rising campaign | 7623.1343 | 2023-03-31
| Activity 4.1.1.3 Academic writing and project lesson learnd book | 7835.8209 | 2023-03-31
| Activity 4.1.2.1 villagers discussion forum on watershed management and climate change | 2216.4179 | 2023-03-31
| Activity 4.1.2.2 project dissemination seminar | 1865.6716 | 2023-03-31
| Activity 4.1.2.3 Evalualuation | 343.2836 | 2023-03-31
| A. Project/Program Excecution Cost | 62947.1814 | 2023-03-31
| B. Project Cycle Managemet Services | 61275.8692 | 2023-03-31
| TOTAL | 782168.4487 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
Note: | [7 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Formulas:
Est. Completion Date = '[1]Financial Data'!$[Est. Completion Date]

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Multi-stakeholders Climate Change Adaptation and Watershed Management Forum cannot be established | Low | Intensive approach to all respective stakeholders and comprehensive and intensive discussion on the importance of the forum with all stakeholders. It will also involve the head and vice head of regency as the local authority.
Stakeholder do not understand the importance of landscape based approach toward watershed management. | Medium | Intensive discussion series involving all respective stakeholders both formal and informal discussion, and awareness rising continuously done by the project facilitators during their stay at the field/site. Project facilitators required to live in at the villages where the project being implemented.
Region-based and Sectoral egoism among stakeholders | Medium | Stakeholder engagement to have the same perspective on watershed management and the risk of climate change. It can be done through discussion involving all stakeholders. Finding the crosscutting issues that will bridge the interest of all stake holders. Improving awareness of all stakeholders that the watershed landscape is inter-connected.
Community refused to get involved in the program | Low | There should be community engagement at the initial phase of the program. The project facilitators are required to live in at the villages project site. The approach should involve communities in organizing strategy.
It is difficult to find the land for demonstration plot | Low | There should be community engagement at the initial phase of the program. The project facilitators are required to live in at the villages project site. Community involvement approach should be used in organizing strategy.
The regency offices not willing to commit for pro climate budgeting for their programs. | Medium | Engagement (approach and lobby) to the regency development agency and the head of district and vice head of district.
Technology is not available and not suitable for activities that need technology input | Low | The technology that will be introduced are the appropriate technologies. The suitability will be tested before-hand.
Synchronization with village mid-term development plan is difficult | Medium | Include the formulation of annual village development budgeting into the project’s programs.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
COVID-19 pandemic outbreak | High | Changing the approach of doing activities, for example reducing meeting participants. The maximum number of participants is 25 people. Activities involving more than 25 meeting participants will be divided into two or three meetings.
There is a gap on the regulations that are used as the legal base for the establishment of the Watershed Forum between Governor Regulation No. 31 2020 and Minister of Forestry Regulation No. 61 2013, and Government Regulation 37 2012. | High | Review has been carried out and consultation with relevant parties has been done to determine which regulation must be served as the legal base for the establishment and legalization of the Watershed Forum.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
At the beginning of the process of establishing the Watershed Forum, it was delayed due to a regulatory gap regarding the reference for the establishment and legalization of the Watershed Forum. in the initial design in the proposal, the legalization of the Watershed Forum refers to government regulation no. 37 of 2012 concerning Watershed Management and Minister of Forestry Regulation No. P.61/Menhut-II/2013 concerning the Watershed Management Coordination Forum which only requires the Regency to legalize the Regency Watershed Forum. However, during the discussions and examination were carried out with stakeholders, it was found that there has been Governor's Regulation Number 31 of 2020 concerning the Watershed Management which mandates the legalization of the regency level watershed forum should be by the Governor (provincial level). Therefore, it was agreed by the stakeholders (districts and provinces) that the legalization of the Watershed Forum refers to the Governor's regulation number 31 of 2020. Another challenge was the change of the village. One of the project village, the lembanna village was not willing to become a project village and withdrew as the project village due to internal problems of the village government. Consequently we ask for the change to the one of the project village. The approval for the change affecting the execution of the project activities, there have been delay at the replacement village. To anticipate the left behind activities at the new village, During the process of the approval the project team have made some preparation such as have initial discussion with village government and community members that would help to accelerate the activities once the change approved.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity
3 – Marginalized and vulnerable Groups
4 – Human rights |  |  | there has been concern about female circumcision practice at project target sites | The project have ensured that communities whom participate on the project activities (beneficiaries) are not practicing the ritual. This is categorized as low impact and risk. | Monitoring is carried out by the executing entity to ensure that no female circumcision practice is carried out by project beneficiaries |  | Each activity carried out have been monitored for the possibility of the project beneficiaries practice the female circumcision
5 – Gender equality and women’s empowerment |  |  | 1. Possibility of widening knowledge and capacity gaps between women and men 2. Possibility of creating a double burden for women due to involvement in program activities | The project design have emphasized on the equal opportunities to get benefit from the project for all groups including women and men. With participatory way, using gender analysis and gender stakeholder consultation the project will ensure the involvement and participation of the women in the implementation of the project by, not only give portion of women participation (minimum 30%) in all relevant project activities, but also design several specific activities for women, such as field school on yard gardening and workshop on the women role on the climate change adaptation action, etc., such activities are to ensure the equality and empowerment for women group. The project will ensure women engagement in several key project activities, such as participatory mapping and watershed management forum. The beneficiary unit of the project is also the household, the project will guarantee that the representation of the households should be not less than 30% are women. | 1. Number of women involved in the management of the DAS Forum; 2. Number of woman engage in capacity building for climate resilient women's groups; 3. Number of woman participate in food self-sufficiency and food resilience initiative through yard gardening |  | Several key activities of the project focus for women. These activities include field schools for yard gardening, utilization of home gardens for household food security and biomass stove activities. All of these activities involve women 100%. In addition, the key activities have provided space for women at both the village and district levels, such as participation of women in the watershed forum.
6 – Core labour rights
7 – Indigenous peoples |  |  | Possibility of knowledge introduction and/or innovation through program activities conflicting with local knowledge of the Ammatoa Kajang indigenous community. | Implementation program ignore local knowledge of indigenous people. Management of the risk: The implementation of the project will always respect and consult the indigenous people knowledge as they are the main beneficiaries and key stakeholder of the project. | 1. Monitoring of complaints that may be submitted by indigenous community members 2. Report on consultation with indigenous community members |  | 1) each activity carried out have worked together with the community to determine the activity schedule, 2) each activity to be carried out, have been discussed with village heads and indigenous peoples regarding the suitability of the activities carried out with the ammatoa kajang customary law.
8 – Involuntary resettlement
9 – Protection of natural habitats
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency |  |  | Ineffective/unefficiency use of resource by using too many materials and resources (including human resources) from outside the area. | For the resource efficiency, the project will ensure the project part will utilize local available resource and make sure to always consider the sustainability of resources use. | Number and/or percentage of resource provision locally |  | The resources provision for the project activities have been from the local resources (when available) such as the seeds for the agroforestry nursery
13 – Public health
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes, monitoring for the ESP risks has been done during the project
Have unanticipated ESP risks been identified during the reporting period? |  | No unanticipated ESP risks identified during the reporting period
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | n/a
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant? |  | Yes, still relevant
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | KEMITRAAN required quarterly report being submitted by Executing Entity, to monitor project implementation closely to comply with the required AF safeguard.
Have the implementation arrangements been effective during the reporting period? |  | Yes. By having 3 monthly reports, IE could evaluate the project implementation thoroughly.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The executing entity have done continuous monitoring on the execution of the activities ensuring that the project beneficiaries have not practiced the female circumcision that is considered violate the human right. The project have ensured the equal opportunities for all groups including women and men to get benefit from the project. Executing entity have also carried out gender analysis and gender stakeholder consultation prior to and during the implementation of the project to ensure the involvement and participation of the women. It is not only give nominal portion of women participation (minimum 30%) in all relevant project activities, but also design several specific activities for women, such as field school on yard gardening and the involvement of women in the watershed forum. Such activities are to ensure the equality for women group. The project have ensured women engagement in several key project activities, such as participatory mapping and watershed management forum. The beneficiary unit of the project is also the household, the project have guaranteed that the representation of the households should be not less than 30% are women. The project have consulted with women and communities prior to the execution of project activities to make sure that the project activities are not giving double burden to the women. For the risk related to the indigenous people, it has been identified that Implementation of the project potentially ignore the local knowledge of indigenous people. The project have mitigate the risk by always respect and consult the indigenous people knowledge in the execution of the project’s activities. Project also have ensured the project execution optimize the local resources to ensure the resources efficiency.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes. All obstacle could be reported and identified immidiately if any to the executiung entity to get solution.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievance submitted to the project during the reporting period
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, it was
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | The project is designed to involve at least 30% of women who will be the direct beneficiaries of project activities. In fact, in this project, several activities, such as resilient woman groups initiation, yard gardening, biomass stoves introduction, have involved at least 350 women. As well as other activities (watershed forum, etc) where women's representation is important.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Establishment of integrated watershed management forum | Output 1.1.1. | Establishment of integrated watershed management forum & Climate Change Adaptation forum 10 of parties involve in the established forum | 0% (as no forum established yet before the project) | 30% of the forum members are representatives of women and vulnerable groups | satisfactory
Climate adaptive sustainable livelihood models practiced at 14 villages in 3 watershed landscape in Indigenous People of Ammatoa Kajang customary area. | Output 2.1.1: | 1.775 household (7100 person) of household practicing sustainable climate resilience livelihood at 14 villages at the 3 watershed area. Male: 4600 Female: 2500 | 0 (no identified climate related livelihood practice at the sites | 2,500 female beneficiaries | satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | KEMITRAAN required quarterly report being submitted by Executing Entity to closely monitor project implementation and compliance with the required AF safeguard.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes. IE could effectively address GP compliance
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The executing entity has ensured that the project activities do not widen the knowledge and capacity gap between men and women, by designing specific activities for women such as yard gardening, climate smart women group and women involvement on watershed forums. To ensure that project activities do not place a double burden on women, the executing entity has always consulted with women and communities before implementing project activities.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | It has been effective to address the GP Compliance
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No capacity gap identified
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
There is No. grievance received gender-related matters.

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Developing model of sustainable integrated watershed management inside the Indigenous People of Ammatoa Kajang customary area (Apparang, Baontoa and Raowa Watershed) |  | Outcome 5 | Process of the establishment of intgrated watershed menagement forum is underway. |  | In process | S
| 2. Promoting and practicing sustainable livelihood adaptive to climate change at the three watershed landscapes in the Indigenous People of Ammatoa Kajang customary area. |  | Outcome 6 | Villagers at project villages received training in and practicing the sustainable climate resilience and adaptive livelihood |  | Although the activity was planned to start in month 13, by the end of the first year, training has been partially conducted and beneficiaries has conducted practices accordingly | HS
| 3. Lobbying and Policy Advocacy for climate adaptive sustainable integrated watershed management and Climate Adaptation Action plan to regency government of Bulukumba and South Sulawesi Provincial government. |  | Outcome 7 | Ongoing process of internalization and integration of pro-climate development programs into regency and village development planning. |  | In process. The process at village level, integration in village devlopment plan, has already been progressing | S
| 4. Raising awareness, knowledge management and disseminating information on the importance of watershed and climate change impact to the Indigenous People of Ammatoa Kajang customary area. |  | Outcome 3 | Knowledge on climate change and integrated watershed management are disseminated to government, villages, regency and province level. |  | According to plan, this activity will only start in the 2nd year of implementation
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dewi Rizki
| Email: | dewi.rizki@kemitraan.or.id
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Due to pandemic situation, the project has started quite slow. In addition, there was a change in one of village involvement that has somehow affected the progress. But despite the obstacles in the beginning, the project has been conducted well and currently still on schedule. Training and application of agricultural practices has even started ahead of the planned schedule and is still ongoing with already some results at the household level. In terms of policy, Village Development Plan has been revised in two villages and still progressing in another 3 villages. Progress needs to be applied to the rest of villages involved in the project, so that inclusive, climate change integrated development plan can be achieved in the next implementation year.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | 1. Developing model of sustainable integrated watershed management inside the Indigenous People of Ammatoa Kajang customary area (Apparang, Baontoa and Raowa Watershed) |  | Outcome 5 | The watershed forum at Regency of Bulukumba established and watershed integrated management document and Climate Change Adaptation Regency Action Plan formulated. |  | The forum is on process of legalizing by the South Sulawesi Governor (Governor Decision Letter). The documents formulation is underway. | S
| 2. Promoting and practicing sustainable livelihood adaptive to climate change at the three watershed landscapes in the Indigenous People of Ammatoa Kajang customary area. |  | Outcome 6 | Villagers at project villages practicing sustainable climate resilience and adaptive livelihood |  | The promotion of the sustainable climate resilience and adaptive livelihood has been underway through agroforestry promotion and field school as well as yard gardening for food family self-sufficiency and household food resilience. | HS
| 3. Lobbying and Policy Advocacy for climate adaptive sustainable integrated watershed management and Climate Adaptation Action plan to regency government of Bulukumba and South Sulawesi Provincial government. |  | Outcome 7 | Internalization and integration of pro-climate development programs into regency and village development planning. |  | The process to integrate the pro climate programs into village develoment planning is being done at the project villages | S
| 4. Raising awareness, knowledge management and disseminating information on the importance of watershed and climate change impact to the Indigenous People of Ammatoa Kajang customary area. |  | Outcome 3 | Knowledge on climate change and integrated watershed management are disseminated to government, villages, regency and province level. |  | The activities will started on the second year.
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Karno B. Batiran
| Email: | karnobatiran@payopayo.or.id
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Component I activities have resulted several outputs including, increasing the capacity of village facilitators, forming an integrated Watershed Management Coordination Forum at the Bulukumba Regency level, collecting data and information needed in the process of drafting the RP-DAS and RAD-API, building mutual understanding with regency level stakeholders related to the importance of establishing a watershed Forum and watershed management document and Regency Action Plan on Climate Change Adaptation document, establishing collaboration with regency level stakeholders in the process of preparing the documents. Component II has succeeded in forming climate resilient women's groups in 14 project target villages totalling 350 households (25 women per village). Women's groups have practiced the use of home yard for gardening by planting vegetables, communities in 11 villages have the capacity to develop agriculture with the agroforestry system, seed houses have been built in 11 project target villages with various types of plants to be planted in agroforestry demonstration plots and lands. inhabitant. Component III has successfully revised the RPJMDes (Village Development Planning) in Dwi Tiro and Pantama villages and is currently in the process of revising the RPJMDes in Bonto Baji, Lolisang and Tugondeng villages. In addition, a workshop on the results of the revised RPJMDes has also been held in Dwil Tiro Village. In the workshop, the response from the village government and the community was quite positive because they had included adaptation activities to climate change into the RPJMDes. Component IV no activities have been carried out
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1.1. | There is a Integrated Watershed Management document & action plans in 3 watersheds in the Ammatoa Kajang Indigenous People Customary area. | no document at the inception of the project | The watershed forum at Bulukumba regency level is on the process of legalization by the South Sulawesi Governor (Governor decision letter). The documents of integrated watershed management plan and Climate Change Adaptation Regency Action Plan are on formulation process. | A document of Integrated Management of the watershed planning on for the 3 watershed inside the customary area of Ammatoa Kajang Indigenous People.
Output 1.1.1. | Establishment of integrated watershed management forum & Climate Change Adaptation forum # of parties involve in the established forum # of women member of the forum | no forum at the inception of the project | The watershed forum Bulukumba regency has been established. 50 stakeholders involved in the watershed forum of Bulukumba regency (as board of guarantee/trustee, expert council, technical coordinator, field coordinator, governing body) The governing board comprise of 46 persons (74% man, 26% woman). | 3 forum, 1 forum each watershed area At least 50 parties (government offices & agencies, village government, CSO) Member of the forum at least 30% in portion are women.
Output 1.1.2. | Formulation of watersheds governance planning Formulation of action plan for integrated watershed management | no document at the inception of the project | Data dan informasi yang akan dijadikan bahan kajian penyusunan RP-DAS dan RAD-API sudah dikumpulkan. | 1 Document of integrated watershed management for each watershed area. 1 set of action plan for each watershed area
Outcome 2.2. | # of household practicing sustainable climate resilience livelihood at 14 villages at the 3 watershed area. | no livelihood practice identified as climate resilience livelihood at the project village on the inception of the project | 220 households at 11 project villages already have the knowledge of the importance of the agroforestry towards climate change, targeted 700 households will practicing the agroforestry at the 11 villages. 350 women at 14 project villages have gain knowledge and practicing the family food self-sufficiency and food resilience through yard gardening. | 1.775 household (7100 person) Male: 4600 Female: 2500
Output 2.2.1. | # of farmers practicing adaptive sustainable livelihood practice in the Indigenous People of Ammatoa Kajang Customary Area | no livelihood practice identified as climate resilience livelihood at the project village on the inception of the project | 220 households at 11 project villages already have the knowledge of the importance of the agroforestry towards climate change, targeted 700 households will practicing the agroforestry at the 11 villages. 350 women at 14 project villages have gain knowledge and practicing the family food self-sufficiency and food resilience through yard gardening. | 1.775 household (7100 person) Male: 4600 Female: 2500
Output 2.2.2. | # of farmer group model practicing soil and water conservation practice, at 6 relevant and suitable villages. (3 at upstream, and 3 at middle stream) | no water and soil concervation practice identified at the project village on the inception of the project | the activities will be started Mei-Juni 2022 | 6 farmer group practicing “terasering” technique at slope field at 6 villages.
Outcome 3.1. | The Bulukumba Regency government issued 1 legislation/regulation product on integrated watershed management and an action plan for adaptation to climate change, as well as commitments of at least 10 government agencies to budget activities in order to support the regulation on integrated watershed management. and palm sugar) | no regulation on watershed on the inception of project | The revision on RPJMDes process at the project village is underway, expected to be completed and achieved on Q7. | 1 government regulation and 10 agreements of 10 government agencies to support integrated watershed management and adaptation action plans.
Output 3.1.1. | The release of regency regulation on integrated watershed management & climate adaptation action plan | no regulation on watershed on the inception of project | It will be carried out on Q7 | 1 Bulukumba Regency government regulation on integrated watershed management and climate change adaptation action plans.
Output .3.1.2. | # of offices Budgeted pro-climate watershed management & Climate Change Adaptation action plan Amount of budget put in the development activities that pro-climate on the watersheds area in the indigenous people of Ammatoa Kajang customary area. | n/a | The revision on RPJMDes process at the project village is underway, expected to be completed and achieved on Q7. | At least 10 government offices and agencies 5% from the total budget of each offices and agencies
Outcome 4.1. | 30.000 people inside and around indigenous people Ammatoa Kajang aware and recognize the importance of watershed and the condition of climate change and its impact to the livelihood. 10.000 people have basic knowledege about the the Adaption Fund project. | 0 | the activities will be started Mei-Juni 2022 | 30.000 people 10.000 people
Output 4.1.1. | # of people who know basic knowledge on the value of watershed and climate change issue. | 0 | the activities will be started on Q5 | 30.000 population within and around Ammatoa Kajang Customary Area.
Output 4.1.2. | # of people know the project | 0 | the activities will be started on Q5 | 10.000 population within and around Ammatoa Kajang Customary Area.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Gender, stakeholders collaboration, policies/regulations, sustainable livelihoods, watershed management.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There are several delays in the implementation of activities: 1) Establishment of an integrated Watershed Management Coordination Forum. The delay was due to the regulation gap, the reference for the formation of the Watershed Forum. The Minister of Forestry Regulation No. 61 of 2013 concerning the Watershed Management Coordination Forum and the Governor Regulation no. 31 of 2020. In the end it was agreed that the establishment and legalization of the Watershed Forum refers to the Governor's Regulation no. 31 year 2020. 2) Delay in preparation of Watershed Management Plan Documents and Regional Action Plans for Climate Change Adaptation (RAD-API). The delay was due to the submission of technical changes to the implementation of activities. In the initial project design, document preparation was carried out for 45 meetings. Then a budget revision was made by reducing the duration of the meeting to 20 times with adding the duration of the meetings. 3) Agroforestry Field School. The delay was caused by the revision of the budget. In the initial design of the project the implementation of the agroforestry Field School was carried out entirely indoor. Then the budget was revised with the implementation of agroforestry field school activities combining indoor and outdoor activities. Outdoor activities do not require a space rental budget so the budget for room rent are diverted to tools and materials cost for the needs of agroforestry field schools.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | First, there was a change of one of the project village. In the initial project design, Lembanna Village was the target village located in the middle of the Raowa watershed. However, due to internal problems, the Lembanna Village government withdrawn as project village. Thus, it was agreed with Payo-Payo/OASE and KEMITRAAN to change villages. The replacement village is the Tambangan Village which is directly adjacent to Lembanna Village which has the same characteristic. Second, the change in activities in Output 1.1.1 where the ratification of the Watershed Forum was carried out by the Regency was changed to the Governor. This change occurred because it was based on Governor's Regulation No. 31 of 2020. The regulation stated that the ratification of the Watershed Forum for Province, Regency, Watershed and Sub-watershed was carried out by the Governor. Then in Output 1.1.2. There are also changes to activities 1.1.2.14. Previously, the activity was carried out for 45 meetings and was later changed to 20 meetings. In the original design, each meeting was a one day meeting. In order to make the results more effective, the meeting was designed to be 3 days.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | it has been effective to avoid the impacts
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Women have an important role in managing and fulfilling the needs of family life, especially in the aspect of family food. In the project design, the formation of climate resilient women's groups was carried out in 14 project target villages. This climate-resilient women's group has implemented a yard gardening by planting various types of vegetables for the family's food needs. It has become the initiative for family food self-sufficient and resilience. More than 350 households in 14 villages use their gardens. During one year the project has taught important lessons that women in the Ammatoa Kajang Customary Law Community have an important role. Women are the group that most at risk of being affected by climate change because women have social, cultural and economic vulnerabilities, yet, women can also play a very important role in efforts to adapt to the impacts of climate change.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | 1) Encourage climate change adaptation actions at the village level such as agroforestry activities, integration of agriculture and animal husbandry, Seed Bank, soil and water conservation, utilization of home gardens by planting vegetables, biomass stoves, organic fertilizer management aimed at increasing environmental sustainability, increasing income community, food self-sufficiency and resilience and reduce public spending to buy vegetables and fertilizers. the activities carried out are models of climate change adaptation. 2) Encourage the establishment of a Watershed Management Coordination Forum. The watershed Forum aims to build synergy, participation, attention, and cooperation from each stakeholder in managing watershed areas in the upstream and middle and downstream. Through this forum, it can be a forum to discuss issues and an action agenda for the ecological crisis in a landscape that has affected the Ammatoa Kajang Indigenous Community. This forum has involved all stakeholders from the village, sub-district to district government levels, as well as the province 3) Advocating policies through Watershed Management Plan Documents (RP-DAS) and Regional Action Plans for Climate Change Adaptation (RAD-API), District Head Regulations on Climate Change Adaptation and Revised RPJMDes at the Village level. The policy advocacy is a step to bind the parties to take action to adapt to climate change, both at the provincial, district and village levels.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | 1) Building collaboration of stakeholders at the district level to the village level in encouraging adaptation actions. 2) Promotion of sustainable livelihoods and initiatives to improve family food resilience can encourage adaptation actions towards impact of climate change to the wider scale.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | one form of concrete adaptation is the initiative to increase household resilience through family food self-suffiency efforts through the yard garden program. This program has helped households to fulfill part of their household food and it is affordable.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | 1) Building collaboration of stakeholders at the district level to the village level in encouraging adaptation actions. 2) Promotion of sustainable livelihoods and initiatives to improve family food resilience can encourage adaptation actions towards impact of climate change to the wider scale.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | 1) Capacity building and encouraging practice of yard gardening for climate resilient women groups. 2) Increasing community capacity by planting various types of plants through the agroforestry system. 3) Internalization of climate change adaptation actions into the Village Medium Term Development Plan (RPJMDes). 4) Building collaboration of stakeholders in encouraging climate change adaptation at the district level.
What measures are/have been put in place to ensure sustainability of the project/program results? | To ensure the sustainability of the project/program results, several things have been carried out: 1) women's groups and communities already have the capacity to develop vegetable farming and agroforestry. Through the Agroforestry Field School, the Kambuno Village Head has committed to budgeting for village development to create Village Nursery activities. 2) the Village Medium Term Development Plan (RPJMDes) has been revised to include climate change adaptation actions. 3) An Integrated Watershed Management Coordination Forum has been established at Bulukumba Regency level by involving government agencies, communities, business actors, NGOs and academics with 50 institutions.
What measures are being/could have been put in place to improve project/program results? | 1) Strengthening the capacity of community groups (women and men). 2) Build strong collaboration with district and provincial level stakeholders. 3) influencing development policies at the village level to include climate change adaptation actions.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Data and information have been analysed for several activities such as preparation of RP-DAS and RAD-API Documents, Revised RPJMDes at Village level, workshops and report writing. And the information used includes; Data and information on the results of participatory mapping of village land use and watersheds, River Ecological Survey Reports, quarterly reports, and village level FGD results.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Currently they are available to the watershed forum members. The information currently only available internally within the watershed forum
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | The knowledge products resulting from project activities are: 1. Ethnographic study report, 2. Land use study report, 3. Report on institutional assessment of project villages. 4. Syllabus of agroforestry field school 5. Maps
If learning objectives have been established, have they been met? Please describe. | Specific learning objectives for the purpose of establishing the watershed forum and the preparation of integrated watershed management documents have been determined at the outset that the project will facilitate relevant and necessary studies in the process of developing integrated watershed management documents. Currently, the results of these studies have been used by the watershed forum in the preparation of integrated watershed management documents. at the same time the members of the das forum have also carried out a learning process together in the process of preparing the document.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | The difficulty encountered in collecting the necessary data and relevant to the project is that not all the required data is available and readily accessible, especially data from government agencies. In addition to availability constraints, there are also constraints on the reliability of the available data, some of the data that can be accessed is data that is not updated, for example population data that is not updated.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Tujuan pembelajaran telah berkontribusi terhadap outcome project. hasil-hasil pembelajaran telah dipergunakan dalam proses penyusunan dokumen rencana pengelolaan das juga misalnya silabus digunakan dalam sekolah lapang agroforestry.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | One of the innovative practices in project activities is the creation of a three-dimensional map that can depict the village landscape in a 3-dimensional view. This 3-dimensional map can help villagers understand village space more easily and holistically, especially related to land used planning and natural resource governance
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative? | No
If you answered yes above, kindly specify the name of the Fund/Organization.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity
Type of implementing entity
Country | Indonesia
Region | Asia-Pacific
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 37532 | 7100 | 30432 | Total | 16263 | 6449 | 9814 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 47% | 35% | 30% | % of female beneficiaries | 46% | 36% | 52% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 15% | 10% | 5% | % of Youth beneficiaries | 16% | 7% | 10% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  | 1 |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 100% |  | Multi-sector |  | 0% |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 30000 | 30% | 1: Aware of neither |  | 30000 | 0% | 1: Aware of neither |  | 0 | 0% | 1: Aware of neither
| Indicator 3.1.1: No. and type of risk reduction actions or strategies introduced at local level | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 0 | 0% | 1: Aware of neither |  | 0 | 0% | 1: Aware of neither
| Indicator 3.1.2: No. of new outlets in the local press and media that have covered the topic | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 0 | 0% | 1: Aware of neither |  | 0 | 0% | 1: Aware of neither
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Water management | water areas | 2: Partially effective |  | Agriculture | land | 2: Partially effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer |  | ha protected | 2: Partially effective | Catchment area/Watershed/Aquifer |  | km protected | 2: Partially effective | Catchment area/Watershed/Aquifer |  | km protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land |  | km protected | 2: Partially effective | Cultivated land/Agricultural land |  | km protected | 2: Partially effective | Cultivated land/Agricultural land |  | km protected | 2: Partially effective |  |  |  |  | 1.4
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 1% to 5% | Agricultural-related | 1775 | 0% | From 40% to 50% | Agricultural-related | 570 | 0% | From 20% to 30% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 20% to 30% | Cultivation | 1775 | 0% | From 20% to 30% | Cultivation | 220 | 0% | From 5% to 10% | Cultivation
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 3: Some |  |  |  | 3: Some |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 2 | Water management | Local | Environmental policy | 2 | Water management | Local | Environmental policy | 2 | Water management | Local | Environmental policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  |  | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective |  | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective |  | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness