Project Completion Summary

In accordance with the project agreement, implementing entities are required to submit a project completion report within six (6) months after Project completion, and the final project progress report (PPR) is considered as a project completion report. While the PPRs meet technical requirements, the information is reported by year and its format is not ideal to convey the overall information and knowledge to wider and more general audiences. To supplement this, implementing entities are requested to prepare a project completion summary.

A project completion summary is intended to cover an entire project life in a reader friendly format by compiling submitted single-year PPRs.  It also gives implementing entities an opportunity to express and share insights from project implementation, findings, challenges etc. which may not be presented by PPRs and captured by a final evaluation report.

A project completion summary consists of narrative information (Section A) and financial information (Section B). Any other information (Section C) can be added to the report as an option. Most of the contents can be filled in by copy-and-paste from the submitted PPRs. The completion report should be no more than 20 pages (excluding annexes).

Project Completion Summary

Section A: Project result and performance

- Basic information

| Title of project/programme | Adapting to Climate Change through Sustainable Integrated Watershed Governance in Indigenous People of Ammatoa Kajang Customary Area in Bulukumba Regency, South Sulawesi Province, Indonesia |
| --- | --- |
| Project/Programme category | Regular Project |
| Project period (if the project was granted an extension, include the original as well as the revised completion date) | 1 April 2022 until 1 April 2023 1st NCE : 1 April 2023- 30 September 2023 2nd NCE : 1October 2023 – 30 March 2024 |
| Country(ies) | Indonesia |
| Sector(s) | Water Management |
| Implementing entity name | KEMITRAAN |
| Type of implementing entity (MIE, NIE or RIE) | NIE |
| Executing entity(ies) | Consortium Payo-Payo Oase |
| Amount of financing approved (USD) | 1,125,015.16 |
| Project contact(s) | Eka Melisa |
| Date of report | 5 June 2025 |

- Key milestones –

| Project inception | 1st April 2022 |
| --- | --- |
| Mid-term review (if applicable) |  |
| Project completion | 30 March 2024 |
| Terminal evaluation | 7 December 2025 |
| If any, delay in implementation and reasons for delay |  |

- Project overview and description

The project “Adapting to Climate Change through Sustainable Integrated Watershed Governance in Indigenous People of Ammatoa Kajang Customary Area in Bulukumba Regency, South Sulawesi Province, Indonesia” has been implemented in three watersheds within Ammatoa – Kajang customary area, which are the Baonto, Apparang and Raowa watersheds. The target area of intervention consisted of 14 villages in the said area that benefited a total of over 35,000 beneficiaries. The selection of the 14 targeted villages was based on vulnerability criteria. This shows, among others, that all source of livelihoods in the targeted villages are experiencing very high exposure towards climate change impact. Overall, the project needed to be extended for another year from the initial proposed implementation timeline of 2 years.

The project entitled “Climate Change Adaptation through Sustainable Integrated Watershed Management in Indigenous Communities in the Ammatoa Kajang Customary Area in Bulukumba Regency, South Sulawesi Province, Indonesia” has been implemented for 3 years in three watersheds within Ammatoa – Kajang customary area, which are the Baonto, Apparang and Raowa watersheds.

The project officially started on 1 April 2021 and was planned to be finalized on 31 March 2023. Due to the approved 2 no-cost-extensions of 6 months each, the project was then finalized on 31 March 2024. The need for the extensions was firstly due to the COVID-19 that limited field activities and further due to delayed implementation of several project activities including among others the watershed management policy development. The watershed management policy is a crucial part in sustaining the efforts to improve the watershed resilience in the future and to strengthen regional ownership of the project results.

The project consists of 4 components, namely:

Component 1: Developing a sustainable integrated watershed management model within the Ammatoa Kajang Customary Area (Apparang, Baonto, and Raowa Watersheds). Through this program, PMU has succeeded in establishing the Bulukumba Regency Watershed Management Coordination Forum (DAS Forum) in the first year of the project.

The DAS Forum involves 50 parties consisting of Provincial government institutions, related Ministry UPTs, Regency Governments, Academics, Business Actors, Communities, and Non-Governmental Organizations. The structure of the DAS Forum consists of a board of advisors, a board of experts, technical coordinators, field coordinators, and a board of directors. Furthermore, the board of directors consists of 46 people with a presentation of 74% men and 26% women. In addition, the Bulukumba Regency Climate Change Adaptation Working Group (API) has been formed, which will continue to encourage adaptation actions in every line of development.

Component 2: Promoting and practicing sustainable livelihoods that are adaptive to climate change in three watershed landscapes in the Ammatoa Kajang customary area. This project has succeeded in establishing nurseries in 11 villages that have produced 110,000 trees. Practices of the system of rice intensification, goat farming, banana planting, and utilization of yard land.

Through this component, the project has also succeeded in transforming knowledge in the community regarding the importance of diverse plants as a strategy amidst climate change. The knowledge transformation was carried out through Agroforestry Field School and Yard Garden Field School activities in 14 villages.

Component 3: Policy Advocacy for integrated watershed management that is adaptive to sustainable climate and the Climate Adaptation Action Plan by the Bulukumba Regency Government and the South Sulawesi Provincial Government. In addition, the adaptation program has been internalized into the Village Medium-Term Development Plan (RPJMDes) and the Regional Apparatus Organization Work Plan.

Component 4: Increasing awareness, knowledge management, and socialization about the importance of watersheds and the impacts of climate change for indigenous communities in the Ammatoa Kajang customary area. This activity was carried out in mid-2023. Writing articles, books, seminars, and other campaigns have been carried out to disseminate information about the importance of watershed management and adaptation actions to climate change.

- Results and key outcomes (Alignment with the Adaptation Fund core impact indicators – Number of Direct Beneficiaries reached including women; Trainings conducted including women trained, Early Warning Systems (EWS); Assets Produced, Developed, Improved, or Strengthened; Natural Assets Protected or Rehabilitated i.e. hectares of natural habitats/ meters of coastlines)

This project is 100% funded by the Adaptation Fund and has directly benefitted XXX and XXX indirectly. During the three years of project implementation, all outputs have been achieved, highlighting among others the diverse adaptive livelihood activities at implemented at village level, the formation of the Bulukumba Watershed Forum (ForDAS) and the inititation of the Bulukumba Regent’s Climate Change Adaptation Action Plan and.

At the village level, a series of adaptive livelihood activities to climate change have also been completed. Starting from Agroforestry, Rice Intensification System, Banana planting, goat farming, utilization of yard gardens with vegetable plants, and the use of biomass stoves. Overall, this project has encouraged climate change adaptation actions at the village level through agroforestry activities, integration of agriculture and animal husbandry, Seed Bank, soil and water conservation, utilization of home gardens by planting vegetables, biomass stoves, organic fertilizer management aimed at increasing environmental sustainability, increasing income community, food self-sufficiency and resilience and reduce public spending to buy vegetables and fertilizers. The activities carried out are models of climate change adaptation. There are beneficiaries who have successfully developed knowledge from the agroforestry field school, namely the nutmeg shoot grafting method to reduce the male type of nutmeg. Males in nutmeg have less fruit than females.

In addition, target groups are also trained to make organic fertilizers, both solid and liquid, and botanical pesticides. This is done as an effort to encourage environmental improvement by reducing the use of chemical fertilizers and replacing them with organic ones. Target groups are also trained to apply land and water conservation measures, and the creation of seed banks as an effort to encourage improvement of the Watershed Area.

To ensure that adaptive livelihood activities and watershed improvement continue, the program encourages the internalization of these activities into the Village Medium-Term Development Plan and is ratified through Village Regulations (RPJMDes). The village government's response to the pro-climate change adaptation RPJMDes has been very good. They also participate in capacity building in promoting sustainable livelihood systems. So far, assistance from PMD in preparing the RPJMDes has been very limited. Including capacity building for village government.

As part of policy advocacy, the ForDAS has been ratified by the Governor of South Sulawesi in accordance with Decree Number 57/1 of 2023. ForDAS members have prepared three River Basin Management Plan Documents (RP DAS), namely Baonto, Aparang, and Raowa. The watershed Forum aims to build synergy, participation, attention, and cooperation from each stakeholder in managing watershed areas in the upstream and middle and downstream. Through this forum, watershed related issues can be discussed and an action agenda for the ecological crisis in a landscape that has affected the Ammatoa Kajang Indigenous Community can be developed. This forum has involved all stakeholders from the village, sub-district to district government levels, as well as the province. The RP DAS document will be ratified through a Governor's Decree. Both legal documents have been processed and will go through several stages in accordance with applicable provisions. The management of legal documents has changed after the project was underway.

In addition, the Regent of Bulukumba has also ratified the Bulukumba Regency Climate Change Adaptation Group in accordance with Decree 188. 45-409 of 2022. During the project implementation, the API Working Group has prepared the Bulukumba Regency Climate Change Adaptation Action Plan Document (RA API) that will be ratified through a Regent's Regulation.

The Governor's Decree and the Regent's Regulation must go through several stages such as examination at the Ministry of Home Affairs, and harmonization at the Provincial Legal Bureau. Once the review is finalized without further request for improvement, the legal documents will be approved.

Policy advocacy is a step to bind the parties to take action to adapt to climate change, both at the provincial, district and village levels.

The entire learning process during the project implementation is documented through several knowledge products such as scientific articles, books and short documentary videos. The program is also actively campaigning for climate change adaptation and improving watershed governance through Posters, Leaflets, and Banners. All campaign tools have been installed in community service centers such as Government Offices, Sub-district Offices, Village Offices, Schools and also places of worship.

Impact: Increased resiliency at the community, national, and regional levels to climate variability and change

|  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |
| --- | --- | --- | --- |
| Total | 37.532 | 7100 | 30432 |
| % of female beneficiaries | 46,00% | 35,00% | 42,00% |
| % of Youth beneficiaries | 16,00% | 10,00% | 5,00% |

Output 1.2 Targeted population groups covered by adequate risk reduction system

| No. of adopted Early Warning Systems | Category targeted | Hazard |  |
| --- | --- | --- | --- |
| 0 |  | Geographical coverage |  |
|  |  | Number of municipalities |  |
| # No. of adopted Early Warning Systems | # Category targeted | # Hazard |  |
|  |  | # Geographical coverage |  |
|  |  | # Number of municipalities |  |
| # No. of adopted Early Warning Systems | # Category targeted | # Hazard |  |
|  |  | # Geographical coverage |  |
|  |  | # Number of municipalities |  |
| # No. of adopted Early Warning Systems | # Category targeted | # Hazard |  |
|  |  | # Geographical coverage |  |
|  |  | # Number of municipalities |  |

Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events

Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events

Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks

| Total staff trained | % of female staff trained | Type |  |
| --- | --- | --- | --- |
| 46 | 30,00% | Public |  |
| Type | Scale | Sector | Capacity level |
| Public | Local | Multi-sector | 3: Medium capacity |

Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance

Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality

| Number of beneficiaries | Scale | Sector | Capacity level |
| --- | --- | --- | --- |
| 0 |  |  |  |

Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability

Core Indicator 5.1: Natural Assets protected or rehabilitated

| Natural resource improvement level |  | Sector | Type |
| --- | --- | --- | --- |
| 3: Moderately effective |  | Agriculture | land |
| Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation |
| Catchment area/Watershed/Aquifer | 3 | km protected | km protected |
| # Natural asset or Ecosystem (type) | # Total number of natural assets or ecosystems protected/rehabilitated | # Unit | # Effectiveness of protection/rehabilitation |
| # Cultivated land/Agricultural land | # 3 | # km protected | # 3: Moderately effective |
| # Natural asset or Ecosystem (type) | # Total number of natural assets or ecosystems protected/rehabilitated | # Unit | # Effectiveness of protection/rehabilitation |
| # Natural asset or Ecosystem (type) | # Total number of natural assets or ecosystems protected/rehabilitated | # Unit | # Effectiveness of protection/rehabilitation |

- Issues, challenges and mitigation measures (Environmental and social risks, gender considerations and other risks)

Related to the overall watersheds management, the authority to manage watersheds has become a polemic, since there are watersheds within one district whose authority is given to the district, while for watersheds that are across districts, management authority lies with the province. Approval of the policy document for the river basin management plan and the climate change adaptation action plan is therefore crucial to accommodate these watershed governing constellations. At the current stage, the project has managed to officially establish the Watershed Management Forum (ForDAS) ratified by the Regent of Bulukumba and submitted a draft for the Integrated Watershed Management Plan, which, to this date, is under review by the Provincial Legal Bureau.

In the livelihood component, on eofefforts to strengthen the assisted farmers groups are through providing cattle. In this case, goat has been chosen, since this is commonly raised by farmers in South Sulawesi to improve income through breeding and trading. During the implementation, the procurement of the goats has experienced slowdown in the distribution, causing delays in group activities. To overcome this, the procurement of the goats was extended by two months to minimize death of goats during the transportation process to the target villages.

- Lessons learned (Best practices, adaptive management, what worked during the implementation and what did not, what corrective actions were taken during implementation, what are the ways to improve the intervention)

Gender:

During this reporting period, women involvement was identified in the Watershed Management Forum and in the Climate Adaptation Working Group. The active women representatives are from Government Official, NGOs and local Adat Community. Their active involvement is visible during the meetings, in which they actively provided input and data to Watershed Management Planning and to the Climate Adaptation Action Plan. The total number of the Watershed Management Forum are 50 with 11 women, or verge to 30% from the total forum members, actively attending each meeting of the forum. Active women involvement during the discussions on the development of Climate Action Plan document is 30% of the 26 permanent members of the Working Group, which is legally stated within the South Sulawesi Governor Decree for the Watershed Management Forum and Bulukumba Regent Decree for the Climate Adaptation Working Group.

The formation of Climate Resilient Women Group that was officialized through a village decree allowing them to conduct farming in their house yard. This women group was also actively involved in the development of adaptive Village Development Plan. This opportunity allows them to improve women opportunity in the target villages to proactively involved in village planning without any social barrier.

Watershed Management:

The existence of advocacy activities towards the government in the form of an action plan contained in the watershed management plan (RPDAS) document. This process involved all

stakeholders including from the community, such as Climate Resilient Women Group, the farmers and rice farmers group, and forest farmers group. The watershed management plan

was developed based on inputs, ideas and suggestions from all involved stakeholders.

Sustainable Livelihood:

An innovative approach related to rice cultivation was implemented through the introduction of the System of Rice Intensification, which has never been applied in the target areas before. Although not all farmers group continued practicing this method, those who continues have proven increased income due to increased yield. The same situation also with the women group applying house yard farming, where those continued practicing this activity has gained economic benefit through the fulfillment of household needs and the selling of excess products.

Collaboration between groups in adjacent villages has been positive, even though only 10% of the total 25 members continued to practice house-yard farming.

- Innovation: description of any innovative practices or technologies that figured prominently in this project

One of the innovative practices in project activities is the creation of a three-dimensional map that can depict the village landscape in a 3-dimensional view. This 3-dimensional map can help villagers understand the village spatial more easily and holistically, especially related to land used planning and natural resource governance and its relation to sound watershed management.

- Description of the vulnerable communities and social groups affected by the project, and how they have been engaged and empowered

Engagement

During the implementation of this project, different communities at different levels are engaged to actively involve in, as well as to institutionally, socially and economically benefit from the project. These community groups consist of government officials, farmers, women and youth.

Farmers are part of the most important communities to be engaged in the overall activities of this project, since most of the direct beneficiaries are farmers. The engagement of farmers is crucial, since most of the farming sites are situated within the watershed areas and therefore become vulnerable to hazards because of the climate change impact. Farming sites are frequently flooded, so affected farmers experienced frequent crop failures affecting their income, thus implicating their social and economic conditions.

Integrated management of the affected watersheds became necessary to achieve sustainable results of the watershed rehabilitation and protection efforts. The role of the local and provincial government is therefore very important in providing legal regulatory frameworks to maintain protection of the watersheds. Therefore, relevant local and provincial government offices and officials are engaged to be actively involved in meetings and discussions related to watersheds management.

Women's involvement was identified in the Watershed Management Forum and in the Climate Change Adaptation Working Group. Active female representatives came from Government Officials, NGOs and local Indigenous Peoples. The total number of Watershed Management Forums was 50 with 11 women, or almost 30% of the total forum members, actively attending each forum meeting. The active involvement of women in the discussion of the preparation of the Climate Action Plan document was 30% of the 26 permanent members of the Working Group, which was legally stated in the South Sulawesi Joint Decree of the Watershed Management Forum and the Bulukumba Regent's Decree on the Climate Adaptation Working Group.

Young generation is the potential agents of change in sustaining the results of climate adaptation projects. Involvement of youth groups became important in the discussions and assessment on environment and ecosystem services, as well as in terms of raising awareness on climate change impact and aspects of climate adaptation.

Since the project is implemented within the customary area of Ammatoa – Kajang, engagement of the customary community needs to be manifested as an integral part of the project. Meetings and discussions with the customary community of Ammatoa – Kajang has been conducted, not only to be actively involved in the project implementation but also to learn from their local wisdom in protecting the watersheds and sustaining their traditional livelihoods.

Empowerment

In terms of community empowerment, capacity building and policy advocacy have been conducted in this project. Institutional empowerment has been introduced through the establishment and/or strengthening of farmers and women groups. In addition, adaptive livelihood practices also targeted women such as the use of biomass stoves, goat farming and the manufacture of organic fertilizers.

1) Capacity building and encouraging yard gardening practices for climate-resilient women's groups.

2) Community capacity building by planting various types of plants through agroforestry systems.

3) Internalization of climate change adaptation actions into the Village Medium-Term Development Plan (RPJMDes).

4) Building stakeholder collaboration in encouraging climate change adaptation at the district level.

5) Pest and disease control in primary commodities

6) Seed banks as an effort to conserve and provide useful local plant seeds

7) Training in making organic fertilizers, both solid and liquid.

8) Group-based goat farming as an effort to encourage economic resilience

- Description of how long-term institutional and technical capacity for effective adaptation has been strengthened

Issues related to climate change at the sub-national level are 1) lack of climate related data, 2) lack of financial capacity at sub-national level to conduct study on the impact and therefore to recognize early enough potential hazards, and 3) poor capacity of local officials in formulating the appropriate climate change adaptation measures. This project has contributed to improve local knowledge and capacity at different levels ranging from local government institutional capacity in the management of watershed, community involvement incl. women in the development of adaptive Village Management Plan and farmers skills and knowledge on implementing different adaptive farming methods. This way, the results of activities implemented on-site provide the modality for long-term impact as such, that interventions are officially supported by local and village governments through official decrees and integrated in the Village Medium Term Development Plan.

At the community level, the project has improved the technical capacity of the beneficiaries, providing them with the adaptive skills and knowledge that has proven to increase their income. Improved economic conditions are important in securing the sustainable results of the project impacts.

- An overview of complementarity and/or coherence of with other climate finance sources in the context of this project (synergies with other projects, national plans etc.)

This project is neither scaled up from nor build upon any other climate finance initiative.

- Sustainability, scalability and replicability

Sustainability:

This project encourages agroforestry patterns in the management and utilization of forests and land with the main crop of Multipurpose Trees with the aim of increasing environmental sustainability, increasing community income, and food security. This project also helps beneficiaries to improve their adaptive capacity in terms of utilizing the house yard for small-scale farming activities to improve their economic conditions, as well as provides cattle for farmers to have alternative sources of income, thus better chance to survive economically, during possible crop failure.

Further, this project also promotes joint policies in Integrated Watershed Management that are connected to the conditions and interests of the upstream and downstream watershed areas.

Scalability and Replicability

Integration of Watershed Management Plan as a measure to adapt to climate change is a strategic step to improve the watershed condition and minimize climate change impact. This becomes a model for other watershed management that can easily be adopted in other areas. The draft policy on the Watershed Management Plan and Climate Change Adaptation Action Plan currently in the process of ratification will be internalized into the Bulukumba Regency government work plan through building strong collaboration with district and provincial level stakeholders.

Section B: Project expenditure

(The use of spreadsheet is recommended to avoid numerical errors.)

| Code | Charging | Activity | Budget | Expenditure Y1 | Expenditure Y2 | Expenditure Y3 | Total Expenditure | Balance | Variance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1.1 |  | Multi-stakeholders watersheds management forum established at three watersheds inside the Indigenous People of Ammatoa Kajang customary area. | 10,112 | 8,246 | 397 | 1,121 | 9,764 | 348 | 0.03% |
| 1.1.1.1 | 21-03-001 | Activity 1.1.1.1 Project Team Orientation | 731 | 731 | 0 | 4,745 | 5,476 | -4,745 |  |
| 1.1.1.2 | 21-03-002 | Activity 1.1.1.2 Program socialization & Kickoff | 2,847 | 1,337 | 397 | -550 | 1,184 | 1,663 |  |
| 1.1.1.3 | 21-03-003 | Activity 1.1.1.3 Series of multi stakeholder workshop for establishing watershed management coordination forum and formulating forum workplan | 5,228 | 4,942 | 0 | -3,074 | 1,868 | 3,359 |  |
| 1.1.1.4 | 21-03-004 | Activity 1.1.1.4 Watershed management multistakeholder coordination forum legalization | 1,306 | 1,235 | 0 | 0 | 1,235 | 71 |  |
| 1.1.2 |  | Watersheds governance planning and action documents formulated and agreed among stakeholders | 170,751 | 107,416 | 18,054 | 42,559 | 168,029 | 2,721 | 0.24% |
| 1.1.2.1 | 21-03-005 | Activity 1.1.2.1 Workshop on preparation for study for formulating integrated watershed management plan and climate adaptation action plan | 1,384 | 1,308 | 0 | 0 | 1,308 | 75 |  |
| 1.1.2.2 | 21-03-006 | Activity 1.1.2.2 Workshop for making instrument for study for formulating integrated watershed management plan and climate adaptation action plan | 4,147 | 3,921 | 1,934 | -2,159 | 3,696 | 451 |  |
| 1.1.2.3 | 21-03-007 | Activity 1.1.2.3 Etnography, institutional analisys, Policy Analysis, Sustainable livelihood analysis, secondary data study on watershed area | 4,466 | 3,921 | 286 | -167 | 4,040 | 426 |  |
| 1.1.2.4 | 21-03-008 | Activity 1.1.2.4 Conservation and biodiversity study on the Watershed area | 4,466 | 3,921 | 286 | 206 | 4,414 | 53 |  |
| 1.1.2.5 | 21-03-009 | Activity 1.1.2.5 Assesment PES (payment ecosystem services) | 4,466 | 4,223 | 0 | 281 | 4,504 | -37 |  |
| 1.1.2.6 | 21-03-010 | Activity 1.1.2.6 Resilience, vulnerability assesment on disaster and climate change impact | 4,466 | 4,223 | 0 | 193 | 4,415 | 51 |  |
| 1.1.2.7 | 21-03-011 | Activity 1.1.2.7 Land use assesmnet (FGD on land use history of village and watershed area) | 4,466 | 3,921 | 286 | 335 | 4,543 | -76 |  |
| 1.1.2.8 | 21-03-012 | Activity 1.1.2.8 Establishment of participatory land use mapping team | 5,433 | 5,137 | 0 | 361 | 5,497 | -64 |  |
| 1.1.2.9 | 21-03-013 | Activity 1.1.2.9 Participatory mapping training | 5,851 | 5,532 | 0 | 208 | 5,740 | 111 |  |
| 1.1.2.10 | 21-03-014 | Activity 1.1.2.10 Land use participatory mapping | 30,746 | 48,405 | 1,340 | -19,044 | 30,700 | 46 |  |
| 1.1.2.11 | 21-03-015 | Activity 1.1.2.11 Area and village land use map making | 17,231 | 16,067 | 803 | -2,781 | 14,089 | 3,142 |  |
| 1.1.2.12 | 21-03-016 | Activity 1.1.2.12 Workshop on land use mapping result | 2,718 | 2,570 | 0 | 1,686 | 4,256 | -1,538 |  |
| 1.1.2.13 | 21-03-017 | Activity 1.1.2.13 Workshop on preparation of integrated watershed management plan document framework and climate adaptarion action plan formulation | 1,674 | 1,583 | 0 | -234 | 1,349 | 325 |  |
| 1.1.2.14 | 21-03-018 | Activity 1.1.2.14 Series of workshop on formulating integrated watershed management plan and climate change adaptation action plan | 75,670 | 2,685 | 13,119 | 60,124 | 75,928 | -258 |  |
| 1.1.2.15 | 21-03-019 | Activity 1.1.2.15 Public consultation integrated watershed management and climate change adaptation action plan document | 3,221 | 0 | 0 | 3,208 | 3,208 | 13 |  |
| 1.1.2.16 | 21-03-020 | Activity 1.1.2.16 Evaluation | 343 | 0 | 0 | 342 | 342 | 2 |  |
| 2.1.1 |  | Climate adaptive sustainable livelihood models practiced at 14 villages in 3 watershed landscape in Indigenous People of Ammatoa Kajang customary area. | 602,222 | 135,913 | 35,117 | 425,787 | 596,818 | 5,404 | 0.48% |
| 2.1.1.1 | 21-03-021 | Activity 2.1.1.1 Agroforestry field school | 54,777 | 28,484 | 19,731 | 20,150 | 68,365 | -13,588 |  |
| 2.1.1.2 | 21-03-022 | Activity 2.1.1.2 Agroforestry Demonstration plot making | 45,149 | 34,926 | 7,369 | -3,221 | 39,074 | 6,076 |  |
| 2.1.1.3 | 21-03-023 | Activity 2.1.1.3 Establishment of Climate resilience women group (14 villages) | 5,433 | 5,137 | 0 | 84 | 5,221 | 212 |  |
| 2.1.1.4 | 21-03-024 | Activity 2.1.1.4 Series of FGD with climate resilience women group at 14 villages (3 times each village) | 16,299 | 15,410 | 0 | 1,521 | 16,931 | -632 |  |
| 2.1.1.5 | 21-03-025 | Activity 2.1.1.5 Yard gardening field school | 28,836 | 27,263 | 0 | 1,152 | 28,416 | 420 |  |
| 2.1.1.6 | 21-03-026 | Activity 2.1.1.6 Yard gardening implementation by climate resilience women group at 14 villages | 26,119 | 24,695 | 0 | 0 | 24,695 | 1,425 |  |
| 2.1.1.7 | 21-03-027 | Activity 2.1.1.7 Biomass stove procurement for women group at 14 villages | 19,590 | 0 | 0 | 18,289 | 18,289 | 1,300 |  |
| 2.1.1.8 | 21-03-028 | Activity 2.1.1.8 Training on using biomass stove for women group at 14 villages | 7,235 | 0 | 0 | 1,002 | 1,002 | 6,234 |  |
| 2.1.1.9 | 21-03-029 | Activity 2.1.1.9 Goat Livestock field school | 100,209 | 0 | 4,668 | 96,588 | 101,257 | -1,048 |  |
| 2.1.1.10 | 21-03-030 | Activity 2.1.1.10 Goat procurement for farmer group | 77,940 | 0 | 0 | 66,560 | 66,560 | 11,381 |  |
| 2.1.1.11 | 21-03-031 | Activity 2.1.1.11 Goat stall/shelter making | 33,381 | 0 | 0 | 31,872 | 31,872 | 1,508 |  |
| 2.1.1.12 | 21-03-032 | Activity 2.1.1.12 Training on making organic fertilizer from goat dunk | 8,358 | 0 | 0 | 15,642 | 15,642 | -7,284 |  |
| 2.1.1.13 | 21-03-033 | Activity 2.1.1.13 Field School on System of Rice Intensification (SRI) | 58,679 | 0 | 965 | 57,253 | 58,217 | 462 |  |
| 2.1.1.14 | 21-03-034 | Activity 2.1.1.14 SRI Practicing/implementation | 2,943 | 0 | 0 | 0 | 0 | 2,943 |  |
| 2.1.1.15 | 21-03-035 | Activity 2.1.1.15 FGD with farmers for Seed bank preparation | 2,086 | 0 | 374 | 569 | 944 | 1,142 |  |
| 2.1.1.16 | 21-03-036 | Activity 2.1.1.16 Seed bank development | 6,791 | 0 | 2,010 | 8,380 | 10,389 | -3,598 |  |
| 2.1.1.17 | 21-03-037 | Activity 2.1.1.17 Field school banana cultivation | 42,658 | 0 | 0 | 42,892 | 42,892 | -234 |  |
| 2.1.1.18 | 21-03-038 | Activity 2.1.1.18 Banana cultivation | 20,321 | 0 | 0 | 20,362 | 20,362 | -41 |  |
| 2.1.1.19 | 21-03-039 | Activity 2.1.1.19 Series of integrated pest management (6x) | 45,419 | 0 | 0 | 46,690 | 46,690 | -1,272 |  |
| 2.1.2 |  | Environment conservation to support sustainable livelihood adaptive to climate change done on three watersheds in Ammatoa Kajang customary area. | 13,127 | 0 | 9,185 | 4,971 | 14,156 | -1,029 | -0.09% |
| 2.1.2.1 | 21-03-040 | Activity 2.1.2.1 Soil and water conservtion training | 10,231 | 0 | 9,185 | 0 | 9,185 | 1,047 |  |
| 2.1.2.2 | 21-03-041 | Activity 2.1.2.2 Terasering demonstration plot for soil and water conservation | 2,552 | 0 | 0 | 2,291 | 2,291 | 261 |  |
| 2.1.2.3 | 21-03-042 | Activity 2.1.2.3 Evaluation | 343 | 0 | 0 | 2,680 | 2,680 | -2,336 |  |
| 3.1.1 |  | Head of Regency regulation on watershed management and climate adaptation action is signed and released. | 11,750 | 0 | 67 | 12,585 | 12,652 | -901 | -0.08% |
| 3.1.1.1 | 21-03-043 | Activity 3.1.1.1 Series of discussion of multisatkeholders watershed management coordination forum to formulate and finalizing regent regulation on integrated watershed management and climate adaptation action plan(10 times) | 7,919 | 0 | 67 | 7,659 | 7,726 | 194 |  |
| 3.1.1.2 | 21-03-044 | Activity 3.1.1.2 Public consultation of regent regulation on integrated watershed management and climate adaptation action plan of Bulukumba regency | 3,178 | 0 | 0 | 4,926 | 4,926 | -1,748 |  |
| 3.1.1.3 | 21-03-045 | Activity 3.1.1.3 legalization of Regent regulation on Integrated watershed management and climate adaptation action plan | 653 | 0 | 0 | 0 | 0 | 653 |  |
| 3.1.2 |  | Pro-climate integrated sustainable watershed management programs budgeted in the annual regency budgeting and Climate adaptive budgeting put into regency annual budgeting | 66,338 | 8,575 | 25,047 | 35,262 | 68,884 | -2,546 | -0.23% |
| 3.1.2.1 | 21-03-046 | Activity 3.1.2.1 Formation of revision team / draft maker of Pro Climate Change Adaptation Village development planning (RPJMDes) at 14 villages. | 2,727 | 1,105 | 1,000 | 1,405 | 3,510 | -783 |  |
| 3.1.2.2 | 21-03-047 | Activity 3.1.2.2 Series of discussions and finalization of revision / drafting of Pro Climate Change Adaptation Village development planning (RPJMDes) at 14 villages. | 50,134 | 6,771 | 20,731 | 20,280 | 47,783 | 2,351 |  |
| 3.1.2.3 | 21-03-048 | Activity 3.1.2.3 Public consultation of Pro Climate Change Adaptation Village development planning (RPJMDes) | 10,343 | 699 | 3,316 | 9,904 | 13,919 | -3,576 |  |
| 3.1.2.4 | 21-03-049 | Activity 3.1.2.4 Roadshow to internalize the integrated watershed management framework to the provincial government development plan (Governor, Bappeda, DLHK, BP-DAS LH) | 2,791 | 0 | 0 | 3,672 | 3,672 | -881 |  |
| 3.1.2.5 | 21-03-050 | Activity 3.1.2.5 Evaluation | 343 | 0 | 0 | 0 | 0 | 343 |  |
| 4.1.1 |  | Knowledge of local people on the importance of watershed and climate change impact increased | 51,568 | 15,058 | 3,792 | 37,062 | 55,912 | -4,345 | -0.39% |
| 4.1.1.1 | 21-03-051 | Activity 4.1.1.1 KAP Baseline and end line survey | 31,354 | 15,058 | 0 | 17,638 | 32,696 | -1,342 |  |
| 4.1.1.2 | 21-03-052 | Activity 4.1.1.2 Awareness rising campaign | 7,623 | 0 | 3,792 | 7,619 | 11,411 | -3,788 |  |
| 4.1.1.3 | 21-03-053 | Activity 4.1.1.3 Academic writing and project lesson learnd book | 12,590 | 0 | 0 | 11,805 | 11,805 | 784 |  |
| 4.1.2 |  | Project information disseminated | 12,509 | 0 | 4,607 | 7,555 | 12,162 | 347 | 0.03% |
| 4.1.2.1 | 21-03-054 | Activity 4.1.2.1 villagers discussion forum on watershed management and climate change | 2,216 | 0 | 0 | 1,625 | 1,625 | 591 |  |
| 4.1.2.2 | 21-03-055 | Activity 4.1.2.2 project dissemination seminar | 4,726 | 0 | 0 | 4,661 | 4,661 | 65 |  |
| 4.1.2.3 | 21-03-056 | Activity 4.1.2.3 Evalualuation | 343 | 0 | 0 | 0 | 0 | 343 |  |
| 4.1.2.4 | 21-03-057 | Activity 4.1.2.4. Monev Kemitraan | 5,224 | 0 | 4,607 | 1,269 | 5,876 | -652 |  |
| b.1 | 21-03-058 | A. Project/Program Excecution Cost | 98,503 | 40,780 | 30,045 | 27,678 | 98,503 | 0 | 0.00% |
| c.1 | 21-03-063 | B. Project Cycle Managemet Services | 88,135 | 26,859 | 10,736 | 50,540 | 88,135 | 0 | 0.00% |
|  |  | TOTAL | 1,125,015 | 342,847 | 137,048 | 645,120 | 1,125,015 | 0 |  |

Section C: Appendices (optional)

- Participants list of the inception workshop

- Key project staff list

| Roles | Staff Name |
| --- | --- |
| Program Leader | Karno Batiran |
| Finance Manager | Muhammad Alfian Murap |
| Program Coordinator | Dadang Anugrah |
| Consultant/Expert (Advocacy Focus ) | Andi Adriardi |
| Field Officer | Abdurahman Abdullah |
| Field Officer | Nurdin |
| Field Officer | Salman |
| Field Officer | Gatot |
| Field Officer | Mulyadi |
| Field Officer | Rudi Tahas |
| Field Officer | Ahmad |
| Admin assistant | Jumarni |
| Admin Assistant | Pratiwi |
| Technical Assistant | Ansar |

- Results tracker

| Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness |
| Total | 0 | Inland flooding | 4: Effective | Total | 9 | Inland flooding | 4: Effective | Total | 9 | Inland flooding | 3: Moderately effective | Total | 10 | Inland flooding | 4: Effective |
| % of female targeted | 0,00% |  |  | % of female targeted | 45,00% |  |  | % of female targeted | 40,00% |  |  | % of female targeted | 45,00% |  |  |
| No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status |
| 0 | Multi-sector | Local | 1: No plans conducted or updated | 1 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated | 0 | Multi-sector | Local | 2: Undertaking or updating of assessments in progress | 1 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated |
| No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  |
|  |  | Geographical coverage |  | 0 |  | Geographical coverage |  |  |  | Geographical coverage |  | 0 |  | Geographical coverage |  |
|  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |
| # No. of adopted Early Warning Systems | # Category targeted | # Hazard |  | # No. of adopted Early Warning Systems | # Category targeted | # Hazard |  | # No. of adopted Early Warning Systems | # Category targeted | # Hazard |  | # No. of adopted Early Warning Systems | # Category targeted | # Hazard |  |
|  |  | # Geographical coverage |  |  |  | # Geographical coverage |  |  |  | # Geographical coverage |  |  |  | # Geographical coverage |  |
|  |  | # Number of municipalities |  |  |  | # Number of municipalities |  |  |  | # Number of municipalities |  |  |  | # Number of municipalities |  |
| # No. of adopted Early Warning Systems | # Category targeted | # Hazard |  | # No. of adopted Early Warning Systems | # Category targeted | # Hazard |  | # No. of adopted Early Warning Systems | # Category targeted | # Hazard |  | # No. of adopted Early Warning Systems | # Category targeted | # Hazard |  |
|  |  | # Geographical coverage |  |  |  | # Geographical coverage |  |  |  | # Geographical coverage |  |  |  | # Geographical coverage |  |
|  |  | # Number of municipalities |  |  |  | # Number of municipalities |  |  |  | # Number of municipalities |  |  |  | # Number of municipalities |  |
| # No. of adopted Early Warning Systems | # Category targeted | # Hazard |  | # No. of adopted Early Warning Systems | # Category targeted | # Hazard |  | # No. of adopted Early Warning Systems | # Category targeted | # Hazard |  | # No. of adopted Early Warning Systems | # Category targeted | # Hazard |  |
|  |  | # Geographical coverage |  |  |  | # Geographical coverage |  |  |  | # Geographical coverage |  |  |  | # Geographical coverage |  |
|  |  | # Number of municipalities |  |  |  | # Number of municipalities |  |  |  | # Number of municipalities |  |  |  | # Number of municipalities |  |
| Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion |  |  |  |
| Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level |
| Total | 0 | Multi-sector | 1: No capacity | Total | 10 | Multi-sector | 3: Medium capacity | Total | 9 | Multi-sector | 2: Low capacity | Total | 10 | Multi-sector | 3: Medium capacity |
| % of female targeted | 0 |  |  | % of female targeted | 40,00% |  |  | % of female targeted | 30,00% |  |  | % of female targeted | 39,00% |  |  |
| Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  |
| 0 | 0,00% | Public |  | 46 | 30,00% | Public |  |  |  |  |  | 46 | 30,00% | Public |  |
| Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level |
|  |  |  |  | Public | Local | Multi-sector | 3: Medium capacity | Public | Local | Multi-sector | 2: Low capacity | Public | Local | Multi-sector | 3: Medium capacity |
| Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level |
|  |  |  |  | 0 |  |  |  |  |  |  |  | 0 |  |  |  |
| Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion |  |  |  |
| Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  |
| 0,00% |  | Multi-sector |  | 100% |  | Multi-sector |  | 0% |  | Multi-sector |  | 100% |  | Multi-sector |  |
| No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  |
| 30000 | 30,00% | 1: Aware of neither |  | 30000 | 0,00% | 1: Aware of neither |  | 0 | 0,00% | 1: Aware of neither |  | 30000 | 0,00% | 1: Aware of neither |  |
| No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  |
| 0 | 0,00% | 1: Aware of neither |  | 0 | 0,00% | 1: Aware of neither |  | 0 | 0,00% | 1: Aware of neither |  | 0 | 0,00% | 1: Aware of neither |  |
| No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  |
| 0 | 0,00% | 1: Aware of neither |  | 0 | 0,00% | 1: Aware of neither |  | 0 | 0,00% | 1: Aware of neither |  | 0 | 0,00% | 1: Aware of neither |  |
| No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  |
| 0 |  |  |  | 2 | 20% to 39% | 3: Partially aware |  | 1 | 20% to 39% | 3: Partially aware |  | 2 | 20% to 39% | 3: Partially aware |  |
| No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  |
| 0 |  |  |  | 1 | Technical guidelines | Local |  | 0 | Technical guidelines | Local |  | 1 | Technical guidelines | Local |  |
| Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion |  |  |  |
| Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  |
| Agriculture | Local | 1: Non responsive (Lacks all elements ) |  | Agriculture | Local | 4: Mostly responsive (Most defined elements) |  | Agriculture | Local | 2: Partially responsive (Lacks most elements) |  | Agriculture | Local | 4: Mostly responsive (Most defined elements) |  |
| Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  |
| Food security | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Food security | 1: Health and Social Infrastructure (developed/improved) | 5: Fully improved |  | Food security | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved |  | Food security | 1: Health and Social Infrastructure (developed/improved) | 5: Fully improved |  |
| # Agriculture | # 2: Physical asset (produced/improved/strenghtened) | # 1: Not improved |  | # Agriculture | # 2: Physical asset (produced/improved/strenghtened) | # 5: Fully improved |  | # Agriculture | # 2: Physical asset (produced/improved/strenghtened) | # 3: Moderately improved |  | # Agriculture | # 2: Physical asset (produced/improved/strenghtened) | # 5: Fully improved |  |
| Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector |
| 0 | Multi-community |  | Multi-sector | 1 | Multi-community |  | Multi-sector | 1 | Multi-community |  | Multi-sector | 1 | Multi-community |  | Multi-sector |
| Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion |  |  |  |
| Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type |
| 2: Partially effective |  | Water management | water areas | 2: Partially effective |  | Agriculture | land | 2: Partially effective |  | Agriculture | land | 3: Moderately effective |  | Agriculture | land |
| Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation |
| Catchment area/Watershed/Aquifer |  | ha protected | 2: Partially effective | Catchment area/Watershed/Aquifer | 3 | km protected | 2: Partially effective | Catchment area/Watershed/Aquifer | 3 | km protected | 2: Partially effective | Catchment area/Watershed/Aquifer | 3 | km protected | km protected |
| # Natural asset or Ecosystem (type) | # Total number of natural assets or ecosystems protected/rehabilitated | # Unit | # Effectiveness of protection/rehabilitation | # Natural asset or Ecosystem (type) | # Total number of natural assets or ecosystems protected/rehabilitated | # Unit | # Effectiveness of protection/rehabilitation | # Natural asset or Ecosystem (type) | # Total number of natural assets or ecosystems protected/rehabilitated | # Unit | # Effectiveness of protection/rehabilitation | # Natural asset or Ecosystem (type) | # Total number of natural assets or ecosystems protected/rehabilitated | # Unit | # Effectiveness of protection/rehabilitation |
| # Cultivated land/Agricultural land |  | # km protected | # 2: Partially effective | # Cultivated land/Agricultural land | # 3 | # km protected | # 2: Partially effective | # Cultivated land/Agricultural land | # 3 | # km protected | # 2: Partially effective | # Cultivated land/Agricultural land | # 3 | # km protected | # 3: Moderately effective |
| # Natural asset or Ecosystem (type) | # Total number of natural assets or ecosystems protected/rehabilitated | # Unit | # Effectiveness of protection/rehabilitation | # Natural asset or Ecosystem (type) | # Total number of natural assets or ecosystems protected/rehabilitated | # Unit | # Effectiveness of protection/rehabilitation | # Natural asset or Ecosystem (type) | # Total number of natural assets or ecosystems protected/rehabilitated | # Unit | # Effectiveness of protection/rehabilitation | # Natural asset or Ecosystem (type) | # Total number of natural assets or ecosystems protected/rehabilitated | # Unit | # Effectiveness of protection/rehabilitation |
| # Natural asset or Ecosystem (type) | # Total number of natural assets or ecosystems protected/rehabilitated | # Unit | # Effectiveness of protection/rehabilitation | # Natural asset or Ecosystem (type) | # Total number of natural assets or ecosystems protected/rehabilitated | # Unit | # Effectiveness of protection/rehabilitation | # Natural asset or Ecosystem (type) | # Total number of natural assets or ecosystems protected/rehabilitated | # Unit | # Effectiveness of protection/rehabilitation | # Natural asset or Ecosystem (type) | # Total number of natural assets or ecosystems protected/rehabilitated | # Unit | # Effectiveness of protection/rehabilitation |
| Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion |  |  |  |
| No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  |
|  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |
| No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  |
|  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |
| No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source |
| 0 | 0,00% | From 1% to 5% | Agricultural-related | 1775 | 0,00% | From 40% to 50% | Agricultural-related | 570 | 0,00% | From 20% to 30% | Agricultural-related | 1775 | 0,00% | From 20% to 30% | Agricultural-related |
| # No. of targeted households | # % of female headed households | # % increase in income level vis-à-vis baseline | # Alternate Source | # No. of targeted households | # % of female headed households | # % increase in income level vis-à-vis baseline | # Alternate Source | # No. of targeted households | # % of female headed households | # % increase in income level vis-à-vis baseline | # Alternate Source | # No. of targeted households | # % of female headed households | # % increase in income level vis-à-vis baseline | # Alternate Source |
| # 0 | # 0,00% | # From 20% to 30% | # Cultivation | # 1775 | # 0,00% | # From 20% to 30% | # Cultivation | # 220 | # 0,00% | # From 5% to 10% | # Cultivation | # 1775 | # 0,00% | # From 20% to 30% | # Cultivation |
| # No. of targeted households | # % of female headed households | # % increase in income level vis-à-vis baseline | # Alternate Source | # No. of targeted households | # % of female headed households | # % increase in income level vis-à-vis baseline | # Alternate Source | # No. of targeted households | # % of female headed households | # % increase in income level vis-à-vis baseline | # Alternate Source | # No. of targeted households | # % of female headed households | # % increase in income level vis-à-vis baseline | # Alternate Source |
| # No. of targeted households | # % of female headed households | # % increase in income level vis-à-vis baseline | # Alternate Source | # No. of targeted households | # % of female headed households | # % increase in income level vis-à-vis baseline | # Alternate Source | # No. of targeted households | # % of female headed households | # % increase in income level vis-à-vis baseline | # Alternate Source | # No. of targeted households | # % of female headed households | # % increase in income level vis-à-vis baseline | # Alternate Source |
| Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy |
| 0 | Physical capital | Agriculture | Community-based adaptation | 17 | Physical capital | Agriculture | Community-based adaptation | 5 | Physical capital | Agriculture | Community-based adaptation | 17 | Physical capital | Agriculture | Community-based adaptation |
| Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source |  |
|  | Agricultural-related |  |  | 1.780 | Agricultural-related |  | 128 | 1.780 | Agricultural-related |  | 128 | 1.780 | Agrcultural-related | Agricultural-related |  |
| # Number of households (total number in the project area) | # Income source |  | # Income level (USD) | # Number of households (total number in the project area) | # Income source |  | # Income level (USD) | # Number of households (total number in the project area) | # Income source |  | # Income level (USD) | # Number of households (total number in the project area) | # Income source | # Income source |  |
| # Number of households (total number in the project area) | # Income source |  | # Income level (USD) | # Number of households (total number in the project area) | # Income source |  | # Income level (USD) | # Number of households (total number in the project area) | # Income source |  | # Income level (USD) | # Number of households (total number in the project area) | # Income source | # Income source |  |
| # Number of households (total number in the project area) | # Income source |  | # Income level (USD) | # Number of households (total number in the project area) | # Income source |  | # Income level (USD) | # Number of households (total number in the project area) | # Income source |  | # Income level (USD) | # Number of households (total number in the project area) | # Income source | # Income source |  |
| Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion |  |  |  |
| Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  |
| 3: Some |  |  |  | 3: Some |  |  |  | 3: Some |  |  |  | 3: Some |  |  |  |
| No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type |
| 2 | Water management | Local | Environmental policy | 2 | Water management | Local | Environmental policy | 2 | Water management | Local | Environmental policy | 2 | Water management | Local | Environmental policy |
| No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness |
| 0 | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective | 4 | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective | 0 | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective | 4 | 4: Enforced (Most elements implemented) |  | 4: Effective |
| Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion |  |  |  |
| Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type |  |
| Food Security | Community |  |  | Food Security | Community | Innovation replicated |  | Food Security | Community | Innovation replicated |  | Food Security | Community | Innovation replicated |  |
| No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness |
| 0 | Food Security | No innovative practices |  | 1 | Food Security | Completed innovation practices | 4: Effective | 1 | Food Security | Undertaking innovative practices | 3: Moderately effective | 1 | Food Security | Completed innovation practices | 4: Effective |
| No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness |
| 0 | Innovative product |  |  | 1 | Innovative product |  | 4: Effective | 0 | Innovative product |  | 4: Effective | 1 | Innovative product |  | 4: Effective |

- Reports and other publications

- Annual Report

- https://bit.ly/4jcNRET - Annual Report (1st year)

- https://bit.ly/3W7G8hp - Annual Report (2nd year)

- https://bit.ly/3C4eA5J - Final report ( 3th year)

- Other Publications

- Adaptation Action Plan Bulukumba Regency - https://bit.ly/4a6I1Rj

- Action Plan Watershed Management for DAS Apparang - https://bit.ly/4aanBqm

- Action Plan Watershed Management for DAS Raowa - https://bit.ly/3WaeNLo

- Action Plan Watershed Management for DAS Baonto - https://bit.ly/3DOmPTV

- Best Practices Book - https://bit.ly/4abNiqG

- Academic Journal - https://bit.ly/4j8HKRF

- Documentery movie - https://bit.ly/3Pqf2yl