## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | December 2020 To December 2021
| Project Title: | Enhance community, local and national-level urban climate change resilience to water scarcity, caused by floods and droughts in Rawalpindi and Nowshera, Pakistan
| Project Summary: | The Pakistan's Adaptation Fund Poject is a joint collaboation of the Government of Pakistan, UNHABITAT and the Adaptation Fund. The project is implemented in two districts of the conuntry. One district is Rawalpindi, which lies in Punjab province while the second project district is Nowshera in Khyber Pakhtunkhwa province. In Rawalpindi seven (7) union councils (UCs) and in Nowshera district eight (8) Neighbourhood Councils (NCs) are selected for project interventions. Main objective of the proposed project is to “enhance community, local and national-level urban climate change resilience to water scarcity, caused by floods and droughts in Rawalpindi and Nowshera cities.” This will be achieved through the following proposed sub-objectives: 1. Community level: Enhance community and household level flood resilient water harvesting facilities (using innovative techniques) and strengthen capacities to plan, construct, operate, maintain and replicate these. 2. District / City level: Enhance city and district-level water harvesting facilities in public buildings and on water storages in public gardens, develop district / city-level spatial strategies as tool to assess climate change re-lated floods, droughts and water scarcity to plan for and manage climate change risks and to strengthen ca-pacities to plan, construct, operate, maintain and replicate water harvesting facilities in public buildings and gardens. 3. National and Provincial level: Strengthen national and provincial-level capacity to guide / direct city-level development considering climate change and disaster risks and impacts, especially water scarcity caused by floods and droughts. The project is implemented through five Government departments and authorities and one civil society welfare trust. Main focus of the project is improvement and building resilience of the local communities and sub-distrcit level institutions in the Rain Water Harvesting facilities. The objective is to improve access of the communities to build their capacities in Rain Water Harvesting through collection and storage at household levels and also to apply the same approach in the Public Buildings, which face acute shortage of water due to droughts and insufficient water management. In addition project is also undertaking activities related to policy formulation on rain water harvesting, development of national urban strategy, preparaing guidelines on spatial planning and water management strategies in the country. The project also implementing the activities related to capacity building of Government authorities, field implementers, community representatives and civil society organisations in planning, constrction, designing and operation of the Rain Water Harvesting faciities and technologies to build the capacities of the stakeholders for broader impacts on climate adaptation and mitigation. The project partners are also organising awareness campaigns, capacity building trainings and workshops for target communities and officials of the relevant departents to enhance their preparedness and awareness levels regarding Rain Water Harvesting and water related Planning and management. Following are the main outputs of the project: Output 1.1. 5000 community / household level flood resilient (i.e. elevated to not be affected by flood water) rainwater harvesting facilities constructed, using innovative techniques. Output 1.2. 15-union/neighborhood council-level community plans developed (7 in Rawalpindi/8 in Nowshera), community members (especially women and youth) trained and practical guide developed to plan, construct, operate, maintain and replicate water harvesting at community level, and to reduce waste in drainage channels through awareness raising campaigns. Output 1.3. Awareness campaigns in all target communities to reduce dumping of solid waste in drainage channels. Output 2.1. 50 district / city-level water harvesting facilities in public buildings and on water storages in public gardens constructed. Output 2.2. Two district / city-level spatial planning strategies developed considering climate change risks and impacts, especially floods and droughts, and including comprehensive water harvesting plans. These strategies are decision-making tools for cities to assess climate change related floods, droughts and water scarcity to plan for and manage climate change-related risks and impact in and beyond city boundaries, taking into consideration multiple sectors. Output 2.3. 50 government officials trained and guidelines developed to plan, construct, operate, maintain and replicate flood resilient water harvesting facilities and to enhance capacity in developing spatial plans. Output 3.1.100 government officials (women / men) trained to guide / direct urban development considering climate change and disaster risks and impacts, using especially spatial planning guidelines and tools. Output 3.2. One National urban strategy focused on climate change / disaster risk reduction developed One set of National guidelines for spatial planning considering climate change / disaster risks developed
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UN-Habitat | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity (MIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Pakistan | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The project's main focus is in two cities of Pakistan; one is Rawalpindi city of Punjab province and the other Nowshera City in Khyber Pakhtunkhwa Province. Total 15 Union Council (UC) in these two cities are being benefiting from the project: In Rawalpindi city following Union Councils are targeteed: UC # 1 Ratta Amral UC # 2 Dhoke Ratta UC # 4 Dhoke Mangtal UC # 5 Dhoke Hassu North UC # 6 Dhoke Hassu South UC # 12 Dhoke Najju UC # 37 Dhoke Dalal. In Nowshera City following 8 Neighbourhood Councils (NC) are being benefitted from the project: 1. Dagi Khel 2. Allah Yar Khel 3. Nawan Kali 4. Shahmeer Gari 5. Bara Khel 6. Behram Khan Khel 7. Mana Khel 8. Kabul River | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2020-01-06
IE-AFB Agreement Signature Date: |  | 2020-01-06 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2020-12-22 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2023-06-01
| Terminal Evaluation Date: | 2024-12-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
1. Inception Report 2-Communication Strategy 3-Minutes of Project Steering Committee
|  | 4-Brochures and Banners Developed by Implementing Partners 5.User Guidelines on Rain Water Harvesting 6.Guidelines on use of materials and technical specifications in the system, and 7.Monitoring reports | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.unhabitat.org.pk | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Khalil Ahmed | Dominican Republic
| Email: | khalil.ahmed@un.org | Ecuador
| Date: | 2021-07-01 | Egypt
| Government DA |  | El Salvador
| Name: | Muhammad Irfan Tariq (Mr)/ Director General Ministry of Climate Change, Islamabad | Equatoral Guinea
| Email: | mirfantariq@gmail.com | Eritrea
| Date: | 1st January 2021 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Laxman Perera, Project Leader, Human Settlements Officer, UN-Habitat Regional Office | Fiji
| Email: | laxman.perera@un.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Shehersaaz Welfare Trust (Shehersaaz), Pakistan | Georgia
| Email: | almas@shehersaaz.org.pk, tassadaq.shah@outlook.com, almas.shehersaaz@gmail.com | Germany
| Date: | 2021-11-05 | Ghana
| Executing Agency |  | Greece
| Name: | National Disaster Management Authority (NDMA), Pakistan | Grenada
| Email: | dirimp@ndma.gov.pk | Guatemala
| Date: | 2022-01-01 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Pakistan Council of Research in Water Resources (PCRWR) | Guyana
| Email: | faizan_ul_hasan@hotmail.com | Haiti
| Date: | 2022-01-01 | Honduras
Executing Agency
| Name: | Ministry of Climate Change, Pakistan
| Email: | mazeemkhoso@gmail.com
| Date: | 2020-12-22
Executing Agency
| Name: | Water and Sanitation Authority (WASA) Rawalpindi, Pakistan
| Email: | rabbaninoor121@gmail.com
| Date: | 2022-01-01
Executing Agency
| Name: | Tehsil Municipal Administration (TMA) Nowshera, Pakistan
| Email: | idrees947@gmail.com
| Date: | 2022-01-01
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: Cumulative from project start to 18th February 2022
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Cumulative total disbursement as of 18 Feb 2022 |  | 137305
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME |  | 0
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT (US$)
|  | Output 1.1 5000 community / household level flood resilient (i.e. elevated to not be affected by flood water) rainwater harvesting facilities constructed, using innovative techniques | 25000
|  | PROJECT EXECUTION COST | 112305
PROJECT/PROGRAMME CYCLE MANAGEMENT FEE
|  | TOTAL | 137305
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST (US$) | Est. Completion Date
|  | Output 1.1: 5000 community / household level flood resilient (i.e. elevated to not be affected by flood water) rainwater harvesting facilities constructed, using innovative techniques | 800000 | 2023-03-01
|  | Output 1.2: 15 union/neighbourhood council-level community plans developed (7 in Rawalpindi/8 in Nowshera), community members (especially women and youth) trained and practical guide developed to plan, construct, operate, maintain and replicate water harvesting at community level, and to reduce waste in drainage channels through awareness raising cam-paigns | 150000 | 2023-03-01
|  | Output 1.3: Awareness campaigns in all target communities to reduce dumping of solid waste in drainage channels. | 50000 | 2023-03-01
|  | Output 2.1: 50 district / city-level water harvesting facilities in public buildings and on water storages in public gardens constructed | 655000 | 2023-03-01
|  | Output 2..2: Two district / city-level spatial planning strategies developed considering climate change risks and impacts, especially floods and droughts, and including comprehensive water harvesting plans.These strategies are decision-making tools for cities to assess climate change related floods, droughts and water scarcity to plan for and manage climate change-related risks and impact in and beyond city boundaries, taking into consideration multiple sectors. | 200000 | 2023-03-01
|  | Output 2.3 Target: 50 government officials trained and guidelines developed to plan, construct, operate, maintain and replicate flood resilient water harvesting facilities and to enhance capacity in developing spatial plans | 40000 | 2023-03-01
|  | Output 3.1:100 government officials (women / men) trained to guide / direct urban development considering climate change and disaster risks and impacts, using especially spatial planning guidelines and tools. | 70000 | 2023-03-01
|  | Output 3.2: One National Urban Strategy focused on climate change / disaster risk reduction developed, and; -One Set of National guidelines for spatial planning considering climate change / disaster risks developed | 110000 | 2023-03-01
|  | PROJECT EXECUTION COST | 169500
|  | PROJECT/PROGRAMME CYCLE MANAGEMENT FEE | 184415
|  | *TOTAL | 2428915
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? |  | N/A
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  | N/A
Foot Note-1: *An important point noted for consideration is that; total amounts under 2nd instalment has a typo error on page number 93 of the Disbursement scedule of the AF project document., and showing total of 2,321,895 US$, which is wrong. Actual and correct total is US$ 2,428,915.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Environmental Risk:
Current climate and seasonal variability and/or hazard events result in infrastructure construction delays or undermine confidence in adaptation measures by local communities | This risk has not created or impacted the progress during reporting year | Not applicable at this stage
Institutional/Social:
Loss of government support (at all levels) for the project (activities and outputs) may result in lack of prioritization of AF project activities | Support from Government Implemnting Partners was very slow due to changing policies and the Covid 19 Pandemic | As per requirement of the Government Implementing Patners, standard legal agreements (AOC) of UN-Habitat are required changes. The document template has now been adjusted in line with the Government policies. This process took much longer than anticipated and currently it is under process of the review and signatures of the partners.
Capacity constraints of local institutions maylimit the effective implementation of interventions | There is some capacity issues in few of the Implementing Partners | The UN-Habitat Country Office Team has assisted the Implementing Partners in compilation and preparation of project documents and agreements. Now capacity of the partners is built upto a minimum required levels for implementation of their resepctive outputs planned under the project.
Communities that have given their consent to the project may revoke their consent (which they have the right to do) or may become unhappy that the project doesn’t match their expectations | So far communities are very cooperative and no issues of cooperation and consent are observed | Not applicable at this stage
Disagreement amongst stakeholders with regards to adaptation measures (infrastructure) and site selection. | All stakeholders and Implementing Partners are at the same level so far, and at present no disgeement has been observed | Not applicable at this stage
Communities may not adopt activities during or after the AF project, particularly infrastructure maintenanc | Activities are in its early stage, and so far no issues of adaptation, howver in the coming years it may occur | An undertaking proforma has been developed and signed before start of field activities related to community participation and sustainability of the interventions after project life.
Delays in project implementation, and particularly in the development of infrastructure interventions | During reporting year delays were mainly occur due to Covid-19 pandemic. | To cope with delays and to expedite progress on the interventions, the four-year plan of the project has been re-aligned and got approved from the project board. The activities remained unachieved during the first year will be implemented and achieved during coming years of the project.
A lack of coordination between and within national government Ministries and Departments | So far no issues related to coordination are observed | Not applicable at this stage
Financial Risks:
Complexity of financial management and procurement. Certain administrative processes could delay the project execution or could lack integrity | Some complexities of financial management observed due to delay in signing of agreements with Ips | Regional Office of UN-Habitat is working on streamline to fill the gaps and delays.
Legal Risks:
Delays or barriers in gaining approval for infrastructure and housing due to delays in the development process or due to land tenure issues | Currently no such issues are observed in the project area. | Not applicable at this stage
Security Risks:
The security situation reduces access to the target sites, and/or makes it unsafe to visit | No such risk are faced currently | Not applicable at this stage
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
N/A

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1]
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law: |  |  | N/A
2 - Access and equity: Activities would exclude any potentially affected stakeholders from fully participating in decisions that may affect them; risk of unequal distribution among target population / communities and households of project benefits. |  |  | Women would be impacted to a greater degree than men, as evidenced by experiences elsewhere in Pakistan | Communities are to be trained to operate and manage the RWH units under Output 1.1 as a means to reduce the potential for inequitable access. Women are being given an equal role in the management. Community planning has been included in the project design as a means to enhance ownerships and reinforce principles of equitable | Gender equal water user groups formed and operational, SOPs prepared, Reports developed. | The each EE will produce monitoring baseline for their respective outputs as per agreed implementation plan. | List of the participants is being prepared, traning need assement will be caried out. Particpation of both men and women will be equally considered in implementation of the activities. | No water user groups have been formed so far. Consultations have been initaited. Both men and women will be taken in these groups by consensus rather than by domination of one group over another. The community plans will also be prepared by joint groups of both men and women including the marginalised segments to maximise equitable access to facilities, prevention of discrimination against women, children, the elderly or disabled, as well as to ensure fair and equitable distribution of water, sustainability and adaptation to future changes. | Proper dialogue and participation in every activity from community members will be ensured by each EE.
3 – Marginalized and vulnerable Groups: Some vulnerable affected groups may not participate in decisions making processes regarding design and planning of activities that may affect them. |  |  | Women would suffer maladaptation –they wouldstill suffer a lack of access to water during water shortage periods, and the project would be exacerbating a situation where women are unequal and face more barriers. Migrants may be discriminated against and not receive services, or non-migrants may receive preferential access. This would bea mal-adaptive situation for migrants and would exacerbate structural inequalities faced by Afghan migrants in societ | Women have been fully integrated into the community management, decision-making and maintenance structures designed by the project. Community plans will also be implemented to ensure the fair distribution of water. Project ‘champions’ in the community will be on hand to help illiterate community members (more likely to be women) to play a more active role. | Men and women have equal access and get equal benefit; equal access for migrant families; and surveys, informal interviews, and focus groups. | Records are maintained at EE level. The UN_Habitat will compile data on annual basis. | It has been agreed between the Implementing Partners and the Implementing Entity that 50% partcipation of the marginalised and vulnerable groups shall be iensured at all levels. | Process of inclusion of the vulnerable groups has been initiated but not completed. | Community cahmpions and members of the committees in each area will include the vulnerable groups, and be equally responsible to ensure that every one benefits from the project interventions. EE will record the aggreegated data in this regard.
4 – Human rights: Risk that land and tenure arrangements and/or community-based property rights are affected; failure to proactively protect the rights (i.e. international standards) of all stakeholders affected by the project. |  |  | N/A
5 – Gender equality and women’s empowerment: Women and men do not have equal opportunities to participate in the project and do not benefit equally from interventions. |  |  | The potential for women to benefit inequitably, or face discrimination exists and this would be a mal-adaptive situation for women | Women will play an active and decisive role in the community management of the project, enhancing their participation, and greatly reducing the risk that they will be excluded. | Women are in decision making positions at the community level, regarding the RWH facilities, and are trained in operation and maintenace | Labour laws are regulary monitored and so far no such observations are recorded. | Women are equally participating in all project activitiesthrough planning, decision making and consensus building activities. | Process has been intitiaed in formation of formal community groups but no formal have been formed yet | Women partcipation is ensured and regularly monitored in all project activities implemented by the EE/IPs.
6 – Core labour rights: Employing underage people and to support underpayment and unsafe working conditions; executing entities for the project may not adhere to the ILO labour Standards and national labour laws. |  |  | People may end up working excessive/unreasonable hours, without contracts, and/or for unfairly low salaries, below the minimum wage. This would exacerbate a situation in Pakistan where many people work in the informal sector for less than $2 per day. Unequal pay for men and women would exacerbate the gender pay gap that exists in Pakistan. Any of the above would exacerbate pre-existing problems that exist in Pakistan, including in the target area. | All labourers employed to work during the construction of the RWH facilities will be formalized, working under legally binding contracts, in compliance with Pakistan’s labour laws and, where these are insufficient, ILO standards and guidelines. All executing entities will be contractually obliged to uphold these standards | All workers have proper contracts, in compliance with the law, paid above minimum wage. Contracts, reporting, workers testimony gained through informal discussions. | Measures are ensured through ensuring practivce consideration of labour laws & policies in procurement and implementation of field activities by EEs | Underage labour will be considered by law unless tey are considered as desserved. | Employment of the underage has not been considere so far. | The IL standards are observed and ensured at all levels.
7 –.Involuntary resettlement: Temporary or permanent and full or partial physical displacement (see also principle 4) |  |  | The risk of resettlement is very negligible. However, there is a risk of some temporary disruption of access to homes while construction takes place, and some disturbance in terms of noise and construction workers in the area. | Communities will also be fully briefed on the exact nature of the construction works before they begin, including the expected duration, the disruption expected and the grievance mechanism. | All people have unhindered access to their houses throughout, and there is no damage. Photographs, testimony gained through informal discussions | So far no cases reported. | Community members and all service providers are well informed in the beginning of each activity to in all sectors avoid such mismanagement. | The construction activities have not yet started. It will be ensured in future field interventions that people will have inhindered access to their houses without damages.. | Equity and access will be ensured at all levels during implementation of the field activities.
8 – Indigenous peoples: Indigenous groups may not participate in decisions making processes regarding design and planning of activities that may affect them. |  |  | N/A
9 – Protection of natural habitats |  |  | N/A
10 – Conservation of biological diversity |  |  | N/A
11 – Climate change |  |  | A slight increase in GHG emissions | Local materials will be used throughout the construction. All hardware required by the project (i.e. tanks, pipes and pumps) are available locally in both cities, meaning that emissions relating to transportation will not be necessary. To that end, all procurement documents will emphasise the need to use locally sourced materials and avoid imports. Aside from this, no additional emissions are expected from the activities | Local materials will be used throughout the procurement. Proper procurement documents will be prepared. | No climate issues from the project are reported so far. | Local materials are preferred in the implementation and construction activities. | Existing procurement policy of the EE is being followed and implemented. In future it will be further improved for field implementation. | Un-Habitat has ensured that all E.Es will follow these prescribed guidelines.
12 – Pollution prevention and resource efficiency: Consumption of raw materials will have a negative effect (elsewhere). |  |  | An unnecessary contribution, howeversmall, to GHG emissions, would preventative measures | UN-Habitat will ensure that waste materials are disposed of being the official waste management services provider. All construction workers will be trained on proper procedures to dispose of waste materials generated during the construction, to ensure that there is no risk of improper disposal. Agreements of Cooperation will stipulate that executing entities are responsible for proper disposal of waste materials and they will be subject to periodic monitoring. | All waste effectively disposed off and procedures are advised in procurement documents and photograps. | No such issues have been reported untill now. | It has been agreed with the EE that during installation of the field activities they they will ensure the proper disposal of generated waste and records are maintained and regularly shared with UN-Habitat.. | Guidelines are being prepared by the E.Es for disposal of the waste and will be complied accordingly. | Regular monitoring is underway to mitigate identified risk during implementation of the field activities by EEs.
13 – Public health: Potential risk: elements of activity construction, operation, or decommissioning pose potential safety risks to local communities (see also principle 6). |  | . | Water-borne diseases are unpleasant and debilitating for people in the target area, and particularly affect thosealready vulnerable. A lack of occupational health and safety standards and procedurescould result in injuries to workers. | Occupation health and safety training will be provided for all construction works, and necessary safety equipment, such as boots and hard hats will be provided. This will be the responsibility of the executing entity, working under Agreement of Cooperation from UN-Habitat. These provisions should be seen in conjunction with those under core labour rights, and are designed to keep the construction workers safe, first and foremost. All construction sites will be demarcated, with fencing, barriers and cones, as appropriate to ensure that community members not involved in the construction are safe, and don’t inadvertently walk into areas where construction is ongoing. | Safety training provided, protective gear available, Photos and reports. Water hygiene practices observed. Training materials. | No public health issues reported so far from the project activities. | All community members, executing entities and project staff and service providers are well informed before initiation of the construction work and they are a;so trained in the relevant field of intervention. | Traninings will be provided, field gears are being provided to the community memebers and labours before construction work starts in the field. | The situation will be regularly and effectively monitored, and recorded. By all E.Es and UUHABITAT.
14 – Physical and cultural heritage: Proposed interventions will affect physical or cultural heritage negatively. |  |  | Though construction does not directly affect heritage buildingsor areas, there could be some temporarydisruption of access or appreciationof heritage buildings without management and mitigation measures. | All construction sites will be demarcated effectively. Before works commence, as part of the full and informed prior consent process, the anticipated disruption to public buildings during construction will be discussed with building managers and building users/surrounding communities (i.e. parents in the case of schools). Construction workers will be trained to ensure there is minimal reduction to public building users, especially where the public buildings in question are schools, and as far as possible, construction will take place outside of school hours. In the case of mosques, no construction will take place on Fridays or at prayer times. | Buildings continue there function, and there is no differece to their aesthetics. | No such issues have been recorded. | Regular awareness, campaigns are conducted to maintain physical and cultural heritage. | It will be ensured that buildings and vicinitay are not altered very much and remain functional during implementation. | EE,s have regular contact with UN-Habitat on regular basis.
15 – Lands and soil conservation: Proposed interventions will have a negative effect on lands and soil conservation. |  |  | N/A
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N./A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant? |  | Yes
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | During implementation of the acivities ESP measures are being checked for compliance in all project interventions. The IE in its meetings with EE have agreed on social inclusion and environmental safeguarding in implementation of the project activities. For this purpose check lists are being prepared before initiation of the activitity, agreements are drafted and signed by the EEs with community and citizen groups.
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The matter of ESP is discussed with all Implementing Partners and stakeholders during planning of each activitity and compliance is obsereved accordingly.Formats are designed by the EE to ensure social enclusion and environmetal safe guards, The IP/EE of the AF project are bound to assess and make inclusion of special deserving groups, poor households and disabled memebrs of the communities and women segments in to consideration during field activities.The same approach is also adopted during procurement of the goods and services in establishment of household water harvesting units for environmental safe guarding.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10] |  | No
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | N/A
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11] |  | N/A
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP] | N/A
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances and complaints received so far |  | Not applicable at present.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, initial gender assessemnt was condcuted during preparation of the project proposal. A gender action plan has been formulated and adapted in all project interventions. It is generally planned that in all project activities 50% of the women members of the communities and partners will be ensured. This will be achieved through enhanced participation of the women from marginalised and vulnerable groups and from the households headed by the women.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes, the result framework has included gender-responsive indicators at objective, outcome and output levels.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Discussions and decisions in communities are gedner equal, disagreegated and equal participation of women in community-based activities ensured | Output 1.1: 5000 community / household level flood resilient (i.e. elevated to not be affected by flood water) rainwater harvesting facilities constructed, using innovative techniques | Engineer’s survey complete, and describe in detail how the needs of women (particularly women who work in the home) have been incorporated Equal number of men and women participate. Attendance registers taken (anonymised) that identify numbers of men and women | No households have RWH facilities and all experience poor quality water during regular and mega floods | Water management at household level is the amin responsibility of women. More than 50% beneficiaries are women are equally benefitting from these interventions. | Satisfactory
Equal number of women particopate in trainings, planning and decision makingTraining for community members trains an equal number of men and women (150 men, 150 women, 300 total) An equal number of male and female community champions identified Community-scale plans equally consider the needs of men and women. Women’s adaptation and development needs are fully incorporated | Output 1.2: Fifteen (15) union/neighbourhood council-level community plans developed (7 in Rawalpindi/8 in Nowshera), community members (especially women and youth) trained and practical guide developed to plan, construct, operate, maintain and replicate water harvesting at community level, and to reduce waste in drainage channels through awareness raising cam-paigns | Training complete with records documenting equal participation from men and women Community champions identified and a brief profile made including recording gender Community plans prepared and reviewed by the Project Manager and PSC | There are no plans in place, no guidelines to support local government or communities and individual knowledge/ capacity is low | Women are equally being considered for meetings, workshops, trainings, planning sessions and awareness campaigns. 50% women participation if being ensured in the planning and management of the interventions by the Ees. | Satisfactory
Campaighn material is developes as that also target women, and through media that women are likely to access and benefit | Output 1.3: Awareness campaigns in all target communities to reduce dumping of solid waste in drainage channels. | Campaign materials developed and reviewed by the project manager and PSC | There are no regular or recent awareness campaigns on the rain water related issues | 50% participants in these campaigs are women memebers of the community. | Good
Training for managers of public buildings will include sensitivity to women/ensuring that the needs of women are highlighted | Output 2.1: 50 district / city-level water harvesting facilities in public buildings and on water storages in public gardens constructed | Training materials prepared that clearly highlight the risk and vulnerability of women, and how the project promotes safeguarding their interest | No training materials and awareness and knowledge products have been developed oreviously | 50 ercerny | Good
The MHVRA and spatial strategies will full consider the differentiated risks and vulnerabilities of women, their adaptation options and potential and outline proposed actions that specifically benefit women | Output 2.2: Two district / city-level spatial planning strategies developed considering climate change risks and impacts, especially floods and droughts, and including comprehensive water harvesting plans | The MVHRA complete with comprehensive analysis of the differentiated risks and vulnerabilities of women, and adaptation options that benefit them | No MHVRAs are condcuted previously in these two cities | Women needs are being considered in the DRR mapping and planning | Satisfactory
20 female officials included in the training All training materials consider the differentiated and/or particular needs of women | Output 2.3: 50 government officials, including 20 women trained and guidelines developed to plan, construct, operate, maintain and replicate flood resilient water harvesting facilities and to enhance capacity in developing spatial plans | Training complete with documentation to show that at least 20 women participated throughout. All training materials clearly indicate the need to consider the particular and differentiated adaptation needs of women | No training materials and awareness and knowledge products have been developed oreviously | Women participation in the trainings and developing the training manuals id under consideration | Satisfactory
An equal number of male and female training participants | Output 3.1: 100 government officials (with an equal number of men and women) trained to guide / direct urban development considering climate change and disaster risks and impacts, using especially spatial planning guidelines and tools. | Training records/registers taken, showing an equal number of men and women attended and completed the training | Women will equally participate in these activities | Equal participation of women in these interventions are planned | Satisfactory
The strategy and guidelines consider the particular and differentiated vulnerability, adaptation and development needs of women | Output 3.2. One National urban strategy focused on climate change / disaster risk reduction developed One set of National guidelines for spatial planning considering climate change / disaster risks developed | The strategy and guidelines are complete, with inputs from various gender experts, including UN_Habitat, ROAP/HQ specialists and the women's development department. | No document existst on Urban Policy and strategy | Women will equally participate and it will furhter enhanced in the planned activities in the implementation of activities | good
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
Genrally, in Pakistan the urban devlopment sector is male dominated and limited opportunities exist for women populations to partivipte in deceision making and implementation of development activities. The same challenge is also faced by the project. however due to its nature of activity and importance directly related to women, the project is considering and attracting women participation due to water management and drought mitigation. Households level water management issues and water availability in most of the cases in the country is primary responsibility of the women. As most of the male members of the household spent their day time out of houses in search of employment and for their businesses. Therefore women are responsible for water management and arrangement, and have more attraction for participation and implementation of the project activities. |  | Good
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Implementing Entity through different meetings, workshops and correspondense have informed the all Executing Entities (EE) /Impleneting Partners (IPs) of the project to take consideration of the gender equity and partcipation of women in all project activities. The EEs/IPs have adopted the propsal and working on the same directions.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes, the Implementing Entity has been monitoring the women participation in different intervntions of the project being implemented by the partners. It has been noted that women are participating in the meetings and discussions for planning, decision making to implementation of the field activities.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | The EE are considering and inviting participation of women for all its activities. It has also been observed by the IE that EEs are working on the gender friendly and women participation perspectives in the project implementation. It is also pricipally agreed between the IE and EEs that women participation will be ensured in all project interventions including training prograames, awareness campagis and planning meetings throughout the project implementation.The Executing Entity (EE) M/s Shehersazz has in compliance to this guideline has ensured required %age of women participation through indcution of 50% women staff in its project team, formed women support groups, and involvement of the equal women partcipants for planning meetings and awareness raising workshops. Women, both as staff members as well as volunteers, were inducted in the field teams in both cities. This is particularly helpful in the social mobilization process aiming to ensure that women participation in the project activities is materialized. Formation of women support groups at the field level to maximise the participation of women in the overall project cycle. This is also important to ensure that young women are also taking active part in the overall project. At least two women organisation are in the process of formation in both cities, which are formed part of the overall community organization structure. This will also include the women and young people-led monitoring committees. Women have also been given prominent place in the beneficiary/household selection process.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | Yes. So far in the implementation of activities women participation has been seen satisfactory. About 50% women participation is being obsereved in the ongoing activities of the project, and it is anticipated that the participation will enhance in the current and coming years.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | So far no such capacity gaps are identified. However, challenge of women participation in projects like this are being addressed through planning, advocacy, communication, motivation and effective coordination.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8] |  | Yes, right from the inception phase of the project a consent/declartion form has been designed and communicated to the beneficiaries to identify and record the grievances and complaints. This is a consent form and is accessible to the beneficiatres, partners and communities. However it is noted that so far no grievances and complaints are received related to gender equity and women empowerment.
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
So far, no grievance and complaints have been received in this regard,. |  | N/A

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project Outcomes/Outputs |  | Expected Progress |  | Progress to Date | Rating
Project Objective is to: Enhance community, local and national-level urban climate change resilience to water scarcity caused by floods and droughts in Rawalpindi and Nowshera, Pakistan
By Project Manager | Outcome-1.1: Increased adaptive capacity within the water sector at community level – 38,885 people – at least half 50% (19,443) of whom women - benefitting directly from rain-water harvesting facilities (7 people per household) and around 200,000 indirectly.Iin line with AF Outcome 4
| Output 1.1: 5000 community / household level flood resilient (i.e. elevated to not be affected by flood water) rainwater harvesting facilities constructed, using innovative techniques |  |  |  | Agreement of Cooperation (AOC) has been signed with the Implemnting Partner The M/S Shehersaaz Welfare Trust. The Implemnting pPartners has initiated activities in the the filed. Communities have been mobilised, project cooperation groups are formed and installation of the Rain water Harvesting Units have been started. So far 12 community-base Rain Water Harwesting Units have been installed and the impementation and construction and installation of other planned Rain Water Harvestiong Units are under progress. | S
Outcome-1.2: Strengthened awareness of flood and water risks and impacts and how to address these at community level and ownership of rainwater facilities built. In line with AF outcome 3
| Output 1.2: 15 union/neighbourhood council-level community plans developed (7 in Rawalpindi/8 in Nowshera), community members (especially women and youth) trained and practical guide developed to plan, construct, operate, maintain and replicate water harvesting at community level, and to reduce waste in drainage channels through awareness raising campaigns |  |  |  | Under the same AOC signed with M/S Shehersaaz preparation of plans has been initiated in both the Rawalpindi and Nowshera cotied. So far two communit-based draft adaptation pland have been prepared. The other are under process. | S
| Output 1.3: Awareness campaigns in all target communities to reduce dumping of solid waste in drainage channels. |  |  |  | Under the above same AOC signed with M/S Shersaaz Welfare Trust, the activity has been initiated and two campaigns have been launched in this regard. | S
Outcome-2.1: Increased adaptive capacity within the water sector at district / city level by identifying water management structures recommended on other critical interlinked structures through spatial planning. In line with AF outcome 4
| Output 2.1: 50 district / city-level water harvesting facilities in public buildings and on water storages in public gardens constructed |  |  |  | Letter of Aagreements with Implementing Partners: Water and Sanotation Aithority in Rwalpindi and Tehsil Municipal Admnitration in Nowshera has been shared and are under process of signing between the Implementing Agency and the Implementing Partners. Field acyivities ware planned for implementation soon after signing of LOUs with both of these partners. | S
Outcome-2.2: Strengthened urban level government capacity to reduce climate change related flood and drought risks, also beyond city boundaries. In line with AF outcome 2
| Output 2.2:Two district / city-level spatial planning strategies developed considering climate change risks and impacts, especially floods and droughts, and including comprehensive water harvesting plans.These strategies are decision-making tools for cities to assess climate change related floods, droughts and water scarcity to plan for and manage climate change-related risks and impact in and beyond city boundaries, taking into consideration multiple sectors. |  |  |  | Letter of Undestanding (LOU) has been signed with National Disater Management Authority (NDMA) amd field activities have been initiated, | S
| Output 2.3: 50 government officials trained and guidelines developed to plan, construct, operate, maintain and replicate flood resilient water harvesting facilities and to enhance capacity in developing spatial plans |  |  |  | Letter of Understanding (LOU) has been signed with the Pakistan Council of Resarch in Water Resources (PCRWR). Activities have been initiated. | S
Outcome-3.1: Strengthened national level government capacity to reduce climate change related risks and impacts in urban areas. In line with AF outcome 2
| Output 3.1: 100 government officials (women / men) trained to guide / direct urban development considering climate change and disaster risks and impacts, using especially spatial planning guidelines and tools. |  |  |  | Under the above mentioned LOU signed with NDMA, the activities has been initiated. Training Need Assessment and Target Group Profiles are being developmed. | S
Outcome-3.2: Policies and plans improved to respond to urban climate change risks and impacts. In line with AF outcome 7
| Output 3.2: One National urban strategy focused on climate change / disaster risk reduction developed One set of National guidelines for spatial planning considering climate change / disaster risks developed |  |  |  | Draftv Letter of Understanding is being rebiewed by the Ministry of Climate Change and project documents are under preparation. Soon will be signed to initiate field activities on this output. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Khalil Ahmed/National Project Manager/AF Project
| Email: | khalil.ahmed@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project was started during hot days when Covid-19 emerged as pandemic worldwide. Like other countries Pakistan also suffered a lot from this challenge. Even Inception Workshop was organised half physical and half vertual. Soon after Inception Workshop a prologed lock-down was prevailed and forced by the Government in the entire country. Due to this pandemic physical meetings and consultations could not be arrnged with implementing partners. Due to the situation hiring of project staff also got delays. and after passing of half of theyear the Covid-19 situation became slow and Government also relaxed the lock down in the country.Despite of the hot pandemic situation in the country and still it prevails, the project team through hardwork and proactive approach has initiated work on preparation and signig of agreements with the Implementing Partners of the project. The Rating of the progress on activities is carefully done, and progress on the so far initiated activities is reported as Satisfactory.It is expected that onward progress on project activities will be expedite through effective coordination and cooperation with IPs of the Pakistan's Adaptation Fund Project.
| Project components/outcomes |  | Expected Progress |  | Progress to Date | Rating
By Implementing Agency/UNHABITAT | Outcome 1.1: Increased adaptive capacity within the water sector at community level – 38,885 people – at least half 50% (19,443) of whom women - benefitting directly from rain-water harvesting facilities (7 people per household) and around 200,000 indirectly. |  | 10% of the work will be furnised |  | Agreements have been signed, and Field work on the activities have been initiated in both of the project cities. 5% work has been achieved and remaining is under progress. A this was the first year of the project, the progress in the coming year will be very fast. | S
| Outcome 1.2: Strengthened awareness of flood and water risks and impacts and how to address these at community level and ownership of rainwater facilities built. |  | 20% |  | Agreement of Cooperation has been signed, funds have been released to the Implementing Partners and 10% of progress on the activitiy has been achied and the remaining target is under progress., It is planned and pushed in the field levels and will be achied soon. | S
| Outcome 2.1: Increased adaptive capacity within the water sector at district / city level by identifying water management structures recommended on other critical interlinked structures through spatial planning. |  | 30% of the planned activities under this out put to be achieved |  | AOC has been signed and activities are kicked off. 20% activities have been achieved so far. | S
| Outcome 2.2: Strengthened urban level government capacity to reduce climate change related flood and drought risks, also beyond city boundaries. |  | 30% progress to be furnished |  | Letter of Understanding (LOU) with implementing Partners was signed and field actovites have been initiated. More than 25% progress has been achieved on the activity. | S
| Outcome 3.1:Strengthened national level government capacity to reduce climate change related risks and impacts in urban areas. |  | 25% |  | After signing of the LOU with Impleeting Partnwr work has been initiated. Alamost 20% of the progress has been achieved on the activity planned. | S
| Outcome 3.2: Policies and plans improved to respond to urban climate change risks and impacts. |  | 10% to be achieved so far |  | So far documentation has been prepared and under process of approval by the Implenting Pattner. Only 5% progress has been achieved in this regard. Bilateral cooperation with the implementing parner is under active lines. And the remaining progress will be achieved soon. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Laxman Perera, Project Leader, Human Settlements Officer, UN-Habitat Regional Office, Fukouka japan
| Email: | laxman.perera@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project was initiated during start of the Corona crisis and peak months of the Covid-19 pandemicin Pakistan. Due to several cahllenges including the health issues, official lock downs and other restriction imposed by the national government, the activities atarted with a low pace in the field. The other challenges such as centralised approval procedures and review of the AOC documents through different sectors also taken a lot of time during kick off period of the project. The other challenges followed by the above was the slow and lenghty payment processes of the project funds.However coping with all the above challenges and procedures now the EE M/S Shehersaaz Welfatre Trust has initiated part of its activities n the both of the project cities in Nowshera and Rawalpindin in Pakistan. It is expected that project progress will be expedited onwards in the remaining period of the project life.
| Project components/outcomes |  | Expected Progress (Number/Targets) |  | Progress to Date | Rating
| Outcome-1.1: (by Shehersaaz) Increased adaptive capacity within the water sector at community level – 38,885 people – at least half 50% (19,443) of whom women - benefitting directly from rain-water harvesting facilities (7 people per household) and around 200,000 indirectly |  | 5000 |  | AOC has been signed and implentation is under progress. So far 12 Rain water Harvesting Units have been unstalled on the community housees in rawalpindi and Nowsher cities. | S
| Outcome-1.2: (By Shehersaaz) Strengthened awareness of flood and water risks and impacts and how to address these at community level and ownership of rainwater facilities built. |  | 35 |  | Agreement has been signed and fiels acticities are being implemented under the AOC by the Implemnting Partner.So far four targets have been achiesed. | S
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | Outcome 2.1 (a): By WASA:- 30 district / city-level water harvesting facilities in public buildings and on water storages in public gardens constructed in (Rawalpindi) |  | 30 |  | LoU is under process | S
| Outcome 2.1 (b): By TMA:- 20 district / city-level water harvesting facilities in public buildings and on water storages in public gardens constructed in (Nowshera) |  | 20 |  | LOU is under process | MS
| Outcome 2.2: By NDMA:- Strengthened urban level government capacity to reduce climate change related flood and drought risks, also beyond city boundaries In line with AF outcome 2 |  | 2 |  | LOU signed and activities initiated | S
| Outcome 2.3: (BY-PCRWR) 50 government officials, including 20 women trained and guidelines developed to plan, construct, operate, maintain and replicate flood resilient water harvesting facilities and to enhance capacity in developing spatial plans |  | 50 |  | LOU signed and activities are initiated | S
| Outcome 3.1: (By NDMA) Strengthened national level government capacity to reduce climate change related risks and impacts in urban areas. In line with AF outcome 2 |  | 100 |  | LOU signed and activities initiated | S
| Outcome 3.2: (By MoCC) Policies and plans improved to respond to urban climate change risks and impacts. In line with AF outcome 7 |  | 2 |  | LOU is under process | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Ms. Almas Shakoor, Executive Director, Shehersaaz Welfare Trust, Islmamabad. Email: almas@shehersaaz.org.pk
| AF Outcomes |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1.1 | Community adaptive capacity level increased through continuous water availability during flood periods | 0 | Instalation of Community RWH units, preparation of climate resilience palns and awareness campaigns on DRR and water harvesting and drought resilience have been initiated and started contributing towards the outcome. | All target communities have continuous water availability throughout regular and mega flood periods
Output 1.1 | No. of HHs with new RWH facilities experiencing reduced impacts from poor water qualities resulting from floods | 0 | Field activities have recently been initiated and 12 community based/household level Rain Water Harvesting facilities are installed | 5000 community / household level flood resilient (i.e. elevated to not be affected by flood water) rainwater harvesting facilities constructed, using innovative techniques
Outcome 1.2 | Government and community capacity improved through plans, guidelines and training | 0 | Activities on the planned outcome have been initiated. | 38,885 people (19,443 women) have the requisite knowledge to adapt to the impacts of flooding, especially in water quality
Output 1.2 | 15 plans developed, 300 community members, including 150 women, trained, and 1 set of guidelines and knowledge products developed | 0 | Work on preparation of 2 Plans have been initiated through review of literture and collection of data under the planned output. Initial user guidelines and knowledge products are also developed. | 15 union/neighbourhood council-level community plans developed (7 in Rawalpindi/8 in Nowshera), community members (especially women and youth) trained and practical guide developed to plan, construct, operate, maintain and replicate water harvesting at community level, and to reduce waste in drainage channels through awareness raising cam-paigns
Output 1.3 | Campaign materials produced | 0 | Cleaning drives of channels were condcuted on Solid Waste Management. 1000 awareness brouchers, three social media accounts have been established. | Awareness campaigns in all target communities to reduce dumping of solid waste in drainage channels.
Outcome 2.1 | Capacity increased at the district/municipal level | 0 | The outcome level contribution through signing of the LOUs have been initiated. | Adaptive capacity through public RWH facilities is in place
Output 2.1 | No. of public Rain Water Harwesting (RWH) facilities constructed | 0 | Activity is not initiated during progress reporting year. | 50 district / city-level water harvesting facilities in public buildings and on water storages in public gardens constructed
Outcome 2.2 | Increased government decision-making capacity at thedistrict/municipal level | 0 | Field activities on the planned outcome have been initiated. | District/municipal ca-pacity for planning and decision making in-creased through strate-gies and guidelines
Output 2.2 | No of decision makers/governme nt staff with increased knowledge through the two strategies developed | 0 | Activity is not yet initiated | Two district / city-level spatial planning strategies developed considering climate change risks and impacts, especially floods and droughts, and including comprehensive water harvesting plans.These strategies are decision-making tools for cities to assess climate change related floods, droughts and water scarcity to plan for and manage climate change-related risks and impact in and beyond city boundaries, taking into consideration multiple sectors.
Output 2.3 | No. of officials trained, disaggregated by gender, guidelines developed and adopted | 0 | Activity is not initiated during progress reporting year | 50 government officials trained and guidelines developed to plan, construct, operate, maintain and replicate flood resilient water harvesting facilities and to enhance capacity in developing spatial plans
Outcome 3 | Increased government decision-making capacity at the national and provincial level | 0 | Letter of Undertanding ( AoCs) are being signied to iniiate activities on the planned outcome. | National level capacity for planning and decision making increased through training and national strategies
Output 3.1 | No. of officials trained, disaggregated by gender | 0 | This activitity is not yet initiated | 100 government officials (women / men) trained to guide / direct urban development considering climate change and disaster risks and impacts, using especially spatial planning guidelines and tools
Output 3.2 | One strategy and, One set of guidelines developed | 0 | Activity is not yet initiated during progress reporting year | One National Urban Strategy focused on climate change / disaster risk reduction developed, and; -One Set of National guidelines for spatial planning considering climate change / disaster risks developed

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1-The Covid-19 pandemic was the most important challenge faced by the project during its first year of implementation. Due to severe impact of the Virus in the year 2021; meetings and agreements with the implementing partners could not be discussed and finalised rapidly. This also badly affected the project progress. 2-Due to change in Government policies regarding foreign funding and NGOs working procedures in Pakistan have created a challenge in the initial times of implementation of the project. So after condcuting series of meetings with selected Government Implementing Partners (IPs) and NGOs, the issue was discussed and then it was placed in the first Project Steering Committee meeeting for further discussion and guidance. After discussion the PSC in its first meeting discussed the existing Agreement of Cooperation (AOC) and decided to take up the matter with Legal office of the UNHABITAT to process the case for conversion of AOC into Letter of Understanding (LOU) so that the Government Exctung Entities are facilited to enter into a formal partnership in the AF project. The acttion on the PSC decision was taken and case was submitted to was submitted to the Legal Office for review and approval. Now the LOU has been finalised and approved by the Legal Office. The project has shared the LOU with the Government IPs to for their submission with technical proposals and re-sending it to UN-Habitat Cuntry office through LOU. 3-At present the project activities are remotely managed from ROAP and Nairobi Offices. The Country Office is responsible for day to day implementation of the project activities but due to very limited financial and administrative delegation and availability of resources at Country Office level affecting the project performance. The issue has been discussed and measyres are being considered to streamline the process as much as possible.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes, serious delays were occured in the first year of implementation of the project due to Cobid-19 pandemic and changing government policies. To cope up with these causes; the modality of alternate-home based work modality, review of the AOC and its conversion into LOU and the vertual mode of implemntation of interventions were adapted. The four-year work plan was also revised and re-aligned and got approval from the Project Steering Committee (PSC).
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design). | No such changes in the project design have been made so far. However the template of legal document has been adjusted inline with the Government policies.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Envrironmental and social safegurads are being considered during implementation of the project activities. These have proofed effective and beneficiaries are appreciating the safeguards. For example, vulnerable and women headed households are being considered in different committees and in decision making so that social inclusion of the marginilised groups are ensured in partcipation in the project interventions and benefits. Similarly environmental friendly installtion of the Rain Water Harvesting Facilities through developing guidelines on use of materials in projects are being considered in the field activities. The approach has encouraged by many households in communities to adopt the Rain Water Harvesting Units at their own expenses who can afford the cost. The AF project has helped in forging partnershipwith Federal Flood Commisssion (FFC) for upscaling teh concept. It has led to development of a joint project with UNHABITAT and FFC in Islamabad to adopt the similar approach for overcoming the flood and drought challenges of Islamabad. The city of Islamabad is located in the ustream of the AF project site.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender participation in various activities of the project are being considered in every intervention at different levels. This happens from planning, implementation and monitoring of the project activities. In Project Steering Committee two women members are working and representing the women segment of the society. At district and field levels women are being considered as integral part of the committees and as well as beneficiaries of the project. In so far implemented field activities almost 50% participants of meetings, workshops and awareness campaigns were from the women members of the communities. The approach has created a positive impact both on the society and on the climate resilient development initiatives at Government and communities as well in the project areas and also at the national levels.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | UNHABITAT
Type of implementing entity | MIE
Country | Pakistan
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries | description | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 2011235 | 389035 | 1622200 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 50% | 50% | 50% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Inland flooding | 1: Ineffective | Total | 6 | Inland flooding | 5: Very effective | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Multi-sector | National | 3: Risk and vulnterability assessments completed or updated | 2 | Multi-sector | National | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Multi-sector | 2: Low capacity | Total | 150 | Multi-sector | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 150 | 50% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 2: Low capacity | Public | National | Multi-sector | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 0 | National | Multi-sector | 2: Low capacity | 4 | National | Multi-sector | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 50% |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 17 | 50% | 5: Fully aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 0 | 20% to 39% | 2: Partially not aware |  | 200 | 40% to 60% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | technical guidelines | National |  | 2 | Technical guidelines | National
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Multi-sector | National | 1: Non responsive (Lacks all elements ) |  | Multi-sector | National | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | National |  | Disaster risk reduction | 2 | National |  | Disaster risk reduction
|  | 0 | Multi-community |  | Water management | 5050 | Multi-community |  | Water management
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 1: None |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | National | Other policy | 1 | Multi-sector | National | Orher policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 1 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness