Enhance community, local and national-level urban climate change resilience to water scarcity, caused by floods and droughts in Rawalpindi and Nowshera, Pakistan

RESPONSE PLAN ON RECOMMENDATIONS OF MID-TERM EVALUATION OF PAKISTAN’S ADAPTATION FUND PROJECT

| RECOMMENDATIONS | RESPONSE PLAN | ESTIMATED TIMELINE FOR ACTION |
| --- | --- | --- |
| Current project implementation scenario |  |  |
| Description: The AF project term ends in December 2025, leaving only 13 months for reaching the target of interventions, namely the installation of 3,700 rooftop water harvesting units at household level (in Nowshera and Rawalpindi), 20 rooftop water harvesting units in public buildings in Nowshera, and the preparation and adoption of the Urban Development Strategy by the MoCC&EC as major milestones. Shehersaaz, the local CSO responsible for the installation of RWHU at household level, has been able to complete 1,300 units in 15 months (broken into smaller contracts of 3, 4 and 8 months). The average burn rate has been USD 27,986/month at the maximum during this period. The CSO has the mandate to spend approx. USD 2 million in 13 months (USD 166,666/month) that seems to be an uphill task, though they have a dedicated and competent team and have been able to do some anticipatory preliminary work. On the other hand, the TMA Nowshera is all set to achieve its target of 20 RWHU units in government buildings, given the account matters are settled on time. The MoCC&EC has yet to take start on the preparation, validation and approval of Pakistan’s First Climate Resilient National Urban Development Strategy and related guidelines. Whereas the deliverable is going to be an important milestone for Pakistan, the administrative procedures are causing delays, leaving the longer time periods required for strategy development and approval on one side. Recommendation: Keeping in view these limitations, it is appropriate to recommend a no-cost extension of at least one year till December 2026. The extension will also allow to properly and effectively consolidate and disseminate the project learnings and achievements at local, sub-national and national level. | - Actively coordinating and maintaining continuous follow-ups, engaging in dialogues, and facilitating discussions with the delayed partners and key stakeholders to ensure swift progress. - A new Agreement of Cooperation (AOC) has been signed with Shehersaaz, and activities have begun. The progress of the EE will be closely monitored and facilitated so that the activities can be completed within the agreed timeframe. Once the EE completes all agreed activities within the given time, another AOC will be signed to accomplish the remaining task. UN-Habitat has discussed with the EE that as the milestone approaches, the preparation of the AOC will begin to avoid gaps between AOCs. If there is any delay in implementation, additional time will be required beyond 2025. - TMA Nowshera is in the process of submitting the draft Letter of Understanding (LOU) to implement the project activities. If this submission is completed in the first quarter of 2025 and the activities are initiated promptly, they can be finished by December 2025. However, if there is a delay in signing the LOU, additional time may be required beyond 2025. It is important to note that the delay is entirely due to government bureaucracy. - MoCC&EC is expecting the approval of its PC-1 from P&DD during January 2025. If this occurs, account opening for the project may take two additional months, and progress will be closely monitored. UN-Habitat will send an official letter to MoCC&EC to expedite the process. It is important to note that the delay is caused by government bureaucracy. - Key Action: By June 2025, the ground situation will be clear, and by then, if still progress remains slow, a further 12 months no-cost extension from January to December 2026 will be requested from the AFB. | - Progress will be monitored and bi-monthly assessed to ensure milestones are achieved. In June 2025, there will be an overall assessment to measure the achievement of committed units. - The decision for a one-year no-cost extension will be considered based on the progress of the EE and the situation on the ground at that time (EE Shehersaaz). - If progress cannot be expedited, a no-cost extension request will be initiated by July 2025 (TMA Nowshera and MoCC&EC). |
| 2. Future Prospects |  |  |
| Description: Among the pressing environmental challenges Pakistan is faced with (e.g. floods, GLOFs, sea water intrusion, droughts etc.), the AF project has been able to highlight another looming challenge on the urban front. Our urban population, currently standing at 85.6 million, is expected to touch 118 million by 2030. This urban population is faced with floods and droughts, mainly owing to improper solid waste management, dis-functioning and aging of drainage systems, and encroachments, merging into poor urban planning. The more recent environmental hazard has been the extremely low Air Quality Index in major cities because of smog. The AF project has successfully demonstrated some strategies at local, district and national level to address some of these problems. However, there is lot more to be done in terms of bringing in regional and global proven strategies, expanding the scope of existing ones and engage more stakeholders for policy impact. The rooftop RWH needs to be coupled with water filtration and ground water recharge, the UC level community based urban planning needs to be institutionalized and replicated in other cities, the Multi-Hazard Risk & Vulnerability Assessment process need to be converted into a viable urban planning tool in mega cities, the urban strategy needs to be followed by Climate Resilient Urban Action Plans for mega cities, and the institutional capacity building needs are only some aspects where immediate response is required. Recommendation: On rational grounds, the successes of the AF project need not to be ended with a halt. A logical follow-up may include a 3-years next phase with increased scope and volume or the development of a new full-fledge project with more partners and increased technical and geographical scope. | - The matter was discussed during the Project Steering Committee meeting of the AF project held in December 2025. - Key Action: Once the Designated National Authority (DNA) of the Government of Pakistan confirms budget availability from AF to Pakistan, UN-Habitat will develop a concept note for AF's consideration. | 2025 |
| 3. Improvement in the effectiveness, efficiency and sustainability |  |  |
| 3a. Enhance local community engagement and ownership: The partnership with Community Based Organizations (CBOs) and elected bodies of local representatives need to be strengthened to improve project transparency and beneficiary targeting. CBOs can be instrumental in mobilizing communities, facilitating communication, and ensuring fair selection, particularly of vulnerable households. These forums can also play a very effective role if monitoring committees are formed within each targeted Neighborhood or Union Council to oversee the installation, operation, and reporting of project interventions. Training these committees can encourage a sense of ownership and responsibility for project success. In addition, these forums can steer a process whereby the active engagement of women, youth, disabled and other marginalized groups will be ensured in decision-making processes at the community level. CBOs and local councils can help guarantee that these groups are fairly represented. | - In the current project, all EEs were directly selected during the project design phase. Therefore, partners working with the same selected organizations (EEs) was mandatory. Community members, leaders and champions are already involved in the project processes. The EEs responsible for the community component will be further advised to enhance the participation of community institutions, local community members, people with disabilities and marginalized and youth segments during the remaining period of the current project. As recommended in the mid-term evaluation, we will ensure the participation of CBOs and local body representatives through the implementing partner, Shehersaaz. | January to December 2025 Progress will be monitored and assessed every two months to ensure effective actions are implemented. |
| 3b. Strengthen horizontal and vertical institutional coordination and capacities: Establish regular coordination meetings involving UN-Habitat, WASA, TMA, PCRWR, NDMA, and Shehersaaz to synchronize efforts and share insights. Enhanced communication can help support each other and reduce bottlenecks. On the other hand, the engagement of Urban Policy Units (UPUs) at the provincial level in Punjab and Khyber Pakhtunkhwa can strengthen the provincial-level integration to enhance urban resilience strategies and establish a unified approach to climate-resilient planning. These UPUs can be the best place to take advantage of climate risk based spatial planning tools (MHRVAs). Vertically, the Public Health Engineering Department in Punjab, and the Local Government & Rural Development (LGRD) in Khyber-Pakhtunkhwa need to be looped in to have a policy impact of the innovations. Imparting additional training on advanced techniques, such as climate-resilient spatial planning, groundwater recharge methods, and monitoring using GIS, will ensure that local and national institutions are well-prepared to manage and sustain project outcomes. | - At present, all relevant stakeholders are engaged in planning, decision making and technical support as and when required. Regular meetings are also held with these partners. These organizations are coordinated and connected by establishing a Project Steering Committee. Coordination will be improved through quarterly steering committee meetings and monthly coordination meetings with the proposed stakeholders in the current project. | January to December 2025 Progress will be monitored and assessed every two months to ensure effective actions are implemented. |
| 3.c. Improve project implementation efficiency: The approval and disbursement of project funds need to be streamlined. The fund transfers to Tehsil Municipal Administration (TMA) Nowshera and Ministry of Climate Change & Environmental Coordination (MoCC&EC) need to expedited by pre-authorizing budgets and standardizing fund request procedures. Ensuring quicker fund access will enable partners to complete their planned activities within set timelines. On the other hand, partnership arrangements at the grassroots level with the CSO (Shehersaaz) require a longer but target oriented approach, going beyond the ad-hoc policy if the targets are to be achieved on time. This need to be coupled with regular and transparent monitoring and progress reporting. Conducting monthly project progress reviews with partners to track timelines and deliverables may be considered. Provide transparent updates on challenges, solutions, and timelines to all stakeholders to maintain alignment on project goals. | - The progress of TMA and MoCC&EC is actively being accelerated through Project Steering Committee meetings and regular coordination meetings with the project team. Moving forward, we will ensure more efficiency by maintaining consistent communication, conducting follow-ups via phone and email, and sending timely reminders. - Shehersaaz has received technical support since the beginning of the project to help build its capacity to deliver its components. Shehersaaz will be further supported to improve coordination at the community level during the remaining period of the project. The EE will also be monitored closely. | January to December 2025 Progress will be monitored and assessed every two months to ensure effective actions are implemented. |
| 3.d. Optimal use of resources: The use of resources must also be optimized by reviewing the resource allocation to ensure that each component has sufficient funding. In some cases, where the rooftop rainwater harvesting is not much effective (e.g. in Nowshera where the annual rainfall is minimal), the option to relocate funds for alternate water harvesting technologies may be considered. In both the project districts, local communities expressed a high demand for water filtration to make the water drinkable. Also, in case of RWH units installed in parks and public buildings where space availability is not an issue, the ground water recharge options may be added to the existing units. Similarly, if resource availability allows, the linking of stored water to normal water infrastructure (water supply pipes) in the households and in public buildings may be considered. This may require the addition of simple sand and gravel filtration system in the RWH units. | - The current project primarily focuses on rooftop rainwater harvesting and storage at the household level for domestic use. It is not possible to change the project's scope and design during its implementation. - In future projects suggested components will be incorporated into the project design and will be complied with as recommended, as it fits. | To consider at the time of developing a concept note for a follow-up project. |
| 3.e. Strengthen data collection, monitoring, and reporting: A centralized project monitoring system may be developed by implementing a central data repository to store and analyze geo-referenced data on water harvesting installations, beneficiary demographics, and project progress. Such a system will support evidence-based decision-making and simplify tracking of long-term outcomes. The Shehersaaz is already using a geo-referenced system for monitoring, and the same may also be replicated by WASA and TMA. The data for such a system will be generated by a participatory local monitoring system, empowering the local partners in their monitoring roles. The partners may be provided training on data collection and reporting, allowing them to play a more active role in monitoring. This will improve accuracy in reporting and foster transparency and accountability. This system may further be supplemented by incorporating feedback loops. Establishing a process for collecting and acting on feedback from beneficiaries obtained through regular satisfaction surveys and community forums can help identify unanticipated issues with system functionality or benefits. | - The M&E Section of the project is developing an online portal that will effectively streamline the sharing, management, and monitoring of data and reports generated under the current AF project. Once the portal is finalized and established, it will be effectively harmonized and shared, ensuring accessibility for all EEs, key stakeholders, and researchers. This will facilitate future consultations and serve as a reliable reference at both local and global levels. | First quarter of 2025. |
| 3.f. Expand capacity for water and waste management training: For the community to solve the problems of water contamination and sanitation arrangements at local level, the training and awareness campaigns have already been conducted by the Shehersaaz. However, a step ahead is required to identify innovative residents or households and enable them to adopt waste and water management practices. This may include, for example, the provision of water filtration kits, kitchen gardening kits (tools and seeds), and organic waste composting (inputs). The innovative households or individuals may be linked to markets to earn income from their practices, and may be highlighted as ‘Water Champions” by giving awards and certificates. This can be a best way to engage energetic youth in water harvesting, management and conservation. | - Community-level water champions have been definitively identified through targeted awareness campaigns and meetings, and they are playing a crucial role in the current project. | January to December 2025 Progress will be monitored and assessed every two months to ensure effective actions are implemented. |
| 3.g. Scale-Up Gender and youth Inclusion, and support for vulnerable populations: Urban climate risks, particularly in the water sector, may have more impact on women as compared to men, because of specific hygiene requirements and their household responsibilities for fetching water. In Rawalpindi and Nowshera, this can also be an opportunity for them to promote themselves as entrepreneurs in urban resilience. Increasing training opportunities for women in technical aspects of rainwater harvesting, water filtration, compost making, kitchen gardening and other innovative waste management can contribute in empowering urban women as entrepreneurs. The youth can play vital role in bringing in change and sustain it for generations. Tailored programs for youth engagement can be designed youth, including school-based activities and local internships with TMA and WASA. Educating youth on climate resilience practices will cultivate a generation of informed advocates for urban resilience. The RWH facilities provided in most of the households are accessible to people with disabilities. In few households, the units are installed on 1st floor which may not be accessible to people with limited mobility. This is very important that water harvesting systems and community facilities are accessible for people with disabilities. This might include designing installations that accommodate limited mobility and involving disabled groups in planning discussions. | - In the community component, the participation and engagement of women and youth have remained the primary focus of the current project. This approach will continue for the remaining duration of the project. The Monitoring and Evaluation (M&E) team will closely monitor disaggregated data collection. - The EEs of the project will be guided to consider the convenience of families with persons with disabilities while installing the remaining rainwater harvesting units at the project sites. - A formal letter will also be sent to the EEs of the AF project, advising them to ensure access and convenience for persons with disabilities at the household level during the establishment of the Rainwater Harvesting units. | January to December 2025 Progress will be monitored and assessed every two months to ensure effective actions are implemented. |
| 3.h. Promote replication and policy integration at the national level: The National Urban Strategy Development may be accelerated by prompting the Ministry of Climate Change & Environmental Coordination to complete the national urban strategy for climate resilience. This strategy should include guidelines for water scarcity mitigation, flood management, and sustainable city planning, forming a model that other cities in Pakistan can replicate. At the same time, there is a need to build a case for policy and funding support. The project successes may be used to advocate for budget allocation at the provincial and national levels to support urban resilience efforts beyond Rawalpindi and Nowshera. The UN-Habitat, MoCC&EC, WASA and TMA should present results in national forums to drive policy adjustments and attract additional funding. One of the options may also be to engage private companies in the water and waste management sectors, particularly those with expertise in environmental solutions (e.g. water harvesting, waste management and recycling, sanitation, water filtration etc.), to create a broader coalition around urban resilience. Collaboration with the private sector can bring in innovative solutions and co-financing opportunities for long-term sustainability. | - During the preparation and consultation workshops under the LOU of the MoCC&EC, the suggested components will be discussed and included in the draft National Urban Strategy. - Once the National Urban Strategy is formulated, efforts will be made to implement the components of the strategy related to UN-Habitat components. - Future projects will enhance collaboration with the private sector through dialogues, consultations, and building linkages in water harvesting, waste management, sanitation, water filtration, and recycling. | April to December 2025 |
| 3.i. Establish a long-term plan for post-project sustainability: Sustainability of the proven project strategies to address climate induced water scarcity in urban areas must be targeted through multi-pronged approach. One of the strategy could be to promote rainwater harvesting in building codes. Advocating with Urban Policy Units, MoCC&EC and TMAs for the integration of rainwater harvesting requirements in building codes, particularly for new construction in urban flood-prone areas can prove successful. Sharing of lessons, best practices and challenges across different stakeholders can create visibility but also add to replication and scalability of the proven strategies. Annual forum for all project stakeholders, including community members, institutional partners, and local governments, may be organized to share lessons learned, discuss ongoing needs, and highlight achievements. This will reinforce community networks and encourage continuous improvement in resilience strategies. | - The Government of Pakistan has now approved green building codes facilitated by UN-Habitat. A project can be developed to implement green building codes in major cities of the country. - A national-level workshop for relevant stakeholders and partners will be organized at the end of the current project to share and disseminate lessons learned, knowledge developed, and best practices. | Last quarter of 2025 (national-level workshop) |