## Overview
Project Performance Report (PPR)* (2nd PPR of Pakistan AF Project)
* Refers to both projects and programs
| Period of Report (Dates) | JANUARY 2022 TO DECEMBER 2022
| Project Title: | Enhance community, local and national-level urban climate change resilience to water scarcity, caused by floods and droughts in Rawalpindi and Nowshera districts in Pakistan
| Project Summary: | Pakistan's Climate Resilience Project Funded by the Adaptation Fund is a joint venture of the Government of Pakistan, Civil Society Organisations and the UNHABITAT. The project is being implemented in two districts of the conuntry; Rawalpindi district lies in the Punjab province while the second project district is Nowshera which falls in the Khyber Pakhtunkhwa province. In Rawalpindi seven (7) union councils (UCs) and in Nowshera district eight (8) Neighbourhood Councils (NCs) are selected for implemntation fo the project interventions. Main objective of the proposed project is to “enhance community, local and national-level urban climate change resilience to water scarcity, caused by floods and droughts in Rawalpindi and Nowshera cities.” This will be achieved through the following proposed sub-objectives: 1. Community level: Enhance community and household level flood resilient water harvesting facilities (using innovative techniques) and strengthen capacities to plan, construct, operate, maintain and replicate these. 2. District / City level: Enhance city and district-level water harvesting facilities in public buildings and on water storages in public gardens, develop district / city-level spatial strategies as tool to assess climate change re-lated floods, droughts and water scarcity to plan for and manage climate change risks and to strengthen ca-pacities to plan, construct, operate, maintain and replicate water harvesting facilities in public buildings and gardens. 3. National and Provincial level: Strengthen national and provincial-level capacity to guide / direct city-level development considering climate change and disaster risks and impacts, especially water scarcity caused by floods and droughts. There are five Government departments and authorities and one civil societyorganisation as Implemnting Partners in the project. As per agreed workplan of the project Letter of understandings have been signed with two Government Agencies and one Civil Society Organisaton for implemention of the planned actiovities. In this regard LOUs have been signed with Pakistan Council of Research on Water esources (PCRWR) and the National Disater Management Authority (NDMA) and also Agreement of Cooperation has been signed with Shehersaaz Weldfare Trust. Further LOUs with Ministry of Climate Change and WASA Rawalpindi are under process of approval at the ROAP Office of the UNHABITAT. meanwhile negotiations for signing of LOU with TMA Nowshera are also in the pipeline. The project progress is as per schedule with some initial delays in impleentation due to Cocin 19 challenges in the first year; i.e 2021.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNHABITAT | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | PAKISTAN | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Rawalpindi city in Punjab Province and Nowshera city in Khyber Pakhtunkhwa Province. Seven Union Councils in Rwalapindi and eight neibourhood councils in Nowshera are being targetted under the project interventions. In Rawalpindi city following Union Councils are targetted: UC # 1 Ratta Amral UC # 2 Dhoke Ratta UC # 4 Dhoke Mangtal UC # 5 Dhoke Hassu North UC # 6 Dhoke Hassu South UC # 12 Dhoke Najju UC # 37 Dhoke Dalal. In Nowshera City following 8 Neighbourhood Councils (NC) are being benefitted from the project: 1. Dagi Khel 2. Allah Yar Khel 3. Nawan Kali 4. Shahmeer Gari 5. Bara Khel 6. Behram Khan Khel 7. Mana Khel 8. Kabul River | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2020-01-06
IE-AFB Agreement Signature Date: |  | 2020-01-06 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2020-12-22 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2023-06-01
2024-06-30
Original Completion Date:
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | www.unhabitat.org.pk | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Khalil Ahmed/National Project Manager | Dominican Republic
| Email: | khalil.ahmed@un.org | Ecuador
| Date: | 1st July 2021 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Mr. Muhammad Farooq/Senior Joint Secretary Development, Ministry of Climate Change, Islamabad | Equatoral Guinea
| Email: | mfarooqbehram@gmail.com | Eritrea
| Date: | 3rd February 2023 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Mr. Jawed Ali Khan | Fiji
| Email: | jawed.ali-khan@un.org | Finland
| Date: | 1st January 2020 | France
| Executing Agency |  | Gambia
| Name: | Muhammad Ashraf/ Chairman, Pakistan Council of Research in Water Resources (PCRWR) | Georgia
| Email: | muhammad_ashraf63@yahoo.com | Germany
| Date: | 1st January 2022 | Ghana
| Executing Agency |  | Greece
| Name: | Mr. Raza Iqbal/ Director Implementation, National Disaster Management Authority (NDMA) | Grenada
| Email: | dirimp@ndma.gov.pk | Guatemala
| Date: | 1st May 2022 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Muhammad Tanveer/Managing Director, Water and Sanitation Agency, Rawalpindi | Guyana
| Email: | wasarawalpindi@yahoo.com | Haiti
| Date: | 1st September 2022 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [FEB 18, 2022] |  |  |  | Financial information PPR 2: cumulative from project start to [31 DEC 2022] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [enter Date] | 137305 |  |  | Estimated cumulative total disbursement as of [December 2022] | 436475 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | The project has been operationlised during July 2021. Initially due to Covid 19 pandemic and also due to changing Government polies the project was delayed and faced slow implementation. |  |  | Add any comments on AF Grant Funds. (word limit=200) | The project has been operationlised during July 2021. Initially due to Covid 19 pandemic and also due to changing Government polies the project was delayed and faced slow implementation. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1 5000 community / household level flood resilient (i.e. elevated to not be affected by flood water) rainwater harvesting facilities constructed, using innovative techniques (Provided to EE) | 25000 |  |  | Output 1.1: 5000 community / household level flood resilient (i.e. elevated to not be affected by flood water) rainwater harvesting facilities constructed, using innovative techniques | 50000
[5 empty] | Output 1.2: 15 union/neighbourhood council-level community plans developed (7 in Rawalpindi/8 in Nowshera), community members (especially women and youth) trained and practical guide developed to plan, construct, operate, maintain and replicate water harvesting at community level, and to reduce waste in drainage channels through awareness raising cam-paigns | 7000
[5 empty] | Output 1.3: Awareness campaigns in all target communities to reduce dumping of solid waste in drainage channels. | 5000
[5 empty] | Output 2..2: Two district / city-level spatial planning strategies developed considering climate change risks and impacts, especially floods and droughts, and including comprehensive water harvesting plans.These strategies are decision-making tools for cities to assess climate change related floods, droughts and water scarcity to plan for and manage climate change-related risks and impact in and beyond city boundaries, taking into consideration multiple sectors. | 150000
[5 empty] | Output 2.3:50 government officials trained and guidelines developed to plan, construct, operate, maintain and replicate flood resilient water harvesting facilities and to enhance capacity in developing spatial plans | 90000
[5 empty] | Output 3.1:100 government officials (women / men) trained to guide / direct urban development considering climate change and disaster risks and impacts, using especially spatial planning guidelines and tools. | 30000
| PROJECT EXECUTION COST | 25000 |  |  | PROJECT EXECUTION COST | 332000
| IMPLEMENTING ENTITY FEE | 112305 |  |  | IMPLEMENTING ENTITY FEE | 104475
| TOTAL | 137305 |  |  | TOTAL | 436475 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: 5000 community / household level flood resilient (i.e. elevated to not be affected by flood water) rainwater harvesting facilities constructed, using innovative techniques | 800000 | 2023-03-01 |  | Output 1.1: 5000 community / household level flood resilient (i.e. elevated to not be affected by flood water) rainwater harvesting facilities constructed, using innovative techniques | 495000 | 2024-06-30
| Output 1.2: 15 union/neighbourhood council-level community plans developed (7 in Rawalpindi/8 in Nowshera), community members (especially women and youth) trained and practical guide developed to plan, construct, operate, maintain and replicate water harvesting at community level, and to reduce waste in drainage channels through awareness raising cam-paigns | 150000 | 2023-03-01 |  | Output 1.2: 15 union/neighbourhood council-level community plans developed (7 in Rawalpindi/8 in Nowshera), community members (especially women and youth) trained and practical guide developed to plan, construct, operate, maintain and replicate water harvesting at community level, and to reduce waste in drainage channels through awareness raising cam-paigns | 50000 | 2023-12-20
| Output 1.3: Awareness campaigns in all target communities to reduce dumping of solid waste in drainage channels. | 50000 | 2023-03-01 |  | Output 1.3: Awareness campaigns in all target communities to reduce dumping of solid waste in drainage channels. | 45000 | 2023-12-20
| Output 2.1: 50 district / city-level water harvesting facilities in public buildings and on water storages in public gardens constructed | 655000 | 2023-03-01 |  | Output 2.1: 50 district / city-level water harvesting facilities in public buildings and on water storages in public gardens constructed | 850000 | 2024-06-20
| Output 2..2: Two district / city-level spatial planning strategies developed considering climate change risks and impacts, especially floods and droughts, and including comprehensive water harvesting plans.These strategies are decision-making tools for cities to assess climate change related floods, droughts and water scarcity to plan for and manage climate change-related risks and impact in and beyond city boundaries, taking into consideration multiple sectors. | 200000 | 2023-03-01 |  | Output 2..2: Two district / city-level spatial planning strategies developed considering climate change risks and impacts, especially floods and droughts, and including comprehensive water harvesting plans.These strategies are decision-making tools for cities to assess climate change related floods, droughts and water scarcity to plan for and manage climate change-related risks and impact in and beyond city boundaries, taking into consideration multiple sectors. | 350000 | 2023-12-20
| Output 2.3:50 government officials trained and guidelines developed to plan, construct, operate, maintain and replicate flood resilient water harvesting facilities and to enhance capacity in developing spatial plans | 40000 | 2023-03-01 |  | Output 2.3 Target: 50 government officials trained and guidelines developed to plan, construct, operate, maintain and replicate flood resilient water harvesting facilities and to enhance capacity in developing spatial plans | 10000 | 2023-12-20
| Output 3.1:100 government officials (women / men) trained to guide / direct urban development considering climate change and disaster risks and impacts, using especially spatial planning guidelines and tools. | 70000 | 2023-03-01 |  | Output 3.1: 100 government officials (women / men) trained to guide / direct urban development considering climate change and disaster risks and impacts, using especially spatial planning guidelines and tools. | 70000 | 2023-12-20
| Output 3.2: One National Urban Strategy focused on climate change / disaster risk reduction developed, and; -One Set of National guidelines for spatial planning considering climate change / disaster risks developed | 110000 | 2023-03-01 |  | Output 3.2: One National Urban Strategy focused on climate change / disaster risk reduction developed, and; -One Set of National guidelines for spatial planning considering climate change / disaster risks developed | 114900 | 2023-12-20
| PROJECT EXECUTION COST | 2075000 |  |  | Total Activity Cost planned by Executing Entititie | 1984900 | 2023-12-20
[5 empty] | PROJECT EXECUTION COST | 169500 | 2023-12-20
| IMPLEMENTING ENTITY FEE | 353915 |  |  | IMPLEMENTING ENTITY FEE/Project Cycle Manageent | 184415 | 2023-12-20
| TOTAL | 2428915 |  |  | TOTAL | 2338815 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
ENVIRONMENTAL RISKS:
Current climate and seasonal variability and/or hazard events result in infrastructure construction delays or undermine confidence in adaptation measures by local communities | Low | Activities are planned according to seasonal siutability, and all implementing partners are well coordinated by the project team.
INSTITUTIONAL/SOCIAL:
Loss of government support (at all levels) for the project (activities and outputs) may result in lack of prioritization of AF project activities | Medium | The planned Government Implementing Partners of the project are being facilitated and supported in preparation and finalisation of the LOU document on need basis. Out of six IPs 3 agreements have been signed and activities are initiated so far.
Capacity constraints of local institutions may limit the effective implementation of interventions | Low | Capacity of the partners is built upto a minimum required levels through meetings, trainings and consultation workshops for implementation of their resepctive outputs planned under the Adaptation Fund Project.
Communities that have given their consent to the project may revoke their consent (which they have the right to do) or may become unhappy that the project doesn’t match their expectations | Medium | Communities shown greater interst and actively particpating in the activites. The implementing partners of the project condcut meetings with the beneficiary communities before starting of each activity of the project.
Disagreement amongst stakeholders with regards to adaptation measures (infrastructure) and site selection. | Low | All stakeholders are involeved in their respective outputs and performing according to their agreed action plans.
Communities may not adopt activities during or after the AF project, particularly infrastructure maintenance | Low | A consent proforma has been developed and signed before start of field activities related to community participation and sustainability of the interventions by the Implementing Partners.
Delays in project implementation, and particularly in the development of infrastructure interventions | Medium | To cope with delays and to expedite progress on the interventions, the four-year plan of the project has been re-aligned and got approved from the project board. Activities are being implemented accordingly
A lack of coordination between and within National Government Ministries and Departments | Low | All activities are beig implemented in a coordinated manner. Implementing agencies are delivering the out puts as per agreed schedule and workplan.
FINANCIAL RISKS:
Complexity of financial management and procurement. Certain administrative processes could delay the project execution or could lack integrity | Medium | Partcipatory planning is being done. Regular coordination meetings with implementing parters are held and so far field activities are as per agreed plans.
LEGAL RISK:
Delays or barriers in gaining approval for infrastructure and housing due to delays in the development process or due to land tenure issues | Low | Activities are timely planned. Sufficient timeframe is given to the implementing partners and activities are being imlemented as per agreed schedule of deliverables.
SECURITY RISKS:
The security situation reduces access to the target sites, and/or makes it unsafe to visit | Low | All field visits are carefully planned. Before moving to project sites, the UNDSS is informed and security advisory is obtained well in time.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Long approval processes of leagal agreemetns will delay transfer of funds to Implementing Partners of the Project from UNHABITAT | Medium | Participatory planning is being done with all implementing partners. The project team assisted the partners in expediting the documentation process through technical support and backstopping in preparation of required dcuments well in time.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The project activities are being re-adjusted and LOUs and AOCs are extended according to overall workplan as there were significant delays of activities due to COVID19 in 2020 which affected overall progress. The IP work plans are discussed with the partners to re-adjust the LOUs and AOC with Implementing Partners. So far all risk mitigation measres such as regular meetings, technical assistance to the partners and regular monitoring of the risk has helped in mitigating the risk described above. In the times of delays or capacity issues at the imlementing partners, the project team has assisted in preparation of necessary documents, work plans and also trainied the officials of the implementing partners in the project design and implementation of field activities. oordination mechnisms have alo been enhanced among the partners to share experiences and best practices. As result of all these efforts the stakeholders and implementing patners of the project have reaised the importance of the project and are showing keen interest in its implementation.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 - Access and equity |  |  | There is a potential risk that, without risk avoidance or reduction measures, for the target beneficiaries to benefit inequitably, or for some groups to be excluded altogether. | Community memebers equally both men and women are being trained and involved to operate and manage the RWH units under Output 1.1 as a means to reduce the potential for inequitable access. Women are being given an equal role in the management. Community planning has been included in the project design as a means to enhance ownerships and reinforce principles of equitable participation and benefit sharing. In the training and capacity building programmes women participation is also being maintained by Implementing Partners of the project. | Gender equal water user groups formed and operational, SOPs prepared, Reports developed. | The each EE will produce monitoring baseline for their respective outputs as per agreed implementation plan. | The Implementing Partners ensuring the equal participation of the both genders in awareness campaigns, trainings and other activities. Records of both men and women participation are maintained in reports. | Women would be impacted to a greater degree than men, as evidenced by experiences elsewhere in Pakistan | Water user groups are being formed with adequate female particiaption. Consultations have been initaited. Ensuring that Women will be given adequate space for their voice during meetings and consultations. The community plans are also being prepared by joint groups of both men and women including the marginalised segments to maximise equitable access to facilities, prevention of discrimination against women, children, the elderly or disabled, as well as to ensure fair and equitable distribution of water, its sustainability and future adaptation.
3 – Marginalized and vulnerable Groups |  |  | There is a posiibility of discrimination against the women groups and afghan migrant populations , who do not appear on official population figures in the target areas but whose presnecece was evident in the community consultations. | Women have been fully integrated into the community management, decision-making and maintenance structures designed by the project. Community plans will also be implemented to ensure the fair distribution of water. Project ‘champions’ in the community will be on hand to help illiterate community members (more likely to be women) to play a more active role. | Men and women have equal access and get equal benefit; equal access for migrant families; and surveys, informal interviews, and focus groups. | Records are maintained at EE level. The UNHABITAT will compile data on annual basis. | Reports are prepared, Gender segrated data is being maintained by IPs | Women and other marginlised groups such as afghan migrants may be discriminated and not receive services. This would be a mal-adaptive situation for the marginlised groups in the project area. | Community cahmpions and members of the committees in each area are formed and will be responsible to ensure that every one benefits from the project interventions. Executing Entities of the project will also record the aggregated data in this regard.
4 – Human rights |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 – Gender equality and women’s empowerment |  |  | The potential for women to benefit inequitably, or face discrimination exists | Women will play an active and decisive role in the community management of the project, enhancing their participation, and greatly reducing the risk that they will be excluded. | Women are in decision making positions at the community level, regarding the RWH facilities, and are trained in operation and maintenace. | Labour laws are regulary monitored and so far no such observations are recorded. | Records are maintained by the IPs and No descrimination cases are reported so far. | There is possibility of the mal-adaptation situation for women | Process has been initiated through designing and signing of agreements with community groups in both of the project sites. to address the risks associated with this issue.
6 – Core labour rights |  |  | There is a possibility that the labour engaged from the communities for unskilled tasks may be underpaid, given insecure work, or face occupational health and safety risks. | All labourers employed to work during the construction of the RWH facilities will be formalized, working under legally binding contracts, in compliance with Pakistan’s labour laws and, where these are insufficient, ILO standards and guidelines. All executing entities will be contractually obliged to uphold these standards. salaries and wages paid to these labours and workers will be fair and will be well above the minimum wage. | All workers have proper contracts, in compliance with the law, paid above minimum wage. Contracts, reporting, workers testimony gained through informal discussions. | Measures are ensured through ensuring practivce consideration of labour laws & policies in procurement and implementation of field activities by EEs | The matter is regularly monitored and so far no issues have been observed in this regard. | People may end up working excessive hours for the project without formal cotracts and or receiving unfairly low salaries below the minimum wages. | All the Executing Entities have been advised by the UNHABITAT to strictly observe the ILO rules and policies and also local government policies regarding payment to the labour working under the project in Pakistan.
7 – Indigenous peoples |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 – Involuntary resettlement |  |  | The risk of resettlement is very negligible. However, there is a risk of some temporary disruption of access to homes while construction takes place, and some disturbance in terms of noise and construction workers in the area. | Communities will also be fully briefed on the exact nature of the construction works before they begin, including the expected duration, the disruption expected and the grievance mechanism. | All people have unhindered access to their houses throughout, and there is no damage. Photographs, testimony gained through informal discussions | So far no such cases reported. | The indicator is being monitored and no evidence of such cases is reported yet. | People would be temporarily inconvenienced by construction activities. No resettlement. Damage is highly unlikely, but potentially possible. Though it would be very minor in nature. | People are taken fully on board before start of every activities at the household levels. SOPs are designed and agreement/consent forms are alos designed and got signed before start of work on suchactivities.
9 – Protection of natural habitats |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10 – Conservation of biological diversity |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 – Climate change |  |  | There could be a risk of some nominal but unnecessary emissions rising from the project. | Local materials will be used throughout the construction. All hardware required by the project (i.e. tanks, pipes and pumps) are available locally in both cities, meaning that emissions relating to transportation will not be necessary. To that end, all procurement documents will emphasise the need to use locally sourced materials and avoid imports. No additional emissions are expected from the activities. | Local materials will be used throughout the procurement. Proper procurement documents will be prepared. | No climate issues from the project are reported so far. | The matter is observed regularly and no such impact has been recorded yet. | A slight increase in the GHG emmissions | Local and environment friendly materials are being procured and ensured through the Executing Entities to keep the GHG emmissions under the control and minimized.
12 – Pollution prevention and resource efficiency |  |  | There is a risk that without effective management and mitigation measures, there coukd be unnecessary and harmful disposal and dumping of waste and surpus construction material. | UNHABITAT has advised all Executing Entities of the AF project to assure that waste materials are disposed of being the official waste management services provider. All construction workers will be trained on proper procedures to dispose of waste materials generated during the construction, to ensure that there is no risk of improper disposal. Agreements of Cooperation will stipulate that executing entities are responsible for proper disposal of waste materials and they will be subject to periodic monitoring. | All waste effectively disposed off and procedures are advised in procurement documents and photograps. | No such issues have been reported untill now. | The issue is being monitored and no complaints are recorded so far. | Very lminimal contribution to environmental pollution and GHG | Guidelines are prepared by the E.Es for proposer disposal of such waste and are implemented accordingly.
13 – Public health |  |  | There is a risk of contamination and improper management that could lead to the spread of water-borne diseases and; secondly these is a risk of occupatonal health and safety issues arising while construction is ongoing | Health and safety trainings and sessions will be provided for all construction works, and necessary safety equipment, such as boots and hard hats provided. The IPs of the AF project working under the agreements with UN-Habitat are respinsible to make it. These provisions should be seen in conjunction with those under core labour rights, and are designed to keep the construction workers safe, first and foremost. All construction sites will be demarcated, with fencing, barriers and cones, as appropriate to ensure that community members not involved in the construction are safe, and don’t inadvertently walk into areas where construction is ongoing. | Safety training provided, protective gear available, Photos and reports. Water hygiene practices observed. Training materials. | No public health issues reported so far from the project activities. | Record is maintained by the I.Ps, and no such issues have been observed so far. | Water-borne diseases are unpleasant and debilitating for people in the target area, and particularly affect those already vulnerable. A lack of occupational health and safety standards and procedures could result in injuries to workers. | After installation of units at household levels the first water stored in the RWH units are being tested for its usefuness and safety for drinking purposes, The EEs are advised to assure it before the communities start using such stored Rain water: SecondlyTrainings are being condcuted before start of practical work, field gears are also provided to the community members and labours before start of the construction work by implemnting pratners.
14 – Physical and cultural heritage |  |  | There is no direct risk on the heritage sites. However a small risk on few existing buildings of mosques, community centres and such other buildings. | All construction sites will be demarcated effectively. Before works commence, as part of the full and informed prior consent process, the anticipated disruption to public buildings during construction will be discussed with building managers and building users/surrounding communities (i.e. parents in the case of schools). Construction workers will be trained to ensure there is minimal reduction to public building users, especially where the public buildings in question are schools, and as far as possible, construction will take place outside of school hours. In the case of mosques, no construction will take place on Fridays or at prayer times. | Buildings continue there function, and there is no differece to their aesthetics. | No such issues have been recorded. | Record is maintained and no harmful incidents are repored so far. | Though construction does not directly affect heritage buildingsor areas, there could be some temporarydisruption of access or appreciationof heritage buildings without management and mitigation measures. | UNHABITAT has advised all Executing Entitities of the AF project to assure that such listed buildings and vicinitay are not altered and remain functional during implementation of project activities.
15 – Lands and soil conservation |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | YES
Have unanticipated ESP risks been identified during the reporting period? |  | NO
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | During implementation of the acivities ESP measures are being checked for compliance in all project interventions. The Implementing Entity (IE) in its meetings with EEs have advised on social inclusion and environmental safeguarding in implementation of the project field activities. For this purpose check lists are being prepared before initiation of the activitities and agreements are drafted and signed acordingly.
Have the implementation arrangements been effective during the reporting period? |  | YES
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The Executing Entities are fully aware of the implementation of the ESP safeguard measures. To achieve the puropse; Invitation Letters, Training Modules and Guidelines are being prepared keeping in view of all the ESP safeguarding mesaures are included. These required mesaures are communicated to communities and implementing partners by the EE for compliance from time to time on reglular and need basis. Details for each EE are provided below: Shehersazz: Shehersaaz has designed the community particpation modalities to ensure that women and vulnerable groups are included in the project activities and progress monitoring inlcudes gathering of disaregated data to ensure such particpation. For environmental safeguards the shehersaaz also has been using knowladge materials in local language and techniques to ensure less damages to the local environment and minimum disturbance to the families during implnetation of activities. The EE NDMA ensures women and vulnerable groups participation is in the activities and progress monitoring inlcudes gathering of disaregated data to ensure such particpation. NDMA also ensured from the planning phase and to further assurance they have employed a female experts to facilitate field activities. The team of NDMA hold meetings with the target communities with adequate women particpiation taking their opinions in developing the spatial plans for two target cities.The environmnetal rehabilitation and safety programmes are also being cosidered in the documentation. The EE m/s PCRWR has ensured participation of women and vulnerable segments of the society in its four training programmes condcured through the project. the project guidelines and training manual also have considered and recommended to use enviromnet friendly materials and constructions under the project interventions and progress monitoring inlcudes gathering of disaregated data to ensure such particpationThe same approach is being to be adopted with other EEs, to whom with the AOCs and LOUs are under discussion and to be signed in the coming quarters.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | YES
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | N/A
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | N/A
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances received from the partners and stakeholders so far |  | N/A
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | YES
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | YES
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Discussions and decisions in communities are gedner equal, disagreegated and equal participation of women in community-based activities ensured | Output 1.1: 5000 community / household level flood resilient (i.e. elevated to not be affected by flood water) rainwater harvesting facilities constructed, using innovative techniques | Engineer’s survey complete, and describe in detail how the needs of women (particularly women who work in the home) have been incorporated Equal number of men and women participate. Attendance registers taken (anonymised) that identify numbers of men and women | No households have RWH facilities and all experience poor quality water during regular and mega floods | 5000 households (38,885 men and 19,443 women have RWH facilities) | Satisfactory
Equal number of women particopate in trainings, planning and decision makingTraining for community members trains an equal number of men and women (150 men, 150 women, 300 total) An equal number of male and female community champions identified Community-scale plans equally consider the needs of men and women. Women’s adaptation and development needs are fully incorporated | Output 1.2: Fifteen (15) union/neighbourhood council-level community plans developed (7 in Rawalpindi/8 in Nowshera), community members (especially women and youth) trained and practical guide developed to plan, construct, operate, maintain and replicate water harvesting at community level, and to reduce waste in drainage channels through awareness raising cam-paigns | Training complete with records documenting equal participation from men and women Community champions identified and a brief profile made including recording gender Community plans prepared and reviewed by the Project Manager and PSC | There are no plans in place, no guidelines to support local government or communities and individual knowledge/ capacity is low | 15 community plans developed and adopted | Good
Campaighn material is developes as that also target women, and through media that women are likely to access and benefit | Output 1.3: Awareness campaigns in all target communities to reduce dumping of solid waste in drainage channels. | Campaign materials developed and reviewed by the project manager and PSC | There are no regular or recent awareness campaigns on the rain water related issues | 300 community members including 150 women have the required capacity and guidelines are well understood | Good
Training for managers of public buildings will include sensitivity to women/ensuring that the needs of women are highlighted | Output 2.1: 50 district / city-level water harvesting facilities in public buildings and on water storages in public gardens constructed | Training materials prepared that clearly highlight the risk and vulnerability of women, and how the project promotes safeguarding their interest | No training materials and awareness and knowledge products have been developed oreviously | 50 district/city level RWH facilities constructed and functional, benefitting up to 150,000 people (of whom at least 75,000 will be women) | Satisfactory
The MHVRA and spatial strategies will full consider the differentiated risks and vulnerabilities of women, their adaptation options and potential and outline proposed actions that specifically benefit women | Output 2.2: Two district / city-level spatial planning strategies developed considering climate change risks and impacts, especially floods and droughts, and including comprehensive water harvesting plans | The MVHRA complete with comprehensive analysis of the differentiated risks and vulnerabilities of women, and adaptation options that benefit them | No MHVRAs are condcuted previously in these two cities | 2 city level spatial plans to be developed also considering the women needs for adpatation | Good
20 female officials included in the training All training materials consider the differentiated and/or particular needs of women | Output 2.3: 50 government officials, including 20 women trained and guidelines developed to plan, construct, operate, maintain and replicate flood resilient water harvesting facilities and to enhance capacity in developing spatial plans | Training complete with documentation to show that at least 20 women participated throughout. All training materials clearly indicate the need to consider the particular and differentiated adaptation needs of women | No training materials and awareness and knowledge products have been developed oreviously | 50 officials including 20 women trained on planning, construction and maintenance as well as developong spatial plans | Good
An equal number of male and female training participants | Output 3.1: 100 government officials (with an equal number of men and women) trained to guide / direct urban development considering climate change and disaster risks and impacts, using especially spatial planning guidelines and tools. | Training records/registers taken, showing an equal number of men and women attended and completed the training | Women will equally participate in these activities | 100 officials including 50 women trained and have sufficient knowledge to plan considering climate change adaptation needs and disater risks | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
N/A |  | N/A
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Implementing Entity through different meetings, workshops and correspondense have informed the all Executing Entities (EE) /Impleneting Partners (IPs) of the project to take consideration of the gender equity and partcipation of women in all project activities. The EEs/IPs have adopted the proposal and have ensured gener women participation in the project interventions.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes, the Implementing Entity has been monitoring the women participation in different intervntions of the project being implemented by the partners. It has been noted that women are participating in the meetings and discussions for planning, decision making to implementation of the field activities and the training programmes of the AF project..
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The EE M/S Shehersaaz has formed citizen groups incorporating equal proportion of men and women. These groups take decisions for both men and women in the field activities of the project. The EE M/S PCRWR has adopted to include both men and women in its all training programmes. And so far more than 20 women have attended the traing programmes organised by the EE. The process was initiated from inivitation stage to encourage the women participants in the trainings. The EE M/S NDMA is also considerigwomen participation in its training programmes and also in the foeld surveys regarding the MHVRA mapping and planning. It has also been ensured that all EEs are working on the gender friendly and women participation perspectives in the project implementation. It is also principally agreed between the IE and EEs that women participation will be ensured in all project interventions including training prograames, awareness campaigns and planning meetings throughout the project implementation.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes. So far in the implementation of activities women participation has been seen satisfactory. Women are equaly benefitting from the project interventions.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | So far no such capacity gaps are identified. However, challenge of women participation in project activities are being addressed through planning, advocacy, communication, motivation and effective coordination.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances have been received nor recorded so far. |  | N/A
Yes
No
Partially

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: UNHABITAT | Output-1.1: 5000 community / household level flood resilient (i.e. elevated to not be affected by flood water) rainwater harvesting facilities constructed, using innovative techniques |  | Outcome 4 | 5000 community based household-level Rain Water Harvesting (RWH) Units to be installed |  | 34 RWH Units have been installed so far, and activitiy is being implemented as per agreed work plan with the IP M/s SheherSaaz. | S
| Output-1.2: 15 union/neighbourhood council-level community plans developed (7 in Rawalpindi/8 in Nowshera), community members (especially women and youth) trained and practical guide developed to plan, construct, operate, maintain and replicate water harvesting at community level, and to reduce waste in drainage channels through awareness raising campaigns |  | Outcome 3 | 15 community based adaptation and DRR plans to be developed |  | 04 plans have been developed so far | HS
| Output-1.3: Awareness campaigns in all target communities to reduce dumping of solid waste in drainage channels. |  | Outcome 3 | 35 awareness workshops will be organised |  | 04 awareness campaigns have been organised so far | HS
| Output-2.2: Two district / city-level spatial planning strategies developed considering climate change risks and impacts, especially floods and droughts, and including comprehensive water harvesting plans.These strategies are decision-making tools for cities to assess climate change related floods, droughts and water scarcity to plan for and manage climate change-related risks and impact in and beyond city boundaries, taking into consideration multiple sectors. |  | Outcome 2 | 02 Plans to be developed |  | Work on prpeparation of the plans has been initiated and data from the three cities have been gathered. Activituy is under preparatons. | S
| Output-2.3: 50 government officials trained and guidelines developed to plan, construct, operate, maintain and replicate flood resilient water harvesting facilities and to enhance capacity in developing spatial plans |  | Outcome 2 | 100 Government officials to be trained |  | 38 Government Officials with good partcipation of women has been trained. Remaining trainings are being implemented as per work plan. | HS
| Output-3.1: 100 government officials (women / men) trained to guide / direct urban development considering climate change and disaster risks and impacts, using especially spatial planning guidelines and tools. |  | Outcome 2 |  |  |  | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Khalil Ahmed/National Project Manager, Pakistan's Adaptation Fund Project
| Email: | khalil.ahmed@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project was started during December 2020 and in the begining like other countries Pakistan was also suffered due to severe prevalence of the Covid-19 Pandemic. Due to this pandemic physical meetings and consultations could not be arrnged with implementing partners untill June 2021. In that prevailing situation hiring of the project staff was also delayed. Soon after hiring of the project team during July 2021 the project activities were kicked off and formal meetings and consultations with selected Implementing Partners of the AF project were undertaken. Letter of Agreements signed and field activities have been initiated during the progress review year. So far two Letter of Understanding (LOUs) have been signed with Government Executing Entities PCRWR and the NDMA. Another final draft LOU has been submitted to UNHABTAT's ROAP office for final approval and signature ith WASA Rawalpindi. One Agreement of Cooperation (AOC) has also been signed with the community base civil society M/S SheherSaaz Welfare Trust. The Rating of the progress on activities is carefully done, and progress on the so far initiated activities. The progress on the field activities is further being expedited through effective communication, coordination, support and cooperation with the Implenting Partners of the Project.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/IP M/s SheherSaaz: | 5000 community / household level flood resilient (i.e. elevated to not be affected by flood water) rainwater harvesting facilities constructed, using innovative techniques |  | Outcome 4 | 5000 rain Water Harvesting units to be installed |  | 34 RWH units have been installed so far as per plan | S
| 15 union/neighbourhood council-level community plans developed (7 in Rawalpindi/8 in Nowshera), community members (especially women and youth) trained and practical guide developed to plan, construct, operate, maintain and replicate water harvesting at community level, and to reduce waste in drainage channels through awareness raising campaigns |  | Outcome 3 | 15 |  | 04 plans have been developed | S
| 20 Awareness campaigns in all target communities to reduce dumping of solid waste in drainage channels. |  | Outcome 3 | 20 |  | 04 have been organised | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ms. Almas Shakoor/Executive Director Shehersaaz, Islamabad
| Email: | almas@shehersaaz.org.pk
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
After implementation of the small Scale Agreement of Cooperation under the Adaptation fund during 2021, the formal Agreement of Cooperation (AOC) was signed with the UNHABITAT by the Shehersaaz.Under the review year AOC activities were implemented and remaining activities are planned to be implemented in the coming months of the next year.The activities are as per agreed work plan.A carefull rating has been given considering the on-going progress on the activities.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | By IP PCRWR
| 50 government officials trained and guidelines developed to plan, construct, operate, maintain and replicate flood resilient water harvesting facilities and to enhance capacity in developing spatial plans |  | Outcome 2 | 50 |  | 38 | HS
By IP NDMA
| Two district / city-level spatial planning strategies developed considering climate change risks and impacts, especially floods and droughts, and including comprehensive water harvesting plans.These strategies are decision-making tools for cities to assess climate change related floods, droughts and water scarcity to plan for and manage climate change-related risks and impact in and beyond city boundaries, taking into consideration multiple sectors. |  | Outcome 2 | 2 |  | 25% | S
| 100 government officials (women / men) trained to guide / direct urban development considering climate change and disaster risks and impacts, using especially spatial planning guidelines and tools. |  | Outcome 2 | 100 |  | 10% | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
From IP/EE PCRWR-Name: |  | Mr. Muhammad Ashraf/Chairman PCRWR Islamabad
| Email: | muhammad_ashraf63@yahoo.com
From IP/EE NDMA-Name: |  | Mr. Raza Iqbal/Director Implementation NDMA, Islamabad
| Email: | dirimp@ndma.gov.pk
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Initaillay the signing of the Letter of Understanding (LOU) with the Government Implementing Partners PCRWR and NDMA took longer time than planned due to lenthy process to be adopted to resolve issues related to legal cluases in the agreement with the IP as a government body . After signing of the LOU the activities are initiated as per agreed work plans and progress is smooth. So far no critcal risks have been faced by the implementing partners who have initiated project interventions. Mid Term Review has not been planned yet. the MTR will be condcuted during the next year of the implementation.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1.1 | Community adaptive capacity level increased through continuous water availability during flood periods | 0 | Implementation of activities under the planned outputs have been initiated and contribution towards the outcome are in progress | All target communities have continuous water availability throughout regular and mega flood periods
Output 1.1 | No. of HHs with new RWH facilities experiencing reduced impacts from poor water qualities resulting from floods | 0 | 40 household level Rain Water Harvesting Units have been istalled and further progress on the activity under the agreement with IP is on-going | 5000 community / household level flood resilient (i.e. elevated to not be affected by flood water) rainwater harvesting facilities constructed, using innovative techniques
Outcome 1.2 | Government and community capacity improved through plans, guidelines and training | 0 | Preparation of community based adaptation and disater risk reduction plans are initiated. Guidelines are being developed and awareness campaighns are also being developed. | 38,885 people (19,443 women) have the requisite knowledge to adapt to the impacts of flooding, especially in water quality
Output 1.2 | 15 plans developed, 300 community members, including 150 women, trained, and 1 set of guidelines and knowledge products developed | 0 | 04 adaptation and risk mitigation plans two in Rawalpindi and two in Nowshera have been developed | 15 union/neighbourhood council-level community plans developed (7 in Rawalpindi/8 in Nowshera), community members (especially women and youth) trained and practical guide developed to plan, construct, operate, maintain and replicate water harvesting at community level, and to reduce waste in drainage channels through awareness raising cam-paigns
Output 1.3 | Campaign materials produced | 0 | 08 mass awreness campaigns have been developed on waste management, drought mitigation and rain water harvesting in the targetted sites of the project | Awareness campaigns in all target communities to reduce dumping of solid waste in drainage channels.
Outcome 2.1 | Increased adptive capacity within the water sector at district/ city level by identifying water management structures recommended on other critical interlinked structures through spatial planning in line with AF outcome 4 | 0 | Letter of Understanding is being finalised with the Executing Entities in both of the project sites to initiate field activities | Adptive capacity through public RWH facilities is in place
Output 2.1 | 50 district/cilty-level water harvesting facilities in public buildings and on water storage in public gardens constructed | 0 | Letter of Understanding is being finalised with the Executing Entities in both of the project sites to initiate field activities | 50 district/ city-level RWH facilities constructed and functional benefitting 75,000 men and 75,000women
Outcome 2.2 | Increased government decision-making capacity at thedistrict/municipal level | 0 | Activities under the planned outputs of his outcome has been initiated during the review year of the project | District/municipal ca-pacity for planning and decision making in-creased through strate-gies and guidelines
Output 2.2 | No of decision makers/governme nt staff with increased knowledge through the two strategies developed | 0 | An LOU has been signed with the EE M/S NDMA and field activities have been initiated as per agreed work plan. | Two district / city-level spatial planning strategies developed considering climate change risks and impacts, especially floods and droughts, and including comprehensive water harvesting plans.These strategies are decision-making tools for cities to assess climate change related floods, droughts and water scarcity to plan for and manage climate change-related risks and impact in and beyond city boundaries, taking into consideration multiple sectors.
Output 2.3 | No. of officials trained, disaggregated by gender, guidelines developed and adopted | 0 | An LOU was signed with the Implemnting Partner M/s PCRWR and two trainings have been condcuted. 38 officials from various relevant deparments have been trained so far. | 50 government officials trained and guidelines developed to plan, construct, operate, maintain and replicate flood resilient water harvesting facilities and to enhance capacity in developing spatial plans
Outcome 3 | Increased government decision-making capacity at the national and provincial level | 0 | Activities under the relevant outputs of this outcome have been initited. | National level capacity for planning and decision making increased through training and national strategies
Output 3.1 | No. of officials trained, disaggregated by gender | 0 | Activity is initiated. Training modiule has been developed and trainings will be organised in the coming months of the next year. | 100 government officials (women / men) trained to guide / direct urban development considering climate change and disaster risks and impacts, using especially spatial planning guidelines and tools
Output 3.2 | One National Urban Strategy Focused on climate change/ disater risk reduction and with comprehensive gender mainstreaming developed. One set of National guidelines for spatial planning considering climate change/ disater risks with comprehensive gender mainstreaming developed | 0 | Letter of Understanding is being finalised with the Executing Entiti to initiate the activity. | The national urban strategy and guidelines developed and approved, increasing knowledge at the national level, and faciltating national level replication

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The Covid-19 pandemic still remained as a challenge until mid of the current review year. Due to severe impact of the Virus in the first half of the year 2022; consultataion were delayed and agreements with the implementing partners could hardly be finalised. When EEs are government entities, finalizing legal agreements took longer than expected due to UN-Habitat legal tools are not go along with Governmnent of Pakistan legal tools. Therefore, extesive discussions took place to come to an agreement. The agreed legal toools can be used for future agreement.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Initial project delays due to COVID 19 has an overall impact of entire workplan.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | Prroject is being implemented as per its original design and no chages have been made so far.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Envrironmental and social safegurads are being considered during implementation of the project activities by the implementing partners. Environmental friendly locally available installtion of the Rain Water Harvesting Facilities through developing guidelines on use of materials in projects are being considered in the field activities. The approach has encouraged by many households in communities to adopt the Rain Water Harvesting Units at their own expenses who can afford the cost. Similarky social safeguards are also being implemented. For example, vulnerable and women headed households are being considered in different committees and in decision making so that social inclusion of the marginilised groups are ensured in partcipation in the project interventions and benefits.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | To ensure Gender equity; equal opportunities for both men and women are being ensured in the project implementation. This is being observed from planning and implementation to monitoring of the project activities. In Project Steering Committee two women members are working and representing the women segment of the society. At district and field levels women are being considered as integral part of the committees and as well as beneficiaries of the project. In so far implemented field activities almost 50% participants of meetings, workshops and awareness campaigns were from the women members of the communities. The approach has created a positive impact both on the society and on the climate resilient development initiatives at Government and communities as well in the project areas and also at the national levels. Women are also participating in the national level training programmes of the project implemented by the project partners from time to time.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | UNHABITAT
Type of implementing entity | MIE
Country | Pakistan
Region | Asia-Pacific
Sector | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 2011235 | 389035 | 1622200 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 50% | 50% | 50% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Inland flooding | 1: Ineffective | Total | 6 | Inland flooding | 5: Very effective | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Multi-sector | National | 3: Risk and vulnterability assessments completed or updated | 2 | Multi-sector | National | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Multi-sector | 2: Low capacity | Total | 150 | Multi-sector | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 150 | 50% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 2: Low capacity | Public | National | Multi-sector | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 0 | National | Multi-sector | 2: Low capacity | 4 | National | Multi-sector | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 50% |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 17 | 50% | 5: Fully aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 0 | 20% to 39% | 2: Partially not aware |  | 200 | 40% to 60% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | technical guidelines | National |  | 2 | Technical guidelines | National
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Multi-sector | National | 1: Non responsive (Lacks all elements ) |  | Multi-sector | National | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | National |  | Disaster risk reduction | 2 | National |  | Disaster risk reduction
|  | 0 | Multi-community |  | Water management | 5050 | Multi-community |  | Water management
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 1: None |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | National | Other policy | 1 | Multi-sector | National | Other Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 1 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness