## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 16 Dec. 2021 -30 Dec. 2022
| Project Title: | Enhancing the resilience inclusive and sustainable human settlement development in the coastal regions of the Mekong Delta in Viet Nam
| Project Summary: | The main objective of the proposed project is “to enhance the resilience, inclusive and sustainable eco-human settlement development through small scale infrastructure interventions in the coastal regions of the Mekong Delta in Viet Nam.” To align with a government request to promote sustainable eco-human settlement in Viet Nam, this project aims to improve the poor and vulnerable communes that climate change impacts have affected the most. It is structured around the following components: Component 1: Institutional and community capacity building toward eco-human settlement development for supporting enhance local climate response actions Component 2: Action plan and strategy development for eco-human settlement, and integrating into planning and policy with participatory approach Component 3: Sustainability built through small-scale protective infrastructure Component 4: Awareness Raising and Knowledge Management
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | VNM/MIE/Urban/2019/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Human Settlements Programme (UN-Habitat) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Viet Nam | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Coastal provinces of the Mekong Delta in Viet Nam: Bac Lieu and Tra Vinh provinces | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2020-06-01
IE-AFB Agreement Signature Date: |  | 2020-08-01 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2020-12-16 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
| Original Completion Date: | 2024-12-15
Revised Completion Date after approval of |  | N/A
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | 1. Inception report - submitted on 15 January 2021 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Nghia Le | Dominican Republic
| Email: | nghia.le@un.org | Ecuador
| Date: | 2021-12-01 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | H.E Tran Hong Ha - Ministry of Natural Resources and Environment | Equatoral Guinea
| Email: | thha@monre.gov.vn | Eritrea
| Date: | 2020-12-15 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Laxman Perera - UN-Habitat | Fiji
| Email: | laxman.perera@un.org | Finland
| Date: | 2020-12-15 | France
| Executing Agency |  | Gambia
| Name: | Tho Dinh Nguyen - Project Management Unit for HREMRD Project | Georgia
| Email: | thodinhnguyen@gmail.com | Germany
| Date: | 2021-08-18 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 03/03/2022 |  |  |  | Financial information PPR 2: cumulative from project start to 31/01/2023 |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31/01/2022 | 270567 |  |  | Estimated cumulative total disbursement as of [enter Date] | 602027 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | As per the signed agreement, the first instalment of USD 516,048 was received from AF. Out of this, the amount of USD 360,000 is committed to Executing Entities (EEs). The actual disbursement by 31/01/2022 to EEs is USD 116,107. The start date of the project implementation has been delayed until 5th November 2021 when the first AOC was signed, thus the delay of fund transfer and disbersement to/by PMU. The main reasons include: i) the change of the project owner together with time-consuming legal procedure and ii) spread of Covid-19 with traveling and meeting restriction regulation. |  |  | Add any comments on AF Grant Funds. (word limit=200) | As of June 2022, UN-Habitat has received 2 instalments from AFB, totaling up to USD 2,294,429. Out of this, the amount of USD 1,826,463 is committed to the designated Executing Entity (Project Management Unit). The actual disbursement by 31/01/2023 to EE is USD 325,158. The delivery of 2nd-year key milestones has been delayed, due to: i) late amendment of the agreement of cooperation with the PMU, resulted from late fund receipt; ii) internal structure rearrangement within the DoA, led to lengthy review and appraisal procedures; and iii) changes in the local context require re-assessment of the project interventions at chosen sites. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | N/A |  |  | INVESTMENT INCOME | N/A |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT | Est. Completion Date | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT | Est. Completion Date | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Activity 1.1.1: Inception workshop, Technical Advisory Group establishment and project's branding identity development | 20106.7 | completed in March - remaining 70% budget (excluding Inception WS) of $19,893 will be disbursed by mid/end of March 2022 |  | Activity 1.1.1: Inception workshop, Technical Advisory Group establishment and project's branding identity development | 38276.11 | completed in March 22. The remaining $1,723.89 can be allocate for other activity upon request of the EE
| Activity 1.1.2: Develop a guideline and training materials for vulnerability and risk assessment at the local levels | 21000 | partially completed - remaining 70% budget of $49,000 will be disbursed in March/April 2022 |  | Activity 1.1.2: Develop a guideline and training materials for vulnerability and risk assessment at the local levels | 64632.1836 | partially completed - remaining 35% budget of $35,367.82 will be disbursed in once the guideline is updated with new climate change scenarios and gender mainstreaming (Jun/Jul 23)
| Activity 1.1.3: Developing planning toolkits and training materials for planning approach, strategy and action plan development on climate change resilience | 24000 | partially completed - remaining 70% budget of $56,000 will be disbursed in March/April 2022 |  | Activity 1.1.3: Developing planning toolkits and training materials for planning approach, strategy and action plan development on climate change resilience | 75719.57 | partially completed - remaining 37% budget of $44,280.43 will be disbursed once the toolkit is updated with gender mainstreaming (Jun/Jul 23)
| Activity 1.1.4: To organize a training enabling facilitation of eco- friendly settlement strategy and action plan development | 24000 | to be completed by the end of March - remaining 70% budget of $56,000 will be disbursed in April 2022 |  | Activity 1.1.4: To organize a training enabling facilitation of eco- friendly settlement strategy and action plan development | 58487.69 | to be completed by Aug/Sep 23 - remaining 51% budget of $61,512.06 will be disbursed in Oct 23
| Activity 1.2.1: To organize a national workshop in HN or Can Tho and provincial workshop in Bac Lieu and Tra Vinh province to enable national/provincial governments to set up eco-human settlement strategy and action plan for climate change adaptation. | 27000 | to be completed by the end of March - remaining 70% budget of $63,000 will be disbursed in April 2022 |  | Activity 1.2.1: To organize a national workshop in HN or Can Tho and provincial workshop in Bac Lieu and Tra Vinh province to enable national/provincial governments to set up eco-human settlement strategy and action plan for climate change adaptation. | 65364.34 | to be completed by Aug/Sep 23 - remaining 78% budget of $234,635.66 will be disbursed in Oct 23
| PROJECT EXECUTION COST | 113908.8 | fully disbursed |  | Activity 2.1.1: Organise dialogue workshops at provincial level to develop a policy framework for integrating local's action plans and strategies for eco-human settlement into planning | 7559.37 | to be completed by Nov/Dec 23 - remaining 89% budget of $62,440.63 will be disbursed in early 2024
| PROJECT/PROGRAMME CYCLE MANAGEMENT FEE | 40551.76 | fully disbursed |  | Activity 2.2.1: Organise training workshops and dialogue workshops at provincial, district and commune levels to develop action plans and strategies for eco-human settlement | 7559.37 | to be completed by Nov/Dec 23 - remaining 91% budget of $72,440.63 will be disbursed in early 2024
[5 empty] | Activity 2.2.2: Organise dialogue workshops at provincial level to integrate the developed/revised action plans and strategies into the relevant/existing planning and policy | 7559.37 | to be completed by Nov/Dec 23 - remaining 85% budget of $42,440.63 will be disbursed in early 2024
[5 empty] | PROJECT EXECUTION COST | 202561.53 | fully disbursed
[5 empty] | PROJECT/PROGRAMME CYCLE MANAGEMENT FEE | 74307.01 | fully disbursed
| TOTAL | 270567.26 | In April 2022, overall disbursement rate will be 75% |  | TOTAL | 602026.5436 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Activity 1.1.2: Develop a guideline and training materials for vulnerability and risk assessment at the local levels | 30000 | May-Aug 2022 |  | Activity 1.2.1: To organize provincial, district, commune level workshop (in Long Hoa, Hoa Minh, Vinh Trach Dong, and Vinh Hau communes) | 120000 | Nov - Dec 2023
| Activity 1.1.3: Develop planning toolkits and training materials for planning approach, strategy and action plan development on climate change resilience | 40000 | May-Aug 2022 |  | Activity 2.1.1: Organise dialogue workshops at provincial level to develop a policy framework for integrating local's action plans and strategies for eco-human settlement into planning | 70000 | Jan-Feb 2024
| Activity 1.1.4: Organise a training enabling facilitation of eco- friendly settlement strategy and action plan development | 40000 | A training for 20 provincial experts was organized in Jan 2022. Other trainings: Sep 2022 |  | Activity 2.2.1: Organise training workshops and dialogue workshops at provincial, district and commune levels to develop action plans and strategies for eco-human settlement | 200000 | Jan-Feb 2024
| Activity 1.2.1: Organise a national workshop in HN or Can Tho and provincial workshop in Bac Lieu and Tra Vinh province to enable national/provincial governments to set up eco-human settlement strategy and action plan for climate change adaptation. | 210000 | Sep-Nov 2022 |  | Activity 2.2.2: Organise dialogue workshops at provincial level to integrate the developed/revised action plans and strategies into the relevant/existing planning and policy | 50000 | Feb-Mar 2024
| Activity 2.1.1: Organise dialogue workshops at provincial level to develop a policy framework for integrating local's action plans and strategies for eco-human settlement into planning | 80000 | Jun-Aug 2022 |  | Activity 3.1.1: Install 5 groundwater purification systems and 2 rainwater harvesting systems | 748044 | 2024-01-01
| Activity 2.2.1: Organise training workshops and dialogue workshops at provincial, district and commune levels to develop action plans and strategies for eco-human settlement | 70000 | Jun-Aug 2022 |  | Activity 3.1.2: Install 860m of eco-friendly infrastructure | 100000 | 2024-01-01
| Activity 2.2.2: Organise dialogue workshops at provincial level to integrate the developed/revised action plans and strategies into the relevant/existing planning and policy | 50000 | 2022-10-01 |  | Activity 3.2.1: Organise training workshops to a working group for the sustainable operation and management of the provided hard interventions | 110000 | 2024-02-01
| Activity 3.1.1: Install 5 groundwater purification systems and 2 rainwater harvesting systems | 748044 | May-Dec 2022
| Activity 3.1.2: Install 860m of eco-friendly infrastructure | 100000 | May-Dec 2022
| Activity 3.2.1: Organise training workshops to a working group for the sustainable operation and management of the provided hard interventions | 110000 | Oct-Dec 2022
| PROJECT EXECUTION COST | 160500 |  |  | PROJECT EXECUTION COST | 117051.57
| PROJECT/PROGRAMME CYCLE MANAGEMENT FEE | 139837 |  |  | PROJECT/PROGRAMME CYCLE MANAGEMENT FEE | 169492.59
| TOTAL | 1778381 |  |  | TOTAL | 1684588.16 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT (additional risks for 2nd reporting period)
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Environmental/Social: Current climate and seasonal variability and/or hazard events result in infrastructure construction delays or undermine confidence in adaptation measures by local communities. Probability: 2 Impact: 4 (1: low - 5 : high) | Low | - Current climatic variability has been taken into account in the planning and design of the project activities, particularly in the design of the infrastructure built under component 3 through feasibility study - Both water treatment system and coastal erosion prevention system have been extensively consulted with communities, local officials, government staffs at the national and local level. Ministry of Natural Resource and Environment (MONRE) and Departments of Natural Resource and Environment (DONREs) Viet Nam especially has been closely involved.
Institutional: Loss of government support (at all levels) for the project (activities and outputs) may result in lack of prioritization of AF project activities. Probability: 1 Impact: 4 (1: low - 5 : high) | Low | - The overall participatory project design has ensured ownership at the national, provincial, district, and commune level, and thus it will enhance government support for the project implementation. - UN-Habitat is planning to make legal binding with MONRE (Project Management Unit-PMU) through MoU and AoC to ensure that PMU will deliver all project activities and outputs in a timely manner
Institutional Capacity: constraints of local institutions may limit the effective implementation of interventions Probability: 1 Impact: 3 (1: low - 5 : high) | Medium | - The project has a strong capacity building and training component, particularly under output 1.1.4; 1.2.1; and 3.2.1., designed to promote effectiveness and sustainability at the national, provincial, district, and commune level for the implementation of interventions. - Direct financial transfers to the local government (commune level) imply a high-level risk (as identified in consultation meeting with various international development partner, especially in Mekong Delta Working Group in Viet Nam). Therefore, commune level activities will be executed and monitored by working group and project steering committee; - UN-Habitat's Vietnam office manages to provide techincal and managerial support/supervision to implmentation partners ensuring all the technical requirements of committed activties.
Institutional/Social: Lack of commitment/buy-in from local communities may result in delay at intervention sites Probability: 1 Impact: 2 (1: low - 5 : high) | Low | - Community stakeholders have been consulted extensively during the concept note and full-size project development phase to ensure their willingness and ownership of this project - Bottom-up approach integrating the community into the AF project’s implementation phases – including community contracting in line with the People’s Process – will be followed - Where possible, the community will have an active role through the ‘People’s Process’ that ensures ownership of the project particularly through community participation in project implementation and monitoring
Institutional/Social: Disagreement amongst stakeholders with regards to adaptation measures (infrastructure) and site selection Probability: 1 Impact: 2 (1: low - 5 : high) | Low | - The adaptation measure (infrastructure) proposed mainly in component 3 of the project was selected through in-depth feasibility study from the technical team - Participatory approach will be applied to the construction of the infrastructure under component 3, through the People’s Process, which employs the beneficiaries directly in the construction of the infrastructure.
Institutional: Communities may not adopt activities during or after the AF project, including infrastructure maintenance Probability: 1 Impact: 4 (1: low - 5 : high) | Low | - The project has consulted with the local government several times to find out their needs and applied it into the both soft and hard interventions - Capacity building and training will be undertaken to improve the awareness of the climate change impact and the importance of adaptation to the current phenomenon - Community members in each commune will be involved in the project implementation and decision making as part of working group
Financial: Complexity of financial management and procurement. Certain administrative processes could delay the project execution or could lack integrity Probability: 1 Impact: 2 (1: low - 5 : high) | Medium | - UN-Habitat’s control framework, under the financial rules and regulations of the UN secretariat, ensure documentation of clearly defined roles and responsibilities for management internal auditors, the government body, other personnel and demonstrates prove of payment / disbursement - Procurement will be done by the executing entities as agreed through AoC. The project manager and the project team have a certifying role. All expenditures/ costs/ payments will be documented in USD
Institutional: Delays in project implementation, and particularly in the development of infrastructure interventions Probability: 2 Impact: 3 (1: low - 5 : high) | Medium | - The participation from the national and local government was high during the project preparation phase which will reduce the risk of delay - The project includes extensive planning and capacity building under component 1 and 2. While the investments under component 3 have been fully identified, improved planning capacity will help to make the implementation smoother and reduce the risk of delays
Institutional: A lack of coordination between and within national government Ministries and Departments Probability: 2 Impact: 2 (1: low - 5 : high) | Low | - To minimize the risks of coordination between and within national government ministries and department, a working group will be organized with representatives from different local governmental departments - MONRE and DONRE will lead the working group with support from Province People’s Committee (PPC) and other departments under PPC
Legal: Delays or barriers in gaining approval for infrastructure and housing due to delays in the development process or due to land tenure issues. Probability: 1 Impact: 4 (1: low - 5 : high) | Low | - No legal issues are foreseen. - The project teams are tasked to ensure close collaboration with the provincial line department of natural resources and environment (DONRE) departments of construction (DOC), agriculture and rural development (DARD), and public health (DOH) for the further process of the project
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
State administration process: Project owner changes from the Ministry Office to the Institute of Strategy and Policy on Natural Resources and Environment-ISPONRE. Level of impact: 4 (1: low - 5 : high) | Project owner changed Medium | The change took longtime to process. It has delayed the start of the project and slowed down the progress of the project implementation. The project team has speeded up the changing process (paper work processing; negotiation and justification) so that the project's activities could start ASAP.
Financial: Delay of grant transfer to the implementing partner is highly affecting the implementation of project's committed activities. Level of impact: 3 (1: low - 5 : high) | Medium | At the time of reporting, the first instalment reached the implementing partners after long-time processing, followed by the second instalment. UN-Habitat's Vietnam and regional offices have intensively communicated with HQ office and Treasury to amend the technical issues, a good lesson learned for the project team in coming years to avoid delay of fund transfer.
Covid-19 Pandemic: Vietnam witnessed all-year-around waves of Covid-19 in 2021 that the Government has put in place travel restrictions, social distancing and restrictions of people gathering. The target provinces remain apprehension of new waves of covid-19 when Vietnam reopens that they are reluctant to verify and receive the project workplan for implementation Level of impact: 3 (1: low - 5 : high) | Medium | Since the 1st-year activities have focused mainly on capacity building and communication, the training events are virtually planned. The UN-Habitat team and the Project Management Unit team have planned on-site activities with care, such as field surveys and training organization. All relevant legal documents as well as Covid-control procedure are prepared in advance to meet planned timeframe.
Structural re-arrangement within the governing ministry (MONRE) and its affiliated agecies. During the transitional period, approval and appraisal processes are significantly slower than expected. These changes have affected all ODA projects implemented by UN agencies. Level of impact: 3 (1: low - 5 : high) | Medium | The project management unit works as advisory team for the new leaders and provides support when needed. However, since the prudence in work deployment and the tightening of administrative procedures at state agencies, the implementation of the project activities is delayed. Official documents/communications became the main tool and measure to address this issue, aside from regular meetings and close follow-ups.
Re-assessment and selection of chosen sites for the project's hard interventions within the same administrative units, proposed by local authorities and communities, based on new local demands. Level of impact: 3 (1: low - 5 : high) | Medium | The project team consulted the target communes/provinces and is planning for feasibility assessment for the project's hard interventions, with the same technical requirements at new locations. Because of this, the project's progress has been affected. Official documents/communications became the main tool and measure to address this issue, aside from regular meetings and close follow-ups.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
As soon as the new risks were identified, UN-Habitat prepared a mitigation plan with specific actions addressing the responsible agencies. Meetings were held and official communications were sent to facilitate the approval process, and request for the recommendation/ proposal of new locations within the same administrative units that fit with the current demands. During the reporting period, the risk was reduced as we received positive feedbacks from the provinces regarding the locations, however, the approval process at ministerial level was still in delay.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | - Land ownership (public or private) will affect the construction interventions (act. 3.1.1 - building water treatment systems and rainwater harvesting systems & 3.1.2- building coastal erosion prevention system); - Failure to comply with laws relating to procurement procedure (act.3.2.1- building capacity for working groups to manage and operate the hard interventions) (1-Technology transfer to local people who are not legally allowed to operate the business models; 2-Only a private company or cooperative can manage the operation of the business models) | - The construction interventions are only on public land with land-use approval from the Department of Natural Resources and Environmental and construction approval from the Department of Construction. - Integrating legal compliance into all technology transfers/training - Consult the legal procedures to establish a community owned business models | - # of meetings with relevant local stakehoders to select sites for construction interventions - # of organized traings for technology transfers - # of established bussiness models | Low | The field visits have been made to the project sites to study and ensure the compliance of the project's interventions against national and local regulations and laws. | no residual impact expected after the implementation | No remedial action required
2 - Access and equity |  |  | - Potential social inequality in term of access to infrastructure, or that preferential access is given to certain groups (Act 3.1.1) - Potential insecurity of school children (Activity 3.1.1) | - New business model to make sure the price stable for the poor and marginalized over time - Pro-poor tariffs will be applied and the price will be determined by Working Group - Community management with rules ensuring that equal access is guaranteed - Make sure the effective operation of waster treatment system for the locals with capacity building and develop the mechanism to provide the service to remote areas - Mechanism for safety of children should be put in place (e.g only access to water treatment facility after school hours) - ‘Business as usual’ mechanism will be applied and minimize the impact on economic activities from the construction of elastocoast such as provide daily labour of construction and using alternative way to reach the livelihood areas | - # of beneficiaries (especially the poor & maginalized in remote areas) - Community management regulations for the business models and construction interventions - # of safety codes for hard construction - Volume of hard interventions achieved | Medium | N/A for the reporting period | - Potential social inequality in term of access to infrastructure, or that preferential access is given to certain groups (Act 3.1.1) - Potential insecurity of school children (Activity 3.1.1) | - New business model to make sure the price stable for the poor and marginalized over time - Pro-poor tariffs will be applied and the price will be determined by Working Group - Community management with rules ensuring that equal access is guaranteed - Make sure the effective operation of waster treatment system for the locals with capacity building and develop the mechanism to provide the service to remote areas - Mechanism for safety of children should be put in place (e.g only access to water treatment facility after school hours) - ‘Business as usual’ mechanism will be applied and minimize the impact on economic activities from the construction of elastocoast such as provide daily labour of construction and using alternative way to reach the livelihood areas
3 – Marginalized and vulnerable Groups |  |  | - There would be small number of vulnerable groups to access to livelihood resources (Activity 3.1.1 and 3.1.2) | - Community co-management with rules ensuring of equal access and information is guaranteed and community based engagement will be applied to encourage the participation from marginalized and vulnerable group - Make sure that the information about the infrastructures will be announced to marginalized groups. - One facility will be installed in the indigenous group community (Resettled area) | - Community-based consensus documents and plans for engagement of marginalized and vulnerable groups in the business models | Medium | N/A for the reporting period | - There would be small number of vulnerable groups to access to livelihood resources (Activity 3.1.1 and 3.1.2) | - Community co-management with rules ensuring of equal access and information is guaranteed and community based engagement will be applied to encourage the participation from marginalized and vulnerable group - Make sure that the information about the infrastructures will be announced to marginalized groups. - One facility will be installed in the indigenous group community (Resettled area)
4 – Human rights |  |  | - Human rights breaches can arise from denying access to water and other basic services | - The Human Rights Officer of UN-Habitat will monitor and ensure that the project is implement to respect and adhere to the requirements of all relevant conventions on human rights. | - Human rights are acknowledged through key messages attached at the invested hard interventions - Legally biding and community consensus for Human-right commitment | Low | N/A for the reporting period | - Human rights breaches can arise from denying access to water and other basic services | - The Human Rights Officer of UN-Habitat will monitor and ensure that the project is implement to respect and adhere to the requirements of all relevant conventions on human rights.
5 – Gender equality and women’s empowerment |  |  | - Women could be denied access to infrastructure, or excluded from making critical decisions (Activity 3.1.1 and 3.1.2) | - The project design considered to integrate gender issues in all project interventions, with a specific focus on capacity building at all levels as well as activities on the ground. During the project's implementation, the Gender Officer and project manager of UN- Habitat will monitor to ensure that gender equality integration follows the technical requirement and guidelines. - Involving women and Local Women Union along process and especially during the implementation and after the end of the project - There will be low risk that women could be denied to access to water infrastructure. - The activities under Component 3 will create employment enabling some marginalized and vulnerable groups including unemployed youth and women to access employment. | - # of women employed by the bussinesses invested by the project - # of women who can lead the businesses invested by the project - at least 40% of women ad girls can access the infrastructure invested by the project - Developed community/public regulations in favour of women and girls in fresh water and basic services | Medium | Gender equality has been mainstreamed in 2nd year activities via planning | No residual impact, however continuous monitroing on gender equlity will be executed | continously monitoring on gender equlity
6 – Core labour rights |  |  | - Labour rights may not be respected when contracting communities (Activity 3.1.2) | - All community contracts must be scrutinized to ensure they comply with both Vietnamese law and international standards. - The relevant national labour laws guided by the ILO labour standards will be followed throughout project implementation. - The safety manual and instruction will be provided. | - Labour rights are integrated in the employment contracts, managed by the communities and supervised by the local authority - Introduced safety principles at the built facilities | Low | N/A for the reporting period | - Labour rights may not be respected when contracting communities (Activity 3.1.2) | - All community contracts must be scrutinized to ensure they comply with both Vietnamese law and international standards. - The relevant national labour laws guided by the ILO labour standards will be followed throughout project implementation. - The safety manual and instruction will be provided.
7 – Indigenous peoples |  |  | - The certain minority group can be denied to access to infrastructures and excluded from the process of decision making (Activity 3.1.1) | - Community's management plans must ensure equal access for vulnerable and poor minority groups - Involving the minorities in the operation processes and management boards of hard infrastructure constructed by projects or infrastructure existing in the region. | - # of minority people engage in supervising construction works; operation and management - Participation of minority people in community's management plan | Medium | N/A for the reporting period | - The certain minority group can be denied to access to infrastructures and excluded from the process of decision making (Activity 3.1.1) | - Community's management plans must ensure equal access for vulnerable and poor minority groups - Involving the minorities in the operation processes and management boards of hard infrastructure constructed by projects or infrastructure existing in the region.
8 – Involuntary resettlement |  |  | - Possible eviction arising from conflicts over land ownership (Activity 3.1.2) | - Ensure provision of appropriate compensation and livelihood restoration in case an involuntary resettlement occurs - The project aims to utilize public land for facility construction. | - public areas of land are used for facility construction | Low | N/A for the reporting period | - Possible eviction arising from conflicts over land ownership (Activity 3.1.2) | - Ensure provision of appropriate compensation and livelihood restoration in case an involuntary resettlement occurs - The project aims to utilize public land for facility construction.
9 – Protection of natural habitats |  |  | - While damage to natural habitats and threats to biological diversity are unlikely, there is a possibility that construction work undertaken or reforestation measures may adversely impact on local biodiversity (Activity 3.1.2) | - Community consultation and involvement in identifying and protecting natural habits - The mangrove species will be tested for sustainability based on community participation | - Meetings with local communities and experts to identify risks and solutions | Low | N/A for the reporting period | - While damage to natural habitats and threats to biological diversity are unlikely, there is a possibility that construction work undertaken or reforestation measures may adversely impact on local biodiversity (Activity 3.1.2) | - Community consultation and involvement in identifying and protecting natural habits - The mangrove species will be tested for sustainability based on community participation
10 – Conservation of biological diversity |  |  | - While damage to natural habitats and threats to biological diversity are unlikely, there is a possibility that construction work undertaken or reforestation measures may adversely impact on local biodiversity (Activity 3.1.2) | - Community consultation and involvement in identifying the plantation areas and originated mangrove species - Community co-management mechanism is in place to ensure the survivor of Mangro afforestation. | - Meetings with local communities and experts to identify risks and solutions | Low | N/A for the reporting period | - While damage to natural habitats and threats to biological diversity are unlikely, there is a possibility that construction work undertaken or reforestation measures may adversely impact on local biodiversity (Activity 3.1.2) | - Community consultation and involvement in identifying the plantation areas and originated mangrove species - Community co-management mechanism is in place to ensure the survivor of Mangro afforestation.
11 – Climate change |  |  | - This project is inherently an adaptation project and as such no maladaptation is foreseen | - Solar power will be used as a part electric source to operate the water purification system which reducing cost and emission | - Invested facilities with mini-solar power systems | Low | N/A for the reporting period | - This project is inherently an adaptation project and as such no maladaptation is foreseen | - Solar power will be used as a part electric source to operate the water purification system which reducing cost and emission
12 – Pollution prevention and resource efficiency |  |  | - Construction of facilities generates wastes and their operation generates waste (Activity 3.1.1 and 3.1.2) | - Incorporating waste management and disposal into design and implementation process based on legal compliance - Strictly follow the handling procedure when using chemicals with gravels. - Chemical residues must be collected and stored in safe places before transferring to hazard/chemical waste treatment facilities. - The environmental effects of chemicals used in elastocoast are analyzed by BASF and ARCADIS, mentioning the compounds pose no threat to the aquaculture environment and the components are non-toxic and naturally degradable. (Test results were shared, will be provided upon request) | - Developed plans for waste management and treatment at the facilities - Community supervision onthe facility construction and facilty operation regarding waste disposal ,collection and treatment | Medium | N/A for the reporting period | - Construction of facilities generates wastes and their operation generates waste (Activity 3.1.1 and 3.1.2) | - Incorporating waste management and disposal into design and implementation process based on legal compliance - Strictly follow the handling procedure when using chemicals with gravels. - Chemical residues must be collected and stored in safe places before transferring to hazard/chemical waste treatment facilities. - The environmental effects of chemicals used in elastocoast are analyzed by BASF and ARCADIS, mentioning the compounds pose no threat to the aquaculture environment and the components are non-toxic and naturally degradable. (Test results were shared, will be provided upon request)
13 – Public health |  |  | - No public health issues are foreseen, and improving public health is a secondary impact area of this project. | - To mitigate the possible risk even though it is low, the test of effectiveness of water treatment system should be done at the project sites to show the evidence to local authorities who are in charge of local public health. - In order to mitigate the potential risks to public health, user guideline/procedure provided by supplier company should be followed and onsite Environmental Management Plan is deployed during the construction phase. | - Volume of clean water is spplied daily to local communities and school children. | Low | N/A for the reporting period | - No public health issues are foreseen, and improving public health is a secondary impact area of this project. | - To mitigate the possible risk even though it is low, the test of effectiveness of water treatment system should be done at the project sites to show the evidence to local authorities who are in charge of local public health. - In order to mitigate the potential risks to public health, user guideline/procedure provided by supplier company should be followed and onsite Environmental Management Plan is deployed during the construction phase.
14 – Physical and cultural heritage |  |  | - No physical or cultural heritage impacts are foreseen | N/A | N/A | Low | N/A | - No physical or cultural heritage impacts are foreseen | N/A
15 – Lands and soil conservation |  |  | - Installation of bio coast may lead to more soil erosion in other unapplied places (Activity 3.1.2) | - Soil conservation will be enhanced through afforestation components as protective measures for land erosion control. - Careful calculation and anticipated impacts of Elastocoast intervention to find best place to introduce the intervention. Monitoring erosion rate of the upgraded area and the surrounding locations. | - Area of plantted Mangrove Forest - Length of built Elastocoast | Low | N/A for the reporting period | - Installation of bio coast may lead to more soil erosion in other unapplied places (Activity 3.1.2) | - Soil conservation will be enhanced through afforestation components as protective measures for land erosion control. - Careful calculation and anticipated impacts of Elastocoast intervention to find best place to introduce the intervention. Monitoring erosion rate of the upgraded area and the surrounding locations.
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes. During the reporting period, where applicable, all project activities were conducted in close collaboration/ in consultation with the national and local governments, as well as local communities to ensure the compliance with the law.
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | A Chief of Techincal Advisor has been assigned to manage and monitor the envionmental and social policy compliance, together with the project manager whose expertise in environmental economics and climate change policy and economics.
Have the implementation arrangements been effective during the reporting period? |  | Yes, the assigned UN-Habitat staff work well in providing technical support and financial advice to EE to develop workplan, monitoring the project implementation, correcting the outputs and results to make sure the project's outputs and outcomes achievable.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Executing Entity has directed the PMU and assigned experts to support the PMU when needed to carry out key activities. Given the replacement of PMU staff occurred sometimes during the reporting period.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | PMU under PSC has funtioned well, under supervision by UN-Habitat, in both project management and techincal supervision.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
There is no grievance received during the second year project implementation |  | The project is taking the idea of developing the grievance mechanism for local communities into serious consideration and will start its step-by-step establishment in the 2nd year onward. The Grievance mechanism includes different communication modalities; the responding team and the checklist for grievance severity. 1. The communication modalities include hotlines; posting address; direct contact persons. They show up on the sigh boards attached at the project’s facilities. The innovative communication modalities such as SEETELL and SNAPTURE may be applied depending on the available budget. 2. The project’s provincial focal points are recruited to support project management and operation on filed. S/he will be responding and discussing the grievance issues to/with the responding team (members from UN-Habitat and PMU) for decision making. 3. The checklist aims to have initial appraisal for the severity of the grievance.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No
Partially
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, Gender Situation in Mekong Delta Region has been highlighted in 4 areas: 1) Income level and livelihoods of Women in Mekong Delta; 2) Access to educational opportunities among girls in Mekong Delta; 3) Cultural barriers including: i) Early marriage and transnational marriage among women and ii) Domestic violence against women; and 4) Women's Vulnerability to Climate Change in Mekong Delta
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes, the results framework has gender-responsive indicators for some key outcomes and outputs though they need to be more specific.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Component 1: Institutional and community capacity building toward ecohuman settlement development for supporting to enhance local climate response actions | Outcome 1.1 (with output 1.1.1) | # of policies and practices ensuring equal participation of men and womnen are introduced and implemented | 0 | At least 40% of women's paticipation and accessibility to capacity building events | Good Output 1.1.1: Due to Covid-19, the inception workshop in December 2020 was organised in small-scale with limited in-person participation. 20 out of 44 participants are women (45%). Output 1.1.1: 60% (6/10) of TAG members are women Output. 1.2.1: 46% (40/87) of women participation in national level capacity building workshop and average 40% (36/83 in Tra Vinh & 20/51 in Bac Lieu) of women participation in provincial level capacity building workshops. Total 96 women government officials, experts and practicioners at all levels
| Outcome 1.2 (with output 1.2.1) |  | 0
| Other outputs: 1.1.2; 1.1.3; and 1.1.4 | # of women's participation in development of training materials and techincal guideline; training courses and workshops | 0 | - At least 40% of women's paticipation - Developed materials with gender integration | Satisfactory Output 1.1.2 & Output 1.1.3: 43% (9/21) of experts and consultants who conducted field assessments, the risk assessment guidelines, climate change action planning toolkits and materials were women. Output 1.1.4: 43% women participants in national-level TOT (18/42 female trainers were trained). The materials will be updated with gender mainstreaming guideline to safeguard gender integration throughout all processes of climate change action planning
Component 2: Action plan and strategy development for eco-human settlement, and integrating into planning and policy with participatory approach | Outcome 2.1 (Output 2.1.1) | % of women and men participation in building strategy and action plan for eco-human settlement; policy dialogues; policy framework development workshops | 0 | - At least 40% of women participating in training workshops; policy dialogues; policy framework development | N/A for this reporting period (the activities of the component 2 were designed with integration of gender equality which will be implemented soon)
| Outcome 2.2 (Output 2.2.1 and 2.2.2) |  | 0 |  | N/A for this reporting period (the activities of the component 2 were designed with integration of gender equality which will be implemented soon)
Component 3: Sustainability built through small-scale protective infrastructure | Outcome 3.1 (Output 3.1.1; 3.1.2) | - # of gender needs are synthesized and incorporated in planning for facilities' construction, operation and maintainance - # of women paticipate in supervision; planning; operating; managing and mainataining the constructed facilities and associated businesses. | 0 | - At least 40% of women participating in planning for facilities' construction, operation and maintainance | N/A for this reporting period (the activities of the component 3 were designed with integration of gender equality which will be implemented soon)
| Outcome 3.2 (Output 3.2.1) | - # of women's participation in training courses and workshops | 0 | - At least 40% of women's participation | N/A for this reporting period (the activities of the component 3 were designed with integration of gender equality which will be implemented soon)
Component 4: Awareness Raising and Knowledge Management | Outcome 4.1 (Output 4.1.1; 4.1.2) | - # of policy dialogues; esminars; workshops with equal participation of men and women | 0 | - At least 40% of women's participation | N/A for this reporting period (the activities of the component 4 were designed with integration of gender equality which will be implemented throughout the project, especially in the 4th year)
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | PMU with support from UN-Habitat has planned for mainstreaming gender equality in the second year activities ensuring at least 40% of women access and participate in all relevant events and activities. The Implementing Entity assigned a gender focal poit to manage and supervise the project's gender mainstreaming.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes, the planned activities with gender equality targets are under implementation, some are under reviewing, assessing and approving. UN-Habitat has arranged staff to make sure follow-up activities and planned ones are achieved on the right track.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | - ISPONRE in collaboration with DLA has established PMU with 5/8 female members. Similarly, the Technical Advisory Groups (TAG) has been established by ISPONRE with 6/10 female experts in different technical areas. - ISPONRE and DLA are well aware of gender equality and prioritize gender integration in the project's activities and implementation. They with support from UN-Habitat to lead PMU to commit gender-sensitive and gender-responsive activities.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Gender equality has been ensured in the PMU taskforce, PSC and TAG members which has effectively manage and carry out the project's activities, though there were drops and new recruitment of personels.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Gender bias as well as gender needs in the project sites have not been well understood to support gender integration planning for the 2nd year activities. It is planned that a gender assessment will be conducted in the targeted provinces. Findings will help to integrate gender in developed technical guidelines and training materials for risk/vulnerability assessment, climate change mainstreaming in development plans.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
There is no grievance received during the first year project implementation |  | Gender analysis will be conducted in the 2nd year of which gender equality will be properly integrated in the project activities, especially the capacity building activities. The grievance mechanism for gender policy compliance is the same as for ESP compliance. It will also include 1) different communication modalities; 2) the responding team and 3) the checklist for grievance severity. 1. The communication modalities include hotlines; posting address; direct contact persons. They show up on the sigh boards attached at the project’s facilities. 2. The project’s provincial focal points are recruited to support project management and operation on field. S/he will be responding and discussing the grievance issues to/with the responding team (members from UN-Habitat and PMU) for decision making. 3. The checklist aims to have initial appraisal for the severity of the gender grievance.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: UN-Habitat Vietnam office | Component 1: Institutional and community capacity building toward ecohuman settlement development for supporting to enhance local climate response actions |  |  | Milestones of the component 1: 1. Activities begin by month 3 2. Guidance and training materials complete by month 12 3. All training complete by month 24 Milestones of year 1: 4. Induction workshop completed (1.1.1) 5. List of trainees developed (1.1.1) 6. Training materials and planning toolkits developed (1.1.2/1.1.3) 7. Training of trainers (ToT) 50% completed (1.1.4) |  | All milestones were sucessfully delivered. All the follow-up activities are being implemented as planned. - Small-scale Agreement of Cooperation (SSAoC) with Clitech (MONRE) was signed for the execution of the national induction workshop under Component 1, while waiting for the approval of the project from Vietnam government side. - Agreement of Cooperation (AoC) with the Project Management Unit (PMU) under MONRE was signed for the execution of Component 1, 2 and 3. - A Project Steering Committee (PSC) was established and first coordination meeting was held with participation of the provinces. - Field missions were undertaken by the project team to Tra Vinh and Bac Lieu provinces to monitor the activities conducted by the EE, and discuss the implementation mechanism of the project at local levels. | S
| Outcome 1.1 Increase awareness on resilience of human settlements and ecosystem as a result of enhanced institutional capacity |  | Outcome 2 | Expected outputs: 1.1.1 National induction workshop 1.1.2 Guidance and training materials development for vulnerability and risk assessment at the local levels 1.1.3 Planning toolkits and training materials development for planning approach, strategy and action plan development on climate change resilience 1.1.4 Project team (facilitators) training enabling facilitation of ecofriendly settlement strategy and action plan development |  | All outputs were sucessfully delivered. The follow-up activities are being implemented as planned. - UN-Habitat has closely monitored, coordinated and provided technical supports/ inputs to all activities under Component 1. This includes the overall and detailed work plans, TORs for the workshops and trainings, technical guidelines and training materials. - The national, provincial, district governments and the communities are fully engaged. - Output 1.1.1: National induction workshop was organized. Technical advisory group (TAG) was established. The project's branding package was developed, the project's video and infographic were presented at the 11th World Urban Forum. - Output 1.1.2 & 1.1.3: guidelines, toolkits and training materials were developed for local (province, district, commune) levels . - Output 1.1.4: TOTs were organized at national and provincial levels. - Output 1.1.4: TORs for 2nd-year refresher TOTs were developed and reviewed. | S
| Outcome 1.2 Strengthen knowledge of climate change adaptation |  | Outcome 3 | Expected outputs: 1.2.1 Training workshops enabling national/provincial/district/commune to set up eco-human settlement strategy and action plan development for climate change adaptation |  | - Capacity building training workshops were organized at national and provincial levels using the guidelines, toolkits and training materials developed. - TORs for follow-up training workshops and community events were developed and reviewed. - The overall and detailed work plan are under review of the national governing ministry (MONRE) | S
| Component 2. Action plan and strategy development for promoting eco-human settlement, and integrating into planning and policy with participatory approach |  |  | Minestones of component 2: 1. Baseline assessment completed by month 12 2. All training materials prepared by month 18 3. Training conducted by month 36 4. Action plan and strategy development complete by 36 months 5. Policy framework development complete by 36 months 6. Revised action plan and strategy integrate into provincial level policy by 48 months Minestones of Year 2: 1. sustainable eco-human settlement review 2. gender equality is mainstreamed in the technical guildelines and training materials 3. action plan and strategy for eco-human settlement in the target provinces 4. Initial installment of Water treatment system and rainwter harvesting system 5. Initial installment of Coastal erosion prevention system |  | Activities under Component 2 have not yet started. Detailed work plan and TORs for activities were developed by EE and being under review by the governing ministry (MONRE). | MS
| Outcome 2.1. Develop provincial/district/commune level's action plan and strategy for promoting eco-human settlement based on local people's needs (40% women) |  | Outcome 4 | Expected outputs: 2.1.1 Action plan and strategy are built for promoting eco-human settlement (provincial/district/commune level) |  | Activities under Component 2 have not yet started. Detailed work plan and TORs for activities were developed by EE and being under review by the governing ministry (MONRE). | MS
| Outcome 2.2. Develop policy framework for integrating climate action and strategy into planning (40% women) |  | Outcome 7 | Expected outputs: 2.2.1 Policy framework is developed for integrating built action plan and strategies in promoting eco-human settlement into planning (provincial level) 2.2.2 The built action plan and strategy are integrated into the relevant/existing planning and policy (provincial level) |  |  | MS
| Component 3. Sustainability built through small-scale protective infrastructure |  |  | Minestones of component 3: 1. Construction complete by month 48 2. Baseline assessment complete by month 24 3. Material development for guidance and manuals complete by 36 4. Operation and management training complete by 48 |  | Activities under Component 3 have not yet started. Discussions with the provinces have been initiated | MS
| Outcome 3.1. Increase community adaptive capacity with climate resilient and development sectors, and increase ecosystem resilience in response to climate change |  | Outcome 2 | Expected outputs: 3.1.1 Water treatment system and rainwter harvesting system are introduced and start the construction 3.1.2 Coastal erosion prevention system is introduced and start the construction |  |  | MS
| Outcome 3.2. Enhance local people’s capacity for management and operation of provided infrastructures (40% women) |  | Outcome 1 | Expected outputs: 3.2.1 trainings on operating the installed systems and building the models of managing and operating them by communities |  |  | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Nghia Le
| Email: | nghia.le@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
All planned activities for component 1 have been delivered and the expected outputs have been achieved at the good quality meeting the technical requirements. The follow-up activities are implemented, while infrastructure-related activities are under review, appraisal and approval. UN-Habitat requested the national executing entity to plan with care for all activities that they will implement and update their progress in the weekly meetings. Any issue unfavorable to the activity implementation will be discussed and solutions are then indetified.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: ISPONRE & DLA. The Project Management Unit-PMU | Component 1: Institutional and community capacity building toward ecohuman settlement development for supporting to enhance local climate response actions |  |  | Milestones of the component 1: 1. Activities begin by month 3 2. Guidance and training materials complete by month 12 3. All training complete by month 24 Milestones of year 1: 4. Induction workshop complete (1.1.1) 5. List of trainees develop (1.1.1) 6. Training materials and planning toolkits develop (1.1.2/1.1.3) 7. Training of trainers (ToT) 50% complete (1.1.4) |  | All milestones were sucessfully delivered. All the follow-up activities are being implemented as planned. | S
| Outcome 1.1 Increase awareness on resilience of human settlements and ecosystem as a result of enhanced institutional capacity |  | Outcome 2 | Expected outputs: 1.1.1 National induction workshop 1.1.2 Guidance and training materials development for vulnerability and risk assessment at the local levels 1.1.3 Planning toolkits and training materials development for planning approach, strategy and action plan development on climate change resilience 1.1.4 Project team (facilitators) training enabling facilitation of ecofriendly settlement strategy and action plan development |  | All outputs were sucessfully delivered. The follow-up activities are being implemented as planned. - National induction workshop was organized. Technical advisory group (TAG) was established. The project's branding package was developed, the project's video and infographic were presented at the 11th World Urban Forum. - Guidance and training materials were developed for vulnerability and risk assessment at local (province, district, commune) levels . - Planning toolkits and training materials were developed for planning approach, strategy and action plan development on climate change resilience (province, district, commune levels) - TOTs were organized at national and provincial levels. - TORs for 2nd-year refresher TOTs were developed and reviewed. | S
| Outcome 1.2 Strengthen knowledge of climate change adaptation |  | Outcome 3 | Expected outputs: 1.2.1 Training workshops enabling national/provincial/district/commune to set up eco-human settlement strategy and action plan development for climate change adaptation |  | Detailed work plan and TORs for activities were developed and being under review by the governing ministry (MONRE) | S
| Component 2. Action plan and strategy development for promoting eco-human settlement, and integrating into planning and policy with participatory approach |  |  | Minestones of component 2: 1. Baseline assessment completed by month 12 2. All training materials prepared by month 18 3. Training conducted by month 36 4. Action plan and strategy development complete by 36 months 5. Policy framework development complete by 36 months 6. Revised action plan and strategy integrate into provincial level policy by 48 months Minestones of Year 2: 1. sustainable eco-human settlement review 2. gender equality is mainstreamed in the technical guildelines and training materials 3. action plan and strategy for eco-human settlement in the target provinces 4. Initial installment of Water treatment system and rainwter harvesting system 5. Initial installment of Coasta erosion prevention system |  | Activities under Component 2 have not yet started. Detailed work plan and TORs for activities were developed by EE and being under review by the governing ministry (MONRE). | MS
| Outcome 2.1. Develop provincial/district/commune level's action plan and strategy for promoting eco-human settlement based on local people's needs (40% women) |  | Outcome 4 | Expected outputs: 2.1.1 Action plan and strategy are built for promoting eco-human settlement (provincial/district/commune level) |  | Activities under Component 2 have not yet started. Detailed work plan and TORs for activities were developed by EE and being under review by the governing ministry (MONRE). | MS
| Outcome 2.2. Develop policy framework for integrating climate action and strategy into planning (40% women) |  | Outcome 7 | Expected outputs: 2.2.1 Policy framework is developed for integrating built action plan and strategies in promoting eco-human settlement into planning (provincial level) 2.2.2 The built action plan and strategy are integrated into the relevant/existing planning and policy (provincial level) |  |  | MS
| Component 3. Sustainability built through small-scale protective infrastructure |  |  | Minestones of component 3: 1. Construction complete by month 48 2. Baseline assessment complete by month 24 3. Material development for guidance and manuals complete by 36 4. Operation and management training complete by 48 |  | Activities under Component 3 have not yet started. Discussions with the provinces have been initiated to identify new locations for some of the project hard interventions within the same districts. TOR for feasibility study of new locations was developed. The overall and detailed workplans for Component 3 were developed. | MS
| Outcome 3.1. Increase community adaptive capacity with climate resilient and development sectors, and increase ecosystem resilience in response to climate change |  | Outcome 2 | Expected outputs: 3.1.1 Water treatment system and rainwater harvesting system are introduced and start the construction 3.1.2 Coasta erosion prevention system is introduced and start the construction |  | EE in coordination with IE have consulted experts, provinces and ministries to develop the action plan for these activities. Procurement documents are being finalized between relevant stakeholders. | MS
| Outcome 3.2. Enhance local people’s capacity for management and operation of provided infrastructures (40% women) |  | Outcome 1 | Expected outputs: 3.2.1 trainings on operating the installed systems and building the models of managing and operating them by communities |  |  | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dinh Tho NGUYEN
| Email: | thodinhnguyen@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The national executing entity (PMU) under supervision of the governing ministry worked with UN-Habitat to plan and implement the activities in compliance with the laws and the changed social-political context of target provinces. The work plan for follow-up activities are under review and approval of MONRE.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | The key activities have been planned by PMU and UN-Habitat. They are under the review and assessment for approval.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | - Structural re-arrangement within the DoA (MONRE) and its affiliated agecies affected the work plam postponing the project's implementation. - The project owner changed from the MONRE Office to ISPONRE has affected the start of the project, resulting in delay of the AoC signing and thus the project's implementation. - Covid-19 pandemic also affected the progress of the project's implementation. To be organized, some capacity building events have to wait for permision from the local governments. - Delay in fund transfer to implementing partners affected the start of activities, especially the ones that use consultancy services. - Transparent and effective communication among/between project team members helped save time for decision making and contribute to the success of the activities' deployment. - Active participation of PMU staff helped address difficulties and challenges quickly, hastening the implementation of activities. - Active coordination between PMU and UN-habitat also helped speed up the progress of the project's implementation - Executive leadership and active participation of ISPONRE (with support from DLA) play an important role in speeding up all implementation processes. - Careful advacne planning is critical for activity implementation and result accomplishment
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The project was expected to start in early 2021, but due to the application process for changing the project owner and the spread of Covid-19 with nearly three months of travel restriction, the project has just started in 5 November 2021. Some other challenges associated with these two main causes include: 1 Staff switching in both UN-Habitat and PMU. The new project manager of UN-Habitat was just on board since 1st December of 2021 2 Provinces applied social distancing and zoning to prevent social events with more than 10 people 3 Vaccination certification for participation in public events and air travel 4 The target provinces remain apprehension of new waves of covid-19 when Vietnam reopens that they are reluctant to verify and receive the project workplan for implementation 5 Structural re-arrangement within the DoA (MONRE) and its affiliated agecies 6 Delay in fund transfer from AFB to UN-Habitat and to PMU (EE) Measures have been taken to reduce delays: 1 Adoption of online working modality 2 Advance preparation for project's readiness. Activties can start right after AoC signed. 3 Adoption of weekly meeting method to monitor and manage the project activities 4 Regular consultation meetings held to support the provinces by PMU and UN-Habitat 5 UN-Habitat support the PMU to draft all activities' concept and made all communications in advance
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | N/A
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes, but in the first year the effectiveness of applying these measures was not clear as all the activities focus on capacity building
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | During the reporting period, gender equality was taken into serious consideration to integrate in all the capacity building events. The participation of women in the project activities is expected to reach at least 40%. The gender equality is being mainstreamed in the technical guidance and training materials for 1) risk and vulnerability assessment and 2) climate change mainstreaming in strategies, planning, and action plans.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A for the reporting period
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A for the reporting period
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A for the reporting period
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A for the reporting period
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A for the reporting period
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A for the reporting period
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A for the reporting period
What measures are/have been put in place to ensure sustainability of the project/program results? | The national guideline on risk and vulnerability assessment was supported by the project is in the finalizing phase which will be isued by the MONRE and applied nationwide. This output would spread the impact of the project ensuring sustainability of the project's results.
What measures are being/could have been put in place to improve project/program results? | N/A for the reporting period
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | A communication plan is being developed, a project's branding identity is also under development. These plan and tools will help deliver images, information, knowledge and good practices to development partners, networks and working groups.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Project information is being made available to relevant stakeholders throught sharing communication messages on the Ministry's officially technical networks and official media channels. UN-Habitat country office also makes images of the project, Adaptation Fund, implementing partners as well as project's goals and objectives available to different working groups and networks such as Climate Change Working Group (CCWG), Mekong Delta Working Group (MDWG), Disaster Management Working Group (DMWG) etc.
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | N/A for the reporting period
If learning objectives have been established, have they been met? Please describe. | N/A for the reporting period
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A for the reporting period
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A for the reporting period
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | N/A for the reporting period
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative? | N/A for the reporting period
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1.1 | % of female’s participation to the capacity building activities | 0 | 13/30 (43%) female officials, but will be accumulatively measured in the coming years. | At least 40% women
| Level of capacity at national level increased | There is limited understanding about the relationship between climate change adaptation/resilience and ecosystem at all levels | 30 governmental oficials attended the training, but will be accumulatively calculated in the coming years. | 100 National and provincial level government officials, experts and practioners
Output 1.1.1 | # of participants | 0 | Ony 44 participants (15 female participants), due to Covid-19; travel restriction and social distancing. | 100 government officials, experts and prationers at all levels (At least 40% of women)
Output 1.1.2 | Developed guidance and training materials for vulnerability and risk assessment at local levels | There is less and not compressive guidance and training materials for vulnerability and risk assessment a all levels | Received final draft of the technical guidance and training materials | A Full package of developed guidance and training materials for vulnerability and risk assessment
Output 1.1.3 | Developed planning toolkits and training materials for planning, strategy and action plan development. | There is less and not holistic planning toolkits and training materials for planning, strategy and action plan development | Received final draft of the technical guidance and training materials | A full package of 3 planning toolkits for all levels (national, provincial and district+ commune) and 3 training materials for all levels
Output 1.1.4 | # of trained facilitators. | 0 | 30 facilitators attended the training | 20 facilitators will be trained
| % of female experts and consultants for being facilitators | 0 | 13/30 (43%) female facilitators | 40% women
Outcome 1.2 | Level of knowledge capacity at all levels | There is constrained condition and capacity to strengthen knowledge for climate change adaptation | 182 participants at the national/provincial/district levels | 200 government officials, experts and practioners at all levels
| % of female’s participation to the capacity building activities | 0 | 79/182 (43.4%) female participants | At least 40% of women
Output 1.2.1 | # of traning workshops | 0 | Completed. 1 workshop at the national level, 2 workshops at the provincial level | 2 training workshops
| # of participants (40% women) | 0 | 79/182 (43.4%) female participants | 200 participants (40% women)
Outcome 2.1 | # of action plans and strategies developed | 0 | will be measured | 4 dialogue workshops (5 action plans and strategies for 2 provinces and 3 districts)
| # of training workshop | 0 | will be measured | 4 training workshops
| % of female’s participation | 0 | will be measured | At least 40% of women
Output 2.1.1 | # of action plans and strategies developed | 0 | will be measured | 4 dialogue workshops (5 action plans and strategies for 2 provinces and 3 districts)
| # of training workshop | 0 | will be measured | 4 training workshops
Outcome 2.2 | # of dialogues workshops | 0 | will be measured | 10 dialogue workshops
| # of integrated action plans and strategies into planning | 0 | will be measured | 8 training workshops
| % of female’s participation for decision making process | 0 | will be measured | At least 40% of women
Output 2.2.1. | # of integrated action plans and strategies into planning | 0 | will be measured | 8 training workshops
| # of dialogue workshop | 0 | will be measured | 8 dialogue workshops
| # of report for policy framework development | 0 | will be measured | 8 reports from 8 dialogue workshops
Output 2.2.2 | # of integrated action plans and strategies into planning | 0 | will be measured | 8 training workshops (integrate with workshops in the output 2.2.1)
| # of dialogue workshop | 0 | will be measured | 2 dialogue workshops
Outcome 3.1 | # of people who benefit from the prevention system | 0 | will be measured | 92,396 beneficiaries (direct and indirect)
| % of female’s participation and accessibility | 0 | will be measured | At least 40% of women
Output 3.1.1 | # of people who benefit from the prevention system | 4,912 households (approximately 25,000) have been vulnerable to saltwater intrusion to ground water | will be measured | 10,148 direct beneficiaries and 57,049 indirect beneficiaries
Output 3.1.2 | # of people who benefit from the prevention system | 25,199 people have been vulnerable to coastal erosion / 61490 affected agricultural ponds | will be measured | 25,199 direct beneficiaries
Outcome 3.2 | # of people who are trained | 0 | will be measured | 50 trained people
(Output 3.2.1) | # of training workshop | 0 | will be measured | N/A (but could be 2 training workshops at 2 districts)
| # of management and operation guidance materials. | 0 | will be measured | A set of guilding and training materials
| # of female's participation | 0 | will be measured | At least 40% of women
Outcome 4.1 | # of dialogue workshops | 0 | will be measured | 10 dialogue workshops /Policy Platform development
| # of report for policy platform development | 0 | will be measured | 10 reports
Output 4.1.1 | # of dialogue workshops | 0 | will be measured | 10 dialogue workshops
Output 4.1.2 | # of report for policy platform development | 0 | will be measured | 1 policy platform development
| # of practices and experience sharing workshop | 0 | will be measured | N/A (could be integrate in the workshops organized during the project life)

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | VNM/MIE/Urban/2019/1
Implementing Entity | United Nations Human Settlements Programme
Type of implementing entity | MIE
Country | Vietnam
Region | Asia-Pacific
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 92396 | 35347 | 57049 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 40% | 40% | 40% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  | Coastal flooding | 4: Effective | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Coastal management | Local | 1: No plans conducted or updated | 9 | Coastal management | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Water management | Local | 1: No plans conducted or updated | 10 | Water management | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Multi-sector | 2: Low capacity | Total | 100 | Multi-sector | 2: Low capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 40% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 100 | 40% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 2: Low capacity | Public | National | Multi-sector | 2: Low capacity
|  | Public | Regional | Multi-sector | 2: Low capacity | Public | Regional | Multi-sector | 2: Low capacity
|  | Public | Local | Multi-sector | 2: Low capacity | Public | Regional | Multi-sector | 2: Low capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 35347 | 40% | 2: Partially not aware |  | 35347 | 40% | 3: Partially aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | technical guidelines | National |  | 2 | Technical guidelines | National
|  | 0 | technical guidelines | Sub-national |  | 2 | Training manuals | Sub-national
|  | 0 | technical guidelines | Local |  | 2 | Handbooks | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Coastal management | Local | 2: Partially responsive (Lacks most elements) |  | Coastal management | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Multi-community |  | Coastal management | 9 | Multi-community
|  | 0 | Multi-community |  | Water management | 10 | Multi-community
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Coastal management | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 1 | ha rehabilitated | 1: Ineffective | Mangroves | 1 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Coasts | 1 | km rehabilitated | 1: Ineffective | Coasts | 1 | km rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 1 | ha protected | 1: Ineffective | Other | 1 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 4 | Disaster risk reduction | National |  | 4 | Disaster risk reduction | National
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 2 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective | 2 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Water management | Community | Innovation rolled out |  | Water management | Community | Innovation scaled-up
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 2 | Water management | No innovative practices | 1: Ineffective | 2 | Water management | Completed innovation practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness