MONITORING REPORT SUBMITTED SIX MONTHS AFTER PROJECT START AND EVERY SIX MONTHS AFTER THE LAST MONITORING REPORT

Date of Submission: 1st April 2024

Monitoring Report Number: Second Report

Implementing Entity: NATIONAL ENVIRONMENT MANAGEMENT AUTHORITY (NEMA) - KENYA

Country: BOTSWANA

Adaptation Fund Grant I.D: NIE022

Grant Type:  SOUTH-SOUTH COOPERATION GRANT

Project Description/Project Title: Support National Implementing Entity (NIE) candidate Selection and Accreditation for Botswana The South South Cooperation grant is for peer to peer mentorship programme for Botswana Meteorological Services (BMS) to identify a suitable candidate and to pursue NIE accreditation status and to support the identified institution to apply for the accreditation.

Project Sector: Peer to peer support

| Activity | Expected Output | Progress (include completion Date “month & year”) | Comments/Explanation (also explain any deviation from initial plan) |
| --- | --- | --- | --- |
|  |  |  | Please paraphrase, for example: Vulnerability assessment carried out, 2 consultants hired, 3 consultations with vulnerable groups held, 2 studies completed etc. |
| MEETINGS | Commitment between Botswana, NEMA, DA on the roadmap on how to execute the mentorship programme | - Brief on the programme to the CEOs, DA, PS in Botswana and Kenya made. - Commitment and support for the project has been given. The Deputy Permanent Secretary attended the inception meeting, thereby giving assurance of the government’s commitment to support the accreditation process. - High Level meetings proposed to be carried out at the end of the Project period. - Technical meetings to start happening virtually as the COVID -19 situation protocols banned travelling out of the country. | The physical meeting planned for could not take place due to the COVID 19 pandemic protocols. |
| IN COUNTRY WORKSHOP | - Action plan for managing accreditation application process developed. - Action plan for gaps (if they exist) in place - Reviewed systems, procedures and documents in place. - Submission of documents for accreditation done. | Inception virtual meeting held on 25th May 2021. The objectives of the meeting were: - Inception of project activities under the South-South Grant to support Botswana Meteorological Services identify an NIE. - Review the approved workplan activities in the context Covid-19 containment measures. - Share the NIE candidate selection criteria. - Share the accreditation process and requirements by AF. - Action Planning. Discussed and agreed: - DA Botswana to engage with the two proposed candidates - National Development Bank (NDB) and Botswana Innovation Hub and select the best suited to pursue accreditation by end of June 2021. | Accreditation requirements and process clarified and expectations levelled. |
|  |  | A follow-up virtual meeting with DA Botswana, NDB and NEMA held on 10th August 2021. The objective of the meeting was: - To assess NDBs readiness status in pursuing the accreditation application, - To find out the existing gaps at NDB - Action Plan to address the gaps identified developed. Deliberations - NDB was requested to start filling the application form in Parts and share with NEMA. They should fill the form Part by Part starting with I & II and share with NEMA for comments by 31st August 2021. Once all the Parts are completed, a meeting to review to be held. - Programme of action developed on how to fill the gaps identified. - Meeting proposal (physical) to review systems, procedures and documents planned for November 2021. | Gaps identified and preliminary action plan developed. |
|  |  | - Physical meeting held from 21st to 25th February 2022 in Nairobi Kenya. Objectives of the workshop included: - Secure commitment from both countries to execute the Adaptation Fund South to South grant towards achieving accreditation - Support in the identification of documents for accreditation submission - Develop an action plan for gaps that needed to be addressed - Training on NEMA’s governance tools Discussed and Agreed - NEMA to share with NDB the adaptation fund project review criteria for ranking proposals that it used to evaluate proposal for submission. - NDB to conclude the ESMF that is under development. - NDB to develop an internal social policy statement policy. - NDB to designate a Grievance Redress Mechanism (GRM) focal person and to dedicate more time to the process. - NEMA – NDB initial application review meeting to be held after initiating the application process. - NDB to submit the accreditation application to AF | Increased knowledge for NDB on Adaptation Fund Operational Procedures and Guidelines and accreditation requirements. |
|  |  | March 1, 2023 - Held a virtual meeting to review the accreditation workflow as populated by NDB. - Review comments given and a timeline to share the revised workflow given. March 11, 2023 - ESMF NDB policy shared with NEMA for comments March 15, 2023 - NDB accreditation workflow and supporting documents evidence per section shared with NEMA. Only the supporting document titles could be accessed. May 10, 2023 - Virtual meeting held to review the revised NDB workflow. - The need to access the description/narrative in the workflow raised. This is to enable NEMA go through the workflow in totality before recommending its submission. - Meeting to go through the workflow description of the sections planned for early July 2023. | Continuous support provided virtually |
|  |  | July 13, 2023 - NDB submitted their accreditation application to AF September 2023 - NDB received the accreditation application review comments. |  |
|  |  | 20th March 2024 - Virtual meeting with NDB Botswana to discuss the progress of the status of the review comments submitted to AF Secretariat. |  |
| TRAINING WORKSHOP | Governance tools: on financial risk management, grievance redress management, social safeguards, gender, anti - corruption, M&E in place | To be held at a later date | Planned for May 2024 |
| Post review of the submitted application by the AF Accreditation Panel. | Submission of a revised application for AF accreditation consideration | TBD |  |
| Overall comment on progress | The project had significant delays due to the COVID 19 pandemic containment measures therefore started late. The project is at approximately 80% completion. |  |  |
| New completion date or Expected completion date | The new expected completion date is June 2024. |  |  |

Contact Person: __Dr. Anne Omambia, NIE Coordinator____			Email: __anomambia2002@yahoo.co.uk_________

Mr. John Wafula, Deputy NIE Coordinator			Email: jswafula@gmail.com