## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | November 2020 - December 2021
| Project Title: | AF-EU-UNDP Innovation Small Grant Aggregator Platform
| Project Summary: | The AF-EU-UNDP Innovation Small Grant Aggregator Platform (ISGAP) aims to support the development, diffusion and evidence building of innovative adaptation practices, tools, and technologies in developing countries. ISGAP is designed to meet this objective through an effective and efficient backbone management architecture and network of global best practitioners to (i) competitively source and screen innovative adaptation project ideas; (ii) grant funding and administering to bring selected project ideas to fruition; (iii) provision of customized technical and business development capacity building, incubation, and acceleration support; and (iv) knowledge management and sharing and result-based monitoring and evaluation. Leveraging this infrastructure, ISGAP aims to achieve the project objective through the following complementary outcomes: 1. Development of innovative adaptation practices, tools and technologies promoted and accelerated. Evidence of effective, efficient adaptation practices, products and technologies generated as a basis for implementing entities and other funds to enable scaling up. 2. Timely and efficient completion of business milestones demonstrated through additional investment and/or support capitalization for scaling 3. Lessons learned codified, documented, and disseminated leading to adoption or replication of project introduced innovations In parallel, AF is providing direct access to similar innovation small grants through National Implementing Entities (NIEs). Therefore, ISGAP’s knowledge management and information sharing design will include joint activities and participation from NIEs that have received the Innovation Small Grants so as to ensure a degree of consistency and parity between NIE and non-NIE recipients of the small grants.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | UNDP - PIMS 6266 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme (UNDP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Multi-country (Global) | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Global | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 11 October 2019 (Decision B.34/33)
IE-AFB Agreement Signature Date: |  | 2020-03-19 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2020-11-18 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | Est. Nov 2022
| Terminal Evaluation Date: | Est. Nov 2024
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1. Programme website (this includes four news articles): https://www.adaptation-undp.org/smallgrantaggregator/ 2. AFCIA brochsure https://undp-my.sharepoint.com/:b:/r/personal/chongguang_yu_undp_org/Documents/Work%20files/AF%20project/Products/AFCIA%20brochure.pdf?csf=1&web=1&e=ecJAaX 3. AFCIA launch videos (opening, high level reprsentatives' speech), file too large to upload, can be shared upon request. Presentation: https://undp-my.sharepoint.com/:p:/r/personal/chongguang_yu_undp_org/Documents/Work%20files/AF%20project/Products/AFCIA%20launch%20event%20UNDP%20Grant%20Funding%20.pptx?d=w8da1369eaa794ee795df786dae8b3761&csf=1&web=1&e=ME4J32 4. Gobeshona Global Conference for Locally Led Action- UNDP session figuring AFCIA (video, can be shared upon request), presentation: https://undp-my.sharepoint.com/:p:/r/personal/chongguang_yu_undp_org/Documents/Work%20files/AF%20project/Products/Adaptation%20Innovation%20Marketplace%20-final.pptx?d=w8cbc3ff3d1de4411b251f9f1b9a4b02f&csf=1&web=1&e=DtNnNm 5. Climate Adaptation Summmit 2021, video can be shared upon request. 6. Adaptation Fund Innovation Knowledge sharing workshop. Presentation: https://undp-my.sharepoint.com/:p:/r/personal/chongguang_yu_undp_org/Documents/Work%20files/AF%20project/Products/AFCIA%20Innovation%20Knowledge%20Sharing%20workshop.pptx?d=w3541a1bdb2904a119be76990df55f6de&csf=1&web=1&e=UykhJV 7. AF-EU-UNDP ISGAP window under AFCIA first board meeting. Minutes: https://undp-my.sharepoint.com/:w:/r/personal/chongguang_yu_undp_org/Documents/Work%20files/AF%20project/Products/Meeting%20notes-ISGAP%201st%20Board%20Meeting%208%20July%202021.docx?d=wa852c082340b4b1d86694b84a8a31168&csf=1&web=1&e=HXX8UT Presentation: https://undp-my.sharepoint.com/:p:/r/personal/chongguang_yu_undp_org/Documents/Work%20files/AF%20project/Products/AF-EU-UNDP%20Innovation%20Small%20Grant%20Aggregator%20Platform%20Board%20Meeting%20Presentation.pptx?d=wcf6f7d89de15429ea42eb75dabd240cd&csf=1&web=1&e=kJwkFD | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | https://www.adaptation-undp.org/smallgrantaggregator/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Artak Melkonyan | Dominican Republic
| Email: | artak.melkonyan@undp.org | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: |  | Equatoral Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Charles (Chongguang) Yu | Fiji
| Email: | chongguang.yu@undp.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: |  | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31 Oct 2021 | 1224
Add any comments on AF Grant Funds. (word limit=200) | The first disbursment was received in April 2020. The expenditures reported below are accumulative until 31 October 2021. Please note that the delivery rate is exceptionally low because of the delay in setting up and fully incporate changes in the goverance structure to also with the approval of additional EU funding into the project that was received at the end of December 2020. Despite the above, it is requested that the next disbursement be released upon the clearance of this PPR because the project plans to deliver around 22 grants in the approx. amount of $800,000 (first tranche of the grant funding to grantees; 40%AF funding, 60% EU funding) early 2022. Additional $1,500,000 will be disbursed by the middle of next year (40%AF funding, 60% EU funding. This includes the first tranche of second round funding and second tranche of first round funding; with additional two large procurement items expected for around $160,000 (one to engage a consortium of NGOs/CSOs for knowledge management $80,000 per year; one to procure a broker network to educate and engage with investors, corporate foundations and family investment offices (competitive bidding, budget around $80,000 one-off to test out one year, if the engagement is positive and well received by grantees, will become yearly).
INVESTMENT INCOME | N/A
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Component 1: Provision of Innovation Small Grants | 0
| Component 2: Provision of Technical and Business Development Capacity Building, Incubation, and Acceleration Support | 64
| Component 3: Knowledge Management and sharing and Result-Based Monitoring and Evaluation | 1160
| Project Management Costs | 0
| TOTAL | 1224
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Component 1: Provision of Innovation Small Grants | 1050000 | 2022-12-31
| Component 2: Provision of Technical and Business Development Capacity Building, Incubation, and Acceleration Support | 190333.3333 | 2022-12-31
| Component 3: Knowledge Management and sharing and Result-Based Monitoring and Evaluation | 110916.6667 | 2022-12-31
| Project Management Costs | 23333.3333 | 2022-12-31
| TOTAL | 1374583.3333
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | N/A
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Misappropriation of the grant funding | [Medium] The risk still remains valid. | Performance based disbursement will be used instead of providing the total grant amount at the grant signing stage. One finance analyst is under recuitment to check on large ticket procurement items from the grantees. Financial audit maybe required as a part of the annual progress report.
Lack of participation at the global call for proposals | [Medium] The risk not valid anymore. | We have received more applications than expected. It was a successful call for proposals.
Project implementation delay | [Medium] The risk still remains valid. | Project implementation is delayed by around 3 months, this is partly due to the new governance structure set up due to EU funding. COVID-19 also has significant impact due to procurement hold-up and delay in PMU recuitment.
Success is overstated in the progress report while failure is understated or unreported | [Medium] The risk still remains valid. | It is crucial that both success and failure are documented and analysed by the grantees. It is a critical part of the knowledge sharing and lessons learned. In fact, one often learns from failure than success. This message will be communicated throughout the programme implementation cycle and regularly monitored.
Grantees fail in securing scale up and replication support and funding from other sources after the completion of the project | [Medium] The risk still remains valid. | It is critical to note that the success rate of any start-up or innovation venture is quite low. With all the support provided by ISGAP and its partners, it is anticipated that the success would be in the range of 20%-30%.
Environmental, social and governance risk not managed, triggering risk events | [Medium] The risk still remains valid. | Environmental, social and governance criteria will be established in every step of the ISGAP programme. UNDP Social and Environmental Safeguards Procedure (SESP) will be used to ensure the controls of this risk are in place. ESG management plan will be prepared before the programme implementation. Call of proposal will highlight potential ESG risk, selection template will contain ESG risk identification questions, ESG expert will be presented in the technical panel, M&E will also contain a ESG reporting section.
ISGAP does not attract sufficient support from private sector | [Medium] The risk still remains valid. | Throughout the various project phases (launch, global call, evaluation, fund disbursement, showcasing etc.), emphasis will be given to engaging like minded private sector partners. Specific conversations related to unlocking private sector support to this agenda will be curated alongside the key project activities. Also engage local and global private sector partners in evaluation panels.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
COVID-19 impact on project implementation | [Highly] - risk still valid | From the project management perspective, digital engagement will be conducted throughout all project activities instead of in-person engagement until COVID-19 situation improve at a global level. From the project implementation perspective, UNDP will work with the grantees to design COVID-19 mitigation strategy under each grantee’s work plan. Necessary procurement of personal protective equipment for project implementation, if required by the grantee, could be considered under their grant budget. Given the project context and operating environment, it might be necessary for the project to provide basic awareness raising and training with regards to COVID-19. This will be part of the technical assistance provided by UNDP to grantees. Internally, Covid-19 has significant impact on UNDP's procurement and recuitment process, this situtation has improved by the second half of this year and we expected system/process will return to normal by the end of this year.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
One new risk has been identified during this year. Staff turnover with the grant applicants has affected the shortlisting process. In total, five shortlisted applicants did not response to our request for proposal process. This risk was mitigated by two actions: 1, the project team has conducted various attempts to contact applicating organizations (using LinkedIn, organizations' website, Country Office network); 3 out of 5 organizations were successfully contacted. 2, Discussion with the grant selection committee, since the shortlisting process was based on a ranking of longlisted applicants, we have extended the shortlisted applicant number from 30 to 32 to make up with the two non-responsive applicants.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1] | N/A
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law
2 - Access and equity |  |  | Communities in the project area (including ethnic minorities) could face economic displacement, changes to land rights and/or restricted access to resources because of the grant recipient businesses and social enterprises expansion. | For this and all other SES-related risks, the Project Board has established screening criteria requiring grantees to incorporate social and environmental risk asessmenet and management measurements. During the selection process and M&E process, a Safeguard expert has been hired to review the grant applicants and ensure that appropriate management measures are in place (this is currently taking place). | Under development
3 – Marginalized and vulnerable Groups |  |  | There is a likelihood that the Project would exclude any potentially affected stakeholders, in particular marginalized groups, from fully participating in decisions that may affect them. NGOs/CSOs that received grant from UNDP also involve in adverse impact from employment. In addition, although the project aims to find climate change adaptation solutions that improve resilience, it is still likely that when handle incorrectly, the grant recipient businesses or social enterprises could exacerbate conflicts among and/or the risk of violence to project-affected communities and individuals by business expansion. | For this and all other SES-related risks, the Project Board has established screening criteria requiring grantees to incorporate social and environmental risk asessmenet and management measurements. During the selection process and M&E process, a Safeguard expert has been hired to review the grant applicants and ensure that appropriate management measures are in place (this is currently taking place). | Under development
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | The grant recipient NGOs/CSOs could limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions given the employment choice and local culture. Project potentially reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits through grant selection. | This program’s screening criteria has gender considerations. The grant proposal will describe how the project would adhere to the UNDP’s Gender policy including gender mainstreaming and women’s empowerment. The proposal will ensure that women and men are provided with an equal opportunity to build resilience, address their differentiated vulnerabilities and increase their capability to adapt to climate change impacts. The proposal will illustrate how gender equality is embedded in the project design, consultation, implementation, monitoring, reporting, and evaluation. From a result perspective, Grantees are required to prepare bi-annual Performance Briefs on the progress of their projects including status of their compliance with UNDP environment, social, and gender policy, in addition, any measures undertaken or impact created that addressing gender equality. | Under development
6 – Core labour rights |  |  | The grant recipient NGOs/CSOs might fail to comply with national and international labor standards.
7 – Indigenous peoples |  |  | The project aims to provide grants to local NGOs/CSOs in developing countries. The project will be working with indigenous peoples, either as grantees, customers of grantees or suppliers of grantees. | Grantees would need to clear to notice project team around indigenous people in their employee or customers. This risk need to be addressed in their workplan if they do employ/service/compete with indigenous peoples. | Under development
8 – Involuntary resettlement
9 – Protection of natural habitats |  |  | Grants to NGOs/CSOs that their business model could cause adverse impacts to habitats, e.g. associated with harvesting of natural forests or harvesting of fish populations or other aquatic species. | For this and all other SES-related risks, the Project Board has established screening criteria requiring grantees to incorporate social and environmental risk asessmenet and management measurements. During the selection process and M&E process, a Safeguard expert has been hired to review the grant applicants and ensure that appropriate management measures are in place (this is currently taking place). | Under development
10 – Conservation of biological diversity |  |  | Grantee might have business activities within or adjacent to critical habitats and/or environmentally sensitive areas, including legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities. | For this and all other SES-related risks, the Project Board has established screening criteria requiring grantees to incorporate social and environmental risk asessmenet and management measurements. During the selection process and M&E process, a Safeguard expert has been hired to review the grant applicants and ensure that appropriate management measures are in place (this is currently taking place). | Under development
11 – Climate change
12 – Pollution prevention and resource efficiency
13 – Public health |  |  | Employment with the NGOs/CSOs could pose a potential risk to health and safety of individuals depends on the business activities (eg. Use of new pesticide, or new fertilizer, using of unfamiliar equipment). | For this and all other SES-related risks, the Project Board has established screening criteria requiring grantees to incorporate social and environmental risk asessmenet and management measurements. During the selection process and M&E process, a Safeguard expert has been hired to review the grant applicants and ensure that appropriate management measures are in place (this is currently taking place). | Under development
14 – Physical and cultural heritage |  |  | The grant recipient NGOs/CSOs or UNDP could lead to commercialize traditional knowledge. As NGOs/CSOs grantees will share their lessons learnt in their innovative approach to climate change adaptation, other actors could use the knowledge product of UNDP to commercialize these traditional knowledge. As part of the project, UNDP is expected to act as an investment broker to find commercial investors to invest commercially in scalable grantees. | For this and all other SES-related risks, the Project Board has established screening criteria requiring grantees to incorporate social and environmental risk asessmenet and management measurements. During the selection process and M&E process, a Safeguard expert has been hired to review the grant applicants and ensure that appropriate management measures are in place (this is currently taking place). | Under development
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | The sageguard consultant is current working with the project team to design M&E for unanticipated ESP risks
Have unanticipated ESP risks been identified during the reporting period? |  | None, as grantees are under final selection process, not yet selected
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Project Bobard has established screening criteria, requiring grantees to incorporate social and environmental risks measurement. During the selection process and M&E process, a Safeguards expert is hired to review the grant applicants and ensure that appropriate management measures are in place. Grantees are asked to submit quarterly update on their risk management plan Safeguard & gender training is planned in the first two months after the grantees are on-board
Have the implementation arrangements been effective during the reporting period? |  | Yes, from understanding the risks perspective; the project has successfully identifying possible risks with the grantees through screening process and proposal submission process.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | IP is the EE in this case
Have the implementation arrangements at the EEs been effective during the reporting period? |  | IP is the EE in this case
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | With grantees are now selected, a ESMF is planned in 2022. For the grant selection process, a screening process has been performed (a mini SESP) for each grantee based on self reporting and safeguard expert review.For each bi-annual reporting, grantees will be reporting Environmental and Social risks (both identified during the project proposal stage and new risks that occurred during the reporting period, in alignment with UNDP SES and cross-checked with AF safeguard principles. All reports will be reviewed by a safeguard consultant and PMU for each reporting period. The IE will report on monitoring measures in Section 5 of ESP sections from PPR2 onwards consoildating the grantee reports.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11] |  | Not in this period, a new ESMF will be developed in 2022.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP] | The IE will report on monitoring measures in Section 5 of ESP sections from PPR2 onwards consoildating the grantee reports.
USP 2: [name the USP] | As above for other 22 grantees
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
N/A
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | No
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Ensure new innovations promote and accelerate gender equality and women’s empowerment |  | #/% of new innovations promoted and accelerated that accounts for the structural barriers and needs of women | 0 | 50% | Good (Gender is a factor in all stage of screening and selection process. Therefore, all grant proposals have provided baseline and planned action that the applicant will enhance or empower women through their operation.)
Ensure evidence base generated is segregated by gender. |  | # of adaptation innovation evidence generated with insights on women | 0 | 50% | n/a (no knowledge products generated yet)
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
N/A
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | Gender is mainstreamed with the entire project implementation. From the application process, gender is one of the screening critieria, applicants need to highlight how their work further empowers women and how their intended innovations promote results in an increase wellfare or livelihood for women
Have the implementation arrangements at the IE been effective during the reporting period? |  | Reasonably effective; a gender consultant will be hired to work with grantees next year (2022) to improve the grantees' reporting on gender issues.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | IE is the EE for this project
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | IE is the EE for this project
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | N/A
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
N/A
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Outcome 1.1: AF MTS ER3 – Development of innovative adaptation practices, tools and technologies encouraged and accelerated |  | It is expected 5-10 innovative adaptation projects will be funded by the ISGAP by now. |  | In November, the grant selection committee has reviewing the 32 shortlisted applicants’ proposals to make a final list of 22 grantees. Out of the 22 finalist, 7 proposals come from the Africa region, 11 from Asia & Pacific, 4 from Latin America. We have 4 proposals from SIDS, and 10 proposals from LDC+SIDS (45%). Out of the 22 finalist, it covers 19 countries. No single country has more than 2 proposals. It has a good balance between regions and LDC/SIDS. Project board has endorsed these finalist on the 15th of December. Grant agreement signing and first disbursement are anticipated to be in early 2022. | Marginally Unsatisfactory (MU)
| Outcome 1.2: AF MTS ER4 – Evidence of effective, efficient adaptation practices, products and technologies generated as a basis for implementing entities and other funds to assess scaling up |  | No expected progress of this outcome at this stage. |  | N/A (milestones from grantee are agreed and approved as part of the grant proposals submitted to the project board meeting. | Satisfactory (S)
| Outcome 2: Grantees’ innovation and business development capacity enhanced |  | It is expected that 5-10 grantees will recevie first tranche of grant disbursement according to agreed grantees’ performance target by now. |  | Technical advisory support, capacity building support and scheduled training events have all been line-up; once the grantees are on-boarded, these will take place without delay. | Satisfactory (S)
| Outcome 3: Lessons learned are codified, documented, and disseminated/shared leading to adoption or replication of project ideas by others |  | No expected progress of this outcome at this stage. |  | In terms of lessons learned sharing events, there are two sessions conducted this year. One was hosted by Adaptation Fund - Adaptation Fund Innovation Knowledge sharing workshop (22nd November); in this workshop, UNDP shared the lessons learned around managing the process of call for proposals at a global level to engage global NGOs/CSOs and the challenges on the selection and screening processes. Another knowledge sharing event was conducted with grant selection committee (30th of November). During this meeting, many feedbacks and suggestions were provided to the project team and we will incorporate these to improve the next round of call for proposals. | Satisfactory (S)
[5 empty] | Overall Rating | Marginally Satisfactory (MS)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Artak Melkonyan
| Email: | artak.melkonyan@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
We have been quite unfortunate with the Project Manager recuitment. The recuitment started last year 2020 November. Due the the new funding from EU, the project manager post has been upgraded and therefore the recuitment process has to restart. In June, we have completed the recuitment and one candidate was identified. However, due to medically condition of the candidate in July, the candidate withdraw the application. Therefore we have to re-advertise the position again in August. We are in the final process of recuitment now, interview of the project manager is expected to be this month. If everything goes well, we should finally have a PM by next month. During this period, the UNDP staff Artak Melkonyan is acting as the interim Project Manager supporting implementation.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Outcome 1.1: AF MTS ER3 – Development of innovative adaptation practices, tools and technologies encouraged and accelerated |  | It is expected 5-10 innovative adaptation projects will be funded by the ISGAP by now. |  | Under component one, the project aims to provide grant funding to global NGOs/CSOs that are working in the field of climate change adaptation with innovative ideas/technology/business models/practice. An initial project launch event took place in November 2020 in collaboration with UNEP and CTCN. A joint project brochure and a project website were designed for the launch event. The launch event was very successful, with 800+ audience members attending the two launch events. In late December, EU had indicated a co-financing opportunity for this project. The funding materialized in early January 2021. Originally, 5-10 grants were planned for year one with Adaptation Fund funding (with another 5-10 in year two). Due to the additional funding from the EU, the project improved targets to provide 15-20 grants in year one and another 15-20 in year two. The first call for proposal was launched in December 2020 and closed in February 2021. UNDP received an overwhelming 383 applications, a lot more than expected (expecting 50-100). Therefore, additional implementation time was spent on engaging with the applicants to ensure they had equal access and opportunity to apply, following up with the applicants that had issues with IT/submission/legal questions (between February and April). With the additional donor, a new governance structure was set up, which caused some delay around project implementation. This is mainly due to a policy constraint which required the project board to approve the grant selection criteria and grant selection committee before the selection process could take place. The project board and technical advisory group was confirmed and established around June 2021. The first board meeting was held on 8th of July 2021; during this project board meeting, the project board endorsed the project governance structure, grant selection criteria and grant selection committee. Since the project board meeting, the implementation has been on schedule, with longlisting completed by August. The grant selection committee completed the shortlisting process by September. 30 shortlisted applicants were given four weeks to submit a detailed proposal, budget and work plan. In November, the grant selection committee reviewed the 32 shortlisted applicants’ proposals to make a final list of 22 grantees. Out of the 22 finalists, 7 proposals come from the Africa region, 11 from Asia & Pacific, 4 from Latin America. We have 4 proposals from SIDS, and 10 proposals from LDC+SIDS (45%). 19 countries are represented amongst the 22 finalists. No single country has more than 2 proposals. There is a good balance between regions and LDC/SIDS. The project board endorsed these finalists on the 15th of December 2021. Grant agreement signing and first disbursement are anticipated to be in early 2022. Please see the list of finalists in the seperate excel file - Summary of first round funding finalists | Marginally Unsatisfactory (MU)
| Outcome 1.2: AF MTS ER4 – Evidence of effective, efficient adaptation practices, products and technologies generated as a basis for implementing entities and other funds to assess scaling up |  | No expected progress of this outcome at this stage. |  | N/A (milestones from grantee are agreed and approved as part of the grant proposals submitted to the project board meeting. | Satisfactory (S)
| Outcome 2: Grantees’ innovation and business development capacity enhanced |  | It is expected that 5-10 grantees will recevie first tranche of grant disbursement according to agreed grantees’ performance target by now. |  | Technical advisory support, capacity building support and scheduled training events have all been lined-up. Once the grantees are on-boarded, these will take place without delay. Centralized training of conducting business with international development partners from UNDP is ready. Grantees will be trained on safeguards, nature-based solutions for sustainable development, ecosystem restoration, green entrepreneurship, gender equality, women’s empowerment and leadership, understanding resilience thinking and more. https://www.learningfornature.org/en/course-offerings/ It is important to note that although not planned in the project, the project team realized that in order to successfully help the local partners to achieve their development objectives, we need to support them with further detail in their grant proposal related to their workplan, financial management and risk management. This work has been conducted by the project team and consultants after the grant selection committee recommended the 22 finalists. It was also a new process designed to screen out high safeguard risk applicants. Each finalist has received substantial support from UNDP to ensure their milestones are aligned with financial planning and result indictors; their result indictors are aligned with international standards and with a means of verification; safeguard risks are screened, and risk mitigation controls are properly planned. | Satisfactory (S)
| Outcome 3: Lessons learned are codified, documented, and disseminated/shared leading to adoption or replication of project ideas by others |  | No expected progress of this outcome at this stage. |  | A consortium of NGOs/CSOs will be the responsible party to conduct the knowledge management and sharing component of the project. Three organizations who have significant experience in engaging grassroots organizations for knowledge sharing and conducting south-south learning events (GRP/ICCCAD/CDKM) have been appointed. They have indicated their interest to support UNDP to share the lessons learnt from the project and engage global grassroots organizations to enhance the work of locally led action, and advocate for the project in international events. Internally, UNDP is working closely with the Youth team and SGP to share the knowledge from this project to wider audiences. The project was presented in the Youth Co:Lab Summit 2021 - Facilitating hotseat on Climate, engaging 500+ youth on the discussion of climate entrepreneurship. In terms of lessons learned sharing events, there were two sessions conducted this year. One was hosted by Adaptation Fund - Adaptation Fund Innovation Knowledge sharing workshop (22nd November); in this workshop, UNDP shared the lessons learned around managing the process of the call for proposals at a global level to engage global NGOs/CSOs, and the challenges in the selection and screening processes. Another knowledge sharing event was conducted with the grant selection committee (30th of November). During this meeting, much feedback and many suggestions were provided to the project team which will be incorporated to improve the next round of call for proposals. | Satisfactory (S)
[5 empty] | Overall Rating | Marginally Satisfactory (MS)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Chongguang Yu
| Email: | chongguang.yu@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The overall objective of the AF-EU-UNDP Innovation Small Grant Aggregator Platform (ISGAP) project, "support the development, diffusion and evidence building of innovative adaptation practices, tools, and technologies in developing countries", has been achieved Marginally Satisfactory. The project has made an important connection to global organizations that are working in the field of adaptation. The first call for proposals received an overwhelming 383 applications from NGOs/CSOs globally. It is expected that 22 organizations will be endorsed as first-round funding grantees before the end of this year and receive their first tranche of grant funding to support their innovative work early next year. Out of the 22 finalists, 7 proposals come from the Africa region, 11 from Asia & Pacific, 4 from Latin America. We have 4 proposals from SIDS, and 10 proposals from LDC+SIDS (45%). The 22 finalists cover 19 countries. No single country has more than 2 proposals. There is a good balance between regions and LDC/SIDS. The project board endorsed these finalists on the 15th of December. Grant agreement signing and first disbursements are anticipated to be in early 2022. Supporting locally led innovative adaptation action is quite a new field of work, and with the experience generated from the first round of proposals, the second round planned next year should run more smoothly. A key challenge encountered during implementation was in addressing 380+ applicants' inquiries and providing them with fair access to the funding. The initially planned two weeks of first stage submission was deemed too short. Therefore, the application time was extended to one month and two weeks. This challenge recurred during the shortlisting stage, where the project team needs to work with each applicants to improve the quality of their proposed indicators and milestones. The project team has set up a separate email address for the grant applicants; the entire project team has access to this email and is working together to respond to all the inquiries from the applicants. Another challenge was to set up the grant selection committee. Since the role of the grant selection committee member is pro-bono to ensure a neutral position, it took a while to find the experts that are qualified and willing to become a committee member. Now with the grant selection committee established, it is hoped that the second round of call for proposals early next year will be implemented without much delay. Positive progress made in the project is the number of partnerships it has generated over this year. The project is proud to have many influential partners in the technical advisory group for the project board. Currently, the technical advisory group consists of Global Resilience Partnership, Climate-KIC, International Centre for Climate Change and Development, LDCs University Consortium, UNCDF and Natural Strategies Investments GmbH (an impact fund). Other project level partnerships include USAID’s Climate Ready programme, WE4F fund, GEF SGP and Youth CO:Lab funded by Citi bank. The strength of the technical advisory group will translate to better technical assistance and capacity building support to the project grantees. Several capacity building and knowledge sharing initiatives have been planned for next year with the project partners. Overall, this year generated many lessons and learnings on how to engage global grassroots organizations for better access to direct international funding. Despite implementation delays, the project is on track to be delivered and implemented in 2022.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
| Number of innovative adaptation practices, tools and technologies funded | 0 | 22 | 15-30
| Quantity and quality of key findings on effective, efficient adaptation practices, products and technologies generated Number of adaptation practices proven to be successful (through monitoring visits) | 0 | 0 | Minimum of 5 out of 10 funded projects that demonstrate findings and evidences of effective and efficient adaptation practices, products, and technologies
| Number of women-led CSOs that develop replication projects | 0 | 0 | (at least 50% with women led organisations or organisations largely benefit women customers)
| Number of grantees that successfully complete innovation and business development milestones and grant disbursement according to agreed grantees’ performance target | 0 | 0 | All grantees complete grant disbursement against performance target within 24 months after grant agreement signed
| Number of grantees that receive additional support/funding to scale up and/or replication | 0 | 0 | At least half of the grantees received additional support/funding to scale up and/or replication
| Annual training events | 0 | 0 | Four annual web-based publication/blog and lessons learned, and at least four technical brief/blog on specific topics (with one lessons learned brief on innovative ways of address gender inequality in adaptation to climate change)
| Citation and/or adoption of shared lessons learned and codified knowledge | 0 | 0 | One annual impact/knowledge publication

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1. Time allowed for local organizations to submit their proposal; and their understanding of adaptation and innovation. The project team has overestimated the capacity of the local organizations to submit proposals on adaptation innovation. Many questions were raised from the applicants, and the initial planned two-week application time was not sufficient. A similar issue occurred during the shortlisting stage, where applicants were asked to submit a detailed proposal. A few local organizations were in the field and weren’t prepared for submitting a detailed proposal over a short duration (although we had communicated the timeline with the applicants, the level of detailed information required in the proposal surprised many applicants). In addition, the project team had to guide a few applicants on their budget and work plan to ensure they met the standard of UNDP’s low-value grant criteria. 2. Definition of what is considered “adaptation innovation”. There were several discussions between experts in the grant selection committee related to “adaptation innovation”. Although many applicants are clearly working on resilience building, and many applicants are working on innovative activities, the combined nexus of adaptation innovation is more limited. This was resolved by having a separate score for adaptation and for innovation, where a combined score is used as comparison between applicants. Therefore, the time spent on designing grant selection criteria was longer than expected. 3. The project has developed strong partnerships, which had a positive impact on project implementation. Adaptation innovation is a relatively new field of work, but many project partners have supported climate innovation before, and they have provided valuable lessons learnt and information in support of this project. Although incorporating additional guidance and information from the partners caused a few delays in designing the governance structure and project documents, the overall quality of implementation improved due to the guidance from partners. In detail, UNCDF provided guidance on the grant selection process, GRP and Climate-KIC provided suggestions on grant selection criteria and M&E process. ICCCAD has provided insights and suggestions on the project governance and knowledge management process. A few industry partners (private sector partners) provided advice on how to structure milestone settings for grantees. The project has received many more applicants than expected due to the partners’ network (UNDP Youth team’s 6000+ young entrepreneurs, Climate-KIC’s graduates of ClimateLaunchpad programme, previous UNDP SGP grantees and GRP’s network of CSOs/NGOs). 4. Feedback from the grant selection committee on the selection process After the selection process, a meeting was held with the grant selection committee, and much feedback was received and taken note of; we plan to improve the next call for proposals as a result of this. Details are captured in the meeting notes. In summary: 1. Better guiding questions on innovation & adaptation, 2. Better design of the grant application portal and proposal, 3. Convene a meeting to discuss "challenging" applications, 4. Separate micro and small grant application forms, 5. Impose word limit on a few sections of the proposal (some proposals have 70+ pages).
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | As mentioned above and in the rating section, implementation delays were caused by additional time for setting up the project governance structure, design and set up of the grant selection criteria and grant selection committee, longer than planned time for the two processes of the grant application (first application and detailed proposal) due to the capacity of local organizations and the number of applicants. Although these issues caused project delays, for each of these issues, the project team has worked with partners and local organizations to ensure the quality of the project implementation was improved due to the strengthing of project processes and support to the project applicants. The project model is a new way to engage local actors on adaptation innovation, and now the project team has a better understanding of the timeframe for each process and issues that could occur in each process which will help the second round of call for proposals in early next year.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | There are no changes in the project design. The additional funding from EU certainly improved the project ambition and caused changes in the project governance structure. From an output perspective, the project now has improved targets of the number of innovative adaptation practices, tools and technologies funded, from 10-15 now to 30-40.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Not yet. A safeguard consultant is currently working with the final project grantees on their workplan to design plans and controls for safeguard risks.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender is mainstreamed with the entire project implementation. From the application process, gender is one of the screening critieria, applicants need to highlight how their work further empowers women and how their intended innovations promote results in an increase wellfare or livelihood for women. This was criteria for both the initial application process and the detailed project proposal process. Interestingly, all project applicants highlighted that their project will support women and empower women. A gender consultant is planned to be recuited to engage with each grantee to understand more on gender empowerment aspect of the project.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 6266
Implementing Entity | UNDP
Type of implementing entity | MIE
Country |  | Global
Region |  | Global
Sector |  | All
No target was set, but we will repor the beneficiaries as we progress in the project.
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total |  |  |  | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
We will report this section in the next PPR, currently 0 since not grants are given yet.
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.