## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | January 2022 - December 2022
| Project Title: | AF-EU-UNDP Innovation Small Grant Aggregator Platform
| Project Summary: | The AF-EU-UNDP Innovation Small Grant Aggregator Platform (ISGAP) aims to support the development, diffusion and evidence building of innovative adaptation practices, tools, and technologies in developing countries. ISGAP is designed to meet this objective through an effective and efficient backbone management architecture and network of global best practitioners to (i) competitively source and screen innovative adaptation project ideas; (ii) grant funding and administering to bring selected project ideas to fruition; (iii) provision of customized technical and business development capacity building, incubation, and acceleration support; and (iv) knowledge management and sharing and result-based monitoring and evaluation. Leveraging this infrastructure, ISGAP aims to achieve the project objective through the following complementary outcomes: 1. Development of innovative adaptation practices, tools and technologies promoted and accelerated. Evidence of effective, efficient adaptation practices, products and technologies generated as a basis for implementing entities and other funds to enable scaling up. 2. Timely and efficient completion of business milestones demonstrated through additional investment and/or support capitalization for scaling 3. Lessons learned codified, documented, and disseminated leading to adoption or replication of project introduced innovations In parallel, AF is providing direct access to similar innovation small grants through National Implementing Entities (NIEs). Therefore, ISGAP’s knowledge management and information sharing design will include joint activities and participation from NIEs that have received the Innovation Small Grants so as to ensure a degree of consistency and parity between NIE and non-NIE recipients of the small grants.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | UNDP - PIMS 6266 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme (UNDP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Multi-country (Global) | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Global | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 11 October 2019 (Decision B.34/33)
IE-AFB Agreement Signature Date: |  | 2020-03-19 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2020-11-18 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2023-01-01
| Terminal Evaluation Date: | Est. Nov 2024
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
Links to access ISGAP Conferences, Events and Communications: 1. Gobeshona Conference- Locally Led Adaptation – Finance, Innovation and Scale: March 29th, 2022. (2 grantees showcased). 2. AFCIA/ISGAP presence at COP 27: short-recorded video showcasing 22 ISGAP grantees (LLA endorsers). 12th November 2022. https://youtu.be/tb9bthLNad8 3. COP 27 Side Event – Accelerating Climate Change Adaptation Action through Innovation: Jointly organized with the AF and UNEP/CTCN. (1 grantee showcased). 17th November 2022. Link: https://youtu.be/d_Dsb8fkN54; https://twitter.com/Srilata_Kammila/status/1592364634987982851 Link: https://www.adaptation-undp.org/cop27-side-event-accelerating-climate-change-adaptation-action-through-innovation ; https://youtu.be/d_Dsb8fkN54 4. Seed to Scale- Accelerating Innovation Enterprises, Resilience Hub, COP 27: lead by the Global Resilience Partnership. (1 grantee showcased). 12th November 2022 https://www.youtube.com/watch?v=5F6a4pbxil4 5. Nature For Life Hub: Video on locally-led action and innovation in agricultural value chains (2 grantees showcased). November 30th, 2022. https://www.youtube.com/watch?v=N7YtO3JZOf8&list=PL4yHLnNwn91NKH81h t82OIyzVydZ-OTjS
Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | https://www.adaptation-undp.org/smallgrantaggregator/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Monica Borrero, ISGAP Global Project Manager (UNDP) | Dominican Republic
| Email: | monica.borrero@undp.org | Ecuador
| Date: | 2023-01-13 | Egypt
| Government DA |  | El Salvador
| Name: |  | Equatoral Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Charles (Chongguang) Yu, Regional Technical Specialist (UNDP- Oversight) | Fiji
| Email: | chongguang.yu@undp.org | Finland
| Date: | 2023-01-13 | France
| Executing Agency |  | Gambia
| Name: |  | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
PPR 1 |  |  |  | PPR 2 |  |  |  | PPR 3 |  |  |  | PPR 4
Financial information: cumulative from project start to 31 October 2021 |  |  |  | Financial information: cumulative from project start to 31 December 2022 |  |  |  | Financial information: cumulative from project start to 31 December 2023 |  |  |  | Financial information: cumulative from project start to 31 December 2022
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31October 2021 (excluding IE fee which is being shown in a separate line below) | 1224 |  |  | Estimated cumulative total disbursement as of 31 December 2022 (excluding IE fee which is being shown in a separate line below) | 647014 |  |  | Estimated cumulative total disbursement as of XXXXX |  |  |  | Estimated cumulative total disbursement as of XXXXX
Add any comments on AF Grant Funds. (word limit=200) | The first disbursment was received in April 2020. The expenditures reported below are accumulative until 31 October 2021. Please note that the delivery rate is exceptionally low because of the delay in setting up and fully incporate changes in the goverance structure to also with the approval of additional EU funding into the project that was received at the end of December 2020. Despite the above, it is requested that the next disbursement be released upon the clearance of this PPR because the project plans to deliver around 22 grants in the approx. amount of $800,000 (first tranche of the grant funding to grantees; 40%AF funding, 60% EU funding) early 2022. Additional $1,500,000 will be disbursed by the middle of next year (40%AF funding, 60% EU funding. This includes the first tranche of second round funding and second tranche of first round funding; with additional two large procurement items expected for around $160,000 (one to engage a consortium of NGOs/CSOs for knowledge management $80,000 per year; one to procure a broker network to educate and engage with investors, corporate foundations and family investment offices (competitive bidding, budget around $80,000 one-off to test out one year, if the engagement is positive and well received by grantees, will become yearly). |  |  | Add any comments on AF Grant Funds. (word limit=200) | Total Expenditures (1 Nov 2021 - 31 Dec 2022): The first disbursment was received on 14th April 2022, and the second disbursement on the 23rd August 2022. The expenditures reported below are from 1 November 2021 - 31 December 2022 (excluding legal commitments). Estimated cumulative total disbursement as of 31 December 2022, as well as the expenditure data and planned expenditure includes UNDP´s agency fee as per Schedule 2 of the Legal Agreement. Planned Expenditures (2023): An total estimation of $1,687,000 will be disbursed during 2023. Most of it belongs to Component 1, as $1,300,000 will be disbursed trhough the ISGAP Low Value Grant Agreements (LVGAs) (corresponds to the first disbursement of the 2nd cohort grantees, and the third disbursement of the 1st cohort grantees). From the total cost of the LVGAs, 40% is charged to AF budget, and 60% to the EU budget. Component 2 ($66.000), corresponds to the ISGAP Finance & Investments Consultant and part of the salary of UNDP´s Regional Technical Specialist. Component 3 ($133.100) corresponds to the portion that will be charged to the AF, to carry our ISGAP workshops and to attend to key conferences and events, also to develop knowledge management products. Project Management Component ($187.900) corresponds to the portion that is charged to the AF, for the operation of ISGAP´s PMU. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | N/A |  |  | INVESTMENT INCOME | N/A |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period (1 Nov 2021 - 31 Dec 2022) | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Component 1: Provision of Innovation Small Grants | 0 |  |  | Component 1: Provision of Innovation Small Grants | 468610.1
| Component 2: Provision of Technical and Business Development Capacity Building, Incubation, and Acceleration Support | 64 |  |  | Component 2: Provision of Technical and Business Development Capacity Building, Incubation, and Acceleration Support | 673.64
| Component 3: Knowledge Management and sharing and Result-Based Monitoring and Evaluation | 1160 |  |  | Component 3: Knowledge Management and sharing and Result-Based Monitoring and Evaluation | 9339.9
| Project Management Costs | 0 |  |  | Project Management Costs | 167166.36
| Total | 1224 |  |  | Total | 645790
| Implementing Entity Fee per Legal Agreement | 201893 |  |  | Implementing Entity Fee per Legal Agreement | 86164
| Grand total | 203117 |  |  | Grand total | 731954
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Component 1: Provision of Innovation Small Grants | 1050000 | 2022-12-31 |  | Component 1: Provision of Innovation Small Grants | 1300000 | 2023-12-31
| Component 2: Provision of Technical and Business Development Capacity Building, Incubation, and Acceleration Support | 190333.3333 | 2022-12-31 |  | Component 2: Provision of Technical and Business Development Capacity Building, Incubation, and Acceleration Support | 66000 | 2023-12-31
| Component 3: Knowledge Management and sharing and Result-Based Monitoring and Evaluation | 110916.6667 | 2022-12-31 |  | Component 3: Knowledge Management and sharing and Result-Based Monitoring and Evaluation | 133100 | 2023-12-31
| Project Management Costs | 23333.3333 | 2022-12-31 |  | Project Management Costs | 187900 | 2023-12-31
| Total | 1374583.3333 |  |  | Total | 1687000
| Implementing Entity Fee per Legal Agreement | 86164 |  |  | Implementing Entity Fee per Legal Agreement | 55564
| Grand total | 1460747.3333 |  |  | Grand total | 1742564
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | N/A. |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? | N/A. MTR will be carried out during January-February 2023. |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Misappropriation of the grant funding | [Medium] The risk still remains valid. | Performance based disbursement is being used, where each grantee has to achieved minimum 70% of progress target indicators as per their LVGA. A dedicated resource (ISGAP Finance Analyst, ISGAP PMU) is also deployed to ensure financial transparency.
Lack of participation at the global call for proposals | The risk not valid anymore. | The risk is not valid anymore. The ISGAP Project has received more applications than expected, and the two call for proposals launched were successful. During the first call for proposals, 384 applications were received. During second call for proposal 462 applications were received.
Project implementation delay | [Medium] The risk still remains valid. | There’s a delay in the implementation, this is partly due to the new governance structure set up because of EU funding. With the additional donor, a new governance structure was set up which has caused some delays in the project implementation. This was mainly due to the policy constraint requiring the project board to approve the grant selection criteria and grant selection committee before the selection process could take place. COVID-19 also had a significant impact due to procurement hold-ups and delays in PMU recruitment. PMU took over a year to set up and start the implementation at a good pace. During 2022, the project team made significant efforts to catch up with project delivery. For 2023, the team has revised and updated the work plan, which was endorsed during the third Board Meeting (December 2022) and is expected to continue catching up with delivery. The Mid- term review will be carried out during the first quarter of 2023. Currently the TORs are being developed to recruit the consultant that will carry out this task. The objective of the MTR is to assess progress towards the achievement of the project objectives and outcomes as specified in the PRODOC. From the next reporting cycle project is planning to revise low-value grant agreement to capture more disaggregated data on beneficiaries as well on innovation practices. Similarly, an online(web-based) project Monitoring and Evaluation system will be developed to bring efficiency to data collection and reporting.
Success is overstated in the progress report while failure is understated or unreported | [Medium] The risk still remains valid. | It is crucial that both success and failure are documented and analysed by the grantees. It is a critical part of the knowledge sharing and lessons learned. In fact, one often learns from failure than success.This message is being communicated constantly on regular basis and also through capacity building and training. This risk is mitigated and monitored in two ways. The first reporting template has an exclusive section on challenges and lessons learned (it is mandatory for the grantees to report their successes and failures). Secondly, the program is also ensuring that every success story should be backed by solid evidence (in terms of its impact) from the grantees.
Grantees fail in securing scale up and replication support and funding from other sources after the completion of the project | [Medium] The risk still remains valid. | It is critical to note that the success rate of any start-up or innovation venture is quite low. With all the support provided by ISGAP and its partners, it is anticipated that the success would be within the range of 20%-30%. The project is supporting grantees through various channels to scale up and replicate high-impact-driven ideas (e.g. capacity building, networking and advocacy and specialized technical assistance). For details please refer to the project indicator sheet.
Environmental, social and governance risk not managed, triggering risk events | [Low] The risk still remains valid. | Environmental, social and governance criteria are established in every step of the ISGAP programme. UNDP Social and Environmental Safeguards Procedures (SESP) are being used as a benchmark to ensure the controls for this risk are in place. Specific ISGAP Social and Environmental Safeguard (SES) guidelines are prepared and in final clearance process, to become the main reference in this matter for upcoming grantee cohorts. A grievance redress mechanism (GRM) has been developed for the project and introduced it to the grantees. The two call for proposals (1st and 2nd cohorts) contained ESG risk identification questions to highlight potential ESG risks and how to manage them. The ISGAP Safeguard Consultant developed a simplified SES template for each selected grantee (1st cohort) to evaluate various social and environmental risks, and grantees are being asked to report against this template quarterly. Each grantee is also being supported with quality assurance and technical guidance in safeguards. During the first quarter of 2023, specific training on safeguards will be carried out. This approach will be replicated with the 2nd cohort of grantees during 2023.
ISGAP does not attract sufficient support from private sector | [Medium] The risk still remains valid. | To manage this risk, three main actions have been implemented during 2022: 1. Despite the early stage of the program, five projects that exhibited strong scaling potential, as well as the inherent expertise capable of accessing professional guidance, were offered the opportunity to join a 6-month mentorship programme offered by the Anderson School of Business, based at UCLA, for skills transfer and exchange. ISGAP´s approach recognized that several of the grantees will soon be able to scale, and that this scaling will be more likely to occur with a professional framing around impact, fundraising and sustainable growth. 2. Two thought-leadership roundtables have been held at Yale University in the past 6 months, to showcase ISGAP, several of the ISGAPgrantees, and evidence of needed and innovative forms of funding. Both events were attended by crucial funding- and intermediary-actors including SIDA, FCDO, BlackRock, Social Finance and MCE Social Capital. 3. Engagements with AVPN were conducted to carry out a series of round tables with private sector stakeholders. The first one with the Asia and the Pacific grantees took place in December 2022; the LAC and Africa roundtables will follow in the first quarter of 2023. This is tailored to expose the grantees to potential investors and relevant private sector stakeholders (funders), to better prepare them for future investor or matchmaking events.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
COVID-19 impact on project implementation | [Highly] - risk still valid | From the project implementation perspective, the project closely worked with the 1st cohort grantees to design COVID-19 mitigation strategies under each grantee’s work plan (LVGA). Necessary procurement of personal protective equipment for project implementation, if required by the grantee, were considered under their grant budget. Internally, Covid-19 has significant impacted on UNDP's procurement and recuitment processes (causing overall project implementation delay during 2020 and 2021), however this situation has improved during 2022 and system/processes are almost returned to normal. From the project management perspective, digital engagement is conducted throughout many project activities instead of in-person engagement, due to the global nature of the project. During 2023 and provided that the COVID-19 global situation remains stable, in-person meetings and workshops will be normally held.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
With few grantees, there has been a lack of engagement and low reporting capacity. But alternative ways are being sought to work with them through UNDP country offices, local partner organizations, close follow-up, doing training refreshers, and strengthening ISGAP´s PMU (complete the team). For the low-performing grantees, the follow-up process needs to be well documented to back up whichever course of action is taken. As a mitigation measure, it is key to flag them formally as low-performing grantees and communicate that clearly to them. They will be asked to fill out a template explaining the various reasons why they are in that situation, ask them to propose a catch-up plan (e.g. 3 months), and evaluate performance again to take a final decision with regards to their LVGAs. Another meeting will be planned with the Project Board to present additional information about the 3 low performing grantees which will help facilitate the decision-making processes.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1] | N/A
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law
2 - Access and equity |  |  | Communities in the project area (including ethnic minorities) could face economic displacement, changes to land rights and/or restricted access to resources because of the grant recipient businesses and social enterprises expansion. | For this and all other SES-related risks, the Project Board has established screening criteria requiring 1st cohort grantees to incorporate social and environmental risk asessment and management measurements. During the selection process and M&E process, a Safeguard Expert was hired to review the 1st cohort applicants and ensure that appropriate management measures are in place. Specific guidance to these grantees on these matters has been provided. Specific SES Guidelines have been developed by the Safeguards Expert, following UNDP´s most recent standards to serve as a reference for the project in terms of safeguard and risk management (still under internal clearance process). A Grievance Redress Mechanism has been developed and put into place. Trainings on risk management/safeguards will be delivered during the 1st quarter of 2023. | Operational and safeguard risks have been identified in a table, evaluated (Low, Medium, High levels) and included in each LVGA from the 1st cohort of grantees. | Baseline conditions for each 1st cohort grantee´s project has been included in the "background context" of each LVGA. | Measures to manage operational and safeguard risks have been included in each LVGA from the 1st cohort of grantees. Grantees need to quarterly report against these risk matrixes to UNDP. ISGAP Safeguard expert provides training and guidance to grantees on risk and safeguard management, specially to those that have "medium level" identified risks. Given the fact that the overall risk assessment of the project was "medium level", no "high risk" grantees are being funded trhough ISGAP because that would trigger different procedures not foreseen in the current ISGAP SES guidelines. See section 12 "List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible" of this PPR report for additional information. | N/A | N/A
3 – Marginalized and vulnerable Groups |  |  | There is a likelihood that the Project would exclude any potentially affected stakeholders, in particular marginalized groups, from fully participating in decisions that may affect them. NGOs/CSOs that received grant from UNDP also involve in adverse impact from employment. In addition, although the project aims to find climate change adaptation solutions that improve resilience, it is still likely that when handle incorrectly, the grant recipient businesses or social enterprises could exacerbate conflicts among and/or the risk of violence to project-affected communities and individuals by business expansion. | For this and all other SES-related risks, the Project Board has established screening criteria requiring 1st cohort grantees to incorporate social and environmental risk asessment and management measurements. During the selection process and M&E process, a Safeguard Expert was hired to review the 1st cohort applicants and ensure that appropriate management measures are in place. Specific guidance to these grantees on these matters has been provided. Specific SES Guidelines have been developed by the Safeguards Expert, following UNDP´s most recent standards to serve as a reference for the project in terms of safeguard and risk management (still under internal clearance process). A Grievance Redress Mechanism has been developed and put into place. Trainings on risk management/safeguards will be delivered during the 1st quarter of 2023. | Operational and safeguard risks have been identified in a table, evaluated (Low, Medium, High levels) and included in each LVGA from the 1st cohort of grantees. | Baseline conditions for each 1st cohort grantee´s project has been included in the "background context" of each LVGA. | Measures to manage operational and safeguard risks have been included in each LVGA from the 1st cohort of grantees. Grantees need to quarterly report against these risk matrixes to UNDP. ISGAP Safeguard expert provides training and guidance to grantees on risk and safeguard management, specially to those that have "medium level" identified risks. Given the fact that the overall risk assessment of the project was "medium level", no "high risk" grantees are being funded trhough ISGAP because that would trigger different procedures not foreseen in the current ISGAP SES guidelines. See section 12 "List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible" of this PPR report for additional information. | N/A | N/A
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | The grant recipient NGOs/CSOs could limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions given the employment choice and local culture. Project potentially reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits through grant selection. | For this and all other SES-related risks, the Project Board has established screening criteria requiring 1st cohort grantees to incorporate social and environmental risk asessment and management measurements. During the selection process and M&E process, a Safeguard Expert was hired to review the 1st cohort applicants and ensure that appropriate management measures are in place. Specific guidance to these grantees on these matters has been provided. Specific SES Guidelines have been developed by the Safeguards Expert, following UNDP´s most recent standards to serve as a reference for the project in terms of safeguard and risk management (still under internal clearance process). A Grievance Redress Mechanism has been developed and put into place. Trainings on risk management/safeguards will be delivered during the 1st quarter of 2023. | Operational and safeguard risks have been identified in a table, evaluated (Low, Medium, High levels) and included in each LVGA from the 1st cohort of grantees. | Baseline conditions for each 1st cohort grantee´s project has been included in the "background context" of each LVGA. | Measures to manage operational and safeguard risks have been included in each LVGA from the 1st cohort of grantees. Grantees need to quarterly report against these risk matrixes to UNDP. ISGAP Safeguard expert provides training and guidance to grantees on risk and safeguard management, specially to those that have "medium level" identified risks. Given the fact that the overall risk assessment of the project was "medium level", no "high risk" grantees are being funded trhough ISGAP because that would trigger different procedures not foreseen in the current ISGAP SES guidelines. See section 12 "List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible" of this PPR report for additional information. | N/A | N/A
6 – Core labour rights |  |  | The grant recipient NGOs/CSOs might fail to comply with national and international labor standards. | For this and all other SES-related risks, the Project Board has established screening criteria requiring 1st cohort grantees to incorporate social and environmental risk asessment and management measurements. During the selection process and M&E process, a Safeguard Expert was hired to review the 1st cohort applicants and ensure that appropriate management measures are in place. Specific guidance to these grantees on these matters has been provided. Specific SES Guidelines have been developed by the Safeguards Expert, following UNDP´s most recent standards to serve as a reference for the project in terms of safeguard and risk management (still under internal clearance process). A Grievance Redress Mechanism has been developed and put into place. Trainings on risk management/safeguards will be delivered during the 1st quarter of 2023. | Operational and safeguard risks have been identified in a table, evaluated (Low, Medium, High levels) and included in each LVGA from the 1st cohort of grantees. | Baseline conditions for each 1st cohort grantee´s project has been included in the "background context" of each LVGA. | Measures to manage operational and safeguard risks have been included in each LVGA from the 1st cohort of grantees. Grantees need to quarterly report against these risk matrixes to UNDP. ISGAP Safeguard expert provides training and guidance to grantees on risk and safeguard management, specially to those that have "medium level" identified risks. Given the fact that the overall risk assessment of the project was "medium level", no "high risk" grantees are being funded trhough ISGAP because that would trigger different procedures not foreseen in the current ISGAP SES guidelines. See section 12 "List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible" of this PPR report for additional information. | N/A | N/A
7 – Indigenous peoples |  |  | The project aims to provide grants to local NGOs/CSOs in developing countries. The project will be working with indigenous peoples, either as grantees, customers of grantees or suppliers of grantees. | For this and all other SES-related risks, the Project Board has established screening criteria requiring 1st cohort grantees to incorporate social and environmental risk asessment and management measurements. During the selection process and M&E process, a Safeguard Expert was hired to review the 1st cohort applicants and ensure that appropriate management measures are in place. Specific guidance to these grantees on these matters has been provided. Specific SES Guidelines have been developed by the Safeguards Expert, following UNDP´s most recent standards to serve as a reference for the project in terms of safeguard and risk management (still under internal clearance process). A Grievance Redress Mechanism has been developed and put into place. Trainings on risk management/safeguards will be delivered during the 1st quarter of 2023. | Operational and safeguard risks have been identified in a table, evaluated (Low, Medium, High levels) and included in each LVGA from the 1st cohort of grantees. | Baseline conditions for each 1st cohort grantee´s project has been included in the "background context" of each LVGA. | Measures to manage operational and safeguard risks have been included in each LVGA from the 1st cohort of grantees. Grantees need to quarterly report against these risk matrixes to UNDP. ISGAP Safeguard expert provides training and guidance to grantees on risk and safeguard management, specially to those that have "medium level" identified risks. Given the fact that the overall risk assessment of the project was "medium level", no "high risk" grantees are being funded trhough ISGAP because that would trigger different procedures not foreseen in the current ISGAP SES guidelines. See section 12 "List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible" of this PPR report for additional information. | N/A | N/A
8 – Involuntary resettlement
9 – Protection of natural habitats |  |  | Grants to NGOs/CSOs that their business model could cause adverse impacts to habitats, e.g. associated with harvesting of natural forests or harvesting of fish populations or other aquatic species. | For this and all other SES-related risks, the Project Board has established screening criteria requiring 1st cohort grantees to incorporate social and environmental risk asessment and management measurements. During the selection process and M&E process, a Safeguard Expert was hired to review the 1st cohort applicants and ensure that appropriate management measures are in place. Specific guidance to these grantees on these matters has been provided. Specific SES Guidelines have been developed by the Safeguards Expert, following UNDP´s most recent standards to serve as a reference for the project in terms of safeguard and risk management (still under internal clearance process). A Grievance Redress Mechanism has been developed and put into place. Trainings on risk management/safeguards will be delivered during the 1st quarter of 2023. | Operational and safeguard risks have been identified in a table, evaluated (Low, Medium, High levels) and included in each LVGA from the 1st cohort of grantees. | Baseline conditions for each 1st cohort grantee´s project has been included in the "background context" of each LVGA. | Measures to manage operational and safeguard risks have been included in each LVGA from the 1st cohort of grantees. Grantees need to quarterly report against these risk matrixes to UNDP. ISGAP Safeguard expert provides training and guidance to grantees on risk and safeguard management, specially to those that have "medium level" identified risks. Given the fact that the overall risk assessment of the project was "medium level", no "high risk" grantees are being funded trhough ISGAP because that would trigger different procedures not foreseen in the current ISGAP SES guidelines. See section 12 "List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible" of this PPR report for additional information. | N/A | N/A
10 – Conservation of biological diversity |  |  | Grantee might have business activities within or adjacent to critical habitats and/or environmentally sensitive areas, including legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities. | For this and all other SES-related risks, the Project Board has established screening criteria requiring 1st cohort grantees to incorporate social and environmental risk asessment and management measurements. During the selection process and M&E process, a Safeguard Expert was hired to review the 1st cohort applicants and ensure that appropriate management measures are in place. Specific guidance to these grantees on these matters has been provided. Specific SES Guidelines have been developed by the Safeguards Expert, following UNDP´s most recent standards to serve as a reference for the project in terms of safeguard and risk management (still under internal clearance process). A Grievance Redress Mechanism has been developed and put into place. Trainings on risk management/safeguards will be delivered during the 1st quarter of 2023. | Operational and safeguard risks have been identified in a table, evaluated (Low, Medium, High levels) and included in each LVGA from the 1st cohort of grantees. | Baseline conditions for each 1st cohort grantee´s project has been included in the "background context" of each LVGA. | Measures to manage operational and safeguard risks have been included in each LVGA from the 1st cohort of grantees. Grantees need to quarterly report against these risk matrixes to UNDP. ISGAP Safeguard expert provides training and guidance to grantees on risk and safeguard management, specially to those that have "medium level" identified risks. Given the fact that the overall risk assessment of the project was "medium level", no "high risk" grantees are being funded trhough ISGAP because that would trigger different procedures not foreseen in the current ISGAP SES guidelines. See section 12 "List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible" of this PPR report for additional information. | N/A | N/A
11 – Climate change
12 – Pollution prevention and resource efficiency
13 – Public health |  |  | Employment with the NGOs/CSOs could pose a potential risk to health and safety of individuals depends on the business activities (eg. Use of new pesticide, or new fertilizer, using of unfamiliar equipment). | For this and all other SES-related risks, the Project Board has established screening criteria requiring 1st cohort grantees to incorporate social and environmental risk asessment and management measurements. During the selection process and M&E process, a Safeguard Expert was hired to review the 1st cohort applicants and ensure that appropriate management measures are in place. Specific guidance to these grantees on these matters has been provided. Specific SES Guidelines have been developed by the Safeguards Expert, following UNDP´s most recent standards to serve as a reference for the project in terms of safeguard and risk management (still under internal clearance process). A Grievance Redress Mechanism has been developed and put into place. Trainings on risk management/safeguards will be delivered during the 1st quarter of 2023. | Operational and safeguard risks have been identified in a table, evaluated (Low, Medium, High levels) and included in each LVGA from the 1st cohort of grantees. | Baseline conditions for each 1st cohort grantee´s project has been included in the "background context" of each LVGA. | Measures to manage operational and safeguard risks have been included in each LVGA from the 1st cohort of grantees. Grantees need to quarterly report against these risk matrixes to UNDP. ISGAP Safeguard expert provides training and guidance to grantees on risk and safeguard management, specially to those that have "medium level" identified risks. Given the fact that the overall risk assessment of the project was "medium level", no "high risk" grantees are being funded trhough ISGAP because that would trigger different procedures not foreseen in the current ISGAP SES guidelines. See section 12 "List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible" of this PPR report for additional information. | N/A | N/A
14 – Physical and cultural heritage |  |  | The grant recipient NGOs/CSOs or UNDP could lead to commercialize traditional knowledge. As NGOs/CSOs grantees will share their lessons learnt in their innovative approach to climate change adaptation, other actors could use the knowledge product of UNDP to commercialize these traditional knowledge. As part of the project, UNDP is expected to act as an investment broker to find commercial investors to invest commercially in scalable grantees. | For this and all other SES-related risks, the Project Board has established screening criteria requiring 1st cohort grantees to incorporate social and environmental risk asessment and management measurements. During the selection process and M&E process, a Safeguard Expert was hired to review the 1st cohort applicants and ensure that appropriate management measures are in place. Specific guidance to these grantees on these matters has been provided. Specific SES Guidelines have been developed by the Safeguards Expert, following UNDP´s most recent standards to serve as a reference for the project in terms of safeguard and risk management (still under internal clearance process). A Grievance Redress Mechanism has been developed and put into place. Trainings on risk management/safeguards will be delivered during the 1st quarter of 2023. | Operational and safeguard risks have been identified in a table, evaluated (Low, Medium, High levels) and included in each LVGA from the 1st cohort of grantees. | Baseline conditions for each 1st cohort grantee´s project has been included in the "background context" of each LVGA. | Measures to manage operational and safeguard risks have been included in each LVGA from the 1st cohort of grantees. Grantees need to quarterly report against these risk matrixes to UNDP. ISGAP Safeguard expert provides training and guidance to grantees on risk and safeguard management, specially to those that have "medium level" identified risks. Given the fact that the overall risk assessment of the project was "medium level", no "high risk" grantees are being funded trhough ISGAP because that would trigger different procedures not foreseen in the current ISGAP SES guidelines. See section 12 "List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible" of this PPR report for additional information. | N/A | N/A
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | The safeguard consultant is currently working with the project team to design M&E for unanticipated ESP risks. This is being inclided in the SES Guidelines for the ISGAP project (currently under internal clearances process).
Have unanticipated ESP risks been identified during the reporting period? |  | No unanticipated ESP risks have been identified for this reporting period.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Project Bobard has established screening criteria, requiring grantees to incorporate social and environmental risks measurement. During the selection process and M&E process, a Safeguards expert is hired to review the grant applicants and ensure that appropriate management measures are in place. Grantees are asked to submit quarterly update on their risk management plan. Safeguard & gender training is planned for the first quarter of 2023. Similar approach will be implemented with 2nd cohort of ISGAP grantees.
Have the implementation arrangements been effective during the reporting period? |  | Yes, from understanding the risks perspective; the project has successfully identifying possible risks with the grantees through screening process, proposal submission process and follow up with grantees on safeguard matters.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | IP is the EE in this case
Have the implementation arrangements at the EEs been effective during the reporting period? |  | IP is the EE in this case
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | A safeguard consultant was enaged to work with the project grantees on their workplan to design plans and controls for safeguard risks.For 22 grantees from the first cohort, SES Guidelines have been developed containing the procedures and specific guidance to mitigate risks identified by each grantees in individual proposals. For the grant selection process, a screening process has been performed for each grantee based on self reporting and safeguard expert review. For each quarterlyreporting, grantees are required to report Environmental and Social risks (both identified during the project proposal stage and new risks that occurred during the reporting period, in alignment with UNDP SES and cross-checked with AF safeguard principles). All reports were reviewed by a safeguard, M&E consultants and PMU for each reporting period.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11] |  | Yes, SES Guidelines along with safeguards risk mitigation plan have been developed with the input and consultation of 1st cohort grantees. Each grantees activities performance risk events are categorized into four risk level (low, moderate, significant, high). Potential Social and Environmental Risks checklist based on the following principles were used to understand and assess grantees current and potential risks. Overarching Principle 1: Leave No One Behind Overarching Principle 2: Human Rights Overarching Principle 3: Gender Equality and Women’s Empowerment Overarching Principle 4: Sustainability and Resilience Overarching Principle 5: Accountability Project-Level Standards Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management Standard 2: Climate Change and Disaster Risks
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
Project 54_LIVESTOCK DEVELOPMENT FOR COMMUNITY | Yes | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, we will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may involve plantation development. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that plantations will be developed but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity outputs and outcomes may be sensitive or vulnerable to potential impacts of climate change or disasters. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that there are potential risks of damaged products by extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where indigenous peoples are present (including activities area of influence). (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "There may be release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts. (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may release pollutants to the environment but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "There may be generation of waste (both hazardous and non-hazardous). (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may involve/lead to waste generation but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
Project 56_BUKIDNON UMAYAMNON TRIBE KAPU-UNAN | Yes | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity outputs and outcomes may be sensitive or vulnerable to potential impacts of climate change or disasters. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that there are potential risks of damaged products by extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where indigenous peoples are present (including activities area of influence). (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "There may be generation of waste (both hazardous and non-hazardous). (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may involve/lead to waste generation and potential use of chemicals and/or hazardous materials but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
Project 59_SANTO SUNSET ENVIRONMENT NETWORK | Yes | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity within the Santo Mountain Chain Biodiversity Hotspot, which currently houses 4 officially recognized Conservation Areas, which are sensitive habitat areas. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may harvest natural forests, involve plantation development, or reforestation. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that the activities may involve natural forest harvest, plantation development or reforestation but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may involve animal husbandry or harvesting of fish populations or other aquatic species. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that the activities may involve animal husbandry or harvesting of fish or other aquatic species but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity will deal with local genetic varieties of local crops like yam, taro, banana and vegetables. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that the activities may genetic species but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity is located in Western Santo Area, this entire location is subject to multiple hazards. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change)" |  |  |  | "A preliminary analysis indicates that the activities may be placed at locations that suffer extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity outputs and outcomes may be sensitive or vulnerable to potential impacts of climate change or disasters. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that there are potential risks of damaged products by extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes like the traditional agriculture practices. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be located on lands and territories claimed by indigenous peoples as the entire initiative is desigend by and for the agricultural adaptation of indiogenous people of the Jarai Alo Kolo tribes. (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "There may be release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts. (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may invovle the release pollutants to the environment but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "There may be generation of waste (both hazardous and non-hazardous). (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may invovle waste generation but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may involve the manufacture, trade, release, and/or use of hazardous materials and/or chemicals. (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may invovle manufacture, trade, release andor use of hazardous materials and chemicals but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may involve the use of chemicals or materials subject to international bans or phase-outs. (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency) For example, DDT, PCBs and other chemicals listed in international conventions such as the Montreal Protocol, Minamata Convention, Basel Convention, Rotterdam Convention, Stockholm Convention." |  |  |  | "A preliminary analysis indicates that the activities may invovle chemicals or materials subject to international bans but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may involve the application of pesticides that may have a negative effect on the environment or human health. (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may invovle the application of pesticides but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may involve significant consumption of raw materials, energy, and/or water. (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may involve significant consumption of raw materials, energy and or water but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
Project 66_CENTRO ECOLOGICO | Yes | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities because the whole region where activities will be developed is surrounded by different categories of protected areas. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may harvest natural forests, involve plantation development, or reforestation because they are oriented to stimulate farmers to recover the original vegetation using native species under agroforestry systems. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that activities may involve harvest of natural forests, plantation development or reforestation but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity outputs and outcomes may be sensitive or vulnerable to potential impacts of climate change or disasters. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that there are potential risks of damaged products by extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where indigenous peoples are present or in land they claim or impact in their resouces (including activities area of influence) as some will be developed where the Mbya Guarani people are. (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "There may be generation of waste (both hazardous and non-hazardous). (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may involve/lead to waste generation but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
Project 71_SUSTAINABLE ENVIRONMENT AND FISHERIES | Yes | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may involve plantation development. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that the activities will involve plantation development but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity outputs and outcomes may be sensitive or vulnerable to potential impacts of climate change or disasters. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that there are potential risks of damaged products by extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may involve construction and/or infrastructure development (e.g. roads, buildings, dams). (Social and Environmentral Risk, SES Activity-level Standard 3: Community H&S)" |  |  |  | "A preliminary analysis indicates that there are activities reltaed to construction. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where Berom indigenous peoples are present (including activities area of influence). They own their land and will eventually co-own the project. (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "There may be generation of waste (both hazardous and non-hazardous). (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may involve/lead to waste generation and potential use of chemicals and/or hazardous materials but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may involve the manufacture, trade, release, and/or use of hazardous materials and/or chemicals. (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may involve/lead hazardous chemicals and/or hazardous materials or chemicals but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
Project 74_YAYSAN BESI PAE | Yes | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may involve reforestation. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that activities will involve reforestation but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity outputs and outcomes may be sensitive or vulnerable to potential impacts of climate change or disasters. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that there are potential risks of damaged products by extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where Adat indigenous peoples are present (including activities area of influence) as it will be located in their village/land. (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may bring occupational health and safety risks due to chemical products that will be used for the agricultural purposes. (Social and Environmentral Risk, SES Activity-level Standard 7: Labour)" |  |  |  | "A preliminary analysis indicates that chemicals will be used but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "There may be release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts. (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may involve/lead to waste generation and potential use of chemicals and/or hazardous materials but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may involve the application of pesticides that may have a negative effect on the environment or human health. (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may involve the use of pesticides but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
Project 82_SOKEHS MENIN KETENGESED | Yes | The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 1. (Social and Environmentral Risk, SES Principle 2: Human Rights) | Yes | Yes | Yes | The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities.
|  | The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them and in consequence the activities will bring grievances or objections because the seaweed will be harvested from areas within the Pohnpei Lagoon, where some communities might feel ownership despite it is a public area. (Social and Environmentral Risk, SES Principle 5: Accountability) |  |  |  | To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities.
|  | The activity may bring adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services within Pohnpei because some of these activities could happen next to Marine Protected Areas. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity) For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes. |  |  |  | A preliminary analysis indicates that the activities may bring adverse impacts to habitats but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk.
|  | The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities of the Pohnpei because some of these activities could happen next to Marine Protected Areas. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity) |  |  |  | A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk.
|  | The activity may bring risks to endangered species as there are populations of turtles that are considered endangered that could be affected by this seaweed harvesting. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity) |  |  |  | A preliminary analysis indicates that the activities may bring risks to endangered species but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk.
|  | The activity will involve seaweed harvesting. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity) |  |  |  | A preliminary analysis indicates that the activities may involve harvesting of fish populations or other aquatic species but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk.
|  | The activity will be subject to working in the lagoon, so bad weather can be an issue. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) |  |  |  | A preliminary analysis indicates that the activities will be placed at locations that may suffer from extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk.
|  | The activity outputs and outcomes may be sensitive or vulnerable to potential changes or disasters like changes in temperature or salinity caused by climate change. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes. |  |  |  | A preliminary analysis indicates that there are potential risks of damaged products by extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk.
|  | The activity may harm or losses due to failure of structural elements of the activities (e.g. collapse of buildings or infrastructure) because the work will be done at a processing center, so this is a risk that we need to address. (Social and Environmentral Risk, SES Activity-level Standard 3: Community H&S) |  |  |  | A preliminary analysis indicates that there are potential risks of failure of structural elements. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk.
|  | The activity may bring adverse impacts on ecosystems and ecosystem services relevant to communities’ health (e.g. food, surface water purification, natural buffers from flooding) in the marine environment where communities fish and collect marine resources for their food. (Social and Environmentral Risk, SES Activity-level Standard 3: Community H&S) |  |  |  | A preliminary analysis indicates that the activities may bring adverse impacts on ecosystems and their services. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk.
|  | The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage) |  |  |  | A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk.
|  | The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement) |  |  |  | The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk.
|  | The activity may be in areas where Pohnpei indigenous peoples are present (including activities area of influence). (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples) |  |  |  | A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk.
|  | The activity may be located on lands and territories claimed by Pohnpei indigenous peoples. (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples) |  |  |  | A preliminary analysis indicates that the activities may be located on lands claimed by indigenous peoples but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk.
|  | The activity may bring occupational health and safety risks due to associated dangers of working in the marine environment. (Social and Environmentral Risk, SES Activity-level Standard 7: Labour) |  |  |  | A preliminary analysis indicates that the activities may bring occupational health and safety risks but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk.
|  | There may be generation of waste (non-hazardous) from packaging and labelling seaweed products. (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency) |  |  |  | A preliminary analysis indicates that the activities may lead to waste generation but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk.
Project 85_FONDO ACCION | Yes | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where indigenous peoples are present (including activities area of influence). (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
Project 86_SPARC- SOCIETY FOR THE PROMOTION OF AREA | Yes | "Duty-bearers (local government) may not have the capacity to meet their obligations in the activities because at this stage we cannot assure a financial commitment from them towards such nature-based homegrown projects. (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "To manage this risk, we will: 1) Secure the government support prior to moving forward with the implementation activities. The Grantee will inform to the UNDP PMU when this is achieved. 2) If such support is not achieved the plan will need to be reviewed and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" |  |  |  | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may change to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods because the local plan may include certain set of rules that may restrict the community to washing their clothes on the edges of the water body. Hence it may impact livlihoods of households that are dependant on these activities for their income. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that the activities may change the use of land but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity outputs and outcomes may be sensitive or vulnerable to potential impacts of climate change or disasters. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that there are potential risks of damaged products by extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may change to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods because the local plan may include certain set of rules that may restrict the community to washing their clothes on the edges of the water body. Hence it may impact livlihoods of households that are dependant on these activities for their income. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that the activities may change the use of land but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity outputs and outcomes may be sensitive or vulnerable to potential impacts of climate change or disasters. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that there are potential risks of damaged products by extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may involve construction and/or infrastructure development (e.g. roads, buildings, dams). (Social and Environmentral Risk, SES Activity-level Standard 3: Community H&S)" |  |  |  | "A preliminary analysis indicates that there are activities related to cosntruction. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may bring risks of water-borne or other vector-borne diseases (e.g. temporary breeding habitats). (Social and Environmentral Risk, SES Activity-level Standard 3: Community H&S)" |  |  |  | "A preliminary analysis indicates that the activity may be dealing with wastewater . Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where indigenous peoples are present (including activities area of influence). (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may be located on lands and territories claimed by indigenous peoples. (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that activities may be located on lands claimed by indigenous peoples but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "There may be release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts. (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may release pollutants to the environment but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "There may be generation of waste (both hazardous and non-hazardous). (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may involve/lead to waste generation any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
Project 112_ASSOCIATION LA VOUTE NUBIENNE | Yes | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur adjacent to a national park in the Attacora Department, in North Benin, along the Pendjari National Park. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity outputs and outcomes may be sensitive or vulnerable to potential impacts of climate change or disasters. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that there are potential risks of damaged products by extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may involve construction and/or infrastructure development of Nubian vaults. (Social and Environmentral Risk, SES Activity-level Standard 3: Community H&S)" |  |  |  | "A preliminary analysis indicates that there are activities related to construction. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may harm or losses due to failure of structural elements of the Nubian vaults on the construction site. (Social and Environmentral Risk, SES Activity-level Standard 3: Community H&S)" |  |  |  | "A preliminary analysis indicates that some activities may structurally fail. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where indigenous peoples are present (including activities area of influence). (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "There may be generation of waste non-hazardous). (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may involve/lead to waste generation but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
Project 113_SOUTH ASIAN FORUM FOR ENVIRONMENT | Yes | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity will occur in the forest fringe villages of Sundarban Biosphere Reserve which is a world heritage site. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity will involve plantation development focused on augmenting the primary productivity. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that the activities may involve plantation development but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity will involve harvesting of native fish species and local sea weeds in inundated coastal areas. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that the activities may involve animal husbandry or harvesting of fish or other aquatic species but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity will be subject to hazards such as coastal flooding and cyclones. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change)" |  |  |  | "A preliminary analysis indicates that there are potential extreme weather events in the activity area. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity outputs and outcomes may be sensitive or vulnerable to extreme weather. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that there are potential risks of damaged products by extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where indigenous peoples are present (including activities area of influence). (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "There may be generation of waste (both hazardous and non-hazardous). (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may involve/lead to waste generation and potential use of chemicals and/or hazardous materials but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
Project 116_MOYO DISTRICT FARMERS ASSOCIATION | Yes | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may involve plantation development or reforestation. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that plantation development may be involved but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity outputs and outcomes may be sensitive or vulnerable to potential impacts of climate change or disasters. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that there are potential risks of damaged products by extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where indigenous peoples are present (including activities area of influence). (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "There may be generation of waste (both hazardous and non-hazardous). (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may involve/lead to waste generation and potential use of chemicals and/or hazardous materials but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
Project 121_OPEN GHANA | Yes | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may involve plantation development. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that plantation development may be involved but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity outputs and outcomes may be sensitive or vulnerable to potential impacts of climate change or disasters. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that there are potential risks of damaged products by extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where indigenous peoples are present (including activities area of influence). (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "There may be generation of waste (both hazardous and non-hazardous). (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may involve/lead to waste generation and potential use of chemicals and/or hazardous materials but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
Project 122_ESPACIO DE ENCUENTRO DE LAS CULTURAS | Yes | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits because the men may be annoyed by the fact that the project prioritises women. (Social and Environmentral Risk, SES Principle 3: Gender)" |  |  |  | "To manage this risk, we will: 1) Secure the support of men prior to moving forward with the implementation activities. The Grantee will inform to the UNDP PMU when this is achieved. 2) If such support is not achieved the plan will need to be reviewed and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services because the men may not agree to allocate a space for the demonstration project for women only. (Social and Environmentral Risk, SES Principle 3: Gender) For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being." |  |  |  | "To manage this risk, we will: 1) Secure the support of men prior to moving forward with the implementation activities. The Grantee will inform to the UNDP PMU when this is achieved. 2) If such support is not achieved the plan will need to be reviewed and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exacerbate risks of gender-based violence due to insecurity for women when they go alone to check and look after their crops. (Social and Environmentral Risk, SES Principle 3: Gender) " |  |  |  | "To manage this risk, we will: 1) Secure the support of men prior to moving forward with the implementation activities. The Grantee will inform to the UNDP PMU when this is achieved. 2) If such support is not achieved the plan will need to be reviewed and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may provide the conditions for the development of plantations or for reforestation due to the new microclimates that the water chanels will create. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that plantation developmetn or reforestation may occur but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may be in areas subject to hazards such as earthquakes, droughts and frosts. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change)" |  |  |  | "A preliminary analysis indicates that the activities will be exposed to extreme weather but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity outputs and outcomes may sufer damage due to extreme climate change related events. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that the activities suffer damage when exposed to extreme weather but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where indigenous peoples are present (including activities area of influence). (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "There may be generation of waste (both hazardous and non-hazardous). (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may involve/lead to waste generation and potential use of chemicals and/or hazardous materials but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
Project 130_CENTRE FOR COMMUNITY INITIATIVES | Yes | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where indigenous peoples are present (including activities area of influence). (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
Project 143_ISLAND FOOD COMMUNITY OF POHNPEI | Yes | "Duty-bearers (e.g. government agencies) may not have the capacity to meet their obligations in the activities due to the recent passing of CWC President. (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "To manage this risk, we will: 1) Secure the government support prior to moving forward with the implementation activities. The Grantee will inform to the UNDP PMU when this is achieved. 2) If such support is not achieved the plan will need to be reviewed and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" |  |  |  | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "Women’s groups/leaders may raise gender equality concerns regarding the activities, (e.g. during the stakeholder engagement process, grievance processes, public statements). (Social and Environmentral Risk, SES Principle 3: Gender)" |  |  |  | "To manage this risk, we will: 1) Secure the concerns are resolved prior to moving forward with the implementation activities. The Grantee will inform to the UNDP PMU when this is achieved. 2) If such concerns are not resovled the plan will need to be reviewed and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may involve plantation development. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that plantation development will be involved but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity outputs and outcomes may be sensitive or vulnerable to potential impacts of climate change or disasters. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that there are potential risks of damaged products by extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may involve the engagement of security personnel to protect facilities and property or to support activities activities should the need rise by hiring security to maintaine or safeguard project equipments, etc. (Social and Environmentral Risk, SES Activity-level Standard 3: Community H&S)" |  |  |  | "A preliminary analysis indicates that there will be security personnel involved in the activities. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where indigenous peoples are present (including activities area of influence). (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
Project 157-SAMPLE UGANDA AQUACULTURE ASSOCIATION | Yes | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may bring adverse impacts on gender equality and/or the situation of women and girls. (Social and Environmentral Risk, SES Principle 3: Gender)" |  |  |  | "To manage this risk, we will: 1) Secure the support of men prior to moving forward with the implementation activities. The Grantee will inform to the UNDP PMU when this is achieved. 2) If such support is not achieved the plan will need to be reviewed and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits. (Social and Environmentral Risk, SES Principle 3: Gender)" |  |  |  | "To manage this risk, we will: 1) Secure the support of men prior to moving forward with the implementation activities. The Grantee will inform to the UNDP PMU when this is achieved. 2) If such support is not achieved the plan will need to be reviewed and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services. (Social and Environmentral Risk, SES Principle 3: Gender) For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being." |  |  |  | "To manage this risk, we will: 1) Secure the support of men prior to moving forward with the implementation activities. The Grantee will inform to the UNDP PMU when this is achieved. 2) If such support is not achieved the plan will need to be reviewed and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals including the elderly, youth and women who are likely to miss out of the project activities and accessing benefits due to dominance by men and other well positioned decision makers who may take up all the available project opportunities. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may involve harvesting of fish populations. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that harvesting of fish or other aquatic species will be involved but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity outputs and outcomes may be sensitive or vulnerable to potential impacts of climate change or disasters. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that there are potential risks of damaged products by extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where indigenous peoples are present (including activities area of influence). (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "There may be release of pollutants to the environment due to water contamination in the crop grow- beds or fish water tanks and over use or un regulated water maintenance . (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that pollutants may be released to the environment but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "There may be generation of waste (non-hazardous) due to the significant agricultural horticulture production that may lead to over-production resulting on huge post-harvest waste because of the lack of readily available markets. (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that waste may be generated to the environment but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
PROJECT 251_PILIER AUX FEMMES VULNERABLES ACTIVES | Yes | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may involve plantation development. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that plantation development will be involved but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity outputs and outcomes may be sensitive or vulnerable to potential impacts of climate change or disasters. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that there are potential risks of damaged products by extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where indigenous peoples are present (including activities area of influence). (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
PROJECT 260-WORL NEIGHBORS | Yes | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may harvest natural forests. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that natural forest harvesting wil be involved but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where indigenous peoples are present (including activities area of influence). (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
PROJECT 273_SMART FARMS FIJI FOUNDATION | Yes | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities and jealousy from people in the community that are not selected to participate. (Social and Environmentral Risk, SES Principle 2: Human Rights)" | yes | yes | Yes | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity outputs and outcomes may be sensitive or vulnerable to potential impacts of climate change or disasters. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that there are potential risks of damaged crops or hydroponic kits by extreme weather events. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is minimized to the extent possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. 3) Ensure the plants and equipment are designed and protected to the extent possible to minimize potential impacts during extreme weather events. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where indigenous peoples are present (including activities area of influence). (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "There may be generation of waste (both hazardous and non-hazardous). (Social and Environmentral Risk, SES Activity-level Standard 8: Pollution and Resource Efficiency)" |  |  |  | "A preliminary analysis indicates that the activities may involve/lead to waste generation and potential use of chemicals and/or hazardous materials but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, these would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Ensure the activities supported by the grant do not involve the use of hazardous materials and/or chemicals subject to international bans or phase outs or the application of pesticides that may have a negative effect on the environment or human health. 2) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
PROJECT 278_RURAL DEVELOPMENT INITIATIVE | Yes | "Duty-bearers (local ward and municipality governments) may not have the capacity to meet their obligations in the activities. (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "To manage this risk, we will: 1) Secure the government support prior to moving forward with the implementation activities.The Grantee will share evidence with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "Rights-holders (Rangelands, where the project will take place, are held in collective ownership by the indigenous Gurung community) may not have the capacity to claim their rights. (Social and Environmentral Risk, SES Principle 2: Human Rights)" |  |  |  | "To manage this risk, we will: 1) Secure the right-holders capacity prior to moving forward with the implementation activities.The Grantee will share evidence with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" |  |  |  | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may bring exacerbation of conflicts among and/or the risk of violence to activities-affected communities and individuals of different caste. This is because higher caste indigenous villagers and lower caste migrant herders comprise the two primary groups of stakeholderds and co-design participants, existing distrust between these two groups that may be magnified by disagreements, perceptions of lack of inclusion, or other possible conflicts. (Social and Environmentral Risk, SES Principle 2: Human Rights)" |  |  |  | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them and may be objecting or retaliation will occur because the primary project stakeholders include indigenous livestock owning families and marginalized migrant herders. Possible grievances may be brought by both; indigenous peoples may object to the full participation of migrant herders in co-design processes, while migrant herders may articulate grievances if their participation is objected to or obfuscated by other parties. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas within the Annapurna Conservation Area Project (ACAP), a protected area defined by the Nepali federal government and National Trust for Nature Conservation (NTNC). . (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may involve animal husbandry. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that activities may involve animal husbandry or harvesting of fish populations or other aquatic species but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may be situated in the earthquake-prone high Himalayas. It is not subject to floods, tsunami, storm surges, or volcanic eruptions. Landslides are rare in this region, as are severe winds. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change)" |  |  |  | "A preliminary analysis indicates that activities may be placed in areas that may suffer from extreme weather but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity outputs and outcomes may be sensitive or vulnerable to potential impacts of climate change or disasters as they will be subjected primarily to possible increased or variable precipitation, drought, changes in temperature, and earthquakes. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change) For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes." |  |  |  | "A preliminary analysis indicates that activity outputs may be sensitive to the extreme weather situations but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may bring adverse impacts to intangible forms of culture as primarily indigenous and emerging forms of herding knowledge play a central role in this project. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that activities may bring adverse impacts to sites but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create alterations to landscapes and natural features with cultural significance. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that the activities may create alterations to landscape with cultural significance but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in rangelands collectively owned by several indigenous communities. (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
PROJECT 289_MESOAMERICAN REEF FUND INC | Yes | "Duty-bearers ( governmental agencies and local NGOs) may not have the capacity to meet their obligations in the activities. (Social and Environmentral Risk, SES Principle 2: Human Rights)" | Yes | Yes | Yes | "To manage this risk, we will: 1) Secure the government support prior to moving forward with the implementation activities.The Grantee will share evidence with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may bring inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities. 16 (Social and Environmentral Risk, SES Principle 2: Human Rights)" |  |  |  | "The selection of beneficiaries who will receive support through the grant will need to ensure an inclusive and transparent process. To manage this risk, the Grantee will: 1) Develop a simplified Stakeholder Engagement Plan to ensure an inclusive process and that affected people are meaningfully engaged in the process. This will include proposed selection criteria for the beneficiaries of the grant activities to ensure a transparent and inclusive process is applied. The Grantee will share the simplified Stakeholder Engagement Plan with the UNDP PMU prior to initiation of activities. 2) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified by the Grantee and the plan will need to be reviewed to ensure application of the relevant UNDP’s SES requirements and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may exclude any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them. (Social and Environmentral Risk, SES Principle 5: Accountability)" |  |  |  | "To manage this risk, we will: 1) Ensure that affected people are informed of and have access to the project Grievance Redress Mechanism as well as UNDP’s Accountability Mechanism. 2) In the case grievances are received or there are incidents, notify the UNDP PMU as soon as possible and no later than within 36 hours. 3) Revisit this risk regularly as part of risk monitoring and reporting. If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and the mechanism will need to be reviewed to ensure application of this UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities."
|  | "The activity may occur within or adjacent to critical habitats and/or environmentally sensitive areas, like reefs. (Social and Environmentral Risk, SES Activity-level Standard 1: Biodiversity)" |  |  |  | "A preliminary analysis indicates that sensitive areas are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may be in areas subject to hazards such as hurricains. (Social and Environmentral Risk, SES Activity-level Standard 2: Climate Change)" |  |  |  | "A preliminary analysis indicates that the activities may be located at areas that may suffer extreme weather conditions but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may utilize tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes. (Social and Environmentral Risk, SES Activity-level Standard 4: Cultural Heritage)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may create economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation). (Social and Environmentral Risk, SES Activity-level Standard 5: Displacement)" |  |  |  | "The activities may replace other previous activities, assets and/or access to resources but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. However, the baseline site conditions would need to be further assessed. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, this will include ensuring the sites selected for the activities are supported by affected people and do not require land acquisition or result in physical displacement. 2) Ensure the risk is regularly monitored as part of risk monitoring and reporting. 3) If subsequent information results in confirmation that there will be some economic displacement then this risk (and overall grant) will be upgraded to a Moderate Risk categorization and the UNDP PMU will be notified and an abbreviated Livelihood Action P{lan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to reduce this risk."
|  | "The activity may be in areas where indigenous peoples are present (including activities area of influence). (Social and Environmentral Risk, SES Activity-level Standard 6: Indigenous Peoples)" |  |  |  | "A preliminary analysis indicates that sensitive areas/practices are present in this country but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
|  | "The activity may bring occupational health and safety risks due to physical and psychosocial hazards form working in an exteme weather context and/or maritime context. (Social and Environmentral Risk, SES Activity-level Standard 7: Labour)" |  |  |  | "A preliminary analysis indicates that the activities may bring occupational health and safety risks but any potential impact from the proposed grant activities would be anticipated to be negligible or minimal at most. Because this risk is rated as “Low Risk”, this SES Standard is not triggered. However, a precautionary approach will be applied to ensure the risk is carefully managed and monitored. To manage this risk we will: 1) Revisit this risk in further design and site selection to ensure the risk is avoided where possible, and regularly as part of risk monitoring and reporting. 2) If subsequent information results in a Moderate Risk categorization then the UNDP PMU will be notified and a plan will need to be in place to ensure application of UNDP’s SES Standard and approved by the UNDP PMU prior to initiation of the relevant activities. In addition, through the capacity building component of the grant supported by UNDP, trainings would include capacity building to manage this risk. "
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances have been received so far for the project |  | N/A
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | No
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Ensure new innovations promote and accelerate gender equality and women’s empowerment |  | #/% of new innovations promoted and accelerated that accounts for the structural barriers and needs of women | 0 | 50% | Good (Gender is a factor in all stage of screening and selection process of the ISGAP grantees. Therefore, all grant proposals have provided baseline and planned action that the applicant will enhance or empower women through their operation.)
Ensure evidence base generated is segregated by gender. |  | # of adaptation innovation evidence generated with insights on women | 0 | 50% | N/A. Considering that grantees from the 1st cohort have been implementing their LVGAs for roughly 9 months, at the moment of writing this PPR, no consolidated knowledge products have been generated yet. Quarterly reporting format is being updated to enhace the capture of dissagregated impact data from each LVGA, including gender-related considerations.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
Each of the 1st cohort LVGAs, identify gender equality and women´s empowerments issues, and determine in their workplans how their work further empowers women and how their intended innovations promote results in an increase wellfare or livelihood for women. Grantees need to report quarterly to ISGAP´s PMU on their progress, including impact indicators (some of which are related to gender). |  | Good
2nd call for proposals selection process mantains a favourable score assigned for those projects that contribute to gender equality and women´s empowerment. The 2nd cohort of grantees´ LVGAs will include equality and women´s empowerments progress and impact indicators. |  | Good
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | Gender is mainstreamed with the entire project implementation. From the application process (1st and 2nd call for proposals), gender is one of the screening critieria, applicants need to highlight how their work further empowers women and how their intended innovations promote results in an increase wellfare or livelihood for women.
Have the implementation arrangements at the IE been effective during the reporting period? |  | All grantees from cohort 1 have gender based indicators as part of their grant agreement, and are reporting progress as well gender issues as part of their implementation plan. Trhoughout the selection process of the 2nd cohort grantees, gender-related criteria are mantained and each LVGA will have specific indicators to report how the project enhances women empowerment, and increase their welfare and livelihoods.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | IE is the EE for this project
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | IE is the EE for this project
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Capacity gaps related to overall reporting (technical and financial) has been identified with few 1st cohort grantees, but is being solved trhough close follow up, training refreshals on reporting, engaging an M&E consultant in ISGAP´s PMU, engaging UNDP´s country offices or the Small Grants Programme (SGPs), or relevant partners that work in SIDS. It was observed during last quarterly reporting cycle of the LVGAs (6 months), that the current reporting template did not capture the information in its entirety (particularly related to some impact data indicators). Therefore, the project is planning to update the template (with focus on minimal changes) to improve the capture of direct and indirect beneficiaries disaggregated data and other indicators, including GP matters. Similarly, an online (web-based) project Monitoring and Evaluation system will be developed to bring efficiency to data collection and reporting, and to nurture the development of knowledge management and communicational products.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances have been received so far for the project (in general, and regarding gender-related matters) |  | N/A
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Outcome 1.1: Development of innovative adaptation practices, tools and technologies encouraged and accelerated |  | Minimum of 5 out of 10 funded projects with innovative adaptation practices, tools and technologies (at least 50% with women led organisations or organisations largely benefit women customers) |  | Innovative adaptation practices are being implemented by 22 grantees and documented Longlisting process for the second cohort of ISGAP grantees underway (expected 18-22 new grants). | Highly Satisfactory (HS)
| Outcome 1.2: Evidence of effective, efficient adaptation practices, products and technologies generated as a basis for implementing entities and other funds to assess scaling up |  | Minimum of 5 out of 10 funded projects that demonstrate findings and evidences of effective and efficient adaptation practices, products, and technologies (at least 50% with women led organisations or organisations largely benefit women customers |  | Innovative adaptation practices are being implemented by 22 grantees and documented Capacity and need assessment of all grantees Mapping exercise for all 22 grantees to identify potential impact areas. 4 partnerships with world leading universities for thought leadership, funder engagement, knowledge and skill transfer. Gender related data: 22 LVGAs have included gender-related progress indicators. First ISGAP cohort: No of estimated women beneficiaries: 54,287 (women:31% of total beneficiaries). Six projects are either women led or have largely women beneficiaries. | Highly Satisfactory (HS)
| Outcome 2: Grantees’ innovation and business development capacity enhanced |  | All grantees complete grant disbursement against performance target within 24 months after grant agreement signed At least half of the grantees received additional support/funding to scale up and/or replication |  | All 22 grantees have received support from UNDP with regards to: Financial reporting, Indicator and milestone reporting (M&E), Innovation concepts, Business development, Individual support to scaling-up their tools/practices/business models, Safeguards and risk management. Overall 19 grantees (86%) achieved their performance target, whereas only three grantees did not reported performance within time due to COVID and capacity related challenges. Project team is closely working with these grantees to improve their capacity. 5 to 7 grantees have high scaling-up or replication potential, they are receiving support from ISGAP to find additional sources of funding (capacity building, network and advocacy, specialized technical assistance). | Highly Satisfactory (HS)
| Outcome 3: Lessons learned are codified, documented, and disseminated/shared leading to adoption or replication of project ideas by others |  | Four annual web-based publication/blog and lessons learned, and at least four technical brief/blog on specific topics (with one lessons learned brief on innovative ways of address gender inequality in adaptation to climate change) |  | 1 knowledge management (KM) workshop with ISGAP grantees 3 training sessions offered trhough the Resilience Knowledge Coalition (1 on story telling, 1 on financing locally-led adaptation, 1 session on tracking LLA progress) Participation in Regional Resilience Hubs to collect voices for COP27 1 Climate Change Adaptation training kit (only visuals) incorporating ISGAP first cohort’s adaptation practices 1 ISGAP grantee article in Climate Tribune Magazine (ICCCAD) 1 ISGAP grantee article in Climate Home News (Adaptation Fund) | Highly Satisfactory (HS)
[5 empty] | Overall Rating | Highly Satisfactory (HS)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Monica Borrero
| Email: | monica.borrero@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
For the current reporting period, the project has been successful in achieving its targets in terms of delivery. The 22 grantees were selected through well-defined criteria and all these grantees' projects are in the first year of their implementation. During this reporting period, the project team worked closely with the 1st cohort of grantees to ensure successful implementation of their LVGAs. The Third Project Board Meeting was carried out on 06 December 2022 where the yearly performance was presented. In the same Board Meeting, the project work plan for 2023 was endorsed. Further information about the implementation can be found in the expected results section above, and in the Annexxes. However overall project implementation is approximately one year behind, partly due to the new governance structure set up required when the EU funding was confirmed. This was mainly due to the policy constraint requiring the project board to approve the grant selection criteria and grant selection committee before the selection process could take place. COVID-19 also has a significant impact due to procurement hold-ups and delays in PMU recruitment during 2021. The PMU took over a year to set up at a minimum and start the implementation at a good pace. During 2022, the project team made significant efforts to catch up with project delivery and for 2023 the team has updated the work plan, to continue catching up with the delay. The Mid- term review will be carried out during the first quarter of 2023. Currently the TORs are being developed to recruit the consultant that will carry out this task. The objective of the MTR is to assess overall progress towards the achievement of the project objectives and outcomes as specified in the grant agreements with the donors (AF and EU). From the next reporting period, the project will update the LVGAs´reporting formats, to improve the capture of more disaggregated data on beneficiaries as well on innovation practices, based on some lessons learnt identified at the project level. Similarly, an online (web-based) project Monitoring and Evaluation system will be developed to bring efficiency to data collection and reporting.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Outcome 1.1: Development of innovative adaptation practices, tools and technologies encouraged and accelerated |  | Minimum of 5 out of 10 funded projects with innovative adaptation practices, tools and technologies (at least 50% with women led organisations or organisations largely benefit women customers) |  | Indicator: Number of innovative adaptation practices, tools and technologies funded Achievements (Annual Progress): Successfully funded 20+ grantees Details: progress indicator has been achieved through the signature of 22 low value grant agreements (LVGAs) (from 1st cohort of grantees; 12 LVGAs of $125,000 each and 10 of $60,000 each).The first call for proposals received 384 applications from NGOs/CSOs globally. The 22 1st cohor grantees, cover 19 countries, no country has more than two LVGAs. Out of the 22 grantees, 7 are from Africa, 11 Asia-Pacific (including 4 SIDS), and 4 from Latin America. Generally, 40% of the 1st cohort of grantees focus on resilience agriculture; 20% on technology and technology related innovation; 10% on community-based adaptation (including traditional knowledge, community knowledge and behaviour change); about 10% around payment for ecosystem services or other financial structures to support adaptation); and lastly, 10% focus on entrepreneurship with focus on women or people with disabilities. The second call of proposals was carried out between September and November this year (2022). The longlisting process has begun. There was a total of 462 proposals received from 92 countries, and most of them again were from Africa. The second largest group was from Asia and Pacific, followed by LAC, and in a lesser amount from Central Asia and the Arab States. Once the longlisting process is completed, the commencement of the shortlisting process will start and a specific Project Board Meeting will take place to endorse the selection (beginning of 2023). | Satisfactory (S)
| Outcome 1.2: Evidence of effective, efficient adaptation practices, products and technologies generated as a basis for implementing entities and other funds to assess scaling up |  | No expected progress of this outcome at this stage. |  | Indicator: Quantity and quality of key findings on effective, efficient adaptation practices, products and technologies generated Achievements(Annual Progress): Adaptation practices are being implemented by 22 grantees. Capacity and need assessment of all grantees Mapping exercise for all 22 grantees to identify potential impact areas. 4 partnerships with world leading universitties for thought leadership, funder engagement, knowledge and skill transfer. Details: 22 grantees have been implementing their LVGAs since April 2022 and the 6-months reports have been submitted to UNDP in October 2022. Under the ISGAP project, grantees are implementing various LVGAs related to climate change adaptation initiatives, from local and indigenous practices to new technologies and products. Some LVGAs are also dedicated to promote entrepreneurship, supporting innovation ecosystem around incubators, startups, green jobs, and livelihood improvements. Grantees are reporting to ISGAP´s PMU quarterly with progress indic.ators and milestones. These reports are the main way to document evidence with regards to the effectiveness and efficiency of the practices, products and technologies. There are roughly 9 months of LVGAs´ implementation at the moment of writing this donor report (PPR). During January 2023, 9-month quarterly reports will be submitted by grantees to report on latest activities. Capacity assessments have been done with all grantees to identify impact areas, to measure resilience, and document the effectiveness of the tools and practices that they are implementing locally. From the 22 grantees that started LVGA implementation, 17 have received the second disbursement, and the remaining are in the pipeline (with some revisions currently underway). 19 grantees have completed their milestones, with few exceptions (e.g. due to local restrictions in the area). Nevertheless, work is being done to catch up and demonstrate milestone completion in the 12-month reporting period. Roughly 6-7 grantees have been identified to have a high scale-up potential. More focus will be paid in those that are ready to engage with potential investors and scale-up. A short-recorded video showcasing 22 ISGAP grantees and the highlights of their work can be found here: https://youtu.be/tb9bthLNad8 66 – Açai berries in Brazil. The project’s goal is to stimulate regenerative agriculture by helping farmers to plant acai in agroforestry by combining acai production with forest management and income generation. It will be working with rural communities and smallholders to prevent the clearing of old growth forests. 85 – Cleantech hub incubator/accelerator (Colombia). An incubator and an accelerate to catalyse green entrepreneurship through turnkey programmes in cleantech ideation, incubation, acceleration and innovation across Colombia. Project aims to create a source for bottom up innovation and green scale-ups, with the most promising cleantech champions in the region receiving support to further develop and validate their business ideas in the market and guide them on their start up journey to become market and investment ready 71 – Greenhouse horticulture in Nigeria. Project targets two villages to help them understand/expand their small-scale farming, using greenhouses and solar powered bore holes. Primarily done through workshops/training through methods of crop growing which is more climate resilient and as that expands, incomes will increase and there will be increased food and water resilience and security. 113 - HEAL horticulture in floating rafts in India. The project supports farmers and fishers through regenerative agriculture on rafts. They help them sell their produce by integrating them into offtake agreements. 121 - Dry-season gardening in Ghana. Conventional agriculture is around wet season growing/irrigated systems and in project's experience/research, income changes dramatically when farmers change to dry season or dry season crops. Training farmers on technical expertise in dry season agriculture will increase their incomes. 157 - Aquaponics in Uganda. Introduction of aquaponics technology through an innovative lease-to-own model to promote aquaponics and horticulture related production, including nursery propagation, in this area of Uganda. The aquaponics-based enterprises aim at promoting both ecosystems and communities’ resilience to the impacts of climate change 260 – Sustainable goat feed meal in Kenya. Small company creating new food for goats that is much cheaper and created by local materials. This is cheaper, more accessible and offers local farmers the opportunity to have more goats. The scaling of the goat farming allows farmers to make money from food creation and goat farmer. Additional source of food. Intention: to scale food product, scaler farmers doing goat farming, and scale food production and purchase. For successful implementation of grants, a need assessment of grantees was conducted to identify the aggregate and individual needs of their individual projects. Based on need assessment grantees were classified into three support categories (light: require little or no help, medium: require help in project implementation, reporting etc. and heavy: require close support during entire grant cycle). A mapping exercise was conducted to identify grantees potential impact areas (this includes adaptation and innovation potential; and social impact). The exercise also helped to assess the grantees projects sector wise contribution across agriculture, livestock, sustainable agriculture, and agroforestry. In order to promote and showcase innovative approaches to financing locally-led action, and the resilience-building have been done through increasing collaboration between the UNDP ISGAP program and its knowledge partner, the Global Resilience Partnership (GRP), and four leading global business schools, namely Yale University School of Management, University of Cape Town Graduate School of Business, IMD in Switzerland and Oxford University Said Business School. This emerging collaboration has various potential opportunities for thought-leadership, donor and funder engagement, and skills and knowledge transfer. To date, the collaboration has focused on showcasing ISGAP, as well as several of the ISGAP projects themselves, as evidence of needed and innovative forms of funding. Two thought-leadership roundtables have been held at Yale University in the past 6 months. Both events were attended by crucial funding- and intermediary-actors, including SIDA, FCDO, BlackRock, Social Finance and MCE Social Capital. | Satisfactory (S)
| Outcome 2: Grantees’ innovation and business development capacity enhanced |  | It is expected that 5-10 grantees will recevie first tranche of grant disbursement according to agreed grantees’ performance target by now. |  | Indicator:Number of grantees that successfully complete innovation and business development milestones, and grant disbursement according to agreed grantees’ performance target. Achievements(Annual Progress):All 22 grantees have received support from UNDP with regards to financial checks, indicator- and milestone-setting, and safeguards advice. Details:Under this output project provided three types of technical assistance. This includes capacity building, tailored support and network and advocacy assistance. 1. Capacity Building: 1. Regarding capacity building with the first cohort of grantees, a series of onboarding sessions have been carried out by the programme. The first was about how to do proper technical and financial reporting. Various grantees are not used to working with international development projects or donors, so it was required to raise their capacities with regard to progress reporting as a pre-requisite to receive subsequent LVGA´s disbursements. 2. An “ISGAP introductory workshop and innovation training session” was also done together with UNDP´s UNDP Asia-Pacific (AP) Regional Innovation Office (RIC). Grantees were introduced to the ISGAP programme´s partners, key innovation concepts were presented, and a practical foresight exercise was done. The foresight exercise included the development of future scenarios, and grantees needed to come up with solutions and how to adapt and scale up their projects in those future scenarios. 3. A series of existing trainings developed by UNDP or other UN agencies were shared with regards to different topics (e.g. nature-based solutions, climate change adaption, gender and climate, how to make “the perfect pitch” to potential investors, green entrepreneurship, etc). Since all grantees had different training needs and levels of knowledge, this compilation was shared so they could pick and do the necessary trainings in a self-paced mode. 4. Engagements with AVPN were conducted to carry out a series of round tables, the first one is going to happen this week with the Asia and the Pacific grantees. The LAC and Africa roundtables will follow in the first quarter of 2023. This is tailored to expose the grantees to potential investors and relevant private sector stakeholders (funders), to better prepare them for future investor or matchmaking events. Work on safeguards has been done on a 1-to-1 basis (e.g. updating their safeguards matrixes, identifying and proposing actions to manage their risks). This tailored support on safeguard has the objective of keeping each project risk´s in a low level, or bring medium risks to low (as much as possible). Training on safeguards is also planned for January 2023. 2. Tailored support. grantees have been receiving technical assistance based on the mapping and needs assessment. The technical assistance has been provided directly by UNDP, ISGAP´s consultants/experts, or partners who have linked them with the right organizations or experts. 5 of the grantees also participated in an UCLA MBA program, in which they were mentored for 6 months by qualified groups of students on product service development, operational capacity, or fundraising, depending on the agreed work plan. Collaborations with other universities is being explored. 3. Advocacy Assistance: The network and advocacy have consisted of the selection of key global conferences with donors and partners to showcase the work of ISGAP and the grantees. Links to access ISGAP Conferences, Events and Communications: 1. Gobeshona Conference- Locally Led Adaptation – Finance, Innovation and Scale: March 29th, 2022. (2 grantees showcased). 2. AFCIA/ISGAP presence at COP 27: short-recorded video showcasing 22 ISGAP grantees (LLA endorsers). 12th November 2022. https://youtu.be/tb9bthLNad8 3. COP 27 Side Event – Accelerating Climate Change Adaptation Action through Innovation: Jointly organized with the AF and UNEP/CTCN. (1 grantee showcased). 17th November 2022. Link: https://youtu.be/d_Dsb8fkN54; https://twitter.com/Srilata_Kammila/status/1592364634987982851 Link: https://www.adaptation-undp.org/cop27-side-event-accelerating-climate-change-adaptation-action-through-innovation ; https://youtu.be/d_Dsb8fkN54 4. Seed to Scale- Accelerating Innovation Enterprises, Resilience Hub, COP 27: lead by the Global Resilience Partnership. (1 grantee showcased). 12th November 2022 https://www.youtube.com/watch?v=5F6a4pbxil4 5. Nature For Life Hub: Video on locally-led action and innovation in agricultural value chains (2 grantees showcased). November 30th, 2022. https://www.youtube.com/watch?v=N7YtO3JZOf8&list=PL4yHLnNwn91NKH81h t82OIyzVydZ-OTjS | Satisfactory (S)
| Outcome 3: Lessons learned are codified, documented, and disseminated/shared leading to adoption or replication of project ideas by others |  | No expected progress of this outcome at this stage. |  | Indicator: Citation and/or adoption of shared lessons learned and codified knowledge Achievements(Annual Progress) 1 knowledge management (KM) workshop with ISGAP grantees 3 training sessions offered trhough the Resilience Knowledge Coalition (1 on story telling, 1 on financing locally-led adaptation, 1 session on tracking LLA progress) Participation in Regional Resilience Hubs to collect voices for COP27 1 Climate Change Adaptation training kit (only visuals) incorporating ISGAP first cohort’s adaptation practices 1 ISGAP grantee article in Climate Tribune Magazine (ICCCAD) 1 ISGAP grantee article in Climate Home News (Adaptation Fund) Details: To advance on the knowledge management aspect of the project, collaborations were made with key partners such as the Resilience Knowledge Coalition (GRP, CDKN, and ICCCAD). An ISGAP knowledge management workshop delivered by the Coalition and UNDP was carried out in September 2022. Training sessions on storytelling and tracking LLA in progress were offered to the grantees, as well as the opportunity to participate in the regional resilience hubs (e.g. Africa) to exchange experiences with other peers and bring key messages to COP 27. Given the fact that the frist cohort of grantees has been implementing their LVGAs for 9 months, information from the quarterly reports was not sufficient to develop a yearly knowledge management product yet with substantial data. However, a climate change adaption training kit with only visuals was developed, incorporating the first cohort´s adaption practices and tools. This training kit does not require any type of translation and can be used directly with the beneficiaries of the LVGAs. Work was done with donors (e.g. AF) and partners (e.g. ICCCAD) to write articles about the grantees´ innovations and showcase them in different media channels (websites). In respect to the implementation of the communications and visibility plan, UNDP/ISGAP´s PMU has done emphasis in promoting the use of the programme´s logo in international events, in its own communicational products, and in different social media channels. Several examples of how grantees have successfully incorporated the programme´s logo in their own communications materials (e.g. promotional t-shirts, training kits, banners) have been also highlighted in the grantees´6-month quarterly reports. | Satisfactory (S)
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Monica Borrero
| Email: | monica.borrero@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words. |  | 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. For the current reporting period project managed to achieve its target results and has developed strong partnerships, which had a positive impact on project implementation. This has been done through an increasing collaboration between the ISGAP program and its knowledge partners, the Resilience Knowledge Coalition (composed by three organizations GRP, ICCCAD, and CDKN), AVPN (with aimed at fostering stronger bridges between potential funders and the ISGAP cohorts) and five leading global business schools, namely Yale University School of Management, University of Cape Town Graduate School of Business, IMD in Switzerland, Oxford University Said Business School and The Anderson School of Business, based at UCLA. It was observed during last quarterly reporting cycle of the LVGAs (6 months), that the current reporting template did not capture the information in its entirety (particularly related to some impact data indicators). Therefore, the project is planning to update the template (with focus on minimal changes) to capture direct and indirect beneficiaries disaggregated data and other indicators, that will nurture the development of KM and communicational products. Grantees from the first cohort are at their early stage of LVGA implementation, so there is space for improvement and adaptation to more complete /efficient reporting requirements with corresponding guidance from the PMU. At grantees level, majority of the issues remains around capital for scaling, operational capacity and implementation challenges (due to security and COVID-19 related restriction). Despite the potential of building local environmental and societal resilience, many locally led activities struggle to access any type of finance. However, despite these challenges grantees have adapted well to the situation, placed mitigation measures and projects are mostly on track and are excited to implement further. A few grantees (three, from SIDS countries) have not been able to submit the 6-month reports within the deadline, or with the required quality and completion, due to capacity and technical issues. Hence, the project team is adapting multiple options to work with these grantees such as: close follow up, training refreshals on reporting, engaging an M&E consultant in ISGAP´s PMU, engaging UNDP´s country offices or the Small Grants Programme (SGPs), or relevant partners that work in SIDS. 2. Detail critical risks that have affected progress. Overall project performance is satisfactory for the current reporting period. There is no critical risk project has faced so far. As mentioned in the earlier section, there's a delay in the implementation because ISGAP's PMU took over a year to set up and start the implementation at a good pace. COVID-19 also had a significant impact due to procurement hold-ups and delays in PMU recruitment. The project team is making efforts to catch up during 2022 and 2023, and has adjusted the workplan accordingly to continue project implementation at a good pace. 3. Outline response to MTR undertaken this reporting period. The Mid- term review will be carried out during the first quarter of 2023. Currently the TORs are being developed to recruit the consultant that will carry out this task. The objective of the MTR is to assess progress towards the achievement of the project objectives and outcomes as specified in the grant agreement with the donors (AF and EU). 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words N/A. Overall project performance is stasficatory. Please refer above rating section.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
1.1. | Number of innovative adaptation practices, tools and technologies funded | 0 | 22 grants have been granted and currently in the implementation phase Longlisting process for the second cohort of ISGAP grantees underway (expected 18-22 new grants). | Minimum of 5 out of 10 funded projects that demonstrate findings and evidences of effective and efficient adaptation practices, products, and technologies
1.2.1. | Quantity and quality of key findings on effective, efficient adaptation practices, products and technologies generated | 0 | Innovative adaptation practices are being implemented by 22 grantees and documented Capacity and need assessment of all grantees Mapping exercise for all 22 grantees to identify potential impact areas. 4 partnerships with world leading universities for thought leadership, funder engagement, knowledge and skill transfer. | Minimum of 5 out of 10 funded projects that demonstrate findings and evidences of effective and efficient adaptation practices, products, and technologies
1.2.2. | Number of women-led Civil Society Organisations (CSOs) that develop replication projects | 0 | 22 LVGAs have included gender-related progress indicators. First ISGAP cohort: No of estimated women beneficiaries: 54,287 (women:31% of total beneficiaries). Six projects are either women led or have largely women beneficiaries. | (at least 50% with women led organisations or organisations largely benefit women customers)
2.1. | Number of grantees that successfully complete innovation and business development milestones and grant disbursement according to agreed grantees’ performance target | Grantees with limited technical, innovation, and business development capacity | All 22 grantees have received support from UNDP with regards to: Financial reporting, Indicator and milestone reporting (M&E), Innovation concepts, Business development, Individual support to scaling-up their tools/practices/business models, Safeguards and risk management. | All grantees complete grant disbursement against performance target within 24 months after grant agreement signed
2.2. | Number of grantees that receive additional support/funding to scale up and/or replication | 0 | Overall 19 grantees (86%) achieved their performance target, whereas only three grantees did not reported performance within time due to COVID and capacity related challenges. Project team is closely working with these grantees to improve their capacity. 5 to 7 grantees have high scaling-up or replication potential, they are receiving support from ISGAP to find additional sources of funding (capacity building, network and advocacy, specialized technical assistance). | At least half of the grantees received additional support/funding to scale up and/or replication
3.1. | Citation and/or adoption of shared lessons learned and codified knowledge | 0 | 1 knowledge management (KM) workshop with ISGAP grantees 3 training sessions offered trhough the Resilience Knowledge Coalition (1 on story telling, 1 on financing locally-led adaptation, 1 session on tracking LLA progress) Participation in Regional Resilience Hubs to collect voices for COP27 1 Climate Change Adaptation training kit (only visuals) incorporating ISGAP first cohort’s adaptation practices 1 ISGAP grantee article in Climate Tribune Magazine (ICCCAD) 1 ISGAP grantee article in Climate Home News (Adaptation Fund) | Four annual web-based publication/blog and lessons learned, and at least four technical brief/blog on specific topics (with one lessons learned brief on innovative ways of address gender inequality in adaptation to climate change)

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Project level- operational and technical challenges: 1. As mentioned in the earlier sections of this format, there's a delay in the implementation because ISGAP's PMU took over a year to set up and start the implementation at a good pace. During 2022 and 2023 the project team is making efforts to catch up with project delivery. 2. A few grantees(three) have not been able to submit 6-month reports within the deadline due to capacity issues. Program team is adapting multiple options to work with these grantees, this includes close follow up, trainings on reporting financial and narrative results and strengthening ISGAP's PMU team by engaging M&E and communication consultant. 3. As all the projects from first round are in their early stage of implementation and it was observed during last reporting (6 months) that current reporting template did not capture the information in its entirety particularly related to beneficiaries, therefore project is planning to revise and update the template (with focus on minimal changes or with additional reporting burden on the grantees) to capture direct and indirect beneficiaries disaggregated data. 4. The project has developed strong partnerships, which had a positive impact on project implementation. This has been done through an increasing collaboration between the UNDP ISGAP program and its knowledge partner, the Global Resilience Partnership, AVPN (with aimed at fostering stronger bridges between potential funders and the ISGAP cohorts) and five leading global business schools, namely Yale University School of Management, University of Cape Town Graduate School of Business, IMD in Switzerland, Oxford University Said Business School and The Anderson School of Business, based at UCLA. Grantees Level Challenges: 5. At grantees level, majority of the issues remains around capital for scaling, operational capcity and implementation challenges (due to security and COVID-19 related restriction). Despite the potential of building local environmental and societal resilience, many locally-led activities struggle to access any type of finance. However despite these challenges grantees have adapted well to the situtation, placed mitigation measures and projects are mostly on track and are excited to implement further.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | During this reporting period (jan 2022- Dec 2022) project did not face any delays, all the planned actvities were delivered on time.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | There are no changes in the project design. The additional funding from EU certainly improved the project ambition and caused changes in the project governance structure. From an output perspective, the project now has improved targets of the number of innovative adaptation practices, tools and technologies funded, from 10-15 now to 30-45.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Social and Environmental Safeguard (SES) guidelines were developed for the ISGAP project. These guidelines contain the procedures and specific guidance on how to mitigate risks identified by each grantees in individual proposals. The main objectives of the ESMF are to • Strengthen the social and environmental outcomes of ISGAP programme • Avoid adverse impacts to people and the environment • Minimize, mitigate, and manage adverse impacts where avoidance is not possible • Strengthen ISGAP grantees and partner capacities for managing social and environmental risks • Ensure full and effective stakeholder engagement, including through a mechanism to respond to complaints from project-affected people Further more project has set up Grievance Redress Mechanism (GRM) to to act as a recourse for situations for stakeholders who have a concern about the program’s potential impacts on them.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender is mainstreamed with the entire project implementation. From the application process, gender was one of the screening critieria, applicants need to highlight how their work further empowers women and how their intended innovations promote results in an increase wellfare or livelihood for women. This was criteria for both the initial application process and the detailed project proposal process. Interestingly, all project applicants highlighted that their project will support women and empower women. The project has started gathering data on gender particularly with focus on women empowerment and livelihood improvement. Futher project plan to revise the reporting structure (for the upcoming cycle) of the grantees to esnure gender data is reported.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A. MTR will be carried out during January-February 2023.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A. MTR will be carried out during January-February 2023.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A. MTR will be carried out during January-February 2023.
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A. MTR will be carried out during January-February 2023.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A. MTR will be carried out during January-February 2023.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A. MTR will be carried out during January-February 2023.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A. MTR will be carried out during January-February 2023.
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A. MTR will be carried out during January-February 2023.
What measures are being/could have been put in place to improve project/program results? | N/A. MTR will be carried out during January-February 2023.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | N/A. MTR will be carried out during January-February 2023.
If learning objectives have been established, have they been met? Please describe. | N/A. MTR will be carried out during January-February 2023.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A. MTR will be carried out during January-February 2023.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A. MTR will be carried out during January-February 2023.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | PIMS 6266
Implementing Entity | UNDP
Type of implementing entity
Country |  | Multi country
Region |  | Global
Sector |  | Multi sector
[5 empty] | Please read comment by UNDP |  |  |  | Please read comment by UNDP |  |  |  | Please read comment by UNDP
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 608194 | 73975 | 534219 | Total | 304097 | 36987 | 267109 | Total
|  | % of female beneficiaries | 0% | 0 | 0 | % of female beneficiaries | 47% | 51% | 46% | % of female beneficiaries | 47% | 49% | 46% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0 | 0 | % of Youth beneficiaries | 53% | 49% | 54% | % of Youth beneficiaries | 53% | 51% | 54% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
[5 empty] | Please read comment by UNDP |  |  |  | Please read comment by UNDP |  |  |  | Please read comment by UNDP
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Focus on communities | Community | Innovation accelerated |  | Focus on communities | Community | Innovation scaled-up |  | Focus on communities | Community | Innovation accelerated
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 54_Livestock Development for Community] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Food Security | Undertaking innovative practices | 3: Moderately effective | 1 | Food Security | Undertaking innovative practices | 4: Effective | 1 | Food Security | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative product |  | 3: Moderately effective | 2 | Innovative product |  | 4: Effective | 1 | Innovative product |  | 3: Moderately effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project112_ASSOCIATION LA VOUTE NUBIENNE] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Urban adapt | Undertaking innovative practices | 3: Moderately effective | 1 | Urban adapt | Undertaking innovative practices | 4: Effective | 1 | Urban adapt | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated |  | Type |  | Effectiveness |  | Type |  | Effectiveness |  | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative technology |  | 3: Moderately effective | 2 | Innovative technology |  | 4: Effective | 1 | Innovative technology |  | 3: Moderately effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project130_CENTRE FOR COMMUNITY INITIATIVES] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Disaster risk reduction | Undertaking innovative practices | 3: Moderately effective | 1 | Disaster risk reduction | Undertaking innovative practices | 4: Effective | 1 | Disaster risk reduction | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative technology |  | 3: Moderately effective | 2 | Innovative technology |  | 4: Effective | 1 | Innovative technology |  | 3: Moderately effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 56_BUKIDNON UMAYAMNON TRIBE KAPU-UNAN] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Nature-based solutions | Undertaking innovative practices | 3: Moderately effective | 1 | Nature-based solutions | Undertaking innovative practices | 4: Effective | 1 | Nature-based solutions | Undertaking innovative practices | 2: Partially effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  | 3: Moderately effective | 2 | Innovative practice |  | 4: Effective | 1 | Innovative practice |  | 2: Partially effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project66_ CENTRO ECOLOGICO] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Food Security | Undertaking innovative practices | 3: Moderately effective | 1 | Food Security | Undertaking innovative practices | 4: Effective | 1 | Food Security | Undertaking innovative practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  | 3: Moderately effective | 2 | Innovative practice |  | 4: Effective | 1 | Innovative practice |  | 4: Effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 71_ SUSTAINABLE ENVIRONMENT AND FISHERIES] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Food Security | Undertaking innovative practices | 3: Moderately effective | 1 | Food Security | Undertaking innovative practices | 4: Effective | 1 | Food Security | Undertaking innovative practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative technology |  | 3: Moderately effective | 2 | Innovative technology |  | 4: Effective | 1 | Innovative technology |  | 4: Effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 74_ YAYSAN BESI PAE] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Focus on communities | Undertaking innovative practices | 3: Moderately effective | 1 | Focus on communities | Undertaking innovative practices | 4: Effective | 1 | Focus on communities | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative product |  | 3: Moderately effective | 2 | Innovative product |  | 4: Effective | 1 | Innovative product |  | 3: Moderately effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 82_SOKEHS MENIN KETENGESED] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Nature-based solutions | Undertaking innovative practices | 3: Moderately effective | 1 | Nature-based solutions | Undertaking innovative practices | 4: Effective | 1 | Nature-based solutions | Undertaking innovative practices | 2: Partially effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  | 3: Moderately effective | 2 | Innovative practice |  | 4: Effective | 1 | Innovative practice |  | 2: Partially effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 85_ Cleant Tech Hub] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Innovative adaptation financing | Undertaking innovative practices | 3: Moderately effective | 1 | Innovative adaptation financing | Undertaking innovative practices | 4: Effective | 1 | Innovative adaptation financing | Undertaking innovative practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative product |  | 3: Moderately effective | 2 | Innovative product |  | 4: Effective | 1 | Innovative product |  | 4: Effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 86_SPARC- SOCIETY FOR THE PROMOTION OF AREA] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Nature-based solutions | Undertaking innovative practices | 3: Moderately effective | 1 | Nature-based solutions | Undertaking innovative practices | 4: Effective | 1 | Nature-based solutions | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative technology |  | 3: Moderately effective | 2 | Innovative technology |  | 4: Effective | 1 | Innovative technology |  | 3: Moderately effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 113_SOUTH ASIAN FORUM FOR ENVIRONMENT] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Food Security | Undertaking innovative practices | 3: Moderately effective | 1 | Food Security | Undertaking innovative practices | 4: Effective | 1 | Food Security | Undertaking innovative practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative technology |  | 3: Moderately effective | 2 | Innovative technology |  | 4: Effective | 1 | Innovative technology |  | 4: Effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 116_MOYO DISTRICT FARMERS ASSOCIATION] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Nature-based solutions | Undertaking innovative practices | 3: Moderately effective | 1 | Nature-based solutions | Undertaking innovative practices | 4: Effective | 1 | Nature-based solutions | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  | 3: Moderately effective | 2 | Innovative practice |  | 4: Effective | 1 | Innovative practice |  | 3: Moderately effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project121_:OPEN GHANA] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Focus on communities | Undertaking innovative practices | 3: Moderately effective | 1 | Focus on communities | Undertaking innovative practices | 4: Effective | 1 | Focus on communities | Undertaking innovative practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  | 3: Moderately effective | 2 | Innovative practice |  | 4: Effective | 1 | Innovative practice |  | 4: Effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 122_ESPACIO DE ENCUENTRO DE LAS CULTURAS] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Food Security | Undertaking innovative practices | 3: Moderately effective | 1 | Food Security | Undertaking innovative practices | 4: Effective | 1 | Food Security | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative technology |  | 3: Moderately effective | 2 | Innovative technology |  | 4: Effective | 1 | Innovative technology |  | 3: Moderately effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 143_ISLAND FOOD COMMUNITY OF POHNPEI] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Food Security | Undertaking innovative practices | 3: Moderately effective | 1 | Food Security | Undertaking innovative practices | 4: Effective | 1 | Food Security | Undertaking innovative practices | 2: Partially effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative product |  | 3: Moderately effective | 2 | Innovative product |  | 4: Effective | 1 | Innovative product |  | 2: Partially effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project157_SAMPLE UGANDA AQUACULTURE ASSOCIATION] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Food Security | Undertaking innovative practices | 3: Moderately effective | 1 | Food Security | Undertaking innovative practices | 4: Effective | 1 | Food Security | Undertaking innovative practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative technology |  | 3: Moderately effective | 2 | Innovative technology |  | 4: Effective | 1 | Innovative technology |  | 4: Effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 251PILIER AUX FEMMES VULNERABLES ACTIVES] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Nature-based solutions | Undertaking innovative practices | 3: Moderately effective | 1 | Nature-based solutions | Undertaking innovative practices | 4: Effective | 1 | Nature-based solutions | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative product |  | 3: Moderately effective | 2 | Innovative product |  | 4: Effective | 1 | Innovative product |  | 3: Moderately effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 260_WORLD NEIGHBORS] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Food Security | Undertaking innovative practices | 3: Moderately effective | 1 | Food Security | Undertaking innovative practices | 4: Effective | 1 | Food Security | Undertaking innovative practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative product |  | 3: Moderately effective | 2 | Innovative product |  | 4: Effective | 1 | Innovative product |  | 4: Effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 273_SMART FARMS FIJI FOUNDATION] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Food Security | Undertaking innovative practices | 3: Moderately effective | 1 | Food Security | Undertaking innovative practices | 4: Effective | 1 | Food Security | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative technology |  | 3: Moderately effective | 2 | Innovative technology |  | 4: Effective | 1 | Innovative technology |  | 3: Moderately effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 278_RURAL DEVELOPMENT INITIATIVE] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Nature-based solutions | Undertaking innovative practices | 3: Moderately effective | 1 | Nature-based solutions | Undertaking innovative practices | 4: Effective | 1 | Nature-based solutions | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  | 3: Moderately effective | 2 | Innovative practice |  | 4: Effective | 1 | Innovative practice |  | 3: Moderately effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 289_MESOAMERICAN REEF FUND INC] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Disaster risk reduction | Undertaking innovative practices | 3: Moderately effective | 1 | Disaster risk reduction | Undertaking innovative practices | 4: Effective | 1 | Disaster risk reduction | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative product |  | 3: Moderately effective | 2 | Innovative product |  | 4: Effective | 1 | Innovative product |  | 3: Moderately effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 59_SANTO SUNSET ENVIRONMENT NETWORK] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Disaster risk reduction | Undertaking innovative practices | 3: Moderately effective | 1 | Disaster risk reduction | Undertaking innovative practices | 4: Effective | 1 | Disaster risk reduction | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative product |  | 3: Moderately effective | 2 | Innovative product |  | 4: Effective | 1 | Innovative product |  | 3: Moderately effective
Aggregated data per sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 54_Livestock Development for Community] [Project 66_ CENTRO ECOLOGICO] [Project 71_ SUSTAINABLE ENVIRONMENT AND FISHERIES] [Project 113_SOUTH ASIAN FORUM FOR ENVIRONMENT] [Project 122_ESPACIO DE ENCUENTRO DE LAS CULTURAS] [Project 143_ISLAND FOOD COMMUNITY OF POHNPEI] [Project 157_SAMPLE UGANDA AQUACULTURE ASSOCIATION] [Project 260_WORLD NEIGHBORS] [Project 273_SMART FARMS FIJI FOUNDATION] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 9 | Food Security | Undertaking innovative practices | 3: Moderately effective | 9 | Food Security | Undertaking innovative practices | 4: Effective | 9 | Food Security | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative product |  | 3: Moderately effective | 18 | Innovative product |  | 4: Effective | 9 | Innovative product |  | 3: Moderately effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 56_BUKIDNON UMAYAMNON TRIBE KAPU-UNAN] [Project 82_SOKEHS MENIN KETENGESED] [Project 86_SPARC- SOCIETY FOR THE PROMOTION OF AREA] [Project 116_MOYO DISTRICT FARMERS ASSOCIATION] [Project 251_PILIER AUX FEMMES VULNERABLES ACTIVES] [Project 278_RURAL DEVELOPMENT INITIATIVE] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 6 | Nature-based solutions | Undertaking innovative practices | 3: Moderately effective | 6 | Nature-based solutions | Undertaking innovative practices | 4: Effective | 6 | Nature-based solutions | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  | 3: Moderately effective | 12 | Innovative practice |  | 4: Effective | 6 | Innovative practice |  | 3: Moderately effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 59_SANTO SUNSET ENVIRONMENT NETWORK [Project130_CENTRE FOR COMMUNITY INITIATIVES] [Project 289_MESOAMERICAN REEF FUND INC | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 3 | Disaster risk reduction | Undertaking innovative practices | 3: Moderately effective | 3 | Disaster risk reduction | Undertaking innovative practices | 4: Effective | 3 | Disaster risk reduction | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  | 3: Moderately effective | 6 | Innovative practice |  | 4: Effective | 3 | Innovative practice |  | 3: Moderately effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project112_ASSOCIATION LA VOUTE NUBIENNE] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Urban adapt | Undertaking innovative practices | 3: Moderately effective | 1 | Urban adapt | Undertaking innovative practices | 4: Effective | 1 | Urban adapt | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated |  | Type |  | Effectiveness |  | Type |  | Effectiveness |  | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative technology |  | 3: Moderately effective | 2 | Innovative technology |  | 4: Effective | 1 | Innovative technology |  | 3: Moderately effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 74_ YAYSAN BESI PAE] [Project 121:OPEN GHANA] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 2 | Focus on communities | Undertaking innovative practices | 3: Moderately effective | 2 | Focus on communities | Undertaking innovative practices | 4: Effective | 2 | Focus on communities | Undertaking innovative practices | 3: Moderately effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative product |  | 3: Moderately effective | 4 | Innovative product |  | 4: Effective | 2 | Innovative product |  | 3: Moderately effective
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated [Project 85_ Cleant Tech Hub] | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Innovative adaptation financing | Undertaking innovative practices | 3: Moderately effective | 1 | Innovative adaptation financing | Undertaking innovative practices | 4: Effective | 1 | Innovative adaptation financing | Undertaking innovative practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative product |  | 3: Moderately effective | 2 | Innovative product |  | 4: Effective | 1 | Innovative product |  | 4: Effective
Feedback on reporting template for the AF
1 | Template should allow to select "multiple types of intervention".Typically, each project contributes to multiple areas, making it crucial to capture the thematic areas beyond the primary focus.
2 | In the effectiveness section, the current options are somewhat subjective and challenging to classify. One suggestion is to offer guidance on the meaning of each option and provide criteria for evaluation. For instance, providing a clear definition of what it means for a project to be considered effective, such as achieving 50% of its target, could be helpful. Alternatively, incorporating a numeric scale could introduce a more objective approach to aggregation, allowing for a quantifiable assessment.
Note on D19: ISGAP grantees in the majority of cases did not count with reliable baseline data on beneficiaries. Hence, we put zero in all cases (from ISGAP cohort 1) to have a more conservative approach. During the signature process of the low value grant agreements, UNDP requested each grantee to estimate target performance beneficiaries data (those persons that will be benefitted by the ISGAP small grant).
Note on H19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Target performance on beneficiaries was estimated by each of the ISGAP grantees and captured in their low value grant agreements. The numbers in this table, represent the aggregated targets on beneficiaries from the 1st cohort of ISGAP grantees only. Aggregated targets on beneficiaries from cohorts 1 and 2 will be provided in next reporting period.
Note on D23: Youth percentage include both male and female age below 18
Note on O328: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: At the moment of completing this report, the 22 grantees from cohort 1 have submitted their 9-month milestone quarterly reports. That is half way trhough their 18 month implementation period LVGAs. Based on this information, UNDP has managed to document in more depth how these innovative adaptation tools, practices and products are implemented, and with this information, it is already possible to produce a KM product during 2023. With regards to their effectiveness, it is still to soon to assess the 22 grantees, but a few of them have certainly demostrated that their solutions work and therefore have been pre-identified by UNDP as grantees with high scaling-up potential.
Note on D329: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: All 22 grantees from the 1st cohort, were selected because they demostrated to be implementing innovative adaptation practices, tools and technologies. Therefore, the baseline for all in Indicator 8.1 is 1 for the 22 grantees. Regarding indicator 8.2. there were not documentet key findings on the efficiency and effectiveness of the 22 ISGAP grantees from cohort 1, therefore the answer is zero in all the cases. One of the main results that the ISGAP Programme seeks to achiebe, is to document the effectiveness and efficiency of these innovative adaptation practices, products and technologies (22 for cohort 1 and 23 for cohort 2).
Note on H329: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Despite the fact that in the PRODOC the level of effectiveness per each initiative/grantee was not defined up-front, for the purpose of this PPR, UNDP has set its performance target at completion that all the tools, practices and products should be accelerated so that they scale from moderately effective to effective. Each of the low value grant agreements with these 22 grantees has set target indicators to improve the efficiency and scalability/replicability of these innovative solutions. UNDP has also set the target to document at least 2 key findings per grantee that receives an ISGAP grant upon completion.
Note on E425: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Out of 9 projects five has "innovative technology" three focused on "innovative practice" and one innovative product
Note on E430: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Four projects are implementing innovative practices. One project involves the development or use of an innovative product. One project involves the development or use of an innovative technology.

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.