## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | August 2014 to August 2015
| Project Title: | Enhancing Resilience of Communities to the Adverse effects of Climate Change on Food Security in Mauritania
Effects of Climate Change on Food Security in Mauritania
| Project Summary: | The Mauritania's Ministry of Environment and Sustainable Development and the United Nations World Food Programme initiated a four-year project to strengthen resilience and promote food security in 100 villages located in the Wilayas of Assaba, Brakna, Guidimakha, Gorgol, Hodh El Chergui, Hodh El Gharbi, Tagant and Trarza. The overall goal of the project aims to improve adaptation in the area of food security in Mauritania by assisting the government in improving technical services at the community level so that village residents, who will be most affected by climate change, can undertake their own analysis of climate change impacts and prepare detailed adaptation plans – including harmonized plans for livestock, land and water management and the overall use of natural resources. The project will also promote climate resilience by protecting threatened resources, such as dunes, community fuel wood forests, and water sources. Finally, villages will be encouraged to explore ways to diversify the sources of livelihood and receive training, coaching, and asset investments to do so. The project includes three components: Component 1: Support technical services and the communities they serve to better understand climate risks, their impacts on resources and food security; and facilitate decentralized and participatory adaptation planning. Component 2: Design and implement concrete adaptation measures identified through community adaptation planning that aim to combat desertification and land degradation. Component 3: Design and implement concrete adaptation measures identified through community adaptation planning that aim to diversify and strengthen the livelihoods of the most vulnerable population.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | MTN/MIE/Food/2011/1/PD | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Word Food Programme (WFP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Mauritania | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Wilaya of Assaba (12 villages); Wilaya of Brakna (12 villages); Wilaya of Gorgol (10 villages); Wilaya of Guidimakha (12 villages); Wilaya of Hodh El Chergui (15 villages); Wilaya of Hodh El Gharbi (14 villages); Wilaya of Tagant (9 villages); Wilaya of Trarza (16 villages) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | July 2012
IE-AFB Agreement Signature Date: |  | July 23 2012 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | August 14 2014 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | September 2016
| Terminal Evaluation Date: | May 2019
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Brochure of the project Poster of the Project Guidance note for the prioritization of project areas Project inception report ACC training report for technical regional services - Kaédi 9-12 Mach 2015 ACC training report for technical regional services - Kiffa 6-9 April 2015 ACC training report for NGO, Kaédi et Kiffa 8-12 June 2015 ACC training report for government representatives at central level 7-9 July 2015 Monitoring Project Activities factsheets Project Progress Report 1st semester 2015 Evaluation report of nurseries | Czech Republic
http://parsacc.yolasite.com/etudes-et-rapports.php
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://parsacc.yolasite.com | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
International Project Manager/Coordinator |  |  | Dominica
| Name: | Ghazi GADER, Project coordinator | Dominican Republic
| Email: | ghazi.gader@wfp.org | Ecuador
| Date: | 14-Agust-2014 | Egypt
| Government DA |  | El Salvador
| Name: | Sidi Mohamed El Wavi, National Project Director | Equatoral Guinea
| Email: | elwavi.sm@gmail.com | Eritrea
| Date: | 14-Agust-2014 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Moise Ballo, WFP Deputy Country Director | Fiji
| Email: | moise.ballo@wfp.org | Finland
| Date: | 14-Agust-2014 | France
| Executing Agency |  | Gambia
| Name: | Alioune FALL, Project coordinator Assistant | Georgia
| Email: | lunef@yahoo.com | Germany
| Date: | 14-August-2014 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [August 2015]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of August 2015 | 2015156 |  |  | 57.75%
Add any comments on AF Grant Funds. (word limit=200) | The amount of $1 163 698,65 includes all expenses and commitments made by: 1. WFP on behalf of MEDD - Executing Entity, 2. MEDD as executing Entity. Actual expenses to date represent $753 328,53 and commitments represent $410 370,12 corresponding to procurement of cereals and salt ($55 971,10) and agricultural material ($354 399,02).
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1 Eight DREDD (regional technical services of MEDD) strengthened to access and analyze climate change information, to monitor local development and to mobilize and support communities | 259268.3241
| Output 1.2 Strengthening of Government's threat, risk and vulnerability analysis | 51042.4101
| Output 1.3: 20 inter-village associations established and supported | 7493.3333
| Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | 11792.8453
| Output 1.5:100 villages, being clustered according to landscape, ecosystem and livelihoods, have prepared adaptation plans that are integrated into local development planning. | 13430.2445
| Output 1.6: Communities share success stories and lessons learned, including support of 8 community radios | 0
| Output 1.7: Monitoring system in place (establishment, training, production of data and reports) to track climate events and ecologic development in project intervention zones. | 0
| Output 2.1: 1500 - 2000 ha of sand dunes fixated | 360663.2855
| Output 2.2: 1000 - 1500 ha of vulnerable zones protected | 134301.2852
| Output 2.3 1,000-1,500 ha of community fuel wood forests planted. | 0
| 2.4 Water retention structures built covering approximately 500 ha | 0
| Output 3.1 300,000 trees for revenue generation and food planted in protected areas | 0
| Output 3.2 4,000 technical staff and community leaders trained in livestock management, agricultural techniques and water utilization | 0
| Output 3.3 5,000 technical staff and community leaders trained and equipped agro-pastoral IGA, including plant multiplication | 0
| Output 3.4 6,000 technical staff and community leaders trained and equipped for poultry development | 0
| Output 3.5 1,000 technical staff and community leaders trained and equipped for apiculture | 0
| Output 3.6 Approx. 20 community cereal banks established. | 0
| Output 3.7 30,000 fuel efficient stoves built | 0
| Output 3.8 2,000 community members (mainly youth) trained and equipped to build and maintain fuel efficient stoves | 0
| EE - Project Execution Costs | 148345.3034
| MIE - Project Management Fee | 177361.6196
| TOTAL | 1163698.6511
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1 Eight DREDD (regional technical services of MEDD) strengthened to access and analyze climate change information, to monitor local development and to mobilize and support communities | 328248.7426 | 2016-09-01
| Output 1.2 Strengthening of Government's threat, risk and vulnerability analysis | 77019.3896 | 2016-09-01
| Output 1.3: 20 inter-village associations established and supported | 24506.6667 | 2016-09-01
| Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | 21797.0495 | 2016-09-01
| Output 1.5:100 villages, being clustered according to landscape, ecosystem and livelihoods, have prepared adaptation plans that are integrated into local development planning. | 24569.7555 | 2016-09-01
| Output 1.6: Communities share success stories and lessons learned, including support of 8 community radios | 274750 | 2016-09-01
| Output 1.7: Monitoring system in place (establishment, training, production of data and reports) to track climate events and ecologic development in project intervention zones. | 96000 | 2016-09-01
| Output 2.1: 1500 - 2000 ha of sand dunes fixated | 86400 | 2016-09-01
| Output 2.2: 1000 - 1500 ha of vulnerable zones protected | 434798.7148 | 2016-09-01
| Output 2.3 1,000-1,500 ha of community fuel wood forests planted. | 294150 | 2016-09-01
| 2.4 Water retention structures built covering approximately 500 ha | 294150 | 2016-09-01
| Output 3.1 300,000 trees for revenue generation and food planted in protected areas | 275900 | 2016-09-01
| Output 3.2 4,000 technical staff and community leaders trained in livestock management, agricultural techniques and water utilization | 202315.7895 | 2016-09-01
| Output 3.3 5,000 technical staff and community leaders trained and equipped agro-pastoral IGA, including plant multiplication | 253894.7368 | 2016-09-01
| Output 3.4 6,000 technical staff and community leaders trained and equipped for poultry development | 215861.5789 | 2016-09-01
| Output 3.5 1,000 technical staff and community leaders trained and equipped for apiculture | 125463.9474 | 2016-09-01
| Output 3.6 Approx. 20 community cereal banks established. | 0 | 2016-09-01
| Output 3.7 30,000 fuel efficient stoves built | 148220 | 2016-09-01
| Output 3.8 2,000 community members (mainly youth) trained and equipped to build and maintain fuel efficient stoves | 92293.6842 | 2016-09-01
| EE - Project Execution Costs | 115830 | 2016-09-01
| MEI | 148830 | 2016-09-01
| TOTAL | 3535000.0555
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | n a
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | n a
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | n a

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
External factors may delay project implementation | Medium to High | Government elections during the initially planned implementation period led to a delay in starting the project activities. However, as soon as the new administration was in place, the project has been making swift progress and hopes to catch up with the planned schedule. The project is a high priority of the Government, and will receive support where difficulties are encountered. Where some of the village clusters are delayed in preparing their adaption plans, other with completed adaptation plans will go ahead with their implementation. Depending on the progress made by various clusters in adaptation plan elaboration and implementation, budgets may be redistributed towards the better performing clusters (based on periodic reviews of progress).
Communities find it difficult to take up the skills, learning and social cohesion necessary to secure protected areas | Medium | Communities will carry out the adaptation actions that they themselves prioritize, and will invest their own resources in addition to those provided by the project. The high degree of participation and ownership promoted by the project, coupled with the provision of income to support what are now major livelihoods, will render the risk of communities not sustaining project results very low.
There is little local specialized management and technical capacity related to climate change, particularly in the entities that are responsible for the project. | From High to Medium | The strengthening of decentralized services is a strategic priority of Government, to which the project will provide valuable support. The project will continue contributing directly to increasing the Government’s technical capacity at these levels.
Lack of adequately qualified partners | Low | A number of qualified partners with a similar project philosophy as WFP are working on the ground, and WFP has good experience in working with them. WFP has a good working experience with some adequately qualified partners which the project may rely on to carry out its activities.
People purchase greater amounts of livestock (beyond carrying capacity) | Low | The project will promote increased community sensitization and raise knowledge and skills towards sustainable natural resources management. Communities will better understand the impact of livestock on their environment. Alternative sources of income will be promoted.
Outsiders bring in additional livestock | Low | Communities will better understand the impact of livestock on their environment and will attach a monetary value to the use of protected areas. This will counterbalance the interest of outsiders to bring in additional livestock.
People cut down planted trees for fuel wood (other than community forest) | Low | Community land ownership (and this protection) as well as and access to alternative sources of income will reduce this risk. In addition, Moreover Government' strategy of promoting natural gas over fuel wood in urban centres,which are the most important market for fuel wood in rural areas, will significantly contribute in reducing risks.
Natural disasters, in particular drought | Medium | As a matter of routine, WFP prepares contingency plans in close collaboration with Government to detect and address risks early on.
Lack of complementary projects and inputs | Low | The project falls fully within Government strategies and related donor strategies. The project advisory group will involve all relevant partners and stakeholders.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Changes in regional project focal points (DREDD) | Medium | Since the inception, 2 changes have occurred in the DREDD position as project focal points at the regional level. One in the beginning of The first change occurred at project start and has no impact on project progress because only one region / Wilaya was affected. The second change happened in August 2015 whereas 6 out of the 8 regions the project intervene were concerned. where the project works. This change has disturbed Consequently, the normal project implementation progress will be affected as the new focal points (DREDD) need to familiarize with the project sites and establish contacts with concerned communities.
Use of Food for work tool | Overcome | The tendering process for purchasing food took a long time to be finalized thus implying delays on food distribution and frustrating communities involved in the Food For Assets activities. WFP and The Ministry of Environment agreed to switch to cash transfer tool which is most indicated in the context of the project.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Rating 1 (hidden)
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1 Eight DREDD (regional technical services of MEDD) strengthened to access and analyse climate change information, to monitor local development and to mobilise and support communities |  | DREDDs, Regional technical services and NGO has participated in programmed training sessions |  | - 2 training sessions organised in collaboration with GIZ's ACCMR project, for DREDDs and Regional technical services on Climate Change's scientific basics and the approach of Integrating Adaptation to Climate Change into Development planning. (80 participants). - 2 training sessions organized for 60 NGO representatives on the scientific basis of climate change, identification and operationalization of the implementation of adaptation measures. These trainings used the latest information regarding climate change projections in Mauritania produced by the ONM (Office National de Météorologie). | S
| Output 1.2 Strengthening of Government's threat, risk and vulnerability analysis | Output 1.2 Strengthening of Government's threat, risk and vulnerability analysis | Most important vulnerable sectors consider Climate Change risks in their Strategies/programs/projects |  | One training Session organised for 50 High level Government representatives from most vulnerable sectors on the Approch of integrating Adaptation to Climate Change into development planning. Concrete work of integrating ACC into sectoral strategies have been initiated for fishing and heath sectors. This training is a contribution to the NAP process initiated by the Mauritanian Govt in collaboration with other financial and technical partners (GIZ, PNUD, ...) in order to ensure integration of adaptation to climate change into strategic plannig. Information regarding climate change projections in Mauritania used in this training have been produced by the ONM (Office National de Météorologie). | S
| Output 1.3: 20 inter-village associations established and supported | Output 1.3: 20 inter-village associations established and supported | Associations established in all targeted projetc areas |  | Most of villages have their organisation structures. The project plaied the role of reactivating some of them which were not really dynamic. Some project area have AGLC association type implemented by ProGRN project in the Wilaya of Hodh El Gharbi and Guidimùakha. Some Difficulties remain in establishing inter-village associations particularly due to social, ethnic issues and also distance between villages. This work requires a lot of time and resources in order to achieve it (i.e. ProGRN experience). The project will continue supporting this consolidation process during the project implementation period as these structures will ensure the sustainability of activities to be undertaken within the framework of the project.
| Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | All communities participated in initial training sessions |  | Initial awareness sessions were organized by DREDD to targeted communities to inform them about risks of climate change on their food security and threats on their livelihoods focusing on the need to be prepared to face this type of difficulties through developping adaptation startegies.
| Output 1.5:100 villages, being clustered according to landscape, ecosystem and livelihoods, have prepared adaptation plans that are integrated into local development planning. | Output 1.5:100 villages, being clustered according to landscape, ecosystem and livelihoods, have prepared adaptation plans that are integrated into local development planning. | Adaptation action plans prepared |  | All targeted sites of the project prepared their adaptation to climate change action plans through a participatory approach involving communities and regional technical services who benefited from the training on the methodology of adaptation to climate change plannaing at local level. These ACC actions plans are Dynamic and will be revised regularly in order to adjust the adaptation measures identified according to constraints that could face the implementation of activities. The ACC action plans have been submettid to regional authorities in order to integrate them into local development, particularly Community Development Plans which are under study in many regions. The project is following up this question with DREDD in order to ensure the integration.
| Output 1.6: Comunities share success stories and lessons learned, including support of 8 community radios | Output 1.6: Comunities share success stories and lessons learned, including support of 8 community radios | CR Feasability study developpend |  | As
| Output 1.7: Monitoring system in place (establishment, training, production of data and reports) to track climate events and ecologic development in project intervention zones. | Output 1.7: Monitoring system in place (establishment, training, production of data and reports) to track climate events and ecologic development in project intervention zones. | Monitoring System in place |  | MEDD developped and put online with the support of GIZ's Pro GRN Project the SEPANE (Monitoring and Evaluation System for The Environment National Action Plan 2) in February 2014. The SEPANE is a web based application (http://www.medd-sepane.mr/sepane/app/accueil.php ) but not yet operationnal. The project will play a key role to contribute in the operationalization of the M&E system in project intervention zones. Discussions with the concerned department are under way to study how to implement the operationalization.
| Output 2.1: 1500 - 2000 ha of sand dunes fixated | Output 2.1: 1500 - 2000 ha of sand dunes fixated | 400 ha of sand dunes fixed
| Output 2.2: 1000 - 1500 ha of vulnerable zones protected | Output 2.2: 1000 - 1500 ha of vulnerable zones protected
| Output 2.3 1,000-1,500 ha of community fuel wood forests planted. | Output 2.3 1,000-1,500 ha of community fuel wood forests planted. | n/a
| 2.4 Water retention structures built covering apporximately 500 ha | 2.4 Water retention structures built covering apporximately 500 ha | n/a
| Output 3.1 300,000 trees for revenue generation and food planted in protected areas | Output 3.1 300,000 trees for revenue generation and food planted in protected areas | n/a
| Output 3.2 4,000 technical staff and community leaders trained in livestock management, agricultural techniques and water utilisation | Output 3.2 4,000 technical staff and community leaders trained in livestock management, agricultural techniques and water utilisation | n/a
| Output 3.3 5,000 technical staff and community leaders trained and equipped agro-pastroal IGA, including plant multiplication | Output 3.3 5,000 technical staff and community leaders trained and equipped agro-pastroal IGA, including plant multiplication | n/a
| Output 3.4 6,000 technical staff and community leaders trained and equipped for poultry development | Output 3.4 6,000 technical staff and community leaders trained and equipped for poultry development | n/a
| Output 3.5 1,000 technical staff and community leaders trained and equipped for apiculture | Output 3.5 1,000 technical staff and community leaders trained and equipped for apiculture | n/a
| Output 3.6 Approx 20 community cereal banks established. | Output 3.6 Approx 20 community cereal banks established. | n/a
| Output 3.7 30,000 fuel efficient stoves built | Output 3.7 30,000 fuel efficient stoves built | n/a
| Output 3.8 2,000 community members (mainly youth) trained and equipped to build and maintain fuel efficient stoves | Output 3.8 2,000 community members (mainly youth) trained and equipped to build and maintain fuel efficient stoves | n/a
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | PMU fully staffed and operational (first quarter from project start) |  | PMU fully staffed and operational (first quarter from project start) |  | Progress is moderate - The project regional focal points are designated (DREDD) according to schedule - Drivers for PMU and DREDD, hired 6 months after project start - Project Coordinator Assistant appointed according to schedule - WFP Project Admin/Fin assistant hired according to schedule - MEDD Finance assistant designated according to schedule Remains only the hiring of the M&E specialist who will join the project team on October 2015. The hiring process managed by an independent committee took more time than planned. The hiring process for the M&E specialist completed by an independent committee took more time than planned. And the M&E specialist will join the PMU in October 2015. Project vehicles arrived 7 months after project start. | MS
| Guideline for project intervention area prioritization completed and applied. | Output 1.2 Strengthening of Government's threat, risk and vulnerability analysis | Guideline for project intervention area prioritization completed and applied. |  | Completed and applied in the 8 regions | S
| Capacity development of government technical services (Central and Regional level) and implementing partners, on climate change issues and integrating Adaptation to climate change into development Planning completed | Output 1.3: 20 inter-village associations established and supported | Capacity development of government technical services (Central and Regional level) and implementing partners, on climate change issues and integrating Adaptation to Climate change into development Planning completed | Output 1.3: 20 inter-village associations established and supported | All planned training sessions for the different targeted groups, have been completed on time. | S
| Communities are sensitized about the adverse effects of CC and its impacts on food security |  | Communities are sensitized about the adverse effects of CC and its impacts on food security |  | Awareness raising visits/sessions have been organized in most project sites inform people about threats of adverse effects of CC on natural resources, livelihoods and food security. These efforts have continued during the elaboration of adaptation action plans with communities. | MS
| Village cluster organizations established | Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | Village cluster organizations established | Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | Most of our targeted sites/villages have organizational structures. Some of these structures were either dormant or not as dynamic; and the project helped in reactivating them before activities are launched. AGLC association type implemented by ProGRN project in the Wilaya of Hodh El Gharbi and Guidimakha are better organizational structures but they are costly and may take time to develop. The project played the role of reactivating some of them which were not really dynamic. Some project area have AGLC association type implemented by ProGRN project in the Wilaya of Hodh El Gharbi and Guidimakha. Some Difficulties remain in establishing inter-village associations particularly due to social, and land property issues and also distance between villages. This work requires a lot of time and resources in order to achieve it (i.e. ProGRN experience). The project will continue supporting this consolidation process during the project implementation period as these structures will ensure the sustainability of activities to be undertaken within the framework of the project. | MU
| Adaptation to Climate Change action plans prepared |  | Adaptation to Climate Change action plans prepared |  | Most targeted sites of the project prepared their adaptation to climate change action plans through a participatory approach involving communities and regional technical services which benefited from the capacity building programme on integrating adaptation to climate change into local planning. | S
| Adaptation measures implementation initiated in the project area |  | Adaptation measures implementation initiated in the project area |  | Dune fixation activity initiated in more than 50 project sites covering about 400 ha out of 1500 ha as objective for the project period. | S
| Project baseline study completed |  | Project baseline study completed |  | Project baseline study completed with some delay due to difficulties in collecting survey data. 100 villages in 8 different regions. This survey was delayed during the month of Ramadan (fasting) and difficult field conditions. | MS
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Ghazi GADER
| Email: | ghazi.gader@wfp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Overall, progress is on track to achieve most of the results during the reporting year even though there were delays on project vehicles procurement and the establishment of the project team. The results obtained were : . the implementation of a capacity building programme for different project partners at central and regional levels, . the good progress in the development of adaptation to climate change action plans in most project sites, . the initiation of implementing the first adaptation measures identified in the Adaptation action plans (sand dune fixation). However, progress on establishing inter-village associations was marginally satisfactory as it is a process that takes time and resources to be completed (based on the experience of GIZ ProGRN project). To note also, a lack of capacity in the DREDDs in terms of staffing and skills. Therefore the implementation strategy should be improved, relying more on other partners such as NGOs or Small Grant Programme (SGP/GEF). Other projects are operating or preparing their intervention in the same areas as the AF project. Discussions are underway with ProLPRAF (FIDA), PASK II (FIDA) looking for possible synergies in order to make our interventions more effective and efficient in the common project sites.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | PMU fully staffed and operational (first quarter from project start) |  | PMU fully staffed and operational (first quarter from project start) |  | Progress is moderate - National Project Director designated according to schedule - Project regional focal points are designated (DREDD) according to schedule - Drivers for PMU and DREDD were hired 6 months after project start - Project Coordinator Assistant appointed according to schedule - WFP Project Admin/Fin assistant hired according to schedule - MEDD Finance assistant designated according to schedule - Project vehicles arrived 7 months after project start. This delayed has greatly affected the field work. Remains only the hiring of the M&E specialist who will join the project team on October 2015. The hiring process for the M&E specialist completed by an independent committee took more time than planned. And the M&E specialist will join the PMU in October 2015. | MS
| Guideline for project intervention area prioritization completed and applied. | Output 1.2 Strengthening of Government's threat, risk and vulnerability analysis | Guideline for project intervention area prioritization completed and applied. |  | The guideline was developed to help prioritize project intervention areas using criteria which will identify the most vulnerable municipalities. Criteria include: . Degree of food insecurity calculated from the WFP FSMS survey, . Degree of exposure to extreme climate events during the last 30 years (drought, flooding, strong wind); . Other projects intervening in the same area, to evaluate the degree of complementarity with AF project. This guideline has been applied in a context of regional participatory workshops involving all the project partners (local authorities, technical services, civil society and communities representatives). | S
| Capacity development of government technical services (Central and Regional level) and implementing partners, on climate change issues and integrating Adaptation to climate change into development Planning completed | Output 1.3: 20 inter-village associations established and supported | Capacity development of government technical services (Central and Regional level) and implementing partners, on climate change issues and integrating Adaptation to Climate change into development Planning completed | Output 1.3: 20 inter-village associations established and supported | - 2 training sessions organized in collaboration with GIZ's ACCMR project, for DREDDs and Regional technical services on Climate Change's scientific basics and the approach of Integrating Adaptation to Climate Change into Development planning. (80 participants). - 2 training sessions organized for 60 NGO representatives on the scientific basics of climate change, identification and operationalization of the implementation of adaptation measures. - One training Session organized for 35 High level Government representatives from most vulnerable sectors on the Approach of integrating Adaptation to Climate Change into development planning. Concrete work of integrating ACC into sectoral strategies have been initiated for fishing and heath sectors. This training is a contribution to the NAP process initiated by the Mauritanian Govt in collaboration with other financial and technical partners (GIZ, PNUD, ...) in order to ensure integration of adaptation to climate change into strategic planning. These trainings used the latest information regarding climate change projections in Mauritania produced by the ONM (Office National de Météorologie). | S
| Communities are sensitized about the adverse effects of CC and its impacts on food security |  | Communities are sensitized about the adverse effects of CC and its impacts on food security |  | Awareness raising visits/sessions have been organized in most project sites about threats of adverse effects of CC on natural resources, livelihoods and food security. These efforts have continued during the elaboration of adaptation action plans with communities. | MS
| Village cluster organizations established | Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | Village cluster organizations established | Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | Most of villages have their organization structures. The project played the role of reactivating some of them which were not really dynamic. Some project area have AGLC association type implemented by ProGRN project in the Wilaya of Hodh El Gharbi and Guidimakha.Most of our targeted sites/villages have organizational structures. Some of these structures were either dormant or not as dynamic; and the project helped in reactivating them before activities are launched. AGLC association type implemented by ProGRN project in the Wilaya of Hodh El Gharbi and Guidimakha are better organizational structures but they are costly and may take time to develop . Some Difficulties remain in establishing inter-village associations particularly due to social, and land property issues and also distance between villages. This work requires a lot of time and resources in order to achieve it (i.e. ProGRN experience). The project will continue supporting this consolidation process during the project implementation period as these structures will ensure the sustainability of activities to be undertaken within the framework of the project. | MU
| Adaptation to Climate Change action plans prepared |  | Adaptation to Climate Change action plans prepared |  | Most targeted sites of the project prepared their adaptation to climate change action plans through a participatory approach involving communities and regional technical services who benefited from the training on the methodology of adaptation to climate change planning at local level. These ACC actions plans are dynamic and will be revised regularly in order to adjust the adaptation measures identified according to constraints that could face the implementation of activities. The ACC action plans have been submitted to regional authorities in order to integrate them into local development, particularly Community Development Plans which are under study in many regions. The project is following up this question with DREDD in order to ensure the integration. | S
| Adaptation measures implementation initiated in the project area |  | Adaptation measures implementation initiated in the project area |  | Dune fixation activity initiated in more than 50 project sites covering about 400 ha out of 1500 ha as objective for the project period. This activity was preceded by the establishment of 58 forest plant nurseries which produced, after evaluation, 161 309 plants. | S
| Project baseline study completed |  | Project baseline study completed |  | Project baseline study completed with some delay due to difficulties in collecting survey data. 100 villages in 8 different regions. This survey was delayed during the month of Ramadan (fasting) and difficult field conditions. | MS
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Moise Ballo, WFP Deputy Country Director, Ghazi GADER, Project Coordinator
| Email: | moise.ballo@wfp.og, | ghazi.gader@wfp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | In its first year of implementation, the project has managed to achieve the following main activities: - Conduct a participatory consultation process that led to prioritize the project areas, - Rely on CREDD as a concertation framework on environmental issues at regional level, to validate the choice of the project areas, - Establish regional technical committees involving main project partners for the technical supervision of project implementation, - Strengthen DREDDs with equipments (vehicles, ITC) and office furniture, allowing them to carry out project tasks in the best conditions, - Implement a capacity building program for DREDD and regional technical services on climate change and integration of Climate Change Adaptation into local planning, - Strengthen the capacity of implementing partners (NGOs) in the field of CC and technical issues related to implementation of adaptation measures, - Strengthen the capacity of the project partners at the central level in the field of Climate change and the integration of CCA into strategic development planning, - Initiate and finalize the development of adaptation to climate change action plans in most project sites, - Initiate the implementation of concrete adaptation measures for combatting desertification (dune fixation) - Carry out the project baseline study for monitoring the achievement of the objectives/outcomes of the project. Major difficulties faced in this reporting period: Some Difficulties remain in establishing inter-village associations particularly due to social, and land property issues and also distance between villages. This work requires a lot of time and resources in order to achieve it (i.e. ProGRN experience). The project will continue supporting this consolidation process during the project implementation period as these structures will ensure the sustainability of activities to be undertaken within the framework of the project. However, the project is working with legal communities' representations (Village Associations, Village Committees, Women cooperatives, etc.). The project did not start working with NGOs as implementing partners because MEDD asked to be more cautious in doing so arguing about previous bad experiences with some NGOs. The PMU will very soon launch consultations with NGOs in all 8 Wilayas to help in carrying out its activities in the second year. It's experience with other projects is not very good and wanted to study more in detail this issue before engaging NGOs. One critical risk should be noted is that DREDD are civil servants and are subject to job promotion or permutation and that usually affect the project progress implementation. Newly affected DREDD have to familiarize themselves with the project sites and activities within the region which take time and resources to achieve ; leading to potential delays in project implementation. These problems will be discussed in the next Project Steering Committee meeting in order to foresee sustainable solutions. This first year reporting period, has raised up a very critical risk related to the food for work tool. The establishment of nursery and plantation activities for sand dune fixation are remunerated under FFA tool. Despite the very early planning of food purchase, we registered a very long delay in the tendering process and this is linked to the low quantities required by the project and food distribution was delayed consequently implying frustration among communities. WFP and MEDD decided to use the cash transfer tool which will be more indicated to overcome this problem and keep a normal rhythm of project execution.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
OBJECTIVE 1: Enhanced understanding, skills and means of decentralized government and communities for leading and facilitating participatory adaptation planning | Number of community adaptation plans prepared through participative local planning supported with information and facilitation by DREDD | No adaptation plans exist in intervention zones | 85 villages prepared their ACC action plan with the support of DREDD and Regional technical services including civil society. This work is a result of the improvement of DREDD and project partners' skills on Climate change issues and integrating ACC into local development approach. | 20 clusters of villages have established adaption plans in a participatory manner
Outcome 1.1: Strengthened awareness, ownership and facilitation capacities of government services (DREDD) | DREDD have played an active and supportive role in the mobilization, organization and implementation of inter-village adaption planning processes | DREDD do not have capacity to provide any support to communities | DREDD led and facilitated the elaboration of ACC action plans in the project area. | DREDD have succeeded to provide information, guidance and facilitation support to 20 village clusters
Output 1.1: Technical services strengthened to access and analyze climate change information, food security, livelihoods and vulnerability information, and to monitor local development, and mobilize and support communities. | DREDD have been trained, have communicated with department and local level, have visited communities, have facilitated village cluster establishment and discussions | DREDD do not visit communities and do not provide information, support, guidance or facilitate processes | - 2 training sessions organized in collaboration with GIZ's ACCMR project, for DREDDs and Regional technical services on Climate Change basics and the approach of Integrating Adaptation to Climate Change into Development planning. (80 participants). This training was followed by a practical exercise in one selected project site to implement the methodology in a real case with the active participation of the communities. - Many visits have been organized by DREDD in all project sites to sensitize communities on project objectives, implication of climate change impacts on natural resources, livelihoods and food security and the necessity to adapt to CC. - DREDDs organized discussions with communities to reactivate village committee/Associations as legal representatives of communities with the project. | DREDDs have regular contact and trustful relationship with village clusters and communities that value their support
Output 1.2: Strengthening of Government’s threat, risk and vulnerability analysis capabilities by expanding current Vulnerability and Analysis methodologies to overlay climate threats and monitoring changes in landscapes using GIS technologies. | Preparation and communication to regional level of up-to-date and reliable information and analysis of climate change information and of government priorities | DREDD hardly receive any guidance, information and analysis from central level | One training Session organized for 35 High level Government representatives from most vulnerable sectors on the Approach of integrating Adaptation to Climate Change into development planning. Concrete work of integrating ACC into sectoral strategies have been initiated in fishing and health sectors. This training is a contribution to the NAP process initiated by the Mauritanian Govt in collaboration with other financial and technical partners (GIZ, PNUD, ...) in order to ensure integration of adaptation to climate change into strategic planning. | Regular communications between central level and DREDD provide up-to date information and guidance, adapted to the capacity at regional level
Outcome 1.2: Strengthened awareness, ownership, planning and management capacities at community level for local natural resource management and climate change adaptation | Communities and their relevant sub-groups (e.g. women, livelihood groups, etc.) have actively participated in the preparation of the inter-village adaptation plans prepared and see their interests adequately reflected. | There is only little joint discussion at community level, and not all groups are involved; no inter-village discussions take place | In all sites where adaptation action plans have been elaborated, communities have played a great role and actively participated to all steps of the process till the identification and prioritization of adaptation options. | About 100 villages in 20 village clusters understand, own and manage their adaption plans and their natural resources
Output 1.3: 20 inter-village associations established and supported. | Inter-village associations exist and are active in on form or the other in each of 20 targeted clusters | In some clusters, some form of cooperation structure may exist, on which the project can build. | Most of villages have their organization structures. The project played the role in reactivating some of them which were not really dynamic. Some project area have AGLC association type implemented by ProGRN project in the Wilaya of Hodh El Gharbi and Guidimakha. | 20 inter-village associations with a role in managing natural resources and adaptation plans recognized by population and DREDD
Output 1.4: Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity. | Number of people (gender-disaggregated) and communities trained | Communities are aware of degrading natural resources, but rarely of context, causes and adaptation options | Communities of 100 villages targeted by the project have participated to awareness raising visits/sessions organized about threats of adverse effects of CC on natural resources, livelihoods and food security. | Communities have the capacity to analyze and understand their situation, and adaptation options
Output 1.5: 100 villages, being clustered according to landscape, ecosystem and livelihoods, have prepared adaptation plans that are integrated into local development planning. Identification of adaptation technology requirements such as integrated livestock water and cropping systems. | 20 village cluster adaptation plans developed in a participatory way and officially recognized by DREDD | Communities and village associations do not prepare comprehensive adaptation plans | 84 Villages have developed adaptation action plans in a participatory way leaded by DREDD with the participation of relevant regional technical services and civil society. | Adaptation plans include analysis, discussion of options, decision on priorities and analysis of implications (costs, maintenance)
| Specific studies on adaptation technology requirements are available at the relevant levels | A number of ad hoc studies exist within several projects, but are not systematically made available | n/a | Studies on technology for 3-4 “standard” adaptation assets are available to all partners and stakeholders
Output 1.6: Communities share success stories and lessons learned, including support of community radios focused specifically on sharing information on early warning and adaptation management. | Community radios are on air, involving communities in programming and feed-back | Communities of 15 sites in the project area have already listen regularly to radio transmissions on a radius ranging from 6 to 70 km. | Community radios (Local Radio) were already established by the Government in all Wilayas including the 8 wilayas targeted by the project. They have been associated to all workshops and trainings organized in the regional level and they were sensitized to the project objectives. Therefore, discussions are still underway with some partners for the best strategy to make these CR playing a real role in sharing information on EWS and successful adaptation experiences. | CR are on air, have strong volunteer involvement and a sustainability strategy
Outcome 1.3: National ecologic monitoring system strengthened and tested | Participating communities and government services have provided quality, timely and reliable ecologic monitoring reports aligned with the national monitoring system | The ecologic monitoring system is established as part of PANE II System and set online in February 2014. | n/a | The new national ecologic monitoring system is known, used and maintained by DREED and in project village clusters.
Output 1.7: Monitoring system in place (training, production of data and reports) to track climate events and ecologic development in project intervention zones. | Number of people trained at regional and village cluster level; amount and quality of data provided by village clusters / regional teams | There is no systematic collection, consolidation and analysis of data on nationally agreed-upon indicators. | n/a | Participating DREDD and village clusters provide data on agreed-upon indicators; and receive, understand and use reports.
OBJECTIVE 2: Design and implement concrete adaptation measures identified through community adaptation planning that aim to combat desertification, soil erosion and land degradation | Number of implemented community adaptation plan action aiming to combat desertification, soil erosion and land degradation | No comprehensive community (cluster) adaptation plans exist in the intervention zones to be selected. | n/a | 20 comprehensive adaptation plans have been implemented with respect to combat desertification, soil erosion and land degradation.
Outcome 2.1: Advance of sand dunes slowed down, halted or reversed | Reduced, halted or reversed dune advance in participating communities | 749 ha of dunes fixed in the project intervention area | n/a | Significant deceleration – and ideally reversal – of dune advance
Output 2.1: 1,500-2,000 ha of dunes fixated. | Plants – and other measures – have stopped advance of dunes | Sand dune fixation does take place as part of several projects, but hardly in the zones to be selected. | 400 ha have been planted in 58 project sites. | Communities have fixated dunes and have a clear plan for maintaining / reinforcing fixation
Outcome 2.2: Increased vegetation cover in intervention zones | Increased Vegetation Cover Index in participating communities | The average density of vegetation is 67 plants per hectare in the project sites | n/a | Increase of the average density per hectare by at least 10% in the participating village clusters until the end of the project with clear prospect of further increases)
Output 2.2: 1,000-1,500 ha of vulnerable zones protected. | Area of land protected from against uncontrolled grazing and bush fires | There will only be sporadic protected areas in selected village clusters | 400 ha have been planned to be protected in the first year. Identification was already done in collaboration of communities. Agreement between Communities, local Authorities and DREDD have to be concluded before the implementation. | 1,000 – 1,500 ha of land protected and encompassed by sustainable management plan
Output 2.3: 1,000-1,500 ha of community fuel wood forests planted. | Area of land planted and controlled for fuel wood production; volume of produced fuel wood | There is hardly any controlled fuel wood plantation in areas to be selected | n/a | Participating communities cover at least 50% of their fuel wood requirements from controlled wood production
Outcome 2.3: Decreased loss of water and soil through surface run-off | Increased surface and sub-soil water availability | There are only 13 sites with water retention structures functioning in areas to be selected | n/a | Area where days of water availability has increased with at least 20%
Output 2.4: Water retention structures built covering approx. 500 ha. | Number, kind, surface size and volume (where applicable) of water retention structures | 13 sites have dams, check dams, Soil and water conservation structures, Soil restoration structures | n/a | Communities construct and maintain retention assets according to plan
OBJECTIVE 3 Design and implement concrete adaptation measures identified through community adaptation planning that aim to diversify and strengthen the livelihoods of the most vulnerable population | Number and type of implemented community adaptation plan action aiming to diversify and strengthen the livelihoods of the most vulnerable population | No adaptation plans are in place, livelihood bases are hardly diversified in areas to be selected | n/a | Communities have implemented adaptation plan action and continue to gain sustainable income from new sources
Outcome 3.1: Increased number of sources of income for participating households | Number and type of sources of income for participating households before and after the project | Livelihood bases are hardly diversified in areas to be selected – specific baselines to be established as part of adaptation plan preparation (The communities practice seven (7) income generating activities including 04 based on the exploitation of natural resources (agriculture, livestock, fishing and fruit picking) | n/a | At least 25% of village cluster population have widened their livelihood bases with new sources of income
Outcome 3.2: Increased income for participating households | Level of income for participating households before and after the project | Participating households are among the poorest in the selected areas. | n/a | Participating households have increased their revenues by at least 40%
Outcome 3.3: Increased availability of and access to food for participating communities | Food gap (number of weeks/months) for participating households before and after the project | Participating households have the greatest food gap in the selected areas. (The number of food deficit months range from 1 to 10) | n/a | Participating households have decreased their food gap by at least 50%
Output 3.1: Approx. 300,000 trees for revenue generation and food planted in protected areas. | Number of trees planted and growing in protected areas; amount of food and revenue gained from these. | Baseline to be established as part of adaptation plan | n/a | Planted trees already are – or have at least a clear prospect of – providing substantial amounts of food and income
Output 3.2: 4,000 technical staff and community leaders trained in livestock management, agricultural techniques and water utilization. | Number of people (gender disaggregated) trained | Hardly any training is available in areas to be selected; extension staff requires training, too | n/a | Extension staff and cluster population are aware of and apply appropriate techniques
Output 3.3: 5,000 technical staff and community leaders trained and equipped for plant/seed multiplication. | Number of people (gender disaggregated) trained | Hardly any training is available in areas to be selected; extension staff requires training, too | n/a | Extension staff and cluster population are aware of and apply appropriate techniques
Output 3.4: 4,000 technical staff and community leaders trained and equipped for poultry development. | Number of people (gender disaggregated) trained | Hardly any training is available in areas to be selected; extension staff requires training, too | n/a | Extension staff and cluster population are aware of and apply appropriate techniques
Output 3.5: 1,600 technical staff and community leaders trained and equipped for apiculture. | Number of people (gender disaggregated) trained | Hardly any training is available in areas to be selected; extension staff requires training, too | n/a | Extension staff and cluster population are aware of and apply appropriate techniques
Output 3.6: Approx. 20 community cereal banks established. | Number of functioning village cereal bank associations; volume of cereals and money in bank. | No village-owned cereal banks exist in areas to be selected | n/a | Participating communities own their VCB, membership, money and food held by associations is stable
Output 3.7: 30,000 fuel efficient stoves provided. | Number of fuel efficient stoves built by participating communities; share of reduced consumption of fuel wood | Fuel-efficient stoves are hardly know and available in areas to be selected – to be confirmed during adaptation planning (The communities of ten villages already use improved stoves) | n/a | Communities know, understand and use fuel efficient stoves; fuel-wood consumption by participating households reduced by at least 40%
Output 3.8: 2,000 community members (mostly youth) trained to build and maintain fuel efficient stoves. | Number of people (gender-disaggregated) trained | No training is available in areas to be selected; extension staff requires training, too. 14 artisans are already trained to manufacture improved stoves) | n/a | In all participating communities a group of people regularly builds and repairs fuel-efficient stoves;

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The lesson learned that we can point out during this reporting period is the inter-sectoral participation in developing local adaptation to climate change action plans. Knowing that climate change is a transversal issue, the key success factors to elaborate and implement adaptation planning are tied to the close collaboration and participation of all sectoral institutions at the regional level, thus capacity building programme in integrating adaptation to climate change into local development planning has concerned not only DREDD, but also decentralized technical services and NGO at regional level.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The tendering process for purchasing food took a long time to be finalized and this imply delays on food distribution which raised up a frustration among communities involved in some Food For Assets activities. WFP and The Ministry of Environment and Sustainable Development agreed to switch to cash transfer tool which is most indicated in the context of the project. DREDD are civil servants and are subject to job promotion or permutation and that usually affect the project progress implementation. Newly affected DREDD have to familiarize themselves with the project sites and activities within the region which take time and resources to achieve ; leading to potential delays in project implementation. These problems will be discussed in the next Project Steering Committee meeting in order to foresee sustainable solutions.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The Output 1.6 : 'Communities share success stories and lessons learned, including the establishment and support of 4 community radios' title has been changed as follows : 'Communities share success stories and lessons learned, including support of community radios' - The project design previewed initially the establishment and the support of 4 local Community Radio (CR). Out of local consultations with MEDD and the project stakeholders it has resulted that these community radios were already established by the Government in all regions or wilayas including the 8 wilayas targeted by the project. Therefore, it has been suggested to carry out a study to assess the needs on capacity development, support and equipments necessary to help extend the broadcast area of these local existing community radios. Output 1.7: Monitoring system in place (establishment, training, production of data and reports) to track climate events and ecologic development in project intervention zones. : The title of Output 1.7 has been changed erasing the word 'establishment' : MEDD with the support of GIZ, have developed in the last 2 years a National M&E system called SEPANE. The SEPANE is a web based application for the MEDD and operating since June 2014. National and regional MEDD services have access to the system and had begun already feeding data into the system. Therefore, recommendations are that we no longer need to hire an international M&E specialist. A national M&E specialist will be sufficient to work on collecting, introducing (feeding) and analyzing data from the project location areas into SEPANE. He will also contribute on the establishment of the Monitoring and Evaluation system for the AF project.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender considerations have been taken into consideration during the elaboration of participatory adaptation action planning. Indeed, special attention was given to the identification of adaptation options considering the gender aspect.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | MTN/MIE/Food/2011/1/PD
Implementing Entity | WFP, Mauritania
Type of implementing entity | MIE
Country | Mauritania
Region | Africa
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 186718 | 37368 | 149350 | Total | 160590 | 23670 | 136920 | Total |  |  |  | Total
|  | % of female beneficiaries | 59.15% |  |  | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 43.6% |  |  | % of Youth beneficiaries | 8% | 8% | 8% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Regional | 1 | 3: Dissemination and communication | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 75 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 300 | Multi-sector | 1: No capacity | Total | 300 | Multi-sector | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 10% |  |  | % of female targeted | 10% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 180 | 10% | Public |  | 180 | 10% | Public
|  | 120 | 10% | NGO |  | 120 | 10% | NGO
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 1: No capacity | Public | National | Multi-sector | 3: Medium capacity
|  | Public | Regional | Multi-sector | 1: No capacity | Public | Regional | Multi-sector | 3: Medium capacity
|  | NGO | Regional | Multi-sector | 1: No capacity | NGO | Regional | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Other | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Other | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 1500 | ha protected | 1: Ineffective | Rangelands | 1500 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 500 | ha protected | 1: Ineffective | Catchment area/Watershed/Aquifer | 500 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1500 | ha protected | 1: Ineffective | Forests | 1500 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 1000 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 1000 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 2000 | ha protected | 1: Ineffective | Other | 2000 | ha protected | 4: Effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 16983 | Agricultural-related |  | 356.2333 |  | Agricultural-related
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 72 | Fishing |  | 775.7767 |  | Fishing
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 688 | Forestry |  | 372.36 |  | Forestry
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 15069 | Livestock production |  | 1115.2 |  | Livestock production
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 3090 | Services |  | 1563.3067 |  | Services
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.

## Financial annex
Explanatory notes on variances between planned and actual expenditures of outputs during the reporting period
ITEM / ACTIVITY / ACTION | Year 1 Actual amount spent US$ | Projected in Prodoc (US$) | Difference (negative amount indicates amount overspent) | Reason for over or underspending
A general reason to the low rate of expenditure during the first reporting year is related to the delay in the effective project start.
Output 1.1 Eight DREDD (regional technical services of MEDD) strengthened to access and analyze climate change information, to monitor local development and to mobilize and support communities | 259268.3241 | 544441.6667 | 285173.3425 | The project did not start working with NGOs as implementing partners because MEDD asked to be more cautious in doing so arguing about previous bad experiences with some NGOs. It was agreed to launch the hiring process of NGOs in the second year as implementing partners of the project. The international consultant who ensured the training organized for DREDD and regional technical services was hired by ACCMR GIZ project. This resulted in savings in the planned budget. The project saved a substantial amount on procurement of 10 project vehicles (about 67 000 USD). 8 vehicles are planned under Output 1.1, one vehicle under 1.2 (CCPNCC) and one vehicle under EE project execution costs.
Output 1.2 Strengthening of Government's threat, risk and vulnerability analysis | 51042.4101 | 100073.3333 | 49030.9232 | The project saved budget on the procurement of CCPNCC vehicle (see output 1.1) as well on budget for training of project partners at the central level. The technical study on climate services was reported to more coordinate with AMCC project (PNUD/GIZ/EU) which is working on the same topic. The 2 projects agreed to study the opportunity to collaborate on this issue.
Output 1.3: 20 inter-village associations established and supported | 7493.3333 | 32000 | 24506.6667 | Due to the delay in the effective project start, this activity which was planned to be totally achieved in the first year have to be continued in order to more support the village associations as main project partners.
Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | 11792.8453 | 33590 | 21797.1547 | Only awareness raising visits/sessions have been organized about threats of adverse effects of CC on natural resources, livelihoods and food security. NGO trained by the project will play a important role to continue this effort.
Output 1.5:100 villages, being clustered according to landscape, ecosystem and livelihoods, have prepared adaptation plans that are integrated into local development planning. | 13430.2445 | 38000 | 24569.7555 | The elaboration of Adaptation to climate change action plans in the project villages have been conducted internally by DREDD with the support of Regional technical services and NGO. This resulted in savings in the planned budget. As the adaptation plans are dynamic, revisions could be conducted to update some of them where necessary.
Output 1.6: Communities share success stories and lessons learned, including support of 8 community radios | 0 | 3750 | 3750 | The feasibility study on community radios was reported. Discussion with the Small Grant Programme (SGP) are underway to capitalize on successful similar experiences in Mauritania or within the region.
Output 1.7: Monitoring system in place (establishment, training, production of data and reports) to track climate events and ecologic development in project intervention zones. | 0 | 27000 | 27000 | The hiring process for the M&E specialist conducted by an independent committee took more time than planned. He will join the PMU in October 2015.
Output 2.1: 1500 - 2000 ha of sand dunes fixated | 360663.2855 | 296400 | -64263.2855 | The budget was under estimated. This activity included, beyond plantation and procurement of agricultural material for fencing the planted area against animal grazing, the establishment of about 60 nurseries, the procurement of bags, seeds and small material. These nurseries will continue to be functional for next plantation campaign.
Output 2.2: 1000 - 1500 ha of vulnerable zones protected | 134301.2852 | 265350 | 131048.7148 | This output include two activities : fencing vulnerable zones and establishment of fire breaks. During the reporting period, we only started the procurement of material for fencing 400 ha of vulnerable zones in the 8 Wilayas.
TOTAL | 837991.7281 | 1340605 | 502613.2719 | 62.51%