## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | September 2018 - September 2019
| Project Title: | Enhancing Resilience of Communities to the Adverse effects of Climate Change on Food Security in Mauritania
Effects of Climate Change on Food Security in Mauritania
| Project Summary: | The Mauritania's Ministry of Environment and Sustainable Development and the United Nations World Food Programme initiated a four-year project to strengthen resilience and promote food security in 100 villages located in the Wilayas of Assaba, Brakna, Guidimakha, Gorgol, Hodh El Chergui, Hodh El Gharbi, Tagant and Trarza. The overall goal of the project aims to improve adaptation in the area of food security in Mauritania by assisting the government in improving technical services at the community level so that village residents, who will be most affected by climate change, can undertake their own analysis of climate change impacts and prepare detailed adaptation plans – including harmonized plans for livestock, land and water management and the overall use of natural resources. The project will also promote climate resilience by protecting threatened resources, such as dunes, community fuel wood forests, and water sources. Finally, villages will be encouraged to explore ways to diversify the sources of livelihood and receive training, coaching, and asset investments to do so. The project includes three components: Component 1: Support technical services and the communities they serve to better understand climate risks, their impacts on resources and food security; and facilitate decentralized and participatory adaptation planning. Component 2: Design and implement concrete adaptation measures identified through community adaptation planning that aim to combat desertification and land degradation. Component 3: Design and implement concrete adaptation measures identified through community adaptation planning that aim to diversify and strengthen the livelihoods of the most vulnerable population.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | MTN/MIE/Food/2011/1/PD | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Word Food Programme (WFP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Mauritania | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Wilaya of Assaba (12 villages); Wilaya of Brakna (12 villages); Wilaya of Gorgol (10 villages); Wilaya of Guidimakha (12 villages); Wilaya of Hodh El Chergui (15 villages); Wilaya of Hodh El Gharbi (14 villages); Wilaya of Tagant (9 villages); Wilaya of Trarza (16 villages) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | July 2012
IE-AFB Agreement Signature Date: |  | July 23 2012 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | August 14 2014 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | January 2017
| Terminal Evaluation Date: | July 2019
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Brochure of the project Poster of the Project Guidance note for the prioritization of project areas Project inception report ACC training report for technical regional services - Kaédi 9-12 Mach 2015 ACC training report for technical regional services - Kiffa 6-9 April 2015 ACC training report for NGO, Kaédi et Kiffa 8-12 June 2015 ACC training report for government representatives at central level 7-9 July 2015 Monitoring Project Activities factsheets Project Progress Report 1st semester 2015 Assessment of nurseries' seedlings production 2015 Brochure - Climate Change Adaptation Planning Approach at Community Level Brochure -Review of the first year of project implementation Report of the assessment study on Soil and Water conservation Report of the assessment study of the promotion of poultry farming programme Report of the assessment study of the beekeeping promotion programme Report of the assessement study of the fruit trees promotion programme Report of the Veterinary Auxiliary Training Veterinary Auxiliaries training manuel Assessment of nurseries' seedlings production 2016 | Czech Republic
https://www.youtube.com/watch?v=TJXPh0mQb9c (Reportage sur les réalisation -2016)
https://www.youtube.com/watch?v=NvMot1jn9js&t=25s (Reportage sur les réalisations du projet - 2017)
https://www.wfp.org/stories/building-resilience-and-adaptive-capacity-communities-sahel
https://www.facebook.com/ParsaccMauritania
http://parsacc.yolasite.com/etudes-et-rapports.php
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://parsacc.yolasite.com | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
International Project Manager/Coordinator |  |  | Dominica
| Name: | Ghazi GADER, Project coordinator | Dominican Republic
| Email: | ghazi.gader@wfp.org | Ecuador
| Date: | 14-Agust-2014 | Egypt
| Government DA |  | El Salvador
| Name: | Sidi Mohamed El Wavi, National Project Director | Equatoral Guinea
| Email: | elwavi.sm@gmail.com | Eritrea
| Date: | 14-Agust-2014 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Yasuhiro TSUMURA, WFP Deputy Country Director | Fiji
| Email: | yasuhiro.tsumura@wfp.org | Finland
| Date: | Agust-2016 to July-2018 | France
| Implementing Entity |  | Ethiopia
| Name: | Rainatou BAILLET WFP Deputy Country Director | Fiji
| Email: | rainatou.baillet@wfp.org | Finland
| Date: | July-2018 | France
| Executing Agency |  | Gambia
| Name: | Alioune FALL, Project coordinator Assistant | Georgia
| Email: | lunef@yahoo.com | Germany
| Date: | 14-August-2014 | Ghana
| Executing Agency |  | Greece
| Name: | Maouloud N'Diaye, M&E specialist | Grenada
| Email: | ndiaye.maouloud@gmail.com | Guatemala
| Date: | 2015-10-01 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Amadou SY, Communication consultant | Guyana
| Email: | amd2sy@hotmail.com | Haiti
| Date: | 15-August-2017 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to September 2019
DISBURSEMENT OF AF GRANT FUNDS | 7559447.26
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of March 2020 | 7559447.26
Add any comments on AF Grant Funds. (word limit=200) | The amount of $7,559,447 includes all expenses made by: 1. WFP on behalf of MEDD - Executing Entity: $3,113,672 2. MEDD as executing Entity: $4,145,637 3. Indirect Support Cost: $300,139 Amount unspent: $247 153 TOTAL: $3,113,672 + $4,145,637 + $247,153 + $300,139 = $7,806,601 (includes 7,803,605 received from Adaptation Fund, interest income of $2,972 and Misc. income of $24)
INVESTMENT INCOME | 2972
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1 Eight DREDD (regional technical services of MEDD) strengthened to access and analyze climate change information, to monitor local development and to mobilize and support communities | 376945
| Output 1.2 Strengthening of Government's threat, risk and vulnerability analysis | 18686
| Output 1.3: 20 inter-village associations established and supported | 0
| Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | 0
| Output 1.5:100 villages, being clustered according to landscape, ecosystem and livelihoods, have prepared adaptation plans that are integrated into local development planning. | 0
| Output 1.6: Communities share success stories and lessons learned, including support of 8 community radios | 97123
| Output 1.7: Monitoring system in place (establishment, training, production of data and reports) to track climate events and ecologic development in project intervention zones. | 36101
| Output 2.1: 1500 - 2000 ha of sand dunes fixated | 74116
| Output 2.2: 1000 - 1500 ha of vulnerable zones protected | 7886
| Output 2.3 1,000-1,500 ha of community fuel wood forests planted. | 52076
| 2.4 Water retention structures built covering approximately 500 ha | 55607
| Output 3.1 300,000 trees for revenue generation and food planted in protected areas | 159476
| Output 3.2 4,000 technical staff and community leaders trained in livestock management, agricultural techniques and water utilization | 0
| Output 3.3 5,000 technical staff and community leaders trained and equipped agro-pastoral IGA, including plant multiplication | 590163
| Output 3.4 6,000 technical staff and community leaders trained and equipped for poultry development | 123681
| Output 3.5 1,000 technical staff and community leaders trained and equipped for apiculture | 56386
| Output 3.6 Approx. 20 community cereal banks established. | 0
| Output 3.7 30,000 fuel efficient stoves built | 310014
| Output 3.8 2,000 community members (mainly youth) trained and equipped to build and maintain fuel efficient stoves | 116614
| EE - Project Execution Costs | 230549
| MIE - Project Management Fee | 12585
| TOTAL | 2318008
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
TOTAL
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | The MEDD spent about 173 000 USD in 2015 as co-financing. This amount was used to pay for project support staff salaries, purchase office supplies, furniture and and computer equipment for DREDDs and inspections. It also contributed to the acquisition of horticultural equipment, fencing material and vegetable seeds.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 2016 : WFP CO contributed in 2016 by co-financing 6 months project support staff salaries totalling about 21 000 USD. 2017 : WFP CO through PRRO programme contributed by providing 60 246 USD Cash Transfer to 713 participants (4278 beneficiaries) for FFA activities in 6 villages in the wilaya of Guidimakha and 4 villages in the wilaya of Gorgol. 2017-2018 : WFP CO through PRRO programme contributed by supporting the payment of salaries of the Project Coordinator, the Admin/Fin Assistant and field missions totalling 51 086 USD The cumulative actual co-financing is 305 332 USD.
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | The government's in-kind contribution consists on a space provided as a project office for the PMU at the MEDD headquarters in Nouakchott.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
External factors may delay project implementation | Overcome | The Presidential elections organised in June 2019 has involved all administrative structures at central and regional levels including MEDD services. This has affected the normal progress of project activities. It was the same case with the legislative and regional elections in June 2018. The project tried to rely on NGOs to continue activities implementation in a normal pace but still experienced some delays in finalizing procurement of key services such as the final audit. A no cost extension until September 2019 was necessary to complete all processes.
Communities find it difficult to take up the skills, learning and social cohesion necessary to secure protected areas | Overcome | Communities organized into management committees have simple management and operating rules that help them to maintain the assets created and manage them sustainably. Most of these Committees have created community funds financed throuh incomes generated by the IGAs. these funds are used in particular to cover the renewal of equipment, guarding, maintenance of solar systems, and also to help some members of the community to overcome social problems.
There is little local specialized management and technical capacity related to climate change, particularly in the entities that are responsible for the project. | Overcome | The project has provided valuable support and continuous contribution to increase the Government’s technical capacity related to climate change, not only for DREDDs, but also for relevant technical services at central and regional levels. The NGO hired in 2017 have been also trained to enhance theire capacities on climate change related issues and this contributed to better manage project implementation. The MEDD has also played a great role through the National Coordination Unit on Climate Change which provide regularely trainnings on Climate Change issues for different sectors.
Lack of adequately qualified partners | Overcome | A number of qualified partners with a similar project philosophy as WFP were identified on the ground, and WFP has good experience in working with them. WFP has a good working experience with some adequately qualified partners which the project relyed on to carry out its activities.
People purchase greater amounts of livestock (beyond carrying capacity) | Overcome | The project promoted and strengthened community awareness and improved knowledge and skills for sustainable natural resource management. Other sources of income have been encouraged to limit investment in livestock purchases that contribute to resource degradation.
Outsiders bring in additional livestock | Overcome | Communities now have a better understanding of the impact of livestock on their environment. The pastoral reserves supported by the project now generate a monetary value related to grazing and the sale of straw. They are managed by operating rules that apply to both village herders and those in neighbouring villages who wish to benefit from these reserves.
People cut down planted trees for fuel wood (other than community forest) | Overcome | The promotion of improved stoves has signically reduced using wood for cooking. Also promoting community land ownership and access to alternative sources of income helped in easing significantly that risk. In addition, Government' strategy of promoting natural gas use over fuel wood in urban centres, will significantly contribute in reducing fuel wood demand in rural areas.
Natural disasters, in particular drought | Overcome | As a matter of routine, WFP prepares contingency plans in close collaboration with Government to detect and address risks early on.
Lack of complementary projects and inputs | Overcome | Synergies have been developpend with GIZ ACCMR project and WFP programmes. We also note the synergy between AF project and WFP programmes which has been extended to 2 Wilayas (Guidimakha and Gorgol).
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Changes in regional project focal points (DREDD) | Overcome | Since inception, 05 changes have occurred in the DREDD assignment as project regional focal points. The first change occurred at the beginning of the project and has no impact on the progress of the project as only one region / Wilaya has been affected. The second change occurred in August 2015 with the reassignment of 6 out of 8 DREDDs. The third one took place in August 2017 where 4 changes were made with the reassignment of 3 new DREDDs that have never worked with the project. The 4th change took place in January 2018 where a new DREDD was assigned to Trarza to replace the one who retired. The last one occured in April 2019: Assignment of 3 new DREDDs in Trarza, Gorgol and Tagant who never been involvedd in the project; and the reassignment of the DREDD of Tagant in Hodh El Gharbi. These repetitive changes in DREDD assignment and particularly the last one, which took place a few months before the end of the project, have disrupted the normal progression of project implementation, because every time new assigned DREDDs need to become familiar with the project approach and reach out to the affected communities.
Use of Food for work tool | Overcome | The tendering process for purchasing food took a long time to be finalized thus implying delays on food distribution and frustrating communities involved in the Food For Assets activities. WFP and The Ministry of Environment agreed to combine Food tool with cash transfer tool.
Mobilisation of national counterpart for 2017 - 2018 | Overcome | MEDD did not mobilize the national counterpart for 2016 and 2017 which contributes to the payment of project support staff salaries. In 2016, WFP CO mobilized half of the required budget from PRRO. The remaining budget (50%) was mobilized from AF project funds. For 2017, after discussions with AF, it was notified that the Project could make changes in budgets according to the guidelines of the Fund, and as further clarified by the Board at its 29th meeting.
Lack of capacity in the DREDDs in terms of staffing and skills. | Overcome | In 04 DREDDs out of 08, we noted a lack of capacity in terms of technical and management skills (poor quality of supervision, reporting and management) and also in terms of staffing. this was accentuated by the appointment in 2019 of 3 new DREDDs who have not previously been involved in the implementation of the project. This situation affected the quality of work and the deadlines for implementing activities in the concerned regions. The project relied on NGOs which have taken over to supervise the implementation of activities and reduced the gap.
During the rainy season (June-August), many project sites become inaccessible due to the impracticability of the terrain. This situation is very cumbersome and causes a slowdown in the execution of activities. | Overcome | Adapt planning schedule and carry out other capacity building activities at Nouakchott or Wilayas Headquarters during these times.
DREDD as Regional responsibles for the environmental sector are fully busy with the bushfire campaign that runs from September to December of each year. In this period there is a lack in supervising project activity execution. | Overcome | The project relied on the NGO partners to follow-up and supervise the project activities progress.
Despite of the different capacity building and support provided to NGOS, the performance of some of them is below expected. | Overcome | Some contracts with NGOs had to be terminated and additional responsilibities were given to other more active partner NGOs present in the same Wilaya. Capacity building of NGO partners is also reinforced.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The continuity of the Project Manager, PMU staff and project technical team has helped the project to continue activities despite changes in authorities at regional level.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/ Coordinator: | Supporting DREDD in project activities implementation |  | Planning, supervision, implementation and monitoring of project activities are improved |  | The contribution of NGOs in improving the implementation of project activities has been very satisfactory. In addition to their role of local support and in raising community awareness and ownership of project activities, the project has expanded the mandate of these NGOs to include the supervision, implementation and monitoring of two major programmes : Income Generating Activities and the promotion of improved stoves, which have been very effective in achieving their objectives. | HS
| Strengthening of Government authorities and technical services on Climate Change threat, risk and vulnerability analysis |  | An Early Warning System (EWS) is set up at community level |  | Given that there is already an initiative for the establishment of an early warning system at the national level, the project focused instead on initiating a process for setting up a early warning system at the community level that could contribute to the National EWS. This process was actually initiated by the project and proposed a partnership framework between the producers of information (National Office of Meteorology, Ago-meteorological Services, Veterinary Services Directorate, National Center for Locust and Avian Control, Directorate of Statistics and Agropastoral Information Systems, Observatory for Food Security) and information broadcasters (Radio Mauritania, Television and Telephone Operators). A framework partnership agreement between the various partners has been prepared. The process of formalization has been entrusted to the Coordination Unit of the National Program on Climate Change (CCPNCC), under the MEDD. | S
| Communities share success stories and lessons learned, including support of 8 community radios |  | Community radios are on air, involving communities in programming and feed-back |  | The support program for Radio Mauritania achieved the objectives initially set. After the capacity development programme to enhence the technical capacities of the local radio stations, the project has supported the jouralists trained previously to visit most of viallges to see the acheivements and record beneficiary testemonials regarding the impacts of adaptation measure implemented on their economic and social life conditions. 9 Local Radio Stations in the 8 Wilayas have designed "Climate change and food security" programs, based on good adaptation practices capitalized by the project. These programs are weekly broadcasted in different local languages according to a predefined grid approuved and agrred between the project and the National Radio-Maritania. These programs have been very successfull. They interested many communuties increasing their awareness about climate change issues and the need to adapt facing ferequeently extreme events more and more observed in the country. | HS
| Communities are trained and sensitized about the adverse effects of CC and its impacts on natural resources, livelihood and food security |  | Communities are aware about the adverse effects of CC and its impacts on natural resources, livelihood and food security |  | With the support of NGOs hired since March 2017, 17 820 beneficiaries (13 320 women, and 4 500 men) were reached through awareness programs covering the following themes: - Objectives and approach of the project, - Climate change challenges on natural resources, livelihoods and food security - Ownership, management of achievements and sustainability of activities This awareness process is still ongoing. The goal is to ensure the appropriation and the sustanability of implemented activities by the communities after the end of the project. | HS
| Communties are trained and senstized about benefits of improved cooking stoves contributing in reducing deforestation and land degradation by improving energy efficiency in households. |  | 200 young artisans and volunteers are trained in the manufacturing and distribution of 30 000 improved cooking stoves. |  | The promotion of improved dual prototype stoves (charcoal and wood) in the project intervention areas has the following main objectives: 1. Strengthening and supporting young volunteers and artisans as key actors in the manufacturing and distribution chain of improved stoves in Mauritania. 2. Improving the living conditions of vulnerable households, especially women, by reducing the time available for collecting wood for cooking and investing it for the benefit of the family and children. 3. Reducing deforestation and land degradation by improving energy efficiency in households. 4. Reducting green house gaz emissions, The project started by providing capacity building and support to 179 young volunteers and artisans among 60 sites of the project in the 8 Wilayas. The objective is to make them key players in the manufacturing and distribution chain of improved stoves in Mauritania. A five (05) days training session in manufactoring improved stoves, regrouping the young volunteers and artisans, was organised in each Wilaya. During the training session, the project purchased and provided free of charge to the artisans and volunteers a set of equipment kits and the raw material (sheet metal drums) necessary for the manufacture of the improved prototype stoves. The usefulness of these improved stoves was demonstrated and appreciated by participants and women in the concerned villages, following a real experience of comparing the energy efficiency of three stoves models to those traditionally used in the village. Among the artisans and volonteers who have confirmed their expertise in the manufacture of improved stoves, the project has engaged them in a major programme, supervised by the NGOs partners to manufacture and distribute improved stoves, which has reached more than 20600 improved stoves to as many households in 73 project intervention sites. The impacts on women's conditions are remarkable. Evaluations conducted by NGOs have shown that, with two (02) hot (cooked) meals per day, the use of improved stoves compared to traditinal three-stone stoves, we got the following results : 1. Save up to 318 Kg of wood per household per year. 2. These avoided quantities of wood allow each household to save about 4,770 MRU (133 USD)/year. 3. Depending on the type of improved stove used (wood or charcoal), a woman can save between 19 and 43 days per year in avoided time in preparing meals that can be used in other household functions. | HS
| Monitoring system in place (training, production of data and reports) to track climate events and ecologic development in project intervention zones. |  | Monitoring system in place and operational |  | Given the Monitoring-Evaluation Guide developped by the project, discussions were conducted with concerned technical offices of MEDD at central level and the DREDDs at regional level to set up an ecological monitoring mechanism. ToRs have been drafted and shared with MEDD technical Directions. Hence the ToRs validated, the project will hire a national consultant to supervise the elaboration of this ecological monitoring mechanism. The monitoring will concern particularly the sand dune fixation areas, wood-fuel plantation areas and the protected grazing areas. The objective is to report on the SEPANE/MEDD indicators covering these activities. It's also planned to train the 8 DREDD's staff on the use of the ecological monitoring system. | S
| Concrete adaptation measures identified through community-based adaptation planning to combat desertification and land degradation initiated in the project area |  | Adaptation measures implementation initiated in the project area to combat desertification and land degradation |  | Since 2015, 59 nurseries have been established in which 1 248 162 forest seedlings have been produced for sand dunes fixation, village afforestation / reforestation and pastoral improvement programs. Sand dune fixation 995 ha of dunes have been stabilized in 36 project sites. The mechanical fixation, which is the first step in the process of stabilizing sand dunes, covered 707 km of weaving. The objective is to protect houses, hydraulic infrastructures and agricultural lands in the sites, threatened by sand encroachment. Village plantation for fuel wood - 460 ha of collective land ranging from 5 to 10 ha were planted in 37 villages for fuelwood production. The objective is to provide communities with a space where they can extract their firewood needs, thus preserving existing natural resources already weakened by over-exploitation and overgrazing. These spaces will be managed by operating regulations that meet certain rules ensuring their sustainable exploitation by the Village Management Committee. Vulnerable protected area 25 Protected community areas ranging from 25 to 50 ha each totaling 1000 ha have been estabished. These spaces have been protected by fences. They will play an important role for these communities, particularly in a drought year when pasture will not be sufficient to cover livestock needs throughout the year. In 2017 and 2018, pastoral improvements were made by planting certain local species in order to replenish the vegetation and improve the forage balance of these reserves. Operating regulations are being prepared to enable the management committees of these areas to better manage, exploit and ensure their sustainability. Water retention structures implementation Restoration of degraded lands and water and soil conservation activities are among the most important activities supported by the project. So far 18 water retention structures were built in 6 villages in Guidimakha and 4 villages in Gorgol. The structures which are water retention digues, filter dams and stony cordons, are totally build by local population without heavy machinery ; only with local tools and supervising technicians offered by the project. These water retention structures have restored and reclaimed approximately 440 ha of lands in which a great amount have been cultivated by the beneficiary communities since the 2018 agricultural campaign. 370 ha of restored lands have been fenced by the project. | HS
| Concrete adaptation measures identified through community-based adaptation planning to diversify and strengthen the livelihoods of vulnerable populations initiated in the project area |  | Adaptation measures implementation initiated in the project area to diversify and strengthen the livelihoods of vulnerable populations |  | Fruit tree plantation programme A total of 3,973 households (23,838 direct beneficiaries) benefited from project support in 20 villages. The project provided 9,330 fruit trees (mango, jujube, lemon, mandarin, grapefruit, orange, guava and banana). This program was implemented with the support of the Center for Agronomic Research and Agricultural Development (CNRADA) and targeted two types of farms: 1. Family farms where the project distributed and helped plant fruit trees in each household at the rate of 3 to 5 trees per household. This is a type of farm that has been very successful because the trees are inside the yard and daily attention is given in terms of watering and maintenance by the beneficiaries. 2. Collective farms are fenced areas covering areas of 0.5 to 2 ha which have been equipped with basins and drip irrigation systems to ensure regular irrigation and water saving. This program has been extended to the planting of local fruit trees adapted to the severe climatic conditions of the region such as Acacia Senegal, Zizyphus mauritanica and Balantine aegyptiaca whose production (gum, fruit) in the medium term will provide an important source of income for the targeted communities. Nearly 280,000 trees were planted in the 25 protected sites. | HS
[5 empty] | High Value Crop production The project supported a total of 42 women's cooperatives to set up their vegetable gardens in the 8 project Wilayas. This activity targeted 8728 participants (76% Women/ 24% men) representing more than 52 000 beneficiaries. In addition to the theoretical training, local support and technical supervision was also provided during the two campaigns 2016 and 2017 to transmit to these cooperatives all the know-how and prepare them to become autonomous in the management of their vegetable gardens without any external support to ensure the sustainability of the activity. Economically, during the 2018-2019 crop year, 70 ha of vegetable gardens were cultivated, producing 189 919 kg of vegetables with an average yield per hectare of about 2713 kg. Each cooperative has on average consumed 30% of its production and sold 70%. Average income per cooperative was valued at 51,198 MRU (~1 422 USD). In addition to the income generated by the sale of excess vegetables, members of concerned cooperatives had acess to a fresh vegetables for a long period of the year, thus improving the nutritional quality of their meals. Also, the proximity of these vegetable gardens has allowed other members of the community to have fresh, good quality vegetables at affordable prices. In addition, the project provided training and equipment for 84 women and 5 men to master simple techniques for preserving and drying surplus vegetables from their gardens. This allowed them to provide an additional 2-3 months of vegetable availability at the household level. Beyond self-consumption and financial revenues, a dozen market gardening cooperatives, without external support, have reinvested part of their profits to finance the establishment of new income-generating activities (IGAs) such as butcheries, community shops or fishmongers. This is a direct effect of the project on improving food security and living conditions of the targeted beneficiaries. Today, 37 cooperatives are autonomous, skilled and continue to apply appropriate techniques for market gardening based only on their own resources. | HS
[5 empty] | Poultry production programme This programme was executed in two phases. A first phase in 2016, which involved the establishment of 10 semi-intensive and 40 traditional poultry houses. The project fully funded the construction of the 50 equipped poultry houses and provided supervision and support to the beneficiaries until their empowerment, while the communities contributed with labour. Unlike the traditional poultry programme, which has experienced difficulties, the semi-intensive program has been a success. After the project financed their first campaign, the 10 semi-intensive poultry production cooperatives are now financially autonomous and have conducted up to 6 production campaigns on their own. In addition, two cooperatives in the Wilaya of Trarza have made profits and reinvested part of their profits to increase the production capacity of their poultry houses, generating even more profits and ensuring the supply of a larger community. Beyond the provision of white meat to the community, which improves food security and overall nutritional quality, this activity has generated profits for these cooperatives, some of which have reinvested part of their profits in other income-generating activities that help households to better cope with crisis situations. In terms of economic profitability, the net profit generated by 10 people who produce a band of 500 chickens is 41,000 MRUs (1 139 USD). The income per band and per woman is about 4,100 MRUs (~114 USD) and the income per woman per day is 136 MRUs (~3,8 USD). In view of the strong demand from the beneficiary communities for a semi-intensive poultry programme, the project has launched a second phase which has resulted in the establishment of Six (06) additional units which just went into production in February 2019. The whole program benefited 560 participants (80% women / 20% Young men) representing 3,360 direct beneficiaries. The traditional poultry programme was not as successful as the semi-intensive programme. In fact in 2017-2018 the project purchased and introduced more than 50 raceur cocks (roosters) in order to start the programme. Unfortunately 2017 and 2018 were very difficult years in terms of drought and high temperature which contributed to the loss of most of the raceur cocks which could not adapt to the difficult weather conditions. Nevertherless, we evaluated that 20% of the traditional poultry programme was successful. It has been found that there is no need to train extention staff because the "Program to Combat Rural Poverty through Support to Production Sectors(ProlPraf)" funded by the FIDA (17.8 Million USD) has been set up in Mauritania over a period of six years, has invested a lot in strengthening the technical capacities of the regional technical services of the Ministry of Agriculture in the field of Poultry farming. The objective of training 4000 technical staff and community leader was largely overestimated in the project document. The number of participants for semi-intensive poultry house or traditional poultry house must not exceed 10 people to be relevant. | HS
[5 empty] | Improving water availability and accessibilty The problem of water availability and accessibilty is a central issue for adaptation to climate change. Given its limited resources, the project did not systematically seek to create new water sources. Instead, it focused on solving problems for existing water sources (wells, boreholes, streams, etc.). The project's support in terms of solving water-related problems covered 46 project sites in the Eight Wilayas through the following actions: - Deepening and rehabilitation of wells - Rehabilitation of boreholes - Installation of solar pumping equipment - Installation of motor pumps - Installation of water storage tanks - Installation of drip irrigation networks - Digging wells and boreholes (accessory) Water management committees have been established and trained on the rational use of water and the maintenance of installed equipment to ensure its sustainability. Access to water has mainly improved for market gardening and small family farming. Several households have resumed agricultural activity through the establishment of their own vegetable gardens, which have enabled them to make money and improve the availability of vegetables for a longer period of time, thus improving the food security of local populations. In most cases, the project interventions had an effect on reducing water costs and time spend by girls and women on seeking drinking water, investing it in other tasks for the benefit of the family and children or promoting other income-generating activities. | HS
[5 empty] | Apiculture Beekeeping is an innovative activity introduced by the project. Eight Sites were targeted in 05 Wilayas where all the ecological and social conditions are met to guarantee the success of this activity. 2 sites in Trarza (Oum El Koura and Nassra 2), 3 sites in Gorgol (Haddad, Dimechgha and Dar El Beidha), 1 site in Brakna (Dounguel Réo), 1 site in Guidimakha (Ndeo) and 1 site in Tagant (Legdeim ). The program was resumed in 2018 and the evaluation undertaken by the project showed that the result was mixed in 4 of the selected sites. This is largely due to the very difficult year 2017-2018, which was characterized by a large rainfall deficit and consequently a drought which affected the apiaries, some of which were completely dissipated. The project has decided to abandon these 4 sites and put all efforts on the other 4 sites where the results are quite interesting. A complement of beekeeping equipment was acquired and distributed to the beneficiaries with a program of support of proximity to ensure the good mastery of the management and the exploitation of the apiaries. We consider that is a good experience which should be consolidated in the framework of other initiatives and projects and/or replicated in other regions where this activity is potentially promising. | MS
[5 empty] | Income Generating Activities (IGA) The project have identified and approved with communities many Income Generating Activities particularely targeted for women : - 25 pastoral reserves - 42 High value crop production cooperatives, - 16 semi-intensive Poultry farming units - 40 traditional poultrly farming units - 04 Beekeeping cooperatives - 20 Fruit trees farming sites - 179 Artisans/volonteers for manufacturing of improved stoves - 22 butchers - 06 bakeries - 34 community shops - 01 vegetable marketing unit - 09 couscous production units - 02 sewing units - 03 fattening units for small ruminants - 02 livestock feed stores - 14 grain mills - 04 dyeing units Beyond the availability of several basic food products for the community, the women / men beneficiaries have invested part of the profits generated in improving household living conditions and creating other IGAs. Most of these IGAs are managed on a rotating basis, cyclically benefiting one group of women/men for a given period of time who pass the hand to another group and so on. The Capital is maintained or increased. The group of women/men is paid and the rest of the profits are stored into a community fund to perform various functions such as maintenance and repair, input material and equipement purchasing and guarding, etc. | HS
[5 empty] | Trainings for the communities The project trained/coached about 31 921 participants (63% Women, 37% Men) in the following topics/fields | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Ghazi GADER
| Email: | ghazi.gader@wfp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The overall rating of the project is satisfactory. The project was successful in achieving almost all objectives. The support and commitment of the Ministry of Environment and Sustainable Development (MEDD) and NGOs, implementing partners have been essential to coordinate activities at the local level and improve implementation, despite movements among DREDD reassignment at the regional level over the past four years. This last year, the implementation of the project was as effective as last year by achieving all planned activities and disbursing almost all of the allocated budget. Overall, all planned activities were implemented in line with the annual work plan. During the reporting period, the focus has been on the following issues: Finalization and validation of the rules for the management and exploitation of pastoral reserves, village afforestation perimeters and defensive sites for the sustainable management of these areas. The partnership established between the project and Radio Mauritania has been a success in raising awareness among a wide audience in rural areas. Following the capacity building of journalists and local radio stations deployed in the project's 8 Wilayas, a radio programme schedule was set up and validated at the level of the various local radio stations and began broadcasting programmes on climate change issues related to food security and adaptation strategies, designed on the basis of the project's best practices and the beneficiaries' testimonies. These programmes are broadcast on a weekly basis in the various local languages and reach thousands of people living even outside the project's intervention areas. This has had a very strong impact in terms of raising awareness about the challenges of climate change and its implications on different natural and human systems. The initiation of the implementation of a Community Early Warning System through the creation of a partnership between Radio Mauritania, the National Meteorological Office and the Agrometeorological Services with the objective of setting up an operational mechanism for disseminating climate information to decision-makers at regional level and rural communities in order to better prepare them for possible difficult years and guide them towards the most appropriate solutions, taking into account seasonal forecasts. In this system, Radio Mauritania’s network will act as a relay to communicate and disseminate information to a very wide audience, including at the community level. Solving water access problems in 17 additional sites with the installation of solar pumping systems and storage basins while training management committees on their proper operation and maintenance. The project also implemented a second phase of the semi-intensive poultry promotion program, which was a great success in its first phase. 6 other villages have benefited from semi-intensive poultry houses that have entered into production since April 2019. The implementation of a programme to manufacture and distribution of 20600 improved stoves for the benefit of households in the project's intervention areas. Evaluations have shown that the use of these improved stoves can save up to 40% of wood and charcoal, saving women valuable time for family and children. Through NGOs, the project continued to build the capacity of village management committees VMC to enable communities to ensure the continuity of activities and their sustainability. Innovations were gradually introduced according to the maturity of these VMC with the establishment of village funds, managed locally by the VMC and fed by the various income-generating activities supported by the project (grazing fees in pastoral reserves, straw sales, poultry farming, shops, butchery, and all implemented IGAs in general). rotational management of these IGAs is a leverage for strengthening solidarity and social cohesion among communities.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Executing Entity | Supporting DREDD in project activities implementation |  | Planning, supervision, implementation and monitoring of project activities are improved |  | The contribution of NGOs in improving the implementation of project activities has been very satisfactory. In addition to their role of local support and in raising community awareness and ownership of project activities, the project has expanded the mandate of these NGOs to include the supervision, implementation and monitoring of two major programmes : Income Generating Activities and the promotion of improved stoves, which have been very effective in achieving their objectives. | HS
| Strengthening of Government authorities and technical services on Climate Change threat, risk and vulnerability analysis |  | An Early Warning System (EWS) is set up at community level |  | Given that there is already an initiative for the establishment of an early warning system at the national level, the project focused instead on initiating a process for setting up a early warning system at the community level that could contribute to the National EWS. This process was actually initiated by the project and proposed a partnership framework between the producers of information (National Office of Meteorology, Ago-meteorological Services, Veterinary Services Directorate, National Center for Locust and Avian Control, Directorate of Statistics and Agropastoral Information Systems, Observatory for Food Security) and information broadcasters (Radio Mauritania, Television and Telephone Operators). A framework partnership agreement between the various partners has been prepared. The process of formalization has been entrusted to the Coordination Unit of the National Program on Climate Change (CCPNCC), under the MEDD. | S
| Communities share success stories and lessons learned, including support of 8 community radios |  | Community radios are on air, involving communities in programming and feed-back |  | The support program for Radio Mauritania achieved the objectives initially set. After the capacity development programme to enhence the technical capacities of the local radio stations, the project has supported the jouralists trained previously to visit most of viallges to see the acheivements and record beneficiary testemonials regarding the impacts of adaptation measure implemented on their economic and social life conditions. 9 Local Radio Stations in the 8 Wilayas have designed "Climate change and food security" programs, based on good adaptation practices capitalized by the project. These programs are weekly broadcasted in different local languages according to a predefined grid approuved and agrred between the project and the National Radio-Maritania. These programs have been very successfull. They interested many communuties increasing their awareness about climate change issues and the need to adapt facing ferequeently extreme events more and more observed in the country. | HS
| Communities are trained and sensitized about the adverse effects of CC and its impacts on natural resources, livelihood and food security |  | Communities are aware about the adverse effects of CC and its impacts on natural resources, livelihood and food security |  | With the support of NGOs hired since March 2017, 17 820 beneficiaries (13 320 women, and 4 500 men) were reached through awareness programs covering the following themes: - Objectives and approach of the project, - Climate change challenges on natural resources, livelihoods and food security - Ownership, management of achievements and sustainability of activities This awareness process is still ongoing. The goal is to ensure the appropriation and the sustanability of implemented activities by the communities after the end of the project. | HS
| Communties are trained and senstized about benefits of improved cooking stoves contributing in reducing deforestation and land degradation by improving energy efficiency in households. |  | 200 young artisans and volunteers are trained in the manufacturing and distribution of 30 000 improved cooking stoves. |  | The promotion of improved dual prototype stoves (charcoal and wood) in the project intervention areas has the following main objectives: 1. Strengthening and supporting young volunteers and artisans as key actors in the manufacturing and distribution chain of improved stoves in Mauritania. 2. Improving the living conditions of vulnerable households, especially women, by reducing the time available for collecting wood for cooking and investing it for the benefit of the family and children. 3. Reducing deforestation and land degradation by improving energy efficiency in households. 4. Reducting green house gaz emissions, The project started by providing capacity building and support to 179 young volunteers and artisans among 60 sites of the project in the 8 Wilayas. The objective is to make them key players in the manufacturing and distribution chain of improved stoves in Mauritania. A five (05) days training session in manufactoring improved stoves, regrouping the young volunteers and artisans, was organised in each Wilaya. During the training session, the project purchased and provided free of charge to the artisans and volunteers a set of equipment kits and the raw material (sheet metal drums) necessary for the manufacture of the improved prototype stoves. The usefulness of these improved stoves was demonstrated and appreciated by participants and women in the concerned villages, following a real experience of comparing the energy efficiency of three stoves models to those traditionally used in the village. Among the artisans and volonteers who have confirmed their expertise in the manufacture of improved stoves, the project has engaged them in a major programme, supervised by the NGOs partners to manufacture and distribute improved stoves, which has reached more than 20600 improved stoves to as many households in 73 project intervention sites. The impacts on women's conditions are remarkable. Evaluations conducted by NGOs have shown that, with two (02) hot (cooked) meals per day, the use of improved stoves compared to traditinal three-stone stoves, we got the following results : 1. Save up to 318 Kg of wood per household per year. 2. These avoided quantities of wood allow each household to save about 4,770 MRU (133 USD)/year. 3. Depending on the type of improved stove used (wood or charcoal), a woman can save between 19 and 43 days per year in avoided time in preparing meals that can be used in other household functions. | HS
| Monitoring system in place (training, production of data and reports) to track climate events and ecologic development in project intervention zones. |  | Monitoring system in place and operational |  | Given the Monitoring-Evaluation Guide developped by the project, discussions were conducted with concerned technical offices of MEDD at central level and the DREDDs at regional level to set up an ecological monitoring mechanism. ToRs have been drafted and shared with MEDD technical Directions. Hence the ToRs validated, the project will hire a national consultant to supervise the elaboration of this ecological monitoring mechanism. The monitoring will concern particularly the sand dune fixation areas, wood-fuel plantation areas and the protected grazing areas. The objective is to report on the SEPANE/MEDD indicators covering these activities. It's also planned to train the 8 DREDD's staff on the use of the ecological monitoring system. | S
| Concrete adaptation measures identified through community-based adaptation planning to combat desertification and land degradation initiated in the project area |  | Adaptation measures implementation initiated in the project area to combat desertification and land degradation |  | Since 2015, 59 nurseries have been established in which 1 248 162 forest seedlings have been produced for sand dunes fixation, village afforestation / reforestation and pastoral improvement programs. Sand dune fixation 995 ha of dunes have been stabilized in 36 project sites. The mechanical fixation, which is the first step in the process of stabilizing sand dunes, covered 707 km of weaving. The objective is to protect houses, hydraulic infrastructures and agricultural lands in the sites, threatened by sand encroachment. Village plantation for fuel wood - 460 ha of collective land ranging from 5 to 10 ha were planted in 37 villages for fuelwood production. The objective is to provide communities with a space where they can extract their firewood needs, thus preserving existing natural resources already weakened by over-exploitation and overgrazing. These spaces will be managed by operating regulations that meet certain rules ensuring their sustainable exploitation by the Village Management Committee. Vulnerable protected area 25 Protected community areas ranging from 25 to 50 ha each totaling 1000 ha have been estabished. These spaces have been protected by fences. They will play an important role for these communities, particularly in a drought year when pasture will not be sufficient to cover livestock needs throughout the year. In 2017 and 2018, pastoral improvements were made by planting certain local species in order to replenish the vegetation and improve the forage balance of these reserves. Operating regulations are being prepared to enable the management committees of these areas to better manage, exploit and ensure their sustainability. Water retention structures implementation Restoration of degraded lands and water and soil conservation activities are among the most important activities supported by the project. So far 18 water retention structures were built in 6 villages in Guidimakha and 4 villages in Gorgol. The structures which are water retention digues, filter dams and stony cordons, are totally build by local population without heavy machinery ; only with local tools and supervising technicians offered by the project. These water retention structures have restored and reclaimed approximately 440 ha of lands in which a great amount have been cultivated by the beneficiary communities since the 2018 agricultural campaign. 370 ha of restored lands have been fenced by the project. | HS
| Concrete adaptation measures identified through community-based adaptation planning to diversify and strengthen the livelihoods of vulnerable populations initiated in the project area |  | Adaptation measures implementation initiated in the project area to diversify and strengthen the livelihoods of vulnerable populations |  | Fruit tree plantation programme A total of 3,973 households (23,838 direct beneficiaries) benefited from project support in 20 villages. The project provided 9,330 fruit trees (mango, jujube, lemon, mandarin, grapefruit, orange, guava and banana). This program was implemented with the support of the Center for Agronomic Research and Agricultural Development (CNRADA) and targeted two types of farms: 1. Family farms where the project distributed and helped plant fruit trees in each household at the rate of 3 to 5 trees per household. This is a type of farm that has been very successful because the trees are inside the yard and daily attention is given in terms of watering and maintenance by the beneficiaries. 2. Collective farms are fenced areas covering areas of 0.5 to 2 ha which have been equipped with basins and drip irrigation systems to ensure regular irrigation and water saving. This program has been extended to the planting of local fruit trees adapted to the severe climatic conditions of the region such as Acacia Senegal, Zizyphus mauritanica and Balantine aegyptiaca whose production (gum, fruit) in the medium term will provide an important source of income for the targeted communities. Nearly 280,000 trees were planted in the 25 protected sites. | HS
[5 empty] | High Value Crop production The project supported a total of 42 women's cooperatives to set up their vegetable gardens in the 8 project Wilayas. This activity targeted 8728 participants (76% Women/ 24% men) representing more than 52 000 beneficiaries. In addition to the theoretical training, local support and technical supervision was also provided during the two campaigns 2016 and 2017 to transmit to these cooperatives all the know-how and prepare them to become autonomous in the management of their vegetable gardens without any external support to ensure the sustainability of the activity. Economically, during the 2018-2019 crop year, 70 ha of vegetable gardens were cultivated, producing 189 919 kg of vegetables with an average yield per hectare of about 2713 kg. Each cooperative has on average consumed 30% of its production and sold 70%. Average income per cooperative was valued at 51,198 MRU (~1 422 USD). In addition to the income generated by the sale of excess vegetables, members of concerned cooperatives had acess to a fresh vegetables for a long period of the year, thus improving the nutritional quality of their meals. Also, the proximity of these vegetable gardens has allowed other members of the community to have fresh, good quality vegetables at affordable prices. In addition, the project provided training and equipment for 84 women and 5 men to master simple techniques for preserving and drying surplus vegetables from their gardens. This allowed them to provide an additional 2-3 months of vegetable availability at the household level. Beyond self-consumption and financial revenues, a dozen market gardening cooperatives, without external support, have reinvested part of their profits to finance the establishment of new income-generating activities (IGAs) such as butcheries, community shops or fishmongers. This is a direct effect of the project on improving food security and living conditions of the targeted beneficiaries. Today, 37 cooperatives are autonomous, skilled and continue to apply appropriate techniques for market gardening based only on their own resources. | HS
[5 empty] | Poultry production programme This programme was executed in two phases. A first phase in 2016, which involved the establishment of 10 semi-intensive and 40 traditional poultry houses. The project fully funded the construction of the 50 equipped poultry houses and provided supervision and support to the beneficiaries until their empowerment, while the communities contributed with labour. Unlike the traditional poultry programme, which has experienced difficulties, the semi-intensive program has been a success. After the project financed their first campaign, the 10 semi-intensive poultry production cooperatives are now financially autonomous and have conducted up to 6 production campaigns on their own. In addition, two cooperatives in the Wilaya of Trarza have made profits and reinvested part of their profits to increase the production capacity of their poultry houses, generating even more profits and ensuring the supply of a larger community. Beyond the provision of white meat to the community, which improves food security and overall nutritional quality, this activity has generated profits for these cooperatives, some of which have reinvested part of their profits in other income-generating activities that help households to better cope with crisis situations. In terms of economic profitability, the net profit generated by 10 people who produce a band of 500 chickens is 41,000 MRUs (1 139 USD). The income per band and per woman is about 4,100 MRUs (~114 USD) and the income per woman per day is 136 MRUs (~3,8 USD). In view of the strong demand from the beneficiary communities for a semi-intensive poultry programme, the project has launched a second phase which has resulted in the establishment of Six (06) additional units which just went into production in February 2019. The whole program benefited 560 participants (80% women / 20% Young men) representing 3,360 direct beneficiaries. The traditional poultry programme was not as successful as the semi-intensive programme. In fact in 2017-2018 the project purchased and introduced more than 50 raceur cocks (roosters) in order to start the programme. Unfortunately 2017 and 2018 were very difficult years in terms of drought and high temperature which contributed to the loss of most of the raceur cocks which could not adapt to the difficult weather conditions. Nevertherless, we evaluated that 20% of the traditional poultry programme was successful. It has been found that there is no need to train extention staff because the "Program to Combat Rural Poverty through Support to Production Sectors(ProlPraf)" funded by the FIDA (17.8 Million USD) has been set up in Mauritania over a period of six years, has invested a lot in strengthening the technical capacities of the regional technical services of the Ministry of Agriculture in the field of Poultry farming. The objective of training 4000 technical staff and community leader was largely overestimated in the project document. The number of participants for semi-intensive poultry house or traditional poultry house must not exceed 10 people to be relevant. | HS
[5 empty] | Improving water availability and accessibilty The problem of water availability and accessibilty is a central issue for adaptation to climate change. Given its limited resources, the project did not systematically seek to create new water sources. Instead, it focused on solving problems for existing water sources (wells, boreholes, streams, etc.). The project's support in terms of solving water-related problems covered 46 project sites in the Eight Wilayas through the following actions: - Deepening and rehabilitation of wells - Rehabilitation of boreholes - Installation of solar pumping equipment - Installation of motor pumps - Installation of water storage tanks - Installation of drip irrigation networks - Digging wells and boreholes (accessory) Water management committees have been established and trained on the rational use of water and the maintenance of installed equipment to ensure its sustainability. Access to water has mainly improved for market gardening and small family farming. Several households have resumed agricultural activity through the establishment of their own vegetable gardens, which have enabled them to make money and improve the availability of vegetables for a longer period of time, thus improving the food security of local populations. In most cases, the project interventions had an effect on reducing water costs and time spend by girls and women on seeking drinking water, investing it in other tasks for the benefit of the family and children or promoting other income-generating activities. | HS
[5 empty] | Apiculture Beekeeping is an innovative activity introduced by the project. Eight Sites were targeted in 05 Wilayas where all the ecological and social conditions are met to guarantee the success of this activity. 2 sites in Trarza (Oum El Koura and Nassra 2), 3 sites in Gorgol (Haddad, Dimechgha and Dar El Beidha), 1 site in Brakna (Dounguel Réo), 1 site in Guidimakha (Ndeo) and 1 site in Tagant (Legdeim ). The program was resumed in 2018 and the evaluation undertaken by the project showed that the result was mixed in 4 of the selected sites. This is largely due to the very difficult year 2017-2018, which was characterized by a large rainfall deficit and consequently a drought which affected the apiaries, some of which were completely dissipated. The project has decided to abandon these 4 sites and put all efforts on the other 4 sites where the results are quite interesting. A complement of beekeeping equipment was acquired and distributed to the beneficiaries with a program of support of proximity to ensure the good mastery of the management and the exploitation of the apiaries. We consider that is a good experience which should be consolidated in the framework of other initiatives and projects and/or replicated in other regions where this activity is potentially promising. | MS
[5 empty] | Income Generating Activities (IGA) The project have identified and approved with communities many Income Generating Activities particularely targeted for women : - 25 pastoral reserves - 42 High value crop production cooperatives, - 16 semi-intensive Poultry farming units - 40 traditional poultrly farming units - 04 Beekeeping cooperatives - 20 Fruit trees farming sites - 179 Artisans/volonteers for manufacturing of improved stoves - 22 butchers - 06 bakeries - 34 community shops - 01 vegetable marketing unit - 09 couscous production units - 02 sewing units - 03 fattening units for small ruminants - 02 livestock feed stores - 14 grain mills - 04 dyeing units Beyond the availability of several basic food products for the community, the women / men beneficiaries have invested part of the profits generated in improving household living conditions and creating other IGAs. Most of these IGAs are managed on a rotating basis, cyclically benefiting one group of women/men for a given period of time who pass the hand to another group and so on. The Capital is maintained or increased. The group of women/men is paid and the rest of the profits are stored into a community fund to perform various functions such as maintenance and repair, input material and equipement purchasing and guarding, etc. | HS
[5 empty] | Trainings for the communities The project trained/coached about 31 921 participants (63% Women, 37% Men) in the following topics/fields | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Alioune Fall, Project Coordinator Assistant; |  |  | Sidi Mohamed El Wavi, National Project Director
| Email: | lunef@yahoo.com |  |  | elwavi.sm@gmail.com
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The overall evaluation of the project is satisfactory. PARSACC is and remain to date the leading project of the Ministry of Environment and Sustainable Development. The feedback received from the communities benefiting from the PARSACC project is very positive, making it one of the priority projects of the MEDD and benefits of high visibility for its achievements in the media. The Minister of the Environment and Sustainable Development gives full support to the project and encourages all other MEDD projects to benefit from its experience and results. As outlined throughout the multiple and detailed answers in this project progress report, PARSACC has achieved a milestone. We can basically say that the main outcome objective of the project is: "enhancing the resilience of vulnerable communities to the effects of climate change on food security". Since inception, progress has been fairly steady towards achieving goals set for the project. Progress could be verified throughout verifiable facts distinguished at different levels: - At the community level, many diversified activities made available by the project with inputs of cash reward to remunerate efforts to achieve activities, income generated tools made available and basically 100% financed, couple those different activities with the raising awareness seminars, to build ownership and increase sustainability of implemented activities contributed greatly in the success and now elevated level of resilience to climate change for communities. - The technical and institutional capacity of Government institutions at regional (DREDD and decentralized institutions), Local (DREDD Inspectors) and national (Ministries), NGOs, vulnerable groups and relevant stakeholders were strengthened with tailored seminars and technical workshops to enhance the management, acquisition and dissemination of climate change data and info to help implement the project activities with beneficiaries. The partnership between MEDD and WFP has been strengthened. There is more synergy in the implementation of activities in the field. WFP is contributing through its programs by implementing complementary activities in PARSACC sites improving the resilience of target communities. Both parties are developing other project proposals that will build on the lessons learned from PARSACC to consolidate achievements and scale up good adaptation and resilience practices. There was not much as limiting factors towards progress, most of the activities were achieved as planned. The Open Door Journey organized with multiple stakeholders at the project ending activity was very innovative and a first for the MEDD. In light of the many achievements in the field in conjunction with a high level of satisfaction of stakeholders and communities in raising awareness and solidifying their resilience, the overall rating of the project is more than satisfactory.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (HU) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
OBJECTIVE 1: Enhanced understanding, skills and means of decentralized government and communities for leading and facilitating participatory adaptation planning | Number of community adaptation plans prepared through participative local planning supported with information and facilitation by DREDD | No adaptation plans exist in intervention zones | 87 villages prepared their ACC action plan with the support of DREDD and Regional technical services including civil society. This work is a result of the improvement of DREDD and project partners' skills on Climate change issues and integrating ACC into local development approach. With the support of NGOs, the baseline reference was improved and More than 50 Action plans have been updated. | 20 clusters of villages have established adaption plans in a participatory manner
Outcome 1.1: Strengthened awareness, ownership and facilitation capacities of government services (DREDD) | DREDD have played an active and supportive role in the mobilization, organization and implementation of inter-village adaption planning processes | DREDD do not have capacity to provide any support to communities | DREDD led, participated and facilitated in the elaboration of ACC action plans in 87 villages of the project intervention area. DREDD supervise in a regular bases with the support of NGO, consultants and others regional technical services, implementation of project activities giving advice and technical support for the communities. | DREDD have succeeded to provide information, guidance and facilitation support to 87 Villages
Output 1.1: Technical services strengthened to access and analyze climate change information, food security, livelihoods and vulnerability information, and to monitor local development, and mobilize and support communities. | DREDD have been trained, have communicated with department and local level, have visited communities, have facilitated village cluster establishment and discussions | DREDD do not visit communities and do not provide information, support, guidance or facilitate processes | - 2 training sessions organized in collaboration with GIZ's ACCMR project, for DREDDs and Regional technical services on Climate Change basics and the approach of Integrating Adaptation to Climate Change into Development planning. (80 participants). This training was followed by a practical exercise in one selected project site to implement the methodology in a real case with the active participation of the communities. Knowledge acquired during these aforementioned capacity building sessions permitted DREDD with regular visits to raise awareness on climate change impacts on food security and to monitor and guide the project's interventions. DREDDs received an additionnal support by consultants in some specific feilds (Aviculture and apiculture) as well as by the contracted NGOs which have been also trained on Climate change issues and integrating adaptation to climate change into local planning. These NGO provided support also in Community sensitization and mobilization, data collection and monitoring of climate change adaptation measures at local level. | DREDDs have regular contact and trustful relationship with villages and communities that value their support
Output 1.2: Strengthening of Government authorities and technical services on CC threat, risk and vulnerability analysis capabilities by expanding current Vulnerability and Analysis methodologies to overlay climate threats and monitoring changes in landscapes using GIS technologies. | Preparation and communication to regional level of up-to-date and reliable information and analysis of climate change information and of government priorities | DREDD hardly receive any guidance, information and analysis from central level | Training of 40 high-level managers, including 4 women representing the main ministerial departments and institutions at the central level, United Nations agencies and technical and financial partners. The training focused on integrating climate change adaptation into development planning. Climate information aspects were addressed, as well as terminology related to climate change, sensitivity, adaptive capacity, vulnerability and adaptation measures. This training adressed also the methodological approach to integrate adaptation into strategies and developement planning. It was perceived by the participants as a major contribution of the project to the development of national capacities in the field of climate change. During the reporting period, the project supported the implementation of a Community Early Warning System through the establishment of a partnership between the National Meteorological Office, the Agrometeorological Services and Radio Mauritania. The objective is to set up an operational mechanism for disseminating climate information to decision-makers at regional level and rural communities in order to better prepare them for possible difficult years and guide them towards the most appropriate solutions, taking into account seasonal forecasts in particular. An institutional inking system has been proposed to ensure the sustainability of this system, which has defined the relationship between information providers and end users, with Radio Mauritanie's network acting as a relay to communicate and disseminate information to a very wide audience, including at the community level. This process has just been launched and the MEDD through the Coordination Unit of the National Climate Change Programme will be responsible for continuing it until it is operationalized. | Regular communications between central level and DREDD provide up-to date information and guidance, adapted to the capacity at regional level
Outcome 1.2: Strengthened awareness, ownership, planning and management capacities at community level for local natural resource management and climate change adaptation | Communities and their relevant sub-groups (e.g. women, livelihood groups, etc.) have actively participated in the preparation of the inter-village adaptation plans prepared and see their interests adequately reflected. | There is only little joint discussion at community level, and not all groups are involved; no inter-village discussions take place | The sensitized communities about climate change impacts in the 87 villages have played a great role and actively participated to all steps of the process of elaboration of adaptation to climate change action plans, till the identification and prioritization of adaptation options. Most of these adaptation to climate change action plans were reviewed and updated by the NGOs with the participation of all targeted groups (man, women and young beneficiaries). | About 100 villagess understand, own and manage their adaption plans and their natural resources
Output 1.3: 20 inter-village associations established and supported. | Inter-village associations exist and are active in on form or the other in each of 20 targeted clusters | In some clusters, some form of cooperation structure may exist, on which the project can build. | The Mid-Term review confirmed that the establishing of inter-village associations in the framework of the AF project is not feasable, particularly due to social, and land ownership issues and also distance between villages. This work requires a lot of time and resources in order to achieve it (i.e. ProGRN experience). Wherever inter-village association structures exist, like AGLC, the project will continue supporting them during the project implementation period as they will ensure the sustainability of project activities. However the project has been working with the village management committies which are created and/or activated in all project sites and played the role of official communities partners throughout the project implementation. | 87 Village Management Commities with a role in managing natural resources and adaptation plans recognized by population and DREDD
Output 1.4: Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity. | Number of people (gender-disaggregated) and communities trained | Communities are aware of degrading natural resources, but rarely of context, causes and adaptation options | The regular visits organized by DREDD to supervise project activities constitute occasions to raise awarness about threats of adverse effects of CC on natural resources, livelihoods and food security. Parallelly to the ACC action plans implementation, many trainings have been organized for communities in different topics (High value crop production, agriculture, Poultry, Apiculture, sand dune fixation, aforestation, Soil and Water conservation, etc.) which adress also issues related to Climate change impacts on natural ressources, livelihood and food security. More than 15 000 participats have been reached since the project start. With the support of NGO, awareness raising and training sessions have been organised for the targeted communities. More than 17 820 people (13 320 wemen, and 4 500 men) were involved in an awareness programme about the following topics: - Objectives and approach of the project, - Climate change challenges on natural resources, livelihoods and food security - Ownership, management of achievements and sustainability of activities This awarness programme continued with the support of NGOs to achieve the goal of ownership and sustainability of project achievements. | Communities have the capacity to analyze and understand their situation, and adaptation options
Output 1.5: 100 villages, being clustered according to landscape, ecosystem and livelihoods, have prepared adaptation plans that are integrated into local development planning. Identification of adaptation technology requirements such as integrated livestock water and cropping systems. | 20 village cluster adaptation plans developed in a participatory way and officially recognized by DREDD | Communities and village associations do not prepare comprehensive adaptation plans | Communities in the 87 villages prepared their ACC action plan with the support of DREDD and Regional technical services including civil society. These ACC action plans were revised with the support of NGOs between March to August 2017. This work is a result of the improvement of DREDD, NGO and project partners' skills on ACC planning participatory approach based on 8 steps : 1. Identification of exposer units 2. Analysis of current vulnerability 3. Analysis of projected vulnerabilty (according to climate scenarios) 4. Identification of adaptaion options 5. Choice of prioritization criteria 6. Prioritization of adaptation options 7. Declination of adaptation options into actions and activities 8. Development of ACC action Plan These actions plans are being implemented in the 87 villages. | Adaptation plans include analysis, discussion of options, decision on priorities and analysis of implications (costs, maintenance)
| Specific studies on adaptation technology requirements are available at the relevant levels | A number of ad hoc studies exist within several projects, but are not systematically made available | The project has documented adaptation measures in terms of the technical aspects and implementation process (Sand dune fixation, Forest plantation, Pastoral reserves implementation and management, Market gardening techniques and management, Apiculture, Fruit trees plantation, etc.). The project has also taken up and adapted measures already developed by other projects and initiatives (Poultry farming techniques, Water and sail conservation techniques, improved stoves manifacturing and dessimination... Several of these measures have already been used by other projects implemented by the MEDD and are available for any other partners at the country level. | Studies on technology for 3-4 “standard” adaptation assets are available to all partners and stakeholders
Output 1.6: Communities share success stories and lessons learned, including support of community radios focused specifically on sharing information on early warning and adaptation management. | Community radios are on air, involving communities in programming and feed-back | Communities of 15 sites in the project area have already listen regularly to radio transmissions on a radius ranging from 6 to 70 km. | Community radios (Local Radio) were already established by the Government in all Wilayas including the 8 wilayas targeted by the project. They have been associated to all workshops and trainings organized in the regional level and they were sensitized to the project objectives. A framework agreement has been signed between the Project and the National Radio. The objective of this agreement is to set up the global partnership framework linking the project and the Radio with a view to operationalizing concrete measures to raise awareness and share the information developed between the public authorities, the beneficiary communities and local authorities, through radio broadcasts that particularly concern: 1. Vulnerability of communities to climate change 2. The management of climate change adaptation, 3. Food safety analyzes, 4. Weather and seasonal forecasts, 5. Early warning system and 6. Prevailing market prices for subsistence products. This will covers the following actions: a. The capacity building of journalists from Radio Mauritania, Rural Radio and local Radios involved in the implementation of the Framework Convention in various fields related to the concepts of climate change, its challenges and the adaptation measures taken implemented or planned by the project, b. Acquisition of equipment for the regional/local radio stations, c. Design, recording and broadcasting of radio programs according to a program schedule agreed between the two parties. d. Archiving of radio programs. In July 2019, the project has completed the following activities : - Procurement, delivery and installation of technical equipments (audio, reporting, computers, energy ...) for the National and local Radio Stations. - A training session to develop the capacities in sustainable development, food security and climate change has been organised for 25 journalists working for Mauritania National, Rural, Youth and Local Radio Stations. - Design, recording and broadcasting of radio programs by the 9 local radios and the rural radio, based on a work of the skilled journalists with the communities benefiting from the PARSACC project in the 8 regions of Mauritania. These radio programs entitled "climate change adaptation and food security" are designed on the basis of good practices and lessons learned from the project as well as testimonials from the beneficiary communities and are weekly broadcasted in local languages ​​according to a grid agreed between the project and Radio Mauritania. | CR goes live are on air, have with strong volunteer involvement and a sustainability strategy
Outcome 1.3: National ecologic monitoring system strengthened and tested | Participating communities and government services have provided quality, timely and reliable ecologic monitoring reports aligned with the national monitoring system | The ecologic monitoring system is established as part of PANE II System and set online in February 2014. | The Monitoring System of the PANE is already set up since 2014 by the MEDD with the support of GIZ and is online (http://www.medd-sepane.mr/). Given the Monitoring-Evaluation Guide developped by the project, discussions were conducted with concerned technical offices of MEDD at central level and the DREDDs at regional level to set up an ecological monitoring mechanism. ToRs have been drafted and shared with MEDD technical Directions. Hence the ToRs validated, the project will hire a national consultant to supervise the elaboration of this ecological monitoring mechanism. The monitoring will concern particularly the sand dune fixation areas, wood-fuel plantation areas and the protected grazing areas. The objective is to report on the SEPANE/MEDD indicators covering these activities. It's also planned to train the 8 DREDD's staff on the use of the ecological monitoring system. | The new national ecologic monitoring system is known, used and maintained by DREED and in project village clusters.
Output 1.7: Monitoring system in place (training, production of data and reports) to track climate events and ecologic development in project intervention zones. | Number of people trained at regional and village cluster level; amount and quality of data provided by village clusters / regional teams | There is no systematic collection, consolidation and analysis of data on nationally agreed-upon indicators. | Training on the use of the monitoring and evaluation guide has been organized for the benefit of the 8 DREDDs. Periodically the ecological monitoring is carried out (DREDD - PMU) in the project intervention sites compared to the baseline situation. The results will be integrated into the national ecological monitoring system. | Participating DREDD and village clusters provide data on agreed-upon indicators; and receive, understand and use reports.
OBJECTIVE 2: Design and implement concrete adaptation measures identified through community adaptation planning that aim to combat desertification, soil erosion and land degradation | Number of implemented community adaptation plan action aiming to combat desertification, soil erosion and land degradation | No comprehensive community (cluster) adaptation plans exist in the intervention zones to be selected. | All the adaptation plans drawn up by the targeted communities, with the support of DREDDs and reviwed by the NGOs in 2017, integrate measures linked to combat desertification, soil erosion and land degradation. They are being implemeted since then and they regroup 36 sites for sand dunes fixation, 37 sites for community fuel wood plantation, 25 sites for protected vulnerable areas and 18 sites for soil restoration and water conservation. | 20 comprehensive adaptation plans have been implemented with respect to combat desertification, soil erosion and land degradation.
Outcome 2.1: Advance of sand dunes slowed down, halted or reversed | Reduced, halted or reversed dune advance in participating communities | 749 ha of dunes fixed in the project intervention area | With the process of mechanical and biological fixation of sand dunes covering 995 ha, the advance of the dunes has been slowed down at the treated sites. In many sites this advance was totally halted even reversed (Tichoutine site in Brakna and Ghoueisbou Site in Assaba). | Significant deceleration – and ideally reversal – of dune advance
Output 2.1: 900 ha of dunes fixated. | Plants – and other measures – have stopped advance of dunes | Sand dune fixation does take place as part of several projects, but hardly in the zones to be selected. | 995 ha of dunes have been stabilized in 36 project sites. The mechanical fixation, which is the first step in the process of stabilizing sand dunes, covered 707 km of weaving. The objective is to protect houses, hydraulic infrastructures and agricultural lands in the sites, threatened by sand encroachment. (Objective totally acheived). Number of participants to implement the activity : 7 370 Number of beneficiaries : 44 392 Distributed cash : 479 706 USD | Communities have fixated dunes and have a clear plan for maintaining / reinforcing fixation
Outcome 2.2: Increased vegetation cover in intervention zones | Increased Vegetation Cover Index in participating communities | The average density of vegetation is 67 plants per hectare in the project sites | 25 protected areas ranging from 25 to 50 ha totaling 1000 ha have been established. These spaces have been protected by fences. In 2017, 2018 and 2019 pastoral improvements were made by planting some 280 000 local plant species in order to replenish the vegetation and increase vegetation cover. 37 wood-fuel plantation areas have been established covering more than 460 ha increasing the vegetation cover 995 ha have been mechanically and biologically fixed in 36 Sites as part of sand dune fixation activity increasing the vegetation cover in the targeted project communities. With plantations with an average density of 400 plants per hectare, it is absolutely clear that the avarage density at the end of the project would be increased by more than 10% compared to the baseline situation. | Increase of the average density per hectare by at least 10% in the participating village clusters until the end of the project with clear prospect of further increases)
Output 2.2: 1,000-1,500 ha of vulnerable zones protected. | Area of land protected from against uncontrolled grazing and bush fires | There will only be sporadic protected areas in selected village clusters | 25 Protected community areas ranging from 25 to 50 ha totaling 1000 ha have been established. These spaces have been protected by fences. In 2017, 2018 and 2019 pastoral improvements were made by planting some local species in order to replenish the vegetation and improve the forage balance of these reserves which will play an important role for these communities, particularly during drought years when pasture will not be sufficient to cover livestock needs throughout the year. Operating regulations have been prepared and communities representatives have been trained on to enable the management committees of these areas to better manage, exploit and ensure their sustainability. Number of participants to implement the activity : 1998 Number of beneficiaries : 12 224 Distributed cash : 102 207 USD | 1,000 – 1,500 ha of land protected and encompassed by sustainable management plan
Output 2.3: 400 ha of community fuel wood forests planted. | Area of land planted and controlled for fuel wood production; volume of produced fuel wood | There is hardly any controlled fuel wood plantation in areas to be selected | 460 ha of collective land ranging from 5 to 10 ha were planted in 37 villages for fuelwood production. The objective is to provide communities with a space where they can extract their firewood needs, thus preserving existing natural resources already weakened by over-exploitation and overgrazing. Operating regulations have been elaborated and communities representatives have been trained on, which meet certain rules ensuring the sustainable management and exploitation of these areas by the Village Management Committee. (Objective totally acheived). Number of participants to implement the activity : 1 618 Number of beneficiaries : 8 777 Distributed cash : 59 612 USD The exploitation of these areas will not be before 10 to 15 years. | Participating communities cover at least 50% of their fuel wood requirements from controlled wood production
Outcome 2.3: Decreased loss of water and soil through surface run-off | Increased surface and sub-soil water availability | There are only 13 sites with water retention structures functioning in areas to be selected | The results of soil and water conservation activities are already perceptible. After the 2017 rainy season, the reservoirs of the three earth dams built in Azgueilem, Jatel and Toueijile in Gorgol were filled increasing the water availability in the soil. Moreover we expect in 2018 with a better rainy season that the amount of water retention to be higher because of the more diversified retention structures such as digues, filter dams and stony cordons. 370 ha of restored lands have been fenced and cultivated by the beneficiary communities starting from the 2018 agricultural campaign taking advantage of the water availability generated by the retention struntures built by the project. | Area where days of water availability has increased with at least 20%
Output 2.4: Water retention structures built covering approx. 500 ha. | Number, kind, surface size and volume (where applicable) of water retention structures | 13 sites have dams, check dams, Soil and water conservation structures, Soil restoration structures | Restoration of degraded lands and water and soil conservation activities are among the most important activities supported by the project. 18 water retention structures were built in 6 villages in Guidimakha and 4 villages in Gorgol. The structures which are water retention digues, filter dams and stony cordons, are totally build by local population without heavy machinery ; only with local tools and supervising technicians offered by the project. These water retention structures have restored and reclaimed approximately 440 ha of lands in which a great amount have been cultivated by the beneficiary communities since the 2018 agricultural campaign. (Objective acheived at 88%). Number of participants to implement the activity : 1 084 Number of beneficiaries : 6 504 Distributed cash : 235 000 USD | Communities construct and maintain retention assets according to plan
OBJECTIVE 3 Design and implement concrete adaptation measures identified through community adaptation planning that aim to diversify and strengthen the livelihoods of the most vulnerable population » | Number and type of implemented community adaptation plan action aiming to diversify and strengthen the livelihoods of the most vulnerable population | No adaptation plans are in place, livelihood bases are hardly diversified in areas to be selected | All the adaptation action plans drawn up by the targeted communities, with the support of DREDDs and revised by the NGOs in 2017, integrate measures aiming to diversify and strengthen the livelihoods of the most vulnerable population. In that end following is a list of diverse activities reflecting the income generating revenue created and implemented in the project sites: - 25 pastoral reserves - 41 High value crop production cooperatives, - 16 semi-intensive Poultry farming units - 40 traditional poultrly farming units - 04 Beekeeping cooperatives - 20 Fruit trees farming sites - 179 Artisans/volonteers for manufacturing of improved stoves - 22 butchers - 06 bakeries - 34 community shops - 01 vegetable marketing unit - 09 couscous production units - 02 sewing units - 03 fattening units for small ruminants - 02 livestock feed stores - 14 grain mills - 04 dyeing units Beyond the availability of several basic food products for the community, women / men beneficiaries earn some of the benefits they can invest in improving the living conditions of the household or the creation of other IGAs. Most of these IGAs are managed on a rotating basis, cyclically benefiting one group of women/men for a given period of time who pass the hand to another group and so on. The Capital is maintained or increased. The group of women/men is paid and the rest of the profits are stored into a community fund to perform various functions such as maintenance and repair, input and equipement purchasing and guarding, etc. | Communities have implemented adaptation plan action and continue to gain sustainable income from new sources
Outcome 3.1: Increased number of sources of income for participating households | Number and type of sources of income for participating households before and after the project | Livelihood bases are hardly diversified in areas to be selected – specific baselines to be established as part of adaptation plan preparation (The communities practice seven (7) income generating activities including 04 based on the exploitation of natural resources (agriculture, livestock, fishing and fruit picking) | New income-generating activities have been introduced in many project sites, which resulted in increased livelihood bases for 46% of project beneficiaries : - High value crop production, in 52% of total project sites - Poultry, in 55% of total project sites - Beekeeping, in 9% of total project sites - Fruit farming, in 21% of total project sites - Manufacturing improved stoves, in more than 70% of project sites - Butchers, in 26% of total project sites - Bakeries, in 7% of total project sites - Community shops, in 40% of total project sites - Vegetable marketing unit, in 1% of total project sites - Couscous production units, in 11% of total project sites - Sewing units, in 2% of total project sites - Fattening units for small ruminants, in 4% of total project sites - Livestock feed stores, in 2% of total project sites - Grain mills, in 16% of total project sites - Dyeing units, in 5% of total project sites | At least 25% of village cluster population have increased their livelihood bases with new sources of income
Outcome 3.2: Increased income for participating households | Level of income for participating households before and after the project | Participating households are among the poorest in the selected areas. | The survey conducted for the final evaulation shows that vegetable production has increased significantly compared to the past. 74.2% of the respondents concerned by market gardening declare that production has greatly increased. In total, 97.1% think that vegetable production has increased. Production is used for both domestic consumption and the sale of surpluses. | Participating households have increased their revenues by at least 40%
Outcome 3.3: Increased availability of and access to food for participating communities | Food gap (number of weeks/months) for participating households before and after the project | Participating households have the greatest food gap in the selected areas. (The number of food deficit months range from 1 to 10) | The survey conducted for the final evaulation shows that 98.5% of respondents benefitting from market gardening recognize that the production of vegetables has improved household nutrition and food security. | Participating households have decreased their food gap by at least 50%
Output 3.1: Approx. 300,000 trees for revenue generation and food planted in protected areas. | Number of trees planted and growing in protected areas; amount of food and revenue gained from these. | Baseline to be established as part of adaptation plan | A total of 3,973 households (23,838 direct beneficiaries) benefited from project support in 20 villages. The project provided 9,330 fruit trees (mango, jujube, lemon, mandarin, grapefruit, orange, guava and banana). This program was implemented with the support of the Center for Agronomic Research and Agricultural Development (CNRADA) and targeted two types of farms: 1. Family farms where the project distributed and helped plant fruit trees in each household at the rate of 3 to 5 trees per household. This is a type of farm that has been very successful because the trees are inside the yard and daily attention is given in terms of watering and maintenance by the beneficiaries. 2. Collective farms are fenced areas covering areas of 0.5 to 2 ha which have been equipped with basins and drip irrigation systems to ensure regular irrigation and water saving. This program has been extended to the planting of local fruit trees adapted to the severe climatic conditions of the region such as Acacia Senegal, Zizyphus mauritanica and Balantine aegyptiaca whose production (gum, fruit) in the medium term will provide an important source of income for the targeted communities. Nearly 280,000 trees were planted in the 25 protected sites. | Planted trees already are – or have at least a clear prospect of – providing substantial amounts of food and income
Output 3.2: 4,000 technical staff and community leaders trained in livestock management, agricultural techniques and water utilization. | Number of people (gender disaggregated) trained |  | Trainings for the communities The project trained/coached about 31 921 participants (63% Women, 37% Men) in the following topics/fields | Extension staff and cluster population are aware of and apply appropriate techniques
Output 3.3: 5,000 technical staff and community leaders trained and equipped for plant/seed multiplication. | Number of people (gender disaggregated) trained | Hardly any training is available in areas to be selected; extension staff requires training, too | High Value Crop production The project supported a total of 42 women's cooperatives to set up their vegetable gardens in the 8 project Wilayas. This activity targeted 8728 participants (76% Women/ 24% men) representing more than 52 000 beneficiaries. In addition to the theoretical training, local support and technical supervision was also provided during the two campaigns 2016 and 2017 to transmit to these cooperatives all the know-how and prepare them to become autonomous in the management of their vegetable gardens without any external support to ensure the sustainability of the activity. Economically, during the 2018-2019 crop year, 70 ha of vegetable gardens were cultivated, totaling 189 919 kg of vegetables with an average yield per hectare of about 2713 kg. Each cooperative has on average consumed 30% of its production and sold 70%. Average income per cooperative was valued at 51,198 MRU (~1 422 USD). In addition to the income generated by the sale of excess vegetables, members of concerned cooperatives had acess to a fresh vegetables for a long period of the year, thus improving the nutritional quality of their meals. Also, the proximity of these vegetable gardens has allowed other members of the community to have fresh, good quality vegetables at affordable prices. In addition, the project provided training and equipment for 84 women and 5 men to master simple techniques for preserving and drying surplus vegetables from their gardens. This allowed them to provide an additional 2-3 months of vegetable availability at the household level. In addition to self-consumption and financial revenues, a dozen market gardening cooperatives, without external support, have reinvested part of their profits to finance the establishment of new income-generating activities (IGAs) such as butcheries, community shops or fishmongers. This can be seen as a direct effect of the project on improving food security and living conditions of the targeted beneficiaries. Today, 37 cooperatives are autonomous, skilled and continue to apply appropriate techniques for market gardening based only on their own resources. This is a summary of the training given to cooperatives: Training topic Nber of participants Women Men High value crop production 8 728 6 633 2 095 vegetable conservation 89 84 5 Cooperative management 80 28 52 | Extension staff and cluster population are aware of and apply appropriate techniques
Output 3.4: 4,000 technical staff and community leaders trained and equipped for poultry development. | Number of people (gender disaggregated) trained | Hardly any training is available in areas to be selected; extension staff requires training, too | This programme was executed in two phases. A first phase in 2016, which involved the establishment of 10 semi-intensive and 40 traditional poultry houses. The project fully funded the construction of the 50 equipped poultry houses, while the communities contributed with labour and provided supervision and support to the beneficiaries until their empowerment. Unlike the traditional poultry programme, which has experienced difficulties, the semi-intensive program has been a success. After the project financed their first campaign, the 10 semi-intensive poultry production cooperatives are now financially autonomous and have conducted up to 6 production campaigns on their own. In addition, two cooperatives in the Wilaya of Trarza have made profits and reinvested part of their profits to increase the production capacity of their poultry houses, generating even more profits and ensuring the supply of a larger community. Beyond the provision of white meat to the community, which improves food security and overall nutritional quality, this activity has generated profits for these cooperatives, some of which have reinvested part of their profits in other income-generating activities that help households to better cope with crisis situations. In terms of economic profitability, the net profit generated by 10 people who produce a band of 500 chickens is 41,000 MRUs (1 139 USD). The income per band and per woman is about 4,100 MRUs (~114 USD) and the income per woman per day is 136 MRUs (~3,8 USD). In view of the strong demand from the beneficiary communities for a semi-intensive poultry programme, the project has launched a second phase which has resulted in the establishment of Six (06) additional units which just went into production in February 2019. This program benefited 560 participants (80% women / 20% Young men) representing 3,360 direct beneficiaries. The traditional poultry programme was not as successful as the semi-intensive programme. In fact in 2017-2018 the project purchased and introduced more than 50 raceur cocks (roosters) in order to start the programme. Unfortunately 2017 and 2018 were very difficult years in terms of drought and high temperature which contributed to the loss of most of the raceur cocks which could not adapt to the difficult weather conditions. Nevertherless, we evaluated that 20% of the traditional poultry programme was successful. It has been found that there is no need to train extention staff because the "Program to Combat Rural Poverty through Support to Production Sectors(ProlPraf)" funded by the FIDA (17.8 Million USD) has been set up in Mauritania over a period of six years, has invested a lot in strengthening the technical capacities of the regional technical services of the Ministry of Agriculture in the field of Poultry farming. The objective of training 4000 technical staff and community leader was largely overestimated in the project document. The number of participants for semi-intensive poultry house or traditional poultry house must not exceed 10 people to be relevant. | Extension staff and cluster population are aware of and apply appropriate techniques
Output 3.5: 1,600 technical staff and community leaders trained and equipped for apiculture. | Number of people (gender disaggregated) trained | Hardly any training is available in areas to be selected; extension staff requires training, too | Eight Sites were targeted in 05 Wilayas where all the ecological and social conditions are met to guarantee the success of this activity. 2 sites in Trarza (Oum El Koura and Nassra 2), 3 sites in Gorgol (Haddad, Dimechgha and Dar El Beidha), 1 site in Brakna (Dounguel Réo), 1 site in Guidimakha (Ndeo) and 1 site in Tagant (Legdeim ). WFP supervised the procurement of equipment needed for the Programme implementation. The project hired Apidesert, a local specialised compagny, to oversee the Programme implementation and beneficiaries’ trainings. In each site an apiary of 30 hives was set up benefiting 10 families. The project also provided all the equipment necessary for the practice of beekeeping (Combinations, smokers, honey extractors, etc.) and provided the necessary training and technical supervision to 517 participants involved in this activity (284 women and 233 men) to ensure the success of the programme which was scheduled to be finalized in march 2018. Unfortunately, there was a setback during the campaign 2017-2018 due to drought, high winds and high temperature which led to the loss of bees and therefore no harvest. Thus, we decided to put the programme on stand by foreseeing better wheather conditions this year. The program was resumed in 2018 and the evaluation undertaken by the project showed that the result was mixed in 4 of the selected sites. This is largely due to the very difficult year 2017-2018, which was characterized by a large rainfall deficit and consequently a drought which affected the apiaries, some of which were completely dissipated. The project has decided to abandon these 4 sites and put all efforts on the other 4 sites where the results are quite interesting. A complement of beekeeping equipment was acquired and distributed to the beneficiaries with a program of support of proximity to ensure the good mastery of the management and the exploitation of the apiaries. We consider that is a good experience which should be consolidated in the framework of other initiatives and projects and/or replicated in other regions where this activity is potentially promising. | Extension staff and cluster population are aware of and apply appropriate techniques
Output 3.6: Approx. 20 community cereal banks established. | Deleted
Output 3.7: 30,000 fuel efficient stoves provided. | Number of fuel efficient stoves built by participating communities; share of reduced consumption of fuel wood | Fuel-efficient stoves are hardly know and available in areas to be selected – to be confirmed during adaptation planning (The communities of 10 villages already use improved stoves) | The promotion of improved dual prototype stoves (charcoal and wood) in the project intervention areas has the following main objectives: 1. Strengthening and supporting young volunteers and artisans as key actors in the manufacturing and distribution chain of improved stoves in Mauritania. 2. Improving the living conditions of vulnerable households, especially women, by reducing the time available for collecting wood for cooking and investing it for the benefit of the family and children. 3. Reducing deforestation and land degradation by improving energy efficiency in households. 4. Reducting green house gaz emissions, This mission was entrusted to the confirmed artisans and volunteers trained by the project with the supporte of NGO proejct partners. The programme has resulted in the manufacture and distribution of more than 20600 improved stoves to as many households in 73 project intervention sites. The impacts on women's conditions are remarkable. Evaluations conducted by NGOs have shown that, with two (02) hot (cooked) meals per day, the use of improved stoves compared to three-stone stoves makes it possible to: 1. Save up to 318 Kg of wood per household per year. 2. These avoided quantities of wood allow each household to save about 4,770 MRU (133 USD)/year. 3. Depending on the type of improved stove used (wood or charcoal), a woman can save between 19 and 43 days per year in avoided time in preparing meals that can be used in other household functions. | Communities know, understand and use fuel efficient stoves; fuel-wood consumption by participating households reduced by at least 40%
Output 3.8: 2,000 community members (mostly youth) trained to build and maintain fuel efficient stoves. | Number of people (gender-disaggregated) trained | No training is available in areas to be selected; extension staff requires training, too. 14 artisans are already trained to manufacture improved stoves) | The project provided capacity building and support to 179 young volunteers and artisans among 60 sites of the project in the 8 Wilayas. It intends to make them key players in the manufacturing and distribution chain of improved stoves in Mauritania. A five (05) days training session in manufactoring improved stoves, regrouping the young volunteers and artisans, was organised in each Wilaya. During the training session, the project purchased and provided free of charge to the artisans and volunteers a set of equipment kits and the raw material (sheet metal drums) necessary for the manufacture of the improved prototype stoves. The usefulness of these improved stoves was demonstrated and appreciated by participants and women in the concerned villages, following a real experience of comparing the energy efficiency of three stoves models to those traditionally used in the village. Among the artisans and volonteers who have confirmed their expertise in the manufacture of improved stoves, the project has engaged them in a major programme to manufacture and distribute improved stoves, which has reached more than 20,000 households in the 8 Wilayas. | In all participating communities a group of people regularly builds and repairs fuel-efficient stoves;

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The beneficiairies sensitization work and the close support given to them helped to change their perception towards the project, which now consider it as a partner. This was reflected in several villages by an unexpected in kind contribution which exceeded expectations. The positive effects of the project started to be visible following the implementation of some income-generating activities. The 10 semi-intensive poultry production cooperatives are now financially autonomous. To illustrate this success, two cooperatives in the Trarza Wilaya made profits and reinvested some of these profits in the expansion of their poutry houses and their production capacity. Moreover, many women have reinvested a portion of their profits in the creation of new income-generating activities without any support of the project. The multi-year intervention in the same villages with an integration of the activities shows the impact on the improvement of the resilience and the capacity of adaptation of the beneficiaries. This is most noticeable in villages where the project is supported by other partners with complementary activities.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | During the rainy season (June-August), many project sites become inaccessible due to the impracticability of the terrain. This situation is very cumbersome and causes a slowdown in the execution of activities. Also, DREDD as Regional responsibles for the environmental sector are fully busy with the bushfire campaign that runs from September to December of each year. In this period there is a lack in supervising project activity execution. NGOs recruitment at the beginning of 2017, helped attenuate this problem and improved the supervision of the project activities. Procurement tender procedures contributed also in delaying implementation. Sometimes qualified or suitable candidates are not always available. Due to these delays in the project and taking into account the recommendation of the Mid-Term Review, a request for the extension of project duration for additional 11 months was approved by the AF board. An additional no-cost extension was granted to allow the completion of the procurement process for audit services.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | WFP and MEDD requested the Adaptation Fund Board to approve the deletion of Project Output 3.6 (establishment of community cereal banks), and the reallocation of its budget to Outputs 3.3 (agro-pastoral income-generating activities) and 3.4 (poultry development), which has been approved by the Decision B.31-32/2 on 3 May 2018. The project Mid-term review underligned for Component 2, after two years of implementation and monitoring of Project's achievements, on one hand, differences, sometimes very considerable, between the initial unit costs considered in the project document and the actual costs (sand dune fixation, fuel wood plantation and vulnerable area protection). In the other hand, there was some difficulties of programming areas as initially planned, like in the case of fuel-wood village reforestation due to land ownership, regulatory and social constraints. So adjustments for the budgets and targets were proposed by the MTR for the Outputs 2.1, 2.2 and 2.3. to be realistic. The Adaptation Fund Board has approved all these proposed changes. | ;
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The workload of women has been taken into account. Adaptation measures to solve the problems of access to water, support for market gardening, poultry farming, grain mills, improved stoves and all other IGAs have benefited women and girls as a priority. Gender has been integrated throughout the training plan. 63% of trained participants are women.Facilitating access to water, . This strategy for women's empowerment is justified by the fact that women are among the groups most affected by climate change, particularly through their traditional role in seeking water and collecting wood, which are particularly difficult tasks. With this range of implemented activities, women have increasingly devoted more time to family and children, improving household living conditions and food security. Overall, the project targeted approximately 32,000 participants, 63% of whom were women.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The lesson learned that we can point out is the inter-sectoral participation in developing local adaptation to climate change action plans. Knowing that climate change is a transversal issue, the key success factors to elaborate and implement adaptation planning are tied to the close collaboration and participation of all sectoral institutions at the regional level, thus capacity building programme in integrating adaptation to climate change into local development planning has concerned not only DREDD, but also decentralized technical services and NGO at regional level. Also, the future projects/programmes should be designed in smaller areas, mainly in the current regions where the Country Strategic Programme has been implemented, in looking for convergence and synergy with others partners. The planification of the activities will meet the participatory approach through the PCP. Integrating many activities in a same village will conrtibute in building a real resilience to climate change. Future projects/programmes for enhenced resilience to climate change should run over more than 4 years to maximise efficiency.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Replication and upscaling of many of the project interventions is already done by beneficiairies in many project villages (traditional poultry farming, High crop production, Soil and water conservation building structures...). Mauritania AF project is now considered as the leading Climate Change project within MEDD and many other environmental projects are now seeking synergies to benefit from its experience.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Activities should be implemented by the communities themselves. Communities often have the know-how to implement several activities that require just a simple development to give more efficiency. A short training on these techniques gives them the ability to do things better. In addition, technical materials written in local language with a very simple pictures, may be developped by the project, to educate the community in topics related the climate change actions. Beneficiaries must also be taught to the concept of partnership in carrying out activities as well as ownership to feel they are owners of assets and thus maintain their sustainability. This ensures that assets created under the project can be maintained and extended even beyond the duration of the project. So we have to build on the technical capacity of communities that have been able for centuries to adapt to the various changes which have occurred.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Replication and scaling up of a large number of project interventions by the beneficiaries themselves (traditional poultry farming, market gardening, building structures for soil conservation and water conservation...), have been noteced in many project villages. The PARSACC project is now considered as the first project on climate change initiated by the MEDD and many other environmental and climate change projects have taken it as a model and have been inspired by its methodological, planning and implementation approaches.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The problem of access to water is a central issue for adaptation to climate change. By partially addressing these aspects, the project has substantially contributed to strengthening community resilience in various areas: agriculture, livestock, drinking water, and so on.
What measures are/have been put in place to ensure sustainability of the project/program results? | The project has forged strong links with communities by helping them to take charge of their own lives. The support provided in termes of capacity building and close support in the implementation of the set of activities, gave the communities a good enough ability to ensure a sustainable management of the acquired assets. The creation of community funds, managed by the Village Management Committees in a collective and transparent manner, is a very promising initiative which reflects a spirit of empowerment and strengthened social cohesion which guarantees the sustainability of the project achievements. Capacity development of Village Management Committees on rules for the management and exploitation of pastoral reserves, reforestation perimeters and sand dune fixation sites are also tools made available to communities to help them managing these assets in a sustainable manner. In addition, the DREDDs and other technical services are permanent structures with a sovereign mandate to support natural resource management and rural development programs, will continue to support the communities supported by the project through technical and the necessary support until their empowerment.
What measures are being/could have been put in place to improve project/program results? | Adaptation measures related to improving access to water have greatly improved the achievement of project results. These measures have contributed significantly to strengthening the resilience of communities to the adverse effects of climate change
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The project used different existing data sources to conduct vulnerability analyzes; namely data from FSMS surveys of WFP/CSA, ONS demographic data, and village surveys carried out by the project. The project used also the data of the different Mauritania's national communications on climate change and Monotoring System the the Environmental National Action Plan (SEPANE).
If learning objectives have been established, have they been met? Please describe. | Yes, several government focal points at central and regional level as well as representatives of civil society have been trained on several aspects such as climate change issues, participatory adaptation planning at local level. Also, members of the target communities were trained on different topics (High value crop production technics, cooperative management, poultry farming techniques, beekeeping techniques, dune fixation techniques, water and soil conservation work, planting techniques, management of pastoral reserves ...)
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | The project consultation process before the implementation has given specially learning opportunities for the regional technical services and local administrative authorities. Its participatory approach engaged the different stakeholders in a way by which they learned about climate change, its impacts on food security and the necessity to adapt to safeguard natural resources and livelihoods against climate impacts. During the project implementation, on-the job training, along with the different course trainings, technical support, and other forms of learning has enabled the different stakeholder groups to realize how they can effectively contribute to building resilience. All this has enhanced capacities of all stakholders to contributing to the different project outcomes.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | MTN/MIE/Food/2011/1/PD
Implementing Entity | WFP, Mauritania
Type of implementing entity | MIE
Country | Mauritania
Region | Africa
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 186718 | 37368 | 149350 | Total | 160590 | 23670 | 136920 | Total | 144769 | 20848 | 123921 | Total | 191526 | 31921 | 159605
|  | % of female beneficiaries | 59.15% |  |  | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 61% | 61% | 61% | % of female beneficiaries | 63% | 63% | 63%
|  | % of Youth beneficiaries | 43.6% |  |  | % of Youth beneficiaries | 8% | 8% | 8% | % of Youth beneficiaries | 20% | 20% | 20% | % of Youth beneficiaries | 20% | 20% | 20%
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Regional | 1 | 3: Dissemination and communication | Geographical coverage | Regional | 0 | 3: Dissemination and communication | Geographical coverage | Regional | 1 | 1: Risk knowledge | Geographical coverage | Regional
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 75 |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 75
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 300 | Multi-sector | 1: No capacity | Total | 300 | Multi-sector | 3: Medium capacity | Total | 213 | Multi-sector | 3: Medium capacity | Total | 337 | Multi-sector | 3: Medium capacity
|  | % of female targeted | 10% |  |  | % of female targeted | 10% |  |  | % of female targeted | 10.33% |  |  | % of female targeted | 14%
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 180 | 10% | Public |  | 180 | 10% | Public |  | 118 | 6.78% | Public |  | 187 | 11% | Public
|  | 120 | 10% | NGO |  | 120 | 10% | NGO |  | 95 | 14.74% | NGO |  | 150 | 17% | NGO
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 1: No capacity | Public | National | Multi-sector | 3: Medium capacity | Public | National | Multi-sector | 3: Medium capacity | Public | National | Multi-sector | 3: Medium capacity
|  | Public | Regional | Multi-sector | 1: No capacity | Public | Regional | Multi-sector | 3: Medium capacity | Public | Regional | Multi-sector | 3: Medium capacity | Public | Regional | Multi-sector | 3: Medium capacity
|  | NGO | Regional | Multi-sector | 1: No capacity | NGO | Regional | Multi-sector | 3: Medium capacity | NGO | Regional | Multi-sector | 2: Low capacity | NGO | Regional | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Other | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Other | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 1000 | ha protected | 1: Ineffective | Rangelands | 1000 | ha protected | 4: Effective | Rangelands | 1000 | ha protected | 4: Effective | Rangelands | 1000 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 500 | ha protected | 1: Ineffective | Catchment area/Watershed/Aquifer | 500 | ha protected | 4: Effective | Catchment area/Watershed/Aquifer | 300 | ha protected | 4: Effective | Catchment area/Watershed/Aquifer | 440 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 400 | ha protected | 1: Ineffective | Forests | 400 | ha protected | 4: Effective | Forests | 273 | ha protected | 4: Effective | Forests | 460 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 1000 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 1000 | ha rehabilitated | 4: Effective | Cultivated land/Agricultural land | 300 | ha rehabilitated | 3: Moderately effective | Cultivated land/Agricultural land | 370 | ha rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 900 | ha protected | 1: Ineffective | Other | 900 | ha protected | 4: Effective | Other | 525 | ha protected | 4: Effective | Other | 955 | ha protected | 4: Effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 16983 | Agricultural-related |  | 356.2333 |  | Agricultural-related |  |  | 12911 | Agricultural-related |  |  | 14696 | Agricultural-related
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 72 | Fishing |  | 775.7767 |  | Fishing |  |  |  | Fishing
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 688 | Forestry |  | 372.36 |  | Forestry |  |  | 979 | Forestry
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 15069 | Livestock production |  | 1115.2 |  | Livestock production |  |  | 720 | Livestock production
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 3090 | Services |  | 1563.3067 |  | Services |  |  | 35 | Services
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on H102: GADER Ghazi: Sand dune fixation
Note on K119: GADER Ghazi: Income level will be evaluated after the project termination
Note on L119: GADER Ghazi: Ménages ayant bénéficiés des activités : Maraichage, Aviculture, Arboriculture, Apiculture
Note on L127: GADER Ghazi: Veterinary Assistnants

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.