## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | October 16th 2020 - October 15th 2021
| Project Title: | AYNINACUY: Strengthening the livelihoods for vulnerable highland communities in the provinces of Arequipa, Caylloma, Condesuyos, Castilla and La Union in the Region of Arequipa, Peru
| Project Summary: | The project objective is to reduce vulnerability and increase adaptive capacity to respond to the impacts of climate change of the highland Andean peasant communities in the provinces of Arequipa, Caylloma, Castilla, La Union, and Condesuyos. In view of the fact that these communities depend almost exclusively on the production of alpaca fiber, the Project seeks to reduce their exposure to the threats of climate risk, through the strengthening of their livelihood through the development of adaptation processes and reduction of climate change risks which grant resilience to this way of life and through the strengthening of capacities of the communities for reducing the risks associated with the economic losses resulting from the effects of climate change. The project promotes the breeding of alpaca and improves fiber production, as well as providing access to safe water and housing in producing communities in extreme poverty. The project includes the installation of SAT early warning modules, improvement of levees, improvement of rustic channels to optimize water management to expand wetlands in Andean highland areas, reconstruction of outhouses to improve sanitary conditions and prevent mortality of pregnant female alpacas and newly born offspring, as well as the placement of protection fences and cultivation of pastures for forage.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PER / RIE / Rural / 2015/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | CAF - Development Bank of Latin America | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Regional Implementing Entity (RIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Peru | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Peasant communities in the provinces of Arequipa, Caylloma, Condesuyos, Castilla y La Union: San Juan de Tarucani, Huayllacucho, Sarpani, Misahuanca, San Antonio, Rio Blanco, Tolconi I, Huaracopalca, Chapacoco, CuspaMaghuanca, Pampamarca, Tecca-Rumiwasi, Huayqui, Huarcaya, Ancaro, Visca, Cristal Puquio, Chojanilayoc,Arirahua, Huamanmarca, Huchumiri I, Huchumiri II, Capilla, Maucallacta, Pusa Pusa, Santa Rosa, Ran Ran, Chungara,Tres estancias,Condorcuyo, Hanansaya I, Hanansaya II, San Antonio de Chuca and Vincocaya. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | March 17, 2017
IE-AFB Agreement Signature Date: |  | September 8, 2017 / Addendum date: August 21, 2018 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | October 15, 2018 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
| Original Completion Date: | april 15, 2021
Revised Completion Date after approval of |  | july 15, 2021 Decision B.35.b/16
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://www.copasa.gob.pe/proyectos/proyecto-ayninakuy/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Maria Angelica Salinas Valencia | Dominican Republic
| Email: | mariangelicasv@hotmail.com | Ecuador
| Date: | 15/10/2018 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Sra. Laura Secada Daly. - General Director of the General Directorate for Climate Change and Desertification - Ministry of Environment of Peru | Equatoral Guinea
| Email: | lsecada@minam.gob.pe | Eritrea
| Date: | 09/11/2019 (RM 343-2019-MINAM) | Estonia
| Implementing Entity |  | Ethiopia
| Name: | María Carolina Torres / Carolina Cortés - Development Bank of Latin America - CAF | Fiji
| Email: | mctorres@caf.com / acortes@caf.com | Finland
| Date: | 15/10/2018 | France
| Executing Agency |  | Gambia
| Name: | Jaime Abarca Huanca- Executive Director - Cooperation for Sustainable Development in Arequipa -COPASA-Arequipa's Regional Government | Georgia
| Email: | jabarcah@copasa.gob.pe | Germany
| Date: | 2020-05-13 | Ghana
| Executing Agency |  | Greece
| Name: | Maria Argüello (Executive Director of the Consortium for the Sustainable Development of the Andean Eco region - CONDESAN) | Grenada
| Email: | maria.arguello@condesan.org | Guatemala
| Date: | 15/10/2018 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The exchange rate for the PEN/USD is not holding above 3.43 | NA | NA
The restrictions foreseen for water resources are increased meaningfully by unforeseeable effects of climate change and of its variability. | NA | NA
Resistance to change in vulnerable communities | NA | NA
The project’s dissemination, communication and motivation strategies are not effective for achieving a broad and active participation on the part of women. | NA | NA
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Climate change manifests itself differently and with greater intensity than projected by analyzes and studies. This could affect the success of particular adaptation measures that will be tested throughout the project’s life. | NA | NA
Change of the Regional Government and local authorities, who will have to commit themselves to a project they are unfamiliar with. A few months will be required for them to comprehend the advantages of the climate change adaptation project. | NA | N/A
Salaries for the Field Technical Specialists – Yachachiqs, and the Field Supervisor are below the market value. | NA | N/A
In the proposal design, only one (1) Field Supervisor was considered: | NA | N/A
Delay in activities due to the impact of the COVID-19 crisis | NA | NA
Change of government and / or officials at the national level due to political instability: (the implementation of the project occurs in a scenario with several changes of the presidential mandate) new officials in the Ministry of the Environment and Public Entities linked to the management of the project requires several months of learning to fulfill commitments. | NA | NA
(1) https://busquedas.elperuano.pe/normaslegales/decreto-supremo-que-declara-el-estado-de-emergencia-en-vario-decreto-supremo-n-010-2020-pcm-1848440-1/ https://busquedas.elperuano.pe/normaslegales/decreto-supremo-que-declara-el-estado-de-emergencia-en-vario-decreto-supremo-n-012-2020-pcm-1850691-2/ (2) https://www.indeci.gob.pe/wp-content/uploads/2020/09/INFORME-DE-EMERGENCIA-N%C2%BA-621-26SEP2020-BAJAS-TEMPERATURAS-EN-EL-DEPARTAMENTO-DE-AREQUIPA-10.pdf
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Financial Data
Financial information PPR 1: cumulative from project start to October 15, 2019 |  |  |  | Financial information PPR 2: cumulative from project start to October 15, 2020 |  |  |  | Financial information PPR 3: cumulative from project start to October 15, 2021
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of of October 15, 2019 | 723956 |  |  | Estimated cumulative total disbursement as of of October 15, 2020 | 1692034.37 |  |  | Estimated cumulative total disbursement as of November 30, 2021 | $ 2,306,173.8.
Add any comments on AF Grant Funds. (word limit=200) | This is the amount that CAF has transferred to the Administrative Executing Entity- CONDESAN. However, AF has transferred a total of USD 923, 255 to the Implementing Entity, CAF. The transfer made by CAF to CONDESAN is based on clause 13 of the Agreement signed between CAF-CONDESAN-COPASA, which states: "CAF will contribute the Funds for the Project, which will be disbursed to the Administrative Executing party, once CAF submits the corresponding disbursement request, which accredits compliance with the Agreement, to CAF's satisfaction The amount of payments to be transferred by CAF to the Administrative Executing party will be transferred up front, on a semi-annual basis, according to the updated semi-annual Acquisition Plan, and according to the level of budget execution (for amounts agreed between the Administrative Executing party and CAF)." |  |  | Add any comments on AF Grant Funds. (word limit=200) | This is the amount that CAF has transferred to the Administrative Executing Entity- CONDESAN. AF has transferred a total of USD 1,867,172 (two disbursements) to the Implementing Entity, CAF. With the presentation of this report, the third disbursement of USD 1,030,589 is requested. This is required to December 2020 to be able to continue the execution and finish the project in 2021 |  |  | Add any comments on AF Grant Funds. (word limit=200) | This is the amount that CAF has transferred to the Administrative Executing Entity- CONDESAN. (See ANNEX I Remesas Recibidas_PY181_Ago2018-Set2021.pdf) AF has transferred a total of USD 2,897,761 (thre disbursements) to the Implementing Entity, CAF.
INVESTMENT INCOME | USD 562 |  |  | INVESTMENT INCOME | USD 829.18 |  |  | INVESTMENT INCOME | 24946.84 |  | *
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| COMPONENT 1: APPLICATION OF MEASURES AIMED AT STRENGTHENING MEANS OF SUBSISTENCE AND SOURCES OF INCOME FOR VULNERABLE COMMUNITIES | 285855.04 |  | II_ANNEX I is attached: detail of expenses executed in the second year. | COMPONENT 1: APPLICATION OF MEASURES AIMED AT STRENGTHENING MEANS OF SUBSISTENCE AND SOURCES OF INCOME FOR VULNERABLE COMMUNITIES | 1155016.73 |  |  | COMPONENT 1: APPLICATION OF MEASURES AIMED AT STRENGTHENING MEANS OF SUBSISTENCE AND SOURCES OF INCOME FOR VULNERABLE COMMUNITIES | 1839481.62
| ANIMAL NOURISHMENT AND PROTECTION AXIS | 267049.99 |  |  | ANIMAL NOURISHMENT AND PROTECTION AXIS | 732032.32 |  |  | ANIMAL NOURISHMENT AND PROTECTION AXIS | 1288681.4
| Products 1.1.1: shelters built for animal protection (in particular alpaca dams and offspring) | 115829.58 |  |  | Products 1.1.1: shelters built for animal protection (in particular alpaca dams and offspring) | 357751.1 |  |  | Products 1.1.1: shelters built for animal protection (in particular alpaca dams and offspring) | 590919.47
| Products 1.1.2: Protective fences, with livestock netting, installed. | 30761.75 |  |  | Products 1.1.2: Protective fences, with livestock netting, installed. | 71347.94 |  |  | Products 1.1.2: Protective fences, with livestock netting, installed. | 210210.21
| Products 1.1.3: Seeding and cultivation of high altitude forage cereals. | 111544.97 |  |  | Products 1.1.3: Seeding and cultivation of high altitude forage cereals. | 244946.88 |  |  | Products 1.1.3: Seeding and cultivation of high altitude forage cereals. | 376115.27
| Products 1.1.4: Seeding and cultivation of improved grasses. | 764.58 |  |  | Products 1.1.4: Seeding and cultivation of improved grasses. | 29410.67 |  |  | Products 1.1.4: Seeding and cultivation of improved grasses. | 29797.37
| Products 1.1.5: Installation of clover in wetlands for improving forage cover | 1185.91 |  |  | Products 1.1.5: Installation of clover in wetlands for improving forage cover | 2636.3 |  |  | Products 1.1.5: Installation of clover in wetlands for improving forage cover | 7655.79
| Products 1.1.6: Animal health campaigns in selected rural communities | 6963.2 |  |  | Products 1.1.6: Animal health campaigns in selected rural communities | 25939.43 |  |  | Products 1.1.6: Animal health campaigns in selected rural communities | 73983.29
| WATER RESOURCE MANAGEMENT AXIS | 18805.05 |  |  | WATER RESOURCE MANAGEMENT AXIS | 180353.87 |  |  | WATER RESOURCE MANAGEMENT AXIS | 228473.2
| Products 1.2.1: Pressurized irrigation modules installed in selected communities. | 7135.86 |  |  | Products 1.2.1: Pressurized irrigation modules installed in selected communities. | 126756.1 |  |  | Products 1.2.1: Pressurized irrigation modules installed in selected communities. | 144847.7
| Product 1.2.2.: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability. | 734.52 |  |  | Product 1.2.2.: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability. | 4971.16 |  |  | Product 1.2.2.: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability. | 4971.16
| Products 1.2.4: Construction of reservoirs for storage of rainfall, runs or natural sources (springs). | 10934.67 |  |  | Products 1.2.3: Construction and improvement of canals to optimize the water resource management in wetlands. | 4919.97 |  |  | Products 1.2.3: Construction and improvement of canals to optimize the water resource management in wetlands. | 15021.91
| COMPONENT 2: IMPLEMENTATION OF MEASURES AIMED AT STRENGTHENING INSTITUTIONAL AND COMMUNITY CAPACITIES TO REDUCE RISKS OF LOSSES OCCASIONED BY CLIMATE CHANGE. | 18538 |  |  | Products 1.2.4: Construction of reservoirs for storage of rainfall, runs or natural sources (springs). | 43706.64 |  |  | Products 1.2.4: Construction of reservoirs for storage of rainfall, runs or natural sources (springs). | 63632.43
| KNOWLEDGE MANAGEMENT AXIS | 18538 |  |  | ATTENTION TO HUMAN HEALTH AXIS | 242630.54 |  |  | ATTENTION TO HUMAN HEALTH AXIS | 322327.02
| Products 2.3.3: Elaboration of technical guides | 18270.32 |  |  | Products 1.3.1: Water Purification Systems installed in the most vulnerable communities, in order to reduce the incidence of diarrheal diseases | 71725.95 |  |  | Products 1.3.1: Water Purification Systems installed in the most vulnerable communities, in order to reduce the incidence of diarrheal diseases | 93251.65
| Products 2.3.4: Training sessions about: | 267.68 |  |  | 1.3.2.2. 72 Composting latrines built | 55996.18 |  |  | 1.3.2.2. 72 Composting latrines built | 80224.72
| TOTAL DIRECT COSTS = (COSTS SUB COMPONENTS 1 +2 OF THE PROJECT), USD | 304393.04 |  |  | 1.3.2.3. 72 of Improved stoves built | 15305.04 |  |  | 1.3.2.3. 72 of Improved stoves built | 15305.04
| PROJECT EXECUTION COST / ADMINISTRATIVE EXPENSES | 71173.89 |  |  | 1.3.2.4. 72 photovoltaic panels installed | 75437.35 |  |  | 1.3.2.4. 72 photovoltaic panels installed | 101363.45
| A.- PROFESSIONAL SERVICES | 65949.78 |  |  | 1.3.2.5. 72 Solar walls | 24166.02 |  |  | 1.3.2.5. 72 Solar walls | 32182.16
| B.- TICKETS AND PER DIEMS | 457.53 |  |  | COMPONENT 2: IMPLEMENTATION OF MEASURES AIMED AT STRENGTHENING INSTITUTIONAL AND COMMUNITY CAPACITIES TO REDUCE RISKS OF LOSSES OCCASIONED BY CLIMATE CHANGE. | 36093.42 |  |  | COMPONENT 2: IMPLEMENTATION OF MEASURES AIMED AT STRENGTHENING INSTITUTIONAL AND COMMUNITY CAPACITIES TO REDUCE RISKS OF LOSSES OCCASIONED BY CLIMATE CHANGE. | 116969.71
| C.- VISIBILIZATION /DISSEMINATION | 230.07 |  |  | RISK AND CLIMATE CHANGE MANAGEMENT AXIS | 7269.96 |  |  | RISK AND CLIMATE CHANGE MANAGEMENT AXIS | 7269.96
| F.- ENVIRONMENTAL MANAGEMENT MONITORING AND EVALUATION | 4536.51 |  |  | Products 2.2.2: Implementation of teaching modules for early warning systems EWS in rural communities | 7269.96 |  |  | Products 2.2.2: Implementation of teaching modules for early warning systems EWS in rural communities | 7269.96
| TOTAL DIRECT + INDIRECT COSTS, USD | 375566.93 |  |  | KNOWLEDGE MANAGEMENT AXIS | 28823.46 |  |  | KNOWLEDGE MANAGEMENT AXIS | 109699.75
[5 empty] | Products 2.3.3: Elaboration of technical guides | 25399.94 |  |  | Products 2.3.1: Preparation of agreements, programs, projects that lend continuity to project activities and achievements. Products 2.3.2: Publication of lessons learned in COPASA’s website and of the organizations that include a similar dissemination in their corresponding websites | 54861.35
| PROJECT IMPLEMENTATION COSTS, USD | 0 |  |  | Products 2.3.4: Training sessions about: | 3423.52 |  |  | Products 2.3.3: Elaboration of technical guides | 34222.94
[9 empty] | Products 2.3.4: Training sessions about: | 20615.46
[5 empty] | TOTAL DIRECT COSTS = (COSTS SUB COMPONENTS 1 +2 OF THE PROJECT), USD | 1191110.15 |  |  | TOTAL DIRECT COSTS = (COSTS SUB COMPONENTS 1 +2 OF THE PROJECT), USD | 1956451.33
[5 empty] | PROJECT EXECUTION COST / ADMINISTRATIVE EXPENSES | 159628.73 |  |  | TOTAL INDIRECT COSTS =PROJECT EXECUTION COST / ADMINISTRATIVE EXPENSES | 251116.53
[5 empty] | A.- PROFESSIONAL SERVICES | 142591.77 |  |  | A.- PROFESSIONAL SERVICES | 198194.28
[5 empty] | B.- TICKETS AND PER DIEMS | 626.67 |  |  | B.- TICKETS AND PER DIEMS | 626.67
[5 empty] | C.- VISIBILIZATION /DISSEMINATION | 230.07 |  |  | C.- VISIBILIZATION /DISSEMINATION | 230.07
[5 empty] | F.- ENVIRONMENTAL MANAGEMENT MONITORING AND EVALUATION | 16180.22 |  |  | F.- ENVIRONMENTAL MANAGEMENT MONITORING AND EVALUATION | 52065.51
[5 empty] | TOTAL DIRECT + INDIRECT COSTS, USD | 1350738.88 |  |  | TOTAL DIRECT + INDIRECT COSTS, USD | 2207567.86
[5 empty] | TOTAL | 1350738.88 |  |  | TOTAL | 2207567.86
| TOTAL | 375566.93 | [6 empty] | * The APCI with letter No579-2021- APCI-DOC authorizes the return of the IGV and IPM a total of $10,279.70, of the tax period from March to June 2019. The APCI with letter No1157-2021-APCI-DOC authorizes the return of the l IGV and IPM a total of $14,667.14, of the tax period from July to December 2019. These amounts have been credited to the project's bank account. (See ANNEX I Remesas Recibidas_PY181_Ago2018-Set2021.pdf, ANNEX II Remesas Recibidas_PY181_oct-nov 2021.pdf, ANNEX III CARTA No579-2021- APCI-DOC_PY Ayninacuy.pdf, ANNEX IV CARTA No1157-2021-APCI-DOC_PY AYNINACUY.pdf)
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST al segundo año | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| COMPONENT 1: APPLICATION OF MEASURES AIMED AT STRENGTHENING MEANS OF SUBSISTENCE AND SOURCES OF INCOME FOR VULNERABLE COMMUNITIES | 1140218.92 |  | Periode of october 16, 2020 to june 15,2021. See III_ANNEX I | COMPONENT 1: APPLICATION OF MEASURES AIMED AT STRENGTHENING MEANS OF SUBSISTENCE AND SOURCES OF INCOME FOR VULNERABLE COMMUNITIES | 789309.6036 | 2021-04-15
| ANIMAL NOURISHMENT AND PROTECTION AXIS | 644159.74 | 2020-10-15 |  | ANIMAL NOURISHMENT AND PROTECTION AXIS | 394398.3382 | *
| WATER RESOURCE MANAGEMENT AXIS | 244170.16 | 2020-10-15 |  | WATER RESOURCE MANAGEMENT AXIS | 45477.6546
| ATTENTION TO HUMAN HEALTH AXIS | 251889.02 | 2020-10-15 |  | ATTENTION TO HUMAN HEALTH AXIS | 349433.6107 | *
| COMPONENT 2: IMPLEMENTATION OF MEASURES AIMED AT STRENGTHENING INSTITUTIONAL AND COMMUNITY CAPACITIES TO REDUCE RISKS OF LOSSES OCCASIONED BY CLIMATE CHANGE. | 141130.63 |  |  | COMPONENT 2: IMPLEMENTATION OF MEASURES AIMED AT STRENGTHENING INSTITUTIONAL AND COMMUNITY CAPACITIES TO REDUCE RISKS OF LOSSES OCCASIONED BY CLIMATE CHANGE. | 133213.1553 | 2021-04-15
| GOVERNANCE AXIS | 1791.41 | 2020-10-15 |  | GOVERNANCE AXIS | 1791
| RISK AND CLIMATE CHANGE MANAGEMENT AXIS | 28455.88 | 2020-10-15 |  | RISK AND CLIMATE CHANGE MANAGEMENT AXIS | 23632.3686
| KNOWLEDGE MANAGEMENT AXIS | 110883.34 | 2020-10-15 |  | KNOWLEDGE MANAGEMENT AXIS | 107789.7867
| PROJECT EXECUTION COST / ADMINISTRATIVE EXPENSES | 75072 |  |  | PROJECT EXECUTION COST / ADMINISTRATIVE EXPENSES | 103361.53 | 15/06/2021**
| A.- PROFESSIONAL SERVICES | 64392 | 2020-09-30 |  | A.- PROFESSIONAL SERVICES | 47542.48
| B.- TICKETS AND PER DIEMS |  |  |  | B.- TICKETS AND PER DIEMS | 1500
| C.- VISIBILIZATION /DISSEMINATION |  |  |  | C.- VISIBILIZATION /DISSEMINATION | 2000
| E.- TRANSPORT AND MOVES |  |  |  | E.- TRANSPORT AND MOVES | 0
| F.- ENVIRONMENTAL MANAGEMENT MONITORING AND EVALUATION | 10680 |  |  | F.- ENVIRONMENTAL MANAGEMENT MONITORING AND EVALUATION | 52319.05
| TOTAL | 1356421.55 |  |  | TOTAL | 1025884.2889
Note: (*)The projection of expenses for the next period (see II_ANNEX II) shows a balance of 764,311.82, as a result of savings from various activities. With this balance, it is proposed to increase the goals of Products 1.1.1, 1.1.2(ANIMAL NOURISHMENT AND PROTECTION AXIS), 1.3.1 and 1.3.2 (ATTENTION TO HUMAN HEALTH AXIS). It has the approval of the Advisory Committee for the fulfillment of goals. As soon as there is a response to the approval from the Fund, the Technical Executing entity COPASA will update its acquisition plan.
[5 empty] | (**) It is required to cover the expenses of the administrative staff, for a period of two months (USD 15,236), after the closure of the project, for activities related to the closure: i) organization of the information, ii) preparation of the Closure Report, iii) attention to external auditors , iv) monitoring and consolidation of agreements, among others.Although it was not foreseen in the initial budget, the fund is requested that the balance of the indirect cost be available for the closing of the project. (See III_ANNEX I). These projections will be subject to review by the AF. |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | • Physical and cultural heritage. • Protection of protected natural areas and natural resources. | 1. At the beginning of the Project, the Project Director verifies with the environmental authority, whether the requirement to submit the Project’s Environmental and Social Management Report (ESMR) is applicable. 2. The Project Director follows up every two weeks to the environmental authority’s response to the consultation regarding the applicability of the requirement to submit the Environmental and Social Management Report (ESMR). 3. In the event that the response to the consultation to the environmental authority (regarding the applicability of the requirement to submit the Project Environmental and Social Management Report (ESMR) implies the need for the Project to assume commitments with regard to the Ministry of Environment, the Project Director will provide a timely response to the required commitments. 4. The Project’s Field Supervisor is executing the plan on a timely basis, in order to respond to commitments in the ESMR. 5. The Field Supervisor verifies the current regulations in environmental matters and physical and cultural heritage before scheduling a field activity, following the planned procedures and, if applicable, informs the competent activity. | (1) Coordination meetings with environmental authorities (2) Document attended (Environmental Management Report) (3) (4) Technical report (5) Field activities carried out to date have not breached any environmental regulations. | Coordination Meeting with the Environmental Authority - SERNANP Semiannual Environmental and Social Management Report, from the Project Director Monthly report of the Field Supervisor on the activities carried out, addressed to the Project Director | (1) (2) Technical meetings were coordinated with the Directors of the Salinas and Aguada Blanca Reserve and the Cotahuasi Sub-Basin Landscape Reserve. During these meetings, it was confirmed that the activities carried out will not generate a greater impact in the targeted areas superimposed on the reserve’s buffer area, because these activities only contribute to the improvement of the dwellings and productive units of the settled population. (2) The Technical Opinion Compatibility Report 954-2018-SERNANP-DGANP was issued by SERNANP (4) The field supervisor reported the measures implemented in the field pertaining to products 1.1.1 Improvement of sheds and 1.1.2 Fences of livestock mesh. | There were no impacts.
2 - Access and equity |  |  | •Effectiveness of the calls •Lack of trust from the community, due to similar projects that were not successful | Regarding the risk in the effectiveness of the calls (in their contacts and motivation), at the following levels: 1.i. COPASA towards local authorities; 1.1. For each cycle of calls, the Project Field Supervisor prepares a synthesized proposal for the call. 1.2 The previous call proposal is reviewed, commented and authorized by the Project Director, who copies the final proposal to the COPASA’s Executive Director and to CAF- Implementing Entity. 1.3. The Project Field Supervisor initiates or implements the call proposal authorized by the Project Director. 1.5. The Environmental Specialist submits an evaluation report to the Project Director, who attaches it to the project’s periodic monitoring and evaluation reports. 1.6. It is the responsibility of the Project Director to verify that each authorized call proposal includes the relevant lessons learned that the Project may have generated. 2. At level ii. The local authorities (district mayors) towards the communities’ representatives, through other figures of the district authorities (vice governors, sub-prefects, commissioners, others) and through community leaders. 2.1. At the beginning of the Project, the Field Supervisor will prepare a list of critical contacts for each District (including contacts for each community, responsibilities, names and, if possible, phone numbers). 2.2. As of the first meeting, the Field Supervisor will be responsible for reaching agreements between the leaders and representatives of each community, organizing a network of key contacts (for each critical contact, two alternative means to deliver information). 2.3. The Field Supervisor initiates and implements the call proposal, authorized by the Project Director. 2.4 In case there are errors made by the Field Technical Specialists that could lead to shortfalls in the calls, these will put in writing by the Field Supervisor. 2.5 The Field Supervisor verifies: - Compliance of the agreements for the selection of direct beneficiaries -The effective call made to community members during the training and instruction sessions. -Compliance with the quarterly schedule of training activities and field days. The role of the activities is shared with the district mayors. 3. Regarding the risk in the coherence of the preparation of the agreements: the agreements must be practical and socially viable. 3.1. An agreement will be drawn up for each of the 18 selected districts and 36 communities targeted by the Project, in order to decide the mechanism to select the direct beneficiaries of the following activities: a. Sheds for camelids, fences, cattle mesh, rustic water canals, rustic reservoirs, pressure irrigation modules. b. Improved housing c. Seeds for the cultivation of forage cereals at altitude, seeds for improved pastures at altitude, seeds to install clovers in wetland buffer areas. d. Tools to improve rustic canals, to optimize water management. e. Supplies for animal health campaigns. f. Training workshops 3.2. As a direct beneficiary of the activities described in items a. and b., the following will be designated: -The head of each productive family unit -Or the representative from a group of two or more families from productive units (in the latter case, members sign a commitment clause where they agree to share these spaces). 3.3. To aspire to become a direct beneficiary of the activities described between a. and e. above, the candidate must have participated in one or more of the corresponding training workshops. 3.4. To aspire to become a direct beneficiary of the activities described between a. and d. above, the candidate must commit to comply with the number of work hours or days set per activity, which must be defined in an agreement signed by the beneficiary. 3.5. Before signing each agreement, the Project Field Supervisor is responsible for distributing a list of the resources available for each activity. 4. Regarding the follow-up to the agreements in decision making processes. 4.1. In all meetings where at least one decision is made related to the selection of direct beneficiaries, the meeting minutes will include written evidence of this decision and all interested parties participating in the meeting will sign the minutes. 4.2. To make such a decision, a complete written copy of the minutes of each meeting must be available, and these minutes must include the agreements for the selection of direct beneficiaries. 4.3. The procedures followed to select the beneficiaries are explained to the community, and a clause acknowledging the selection process will be included in the minutes. In agreements made prior to the Project’s activities or its outputs. 5. Before the beginning of an activity cycle or developing a Project output, the Project Field Supervisor is responsible for: 5.1. Verifying that a workplan is prepared for the development of the activities or products. 5.2. Verifying that the workplan for the implementation of the activities or products is shared with the corresponding beneficiaries and participants. 5.3. Verifying that the contributions, opinions and requests of the beneficiaries and participants regarding the workplan for the implementation of the activities or products and its implications, are included in its dissemination. 5.4. If the beneficiaries request any modifications to the workplan, these will be submitted to the consideration of the communal Assembly . 5.5. Verifying that during the dissemination of the workplan, community members’ comments, opinions, requests or complaints and concerns related to other aspects of the project, are compiled in writing to the project Director and that the response is communicated in a timely manner to the community. | (1.1) (1.2) Plan implemented (1.3) Technical report (2.1) Directory implemented (2.2) Signed Agreements and/or Minutes (2.3) Planning the call (2.4) (2.5) Monthly Technical Report. Monthly oversight report (2.5) Attendance lists Signed agreements and/or Minutes (3.1) (3.2) Signed agreements (3.3) Attendance list (3.4) Commitment minutes Report Delivered (4.1)(4.2)(4.3)(4.4)Meeting Minutes Signed minutes (5.5) Monthly report | Training Development Plan and coaching sessions. Field Technical Experts' monthly progress report Field Supervisor’s monthly project progress report. Project Director’s Quarterly Project Progress Report 2,1 Directory of Stakeholders (2.2) 4 agreements with Provincial Governments, 18 agreements with district governments and 36 minutes signed and ratified (2.3) Call plan proposal submitted to the Project Director (2.4) Monthly activities report from Field Technical Experts (2.4) (2.5) Field Supervisor’s quarterly project progress report (3.1) (3.2) District and Communal Agreements signed (3.1) (3.2) Minutes signed by the beneficiaries (3.3) Attendance list of training sessions (3.4) Minutes signed by the beneficiaries Field supervisor Monthly Report (4.1)(4.2)(4.3)(4.4) Minutes of community meetings 1 workplan 36 agreement minutes per meeting Field Supervisor’s monthly report on Plan compliance Project Director’s Quarterly Report | (1.1) (1.2) The Training Plan was prepared, and it includes the activities to carry out the calls: Objectives, call activities, contents of the calls, a list of the leaders/representatives or contacts to be convened and support strategy or strategies. (1.3) The Field Supervisor made the call before the field work, as follows: - initiated the call, in January 2019, with local authorities, to sign the agreements to initiate Project activities (outputs 2.1.1 and 2.2.2, 2.3.1) - In April 2019, the call for activities 1.1.1 Improvement of sheds and 1.1.2 Fences of livestock mesh and 2.3.4 Training sessions for the improvement of sheds and installation of fences began. (2.1) The directory was prepared in accordance with the map of stakeholders and development of a directory with key stakeholders: - Governmental: Mayors, Municipality’s Agricultural Technician, President and vice president of the community. - At the educational level, the director of the Local Educational Management Unit (UGEL) was identified. - Head of the Natural Reserve - Head of the Landscape Reserve - Head of Agrarian Agency of the 5 provinces. - Director of SENAMHI -Arequipa. - Head of the Regional Office of Civil Defense (2.2) There are signed agreements from 5 provinces: Arequipa, Caylloma, Castilla, Condesuyos and La Unión. 18 districts: S.J. Tarucani, Orcopampa, Pampacolca, Chachas, Chilcaymarca, Puyca, Pampamarca, Huaynacotas, Toro, Chuquibamba, Andaray, Yanaquihua, Salamanca, Caylloma, Tuti, Sibayo, Callalli, San Antonio de Chuca 36 communities: S.J.Tarucani, Huayllacucho, Sarpani, Misahuanca, San Antonio, Rio Blanco, Toconi I, Huaracopalca Chapacoco, Huilluco, Cuspa, Maghuanca, Pampamarca, Tecca-Rumihausi, Huayqui, Huarcaya,Ancaro, Visca, Cristal puquio, Chojanilayoc, Arirahua, Huamanmarca/Ochuro/Tumpullo, Huchumiri I, Huchumiri II, Capilla / Pucuncho I, Maucallacta , Pucuncho II, Pusa Pusa, Caylloma/ Santa Rosa, Ran Ran, Tuti / Chungara, Tres Estancias, Condorcuyo, Hanansaya I, Hanansaya II, San Antonio de Chuca, Vincocaya / Imata. (2.3) The Field Supervisor implemented the call proposal, coordinating on a monthly basis with the Field Technical Specialists. Invitations to the activities were carried out effectively: presenting and increasing awareness of the project at the local and community level, presenting the Activity Plan, the training program, selecting the beneficiaries, and implementing training sessions to improve sheds and fences. (2.4) (2.5) The Field Supervisor verified the selection agreements with local and communal authorities, and identified the following: -In 95% of the districts the initial communal assembly commitments were met. - The Mayor of the Anduaga district is not willing to be part of the project due to political discrepancies with his predecessor. Given this situation, the Mayor of Pampacolca’s request for the project to benefit the communities in her district was approved. - There is still limited participation of women, in 3 communities (10%) because their communities are in very dispersed areas. These communities are Rio Blanco, Cristal Puquio, Huilluco. To improve the call, work will be carried out in advance in order to engage the participation of more women. There are 71 attendance lists for training events, prior to the implementation of activities to improve the sheds and install the fences. There are 18 District agreements and 36 communal agreements. There are 42 minutes signed by the beneficiaries (16 men, 10 women) Certification from the Household Targeting System (SISFOH). There are 33 attendance lists to training workshops for the improvement of sheds and the installation of livestock mesh fences. There are 42 minutes signed by the beneficiaries. In the monthly reports, the Field Supervisor has provided information on the agreements and commitments signed by the beneficiaries: Proper material storage and use, compliance with the technical specifications for the improvement of sheds and installation and livestock mesh, adequate use of the improved spaces. (4.1) (4.2) (4.3) (4.4) There are minutes that have been signed by the communities, containing clauses that define the mechanisms for the selection of beneficiaries and the annulment procedure. (5.1) (5.2) (5.3) Operational Plan presented to 36 communities, shared during the first training meetings for the improvement of sheds and the installation of fences. (5.4) 42 training sessions were held in which the beneficiaries were informed about the scope of each activity carried out: the improvement of sheds and the installation of fences. The Field Supervisor’s activity report includes the following suggestions made by beneficiaries regarding the training sessions: - Training events should not be schedules on the same dates as local holidays. - The official Agricultural and alpaca management calendar should be taken into account. - The opinion of the community leaders should be taken into account when making decisions regarding the beneficiaries. - It is important to coordinate with other institutions that are working in the area, to avoid scheduling activities on the same date. These suggestions were collected and taken into account when selecting beneficiaries and when programming project activities. | There were no impacts.
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | • Participation of women. • Women's access to the benefits of the project. | 1. Before each cycle of calls, the Project Director is responsible for preparing a call strategy. 2. The Project Director will be responsible for evaluating and reinforcing the communication proposals of the Field Supervisor regarding the clarity of the contents, promoting improvements (including the objectives of the project and the participation of women in connection with the activity) and the consistency with the call strategy. 3. The Project Field Supervisor will be responsible for training and strengthening the proposals and communication skills of the Field Technical Specialists (Yachachis), as described in the previous paragraph. 4. At the beginning of each cycle of activities, the project’s Field Supervisor will make a positive motivational acknowledgement and will reinforce the call and the results obtained regarding the overall participation and the participation of women. 5. At the end of each call cycle, the Project Director is responsible for evaluating the call strategy resulting from the implementation and for including the relevant lessons learned in the evaluation report. 6. During the implementation of the project activities, the Field Supervisor will be responsible for reminding the parties responsible for the activity, to verify the following recommendations during the implementation of the follow-up activities: • In all Project activities involving collective or group participation, establish criteria for women’s participation: women should be treated equally when they speak and then they vote on decisions. The location of men and women in workshops should be arranged equitably. • Encourage gender equity in all training and coaching sessions. | Training Plan (including the call strategy) Monthly Progress Report | Training plan approved by the Project Director Monthly Report of the Field Technical Specialist (Yachachiq) Monthly report of the Field Supervisor. Quarterly Report of the Project Director | The Training Plan foresees that the Training Module will be developed by taking into account women’s equality and participation. Five guides highlighting the participation of women were prepared: 1) improvement of sheds, 2) adaptation to climate change, 3) planting forage cereals, 4) installation of irrigation pilot 5) operation of the early warning system. | There were no impacts.
6 – Core labour rights
7 – Indigenous peoples |  |  | There weren't any risks identified, as the project involves only rural Andean (non-indigenous) communities. However, the presence of a Yachachiq Field Technical Specialist, who acts as a Quechua and Spanish translator/interpreter, guarantees that participants in all meetings and workshops are able to understand. | 1. At the beginning of each activity in the communities, the Project Field Supervisor is responsible for verifying in which language the training will be carried out (Spanish or Quechua). 2. At the end of each meeting, the group will consult on the need to maintain the interpreter / translation mechanism during the following Project meetings or activities with the same community. 3. The decision to continue with the interpreter/translator for the following Project meetings or activities with the same community, shall be recorded in the minutes of the meeting. 4. In case there is consensus on the decision not to perform a translation, the decision will be recorded in the meeting minutes. | Translator / Interpreter identified and meeting minutes | 5 Field Technical Specialists - Yachachiqs with bilingual Quechua / Spanish skills | - 5 Field Technical Specialists - Yachachiqs were hired with native language skills: Quechua / Spanish. - A leader was identified for each community (a native), to support the Yachachiq during the trainings. - During the first training sessions for the improvement of sheds and installation of fences with livestock mesh, a decision was made regarding the language to be used for the training, | There were no impacts.
8 – Involuntary resettlement
9 – Protection of natural habitats |  |  | Protection of protected natural areas and natural resources | In the event that the selection of the project’s direct beneficiaries (in line with the relevant procedures) includes areas within the limits of the Reserve, to be intervened by the project: 1. The Project Director provides notification to the environmental authority- SERNANP of the situation, while also including a summary of the project’s objectives, activities and progress. 2. The Project Director monitors the response of SERNANP. 3. In the event that the response from SERNANP applies environmental and/or social requirements to the project, the Project Director will include the measures to comply with the requirements in this component of the Environmental and Social Management Plan. 4. The Field Supervisor sends the requirements to the Field Technical Specialists and verifies and documents compliance with the requirements made by SERNANP. | Requirement made by the Environmental Authority Field Supervisor’s technical report | By means of the Technical Executing Entity, the Project Director, sends the request to the Environmental Authority for the Opinion on Technical Compatibility. Quarterly Report of the Project Director Monthly Report of the Field Supervisor | SERNANP was informed of the implementation of the project and it issued the Compatibility Report and gave a favorable opinion regarding the Environmental and Social Management Plan. (954-2018-SERNANP-DGANP), since the project will not carry out activities within the reserve. Before the beginning of each activity, the Field Supervisor reviews the conditions outlined in the Compatibility Report and reports on any contingencies identified. | There were no impacts.
10 – Conservation of biological diversity |  |  | • No risks were identified; preventive measures were established, nonetheless. | 1. It is up to the Project Director to consult with the relevant environmental authority, regarding the ecological adoption of species such as Ryegrass and Dactylis Glomerata (grasses) and other non-native cultivated grasses as forage alternatives. 2. In the event that the authority’s eventual response implies decisions that affect the programming of project activities with regard to the cultivated pastures, the Project Director and CAF-Implementing Entity will agree on an alternative plan for the activities that could be affected. 3. If an alternative plan has been defined for the project activities in relation to cultivated pastures, the Project Director implements the plan accordingly. | Technical report | Field Supervisor Report on crops approved by the environmental authority-SERNAP | Safeguard measures have not been implemented, because activities 1.1.3 Seeding and cultivation of highland forage cereals and 1.1.4 Installation of clover in wetlands for improving forage cover, have not yet been implemented. | There were no impacts
11 – Climate change |  |  | • Conversion of peat deposits • Greenhouse gas emissions from vehicles | 1. Before taking part in the activities, a photographic record will be produced on the state of the wetlands. 2. The processes defined for the improvement of the existing rustic channels will be authorized by the Project Field Supervisor, before implementation. 3. The areas used for planting the resistant native species proposed by the Project, will be authorized by the Project Field Supervisor, in accordance with the following principles: 3.1. The parts of the wetland that are wet, will remain wet and will not be intervened. 3.2. As far as possible, dehumidification will be attempted in the parts of the wetland that can be drained. 3.3. For parts of the wetland that are unlikely to be re-humidified, some of the following management measures will be implemented if possible, given the terrain conditions: cleaning the wetland; implementing measures to prevent overgrazing; irrigating buffer zones and sowing clover seeds. 3.4. The use of native resistant species (red and white clovers) for the recovery/expansion of the wetland, will only be implemented in the re-humidified areas of the wetland or in the expanded irrigation areas obtained by managing rustic canals. 4. Prior to the implementation of the activities for the recovery and expansion of the wetland, the Project Director will order that at least two soil samples are taken from two large wetlands that can be located in several areas (a sample from each wetland), and which can be included in the wetlands to be recovered. Control greenhouse gas emissions-GHG from the project’s vehicles. 5. The Field Supervisor is responsible for maintaining an updated registry of each vehicle used for Project activities. 6 The Field Supervisor is responsible for maintaining an updated copy of the Official Gas Certificate for each vehicle. This copy shall be kept in the registry of vehicles used for Project activities. | (1) Photographic record of the state of the wetlands (2) (3) Approved technical report (5) Registry for each vehicle (6) Official Gas Certificate for each vehicle (4) Soil study (5) Contracts and agreements (6) (7) Semiannual report | Photographic record per wetland (72 hectares) Technical Intervention report from the Environmental Specialist Monthly Field Supervisor Report Quarterly Report from the Project Director (5) Contractual clauses (6) (7) Semiannual Supervisor’s Report Quarterly report from the Administrator | Safeguard measures have not been implemented, because activity 1.1.5 for the recovery of wetlands has not been implemented yet. The following means are used to transport personnel and materials. They all have the circulation and smoke control permits required by law: - 1 COPASA 4x4 truck - 5 trucks from Local Governments (one per province) - 5 motorcycles | There were no impacts
12 – Pollution prevention and resource efficiency |  |  | • Solid waste | 1. Before performing the following activities: i. events related to skills development and ii. activities to improve or build sheds for animal protection, the party responsible for the activity will prepare the elements to contain solid waste, considering the following classification: organic waste, recyclable inorganic waste and other waste. Containment elements will include plastic bags and/or plastic containers. 2. At the beginning of the activities, participants will be instructed on the classified collection of solid waste. 3. At the end of the event, it will be verified that the classified waste is brought to the local solid waste management system. If the activity is carried out in a rural area, the party responsible for the activity will verify that the classified waste is properly disposed of or that it is transported to an urban area to be incorporated into the local solid waste management system. 4. The party responsible for the activity will document the activities described in this section, including by means of a photographic record. | Implemented Plan Photographic record Activity Report | Solid Waste Management Plan Project Monthly Field Supervisor Report Quarterly Report of the Administrative Assistant (purchases are also linked to the waste issue) | For the implementation of these measures, a Solid Waste Management Plan was developed for the Project activities, carried out so far: a. Training Sessions b. Coaching sessions c. Workshops | There were no impacts
13 – Public health |  |  | - Health Risks in communities due to Covid 19. This safeguard had not been foreseen, because there were no health risks from the project activities. Given the current COVID 19 crisis and given that the project is being carried out in 18 high Andean districts with highly vulnerable population strata, it is expected that there is a medium risk of contagion, indirectly caused by the execution of the activities that require of the constant transfer of field personnel and suppliers that provide the material transfer service.. | Measures to the project team: 1. Biosecurity measures are implemented, paying attention to the daily updates provided by the government. 3. The provision of services of officials under the modality of remote work is prioritized, as determined by the Ministry of Labor. 4. Services will be provided in the activities authorized according to DS N ° 080-2020-PCM, and as long as the activity of the project to which it is linked has a direct relationship with the activities authorized in accordance with the provisions of "Resumption of activities" . 5. Include protection measures for communities to avoid serious damage to their health due to their fragile immune systems. Internal requirements, in application to government regulations, in safeguarding the well-being of employees and the communities with which it interacts: 1. The person in charge of the project must define the real and decisive need to mobilize the personnel. Said responsibility and necessity must be exposed in writing to the highest authority of COPASA as the Executing Technical Entity, with the knowledge of CAF, which is the donor Institution and CONDESAN. 2. General authorization of the Legal Representative of COPASA for the restart of activities in the field of the technical personnel of the project, supervisors and Yachachiq's. 3. Certification or confirmation from the Mayors of Municipalities to be visited, which allows them to enter the communities that includes: date of entry, date of departure, who arrives, reason for the visit. 4. Implementation of the biosafety protocol. | Plan approved and implemented Protocol approved and implemented Monthly Report of the Supervisor of measures only | Process approved by the National Health Authority MINSA and implemented by the Administrative Executing Entity - CONDESAN. Mandatory compliance for project staff. Process approved and implemented by the Administrative Executing Entity - CONDESAN. Mandatory compliance for project staff. Measures implemented for training and construction activities that require more than 10 people to meet. It includes communications and approval from local authorities for the restart of activities. | - CONDESAN has a Surveillance, Prevention and Control Plan of COVID 19 and has provided for the draft protocol "PROTOCOL OF PROGRESSIVE RETURN TO THE PRESENCE WORK MANDATORY BY COVID-19 FOR OFFICIALS LINKED TO THE AYNINACUY PROJECT, IN AREQUIPA - PERU" - Field Supervisors have been trained in the implementation of biosecurity measures prior to COVI 19. At the Field Departure, they trained the Technical Field Specialists - Yachachiq. The technicians, prior to the start of their field activities, implement the measures and develop a short training for the beneficiaries. | There were no impacts
14 – Physical and cultural heritage |  |  | • Archaeological remains | 1. If the activity (improving or building the shed or implementing the water reservoir) is carried out on previously intervened land, the Certificate of Non-Existence of Archaeological Remains (CIRA) process is not applied. 2. The Field Supervisor verifies that the assigned location is technically adequate; and also confirms that, given its location, the work will not interfere with a body of water or with a wetland. 3. A photographic record will be made, and a label will be placed in the area defined for the activity. 4. The Field Supervisor collects information for the request made by CIRA [Certificate of non-existence of archaeological remains], in accordance with Circular 1998-2016-DDC-ARE / MC of the Decentralized Directorate of Culture of Arequipa. | Photographic record Activity report | Photographic record Quarterly Field Supervisor Report Project Director’s Annual report | The activities to improve sheds, carried out in 30 communities, took place in previously intervened areas, so it was not necessary to request the Certificate of Non-existence of Archaeological remains - CIRA. | There were no impacts
15 – Lands and soil conservation |  |  | • Soil conservation | 1. 1. Avoid compaction of the original soil layer in the area surrounding the work, to the extent possible. 2. Remove the layer of soil when it is dry, or the moisture content is less than 75%. 3. Keep the topsoil separated from the inorganic excavated subsoil; locate both separate piles where there is no chance of cascading and there are adequate drainage conditions. Protect them with a plastic cover to avoid erosion losses. 4. In the case of a reservoir, where storing the topsoil is not feasible, to the extent possible, relocate it nearby so that it can be recovered in case the reservoir is subsequently closed. 5. At the end of the activity, leave the workplace surroundings in better or similar conditions to those found before work. 6. Gather, classify and dispose of solid waste resulting from the activity, in accordance with the best practices in the area. If a disposal place is not found, take the waste to an appropriate disposal site, within the same district. 7. Document the management measures implemented, including the photographic archive. | Procedure Implemented Field Supervisor Report Photographic Registry | Procedure implemented by the Field Technical Specialist -Yachachiq Monthly Report by the Field Supervisor | No safeguard measures have been implemented because the activities have not yet been implemented: 1.2.3 Improvement of channels to improve water resources in wetlands, 1.2.4 Construction of rustic reservoirs for water storage rains, streams and natural springs. | There were no impacts
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Risk monitoring of the project proposal, is performed according to the ESMP, and the risks are within the levels identified by the project. In this period, there were mainly health risks due to the spread of COVID-19.
Have unanticipated ESP risks been identified during the reporting period? |  | N/A
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | - CAF ensured the hiring of the environmental consultant to know the environmental and social performance of the Ayninacuy project. At the end of this period, there are two follow-up reports to the Environmental and Social Plan of the project; one corresponds to the evaluation and monitoring of the activities of the second year and the other corresponds to the third year of implementation of the project. - The reports issued by the environmental supervisor verify compliance with the environmental, social and occupational safety aspects set out in: (i) the project proposal and its environmental and social management plan, a document published on the FA website; (ii) the applicable rules; (iii) AF safeguards; (iv) CAF safeguards; (vi) the monitoring reports generated in the project; (vii) agreements associated with the project; and other normative documents applicable to environmental, social and safety management at project work. -In addition, ongoing evaluation and follow-up meetings have been held with the project team. Despite covid19 restrictions, field visits have been conducted to verify the actions of the project team and evaluate the final products.
Have the implementation arrangements been effective during the reporting period? |  | Yes, they have been effective in fulfilling the established contractual commitments and thereby the measures for each of the environmental and social principles
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | - COPASA maintained coordination with the environmental authority - National Service of Protected Natural Areas - SERNANP, in order to comply with the protocols and intervention permits in the natural reserves. In this period, a new compatibility opinion report was requested, in order to expand the goals of the project, which was positive. - CONDESAN, coordinates with the entities of Health and Safety at work to effectively comply with the Plan of surveillance, prevention and control of the COVID-19. - Coordination was maintained with local governments to ensure strong implementation of project activities and the participation of women in training sessions. This has made it possible to expand the commitments for the development of the new goals, which began to be executed in April. Renewing the commitments with the local and communal authorities has allowed their rapid implementation and execution of the works.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes, despite the current crisis, the agreements signed with the authorities in the previous period they have been effective. The acceptance of the project and the conditions for its intervention have been maintained. As for measures to mitigate social and environmental risks, they are well accepted by the community because they are part of their traditional environmental care practices.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | N/A
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | N/A
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Sí, se realizó la evaluación de género y las actividades de consulta se llevaron a cabo con interacción de las mujeres de las comunidades. Como resultado se incorporaron las siguientes actividades e indicadores sensibles al género: 1. El proyecto orientará su acción con los siguientes criterios que promuevan la participación igualitaria y el empoderamiento de la mujer en la toma de decisiones: i) Durante la información, difusión y convocatoria; ii) En las reuniones y toma de decisiones en las comunidades; iii)En la logística de los diferentes eventos; iv) En la coordinación con las autoridades y los líderes de la comunidad se consigue el compromiso de participación de las mujeres; v) La Directora del Proyecto aprovecha las oportunidades para motivar las participaciones de las mujeres, durante el seguimiento y monitoreo, identificando las brechas y problemas. Se realiza un seguimiento continuo de los resultados de las estrategias de convocatoria y la participación de la mujer. 2. Para la selección de beneficiarios/as se incluyó un parámetro de priorización para mujeres jefas de hogar. 3. Para las actividades de capacitación de todo el proyecto se considera una meta de participación mínima de mujeres. Específicamente en el componente de mejora de la vivienda, se incrementa el porcentaje. 4. A nivel organizacional, se incluye al menos una mujer en las plataformas de defensa civil a nivel distrital y comunal. 5.Elaboración de una guía sobre el desarrollo y fortalecimiento personal y familiar de la mujer.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Sí, está incluido, como se muestra a continuación: RESULTADO 1.3: Mejora de las condiciones de calidad de la vivienda para soportar condiciones climáticas extremas. - Indicador 1.3.2 Mujeres jefas de hogar priorizaron en los criterios de selección de beneficiarios. RESULTADO 2.1: Mayor concienciación y apropiación de los procesos locales de gestión y autogestión para la adaptación y reducción del riesgo climático. - Indicador 2.1.2 % de la población objetivo consciente de los procesos locales de gestión y autogestión para la adaptación y reducción del clima. RESULTADO 2.2: Mayor conciencia y apropiación de los procesos locales de adaptación y reducción del riesgo climático. Indicador 2.2.4.3: Incorporar al menos una mujer a la Plataforma de Defensa Civil distrital y por plataforma de defensa civil comunal. - PRODUCTO 2.2: Actividades de sensibilización sobre la adaptación y la reducción de riesgos con la participación del grupo de la población objetivo: ver productos específicos Bajo. Indicador 2.2.4.3 N° de mujeres incluidas en la formación de cada plataforma a nivel de distrito. indicador 2.2.4.6 N° de mujeres incluidas en la formación de cada plataforma a nivel comunitario. RESULTADO 2.3: mejora de la sensibilización y de la gestión del riesgo climático y de las técnicas de adaptación. - SALIDA 2.3.4: Sesiones de entrenamiento. Indicador % de mujeres participantes (25% para todas las actividades, 30% mejoras de vivienda) - Productos 2.3.3: Elaboración de guías técnicas : 1.000 guías sobre desarrollo y fortalecimiento personal y familiar dirigidas principalmente a mujeres.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Prioritization of female heads of household as beneficiaries. | outcome 1.3 Improvement in the conditions of housing quality to withstand extreme climate conditions Sec. 1.3.2: | N° Women head of households prioritized in the criteria of beneficiary selection | 0, women head of households | 1 woman per community (it is expected that 36 women will benefit) | Good, it surpassed the set in the indicator. 67 mujeres beneficiadas
Equal participation and empowerment of women in decision making regarding project activities. | outcome 2.1 Greater awareness and ownership concerning the local processes of management and self-management for adaptation to and reduction of climate risk. Sec 2.1.2 | % of target population aware of local processes of management and self-management for adaptation to and reduction of climate risk is made up of women. | No uniform and reliable baseline information was identified. | 25% set as the project goal. | Satisfactory. During the implementation of the project, 298 training workshops were carried out. Female participation was 41% (2230 shares out of 5584)
Include women at the organizational level in climate risk management | output 2.2.4 Advisories for the formation and strengthening of district and community level civil defense platforms (reconnoitering, startup). Sec 2.2.4.3 | N° of women included in the formation of each platform at district level. | Without precedents. The project will promote the formation of the first platforms. | 1 woman per district platform | This activity could not be carried out due to the restrictions of COVID 19, which did not allow the development of meetings and events.
Include women at the organizational level in disaster risk management. | output 2.2.4 Advisories for the formation and strengthening of district and community level civil defense platforms (reconnoitering, startup). Sec 2.2.4.3 | 2.2.4.6 N° of women included in the formation of each community level platform. | Without precedents. The project will promote the formation of the first platforms. | 1 woman per communal platform | This activity could not be carried out due to the restrictions of COVID 19, which did not allow the development of meetings and events.
Personal and family development | output 2.3.3 Elaboration of technical guides. - about personal and family development and strengthening aimed primarily at women. | N° developed guides and delivered | Baseline value not applicable | 1000 guides delivered | Good. They deliver 4000 guides N°11.- Gender and adaptation to climate change.
Equal participation and empowerment of women in decision making regarding project activities.. | output 2.3.4 Training sessions. Sec 2.3.4.4 | % of women participants | Baseline value not applicable | 25% for all the activities except for household improvement activities | Satisfactory. During the implementation of the project, 298 training workshops were carried out. Female participation was 41% (2230 shares out of 5584)
Equal participation and empowerment of women in decision making regarding project activities.. | output 2.3.4 Training sessions. Sec 2.3.4.4 | % of women participants | Baseline value not applicable | 30% for housing improvement activities. | Good, During the training sessions there was 43% participation of women (196 women participated in 22 workshops, for the improvement of 36 homes)
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | N/A
Have the implementation arrangements at the IE been effective during the reporting period? |  | N/A
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | N/A
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | N/A
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | N/A
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| All project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | All Project components/outcomes |  | Outcome 3 | Outcome 6 | Outcome 5 | -Agreement signed between entity executors before implementation of project implementation |  | For the current period, an addendum was issued to the agreement signed between the Implementing Entity - CAF, Executing Technical Entity - COPASA and the Executing Administrative Entity - CONDESAN. This agreement was made to extend the validity of the agreement, in view of the fact that the project extended its end date, in addition this addendum allowed to establish clauses that allow to improve the obligations of each of the parties, the periodicity of the disbursements of the same and the legal terms of the Non-Novation of the Agreement. See ANNEX VII ADENDA NRO 003 AYNINAKUY.pdf | S
| All Project components/outcomes |  | Outcome 3 | Outcome 6 | Outcome 5 | -The different areas of CAF carry out the fiduciary and financial supervision of the implementation of the funds, as well as the monitoring of the technical progress of the Project |  | - CAF gestiona la tercera adenda Convenio Tripartito de Ejecución del proyecto Ayninacuy, la cual se emite para atender la extensión de plazo aprobada por el Fondo de Adaptación. Las principales cláusulas que atiende la adenda son: cláusula 5 del Acuerdo relativa a la Duración y la cláusula 15, relativa a la Compensación del Ejecutor Administrativo. - CAF asked CONDESAN to carry out the second audit of the project, which concludes "Our review did not reveal significant deficiencies in internal control"See ANNEX XII - Informe Auditoria Proyecto segundo año de jecución.pdf | S
| All Project components/outcomes |  | Outcome 3 | Outcome 6 | Outcome 5 | ´Level of budget implementation |  | - In this period the AF was requested an extension of 2 months to the date of completion of the project, which was approved on April 14 (see annex). The activities of the project in the field culminated on July 15, but according to the hiring regime, the hiring of personnel was maintained until July 30, a period in the project team that completed its administrative procedures. During the period from July to November, the closing activities of the project were developed. - The period of national health emergency has been extended until December 31, 2021 (see aneco), and the permanence of the restrictions for the development of events and other activities of the national sector, determined that the following activities could not be executed Products 2.2.1 N° of disaster drills, at the provincial level, Products 2.2.2 N° modules for EWS early warning systems in rural communities, Products 2.3.4.2 N° of participants per workshop in the improvement of community civil defense platforms, Products 2.3.4.3 N° students per workshop, Products 2.3.4.4 N° of participants per workshop held in 05 provincial municipalities for EDAN teams, Products 2.3.4.5 N° of the beneficiary households participate in the process of developing prevention plans through training programs | S
[7 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | María Carolina Torres -Directorate for Sustainability, Inclusion and Cimate Change Executive, CAF
| Email: | mctorres@caf.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project maintained good progress in component 1 activities, despite unforeseen situations due to climate change and the current COVID 19 crisis. On July 15, the original activities and new goals were completed. The arrangements proposed by the project team to change the training methodologies have allowed the radio guides to be developed, having a greater scope of beneficiaries than those foreseen in the project. As previously reported, some of the activities under component 2 could not be carried out. The budget balances allowed the adaptation fund to approve an expansion of the goals proposed in the previous report. The efforts of the project team to maintain communications and strengthen government support in the work areas have been key to completing the project, despite the limitations generated by COVID 19, which are still maintained.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | OUTCOMES 1.1, 1.2 and 1.3 |  | Outcome 6 | Outcome 5 | 1- Implementation of administrative activities for the programming of activities. 2- Awareness of the benefits of the project at the national, subnational and community level. 3- Selection of the beneficiaries of the project. |  |  | - The implementation of the activities is focused on the expansion of the goals. - In the month of April, the selection of beneficiaries for the new goals was completed and the delivery of materials was fulfilled. | S
| All Project components/outcomes |  | Outcome 6 | Outcome 5 | 1- Technical personnel installed in the 5 provinces. 2- Supervisor meets the needs in the 5 provinces |  |  | - In this period, due to the COVID 19 crisis, two technical specialists from Campo - Yachachic fell ill, a situation that has delayed the selection activities of new beneficiaries in the province of Caylloma and Castilla. - 2 promoters of Campo were contracted to support the animal health campaign, because it seeks to cover all the beneficiaries of sheds. | S
| OUTCOMES 1.1, 1.2 and 1.3 |  | Outcome 5 | Outcome 6 | 1- Implementation of purchasing mechanisms and inventory development in the third quarter of implementation. |  |  | - The documentary collection of inventories, records of delivery of materials and completion of works has been developed, in a digital way, to keep a better control of the documentation, due to the limitations of remote work. | S
| OUTCOME 2.1: Greater awareness and ownership concerning the local processes of management and self- management for adaptation to and reduction of climate risk. |  | Outcome 5 | Outcome 6 | 1- Commitment and agreements signed with authorities and beneficiaries in the first quarter of implementation. |  |  | - Local governments and communal authorities ratified their agreements and commitments to implement the expansion of the goals. 18 add-ons were signed between COPASA and the Municipalities. -Agreements were signed with the Environmental Authority National Service of Natural Areas Protected by the State - SERNANP to complete the Installation of Products 2.2.2 N° modules for EWS early warning systems that were purchased and could not be installed by the project team. This activity presented delays due to the activity that the Educational Entities were closed due to the restrictions of COVID 19. | S
[7 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Maria Angelica Salinas Valencia
| Email: | mariangelicasv@hotmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
´The project has completed 100% of its component 1 activities, some products had to adjust due to COVID 19 restrictions. It was the activities in the bofedales that had to be modified because there were limitations due to the restrictions imposed by SERNANP for the last year of execution and the delay in the collection of soil samples that is required to start the intervention. Outputs 1.1.5 were reprogrammed to operate only in communities that were not in protected natural areas. As for component 2, 90% of the activities were executed in the field, due to the restrictions to develop events and meetings were maintained until the closure of the project. In order to compensate for part of these activities and strengthen knowledge about climate change adaptation strategies taught by technical field specialists, radio educational guides were developed and transmitted in the 5 provinces benefiting from the project. It is concluded that the project has had a satisfactory level of execution despite the restrictions of the current pandemic, the changes of officials and the political instability and climatic effects that delayed the activities at different times.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
OUTCOME 1.1: Improvements in the conditions and means of providing animal nourishment and health, through strengthening the life strategies in relation to the impacts of climate change. | Products 1.1.1 N° of shelters built. | 0 | completed | 342 sheds*
| Products 1.1.2 N° of fences installed | 0 | completed | 216 fences*
| Products 1.1.3 Ha of high altitude forage cereals planted | 0 | completed | 900 Ha
| Products 1.1.4 Ha of improved grasses seeded | 0 | completed | 72 Ha
| Products 1.1.5 Ha of wetlands improve with clover | 0 | partially completed, It was not possible to complete the planting of clover in 4 of 36 communities (Misahuanca, Tecca, Huayqui and Visca), due to the restrictions of the Environmental Authority for the areas of natural reserve, but the execution of this product was extended in other communities outside this area (Chojanitayo, Tumpullo, Pucuncho II) | 72 Ha
| Products 1.1.6 N° of dosed animals executed. | 0 | completed | 20,000 doses*
OUTCOME 1.2: Improvements in the availability of water and irrigation conditions allow for providing greater volumes of vegetal production and of greater areas consolidated for animal feed | Products 1.2.1 N° of modules irrigation installed. Ha of improved grasses | 0 | completed | 73 modules**
| Products 1.2.2 N° of wetlands with improved irrigation via rustic canals. | 0 | completed | 36 wetlands
| Products 1.2.3 N° meters of improved canals | 0 | completed | 20,000 m*
| Products 1.2.4 N° of reservoirs (ponds) built. | 0 | completed | 36 reservoirs
OUTCOME 1.3 Reduction in cases indexes of ARIS and ADDS in communities and beneficiary households | Products 1.3.1.1 N° of safe water purification systems installed | 0 | completed | 72 Systems
| Products 1.3.2.2 N° of Composting Latrines Built | 0 | completed | 72 units
| Products 1.3.2.3 N° of improved stoves built | 0 | completed | 72 units
| Products 1.3.2.3 N° of photovoltaic panels installed | 0 | completed | 72 units
| Products 1.3.2.4 N° of solar walls | 0 | completed | 72 units
OUTCOME 2.1: Greater awareness and ownership concerning the local processes of management and self- management for adaptation to and reduction of climate risk. | Products 2.1.1.1 N° of agreements (covenants) Provincial | 0 | completed | 5
| Products 2.1.1.1 N° of agreements (covenants) District | 0 | completed | 36
| Products 2.1.2.1 N° of dissemination and motivation visits (Community) | 0 | completed | 1
OUTCOME 2.2: Greater awareness and ownership of local processes of adaptation to and reduction of climate risk | Products 2.2.1 N° Staging of disaster drills, at provincial level. | 0 | Activity suspended due to COVID 19 restrictions, due to the national Authority in Civil Defense - INDECI suspended drills at the national level and this activity depended on coordination with INDECI. This was reported in the request for extension of concrete adaptation Ayninacuy. | 5 events
| Products 2.2.2 N° Implementation of teaching modules for early warning systems EWS in rural communities | 0 | 35 Implementation of modules, Due to the security limitations presented by the IE PARACSA Educational Entity in the community of YANAQUIHUA, the SAT module could not be installed. As classes were suspended due to COVID 19 restrictions, the entity did not have personnel in the place to protect the installed equipment. The limitations to complete this activity were also reported to the Adaptation Fund with the request for extension of concrete adaptation Ayninacuy. | 36 modules
| Products 2.2.3 N° Accompaniment to educational institutions, in elaboration of their prevention plans and disaster attention, as an adaptation measure to climate change. | 0 | Activity suspended due to COVID 19 restrictions. Although in the last report to the AF, it was scheduled to be executed in this period, because the National Government extended the restrictions and suspension of the educational service, this activity could not be executed. See ANNEX VIII Latest national regulations in the face of covid 19.pdf | 5 assisted plans
| Products 2.2.4 Advisories for formation and strengthening of community and district civil defense platforms (reconnoitering, and startup). | 0 | partially completed due to COVID 19 restrictions. | 18 events
OUTCOME 2.3: improvement in awareness and climate risk management and adaptive techniques skills. | Products 2.3.3.1 N° developed guides | 0 | 12 guias completed, The guide on Adaptation and prevention of risks in educational institutions was not developed because the Ministry of Education already had a guide developed in this area. | 13 guides
| Products 2.3.3.2 N° of printed copies | 0 | 40,500 Guides printed completed, 2,500 Non-printed guides, corresponded to the guide on Adaptation and prevention of risks in educational institutions | 43,000 guides
|  | 0 | 40,500 Guides printed completed, 2,500 Non-printed guides, corresponded to the guide on Adaptation and prevention of risks in educational institutions | 43,000 guides
| Products 2.3.4.1 N° of participants per workshop (5 per community) for the installation of early warning EWS teams | 0 | More than 180 people trained through radio educational guides | 180 participants
| Products 2.3.4.2 N° of participants per workshop in the upgrading of the community civil defense platforms | 0 | More than 540 people trained through radio educational guides | 540 participants
| Products 2.3.4.3 N° students per workshop | 0 | More than 1000 students trained through radio educational guides | 1000 participants
| Products 2.3.4.4 N° of participants per workshop held in 05 provincial municipalities for EDAN teams | 0 | Could not be executed due to covid 19 restrictions | 64 participants
| Products 2.3.4.4 % of women participants (25% for all activities, 30% housing improvements) | 0 | 41% for all activities, 43% housing improvements | 25% for all activities, 30% housing improvements
| Products 2.3.4.5 N° of beneficiary households participate in the process of elaboration of prevention plans through training programs. | 0 | More than 1000 students trained through radio educational guides | 540 participants
| Products 2.3.4.6 N° of participants per workshop, municipal official and community representatives are trained in prevention workshops, | 0 | Could not be executed due to covid 19 restrictions | 142 participants
| Products 2.3.4.7 N° of participants per workshop, Training sessions for the transfer of techniques for improvement of rural Andean highland housing: Trombe solar walls. | 0 | 563 participants, completed | 140 participants
| Products 2.3.4.8 N° of participants per workshop, Construction of composting latrines | 0 | 563 participants, completed | 141 participants
| Products 2.3.4.9 N° of participants per workshop, Construction of improved stoves | 0 | 563 participants, completed | 142 participants
| Products 2.3.4.10 N° of participants per workshop, Installation of photovoltaic panels | 0 | 579 participants, completed | 143 participants
| Products 2.3.4.11 N° of participants per workshops (144 workshops) | 0 | 5,584 participants, completed | 3,750 participants/ beneficiary
Nota: * These goals were expanded during the current period, were reviewed by the Advisory Committee and recognized by the technical secretariat of the Adaptation Fund. See ANNEX IX_A - Notification COVID-19_no-cost_extension_CAF_Ayninacuy.pdf, ANNEX IX_B REQUEST FOR EXTENSION OF CONCRETE ADAPTATION AYNINACUY.pdf y ANNEX IX_C RV_ Request for extension - Ayninacuy project.eml ** Exceptional Request of the Technical Executing Entity COPASA and approved by CAF. See y ANNEX X_A Target expansion Products 1_1_2 modules irrigation.pdf y ANNEX X_B CAF Approval_Target expansion Products 1_1_2 modules irrigation.eml

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1. Extreme weather events occurred. Intense rains during January - March and snowfalls with low temperatures during June - July - 2021, which limited the transfer of materials and the execution of planting activities. 2. The COVID 19 Crisis has been the main factor in delaying activities in this period. This situation was successfully overcome due to: 1. Agreements signed, in the previous period, with local and communal authorities have ensured institutional support for both the use of deposits, surveillance and transport of materials to beneficiary communities from their territorial areas; monitoring of field activities. 2. Good coordination with local authorities and the permanent residence of The Technical Field Specialists -Yachachiqs in the priority districts, has enabled, despite the difficulties, that project activities are not delayed for long periods.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | In order to overcome the arrears, the following measures were carried out: 1. Despite the restrictions and paralysis of activities, the Coordinations were maintained on a permanent basis by the technical team with the local and community authorities. The current COVID 19 crisis has made it possible to improve communications remotely, generating a need for local authorities to use different means to communicate remotely with all national and regional organizations. Favoring the implementation of changes for distance training. 2. With the experience gained in the previous period, field activities were better programmed so that they are not affected by climate events. 3. Rescheduling of activities according to the agricultural and alpaquero calendar, prioritizing the implementation of field activities so that they are completed within the planned deadlines.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | 1. The activities were programs that adhered to the calendar of agricultural activities, the calendar of alpaque breeding activities and the calendar of the water cycle, which are managed by the communities. This improved the execution times of the activity. Staff vacation periods were scheduled during this period. 2. The execution period of the Project is extended, in order to compensate for the delay generated by the current COVID 19 crisis. 3. Part of the project's financial balance of 29% was used to expand the project's goals in animal health and protection activities, and improvement of bofedal canals. 4. Decisions to expand goals and extend the project are socialized at the meetings of the Advisory Committee. See ANNEX XI MINUTA COMITÉ DIRECTIVO AYNINACUY 28 OCT 2021.pdf 3. Limitations in holding events have led to a change in methodologies for technical assistance and training. These are planned through streaming sessions, video, and remote meeting sessions. 4. Although the training activities have been limited mainly to the family nucleus and mainly in the countryside, this does not limit the participation of the beneficiaries and the community. 5. The low rates of contagion in the high Andean areas of the Arequipa region did not affect the delay in field activities, these delays were marked by the effects on the transfer of materials and the impediments that some suppliers had in obtaining their permits to comply with biosecurity protocols. 6. It is hoped that the broadcasting sessions will allow communities to have a better scope of the project. 5. The savings in various activities of the project, has allowed the increase of the goals of Component 1, allowing to increase the beneficiaries and strengthen their physical assets (sheds, fences, housing)
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes because: • They have enabled carrying out an early evaluation of the project’s area of probable influence; the identification of communities and groups that may be affected by the project, and initial estimates regarding the potential social risks and benefits related to the project. • They have allowed us to transmit and assume the importance of proper solid waste management before, during and after trainings, meetings and / or community assemblies. • It is planned to carry out preventive and permanent maintenance of vehicles working on the project (van and motorcycles), ensuring that they have their respective technical reviews from the Ministry of Transportation and Communications (MTC). • Permanent coordination with the National Service of Protected Natural Areas (SERNANP). • There are reports on the activities carried out. • There are Quechua-speaking technicians in the work team. • In all collective activities, women’s equal participation has been taken into account. This means that they are able to vote on decisions and locate themselves wherever they decide. • Faced with the COVID 19 crisis, the Public Health safeguard was implemented, which is not part of the initial project proposal. This has made it possible to implement necessary processes to reduce the risk of contagion in the work team, the communities and beneficiaries.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | 1. Women's participation in the training sessions was ensured. During the implementation of the project, a partition of 41% of women was reached, exceeding the indicator foreseen in the project. 2. Compliance with gender-sensitive indicators, such as the selection of women heads of household in the beneficiary community, remains well accepted by communities. This has been reflected in the priority they have given to the selection of improvements in the improvement of women's housing and participation in training sessions, exceeding the 30% foreseen as an indicator of these activities. 3. The participation of 2 mayors in charge of the municipalities of Pampacolca and Chachas in the project, raises the level of empowerment and participation of women in their communities, due to their active and political role with the population. 4. Agreements with the authorities have confirmed their commitment to involve women in civil protection platforms. 5. The participation of women in all project activities was promoted. Overall, 35 per cent of the beneficiaries are women, heads of household in poverty and extreme poverty.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | - The budget must contemplate and guarantee the formation of a capable, robust technical team with facilities to meet the objectives of the project, in addition to the logistical needs to access the intervention areas. - It is important to have actors who know the area of influence and maintain relationships with local institutions and authorities. In this sense, COPASA's extensive experience in the intervention area, related to its previous work with farmers and ranchers, facilitated the identification of the needs of the population and therefore, of the components to be executed in the project. - The participation of the Yachachiq, technical personnel who live in the intervention area, speak the language and know the needs of the beneficiary population. The Yachachiq allowed the deployment of the project, even during the health crisis, in addition to generating trust with the community, which facilitated the development of the work. Its main task was to transmit the knowledge in a practical way to the Alpaquero and communal leaders, so that the families themselves will be able to execute the activities of the project.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | ´- El desarrollo de actividades con la participación de los Yachachi, agricultores y miembros de la comunidad aprendieron de manera práctica a ejecutar las actividades del proyecto (armar los cobertizos, vacunar a los animales, etc.), esta metodología de trabajo de "aprender haciendo" es lo que ha permitido la optimización del uso de los recursos del proyecto y proporcionar más conocimiento a los beneficiarios sobre la importancia de las estrategias de intervención del proyecto, materializados en los productos, que les han permitido aprender a realizar actividades productivas (cría de camélidos y siembra) resilientes al clima.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | NA
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | NA
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | The agreements with the local authorities have been key to speed up the work in the communities, from this level there is recognition of the impact of climate change and the need to implement measures that increase the residence of micro alpaquero producers. The use of simple technology affordable by the local population, training and development of technical guides, allows any farmer in the region to improve their shed, housing, recovery of bofedales, alpaquero management, installation of irrigation systems and recovery of rustic ponds.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The Empowerment between the community and the local authorities, will allow to replicate the intervention in other areas not prioritized by the project in the same region Arequipa and it is expected that the final reports and the publication of the lessons learned will allow other high Andean regions of similar characteristics such as Ayacucho, Huancavelica, Puno, Moquegua, to develop projects based on the results obtained.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | A distinctive and fundamental element for the sustainability of Ayninacuy is its "Learning by doing" methodology, which is attractive and, unlike other projects, allowed the population to train in a practical way and execute the activities individually and collectively. In this work, the availability of the communities and their commitment have also been essential factors for the results proposed by the project to be achieved.
What measures are/have been put in place to ensure sustainability of the project/program results? | The co-participation of local governments and other actors will allow the components of the project to be replicated, as well as the successes and lessons learned. This is reflected in the interest of the Authorities that have intervened to seek new financing to continue carrying out the activities carried out by the project.
What measures are being/could have been put in place to improve project/program results? | It has been identified that the use of technology, even more so during the pandemic, could have facilitated collaboration and practical monitoring of activities carried out in the field.D27
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Awareness-raising and training activities on climate risk, administration and adaptive techniques were carried out. Within these actions, technical guides were developed on topics such as adaptation to climate change, the use of an early warning system, adaptation and risk prevention for educational institutions; and, livestock production, administration and improvement of the family home.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Yes, The development of the guides has been published on the COPASA website and has been delivered to local and communal authorities. In addition, during the last year, the guides were developed in a radial way, which has allowed a greater scope to be achieved with respect to the knowledge of the strategies of adaptation to climate change in terms of the breeding of camelids, production of pastures, management of water resources and improvement of housing.
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | La informacion se encuentra publicada en la pagina web de COPASA
If learning objectives have been established, have they been met? Please describe. | If , the knowledge management has been fulfilled, this is evidenced during the supervision visits and it is appreciated that the beneficiaries put into practice what they have learned, there have been replications from the community in terms of installation of new irrigation systems, accessibility to water, improvement of sheds. Another important element is that all the works carried out are developed by the same beneficiaries, who receive only technical assistance from Yachachic and the Field Supervisor, if the learning had not been assimilated, they would not have been with the finished and working products.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | The budget of the project does not contemplate the expenditure for actions of diffusion of the experiences and results, through virtual platforms and social networks. The restrictions of COVID19 allowed innovation in the development of training in a radial way, in this way the lessons that were made in the field were now heard by more people in the community and shared on the social networks of the local authorities.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | To the fulfillment of the products, these depended on the disposition of the beneficiaries and the community, the project only provided technical and material assistance. The fulfillment of the products evidences the learning acquired by the beneficiary population, as well as the replicas that the community has developed.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | NA
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | PER / RIE / Rural / 2015/1
Implementing Entity | Development Bank of Latin America (CAF)
Type of implementing entity | RIE
Country | Peru
Region | Latin America and Caribbean
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 80665 | 16824 | 63.841 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 2.7% | 41% | 3.5% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 2% | 2% | 2% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 6.93% |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 2: Partially not aware |  | 5584 | 41% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
[6 empty] | 2: Partially effective |  | Water management | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
[6 empty] | Other | 18 | ha protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
[6 empty] | 2810 | 41% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0%
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies | Multi-sector | Livelihoods | 342 shelters | Adaptation strategies | Other | Supporting livelihoods
[6 empty] | 216 fences | Adaptation strategies |  | Supporting livelihoods
[6 empty] | 900 has of fodder cereals | Adaptation strategies |  | Supporting livelihoods
[6 empty] | 72 has of improved pastures | Adaptation strategies |  | Supporting livelihoods
[6 empty] | 73 irrigation modules | Adaptation strategies |  | Supporting livelihoods
[6 empty] | 36 rustic reservoirs | Adaptation strategies |  | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness