## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 01.04.2020 - 31.03.2021
| Project Title: | Building adaptive capacities of livelihoods, communities and ecological security in the Kanha-Pench Corridor in Madhya Pradesh.
| Project Summary: | Being one of the most crucial conservation units of the flagship species - Tiger, the Kanha-Pench Corridor (KPC) supports rich biodiversity and provides important ecosystem services like regulating hydrology and sequestering carbon. Besides its ecological functions, the landscape supports a substantial human population, mostly indigenous, who are extremely vulnerable to climate change impacts. In the last few decades, the KPC has faced severe degradation caused by anthropogenic pressures and climate change, which has reduced its ability to perform important ecological functions. The project aims to restore the corridor’s functionality by building and enhancing the adaptive capacities of its communities, livelihoods and landscape. It aims to do so by adopting a holistic approach of Ecosystem Conservation, Institutional Development, and Promotion of Climate Resilient Livelihoods.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | IND/NIE/Forests/2015/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | National Bank of Agriculture and Rural Development (NABARD) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | NIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | India | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Balaghat, Mandla and Seoni districts located in the South Eastern part of the Central Indian State of Madhya Pradesh. The important water bodies include the Wainganga, Pench and Banjar rivers. Other important areas are - Kanha Tiger Reserve and Pench Tiger Reserve. The National Highway 7 runs through the landscape. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone | Baseline data collection through Focussed Group Discussion (FGD/ Participatory Rural Appraisal (PRA)/ Geogrphical Information Services (GIS) data and baseline report preparation: 0-6 months Creation of 56 village development plans: 0-6 months Formation and strengthening of village level community institutions & capacity building: 3-36 months Participatory impact monitoring: 18-24 months, 37-48 months Implementing livelihood activities: 7-42 months Entry point activities (water related): 0-6 months Installation of agromet stations: 0- 12 months Watershed improvement, efficient irrigation mechanisms: 4-42 months Development of design of knowledge material: 7-24 months Workshops, Awareness sessions: 10-48 months Monitoring: 3-50 months Evaluation: 23 month (midterm) 45 month(final) | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 06.10.2016
IE-AFB Agreement Signature Date: |  | 01.04.2017 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 01.04.2017 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 31.03.2019
| Terminal Evaluation Date: | 30.09.2025
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | - Project Inception report - Baseline report (draft) - Minutes of the Project Steering Committee - Knowledge Management Framework (draft) - Audited Financials for FY 20-21 | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.conservingcentralindia.org/ | Democratic Republic of the Congo
|  | Website in process of being enhanced with project details | Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Tapan Kumar Sahoo | Dominican Republic
| Email: | tapan.sahoo@nabard.org | Ecuador
| Date: | 23.08.2025 | Egypt
| Government DA |  | El Salvador
| Name: | Rajasree Ray, Economic Advisor, MoEF&CC | Equatoral Guinea
| Email: | rajasree.r@nic.in | Eritrea
| Date: | 23.08.2025 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | National Bank for Agriculture and Rural Development | Fiji
| Email: | dcas@nabard.org | Finland
| Date: | 23.08.2025 | France
| Executing Agency |  | Gambia
| Name: | NatWest India Foundation (Formely known as RBS Foundation India) | Georgia
| Email: | n.sunil.kumar@natwest.com | Germany
| Date: | 28.02.2022 | Ghana
| Executing Agency |  | Greece
| Name: | NatWest India Foundation (Formely known as RBS Foundation India) | Grenada
| Email: | soujanya.shrivastava@natwest.com | Guatemala
| Date: | 28.02.2022 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31.03.2021
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? 1 USD = INR 65
Estimated cumulative total disbursement as of [31.03.2021] |  | 1534238
Add any comments on AF Grant Funds. (word limit=200) |  | NABARD has received an amount of USD 2,556,093 from AF and out of that, NABARD has released an amount of USD 1,534,238 as per the following: 1st installment - 22.05.2017 - USD 170,763 2nd installment - 18.04.2018 - USD 480,249 3rd installment - 19.03.2019 - USD 491,268 4th installment - 01.09.2020 - USD 391,958
INVESTMENT INCOME * |  | 22143.21
*Interest on unspent balance has been calculated on notional basis and converted to USD based on rate as on 31 Mar 2021 (1 USD = 73.2065 INR), including the EE level interest of USD 5839
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT (USD) (During the reporting period) | AMOUNT (USD) (Cumulative)
| Component 1: Integrated socio - economic and ecological assessment and planning | 1.1 Socio economic baseline report with village level detailed analysis in the project villages | 317 | 17835
|  | 1.2 Baseline mapping and change assessments of natural resource base in project villages using GIS. | 3188 | 9351
| Component 2: Community mobilization for building adaptive capacities | 2.1 Robust community institutions in 56 villages with collective decision making of stakeholders at village / cluster / district / landscape level on issues of conservation, climate change, gender and development. | 41534 | 172460
|  | 2.2 Participatory Impact monitoring | 1176 | 4365
| Component 3: Integrated approach for ecosystem resilience and sustainable livelihoods as a means for adaptation | 3.1 Adoption of climate resilient agricultural practices by 5,000 households | 141647 | 725637
|  | 3.2 Adoption of diversified livelihoods for poverty reduction and enhanced climate change resilience by 2,000 households. | 60681 | 248437
|  | 3.3 Enhanced vocational skills in 500 individuals. | 523 | 41140
|  | 3.4 Adoption of energy efficient mechanisms by households to reduce fuel wood dependency and drudgery amongst women. | 38417 | 72002
|  | 4.1 Knowledge management plan covering all main KPC-dependent user groups to improve awareness levels and facilitate informed decision making to address threats to KPC | -0.38462 | 5994.6154
|  | 4.2 Developed pool of products comprising research studies, learning/ case studies from the project, training modules and capacities for its dissemination through relevant tools. | 41747 | 60486
|  | 4.3 Local and National Level Campaigns/Workshops for dissemination | 12272 | 23707
|  | 5. Management costs | 12300 | 157644
|  | TOTAL | 353801.6154 | 1539058.6154
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST (USD) | Est. Completion Date
|  | 1.1 Socio economic baseline report with village level detailed analysis in the project villages | - | Sanctioned project period completed as on 31 March 2021 and the EE communicated its exit from the project at current level of achievement.
|  | 1.2 Baseline mapping and change assessments of natural resource base in project villages using GIS. | -
|  | 2.1 Robust community institutions in 56 villages with collective decision making of stakeholders at village / cluster / district / landscape level on issues of conservation, climate change, gender and development. | -
|  | 2.2 Participatory Impact monitoring | -
|  | 3.1 Adoption of climate resilient agricultural practices by 5,000 households | -
|  | 3.2 Adoption of diversified livelihoods for poverty reduction and enhanced climate change resilience by 2,000 households. | -
|  | 3.3 Enhanced vocational skills in 500 individuals. | -
|  | 3.4 Adoption of energy efficient mechanisms by households to reduce fuel wood dependency and drudgery amongst women. | -
|  | 4.1 Knowledge management plan covering all main KPC-dependent user groups to improve awareness levels and facilitate informed decision making to address threats to KPC | -
|  | 4.2 Developed pool of products comprising research studies, learning/ case studies from the project, training modules and capacities for its dissemination through relevant tools. | -
|  | 4.3 Local and National Level Campaigns/Workshops for dissemination | -
TOTAL
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? |  | NA
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk | Category of Risk
Failure in Community Mobilization to undertake the activities of building adaptive capacities of the community residing in the landscape. | Community has been sensitized and mobilization to undertake project activities is ongoing. Village level leadership is emerging and is a positive sign for project sustainability | Local resource persons have been selected as community mobilizers. Regular awareness building workshops, training sessions and exposure visits are being conducted for the community. Livelihood interventions are driven by skilling local resources - Paravets (men and women) for agriculture, livestock and alternative livelihoods have been created | Low
All stakeholders may not take part in the process as the individuals' capacity and commitment vary. There can be resistance from some stakeholders in adopting the suggested measures on account of perceptional differences. | The project's strength is working with multiple stakeholders. During Y IV, all stakeholders continued working together (including community, forest department, government line department and local CSOs) | The project has adopted a consultative and inclusive approach since project formulation. Regular interactions with the stakeholders is maintained through verbal and written updates about the project. The team is working in consonance with the roles and responsibilities of all the stakeholders. Additionally, the Village development plans and wealth ranking process which was done in participatory mode has ensured that all are represented and the most vulnerable are prioritized. | Low
Slow progress in implementation of the interventions due to unfavourable climatic factors and location accessibility issues | There were no unfavourable climatic impacts to the extent that caused damaged to the watershed structures or created accessibility issues | Watershed structures especially at mid ridge level are being redesigned to withstand sudden water burst. Accessability issues are dealt by ensuring frequent coordination with the community resources and village leaders using mobile phones. | Medium
Extreme weather events during the project lifetime undermine confidence of local communities in adaptation measures promoted by the project. | Late onset of monsoon, dry spells during monsoon period, less rainfall during crop growth period has caused loss in agriculture production systems. Heat waves in central India also impacted the NTFP collection rates | Community is responding satisfactorily to project interventions.Agromet stations have been installed and local weather advisories are made available to the farmer. It recognizes climate change is affecting them and the practices promoted have the potential of addressing these impacts in the long run. This has helped prevent crop losses due to hailstroms and other adverse climattic events Their confidence in allied livelihoods like Livestock management and poultry is also increasing and adoption is rising with demonstration effect. | Medium
Limited capacity/expertise of partner organisations to deliver project outputs. | Partner organizations are capacitated to deliver project outcomes successfully. Additional capacity has been developed by partnering with technical experts and CSOs | Project team has been conducting cross-learning sessions. During the reporting period various visits were made to different CSOs, KVKs, and other technical institutions for identifying innovations/best practices in agriculture and livelihoods. The project team is ensuring that there is continuous knowledge transfer and best practise sharing between the implementing partners. | Medium
Failure to create ownership of the project at the local level. | Project is accepted by the community and stakeholders at the local level | An inclusive approach has been adopted since project inception with focus on developing robust community based institutions in each of the project villages. Concurrence of Gram Panchayat is ensured for all the project activities to ensure ownership of the project with local government | Medium
Financial mismanagement | Financial practices are transparent, consistent and backed by evidence. | Strong systems of financial reporting have been developed in the project. Three levels of monitoring and reporting is being followed | High
Non-compliance with the laws and other administrative orders of national and state government | Villlage institutions as well as FES are following different laws around environment and labour are strictly followed up. | Strict adherence to the laws and administrative regulations are followed at all times. Any non-compliance is immediately reported and punitive action is taken within organizational policy framework. | High
Lack of interest to participate in project activities | Project participants are coming forward for proper implementation of the project. | Project participants are contineously imparted training on PRIs,conservation, adaptation and organic package of practices in order to generate interest among the participants.How ever during the reporting period, COVID induced restrictions and apprehensiond has hampered the pace of training and exposure visit resulted in slight disengagement in the implementation. | Medium
Exclusion of marginalised group from project benefits | Marginalised groups have been given equal importance . | VI is giving priority to land less families to get the work in the project and is planning to share the benefits in non land and non agriculte related activities.COVID-19 has also created some more vulnerable and maginalised HHs in the project villages. Team has taken initiatives to provide them rations, agri inputs and medicines from different sources to get them engaged with the purpose of the projects. | Medium
Inequitable representation of women in the village planning activities | Village institutions are taking the opinion of the women in planning process and sharing the plans in women groups meeting. | Regular women group meeting and involvement of SHG members has increased the women member's say in village level decision making process. | Medium
Lack of confidence in women folk to participate in project activities | Number of women participants is increasing day by day. | We are organising women groups meeting and in the process of regularising habitation level women groups meeting and conducting training programme for the women members resulted in active participation of women. | Low
Delay in wage payments | Payments are made through A/C transfer. | During reporting period payments have been released through accounts of the beneficiary. | High
Non adherence to minimum wage | Payments are made through A/C transfer/Cheques. | we are following the minimum wages as announced by the district collector from time to time. In case there is delay in announcement we are following the MGNREGA rates. | Medium
Child labours | No children are engaged in any of the works supported from the project. | Village institutions are well aware and are closely monitoring works. VI does not allow any child labour in the work. | High
Labour hours | Village institutions are ensuring that one labour should not work more that 8 hours in a day in the work sites supported through project. | Work hours are defined for the laborers. They stick to the norms | Low
Treatment of non-biodegradable material like polythene bags of saplings , micro irrigation materials etc. | Village institutions have been trained and are taking appropriate measure on waste disposal. | Awareness towards hazards of non-biodegradable material such as polythene etc is created and immediate removal of such materials from site is practised. | Medium
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Category >50%
COVID 19 Pandemic | COVID 19 pandemic may affect implementation of planned activities | During Reporting period we have engaged community to follow the COVID norms and abided by the rules for controlling infections. COVID awareness campaign, developing small videos, messages, posters etc, engaging project participants in various webinar etc have been taken regularly to improve the community awareness on COVID. with some precautions, project implemented smoothly. | High
Changes in forest department staff | Transfer of officers in forest department in the project area leading to slight delays. | Regular meeting with forest department at the state level and at the district level is being undertaken. | Medium
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Risk mitigation measures included - 1. Covid-19 pandemic situation has affected socio-economic dynamics of the project region. The communities as well as the implementing teams are facing unprecedented and new challenges due to travel restrictions, extended lockdowns and shortage of labour. The implementing team and the communities have come together along with the local authorities following diligently the norms of social distancing and maintaining hyegiene to minimize the spread of Covid-19. The implementing teams in cooperation with the governemnt authorities have provided support to the communities in terms of groceries and medical aid that have been funded by either government programs or donations from other agencies/CSRs.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity |  |  | Biasness in allocating project benefits | Project beneficiaries would be selected unanimously in the village level planning process. | Poorest of the poor would be allocated benefits. Vulnerable sections and partiularly the women headed/ single women headed HHs given priority in allocating benefits. | Dominant caste in the projet villages influence gram sabha to grab the benefits allocated through project. Single women headed HHs and women headed HHs not been considered as the participants in any project. | Benefiiaries have been selected through a unanimous decision taken in the Gram sabha and on the basis of a a wealth ranking exercise.Demography and gender aspects have been taken into consideation while allocating project benefits under project |  | Robust mechanism have been established to select to Poorest of the poor and vulnerable HHs to be the part of the project. Baisness in selection have been avoided. | Most of the project villages are falling within the jusrisdiction of the Fifthe schedule area of India constitution.In each of the project village, village institution in the name of Gram Paryavaran samiti, village development committee etc have been formed by taking the members unanimously selected by the gram sabha. While undertaking any intervention, Village institution convene it's meeting to select the proper beneficiary. Different factors are taken into consideration on priority basis such as landless/ vulnerability/ women headed household/ single women HHs/marginal farmers/demography/gender etc for selecting the beneficiaries. Again beneficiaries are selected through an unanimous decision taken in the Gram sabha and on the basis of a a wealth ranking exercise. Beneficiaries have been selected through the unanimous decision of the Gram sabha and along with that interventions on common land have been undertake which has benefited a lot to all the house holds in village. The intervention on commons, open discussion and unanimous decision making at the level of gram sabha have contributed towards increased participation of community in project implementation.Village institutions are taking proper care and more sensitive towards inclusion of most vulnerable community to be the part of project.
|  |  | Lak of interest to participate in project activities | Village level institution i.e Gram Sabha and Village natural resource management committee would prioritise and support the most vulnerable and deserved house holds through the project. | The most vulnerable and deserved beneficiaries selected through the unanimous decision taken in the gram sabha. | Influential section of the society used to grab thedifferent opportunity available | Beneficiaries have been selected through the unanimous decision of the Gram sabha and along with that interventions on common land have been undertake which has benefited a lot to all the house holds in village. The intervention on commons, open discussion and unanimous decision making at the level of gram sabha have contributed towards increased participation of community in project implementation. |  | Community interest in project implementation is improving day by day.They are spontaneously taking initiative to replicate the model introduced through project.
3 – Marginalized and vulnerable Groups |  |  | Exclusion of marginalised groups from project benefits | All the project villages are located in the 5th scheduled area and 72% of the population are from scheduled tribe community. To avoid social exclusion of maginalised communities orientation and sensitisation would be initiated at village level to ensure equal participation and no social impact fall on the marginalised and vulnerable group. | Scheduled tribe community and women have been given priority while undertaking various intervention through project. Initiatives have been taken to improve the participation of women in the village level decision making process through various trainings and involvement in collective action and strengthening of existing SHGs. | Scheduled tribe community were not given due importance in the village level decision making processes as well as access & benefit sharing. Women representation in Gram sabha was less than 10% and participation in the village level decision making was invisible. | The vulnerable community (i.e SC/ST and women members) have been given due importance and priority while deciding the benefit sharing and access to new opportunity. The selection is being done through usinng the tools such as PRA and wealth ranking. Habitation level women groups have been formed and regular meetings of these groups are being ensured. Revival of the defunct SHGs, capacity building of the the SHG members have been a regular activity to ensure the improved participation of women members in decision making process. |  | Village institutions are taking proper care and more sensitive towards inclusion of most vulnerable community to be the part of project.
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | Inequitable representation of women in village level planning process | Capacity building of women would be given focus.Women SHGs would be revived.Equitable participation of women would be ensured . | Training of women on gender , PRI,and othr related themes.Formation, revival and strengthening of women groups and SHGs. Improvement in the no of women participation in gram sabha and there by decision making process. | No structured training were being imparted to the women members.Women SHGs lied defunct.Regular interaction of women in a group around gender issues were not taking place. Women were not given due importance in decision making process. | Structured trainings have been designed and the women members are being trained accordingly. Training around gender discrimination, role of women in Panchayat Raj Institution, decision making process, women as a farmers etc have been imparted. Women have been provided a platform at habitation level to be in group, so that they can present their say in the village level decision making process. |  | Gradually the women participation in the village level meeting has improved. Women members are becoming well informed about gender discrimination and more vocal in presenting their stake in village level decision making process.
6 – Core labour rights |  |  | Delay in Wage Payment | Timely payment would be ensured for all the labour centric works undertaken in the project. | A set of financial document maintained at village level and Payment to Labourers within a period of 7-15 days after the completion of specific task is ensured . | No financial document at village level and non maintainace of financial details at village level. | Village Institution are maintaining a set of record both physical and financial to maintain every minute details of the different interventions being undertaken. Duration of the work, end date of the work etc. are maintained . Payment is made through the bank account transfer from the implementing agencies within 15 days of the completion of work. |  | Timely payment has been ensured. It resulted in improved participation of community in implementation of the project and replicating the impact of different intervention.
|  |  | Non adherene to minimum wage | Wages would be determined on task allotted and wage rate will be calculated on the basis of the prevailing minimum wage rate for the task. | Wages determined on the basis of the task allotted and keeping in view the minimum wage rate as declared by District Colletor in each financial Year. Technical estimates based on SOR for each piece of work is prepared and maintained. Labour payment is made accordingly. | Non adherence of the minimum wage act and wages were being paid according to the system based at village level. | All the payment are made on the basis of the SOR rate and the minimum wage rate declared by District Collector in eah financial year.
|  |  | Child labour | No child labourer would be engaged in any of it's activity and any forms of forced and compulsory labour would be eliminated | Labourers beyond 18 years of age are engaged in the work. | Child labour norm were not being followed. | Village institution members and leaders are informed about differen Act to prevent the child labour and they are vigilant enough not to engage the persons bellow 18 years of work in any of the activities undertaken through the project.
|  |  | Labour hours | Timing of working hours determined in consultation with the labour and prevailing practices in the area | On an average 8 hours of working is ensured. How ever labour hours are proportionately adjusted based on the technical estimate of the piece work. | Prescribed labour hours were not the practice of the day. | Minimum labours hours is followed irrespective of the nature and pattern of the work.
7 – Indigenous peoples |  |  | Activities that are inconsistent with the tribal groups culture and practices | • The project will not contravene the rights of indigenous people. • The indigenous communities will form the majority of the beneficiaries through the project activities. As much as 70% of the beneficiaries are expected to be indigenous. • The project activities planned to be implemented will be finalized through a participatory process and will ensure that indigenous communities are consulted before finalizing and implementing any project activity. • Consultations have already been undertaken in villages with 100% indigenous population, wherein their buy-in was taken to undertake the project activities in the village. Similar consultative process will be initiated in other project villages. | Number/percentage of project activities validated through participatory consultations with indigenous communities; Proportion of indigenous beneficiaries among total project beneficiaries (target: 70%); Number of grievances/complaints raised by indigenous communities regarding cultural incompatibility of activities | At project inception, consultations were undertaken in selected villages with 100% indigenous population – baseline participation was established at these pilot consultations. Baseline beneficiary composition: ~0% coverage before project start (indigenous households not yet enrolled as beneficiaries). Baseline for grievance redressal: No formal complaints documented at project inception. | Consultations: Structured participatory consultations were held with indigenous households before finalizing activities. Their views were incorporated, ensuring cultural compatibility. Beneficiary targeting: As per progress data, indigenous households constitute the majority of current beneficiaries, in line with the project’s 70% target. FPIC process: Documentation of community consent (meeting minutes, signed attendance registers) was collected in project villages where new interventions were initiated. Capacity building: Orientation meetings conducted with project staff and implementing partners on cultural sensitivity and rights of indigenous people under ESP.
8 – Involuntary resettlement
9 – Protection of natural habitats
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency |  |  | • Polluting of the ecotourism sites developed under the project by the tourists visiting • Treatment of non biodegradable material like polythene bags of saplings, micro irrigation material etc. | • Capacity building of the tourist operators will be done to instruct tourists not to litter when they visit the eco tourism sites developed. Sign boards will be put up at the ecotourism place requesting tourist to keep the site clean and pristine. • CBOs will be capacitated/ byelaws will be made to impose fines on tourists operators who fail to prevent tourist littering and causing harm to the pristine environment. • Community will be mobilized with the effect of littering/burning of non biodegradable materials like polythene bags and other plastic material. • Field staff will ensure that while supplying inputs to project beneficiaries non biodegradable material is collected and stored at a place till collected by the waste collector for recycling. • Community will be sensitized for disposal of plastic pipes used in the case of micro irrigation and will be guided to a local recycling plant. | Number of awareness signboards installed at ecotourism sites. Quantity of non-biodegradable material (sapling bags, irrigation pipes, etc.) collected for recycling (kg/tonnes). Number of storage/collection points established for temporary storage of plastic waste. | At inception, no signboards installed at ecotourism sites. Tourist operators had no formal training on waste management or litter prevention. No formal monitoring/reporting of littering incidents at project sites | Signboards were installed at all ecotourism sites with clear instructions to maintain cleanliness. Capacity-building sessions were conducted for tourist operators on waste management and eco-friendly practices. Community-Based Organizations (CBOs) were oriented and supported to draft byelaws imposing penalties on operators failing to prevent tourist littering.
13 – Public health
14 – Physical and cultural heritage
15 – Lands and soil conservation |  |  | Damage to land and soil resources. | Implementation of development of watershed/application of efficient irrigation mechanisms will be done through a participatory process which will include recommendations from technical experts as well as of the community members involved. | Adequate water supply | Water supply is not suffient | Land and water conservation and management practices are implemnted
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No risks identified
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | NA
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | A set of institutional mechanism has been introduced to implement the ESP safe guard measure. Village level institution have been formed through the approval of Gram panchayat. The village institutions through it's gram sabha ensures to implement it. Village institutions develop governance mechanism for ensuring the proper management of the natural resources, creating spaces for the poorest of the poor, provides space for women to have their say in Village level decision making process, maintaining transparency in financial transaction, prevent child labour , protecting the interest of the indegenous people, ensuring community interest and participation in projet implementation, conservation of the local biodiversity, reducing the human -wild life conflict etc.
Have the implementation arrangements been effective during the reporting period? |  | Implementation arragements has steadily improved over time and showing evidences of effectiveness.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The Executing Entity provided the consulting support and expertise on Environment and Social Compliance to the implementing agencies. The on-field imlementations are reguarly monitored by the EE. Any lapse in comliance to the ESP compliances are highlighted immediately and corrective actions are taken by implementing agencies.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Implementation arragements has steadily improved over time and showing evidences of effectiveness. However due to COVID -19 induced restrictions, travel to all the locations, undertaking monitoring etc has slightly hampered
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts? |  | Yes
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievance received
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | YES
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Enhanced capability of the community to take collective action, practice adaptive livelihoods and conservation | Outcome | Number of robust community institutions in the project villages, with active women particpation | Limited or no participation of women in the decision making process | Robust and gender neutral village level community based institutions in 56 project villages | Good
Robust community institutions in 56 villages with collective decision making of stakeholders at village / cluster / district / landscape level on issues of conservation, climate change, gender and development | Output | Number of men and women participants in the workshops/ training sessions | Lack of cohesiveness in the community, low participation of women in the decision making process | At least 30% women participants in village CBOs | Satisfactory
Robust community institutions in 56 villages with collective decision making of stakeholders at village / cluster / district / landscape level on issues of conservation, climate change, gender and development | Output | Number of women covered through gender based trainings/exposure visits | Lack of confidence in women | - 56 exposure visits are provided to selected women SHGs members -At least 1,500 women are mobilized into active SHGs | Satisfactory
Improved adaptive capacity of the community and landscape | Outcome | % decrease in women drudgery | Women face extreme drudgery as they are the primary contributor to the farm as well as the household level activities which include collecting fuel wood and fodder, fetching drinking water | Reduction in women drudgery by 20-25% in 1,000 households | Satisfactory
Improved understanding on threats and climate change impacts on the landscape and enhanced involvement of stakeholders | Outcome | % of households having improved understanding on the importance of having robust and gender neutral CBOs as means to climate resilience | Lack of community sensitivity/awareness towards the importance of institutions/ forest conservation / gender issues/climate change impacts | Enhanced awareness on the importance of being a part of active and gender neutral CBOs, collective decision making, and adopting resilient livelihoods | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
Nil |  | Nil
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | Yes,
Have the implementation arrangements at the IE been effective during the reporting period? |  | Implementation arragements has steadily improved over time and showing evidences of effectiveness.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The Executing Entity provided the consulting support and expertise on GenderCompliance to the implementing agencies. The on-field imlementations are reguarly monitored by the EE. Any lapse in comliance to the ESP compliances are highlighted immediately and corrective actions are taken by implementing agencies.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Implementation arragements has steadily improved over time and showing evidences of effectiveness.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Yes. Project staffs, volunteers have been trained on various legal provisions around gender related issues. Sensitisation programme for the project staffs , community resource persons volunteers have been undertaken to make them gender sensitive while working community on different issues related to gender.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances received
Yes
No
Partially

## ESP and GP Guidance Notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1 Socio economic baseline report with village level detailed analysis in the project villages. |  | Completed Socio Economic Assessment of the Project villages. |  | Socio-economic profile of project villages through Focussed group discussion has been created. Wealth Ranking and Village Development plans have been completed. The project team undertaken a Household - Economic Analysis which has been incorporated in the Socio - Economic analysis/ Basline report. | S
| Output 1.2 Baseline mapping and change assessments of natural resource base in project villages using GIS. |  | GIS mapping and analysis for KPC landscape has been completed. Landsat imagery is captured and initial analysis of the same is completed. |  | Landsat imagery using GIS has been created for the landscape and initial analysis of the same is completed. The findings endorse that assumptions made in the proposal like degradation/ reduction of edge density of fringe forests. Annual change assesment to measure changes to the village woodlots/surrounding forests is ongoing and will be incorporated in the Final Baseline report. Comprehensive set of maps that outline the natural resources in the 56 project villages at baseline have been created too. | S
| Output 2.1 Robust community institutions in 56 villages with collective decision making of stakeholders at village / cluster /district / landscap level on issues of conservation, climate change, gender and development. |  | Creation of new/ Strengthening of existing village level/ gender centric institutions is completed. |  | Village institutions are in place in all the project villages. Gender neutrality in institutions has also been ensured through engaging Self-Help Groups (SHGs) and Mahila Sabha. In the mean time the women group have created a space for them selves in the village level decision making process. Further, through exposure visits, meetings and classroom trainings the community has been constantly exposed to issues related to resource extraction, conservation and protection. Process of creating Byelaws around resource extraction/ protection is in place. During the reporting period, owing to Covid-19 pandemc restrictions Capacity Building of the women members has hampered to some extent. | S
| Output 2.2 Participatory impact monitoring. |  | PIMs were planned for 46 villages. |  | PIM interventions were required to be intensified and scaled-up. In the reporting period, project implenting partners had planned for this intervention, however due to second wave of Covid-19 pandemic the progress on the same has been hampered. | MU
| Output 3.1: Adoption of climate resilient agricultural practices by 5,000 farmers. |  | 1010 farmers are mobilzed on improved/ climate resilient agricultural practices in the project villages of Mandla and Balaghat districts. (Completed for 3990 farmers by March 2020) Water-related entry point activities are completed in all the project villages and Land Development/ Restoration activities are completed on 265 hectares. (Completed in 1535 hectares by March 2020) Micro-irrigation is promoted with 266 farmers. (Completed with 294 farmers by March 2021) |  | The project has reached out to 4582 farmers through demonstrations, exposure visits, classroom trainings and input support. (592 farmers reached in FY 2020-21) The farmers are trained and handholding support given to adapt improved practices like SRI, Organic farming, Indigenous seed/ improved seed, bio-pesticides etc. (Water-related entry point activities are completed in 288 hectared in FY 2020-21) Eight (8) Agromet stations have been installed and weather advisories are being issued to the farmers regularly. Entry point activities have been completed in all the project villages in YI. Promotion of micro irrigation mechanisms has been completed with 305 farmers. (Completed with 11 farmers in FY 2020-21) | S
| Output 3.2 Adoption of diversified livelihoods for poverty reduction and enhanced climate change resilience by 2,000 households. |  | 503 households supported for alternative livelihood or enterprises (completed for 1497 households by March 2020) |  | 1913 households supported for alternative livelihood and enterprises in by March 2021 (completed for 416 in FY 2020-21). | S
| Output 3.3 Enhanced vocational skills for 500 individuals. |  | 391 youth imparted training in improvement of skills and alternative enterprises (completed for 109 youth by March 2020). |  | 110 youth imparted training in improvement of skills and alternative enterprises (completed for only 1 youth in FY 2020-21) | U
| Output 3.4 Adoption of energy efficient mechanisms by 1,000 households to reduce fuel wood dependency and drudgery amongst women. |  | 320 biogas plants, 530 cook stoves (domestic), 100 cook stoves (commercial) and 240 solar lights installed covering at least 840 households |  | 175 biogas plants, 70 cook stoves (domestic only), and 673 solar lights have been installed covering 923 households. (95 biogas plants and 313 solar lights installed in FY 2020-21). Note: After March 2021 (in FY 2021-22), additional 95 biogas plants were installed for which 'advance against expenditure' of INR 19,60,000 was booked in FY 2020-21. The sanctioned funds under the component were utilized for the same within the unit cost limit. | S
| Output 4.1 Knowledge management plan covering all main KPC-dependent user groups to improve awareness levels and facilitate informed decision making to address threats to KPC. |  | Finalization of the Knowledge Management Framework. Implementaion of KM. VDC level plan and organic cultivation modules prepared |  | Implementation is started. Experts have been identified and consultation workshop has been conducted for commensing the research around invasive species, human animal conflict etc. These are expected to be intesified and completed in the year IV. Vegetable cultivation, organic cultivation modules are being developed | U
| Output 4.2 Developed pool of products comprising research studies, learning/ case studies from the project, training modules and capacities for its dissemination through relevant tools. |  | Four research studies, documentries, training modules have been planned in the third year. |  | KM framework has been finalized. Secondary review has been initiated for research studies. Module on "Women and Child Development" have been prepared and distributed. | U
| Output 4.3 Local and National Level Campaigns/Workshops for dissemination |  | Planned to be undertaken in year IV |  | 4 out of 8 inter-community workshops completed (3 completed in FY 2020-21) | S
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Soujanya Shrivastava
| Email: | soujanya.shrivastava@natwest.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
1) Ratings have been provided based on achievements in project implementation and its acceptance by the community. The overall rating of the project would be between Satisfactory. Community participation is strong and community is planning and owning up project activities. Learnings of program and knowledge management is one aspect that was needed to be taken up in the last year. There has been some delay in conducting research studies but it will help to capture the impact which is now clearly evident. Soil erosion and subsequent land degradation has reversed. 2) During the mid-term evaluation of the project the observations on the ground and responses from beneficiaries were found to be highly positive. During the interaction with community members, they were observed to be satisfied and motivated towards bringing positive change in their respective villages with enthusiasm and awareness towards importance of ecological conservation. 3) The positive trend continues in interventions of Land restoration - Lantana Eradication for eg., that has created multiple benefits like - reduced man-animal conflicts; improved regeneration, created grazing areas, reduced dependence of livestock on forests. The land restoration activities have enhanced wider in scope and is being taken up as among the priority activities by villagers. Community is now more involved in Protection/Conservation of commons and surrounding forests. There are positive trends noticed in adoption of improved farming practices - over 4000 farmers have benefitted from improved/ climate resilient agricultural practices in the project villages. 4) Strengthening of village institutions in all 56 project villages has been one of the key achievements of the project so far. The gender focussed interventions through Mahila Sabhas (Womens’ Groups) in 32 project villages have helped in empowering the women who have created space for themselves and being the part in the decision making process at the village level. 5) Progress has been slow on Knowledge Management interventions in 24 villages and Participatory Impact Monitoring in all project villages. Implementation has delayed, but started and a fair progress has been made in the form of workshops on research around invasive species and human-animal conflicts. VDC level plan and organic cultivation modules have been prepared for 32 villages. KM interventions will be intensified in Y IV. PIM actvities will be coordinated and monitored in the Y IV
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Output 1.1 Socio economic baseline report with village level detailed analysis in the project villages. |  | Completed Socio Economic Assessment of the Project villages. |  | Socio-economic profile of project villages through Focussed group discussion has been created. Wealth Ranking and Village Development plans have been completed. The project team undertaken a Household - Economic Analysis which has been incorporated in the Socio - Economic analysis/ Basline report. | S
| Output 1.2 Baseline mapping and change assessments of natural resource base in project villages using GIS. |  | GIS mapping and analysis for KPC landscape has been completed. Landsat imagery is captured and initial analysis of the same is completed. |  | Landsat imagery using GIS has been created for the landscape and initial analysis of the same is completed. The findings endorse that assumptions made in the proposal like degradation/ reduction of edge density of fringe forests. Annual change assesment to measure changes to the village woodlots/surrounding forests is ongoing and will be incorporated in the Final Baseline report. Comprehensive set of maps that outline the natural resources in the 56 project villages at baseline have been created too. | S
| Output 2.1 Robust community institutions in 56 villages with collective decision making of stakeholders at village / cluster /district / landscap level on issues of conservation, climate change, gender and development. |  | Creation of new/ Strengthening of existing village level/ gender centric institutions is completed. |  | Village institutions are in place in all the project villages. Gender neutrality in institutions has also been ensured through engaging Self-Help Groups (SHGs) and Mahila Sabha. In the mean time the women group have created a space for them selves in the village level decision making process. Further, through exposure visits, meetings and classroom trainings the community has been constantly exposed to issues related to resource extraction, conservation and protection. Process of creating Byelaws around resource extraction/ protection is in place. During the reporting period, owing to Covid-19 pandemc restrictions Capacity Building of the women members has hampered to some extent. | S
| Output 2.2 Participatory impact monitoring. |  | PIMs were planned for 46 villages. |  | PIM interventions were required to be intensified and scaled-up. In the reporting period, project implenting partners had planned for this intervention, however due to second wave of Covid-19 pandemic the progress on the same has been hampered. | MU
| Output 3.1: Adoption of climate resilient agricultural practices by 5,000 farmers. |  | 1010 farmers are mobilzed on improved/ climate resilient agricultural practices in the project villages of Mandla and Balaghat districts. (Completed for 3990 farmers by March 2020) Water-related entry point activities are completed in all the project villages and Land Development/ Restoration activities are completed on 265 hectares. (Completed in 1535 hectares by March 2020) Micro-irrigation is promoted with 266 farmers. (Completed with 294 farmers by March 2021) |  | The project has reached out to 4582 farmers through demonstrations, exposure visits, classroom trainings and input support. (592 farmers reached in FY 2020-21) The farmers are trained and handholding support given to adapt improved practices like SRI, Organic farming, Indigenous seed/ improved seed, bio-pesticides etc. (Water-related entry point activities are completed in 288 hectared in FY 2020-21) Eight (8) Agromet stations have been installed and weather advisories are being issued to the farmers regularly. Entry point activities have been completed in all the project villages in YI. Promotion of micro irrigation mechanisms has been completed with 305 farmers. (Completed with 11 farmers in FY 2020-21) | S
| Output 3.2 Adoption of diversified livelihoods for poverty reduction and enhanced climate change resilience by 2,000 households. |  | 503 households supported for alternative livelihood or enterprises (completed for 1497 households by March 2020) |  | 1913 households supported for alternative livelihood and enterprises in by March 2021 (completed for 416 in FY 2020-21). | S
| Output 3.3 Enhanced vocational skills for 500 individuals. |  | 391 youth imparted training in improvement of skills and alternative enterprises (completed for 109 youth by March 2020). |  | 110 youth imparted training in improvement of skills and alternative enterprises (completed for only 1 youth in FY 2020-21) | U
| Output 3.4 Adoption of energy efficient mechanisms by 1,000 households to reduce fuel wood dependency and drudgery amongst women. |  | 320 biogas plants, 530 cook stoves (domestic), 100 cook stoves (commercial) and 240 solar lights installed covering at least 840 households |  | 175 biogas plants, 70 cook stoves (domestic only), and 673 solar lights have been installed covering 923 households. (95 biogas plants and 313 solar lights installed in FY 2020-21). Note: After March 2021 (in FY 2021-22), additional 95 biogas plants were installed for which 'advance against expenditure' of INR 19,60,000 was booked in FY 2020-21. The sanctioned funds under the component were utilized for the same within the unit cost limit. | S
| Output 4.1 Knowledge management plan covering all main KPC-dependent user groups to improve awareness levels and facilitate informed decision making to address threats to KPC. |  | Finalization of the Knowledge Management Framework. Implementaion of KM. VDC level plan and organic cultivation modules prepared |  | Implementation is started. Experts have been identified and consultation workshop has been conducted for commensing the research around invasive species, human animal conflict etc. These are expected to be intesified and completed in the year IV. Vegetable cultivation, organic cultivation modules are being developed | U
| Output 4.2 Developed pool of products comprising research studies, learning/ case studies from the project, training modules and capacities for its dissemination through relevant tools. |  | Four research studies, documentries, training modules have been planned in the third year. |  | KM framework has been finalized. Secondary review has been initiated for research studies. Module on "Women and Child Development" have been prepared and distributed. | U
| Output 4.3 Local and National Level Campaigns/Workshops for dissemination |  | Planned to be undertaken in year IV |  | 4 out of 8 inter-community workshops completed (3 completed in FY 2020-21) | S
[5 empty] | Overall Rating | MS | Except slow progress, project is satisfactorily positive impact as per project targets.
| Name: | Tapan Kumar Sahoo
| Email: | dcas@nabard.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project has made notable progress in achieving its intended outcomes, though only around 65% of the planned activities could be completed during the implementation period. Despite this shortfall in activity completion, the project succeeded in meeting most of its key objectives and generating positive impacts on communities and ecosystems. Community participation remained strong, with villagers actively planning, implementing, and sustaining project activities. The overall performance rating of the project is assessed as Marginally Satisfactory
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other |  |  | NIL
NIL
NIL
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1: Improved understanding of prevalent dynamics and changes in area of interventions | · Number of village level meetings conducted | · Only demographic data is available for these 56 villages (Census, 2011) | One consolidated report capturing information of aff 56 villages prepared | One report with 56 project village level profiles will be created; these will include the socio economic and environmental profile of the village.
| · % of village households represented in meetings | · No socio-economic and environmental data is available at the village level. | 56 village development plans prepared | 56 Village development plans will be created through adopting a participatory rural appraisal approach.
| · Number of men and women participants | · No information about village institutions is available | Village wealth ranking prepared for all 56 villages | Village level wealth ranking will be done to prioritize beneficiaries
| · Number of village development plans prepared | · No village development plans are available and development activities are undertaken in a sporadic manner
Output 1.1: Socio economic baseline report with village level detailed analysis in the project villages | · Number of village level meetings conducted | · No information about the prevalent issues in the villages. | Prepared the comprehensive plan covering all 56 villages | 1 comprehensive baseline document including socio economic and environmental profile of the 56 villages.
| · % of village households represented in meetings | · No broad wealth ranking available at village level. | Relevant information was made available to the project team; 50% of the village households represented in meetings | · Relevant Information available to the project team to prioritize, plan and implement project activities at the village level
| · Number of men and women participants |  | Development activities we implemented using the plan; 9687 participants in the meeting | · Development activities are implemented in the village using a plan created through a consultative approach in order to achieve long term resilience.
Output 1.2 Baseline mapping and change assessments of natural resource base in project villages using GIS. | · Area/villages covered with Satellite imagery | · No satellite level data available for project villages | 56 plans prepared outlining the natural resources in the village at baseline | · Comprehensive set of maps that outline the natural resources in the 56 project villages at baseline.
| · Number of villages with mapping of natural resources | · No mapping of natural resources for the 56 villages is available at the baseline level | Annual change assessments performed at all vilages | · Annual change assessments to measure changes to the village woodlots/ surrounding forests.
Outcome 2: Enhanced capability of the community to take collective action, practice adaptive livelihoods and conservation | Number of robust community institutions in the project villages Number of meetings, trainings and exposure visits conducted on institution building % of people participating in institution meetings % of women participants Area of forest under community conservation | Lack of robust village level institutions with good governance Lack of collective action and awareness towards village development and conservation Limited or no participation of women in the decision making process | All 56 gender neutal community based institutions are in place. Awareness level and capacity for collective action enhanced | Robust and gender neutral village level community based institutions in 56 project villages. Enhanced awareness levels and collective action ability towards village development and conservation activities.
Output 2.1: Robust community institutions in 56 villages with collective decision making of stakeholders at village / cluster / district / landscape level on issues of conservation, climate change, gender and development. | · Number of meetings / trainings conducted for formation and strengthening of CBOs | · Lack of robust institutions, collective action due to conflicts, defunct institutions | Regular monthly meeting conducted in all 56 villages (2424 number of meetings conducted) | · Monthly meetings of village CBOs conducted for 56 villages for 4 years
| · Number of men and women participants in the workshops/ training sessions | · Over extraction of forest resources leading to degradation | 97 trainings and 44 exposure visits conducted (2680 particpants) | · 112 trainings and 56 exposure visits on capacity building are provided to selected members of 56 village level CBOs.
| · % of participants with respect to total village population | · Lack of cohesiveness in the community, low participation of women in the decision making process | 3000 hectares of forest area is marked under sustainable management | · At least 3,000 hectares of forest area is brought under sustainable management
| · Area brought under community management/ protection. | · Lack of confidence in women | 81 SHGs revived/created | · At least 150 SHGs are revived/ created and 4 trainings per year are provided to women SHG members
| · Number of self-help groups active with average savings and active inter- loaning | · No internal saving mechanism which can meet emergency requirements is available with the village community | 24 exposure visits completed for women SHGs | · 56 exposure visits are provided to selected women SHGs members
| · Number of women covered through gender based trainings/exposure visits. |  | 50% of the village households particpated in the planning process | · At least 50% of the village households actively participate in planning and implementing village development plans.
|  |  | 30% women participated in village CBOs | · At least 30% women participants in village CBOs
|  |  | 1651 women covered | · At least 1,500 women are mobilized into active SHGs
Output 2.2: Participatory Impact monitoring | · Number of village level CBOs undertaking participatory impact monitoring | · Sporadic implementation of development activities in the project village with no monitoring or performance measurement | 11 Particpatory impact monitoring conducted, with 138 particpants, which is around 2% of the village polupation | · 112 (Midterm and end term) participatory impact monitoring exercises conducted by members of the village level CBOs for all the 56 villages
| · Number of participants | · No long term village development plans and no involvement of the village community in monitoring performance
· % of participants with respect to total village population
Outcome 3: Improved adaptive capacity of the community and landscape | % of households having capacity, access to inputs and mechanisms to implement sustainable and adaptive livelihood techniques. % increase in gross income of households % increase in cropping intensity % decrease in women drudgery % reduction in forest resource dependence of beneficiary households | Practice of traditional livelihoods with high vulnerability to climatic variations and with high forest dependence. Forest resources are the coping mechanism for community during period of economic stress caused due to livelihood failures Low education levels and information outreach Lack of informed decision making; Decision making influenced by individuals/ enterprises with vested interest.  Information, resources and skills about other market driven alternate livelihoods/ vocations is lacking, leading the community missing out on diversified employment opportunities Women face extreme drudgery as they are the primary contributor to the farm as well as the household level activities which include collecting fuel wood and fodder, fetching drinking water. | 2850 HH have direct access to at least one of the improved practices Every household having an increased income of Rs.15000-20000/annum due to different intervention undertaken in the project 1497 households (96% of the target) have been benefitted from interventions on demonstration of alternate livelihood / enterprise options and supply of inputs and implements Achieved the reduction in fuel wood dependency on KPC by at least 1,500 tons. 1.5 tonnes of grass fodder is being produced from one hectare. Accordingly there is an improvement of 3144 tonnes of grass fodder production and proportionate reduction in dependency on KPC | At least 75% households in 56 villages have access to and practice at least one of improve agricultural/ livestock/ energy efficient/ alternative livelihoods/ vocational skills practices / practices that enhance community and landscape resilience. At least 15-20% rise in gross income of the beneficiary households Increase in cropping intensity by 50% Improved livelihoods related decision making in at least 50% households due to improved access to information. Reduction in livestock fodder dependency on KPC by at least 3,000 tons. Reduction in fuel wood dependency on KPC by at least 1,500 tons.
Output 3.1: Climate resilient agricultural practices are adopted by the identified beneficiaries | · Number of agricultural demonstrations conducted for par workers and farmers. | · Present agricultural practices are found to be non climate resilient against climatic risks like extended dry spells, high intensity rainfall, hailstones and Frost | 4582 housedolds achieved | · At least 5,000 households receive inputs, technical assistance and linkage support for improved and climate resilient agricultural livelihoods.
| · Number of households practicing SRI, other improved package of practices. | · Agriculture practiced is mostly rainfed, with high crop raiding by wild herbivores making the agriculture in the region extremely sensitive and prone to regular crop failures. | 24 trainings completed | · 8 trainings are conducted for 28 paraworkers (16 training days for 4 years)
| · Area treated through watershed activities | · Farmers are lured towards high yielding hybrid crop varieties requiring heavy inputs (water, fertilizers and pesticides) | 55 demonstration plots completed | · 64 demonstrations are conducted for the farmers (16 per year)
| · Number of households with access to micro irrigation mechanism |  | 4763 farmers received mobilisation trainings | · Each farmer receives 4 mobilization training days each year
| · Number of households with access to weather information |  | 1823 ha is covered under watershed development | · Atleast 1,800 ha is covered by watershed development activity
|  |  | 304 households supported for microirrigation | · At least 560 households support on installing Micro irrigation mechanism.
|  |  | 4 agromet stations completed | · At least 5 agromet stations are installed covering the 56 villages
Output 3.2: Adoption of diversified livelihoods for poverty reduction and enhanced climate change resilience by 2,000 households | · Number of households adopting alternative livelihoods | · Limited information and means to practice diversified livelihoods. | 1913 households adopted alternate livelihood measures | · At least 2,000 households have access and means to practice alternative livelihoods and diversify their income sources.
| · Number of linkages created to complement alternative livelihoods | · No alternative livelihoods for landless other than agriculture labor/ migration | 1537 beneficiries received mobilisation trainings | · Each beneficiary receives 4 mobilization training days each year on alternative livelihood adopted
|  |  | One market linkage system established | · At least 2 robust market linkages are created for alternative livelihoods
Output 3.3: Enhanced vocational skills in 500 individuals. | · Number of youth that have undergone skill training. | · Distress migration of unskilled labor leading to many social and physical impacts to the household | 110 youth trained | · At least 500 youth are skill trained for employability.
| · Linkages created to complement supply of skilled youth | · Lack of awareness in the youth about the market driven vocational employment opportunities available | 22% youth facilitated | · At least 50% youth are facilitated with placement linkages
· Limited local opportunities for training in vocational skills and increasing demand of skilled manpower
Output 3.4 Energy efficient mechanisms to reduce fuel wood dependency are adopted | · Number of households having access to bio-gas plants | · Lack of alternative energy sources/ arrangements. | 175 households have access to biogas | · At least 400 household have access to bio-gas
| · Number of households and establishments having access to efficient cooking stoves | · Drudgery in women and adverse impacts on health | 70 households have access to energy efficient cooking stoves | · At least 600 households have access to energy efficient cooking stoves
| · Number of households have access to solar lanterns | · High extraction of fuel wood from the forest for meeting energy requirements | No achievement | · At least 100 efficient cooking stoves are provided to small establishments
|  |  | 673 households provided with solar lanterns | · At least 600 households are provided with solar lanterns
Outcome 4: Improved understanding on threats and climate change impacts on the landscape and enhanced involvement of stakeholders | % of households having improved understanding on the importance of having robust and gender neutral CBOs as means to climate resilience. % of household having improved understanding on the importance of conserving and utilizing the forest resources in a sustainable manner in the context of climate change. % of households having improved knowledge/decision making ability on climate resilient agricultural and other livelihood practices Adaptive strategies through project learning articulated, developed and communicated for replication and policy changes Number of case studies/ research studies published in peer reviewed journals Number of print/ audio/video media coverage generated | Lack of community sensitivity/awareness towards the importance of institutions/ forest conservation / gender issues/climate change impacts Lack of community awareness on adaptive agricultural, alternative and vocational livelihoods No adaptive strategies have been articulated, developed and communicated | Various activities implemnted as part of the project improved understanding on threats and climate change impacts on the landscape and enhanced involvement of stakeholders | Enhanced sensitivity and awareness levels in the community towards KPC, its functions and its conservational importance. Enhanced awareness on the importance of being a part of active and gender neutral CBOs, collective decision making, and adopting resilient livelihoods Enhanced awareness about KPC in the local, state and national scenario and importance of its conservation Availability of models and processes to adopt in similar landscapes for enhancing community resilience. Case studies/ research studies published in at least 4 platforms (magazines/ peer reviewed journals) Project covered at least 8 times by the Local and National Media
Output 4.1: Knowledge management plan covering all main KPC-dependent user groups to improve awareness levels and facilitate informed decision making to address threats to KPC | · Number of workshops conducted | · No strategy of knowledge management available | A knwoledge managemnet plan developed and 4 workshops undertaken | · A knowledge management plan created which is used as a strategy document for creating, developing, designing and communicating knowledge covering various stakeholders of KPC.
Output 4.2: Developed pool of products comprising research studies, learning/ case studies from the project, training modules and capacities for its dissemination through relevant tools. | · Number of audio visual content designed and developed for dissemination | · Lack of appropriate knowledge material/ platform available for dissemination to the community and other stakeholders | 2 audio visual contents developed | · At least 5 number of audio visual content developed (short movies/documentaries)
| · Number of Newsletters ; Pamphlets, stickers, modules and posters designed and developed for dissemination |  | 4 newsletters prepared | · At least 16 newsletters developed
| · Number of research studies commissioned |  | No achievement | · At least 3 modules for school children prepared
| · Number of success stories developed for dissemination |  | 4 posters prepared | · At least 12 posters and pamphlets developed
| · IT platform created for dissemination |  | 4 research studies completed | · At least 4 research studies are commissioned to be published in peer reviewed journals
|  |  | 36 success stories and case studies developed | · At least 20 success stories/case studies are developed and designed for dissemination
|  |  | No achievement | · 1 website developed
Output 4.3: Local and National Level Campaigns/Workshops for dissemination | · Number of village/school level dissemination workshops held for the community | · Lack of multi –stakeholder platforms and appropriate channels to share KPC information | 5 village level awareness workshops conducted | · At least 12 village level awareness workshops per village are conducted in 56 project villages
| · Number of inter –community awareness/cross learning workshops |  | 4 inter community workshops conducted | · At least 8 inter – community awareness and cross learning campaigns/ fairs/ workshops are conducted
| · Number of project level awareness workshops |  | 1 project level awareness workshops conducted | · At least 4 project level awareness level workshops are conducted
| · Number of national level awareness workshops |  | 1 national level workshop conducted | · At least 2 national level awareness workshops are conducted
| · Number of participants from homogenous groups / % of households participating |  | No achievement | · Atleast 6 media field exposure visits are conducted.
· Number / % of attendees in awareness workshops
· Number of website hits
· Number of media trips organized

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | There has been low participation of community members in labor oriented works. There are two reasons for this. Migration to near by cities and another areas for labor work and higher per day wage from MNERGA. This has negatively affected project implementation.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | COVID-19 induced restrictions and apprehensions of getting infected was a compelling factor for both the community aswell as implementing partner to undertake capacity building programmes. How ever with proper precauions e.g using sanitiser, wearing mask and maintaining social distance and with the consent of the participants , various training and workshops were conducted in last quarter of the reporting period. Exposure visti could not bo organised owing to travel restrictions. Implementing partner organised exposure visit in small groups locally.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Community participation has been promoted in project activities. Apart from the activities committed in the project, low cost water harvesting structures have been constructed across streams and gating mechanism introduced in stopdam to make the water available in summer season. this work has been done completely through community contribution.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Participation of women in decision making at community level has increased. More number of women particiaptes in SHGs and generate income for their families which has lifted their role in the family itself. Women drudgery activities are also taken place such as provision of Bio gas and solar light. Skill development is being undertaken - Wasundhara Sevikas/ paravets/ pashu Sakhis etc are trained under poultry, goatery, and piggery are being implemented.
Please complete the following section at mid-term and project completion
Lessons for Adaptation
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Farmers were ready to move towards adotping organic agriculture, micro irrigation and use of weather advisories. These measures has helped in reducing input cost and crop failures. Holistic approach towards integrated natural resource management along with climate resileint agriculture has increased resilience towards climate change.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | There is huge potential for replicating the project learnings in semi arid areas of the country and especially in areas adjoining national park/sancturies.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | NA
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | NA
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Involvement and participation of community is key to create ownership towards the project activities. Participation of women, landless and marginal households has also ensured that conservation measures are adopted in totality. The project has worked in close collabartion with gram panchayts which has ensured sustainability to the measure adopted. Post project, Gram Panchayats along with VDCs are expected to take forward climate adaptation measures through mainstream development interventions.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Integrated natural resource management adopted in this project has huge potential to get adopted across semi arid regions of India.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The project has successfully established the importance of community participation as well as interest of local government in addressing natural resource degradation issuses such as inadequate rain water harvesting, soil erosion, forest degradation and lack of management of livestock. The learning of the community is that if all these issues are simultaneously addressed, their vulnerability to climate change could be reduced considerably.
What measures are/have been put in place to ensure sustainability of the project/program results? | Community has been kept integral to all interventions. All decisions are driven by the committees wherein the most vulnerable are provided preference. Robustness and effectivness of the committees will ensure the sustainability. These members of the committee are also part of the PRIs - Panchayati Raj Institutions. The practices and governance of the committee is being percolated to the PRIs in the project area. This ensures that there is sustainability of the project activities.
What measures are being/could have been put in place to improve project/program results? | A district level community of functionaries of different depratments to ensure convergence and for sharing project outcomes could have ensured better support from district administration. This would have also ensured sustainability of project interventions post completion of project.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The project staff has been in close touch with different departments. Schemes, information and knowledge material of different organisations (Government, KVKs, Companies and NGOs) has been regularly shared with VDCs and SHGs. Weather based advisories were shared on fortnightly basis.
If learning objectives have been established, have they been met? Please describe. | Knowledge material is being prepared based on project learnings. These learnings will be widely disseminated through different platforms.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | No
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | The project has made consious effort to learn from existing good practices. Efforts have been made to adopt successful models of drip irrigations, vegetable cultivation, renewable energy and NRM. Staff and VDC members were trained as planned and whenever an opportunity to learn was observed.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | IND/NIE/Forests/2015/1
Implementing Entity | National Bank of Agriculture and Rural Development (NABARD)
Type of implementing entity | NIE
Country | INDIA
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 32292 | 15516 | 16776 | Total | 24112 | 11432 | 12680 | Total | 32292 | 15516 | 16776
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 48% | 30% | 63% | % of female beneficiaries | 50% | 50% | 50%
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 25% | 25% | 25% | % of Youth beneficiaries | 18% | 10% | 24% | % of Youth beneficiaries | 25% | 25% | 25%
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 |  | 1: Ineffective | Total | 32292 | Drought | 4: Effective | Total | 24112 | Drought | 3: Moderately effective | Total | 32292 | Drought | 4: Effective
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted | 50%
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 |  |  |  | 1 | Agriculture | Local | 3: Risk and vulnterability assessments completed or updated | 1 | Agriculture | Local | 2: Undertaking or updating of assessments in progress |  | Agriculture | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
[7 empty] | Water management | Local | 3: Risk and vulnterability assessments completed or updated |  | Water management | Local | 2: Undertaking or updating of assessments in progress |  | Water management | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Local | 2 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Multi-sector | 2: Low capacity | Total | 50 | Multi-sector | 4: High capacity | Total | 50 | Multi-sector | 3: Medium capacity | Total | 50 | Multi-sector | 3: Medium capacity
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted | 50%
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | NGO |  | 18 | 25% | NGO |  | 8 | 25% | NGO |  | 8
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | NGO | Regional | Multi-sector | 3: Medium capacity | NGO | Regional | Multi-sector | 4: High capacity | NGO | Regional | Multi-sector | 3: Medium capacity | NGO | Regional | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 70 |  | Multi-sector |  | 50 |  | Multi-sector |  | 50 |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 32292 | 50% | 4: Mostly aware |  | 32292 | 50% | 4: Mostly aware |  | 32292 | 50% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
[6 empty] | Multi-sector | Local | 4: Mostly responsive (Most defined elements) |  | Multi-sector | Local | 3: Moderately responsive (Some defined elements) |  | Multi-sector | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
[6 empty] | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
[6 empty] | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
[6 empty] | Food security | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved |  | Food security | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved |  | Food security | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved
[6 empty] | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
[6 empty] | Health | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved |  | Health | 1: Health and Social Infrastructure (developed/improved) | 2: Somewhat improved |  | Health | 1: Health and Social Infrastructure (developed/improved) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Multi-sector | water areas | 4: Effective |  | Multi-sector | water areas | 3: Moderately effective |  | Multi-sector | water areas | 3: Moderately effective |  | Multi-sector | water areas
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1 | ha protected | 1: Ineffective | Forests | 3000 | ha protected | 2: Partially effective | Forests | 3000 | ha protected | 3: Moderately effective | Forests | 3144 | ha protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 1 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 1500 | ha rehabilitated | 4: Effective | Cultivated land/Agricultural land | 1933 | ha rehabilitated | 3: Moderately effective | Cultivated land/Agricultural land | 1933 | ha rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 1: Ineffective | Catchment area/Watershed/Aquifer | 1800 | ha rehabilitated | 3: Moderately effective | Catchment area/Watershed/Aquifer | 1823 | ha rehabilitated | 3: Moderately effective | Catchment area/Watershed/Aquifer | 1823 | ha rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 5000 | 50% | 4: High improvement |  | 5000 | 50% | 3: Moderate improvement |  | 5000 | 50% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0 to 0.5% | Agricultural-related | 2000 | 50% | From 20% to 30% | Agricultural-related | 2000 | 50% | From 20% to 30% | Agricultural-related | 2000 | 50% | From 20% to 30% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0.5 to 1% | Forestry | 2000 | 50% | From 20% to 30% | Forestry | 2000 | 50% | From 20% to 30% | Forestry | 2000 | 50% | From 20% to 30% | Forestry
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0.5 to 1% | Livestock production | 2000 | 50% | From 20% to 30% | Livestock production | 2000 | 50% | From 20% to 30% | Livestock production | 2000 | 50% | From 20% to 30% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD)
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD)
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD)
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD)
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 |  |  |  |  | Water management | Regional |  | 1 | Water management | Regional |  | 1 | Water management | Regional
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.