## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | October 2018 - October 2019
| Project Title: | Reducing vulnerability and increasing resilience of coastal communities in the Saloum Islands (Dionewar)
| Project Summary: | This project has been developed to respond to the threats posed by the effects of climate change, namely coastal erosion, floods and reduced mangrove productivity. The objective pursued through the project implementation is to contribute to reducing the vulnerability of the populations of Dionewar to floods and to increasing their resilience capacity through the revival of the main productive sectors and the promotion local adaptation strategies. The project will have a major role to play in improving the living conditions of the coastal communities of Dionewar. It will help to obtain the following results: • improving the resilience of the fisheries, aquaculture and forestry sectors to climate change and other natural disasters; • reducing the vulnerability of populations through the fight against floods; • and strengthening local development through climate-sensitive planning, setting up local conventions and documenting lessons learned.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | SEN/NIE/Coastal/2015/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | CENTRE DE SUIVI ECOLOGIQUE (CSE) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | SENEGAL | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Village of Dionewar | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 05 July 2017
IE-AFB Agreement Signature Date: |  | 05 October 2017 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 23 October 2018 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 23 October 2020
Original Completion Date: |  | 23 April 2022
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Moussa NDIAYE, Coordinator of the Project Management Unit | Dominican Republic
| Email: | djiguibala@yahoo.fr | Ecuador
| Date: | 15 October 2018 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Dior Alioune SIDIBE - Department of Environment and Classified Establishments | Equatoral Guinea
| Email: | diorsidibe@yahoo.fr | Eritrea
| Date: | 02 October 2018 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Centre de Suivi Ecologique (CSE) | Fiji
| Email: | assize@cse.sn ; aissata.sall@cse.sn | Finland
| Date: | 05 October 2017 | France
| Executing Agency |  | Gambia
| Name: | Association for the Development of Dionewar-National Council for Functional Literacy (ADD-CONAF) | Georgia
| Email: | ousmandong@yahoo.fr | Germany
| Date: | 01 October 2018 | Ghana
| Executing Agency |  | Greece
| Name: | National Agency for Aquaculture (ANA) | Grenada
| Email: | magatte_ba@hotmail.com | Guatemala
| Date: | 27 September 2018 | Guinea
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 23 October 2018 |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 06 December 2017 (reporting is done according to the rate of receipt of funds, one dollar is equivalent to 550.5 xof) | 500000 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | Most of activiries planned currently is already take place. These are linked to the installation of oyster farms, the plantation of palm and coconut groves as wall as the restoration of mangrove. However, the activities related to the construction of dikes and the implementation of the automatic weather station accused some delay due the procurement procedures |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1. Alternative fish and oyster farming production system developed for 18 women associations, including the setup of 60 growing cages, 500 spat collectors and 2000 growing bags | 41619.2861
| 1.2. At least 6 ha of trees planted (enrichment planting primarily with coconut and oil palms) and 5 ha of mangrove rehabilitated in Dionewar to revitalize the main productive sectors | 4337.1499
| 1.3. At least 18 economic interest women’s groups and natural resource management committees trained to improve their technical performance | 7528.4305
| 1.4. Management plans for fish and oyster farms management developed | 0
| 2.1. Protect, rehabilitate and extend the three (03) dikes against flooding over 1.2 km area | 279.2371
| 2.2. Develop a maintenance plan, involving key stakeholders | 0
| 3.1. The Communal Development Plan (PCD) is reviewed in order to integrate adaptation to climate changes options & cost benefits | 0
| 3.2. Rules governing the exploitation of timber and non-timber forest products and the biological rest updated and formalized through a Local Convention | 0
| 3.3. Project’s lessons learned are documented and shared | 0
| 3.4. One (01) meteorological station is installed in Dionewar | 800.812
| M & E specialist salary | 4541.5913
| Local coordinator salary | 5449.1117
| Admin and fin assistant salary | 2724.5559
| Allowances of CADL technical staff | 847.6839
| Refection former rural community office | 0
| Office furniture | 0
| Computing equipment | 3004.7902
| Maintenance | 0
| Office supplies | 0
| Commodities | 0
Transportation
| Communication | 0
| Inception workshop | 8628.4251
| Steering committee meeting | 908.5177
| TOTAL | 80669.5913 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1. Alternative fish and oyster farming production system developed for 18 women associations, including the setup of 60 growing cages, 500 spat collectors and 2000 growing bags | 48507.4659 | October 2020 (Q4/Y2)
| 1.2. At least 6 ha of trees planted (enrichment planting primarily with coconut and oil palms) and 5 ha of mangrove rehabilitated in Dionewar to revitalize the main productive sectors | 77957.0027 | October 2020 (Q4/Y2)
| 1.3. At least 18 economic interest women’s groups and natural resource management committees trained to improve their technical performance | 26028.8828 | October 2020 (Q4/Y2)
| 1.4. Management plans for fish and oyster farms management developed | 26926.4305 | December 2020 (Q1/Y3)
| 2.1. Protect, rehabilitate and extend the three (03) dikes against flooding over 1.2 km area | 222772.3324 | June 2021 (Q2/Y3)
| 2.2. Develop a maintenance plan, involving key stakeholders | 0 | 0
| 3.1. The Communal Development Plan (PCD) is reviewed in order to integrate adaptation to climate changes options & cost benefits | 12765.1226 | June 2020 (Q2/Y2)
| 3.2. Rules governing the exploitation of timber and non-timber forest products and the biological rest updated and formalized through a Local Convention | 20055.2044 | October 2020 (Q4/Y2)
| 3.3. Project’s lessons learned are documented and shared | 16455.0409 | October 2020 (Q4/Y2)
| 3.4. One (01) meteorological station is installed in Dionewar | 9374.3869 | October 2020 (Q4/Y2)
| M & E specialist salary | 5983.6512 | October 2020 (Q4/Y2)
| Local coordinator salary | 7180.3815 | October 2020 (Q4/Y2)
| Admin and fin assistant salary | 3590.1907 | October 2020 (Q4/Y2)
| Allowances of CADL technical staff | 4786.921 | October 2020 (Q4/Y2)
| Office furniture | 598.3651 | October 2020 (Q4/Y2)
| Maintenance | 199.455 | October 2020 (Q4/Y2)
| Commodities | 1196.7302 | October 2020 (Q4/Y2)
| Transportation | 997.2752 | October 2020 (Q4/Y2)
| Communication | 698.0926 | October 2020 (Q4/Y2)
| Mid-Evaluation | 2991.8256 | June 2020 (Q2/Y2)
| Steering committee meeting | 1994.5504 | October 2020 (Q4/Y2)
| TOTAL | 491059.3079 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Institutional and political The local elected representatives and the representatives of the State who have already been trained by the project have changed after the local elections in 2017 | Inexistent | The project began after the local elections so it does not have any impact on the project implementation.
Climatic Extreme weather events affect the realizations of the project | Moderate impact | The rainy season of summer 2019 led to the destruction of some plants that have been reforested. Right after that the coordination unit along with the forestry department started the protection of the plants to avoid destruction.
Financial The implementation of alternative options of production (fish farming, oyster farming, etc.) will generate important financial resources, which can be sources of conflict between stakeholders or subject to embezzlement. This might compromise the financial sustainability of the project achievements. | No conflicts have been raised. | The selection of beneficiaries for the alternative options production have not started yet. But the selection will be done with all the local authorities and the members of local economic groups to make sure that all elements have been taken into account.
Social The arrival of a foreign workforce and the establishment of protective infrastructure and income-generating activities in a single village in the municipality (which counts three villages) can be a source of conflicts and tension between the villagers. | The risk has not been raised. | Local workforce have been used for the construction of the oyster and fish farms. The same process will be used for the rehabilitation of the dikes.
Environmental and social harms | The risk has not been raised.
Challenging measures aiming at a sustainable use of natural resources | The risk has not been raised.
Child labor and work related accidents | No case has been reported. | Children have not been included in the construction of the oyster and fish farms. Only adults have been recruted by the companies in charge of the works.
The use of shell mounds | No case has been reported.
Conflicts during the selection of the members of committees or the beneficiaries of trainings | No case has been reported. | The choice of the members of the committees have been made with the existing economic groups and local consensus with all local stakeholders. The women were the main beneficiaries of the fish and oyster activities so they are composing the management committee for those activities at 80%. A local surveillance committee has also been put in place with 50% of women.
Women exposed to hazards in case of capsizing which can lead to loss of lives and goods | No case has been reported. | Lifejackets have been provided to the women beneficiaries of the fish farms and oyster farms.
Non integration of the women in decision making bodies (infrastructure, forest products management committees, steering committee for the local convention) | Ongoing | Women represent 50% of the members of the local surveillance committee and 80% of the fish and oyster farms management committees. The committees for the infrastructures and the local convention have not been set yet since the activities have not been started yet.
Accidents | No case has been reported.
Bad working conditions | No case has been reported. | Weekly surveillance and monitoring field missions have been conducted during the implementation of the fish and oyster farms. The same work will be done during the rehabilitation of the dikes.
Child labor | No case has been reported.
Involuntary resettlement of economic activities (temporary stop of shellfish resources exploitation) due to biological rest | Nothing to mention. | The convention which initiate the biological rest has not been set yet. The coordination unit is in discussion of local NGOs to undertake the beekeeping activity once the biological rest will be instaured.
Mangrove and spawning areas can be affected by the changes in water flow direction and the accumulation of sand | The risk has not been raised.
Introduction of exotic species | No case has been reported. | ANA only used local species for the oyster and fish farms.
Pollution due to a non-appropriate use of fish food | No case has been reported. | Beneficiaries who will feed the fishes have been trained on how to feed them and how to use the fish food to avoid this risk.
Use of mangrove wood and shell mounds | For the use of mangrove wood, some cases have been reported. For the use of shell mounds no case have been reported with the project. | The marine protected area (AMP) and the Forestry Department provide cutting permit before any wood cut. For the shell mounds, sensitization and awareness raising activities during village Assembly.
Works during spawning and growing out periods | No case has been reported.
Accidental spills | No case has been reported. The works have not start yet.
Increase of the organic matter (overproduction of organic waste due to uncontrolled fish density) | No case has been reported.
Waste generation | No case has been reported.
Outbreak of sexually transmitted infections, including HIV/AIDS | No case has been reported.
Waterborne diseases | No case has been reported.
Ocular or respiratory diseases | No case has been reported.
Accidents | No case has been reported.
Falls or drowning | No case has been reported. | Lifejackets have been provided to the beneficiaries of the oyster and fish farms.
Fortuitous discovery of sites or objects of cultural, sacred or archaeological importance | No case has been reported.
Pollution of soil and lands | No case has been reported. | The activities that could have lead to soil or land pollution have not started yet.
Modification of soil structure | No case has been reported.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | - Environmental and social harms - Challenging measures aiming at a sustainable use of natural resources - Child labor and work related accidents - Use of shell mounds | -Undertake an ESIA and ensure a sound implementation of the associated ESMP - CSE and the PMU will ensure that relevant local authorities (sub-prefect, municipality) be informed in written prior to the launch of any activity - CSE and the PMU will ensure that the company will provide all required protection equipment and will conduct awareness campaign about the risks by including these measures in the technical specifications. - CSE and PMU will ensure that children will not be involved in works on the project sites and this measure will be included in the convention with the executing entities and the service providers - In close collaboration with the DAMCP, CSE and the project’s management unit will ensure that the firm in charge of the works complies with the protection status of shell mounds. This will be part of the technical specifications and a contract clause. The feasibility study will be given to the firm in charge of the works and any failing to observe this requirement may lead to the termination of contracts. - Unexpected site visits will be organized with the view to check compliance with the requirements of the feasibility study related to the type of materials to be used - Capacity building activities will include a module on the cultural heritage of the Dionewar Island | - Quality of the equipment - Percentage of minor included in the works - Number of visit | - Zero equipment provided - Zero minor included in the works - Zero visits | - Protection equipment have been provided for the aquaculture activities - Awareness raising campaign are implemented for child labor, the use of shell mounds and the risks related to the works. - Field visits are carried by the PMU on a week basis for the implementation of the oyster and fish farms. Those visits will continue during the works for the rehabilitation of the dikes
2 - Access and equity |  |  | - Conflicts during the selection of the members of committees or the beneficiaries of trainings | - Setup a local committee in charge to oversee the distribution of the project’s assets and the access to the project’s benefits
3 – Marginalized and vulnerable Groups |  |  | - Women exposed to hazards in case of capsizing which can lead to loss of lives and goods | - Provide women groupings with life jackets - Raise awareness on such risks (by including in the training sessions first aid, behavior during distress at sea). | - Quality of the equipment | - Zero equipment initially provided | - Life jackets have been povided to those who are going on the oyster and fish farms mainly women
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | - Non integration of the women in the decision making bodies (infrastructure, forest products management committees, steering committee for the local convention) | - Breakdown the M&E indicators based on gender. - Executing agencies will used gender based approaches during consultative processes | - Number of Economic Interest Group trained and involved in the management committees | - No management committees have been implemented yet
6 – Core labour rights |  |  | - Accidents - Bad working conditions - Child labor | - Provide protection equipment to avoid accident - Conduct awareness campaign for the workers about the risks of accidents - Enforce relevant labor regulations - Prohibit any kind of child labor | - Quality of the equipment - Percentage of minor included in the works - Number of visit | - Zero equipment initially provided | - Life jackets have been provided for those who were doing the works on the oyster and fish farms - Field visits have been carried on | - Accidents - Bad working conditions - Child labor | - The workers on the rehabilitation works will be provided with security equipment - The awareness campaigns will start when the works on rehabilitation of the dikes will start
7 – Indigenous peoples
8 – Involuntary resettlement |  |  | -Involuntary resettlement of economic activities (temporary stop of shellfish resources exploitation) due to biological rest | - Propose alternative economic alternative (beekeeping is proposed) | - Number of monitoring field mission | - Zero alternative activity was proposed or carried on initially | - Discussions are ongoing with some associations to start the beekeeping activities once the local convention is implemented | -Involuntary resettlement of economic activities (temporary stop of shellfish resources exploitation) due to biological rest | - The beneficiaries of the beekeeping activity will be selected - The beekeeping activity will be installed with the local associations which have experience on it
9 – Protection of natural habitats |  |  | - Mangrove and spawning areas can be affected by the changes in water flow direction and the accumulation of sand | - Identify during implementation the spawning areas that might be affected - Identify the direction of water flow - Monitor the sedimentation at the spawning areas - Use mechanical action to reduce the accumulation of sand - Establish a committee comprising the project management, the DAMCP, the Forestry Service, local CSOs (CONAF, ADD, women grouping leaders), the local representative of the Directorate of Environment, the sub-Prefect and the Mayor. This committee will be tasked to monitor, identify and implement the above listed actions. | - Field visits to monitor the sedimentation at spawning areas - Existence of the committee | - The sedimentation is not monitored - No committee has been created | - The committee has been created to monitor all the activities of the project including the monitoring of sedimentation at spawning areas | - Mangrove and spawning areas can be affected by the changes in water flow direction and the accumulation of sand | - Conduct field visits when the works for the rehabilitation of the dikes will start
10 – Conservation of biological diversity |  |  | - Introduction of exotic species - Pollution due to a non-appropriate use of fish food - Use of mangrove wood and shell mounds - Works during spawning and growing out periods | - Use only local species - Organize the works out of the spawning and growing out periods - Train the populations on how to feed fishes without generating pollutions - Prohibit the use of mangrove woods and shell mounds | - Field visits to ensure that only local species have been introduced and how the fishes are fed - Awareness raising on the use of mangrove woods and shell mounds | - No fish farms have been implemented - The population was using the mangrove woods and the shell mounds for construction | - Field visits are conducted on a week basis to make sure that only local species will be introduced - Awareness raising campaigns are regularly conducted
11 – Climate change
12 – Pollution prevention and resource efficiency |  |  | - Accidental spills - Increase of the organic matter (overproduction of organic waste due to uncontrolled fish density) - Waste generation | - Develop a waterproof space - Maintain regularly the concrete mixer - Avoid overloading canoes during transport of hydrocarbons - Ensure containers are airtight - Control high fish densities - Monitor water quality (regular chemical analysis) (for the fish cages) - In case of overcrowding make transfers to other cages - Develop and implement a waste management plan | - Number of management plan realized - Number of analysis report - Fish density in the spawning areas | - No management plans have been implemented for the existing dikes - No analysis have been carried out | - The fishes have just been introduced in the cages | - Accidental spills - Increase of the organic matter (overproduction of organic waste due to uncontrolled fish density) - Waste generation | - Develop a waterproof space - Maintain regularly the concrete mixer - Avoid overloading canoes during transport of hydrocarbons - Ensure containers are airtight - Control high fish densities - Monitor water quality (regular chemical analysis) (for the fish cages) - In case of overcrowding make transfers to other cages - Develop and implement a waste management plan
13 – Public health |  |  | - Outbreak of sexually transmitted infections, including HIV/AIDS - Accidents, - Waterborne diseases - Falls or drowning - Ocular or respiratory diseases | - Sensitization of workers and populations (through the environmental and social management plan) - Provide protective equipment (life jackets, lifebelts) for the operators of the aquaculture sites - Provide protective equipment to the workers (gloves, masks, glasses, helmets) (for the rehabilitation of the dikes) - Spray regularly the sites (dikes and borrowing sites) to avoid the dust takeoffs - Completely cover the top of the truck’s body and the load of laterite | - Quality of the equipment
14 – Physical and cultural heritage |  |  | - Fortuitous discovery of sites or objects of cultural, sacred or archaeological importance - The use of shell mounds | - Protect and secure these sites - Immediately cease activity on the sites concerned -Prohibit the use of shell mounds | - Awareness raising on the use of mangrove woods and shell mounds | - The population was using the mangrove woods and the shell mounds for construction | - Awareness raising campaigns are regularly conducted | - Fortuitous discovery of sites or objects of cultural, sacred or archaeological importance - The use of shell mounds | - Continue the awareness raising campaigns regularly
15 – Lands and soil conservation |  |  | - Pollution of soil and lands - Modification of soil structure | - Sensitize operators to rational use of fertilizers - Ensure the supervision of the activity by the water and forest service - Promote the use of natural fertilizers - Ensure soil leveling at the end of the work | - Awareness raising on the use of fertilizers and workshop to promote the use of natural fertilizers | - The population was using fertilizers without taking any precautions | - The awareness campaigns have not started yet - The works have not start yet to level the soil structure | - Pollution of soil and lands - Modification of soil structure | - Awareness raising on the use of fertilizers and workshop to promote the use of natural fertilizers
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | NO
Have unanticipated ESP risks been identified during the reporting period? |  | NO
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | NO
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | ESP Safeguards measures have been included in the agreements signed between the Executing entities and the implementing entity. In addition to that, local committees have been set up in order to monitor the effectiveness of the measures on site.
Have the implementation arrangements been effective during the reporting period? |  | YES
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures?
Have the implementation arrangements at the EEs been effective during the reporting period?
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | NO
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | YES
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Inclusion of women in the local climate issues and implementation of adequate measures | Outcome | Number of persons (including decision makers) aware of local climate issues and adequate measures to be implemented | 0 | 100 persons (50 at mid-term) (half of them women and half of them men) | Satisfactory
Training of women in order to improve their performance | Output | Number of women’s economic groups trained | 0 | 18 (10 at mid-term) | Good
Training of women in order to improve their performance | Output | Number of members of management committee and of community based organizations trained | 0 | 30 women | Satisfactory
Women and girls are aware of local climate change issues and the type of measures to be implemented | Output | Number of persons (including decision makers) informed of local climate change issues and adequate measures to be implemented | 0 | 410 persons (270 adult women, 120 adult men, 20 students (10 girls and 10 boys) | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
Women exposed to hazards in case of capsizing which can lead to loss of lives and goods |  | Good
Non integration of the women in the decision making bodies (infrastructure, forest products management committees, steering committee for the local convention) |  | Satisfactory
Conflicts during the selection of the members of committees or the beneficiaries of trainings |  | Good
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP
Have the implementation arrangements at the IE been effective during the reporting period? |  | YES
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5]
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | YES
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | NO
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Outcome 1: The resilience of the main productive sectors of Dionewar Island is enhanced and sustainable livelihoods of populations are improved |  | Outcome 5 | Natural resources assets are created |  | For the first year of project implementation, 0.98 ha of coconut trees, 1.4 ha of palm trees and 2.102 ha of mangrove have been planted. | HS
|  |  | Outcome 6 | Different livelihoods and sources of income are proposed to the vulnerable groups. Especially fish and oyster farming for women groupings |  | 20 fish cages, 200 spat collectors and 1,500 growing bags have been constructed and implemented for the fish farms and the oyster farms. | MS
| Outcome 2: The vulnerability of populations in Dionewar to hazards is reduced with the construction or rehabilitation of protection structures |  | Outcome 4 | Infrastructures assets such as protection dikes are rehabilitated in order to protect the village and the population from floodings |  | The procurement stage is still on going | U
| Outcome 3: Climate change is integrated in Communal Development Planning, natural resources are used in a more sustainable way and lessons learned are documented and shared |  | Outcome 3 | Populations and decision makers are aware of the climate hazards and are adopting climate risk reduction processes |  | The awareness raising campaigns are conduted regularly | MS
|  |  | Outcome 7 | Resilience measures are included in the local policies |  | It has not started yet, it will be conducted in the second year of implementation. But the local government representatives are regularly sensitize on the importance of included resilience measures into local planning. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Aïssata Boubou SALL SYLLA
| Email: | aissata.sall@cse.sn
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator:
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective | Number of risk-exposed coastal households benefiting of adaptation measures | 451 households threatened by flooding and coastal erosion | 0 | At least 270 households are protected
| Are (ha) of mangrove and terrestrial ecosystems restored | 0 | 2.102 ha of mangrove restored 2.38 ha of coconut trees and palm trees planted | 5 ha of mangrove restored 6 ha of terrestrial ecosystems (palm trees and coconut trees) planted
| Percentage of increase of income of population involved in alternative income generating activities (breakdown by gender) | 0 | 0 | Increase of 25% at least
Outcomes | Number of dikes rehabilitated and built to protect households and socioeconomic infrastructures against flooding and coastal erosion | 0 | 0 | 3 dikes are rehabilited
| Number of persons (including decision makers) aware of local climate issues and adequate measures to be implemented | 0 | 0 | 100 persons (50 at mid-term) (half of them women and half of them men)
| Number of local development tools that integrate adaptation measures | 0 | 0 | 2 local planning documents are updated integrating adaptation measures
Outputs | Number and type of adaptive production systems | 0 | 2 | 3
| Number of fish cages | 0 | 20 | 60
| Number of spat collector | 0 | 500 | 500
| Number of growout bags | 0 | 1500 | 2000
| Number of analysis report for the monitoring of the physicochemical and bacteriological parameters of the oyster farm’s site | 0 | 0 | 12
| Number of analysis report for the monitoring of the physicochemical and bacteriological parameters of the fish farm’s site | 0 | 0 | 12
| Area (ha) of trees planted | 0 | 2.38 ha of coconut trees and palm trees planted | 6 ha of palm trees and coconut trees) planted
| Area (ha) of mangrove rehabilitated | 0 | 2.102 ha of mangrove restored | 5 ha of mangrove restored
| Number of women’s economic groups trained | 0 | 18 | 18
| Number of members of management committee and of community based organizations trained | 0 | 0 | 30
| Number of management plans | 0 | 0 | 2
| Number of new dikes restored or extended | 0 | 0 | 3
| Number of dikes’ maintenance plan developed | 0 | 0 | 1
| Number of planning documents reviewed that integrated adaptation options | 0 | 0 | 2
| Number of local convention on sustainable management of natural resources adopted | 0 | 0 | 1
| Number of field missions for monitoring the implementation of the alternative activities (bee-Keeping, etc.) | 0 | 0 | 6
| Number of production of lessons learned | 0 | 0
| Number of persons (including decision makers) informed of local climate change issues and adequate measures to be implemented | 0 | 100 | 410
| Number of meteorological station implemented | 0 | 0 | 1

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The procedure for recruiting the company responsible for carrying out the dike rehabilitation work took a long time. The executing agency which was to carry out the recruitment did not have all the technical skills to prepare the tender documents. Therefore, support from the CSE and a specialist in the field was needed to facilitate the preparation of the tender documents. - A local project monitoring committee was established to ensure close monitoring of project activities. This committee is composed of the Mayor, the local technical services and the project executing agencies. The presence of this committee makes it possible to identify delays in the implementation of the project and to define solutions to overcome them.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Two main delays were noted during the first year of project implementation. - The first noted delay is related to the establishment of the national steering committee. Indeed, given the institutional arrangements put in place at national level, a steering committee must be set up by ministerial order. This committee has the task of validating the PTBAs, the start-up and progress reports as well as the annual reports and the project closure report. Within the framework of this project, the creation of the steering committee took more than 5 months to be effective. As a result, the progress report as well as the PTBA for the first year could not be validated earlier. - The second delay noted is related to the procurement process mainly concerning the recruitment contract of the company in charge of the dyke rehabilitation works.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No particular changes were noted in the outputs. However, a few small changes were made, notably in relation to the acquisition of a fence for the nursery. In view of the fact that animals wander in the reforestation area, it was agreed to also fence in the coconut and oil palm plants.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | The implementation of the ESMP is followed regularly by each executing agency. The environmental and social safeguard measures are implemented for each related activity.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender was taken into account during the project formulation phase. Indeed, the results framework includes gender-specific indicators. Since the village of Dionewar is a society in which vulnerable groups including women are well included in the activities, it was not difficult to include gender in the project activities. As women are the main beneficiaries of the fisheries activities, they represented 86% of the people trained in aquaculture techniques. These trained persons will be the people who will operate the fish and oyster farms. It was therefore necessary to involve these people as soon as possible in order to ensure a good appropriation of the project activities and especially a sustainability of the project achievements. The main indicators that highlight the role of women in the management of adaptation to climate change are the following: - Involvement in training on aquaculture techniques and natural resource management - Involvement in natural resource management committees - Improving knowledge of climate change issues Some indicators relate to the reporting period of year 2.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | SEN/NIE/Coastal/2015/1
Implementing Entity | Centre de Suivi Ecologique
Type of implementing entity | NIE
Country | Senegal
Region | Africa
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 5395 | 3480 | 1915 | Total | 5395 | 3480 | 1915 | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Other
Output 3.1: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 2970 | 50% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 0 | 20% to 39% | 1: Aware of neither |  | 4 | 40% to 60% | 5: Fully aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | Training manuals | Local |  |  | Training manuals | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Other | Local | 4: Mostly responsive (Most defined elements) |  | Other | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Disaster risk reduction | 3 | Community |  | Disaster risk reduction
|  | 0 | Community |  | Other | 2 | Community |  | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 4: Effective |  | Other | biological assets | 4: Effective |  | Other | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha rehabilitated | 1: Ineffective | Forests | 6 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves |  | ha rehabilitated | 2: Partially effective | Mangroves | 5 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 270 |  | 4: High improvement |  | 270 |  | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 1 | Adaptation strategies | Other | Strengthening infrastructure
|  | 1 | Adaptation strategies | Other | Mangrove reforestation
|  | 1 | Adaptation strategies | Other | Sustainable forest management
|  | 1 | Adaptation strategies | Other | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 415 | Aquaculture |  |  | 415 | Aquaculture
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 415 | Fishing |  |  | 415 | Fishing
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 415 | Forestry |  |  | 415 | Forestry
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 4: Most |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | Local | Other policy | 1 | Multi-sector | Local
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 1 | 4: Enforced (Most elements implemented) |  | 4: Effective | 1 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste