## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | October 2021 - October 2022
| Project Title: | Reducing vulnerability and increasing resilience of coastal communities in the Saloum Islands (Dionewar)
| Project Summary: | This project has been developed to respond to the threats posed by the effects of climate change, namely coastal erosion, floods and reduced mangrove productivity. The objective pursued through the project implementation is to contribute to reducing the vulnerability of the populations of Dionewar to floods and to increasing their resilience capacity through the revival of the main productive sectors and the promotion local adaptation strategies. The project will have a major role to play in improving the living conditions of the coastal communities of Dionewar. It will help to obtain the following results: • improving the resilience of the fisheries, aquaculture and forestry sectors to climate change and other natural disasters; • reducing the vulnerability of populations through the fight against floods; • and strengthening local development through climate-sensitive planning, setting up local conventions and documenting lessons learned.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | SEN/NIE/Coastal/2015/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | CENTRE DE SUIVI ECOLOGIQUE (CSE) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | SENEGAL | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Village of Dionewar | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 05 July 2017
IE-AFB Agreement Signature Date: |  | 05 October 2017 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 23 October 2018 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 23 October 2020
23 April 2021
Original Completion Date:
Revised Completion Date after approval of |  | 30 April 2023 (1,5 year extension)
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Moussa NDIAYE, Coordinator of the Project Management Unit | Dominican Republic
| Email: | djiguibala@yahoo.fr | Ecuador
| Date: | 15 October 2018 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Mame Faty Niang SEYDI | Equatoral Guinea
| Email: | mamefatyniang@yahoo.fr | Eritrea
| Date: | 9 June 2022 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Centre de Suivi Ecologique (CSE) | Fiji
| Email: | mbow@cse.sn aissata.sall@cse.sn | Finland
| Date: | 05 October 2017 | France
| Executing Agency |  | Greece
| Name: | Association for the Development of Dionewar-National Council for Functional Literacy (ADD-CONAF) | Grenada
| Email: | ousmandong@yahoo.fr | Guatemala
| Date: | 01 October 2018 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | National Agency for Aquaculture (ANA) | Guyana
| Email: | sentening@gmail.com | Haiti
| Date: | 27 September 2018 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to October 2019 |  |  |  | Financial information PPR 2: cumulative from project start to October 2020 |  |  |  | Financial information PPR 3: cumulative from project start to October 2021 |  |  |  | Financial information PPR 4: cumulative from project start to October 2022 |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 06 December 2017 (reporting is done according to the rate of receipt of funds, one dollar is equivalent to 550.5 XOF) | 500000 |  |  | Estimated cumulative total disbursement as of 06 December 2017 (reporting is done according to the rate of receipt of funds, one dollar is equivalent to 550.5 XOF) | 500000 |  |  | Estimated cumulative total disbursement as of 12 April 2021 (recording is done according to the rate of receipt of funds, one dollar is equivalent to 550.5 XOF) | 939048 |  |  | Estimated cumulative total disbursement as of 09 September 2022 (recording is done according to the first rate of receipt of funds, one dollar is equivalent to 550.5 XOF) | 1148760 |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | Most of activiries planned currently taken in place. These are linked to the installation of oyster and fish farms, the plantation of palm and coconut trees as well as the restoration of mangrove. However, the activities related to the construction of diks and the implementation of the meteorologic station had some delays due the procurement procedures |  |  | Add any comments on AF Grant Funds. (word limit=200) | Only one disbursement has been received from the AF since December 2017. To date, it is important for CSE to request the other disbursements to ensure an efficient execution of project activities. Most of activities planned during the period were executed. These are linked to the installation of fish farms, the plantation of palm and coconut trees as well as the restoration of mangrove, and the capacity building activities. However, the activities related to the construction of dikes counted some delays due the coronavirus pandemic. |  |  | Add any comments on AF Grant Funds. (word limit=200) | The second disbursement for an amount of 398,313$ have been received in April 2021. Most of the activities planned during the period were executed. These are linked to the plantation of palm and coconut trees as well as the restoration of mangrove, the capacity building activities, the fact of putting the fishes into the enclosures and the fish and oyster collection. The rehabilitation of the dikes has started and the companies and the cabinet of control have received their first disbursement.We wish to receive the reste of disbursement to honor our commiments with the consultants. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1. Alternative fish and oyster farming production system developed for 18 women associations, including the setup of 60 growing cages, 500 spat collectors and 2000 growing bags | 41619.2861 |  |  | 1.1. Alternative fish and oyster farming production system developed for 18 women associations, including the setup of 60 growing cages, 500 spat collectors and 2000 growing bags | 40976 |  |  | 1.1. Alternative fish and oyster farming production system developed for 18 women associations, including the setup of 60 growing cages, 500 spat collectors and 2000 growing bags | 37306.3815 |  |  | 1.1. Alternative fish and oyster farming production system developed for 18 women associations, including the setup of 60 growing cages, 500 spat collectors and 2000 growing bags | 32047.426
| 1.2. At least 6 ha of trees planted (enrichment planting primarily with coconut and oil palms) and 5 ha of mangrove rehabilitated in Dionewar to revitalize the main productive sectors | 4337.1499 |  |  | 1.2. At least 6 ha of trees planted (enrichment planting primarily with coconut and oil palms) and 5 ha of mangrove rehabilitated in Dionewar to revitalize the main productive sectors | 31313 |  |  | 1.2. At least 6 ha of trees planted (enrichment planting primarily with coconut and oil palms) and 5 ha of mangrove rehabilitated in Dionewar to revitalize the main productive sectors | 14662.1253 |  |  | 1.2. At least 6 ha of trees planted (enrichment planting primarily with coconut and oil palms) and 5 ha of mangrove rehabilitated in Dionewar to revitalize the main productive sectors | 25289.752
| 1.3. At least 18 economic interest women’s groups and natural resource management committees trained to improve their technical performance | 7528.4305 |  |  | 1.3. At least 18 economic interest women’s groups and natural resource management committees trained to improve their technical performance | 11254 |  |  | 1.3. At least 18 economic interest women’s groups and natural resource management committees trained to improve their technical performance | 2537.693 |  |  | 1.3. At least 18 economic interest women’s groups and natural resource management committees trained to improve their technical performance | 16549.5786
| 1.4. Management plans for fish and oyster farms management developed | 0 |  |  | 1.4. Management plans for fish and oyster farms management developed | 0 |  |  | 1.4. Management plans for fish and oyster farms management developed | 22497.7293 |  |  | 1.4. Management plans for fish and oyster farms management developed | 0
| 2.1. Protect, rehabilitate and extend the three (03) dikes against flooding over 1.2 km area | 279.2371 |  |  | 2.1. Protect, rehabilitate and extend the three (03) dikes against flooding over 1.2 km area | 452 |  |  | 2.1. Protect, rehabilitate and extend the three (03) dikes against flooding over 1.2 km area | 1730.3506 |  |  | 2.1. Protect, rehabilitate and extend the three (03) dikes against flooding over 1.2 km area | 312180.6899
| 2.2. Develop a maintenance plan, involving key stakeholders | 0 |  |  | 2.2. Develop a maintenance plan, involving key stakeholders | 0 |  |  | 2.2. Develop a maintenance plan, involving key stakeholders | 0 |  |  | 2.2. Develop a maintenance plan, involving key stakeholders | 0
| 3.1. The Communal Development Plan (PCD) is reviewed in order to integrate adaptation to climate changes options & cost benefits | 0 |  |  | 3.1. The Communal Development Plan (PCD) is reviewed in order to integrate adaptation to climate changes options & cost benefits | 0 |  |  | 3.1. The Communal Development Plan (PCD) is reviewed in order to integrate adaptation to climate changes options & cost benefits | 6874.2053 |  |  | 3.1. The Communal Development Plan (PCD) is reviewed in order to integrate adaptation to climate changes options & cost benefits | 0
| 3.2. Rules governing the exploitation of timber and non-timber forest products and the biological rest updated and formalized through a Local Convention | 0 |  |  | 3.2. Rules governing the exploitation of timber and non-timber forest products and the biological rest updated and formalized through a Local Convention | 0 |  |  | 3.2. Rules governing the exploitation of timber and non-timber forest products and the biological rest updated and formalized through a Local Convention | 13809.446 |  |  | 3.2. Rules governing the exploitation of timber and non-timber forest products and the biological rest updated and formalized through a Local Convention | 190.9173
[5 empty] | 3.3. Project’s lessons learned are documented and shared | 0 |  |  | 3.3. Project’s lessons learned are documented and shared |  |  |  | 3.3. Project’s lessons learned are documented and shared | 2234.3324
[5 empty] | 3.4. One (01) meteorological station is installed in Dionewar | 22050 |  |  | 3.4. One (01) meteorological station is installed in Dionewar | 666.6303 |  |  | 3.4. One (01) meteorological station is installed in Dionewar | 2064.7284
[5 empty] | M & E specialist salary | 5450 |  |  | M & E specialist salary | 5449.5913 |  |  | M & E specialist salary | 5033.3025
[5 empty] | Local coordinator salary | 6540 |  |  | Local coordinator salary | 6539.5095 |  |  | Local coordinator salary | 6730.2452
[5 empty] | Admin and fin assistant salary | 3270 |  |  | Admin and fin assistant salary | 3269.7548 |  |  | Admin and fin assistant salary | 3365.1226
[5 empty] | Allowances of CADL technical staff | 3995.1499 |  |  | Allowances of CADL technical staff | 3633.0463 |  |  | Allowances of CADL technical staff | 3027.5677
| 3.3. Project’s lessons learned are documented and shared | 0 |  |  | Refection former rural community office | 3917.802 |  |  | Refection former rural community office | 0 |  |  | Refection former rural community office
| 3.4. One (01) meteorological station is installed in Dionewar | 800.812 |  |  | Office furniture | 1266 |  |  | Office furniture | 564.941 |  |  | Office furniture
| M & E specialist salary | 4541.5913 |  |  | Computing equipment | 0 |  |  | Computing equipment | 0 |  |  | Computing equipment
| Local coordinator salary | 5449.1117 |  |  | Maintenance | 0 |  |  | Maintenance |  |  |  | Maintenance
| Admin and fin assistant salary | 2724.5559 |  |  | Office supplies | 504 |  |  | Office supplies | 494.7775 |  |  | Office supplies
| Allowances of CADL technical staff | 847.6839 |  |  | Commodities | 0 |  |  | Commodities |  |  |  | Commodities | 569.4423
| Refection former rural community office | 0 |  |  | Transportation | 145 |  |  | Transportation | 315.6222 |  |  | Transportation | 35.8629
| Office furniture | 0 |  |  | Communication | 397 |  |  | Communication |  |  |  | Communication | 349.6994
| Computing equipment | 3004.7902 |  |  | Inception workshop | 0 |  |  | Inception workshop | 0 |  |  | Inception workshop | 8652.2979
| Maintenance | 0 |  |  | Steering committee meeting | 0 |  |  | Steering committee meeting | 0 |  |  | Steering committee meeting | 2652.1344
[9 empty] | Fees | 40735 |  |  | Fees | 33200
| TOTAL | 71132.6485 |  |  | TOTAL | 131529.9519 |  |  | TOTAL | 161086.8038 |  |  | TOTAL | 420973.0995 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1. Alternative fish and oyster farming production system developed for 18 women associations, including the setup of 60 growing cages, 500 spat collectors and 2000 growing bags | 48507.4659 | October 2020 (Q4/Y2) |  | 1.1. Alternative fish and oyster farming production system developed for 18 women associations, including the setup of 60 growing cages, 500 spat collectors and 2000 growing bags | 61525.8856 | October 2021 (Q4/Y3) |  | 1.1. Alternative fish and oyster farming production system developed for 18 women associations, including the setup of 60 growing cages, 500 spat collectors and 2000 growing bags | 39328.3324 | October 2022 (Q4/Y4) |  | 1.1. Alternative fish and oyster farming production system developed for 18 women associations, including the setup of 60 growing cages, 500 spat collectors and 2000 growing bags | 85085 | Avril 2023 (Q4/Y4)
| 1.2. At least 6 ha of trees planted (enrichment planting primarily with coconut and oil palms) and 5 ha of mangrove rehabilitated in Dionewar to revitalize the main productive sectors | 77957.0027 | October 2020 (Q4/Y2) |  | 1.2. At least 6 ha of trees planted (enrichment planting primarily with coconut and oil palms) and 5 ha of mangrove rehabilitated in Dionewar to revitalize the main productive sectors | 32951.8619 | October 2021 (Q4/Y3) |  | 1.2. At least 6 ha of trees planted (enrichment planting primarily with coconut and oil palms) and 5 ha of mangrove rehabilitated in Dionewar to revitalize the main productive sectors | 128560.7248 | October 2022 (Q4/Y4) |  | 1.2. At least 6 ha of trees planted (enrichment planting primarily with coconut and oil palms) and 5 ha of mangrove rehabilitated in Dionewar to revitalize the main productive sectors | 103542.2343 | Avril 2023 (Q4/Y4)
| 1.3. At least 18 economic interest women’s groups and natural resource management committees trained to improve their technical performance | 26028.8828 | October 2020 (Q4/Y2) |  | 1.3. At least 18 economic interest women’s groups and natural resource management committees trained to improve their technical performance | 9718.4378 | Mars 2021 (Q2/Y3) |  | 1.3. At least 18 economic interest women’s groups and natural resourc+AC49+U46:U48 | 13479.8765 |  |  | 1.3. At least 18 economic interest women’s groups and natural resource management committees trained to improve their technical performance |  | Avril 2023 (Q4/Y4)
| 1.4. Management plans for fish and oyster farms management developed | 26926.4305 | December 2020 (Q1/Y3) |  | 1.4. Management plans for fish and oyster farms management developed | 24523.1608 | October 2021 (Q4/Y3) |  | 1.4. Management plans for fish and oyster farms management developed | 10502.2707 |  |  | 1.4. Management plans for fish and oyster farms management developed | 0 | Avril 2023 (Q4/Y4)
| 2.1. Protect, rehabilitate and extend the three (03) dikes against flooding over 1.2 km area | 222772.3324 | June 2021 (Q2/Y3) |  | 2.1. Protect, rehabilitate and extend the three (03) dikes against flooding over 1.2 km area | 418710.2634 | October 2021 (Q4/Y3) |  | 2.1. Protect, rehabilitate and extend the three (03) dikes against flooding over 1.2 km area | 574980.4124 | October 2022 (Q4/Y4) |  | 2.1. Protect, rehabilitate and extend the three (03) dikes against flooding over 1.2 km area | 262800 | Avril 2023 (Q4/Y4)
| 2.2. Develop a maintenance plan, involving key stakeholders | 0 | 0 |  | 2.2. Develop a maintenance plan, involving key stakeholders | 21630.3361 | June 2021 (Q3/Y3) |  | 2.2. Develop a maintenance plan, involving key stakeholders | 23815 | October 2022 (Q4/Y4) |  | 2.2. Develop a maintenance plan, involving key stakeholders | 0 | Avril 2023 (Q4/Y4)
| 3.1. The Communal Development Plan (PCD) is reviewed in order to integrate adaptation to climate changes options & cost benefits | 12765.1226 | June 2020 (Q2/Y2) |  | 3.1. The Communal Development Plan (PCD) is reviewed in order to integrate adaptation to climate changes options & cost benefits | 11989.1008 | June 2021 (Q3/Y3) |  | 3.1. The Communal Development Plan (PCD) is reviewed in order to integrate adaptation to climate changes options & cost benefits | 16725.7947 |  |  | 3.1. The Communal Development Plan (PCD) is reviewed in order to integrate adaptation to climate changes options & cost benefits | 0 | Avril 2023 (Q4/Y4)
| 3.2. Rules governing the exploitation of timber and non-timber forest products and the biological rest updated and formalized through a Local Convention | 20055.2044 | October 2020 (Q4/Y2) |  | 3.2. Rules governing the exploitation of timber and non-timber forest products and the biological rest updated and formalized through a Local Convention | 21525.8856 | Mars 2021 (Q2/Y3) |  | 3.2. Rules governing the exploitation of timber and non-timber forest products and the biological rest updated and formalized through a Local Convention | 9890.554 | October 2022 (Q4/Y4) |  | 3.2. Rules governing the exploitation of timber and non-timber forest products and the biological rest updated and formalized through a Local Convention | 0 | Avril 2023 (Q4/Y4)
| 3.3. Project’s lessons learned are documented and shared | 16455.0409 | October 2020 (Q4/Y2) |  | 3.3. Project’s lessons learned are documented and shared | 14078.1108 | October 2021 (Q4/Y3) |  | 3.3. Project’s lessons learned are documented and shared | 23050 | October 2022 (Q4/Y4) |  | 3.3. Project’s lessons learned are documented and shared | 33459.5958 | Avril 2023 (Q4/Y4)
| 3.4. One (01) meteorological station is installed in Dionewar | 9374.3869 | October 2020 (Q4/Y2) |  | 3.4. One (01) meteorological station is installed in Dionewar | 4904.6322 | June 2021 (Q3/Y3) |  | 3.4. One (01) meteorological station is installed in Dionewar | 8882.5577 | September 2021 (Q3/Y4) |  | 3.4. One (01) meteorological station is installed in Dionewar | 0 | Avril 2023 (Q4/Y4)
| M & E specialist salary | 5983.6512 | October 2020 (Q4/Y2) |  | M & E specialist salary | 5449.5913 | October 2021 (Q4/Y3) |  | M & E specialist salary | 5449.5913 | October 2022 (Q4/Y4) |  | M & E specialist salary | 2724.7956 | Avril 2023 (Q4/Y4)
| Local coordinator salary | 7180.3815 | October 2020 (Q4/Y2) |  | Local coordinator salary | 6539.5095 | October 2021 (Q4/Y3) |  | Local coordinator salary | 6539.5095 | October 2022 (Q4/Y4) |  | Local coordinator salary | 3269.7548 | Avril 2023 (Q4/Y4)
| Admin and fin assistant salary | 3590.1907 | October 2020 (Q4/Y2) |  | Admin and fin assistant salary | 3269.7548 | October 2021 (Q4/Y3) |  | Admin and fin assistant salary | 3269.7548 | October 2022 (Q4/Y4) |  | Admin and fin assistant salary | 1634.8774 | Avril 2023 (Q4/Y4)
| Allowances of CADL technical staff | 4786.921 | October 2020 (Q4/Y2) |  | Allowances of CADL technical staff | 3633.0463 | October 2021 (Q4/Y3) |  | Allowances of CADL technical staff | 3633.0463 | October 2022 (Q4/Y4) |  | Allowances of CADL technical staff | 1816.5232 | Avril 2023 (Q4/Y4)
| Office furniture | 598.3651 | October 2020 (Q4/Y2) |  | Office supplies | 544.9591 | October 2021 (Q4/Y3) |  | Office supplies | 0 | October 2022 (Q4/Y4) |  | Office supplies | 544.9591 | Avril 2023 (Q4/Y4)
| Maintenance | 199.455 | October 2020 (Q4/Y2) |  | Maintenance | 0 |  |  | Maintenance | 0 |  |  | Maintenance |  | Avril 2023 (Q4/Y4)
| Commodities | 1196.7302 | October 2020 (Q4/Y2) |  | Commodities | 1089.9183 | October 2021 (Q4/Y3) |  | Commodities | 1089.9183 | October 2022 (Q4/Y4) |  | Commodities | 0 | Avril 2023 (Q4/Y4)
| Transportation | 997.2752 | October 2020 (Q4/Y2) |  | Transportation | 908.2652 | October 2021 (Q4/Y3) |  | Transportation | 592.6431 | October 2022 (Q4/Y4) |  | Transportation | 0 | Avril 2023 (Q4/Y4)
| Communication | 698.0926 | October 2020 (Q4/Y2) |  | Communication | 635.7856 | October 2021 (Q4/Y3) |  | Communication | 141.0082 | October 2022 (Q4/Y4) |  | Communication | 0 | Avril 2023 (Q4/Y4)
| Mid-Evaluation | 2991.8256 | June 2020 (Q2/Y2) |  | Mid-Evaluation | 2991.8256 | October 2021 (Q4/Y3) |  | Mid-Evaluation | 2991.8256 | October 2022 (Q4/Y4) |  | Mid-end-Evaluation | 10000 | Avril 2023 (Q4/Y4)
| Steering committee meeting | 1994.5504 | October 2020 (Q4/Y2) |  | Steering committee meeting | 1816.5304 | October 2021 (Q4/Y3) |  | Steering committee meeting | 1816.5304 | October 2022 (Q4/Y4) |  | Audit | 10500 | Avril 2023 (Q4/Y4)
[13 empty] | Closer worshop | 10000
[9 empty] | FEES | 74100 |  |  | FEES | 40900
| TOTAL | 491059.3079 |  |  | TOTAL | 648436.861 |  |  | TOTAL | 948839.3506 |  |  | TOTAL | 566277.7402 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? | Not applicable |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Note on AD23: Aissata B. SALL: This activity was carried out by another partner, so the project made an economy of scale by reallocating the budget to one activity.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Institutional and political The local elected representatives and the representatives of the State who have already been trained by the project have changed after the local elections in 2017. | Inexistent | The project started after the local elections, which did not impact project implementation. However, there were local elections that coincided with the implementation phase but did not impact project execution.
Climatic Extreme weather events affect the realizations of the project | existent | Due to the very particular character of the island, during the rainy season, the companies take advantage and accelerate the works during the rainy breaks. Very adequate building materials are used and are resistant to flood waters.
Financial The implementation of alternative options of production (fish farming, oyster farming, etc.) will generate important financial resources, which can be sources of conflict between stakeholders or subject to embezzlement. This might compromise the financial sustainability of the project achievements. | No conflicts have been raised. | Since the activities in the project phase are being carried out with the supervision of the National Aquaculture Agency (NAA), the targeted beneficiaries are in the process of appropriating the techniques and operations. As a result, these same actors who have shown their commitment to the work will continue the activity in a collaborative framework and always under the supervision of the ANA. This is part of the ANA's field of intervention and mission at the national level.
Social The arrival of a foreign workforce and the establishment of protective infrastructure and income-generating activities in a single village in the municipality (which counts three villages) can be a source of conflicts and tension between the villagers. | The risk has not been raised. | Local workforces were used for the construction of the oyster and fish farms. This local workforce was also heavily involved in the rehabilitation of the dikes. The communities in Dionewar are highly organized and decisions are made by consensus and without discrimination. The project has benefited greatly from this comparative advantage.
Environmental and social harms | The risk has not been raised.
Challenging measures aiming at a sustainable use of natural resources | The risk has not been raised.
Child labor and work related accidents | During the year 2022, no incidents related to the presence of children on the dike work sites were noted. The PMU and the control firm "Poly services" are very careful about the movement of minors to these work sites. | In addition to the project actors meeting about sharing "environmental clauses", the PMU organized a special village assembly to reinforce awareness of the risks that the inhabitants could encounter, especially the children who are often attracted by the work in the various construction sites. A lot of awareness was developed during the sectoral meetings with the women's MSEs and the CSAs, to remind them of the prohibitions and the safety measures to be applied in the construction sites and their surroundings.
Use of shell mounds | The strict ban on the use of shell mounds remains a major concern of the project. | The Project document "environmental clauses" insists a lot on this prohibition. The PMU always has this document on hand to remind and warn, whenever necessary, of the environmental risks linked to the abusive use of shell mounds which constitute a natural and historical heritage of the locality whose progressive destruction constitutes a catastrophe. The companies that build the dykes use laterite produced in the region of Thies instead of the shells that they can find a few blocks from their sites. This is to say that they systematically respect the ban on this material.
Conflicts during the selection of the committees | No conflicts have been raised. | The choice of people for the establishment of all committees is well organized in the village and obeys the balance/rotation of the districts. This makes it easier for the project to recruit staff and for the companies to recruit workers and labourers. All the committees set up for the management of fish or oyster products, but also for the monitoring of beekeeping activities and the future operation of the dykes respect these requirements.
Women exposed to hazards in case of capsizing which can lead to loss of lives and goods | No cases have been raised. | The women of FELOGIE/Dionewar, the first operational partners of the project, continue to use the protective tools (masks, gloves, boots, and vests) acquired in the first years of the project for the management of aquaculture farms and the reforestation of the mangrove. However, in 2022, despite the insistence of the PMU and the Control Office, the companies building the dikes did not comply with the requirements for personal protective equipment (PPE). Wearing helmets, boots and gloves seems to be optional, while the "environmental clauses" document is very strict on this issue. Furthermore, the recommended beacons to indicate work sites are still not installed.
Involuntary resettlement of economic activities (temporary stop of shellfish resources exploitation) due to biological rest | Some fisheries are covered by mangrove reforestation | For the time being, the companies' work bases do not interfere with the movement of carts, let alone the livestock. Clear provisions are made in the document of "environmental clauses". Even if they are not applied by the companies, road users avoid the construction sites themselves. Concerning the management of these bases, the Bureau de contrôle des travaux des entreprises received on 27/06/22, a letter from the Dionewar Town Hall, demanding that the companies pay "the taxes for occupying the public domain". This correspondence was challenged by the companies and by the PMU because the communal institution never acted any allocation of public space to the companies to be used as "base of building site". This is why the president of the ADD/CONAF consortium leader sent a letter to the mayor of the commune dated 13/09/2022, requesting a meeting on this subject. The scheduling of this meeting is still awaited from the mayor's office. The Project has initiated a "sub-project" on beekeeping to allow women of the FELOGIE MSEs and fishermen whose fishing zones are involuntarily covered by the reforestation of the mangrove, to have alternative activities to compensate for the reduction of their economic resources. Actors have been trained for this purpose and the project has developed TORs for the purchase of equipment essential for the start of beekeeping production activities before the end of October 2022.
Use of mangrove wood | Cases are recurrent in the village but the project does not use mangrove wood. | . This year, the project planned and used quite substantial financial means to buy eucalyptus wood in Fimela for the protection of the plants. This option allowed the PMU to spare the mangrove and serve as an example for the population to consider. In 2021 the project had resorted to iron gabions but the operation was quite expensive for poor quality. It is to show that the project is concerned with the protection of the mangrove forest. The importance of this vegetation to contribute to the protection of the ozone layer and the fight against coastal erosion is known.
Accidents | No case has been reported.
Bad working conditions | No case has been reported. | Weekly surveillance and monitoring field missions have been conducted during the implementation of the fish and oyster farms. The same work is done during the works for the rehabilitation of the dikes.
Mangrove and spawning areas can be affected by the changes in water flow direction and the accumulation of sand | The risk has not been raised.
Introduction of exotic species | No case has been reported. | ANA only used local species for the oyster and fish farms.
Pollution due to a non-appropriate use of fish food | No case has been reported. | Beneficiaries who feed the fishes have been trained on how to feed them and how to use the fish food to avoid this risk.
Works during spawning and growing out periods | No case has been reported.
Accidental spills | No case has been reported. The works have not start yet.
Increase of the organic matter (overproduction of organic waste due to uncontrolled fish density) | No case has been reported.
Waste generation | No case has been reported.
Outbreak of sexually transmitted infections, including HIV/AIDS | No case has been reported.
Waterborne diseases | No case has been reported.
Ocular or respiratory diseases | No case has been reported.
Accidents | No case has been reported.
Falls or drowning | No case has been reported. | Lifejackets have been provided to the beneficiaries of the oyster and fish farms.
Fortuitous discovery of sites or objects of cultural, sacred or archaeological importance | No case has been reported.
Pollution of soil and lands | No case has been reported. | Weekly surveilland and monitoring are undertake during the works to make sure that no leaking is noted.
Modification of soil structure | No case has been reported.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal?
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)?
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Inclusion of women in the local climate issues and implementation of adequate measures | Outcome | Number of persons (including decision makers) aware of local climate issues and adequate measures to be implemented | 0 | 100 persons (50 at mid-term) (half of them women and half of them men) | Good
Training of women in order to improve their performance | Output | Number of women’s economic groups trained | 0 | 18 women’s economic groups | Good
Training of women in order to improve their performance | Output | Number of members of management committee and of community based organizations trained | 0 | 30 women | Good
Women and girls are aware of local climate change issues and the type of measures to be implemented | Output | Number of persons (including decision makers) informed of local climate change issues and adequate measures to be implemented | 0 | 410 persons (270 adult women, 120 adult men, 20 students (10 girls and 10 boys) | Good
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
Women exposed to hazards in case of capsizing which can lead to loss of lives and goods |  | Good
Non integration of the women in the decision making bodies (infrastructure, forest products management committees, steering committee for the local convention) |  | Good
Conflicts during the selection of the members of committees or the beneficiaries of trainings |  | Good
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | In addition to setting up a regular monitoring system related to gender aspects, CSE ensures the quality of entry of all TORs and see if it is well integrated
Have the implementation arrangements at the IE been effective during the reporting period? |  | YES (Completely)
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | ADD-CONAF and ANA are complying with the indicators included in the agreements that they have signed with CSE.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | YES (Completely)
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | NO
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Yes
No
Partially

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | - Environmental and social harms - Challenging measures aiming at a sustainable use of natural resources - Child labor and work related accidents - Use of shell mounds | - CSE and the PMU will ensure that relevant local authorities (sub-prefect, municipality) be informed in written prior to the launch of any activity - CSE and the PMU will ensure that the company will provide all required protection equipment and will conduct awareness campaign about the risks by including these measures in the technical specifications. - CSE and PMU will ensure that children will not be involved in works on the project sites and this measure will be included in the convention with the executing entities and the service providers - In close collaboration with the DAMCP, CSE and the project’s management unit will ensure that the firm in charge of the works complies with the protection status of shell mounds. | - Quality of the equipment - Percentage of minor included in the works - Number of visit | - Zero equipment provided - Zero minor included in the works - Zero visits | - Protection equipment have been provided for the aquaculture activities - Awareness raising campaign are implemented for the child labor, the use of shell mounds and the risks related to the works. - Field visits are carried by the PMU on a week basis for the implementation of the oyster and fish farms and for the works for the rehabilitation of the dikes
2 - Access and equity |  |  | - Conflicts during the selection of the members of committees or the beneficiaries of trainings | - Setup a local committee in charge to oversee the distribution of the project’s assets and the access to the project’s benefits | - Local committee | - No local committee because this activity did not exist | - A local committee has been set up and the Sub-Prefect, the mayor and all local technical services are members of the committee.
3 – Marginalized and vulnerable Groups |  |  | - Women exposed to hazards in case of capsizing which can lead to loss of lives and goods | - Provide women groupings with life jackets and protection equipment - Raise awareness on such risks (by including in the training sessions first aid, behavior during distress at sea). | - Quality of the equipment | - Zero equipment initially provided | - Life jackets and other protection equipment have been povided to those who are going on the oyster and fish farms mainly women
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | - Non integration of the women in the decision making bodies (infrastructure, forest products management committees, steering committee for the local convention) | - Breakdown the M&E indicators based on gender. - Executing agencies will used gender based approaches during consultative processes | - Number of Economic Interest Group trained and involved in the management committees | - No management committees have been implemented yet | - 18 Economic Interest Group have been trained on forestry products transformation and on aquaculture techniques - Women are part of the management committees of the fish and oyster farms
6 – Core labour rights |  |  | - Accidents - Bad working conditions - Child labor | - Provide protection equipment to avoid accident - Conduct awareness campaign for the workers about the risks of accidents - Enforce relevant labor regulations - Prohibit any kind of child labor | - Quality of the equipment - Percentage of minor included in the works - Number of visit | - Zero equipment initially provided | - Life jackets have been provided for those who were doing the works on the oyster and fish farms - Field visits have been carried on - The works have started and no minor are included in the works. Monitoring missions are carried out weekly to ensure that no minor have been included in the works. | - Accidents - Bad working conditions - Child labor | - The workers on the rehabilitation works are provided with security equipment - The awareness campaigns started with the launching of the works for the rehabilitation of the dikes.
7 – Indigenous peoples
8 – Involuntary resettlement |  |  | -Involuntary resettlement of economic activities (temporary stop of shellfish resources exploitation) due to biological rest | - Propose alternative economic alternative (beekeeping is proposed) | - Number of monitoring field mission | - Zero alternative activity was proposed or carried on initially | - Training sessions on beekeeping activities have been undertaken. Trainees have been provided with equipment. | -Involuntary resettlement of economic activities (temporary stop of shellfish resources exploitation) due to biological rest | - The beneficiaries of the beekeeping activity have been selected - The beekeeping activity have been installed with the local associations which have experience on it
9 – Protection of natural habitats |  |  | - Mangrove and spawning areas can be affected by the changes in water flow direction and the accumulation of sand | - Monitor the sedimentation at the spawning areas - Use mechanical action to reduce the accumulation of sand - Establish a committee comprising the project management, the DAMCP, the Forestry Service, local CSOs (CONAF, ADD, women grouping leaders), the local representative of the Directorate of Environment, the sub-Prefect and the Mayor. This committee will be tasked to monitor, identify and implement the above listed actions. | - Field visits to monitor the sedimentation at spawning areas - Existence of the committee | - The sedimentation is not monitored - No committee has been created | - The committee has been created to monitor all the activities of the project including the monitoring of sedimentation at spawning areas | - Mangrove and spawning areas can be affected by the changes in water flow direction and the accumulation of sand | - Field visits are conducted on a weekly basis since the beginning of the works for the rehabilitation of the dikes
10 – Conservation of biological diversity |  |  | - Introduction of exotic species - Pollution due to a non-appropriate use of fish food - Use of mangrove wood and shell mounds - Works during spawning and growing out periods | - Use only local species - Organize the works out of the spawning and growing out periods - Train the populations on how to feed fishes without generating pollutions - Prohibit the use of mangrove woods and shell mounds | - Field visits to ensure that only local species have been introduced and how the fishes are fed - Awareness raising on the use of mangrove woods and shell mounds | - No fish farms have been implemented - The population was using the mangrove woods and the shell mounds for construction | - Field visits are conducted on a week basis to make sure that only local species are introduced - The aquaculture agency only used local species for the implementation of the farms - Awareness raising campaigns are regularly conducted
11 – Climate change
12 – Pollution prevention and resource efficiency |  |  | - Accidental spills - Increase of the organic matter (overproduction of organic waste due to uncontrolled fish density) - Waste generation | - Develop a waterproof space - Maintain regularly the concrete mixer - Avoid overloading canoes during transport of hydrocarbons - Ensure containers are airtight - Control high fish densities - Monitor water quality (regular chemical analysis) (for the fish cages) - In case of overcrowding make transfers to other cages - Develop and implement a waste management plan | - Number of management plan realized - Number of analysis report - Fish density in the spawning areas | - No management plans have been implemented for the existing dikes - No analysis have been carried out | - The fishes have been introduced in the cages and their growing is controlled regularly - Analysis are carried out to control water quality - The works have started but the management plans have not been developed yet - A waste management plan has been developed
13 – Public health |  |  | - Outbreak of sexually transmitted infections, including HIV/AIDS - Accidents, - Waterborne diseases - Falls or drowning - Ocular or respiratory diseases | - Sensitization of workers and populations (through the environmental and social management plan) - Provide protective equipment (life jackets, lifebelts) for the operators of the aquaculture sites - Provide protective equipment to the workers (gloves, masks, glasses, helmets) (for the rehabilitation of the dikes) - Spray regularly the sites (dikes and borrowing sites) to avoid the dust takeoffs - Completely cover the top of the truck’s body and the load of laterite | - Quality of the equipment
14 – Physical and cultural heritage |  |  | - Fortuitous discovery of sites or objects of cultural, sacred or archaeological importance - The use of shell mounds | - Protect and secure these sites - Immediately cease activity on the sites concerned -Prohibit the use of shell mounds | - Awareness raising on the use of mangrove woods and shell mounds | - The population was using the mangrove woods and the shell mounds for construction | 0 | - Fortuitous discovery of sites or objects of cultural, sacred or archaeological importance - The use of shell mounds | - Continue the awareness raising campaigns regularly
15 – Lands and soil conservation |  |  | - Pollution of soil and lands - Modification of soil structure | - Sensitize operators to rational use of fertilizers - Ensure the supervision of the activity by the water and forest service - Promote the use of natural fertilizers - Ensure soil leveling at the end of the work | - Awareness raising on the use of fertilizers and workshop to promote the use of natural fertilizers | - The population was using fertilizers without taking any precautions | - The awareness campaigns have not started yet - The works have not start yet to level the soil structure | - Pollution of soil and lands - Modification of soil structure | - Awareness raising on the use of fertilizers and workshop to promote the use of natural fertilizers
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | YES
Have unanticipated ESP risks been identified during the reporting period? |  | YES
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | 1. Risks related to the sanitary pandemic of Coronavirus (COVID-19) were identified. In fact, the breakout of the pandemic leads the senegalese government to enter into a emergency state with the prohibition of national and interregional movements. Once the emergency state has been stopped, it was important to keep respecting the sanitary measures recommended by the Health Ministry. Therefore, the main safeguards measures adopted were: - the reduction of the number of participants during the training sessions in order to make sure to respect the social distancing - the provision of masks and hydroalcoolic gels - the population was sensitized on the sanitary risks due to coronavirus 2. Strong currents were noted in the area in which the floating cages were installed. These currents led to the deflection of the cages despite the installation of anchors. It was therefore decided, instead of the additional cages, to build fixed enclosures in order to avoid any deviation.
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | ESP Safeguards measures have been included in the agreements signed between the Executing entities and the implementing entity. In addition to that, local committees have been set up in order to monitor the effectiveness of the measures on site.
Have the implementation arrangements been effective during the reporting period? |  | YES
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | - ADD-CONAF have included into the call of interest for the rehabilitation of the dikes all the environmental and social measures to make sure that the company in charge of the construction will take into account all the environmental and social risks and put in place the necessary measures to mitigate those risks. - ANA have undertake follow-up missions and the analysis of physico-chemical parameters to make sure that the water in which the fish and oyster farms are immersed.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | YES
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
The main grievances are related to the delay for the rehabilitation of the dikes mainly after the rainy season which led to floodings |  | The coordination unit undertook sensitization campaign during local community activities to provide information on the causes of the delay.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Outcome 1: The resilience of the main productive sectors of Dionewar Island is enhanced and sustainable livelihoods of populations are improved |  | Outcome 5 | Natural resources assets are created |  | Since the project inception, 4.392 ha of mangrove have been restored and 5.389 ha of coconut trees and palm trees planted. | HS
|  |  | Outcome 6 | Different livelihoods and sources of income are proposed to the vulnerable groups. Especially fish and oyster farming for women groupings |  | 20 fish cages, 4 enclosures (100m3 each), 200 spat collectors and 3,500 growing bags have been constructed and implemented for the fish farms and the oyster farms. | HS
| Outcome 2: The vulnerability of populations in Dionewar to hazards is reduced with the construction or rehabilitation of protection structures |  | Outcome 4 | Infrastructures assets such as protection dikes are rehabilitated in order to protect the village and the population from floodings |  | The companies have been selected and the works are in progress and are at a very advanced stage | MS
| Outcome 3: Climate change is integrated in Communal Development Planning, natural resources are used in a more sustainable way and lessons learned are documented and shared |  | Outcome 3 | Populations and decision makers are aware of the climate hazards and are adopting climate risk reduction processes |  | The awareness raising campaigns are conduted regularly. Decision makers have also been trained on climate change management. | HS
|  |  | Outcome 7 | Resilience measures are included in the local policies |  | The local government representatives have been trained and sensitized on resilience measures. | HS
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mrs Aïssata Boubou SALL SYLLA, Head of Climate Finance Unit (CSE)
| Email: | aissata.sall@cse.sn
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
In this project, the accredited entity did not have to implement any activities. However, as part of its daily monitoring and compliance with procedures and commitments, the CSE noted a good dynamic of the project as a whole. The involvement of the implementing agencies and the coordination work carried out by the project management unit was a key factor in the achievement of the results identified above. Despite the delays in the implementation of some project activities, particularly the rehabilitation of dykes and reforestation, the various stakeholders always maintained the necessary rigor in order to find solutions to the difficulties encountered.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 1: The resilience of the main productive sectors of Dionewar Island is enhanced and sustainable livelihoods of populations are improved |  | Outcome 5 | Natural resources assets are created |  | Since the project inception, 4.392 ha of mangrove have been restored and 5.389 ha of coconut trees and palm trees planted. | HS
|  |  | Outcome 6 | Different livelihoods and sources of income are proposed to the vulnerable groups. Especially fish and oyster farming for women groupings |  | 20 fish cages, 4 enclosures (100m3 each), 200 spat collectors and 3,500 growing bags have been constructed and implemented for the fish farms and the oyster farms. | HS
| Outcome 2: The vulnerability of populations in Dionewar to hazards is reduced with the construction or rehabilitation of protection structures |  | Outcome 4 | Infrastructures assets such as protection dikes are rehabilitated in order to protect the village and the population from floodings |  | The companies have been selected and the works are in progress and are at a very advanced stage | MS
| Outcome 3: Climate change is integrated in Communal Development Planning, natural resources are used in a more sustainable way and lessons learned are documented and shared |  | Outcome 3 | Populations and decision makers are aware of the climate hazards and are adopting climate risk reduction processes |  | The awareness raising campaigns are conduted regularly. Decision makers have also been trained on climate change management. | HS
|  |  | Outcome 7 | Resilience measures are included in the local policies |  | The local government representatives have been trained and sensitized on resilience measures. | HS
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mr Moussa Ndiaye, Project Coordinator
| Email: | djiguibala@yahoo.fr
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The reforestation of mangroves, coconut trees and palm trees, initiated by the implementation agency ADD-CONAF, has progressed in a very positive way with an effective involvement of the population in the realization of this activity. Taking into account endogenous knowledge has been one of the success factors of this activity. This knowledge made it possible to take into account very early on the problem of domestic animals wandering. Plant protection measures were proposed for this purpose. The failure to reach the objectives set by the project (5ha for mangroves and 6ha for fruit species) is generally due to the space problem observed in the village. However, the Project Management Unit continues to prospect for spaces to fill the remaining number of hectares. It is also worth mentioning the problems encountered with the seedling supplier who was late in providing the seedlings to be used for reforestation in 2021 as mentioned in the last PPR. Regarding the fish and oyster farming activities, the strong involvement of women has been the main factor of success. The Implementing Agency, ANA, has faced some difficulties regarding fish farming activities. The maintenance of the cages had to be carried out at a regular pace because of the current that runs through the area where the cages are located. As for the rehabilitation of the dikes, the companies have been hired and the work has started and is at a very advanced stage. However, the covid 19 pandemic had a great impact on the work at the beginning with health restrictions and travel bans. In addition to these factors, the consideration of the winter season (rainy season) is a factor in slowing the pace of work, with the consequences of flooding and marine intrusions. The main negative point to mention about the implementation of the project is the delay noted in the rehabilitation of the dykes, which is the main activity of the project. All the expectations of the populations are put on this activity. However, this delay is due to the natural factor raised above such as the rainy season which accentuates the intrusion of sea water and even floods. Beyond this activity, the negative point is the fish farming activity, with the choice of fixed cages at the beginning of the project, which was not the right choice in view of the results obtained for the first year of implementation of the project. In this sense, the implementing agency ANA, conducted the experiment with the establishment of floating cages which proved more beneficial and more profitable for the exploitation but is also subject to a number of constraints. Overall, the positive point in the implementation of the project is the approach put in place by the project coordination in creating this framework for continuous consultation with the various stakeholders of the project.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective | Number of risk-exposed coastal households benefiting of adaptation measures | 451 households threatened by flooding and coastal erosion | 0 | At least 270 households are protected
| Are (ha) of mangrove and terrestrial ecosystems restored | 0 | 4. 392 ha of mangrove restored 5.389 ha of coconut trees and palm trees planted | 5 ha of mangrove restored 6 ha of terrestrial ecosystems (palm trees and coconut trees) planted
| Percentage of increase of income of population involved in alternative income generating activities (breakdown by gender) | 0 | 0 | Increase of 25% at least
Outcomes | Number of dikes rehabilitated and built to protect households and socioeconomic infrastructures against flooding and coastal erosion | 0 | 0 | 3 dikes are rehabilited
| Number of persons (including decision makers) aware of local climate issues and adequate measures to be implemented | 0 | 66 | 100 persons (50 at mid-term) (half of them women and half of them men)
| Number of local development tools that integrate adaptation measures | 0 | 2 | 2 local planning documents are updated integrating adaptation measures
Outputs | Number and type of adaptive production systems | 0 | 3 | 3
| Number of fish cages | 0 | 60 | 60
| Number of spat collector | 0 | 500 | 500
| Number of growout bags | 0 | 3500 | 2000
| Number of analysis report for the monitoring of the physicochemical and bacteriological parameters of the fish farm’s site | 0 | 8 | 12
| Area (ha) of trees planted | 0 | 5. 389 ha | 6 ha of palm trees and coconut trees planted
| Area (ha) of mangrove rehabilitated | 0 | 4. 392 ha | 5 ha of mangrove restored
| Number of women’s economic groups trained | 0 | 18 | 18
| Number of members of management committee and of community based organizations trained | 0 | 100 | 30
| Number of management plans | 0 | 3 | 2
| Number of new dikes restored or extended | 0 | 0 | 3
| Number of dikes’ maintenance plan developed | 0 | 0 | 1
| Number of planning documents reviewed that integrated adaptation options | 0 | 2 | 2
| Number of local convention on sustainable management of natural resources adopted | 0 | 1 | 1
| Number of field missions for monitoring the implementation of the alternative activities (bee-Keeping, etc.) | 0 | 0 | 6
| Number of production of lessons learned | 0 | 3 | 4
| Number of persons (including decision makers) informed of local climate change issues and adequate measures to be implemented | 0 | 395 | 410
| Number of meteorological station implemented | 0 | 1 | 1
Note on G8: Mouhamed Abdallah SALL : The number of households threatened by flooding that benefit from the measures is not yet determined by the project because the protective dikes are being rehabilitated.
Note on G10: Mouhamed Abdallah SALL : As an alternative activity, the Project had initiated beekeeping. For this, a group of 15 people representing the Federation of Women's MSEs, 3 representatives of the districts and 2 representatives of the CBOs were trained in beekeeping management techniques. It remains the practical application before the multiplication of the training.
Note on G11: Mouhamed Abdallah SALL : The dikes have not yet been delivered, but the companies have started work since September 2021 and are at a very advanced stage.
Note on G24: Mouhamed Abdallah SALL : The rehabilitation of the dikes is underway and a control office is on site to ensure that the work is carried out properly and that environmental and social standards are respected.
Note on G25: Mouhamed Abdallah SALL : The maintenance plan has not yet been completed. The rehabilitation of the dikes is underway. The control office in charge of supervising the execution of the works will have to establish the maintenance plan of the dikes. It will also have to train the infrastructure management committee that will be formed at the end of the work.
Note on G28: Mouhamed Abdallah SALL : Beekeeping was chosen as an alternative activity during the biological rest period imposed by the local convention. Therefore, a training in beekeeping techniques has been carried out during September 2021. It only remains to acquire the material for the effective implementation of the activity. Once the activity is implemented, the PMU will carry out regular monitoring missions.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The main positive lessons that have affected the progress of implementation are related to the involvement of local communities. For this type of project, it is important that local communities fit into the planned activities. For example, the reforestation activities were completely and entirely taken over by the local communities, who took days off work to participate in the reforestation. The local communities were also involved in the production of fish, oysters, from the construction of the grow bags to the collection of the oysters. In addition, local people were prioritized for the recruitment of workers for the village protection dyke.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | During this reporting period, companies were faced with inflation of certain costs (transportation, inputs and labor costs among others). This in periodically slowed down the work. The community of Dionewar provided as a support to the project dugout canoes and carriages bought within the framework of the project to the companies for the routing of materials. Added to this corona virus pandemic and/or weather hazards,
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | The drainage system was not installed as initially planned because the quality of the well water had become brackish. The ADD/CONAF in agreement with the CSE, has decided to connect the nursery to the village water system and to build ponds to eliminate the use of well water.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | The implementation of the ESMP is followed regularly by each executing agency. The environmental and social safeguard measures are implemented for each related activity.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender was taken into account during the project formulation phase. Indeed, the results framework includes specific, disaggregated gender indicators. As Dionewar village is a society in which vulnerable groups such as women are well included in the activities, there was no difficulty in integrating gender into the project activities. Women being the main beneficiaries of the fishing activities, they represented 86% of the people trained in aquaculture techniques. These trained people will be the ones who will operate the fish and oyster farms. It was therefore necessary to involve these people as early as possible in the process in order to ensure a good appropriation of the project's activities and especially the sustainability of the project's achievements. The main indicators that highlight the role of women in the management of adaptation to climate change are the following - Involvement in training on aquaculture techniques and natural resource management. - Participation in natural resource management committees - Improvement of knowledge on climate change
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | When it comes to adaptation projects, it is important to have experienced firms in the field of work to ensure strict compliance with the technical specifications of the tender documents. This is a key element in the sustainability of the adaptation technologies implemented.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | One adaptation measure that has good potential for scaling up is oyster farms. This activity has shown good results that can be scaled up in estuarine areas.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | These guidance documents are useful both during the formulation phase of our projects and during the implementation phase. The institutional focal points draw heavily on them during the gaps assessment process and the resulting action plans.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | The design of adaptation projects requires the involvement of local communities from the formulation phase, taking into account endogenous knowledge combined with new technologies for better results.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Among the concrete adaptation interventions undertaken by the project and which can be scaled up, we can mention the oyster farming activity. This activity constitutes an alternative activity with an important potential at the level of the project's intervention area, where the majority of the actors are women. the development of this production chain could constitute an important source of income for these women and will allow them to reduce their vulnerability in a considerable way to the effects of climate change.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The ownership and involvement of the project activities by the local communities were the most important elements of the project, both in terms of achieving the targeted indicators and the sustainability of the project activities
What measures are/have been put in place to ensure sustainability of the project/program results? | The project's Management Unit, being selected at the level of the project's intervention zone, has encouraged the involvement of the local population in the project's activities. The sustainability of the project's results is intrinsically linked to the ownership of the local communities. The basis of this ownership has been based on continuous and transparent communication with the beneficiaries
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | As noted in the 2021 report, as a result of the awareness sessions and trainings organized in the village by the Project, there is a better understanding of the effects of climate change and an improvement in the behavior of the population with regard to the fight against the effects of these disturbances: Better mobilization during reforestation activities and human investment for the protection of the island (construction of bunds of PPE and low walls in front of the village); Better mobilization during forums on environmental management; At the regional and NGO level, we note that more attention is paid to the REVARD Project (invitation to workshops related to climate change: ARD workshops in Fatick and ENDA-ENERGIE in Saly Portudal. )
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | all project information/data/knowledge to be made public has been shared with relevant stakeholders. the dissemination channels used depend on the type of information/data/knowledge to be covered. Depending on the target audience, informations are disseminated through the community radio, by email or by formal mail.
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | The Project Management Unit initiated the development and collection of project knowledge products in the early years of implementation: Photo album of the project's achievements Strategies and plans developed in the field of ostreicultural farms Local convention developed Technical report (physico-chemical) on the quality of water in fish farms All training reports (organizational management, climate change, beekeeping etc.) have been elaborated
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | The project is working on a capitalization document in which all these aspects will be highlighted
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | The innovation aspect relates to the approach used to implement this project. A real structured dialogue between all project stakeholders. Transparency in the sharing of information.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | SEN/NIE/Coastal/2015/1
Implementing Entity | Centre de Suivi Ecologique
Type of implementing entity | NIE
Country | Senegal
Region | Africa
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 5395 | 3480 | 1915 | Total |  |  |  | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 2: Partially not aware |  | 3480 | 50%
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 0 | 20% to 39% | 2: Partially not aware |  | 4 | 40% to 60% | 5: Fully aware |  | 2 | 40% to 60% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | Training manuals | Local |  | 4 | Training manuals | Local |  | 3 | Training manuals | Local
|  | 0 | technical guidelines | Local |  | 1 | Technical guidelines | Local |  | 1 | Technical guidelines | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Disaster risk reduction | Local | 2: Partially responsive (Lacks most elements) |  | Disaster risk reduction | Local | 4: Mostly responsive (Most defined elements) |  | Disaster risk reduction | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
|  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Disaster risk reduction | 3 | Community |  | Disaster risk reduction | 3 | Community |  | Disaster risk reduction
|  | 0 | Community |  | Food security | 2 | Community |  | Food security | 2 | Community |  | Food security
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 3: Moderately effective |  | Other | biological assets | 4: Effective |  | Other | biological assets | 4: Effective |  | Other | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha rehabilitated | 1: Ineffective | Forests | 6 | ha rehabilitated | 4: Effective | Forests | 5 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves |  | ha rehabilitated | 2: Partially effective | Mangroves | 5 | ha rehabilitated | 4: Effective | Mangroves | 4 | ha rehabilitated | 4: Effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 451 |  | 2: Limited improvement |  | 270 |  | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 30 |  |  | Aquaculture | 30 |  |  | Aquaculture | 65 |  |  | Aquaculture
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies | Disaster risk reduction | Coastal drainage and infrastructure | 3 | Adaptation strategies | Disaster risk reduction | Coastal drainage and infrastructure | 0 | Adaptation strategies | Disaster risk reduction | Coastal drainage and infrastructure
|  | 1 | Adaptation strategies | Other | Mangrove reforestation | 1 | Adaptation strategies | Other | Mangrove reforestation | 1 | Adaptation strategies | Other | Mangrove reforestation
|  | 1 | Adaptation strategies | Other | Sustainable forest management | 1 | Adaptation strategies | Other | Sustainable forest management | 1 | Adaptation strategies | Other | Sustainable forest management
|  | 0 | Adaptation strategies | Other | Supporting livelihoods | 2 | Adaptation strategies | Other | Supporting livelihoods | 2 | Adaptation strategies | Other | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 451 | Aquaculture |  |  | 30 | Aquaculture |  | 350 | 65 | Aquaculture
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 451 | Fishing |  |  | 30 | Fishing |  | 350 | 65 | Fishing
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 451 | Forestry |  |  | 270 | Forestry |  | 66
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
1: None
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | Local | Environmental policy | 2 | Multi-sector | Local | Environmental policy | 2 | Multi-sector | Local | Environmental policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 1 | 4: Enforced (Most elements implemented) |  | 4: Effective | 1 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste