## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 1 August 2018-31 July 2019
| Project Title: | PILOT RURAL DESALINATION PLANTS USING RENEWABLE POWER AND MEMBRANE TECHNOLOGY AT BETHANIE AND GRÜNAU, //KARAS REGION, NAMIBIA
| Project Summary: | Namibia relies heavily on groundwater for the supply of water, and the predicted increase in both temperature and rainfall variability due to climate change will increase this reliance. However, in many areas the dissolved solids content of the locally available groundwater exceeds the approved threshold for human consumption. Decreased aquifer recharge due to periods of lower rainfall caused by climate change is likely to cause an increase in total dissolved solids in groundwater, which will exacerbate the water quality situation. Pumping water over long distances from other water sources is not a feasible option for supplying small communities with good quality water. An alternative is to improve the quality of locally abstracted groundwater by applying treatment techniques. These techniques require energy in the form of electricity, but many of the small communities are not coupled to the national electricity grid. It is also considered that the energy needs for treatment should be met by sustainable and environmentally sound resources.
The aim of the proposed project is thus to pilot the treatment by reverse osmosis (RO) of poor quality local groundwater to a level that complies with the national standards for drinking water, using sun and wind energy to power the process. Execution of the project will yield a wide range of information and knowledge on both technical and social aspects of establishing and operating such treatment and power plants. The acquired information, knowledge and skills will then be communicated to stakeholders in the water supply sector in order that the applied technology could be mainstreamed and replicated elsewhere in the country. The project will result in improved resilience of vulnerable communities and groups to climate change impact, specifically to a decrease in chemical water quality of existing groundwater sources. In addition to providing benefits to vulnerable communities in the target areas, the project will also serve to increase the capacity of government agencies to integrate climate change adaptation considerations into water supply planning and policy processes. It is considered essential to pilot two plants in a rural setting, where the water demand of the communities differs by an order of magnitude. This would allow the opportunity to establish how plant size affected aspects such as operation, management and maintenance requirements, the unit cost of water produced, the involvement of beneficiaries; and the interest of stakeholders. The two selected project sites are at Grünau settlement and at Bethanie village, both located in the far south of the country.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | NAM/NIE/Water/2015/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Desert Research Foundation of Namibia (DRFN) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Republic of Namibia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | 1. Bethanie Village, //Karas Region (Southern Namibia) 2. Grünau Settlement, //Karas Region (Southern Namibia) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 10-13 October 2017 during 30th Adaptation Fund Board Meeting
IE-AFB Agreement Signature Date: |  | 2018-01-15 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2018-08-01 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | Not planned - project duration 4 years
| Terminal Evaluation Date: | 2022-11-30
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Reports - Inception Workshop Report - Analysis of project inception and execution delays - Adaptation Fund questionnaire on project inception delays - Request for revised disbursement schedule - Investment Income Report for January to March 2018 - Investment Income Report for April 2018 to June 2018 - Investment Income Report for July 2018 to September 2018 - Investment Income Report for October to December 2018 - Investment Income Report for January to March 2019 - Investment Income Report for April 2018 to June 2019 - Inception Report for engineering consulting services - Concept Design Report for plants at Grünau and Bethanie - Preliminary Design Report for plants at Grünau and Bethanie - Detail Design Report for plants at Grünau and Bethanie - Final Draft ESIA for Grünau - Final Draft ESMP for Grünau - Final Draft ESIA for Bethanie - Final Draft ESMP for Bethanie Documents - Grant Agreement between DRFN and NamWater - Minutes of Planning and Preparation Meeting - Record of meeting to discuss investment of first tranche - Minutes of Inception Workshop - Prescribed NamWater external financial audits - DRFN comment on draft ToR for engineering consulting services - RFP for procurement of engineering consulting services | Czech Republic
- Procurement Committee submission on engineering consulting services - Letter of award of tender for engineering consulting services - Minutes of Kick-off Meeting with engineering consultant - Presentation on first engineering site visit - 4 x Minutes of Progress Meetings with engineering consultant - RFP for construction of plant at Bethanie - RFP for construction of plant at Grünau - DRFN comment on draft ToR for environmental consulting services - RFP for procurement of environmental consulting services - Procurement Committee submission on environmental consulting services - Letter of award of tender for environmental consulting services - Minutes of Kick-off Meeting with environmental consultant - Minutes of Progress Meetings with environmental consultant - Minutes of meeting with environmental consultant on water costing and tariffs - ToR for Project Steering Committee - Minutes of Project Steering Committee Meeting - Results framework - Risk register - RFP for construction of Bethanie plant (Bidding documents -545 pp, BoQ – 29 Excel sheets, Drawings – 86 pp) - RFP for construction of Grünau plant - Advertisement of construction tenders - Disbursement requests from NamWater - Invoices from NamWater - Quarterly project cost reports - Control and record sheet (budget and expenditure)
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.drfn.org.na | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Dr. Martin Schneider | Dominican Republic
| Email: | martin.schneider@drfn.org.na | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Mr. Teofilus Nghitila | Equatoral Guinea
| Email: | tnghitila@yahoo.com | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Dr. Martin Schneider | Fiji
| Email: | martin.schneider@drfn.org.na | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Mr. Romeo Likando | Georgia
| Email: | likandor@namwater.com.na | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31 July 2019
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
NOTE: All expenditure and ROI took place in NAD (N$). For the purpose of the PPR1 all expenditure and ROI amounts were converted to USD (US$) at the exchange rates applicable on the respective days that the Project funds (A+B) and the NIE fee (C) received from the AF were converted to NAD (N$). The exchange rates (N$:US$) applied for reporting are: Project funds (A+B): 11,691 ROI on Project funds (A+B): 11,691 NIE fee (C): 11,84 ROI on NIE fee (C): 11,84
Estimated cumulative total disbursement as of January 2018 | ITEM | AMOUNT (US$)
| TOTAL SPENT | 311029.2976
| Project formulation grant | 25000
| Project grant (A+B+C) | 286029.2976
| Project funds (A+B) | 150419.5792
| NIE fee (C) | 95181
| ROI on C | 3417
| Advance to NIE | 37011.7184
Add any comments on AF Grant Funds. (word limit=200) | The change in NAD-USD exchange rate from the time of budget compilation to receipt of Tranche 1 resulted in a loss of approximately 10% of the project budget in NAD. Since Tranche 1 comprises 82,5% of the total Project Grant, the exchange loss amounted to 8.3% of the total project budget. However, prudent investment of Tranche 1, coupled to a change in project execution schedule that delayed spending of the bulk of the Project Activities Cost (A), has yielded a return on investment that has fully recovered the exchange rate loss on Tranche 1. At the project inception workshop the EE presented its final strategy for executing the project, which would necessitate changes to be made to both the AF-approved execution schedule and the projected annual cash flows under the Project Activities Cost (A). The implication was that funds intended for all activities under Component 1 and Component 2 (development of plants) would be appropriated over Years 1 and 2, and not in Year 1 as was indicated in the project proposal. The NIE on 25 October 2018 submitted a request for a revised disbursement schedule, which the AF Board approved in terms of Decision B.32-33/11.
INVESTMENT INCOME | TOTAL ROI Project funds (A+B) NIE Fee (C) | US$ 476 039 US$ 472 622 US$ 3 417
Amount of annual investment income generated from the Adaptation Fund’s grant
Upon receipt of Tranche 1, all funds were converted to N$ and invested in line with AF Decision AFB/EFC.21/6 of 9 October 2017. The NIE’s investment strategy was to provide a proper balance between security of investment, availability of funds when required and maximizing return on investment. The sum of the Project Activity Cost (A) and Project Execution Cost (B) was invested separately from the Project Management Fee (C). Our interpretation of Paragraph 10 (b) (ii) of the AF Decision AFB/EFC.22/5 of March 2018 (“To use the income earned on amounts held in respect of Adaptation Fund project grants solely for the purposes of the associated project/programme”) was that the return on investment (ROI) on invested Project Management Fee (C) funds may be utilised by the NIE to carry out project management activities. For this reason the ROI of US$ 3 417 was used by the DRFN and the expenditure is included in the disbursement record of AF funds above.
However, it has since been brought to our attention that this interpretation is wrong and that the ROI on the Project Management Fee (C) may only be used to supplement the Project Activity Cost (A). The ROI of US$ 3 417 thus has to be returned to the investment account for Project funds (A+B) from the NIE funds for Year 2. The DRFN obtained approval from the AF for an advance of US$ 30 000 from the ROI on investment of A+B (email dated 23 January 2019), to supplement the amount provided under Tranche 1 for Project Management Fee (C) in Year 1, which is to be returned to the investment account for Project funds (A+B) from the NIE funds for Year 2. The amount borrowed in N$ amounted to US$ 37 012 at the exchange rate applicable on the day when the first tranche for A+B was converted to N$, but amounted to US$ 30 000 at the exchange rate applicable on the day of borrowing. This money was spent over and above the Tranche 1 amount received under B, i.e. to execute our project management activities. Utilisation of the loan amount is set out in the block under "EXPENDITURE DATA" below.
Why an advance was required: 1. The business model of the DRFN is to finance its activities by means of income generated through the execution of projects. In the case of this AF-funded project that is being executed by NamWater, the DRFN is paid a fee referred to by the AF as the Project Management Cost (C) to manage implementation of the project. 2. This fee is intended to cover all internal and external expenditure that DRFN incurs in managing the project, including the cost of time spent on the project by its own staff and by external consultants used by the DRFN. 3. The project proposal approved by the AF provided for the project to have an execution period of 4 years, starting in April 2018. As such, the DRFN would have an implementation involvement for 4 years, plus the execution of a limited amount of pre-project work (such as planning and preparing for the Inception Workshop) to get the project going and some post-project work associated with project closure. The budget that the DRFN submitted to the AF was therefor based on the normally expected cost to manage implementation of a project that is executed by a competent entity over a period of 4 years, including the cost to start up and close the project.
4. However, due to various reasons, implementation of the project did not proceed as planned. This has led to an increase in planned project expenditure by the DRFN and led to an accelerated cash flow that could not be accommodated from the project management fee under Tranche1 as is elaborated below. 5. In the interest of continued management of implementation of the project to the standards required by the AF, the DRFN requested and obtained approval from the AF to, on the basis of a loan, utilise some of the accumulated income that has been generated by investment of the A and B parts of Tranche 1.
6. The reason why cash flow problems were created are addressed below: • Pre-project work already started on 16 November 2017 with DRFN having the first planning and preparation meeting with NamWater. At that meeting it became clear that NamWater did not have a project execution strategy, that the technical execution entities in NamWater were not on board the project since they were not adequately involved in formulating the project proposal and that execution would not start in April 2018. The implication was that the DRFN had to spend more time on pre-project work than would have been required otherwise. In addition, the approach to and the handling of some of the pre-project activities by NamWater required the DRFN to incur unnecessary and unplanned staff time inputs to get the project started; an example of this is the uncoordinated approach that NamWater had to finalizing the DRFN-NamWater agreement, which required numerous meetings and much correspondence between 30 January 2018 when the DRFN supplied the draft agreement to NamWater and 18 May 2018 when the agreement (with minor changes to the original draft) was finally signed by NamWater. The implication is that the DRFN spent much more money than planned on the pre-project phase, which had a direct and negative impact on cash flow. • The first tranche from the AF was received on 25 January 2018, which was intended to cover the project costs for the first project year that was to start in April 2018 and run up to March 2019 after which the second tranche was due. However, although project activities by NamWater already started in April 2018 with preparation of tender documents and advertisement of the tender for engineering services on 20 April 2018, the official project starting date was postponed to August 2018. The implication is that project execution will now actually take 4 years and 4 months, with the first project year having a real duration of 16 months from April 2018 to July 2019, and that the DRFN has to cover all project costs incurred over a period of 16 months from April 2018 to July 2019 with a fee intended for a first project year of 12 months only.
• The increase in DRFN expenditure was further compounded by the fact that NamWater realised that construction of the plants could not be carried out in Project Year 1 as per the project proposal, but would only be completed (hopefully) in Project Year2. As a result the DRFN had to compile a new budget for Project Year 1 and 2 for the Project Activities Cost (A), approach the AF with a request to allow a change to the project plan and to approve a restructuring of the tranches. This was approved by the AF, but required a variation to the AF-DRFN agreement and a report on project delays to be compiled and submitted by the DRFN to the AF. The activities by the DRFN to successfully achieve the required changes cost a substantial amount of time and associated cost that were not budgeted for. • It is also our view that the DRFN in the interest of the project has spent much time in assisting NamWater with various activities that should have been the sole responsibility of NamWater, thereby further increasing unplanned expenditure by the DRFN.
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT (US$)
| Project Activity Cost (A) | 22574.0313
| Comp 1: Develop desal plants | 13619.6219
| 1.1 Civil works | 2483.1922
| 1.2 Water treatment plants | 8277.0507
| 1.3 M&E works | 2859.379
| Comp 2: Develop energy plants | 8954.4094
| 2.1 Turbines | 2189.6331
| 2.2 Solar fields | 2575.3143
| 2.3 Battery banks | 1070.396
| 2.4 Inverters & BOS | 1070.396
| 2.5 Electrical & SCADA | 1070.396
| 2.6 Civil: safety & security | 978.2739
| 2.7 Professional fees | 0
| Comp 3: Test, commission, train | 0
| Comp 4: Piloting of plants | 0
| Comp 5: Supply quality water | 0
| Comp 6: Sensitise stakeholders | 0
| Comp 7: Info & knowledge | 0
| Project Execution Cost (B) | 127845.5479
| 1. Management and supervision | 24577.8774
| 2. Data collection | 333.5899
| 3. Progress meetings/reports | 25749.0369
| 4. Financials | 1316.9464
| 5. Site scientist/engineer | 20861.7073
| 6. Capacity building | 55006.39
| Project Management Fee (C) | 95181.4443
| 1. Management | 48849.6975
| 2. Operations | 2038.6754
| 3. Office services and supplies | 19800.8406
| 4. Auditing and consulting | 17118.2308
| 5. Knowledge dissemination | 7374
| ROI on Project Management Fee (C) to supplement Fee (C) | 3417
| 1. Management | 2533.208
| 2. Operations | 178.0839
| 3. Office services and supplies | 62.1146
| 4. Auditing and consulting | 643.5935
| 5. Knowledge dissemination | 0
| Advance to NIE to supplement Proj. Management Fee (C) | 37011.7184
| 1. Management | 27438.7999
| 2. Operations | 1928.9411
| 3. Office services and supplies | 672.803
| 4. Auditing and consulting | 6971.1744
| 5. Knowledge dissemination | 0
| PROJECT (A+B+C) | 286029.7419
PLANNED EXPENDITURE SCHEDULE
NOTE: Planned expenditure under Project Activity Cost (A) consists of the remainder of Tranche 1 for A (= US$ 3 789 485), plus Tranche 2 for A (= US$ zero as per approved revised disbursement schedule). Planned expenditure under Project Execution Cost (B) consists of the remainder of Tranche 1 for B (= US$ 88 142) plus Tranche 2 for B (= US$ 113 688), amounting to US$ 201 830. Planned expenditure under Project Management Cost (C) consists of Tranche 2 for C (= US$ 93 285) minus the advance to be repaid (= US$ 37 012), minus the ROI on C for Year 1(=US$ 3 417) to be repaid, amounting to US$ 52 857.
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST (Project Year 2) | Est. Completion Date
| Project Activity Cost (A) | 3789484.9687
| Comp 1: Develop desal plants | 2270610.3781 | 2020-07-31
| 1.1 Civil works | 868456.8078 | 2020-07-31
| 1.2 Water treatment plants | 1129610.9493 | 2020-07-31
| 1.3 M&E works | 272542.621 | 2020-07-31
| Comp 2: Develop energy plants | 1477199.5906 | 2020-07-31
| 2.1 Turbines | 399072.3669 | 2020-07-31
| 2.2 Solar fields | 547301.6857 | 2020-07-31
| 2.3 Battery banks | 311021.604 | 2020-07-31
| 2.4 Inverters & BOS | 58374.604 | 2020-07-31
| 2.5 Electrical & SCADA | 13791.604 | 2020-07-31
| 2.6 Civil: safety & security | 43606.7261 | 2020-07-31
| 2.7 Professional fees | 104031 | 2020-07-31
| Comp 3: Test, commission, train | 19161 | 2020-07-31
| 3.1 Test components and complete systems, etc. | 1916 | 2020-07-31
| 3.2 Provide specialized training to O&M staff | 8431 | 2020-07-31
| 3.3 Produce training and maintenance manuals | 5173 | 2020-07-31
| 3.4 Involve tertiary institution students, etc. | 3641 | 2020-07-31
| Comp 4: Piloting of plants | 19321 | 2022-07-31
| 4.1 Operate, maintain and improve the desalination plants | 0 | 2022-07-31
| 4.2 Operate, maintain and improve the power plants | 0 | 2022-07-31
| 4.3 Update the training, operations and maintenance manuals | 6000 | 2022-07-31
| 4.4 Collect technical and social information, etc. | 8400 | 2022-07-31
| 4.5 Inform beneficiaries of what plants do and the benefits to be achieved | 4921 | 2022-07-31
| Comp 5: Supply quality water | 0 | 2022-07-31
| 5.1 Operate, maintain the plants | 0 | 2022-07-31
| 5.2 Hand over infrastructure to NamWater to ensure continuation of water supply | 0 | 2022-07-31
| Comp 6: Sensitise stakeholders | 1824 | 2022-07-31
| 6.1 Public meetings to share information | 1059 | 2022-07-31
| 6.2 Information supply to school children | 218 | 2022-07-31
| 6.3 Impart knowledge and skills to community women | 547 | 2022-07-31
| Comp 7: Info & knowledge | 1369 | 2022-07-31
| 7.1 Share project experience and lessons learnt | 931 | 2022-07-31
| 7.2 Distribute technical information | 438 | 2022-07-31
| Project Execution Cost (B) | 201830.4568 | 2022-07-31
| 1. Management and supervision | 52817.8123 | 2022-07-31
| 2. Data collection | 55656.7022 | 2022-07-31
| 3. Progress meetings/reports | 54559.0592 | 2022-07-31
| 4. Financials | 26873.2729 | 2022-07-31
| 5. Site scientist/engineer | 11923.6101 | 2022-07-31
| 6. Capacity building | 0 | n/a
| Proj. Management Fee (C) (Note: Planned expenditure for Year 2 as per the Project Proposal is reduced by the advance and the ROI on C to be paid back to the investment account for funds under A+B.) | 52857 | 2022-07-31
| 1. Management | 19336 | 2022-07-31
| 2. Operations | 9068 | 2022-07-31
| 3. Office services and supplies | 14714 | 2022-07-31
| 4. Auditing and consulting | 4385 | 2022-07-31
| 5. Knowledge dissemination | 5354 | 2022-07-31
| PROJECT (A+B+C) | 4044172.4255 | 2022-07-31
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | n/a
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | n/a
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | n/a

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Level | Steps Taken to Mitigate Risk
Financial risks
Ineffective Financial Management Systems | Low | Management arrangements were defined in the grant agreement between NIE and EE and subsequently implemented. Financial management procedures are effective and application continues to be monitored.
Delays in the disbursement of funds, procurement and institutional inefficiencies (e.g. lengthy approval processes) result in delayed delivery of equipment and other services and hence project implementation. | Low | Procedures for submission of disbursement requests by the EE and subsequent disbursement by the NIE have been established and implemented. The risk of delayed disbursement and associated cash flow problems within the EE have effectively been removed, subject to continued application of the procedures.
| Low | Disbursements by the EE to suppliers is done according to the EE's financial policy and procedures and no delays have been experienced. The risk is regarded to have been fully mitigated, subject to continued application of policy and procedures.
| High | Inefficiencies in the approval process of documents produced (e.g. design reports) within the EE and in application of the Government Procurement Act have resulted in project execution delays. The NIE continuously applies project management techniques to attempt to ensure that an agreed execution schedule is adhered to. The NIE has convinced the EE to request exemption from the requirement that tenders larger than N$ 35 million should be handled by the Central Procurement Board of Government. The risk of inefficiencies continues to exist and requires constant attention from the NIE.
Fluctuations in exchange rate (USD: NAD) which could affect the funding available for implementation and lead to budgetary constraints. | Low | The change in NAD-USD exchange rate from the time of budget compilation to receipt of Tranche 1 resulted in a loss of approximately 10% of the project budget in NAD. Since Tranche 1 comprises 82,5% of the total Project Grant, the exchange loss amounted to 8.3% of the total project budget. However, investment of Tranche 1, coupled to a change in project execution schedule that delayed spending of the bulk of the Project Activities Cost (A), has yielded a return on investment that has fully recovered the exchange rate loss on Tranche 1. It is anticipated that, when the remaining tranches are received, the exchange rate will favour the NAD compared to when the project budget was compiled. Exchange rate risk is currently low.
Ineffective management of project funds affects project implementation. | Low | A Project Accountant has been assigned to the Project Team to ensure appropriate management of project funds. Procurement complies with the NamWater procurement policy and procedures and with the directives of the Government Procurement Act. The NIE is provided with all tender documentation, including bid evaluations and award recommendations, all of which requires a "no objection" from the NIE before the EE can proceed. The NIE requires an annual external annual financial audit of the EE's financial statements for the project. The NIE provides the EE with a quarterly investment report, which also conveys the status of unutilised AF funds and the ROI. The NIE applies proper accounting of AF funds received.
Project risks
Failure to achieve milestones and provide deliverables on time | High | Despite the EE having appointed a dedicated project manager, cumbersome administrative and project processes have resulted in milestones not being achieved as scheduled. The NIE continuously applies project management techniques in an attempt to ensure that an agreed execution schedule is followed. Intense engagement between NIE and EE includes regular monitoring, assessment and project progress meetings.
Long distances to the sites result in logistically challenging implementation of project interventions. | Low | Various road safety measures are applied to staff doing site visits. A full-time resident engineer will be on site during construction. SCADA systems have been incorporated in plant design to allow transfer of plant operations data to the Regional Office and to the Head Office of the EE to cut down on travelling required for monitoring and control of plant operation.
Failure to involve adequate representation of vulnerable communities, particularly women, and therefore failure to create ownership of the project at the community level at project sites. | High | In Year 1 only two community meetings took place at each project site. The NIE regards this level of involvement to be inadequate. The NIE requested the EE to implement the public consultation/communication programme and the appointment of the Programme Public Relations Coordinator and the Gender and Social Expert as respectively proposed in the original project proposal (Environmental and Social Management Plan for Bethanie, Annexure 4, page 106) and in Table 38 on page 105.
Communities are incapable of managing and maintaining assets and structures built through the project. | Low | The aspect of communities being incapable of managing and maintaining project assets and infrastructure was wrongly identified as a risk in the project proposal. The assets and structures will be managed and maintained by the EE and not by the communities since it is the responsibility of the EE as eventual owner, manager and operator of the plants. Specific measures will, however, be put in place to prevent theft of solar panels which is common throughout Namibia.
Technology transfer with its associated uncertainties | Low | Technology transfer to communities on desalination and renewable energy is not applicable (see block above). Training of EE staff is attended to under scheduled project activities and students have taken part in plant design. The construction tender requires the contractors to accommodate students for transfer of knowledge obtaining hands-on experience.
Operation and maintenance of the plant | Low | Operation and maintenance requirements have been thoroughly considered in the design of the plants. Extensive training of future EE staff to be employed has been identified to be carried out during construction and commissioning of the plants.
Water quality | Low | The mitigation measures indicated below will be applied once plants are commissioned. Water will be sampled at specified intervals and sent to the NamWater laboratory for internal or external testing in terms of bacterial and chemical analysis. The results will be made available to the project team to attend to as part of the piloting of the plants. In the event of non-compliance, NamWater is obliged to terminate the operation of the plant and attend to all defect processes before operation may continue. In terms of the Water Resources Management Act, 2013 the specified water quality testing regime must be continued for the lifetime of the plant. The design of the pilot plants provides for more than adequate monitoring of water quality at various stages of the treatment train. The data will be transferred by SCADA to Windhoek to ensure prompt adjustment in case of deviation from required standards.
Sustainability of the plant | Medium | One of the objectives of the pilot plant is to test the sustainability of the plant. The sustainability will be reviewed during the pilot project and mitigation measures will be recommended to ensure sustainability.
Institutional risks
Low capacity, awareness and acceptance of the need to tackle the impacts of climate change among key stakeholders limit the support for the project and limit likelihood of project outputs being mainstreamed into plans and budgets. | Medium | Activities under a capacity building programme by the EE have been scheduled, to start in Year 2.
Poor coordination with other climate change projects in Namibia limits the potential to learn from and build on the experiences of climate change related projects. | Low | Sharing of information with other actors involved in the execution of climate change projects in Namibia is taking place continuously. This includes the Designated Authority, Government ministries and agencies, State-owned enterprises and local authorities.
Limited capacity of project partners to deliver project outputs. | Low | Engaged project partners all have experience in coordinating, implementing and delivering outputs in their relevant spheres of expertise, as demonstrated by the successful execution of plant design and environmental studies. Construction will be done by competent contractors selected by means of a thorough bid evaluation process.
Staff turnover within NamWater, Local Authorities, project partners, consultants and contractors may hamper progress. | Low | Institutional rather than individual relationships have been established between NamWater and Local Authorities and with project partners, limiting the negative impact of staff turnover.
Environmental risks
Non-compliance with the laws and other administrative orders of national and state government. | Low | Continuous ensurance that all laws and orders are complied with. Environmental clearance certificate and waste water disposal permit are still to be obtained after completion of EIA and ESMP. Groundwater abstraction permits exist.
Land acquisition and potential removal of local animals | Low | The draft EIA has found that the identified land is not a sensitive habitat and does not harbour priority species The land at Bethanie will be purchased and the land at Grünau will be leased by NamWater- this is in process. Proper protocol or consultation with relevant stakeholders or local authorities will be followed to acquire a piece of land if necessary - this is being done. No unintentional removal of local animals will be allowed, and if required consultation should be made with the Ministry of Environment and Tourism - no local animals have been identified that will be removed.
Law changes during Construction Phase | Low | Proper communications exist between NamWater and the various competent authorities (MET, MAWF etc.) to ensure that possible law changes are accommodated.
Land and vegetation clearing | Low | Clear only the vegetation absolutely necessary for the plant construction and proper operations - this has been specified in the draft ESMP. Only clear vegetation in phases, to minimise erosion and windblown dust - will be adhered to once construction starts. Save the topsoil so that it can be reused later during rehabilitation - - this has been specified in the draft ESMP. Any Protected trees that needs to be removed, needs a permit from MAWF before this can be done - will be adhered to once construction starts.. It has been established that appointment of a botanical specialist is not required. | Also in Env risks
Protection of natural systems | Low | Disturbance of vegetation and faunal communities and their habitats is kept to a minimum - will be adhered to once construction starts. Heavy construction vehicles should be kept out of the seasonal and ephemeral stream channels and the movement of construction vehicles should be limited where possible to the existing roads - will be adhered to once construction starts. There are no rivers/oshanas located on the project sites. All earthworks equipment operators shall be informed to cease operating immediately if any artefact is unearthed and to report the finding immediately to the Engineer / ECO and OTC, who in turn shall notify the National Heritage Council - will be adhered to once construction starts. | Also in Env risks
Pollution of soil and groundwater | Low | Design must include a proper lining to prevent leakage, and adequate capacity for heavy rainfall events - done. The Contractor shall ensure that all liquid fuels are stored in tanks or mobile bowsers with lids that are kept firmly shut - included in draft ESMP. All tanks and/or mobile bowsers shall be situated in a bunded area - will be adhered to once construction starts. The Contractor shall ensure that there is adequate fire-fighting equipment at the fuel storage areas - will be adhered to once construction starts. | Some duplicates
Access, traffic and haul roads | Low | The Contractor shall be held responsible for the control of all project related traffic, including that of his suppliers, in ensuring that vehicles associated with the project remain on designated routes and within the designated working times. Fencing to be installed and properly maintained. All addressed in draft ESMP. | Some duplicates
Solid waste management | Low | The Contractor shall provide sufficient number of rubbish bins with secured lids to prevent animal scavenging. No waste materials, including domestic, organic or construction wastes shall be burnt, dumped or buried on the site. All solid waste management actions have been addressed in draft ESMP.
Hazardous substances | Low | Risk management actions re hazardous substances have been addressed in the draft ESMP.
Trenches | Low | Trenches shall be demarcated appropriately and securely and regularly monitored to ensure that pedestrians/animals (and vehicular) access to these areas is strictly prohibited. Addressed in draft ESMP.
Erosion, water quality, and storm water | Low | The Contractor shall take all reasonable steps to prevent or remediate damage to the environment resulting from the Works in the form of erosion and sedimentation. The Contractor shall immediately remedy any situation that is or has the potential to result in soil erosion, water pollution and sedimentation from the works because of storm water flows. Storm water should be managed appropriately at the culvert crossing where the pipeline is planned to go through underneath the road, so that blockage does not occur. Addressed in draft ESMP.
Leakage of brine into soil and groundwater from ponds (poor design, damage of lining during cleaning, flooding during heavy rain) | Medium | Design must include a proper lining to prevent leakage, and adequate capacity for heavy rainfall events - done. Competence of operating staff employed at the plant - staff will be properly trained. Develop a proper and up to date Operation and Maintenance (O&M) manual of procedures with technical guidelines - scheduled for execution. Routine and proper environmental monitoring of all aspects of the plant - part of draft ESMP. Establish regular reporting procedures on maintenance - to be included in Operations and Maintenance Manuals when they are compiled. Undertake regular inspection and maintenance of all infrastructure to ensure in working order and to assess damaged/ deficient equipment, as per the Operation and Maintenance Manual - to be done once plants become operational. Brine peak flow monitoring by monitoring the incidence of overflow at pump stations leading to the ponds and accurate recording of flow metering - design provides instrumentation for monitoring complete treatment train. Monitoring of surrounding boreholes for potential contamination of surrounding sources or from the brine evaporation ponds - to be included in ESMP.
Non-sustainability of water sources being over used | High | The design provides for continuous monitoring of water balance. NamWater is required to utilise boreholes within their recommended abstraction rates and the aquifer within its long-term sustainable yield. Recording of pump and rest water levels is part of standard operating procedure - intervals will be specified in the Operations Manual. Regular assessment of sustainable utilisation to be specified in ESMP.
Health hazard to animals entering the pond area | Low | The design provides for proper fencing of the plants and ponds.
Collision of birds with wind turbines | Low | It has been established that wind power is not cost-effective at the two project sites compared to solar power. Only one small experimental wind turbine will be installed at each site, with low risk of bird collision.
Potential of birds being attracted to the ponds | Low | The water would be salty but with no hazardous chemicals. The draft ESIA has found that birds avoid water that is not suitable for drinking and that birds will thus not be impacted.
Fire or explosion of plant | Low | This is a very low risk. No fires or explosions have occurred at NamWater plants since the establishment of the entity approximately 20 years ago. Chemicals used at this plant are not flammable. Use of electrical circuit protection devices is standard, as is lightning protection.
Used equipment such as RO filter disposal | Low | Solid waste management actions have been identified under the draft ESMP. End-of-life plant components are included.
Improper reuse of the brine / salt-by-product | Low | Solid waste management actions have been identified under the draft ESMP. Salt from evaporation ponds is included.
Social risks
Human rights (e.g. water as a basic need) | Low | Avoid adverse impacts of the project on communities of Indigenous Peoples, or when avoidance is not possible, to minimize and/or compensate for such impacts. No communities of Indigenous People exist that can be negatively affected.
Land acquisition and potential removal of local people | Low | Addressed above under Environmental Risks.
A temporary loss of land and assets to the road servitude or areas to be occupied by project-related surface infrastructure - Indigenous People | Low | There are no communities of Indigenous People that will be affected. The land at Bethanie will be purchased from the Village Council and the land at Grünau will be leased from a commercial farmer.
A population influx (due to the presence of a construction workforce, as well as an influx of job-seekers into the area), with a possible concomitant increase in social pathologies and increased pressure on existing infrastructure and services. | Low | The recruitment policy used to employ people on the project must be fair and transparent. The intention of giving preferential employment to locals is clearly communicated, to discourage an influx of job-seekers from other areas - done. Inform local businesses about the expected influx of construction workers so that they could plan for extra demand - public consultations have taken place, businesses are aware of the project. Ensure that employment procedures/ policy of the contractor is communicated to local stakeholders, local farmers and Local Ward Councillor to be done, contractors still to be appointed. Have clear rules and regulations for access to the construction site to control loitering - addressed in construction tender documents. Consult with the local private security companies and Police to establish standard operating procedures for the control and removal of loiterers at the construction site -still to be done. Construction workers should be clearly identifiable by wearing proper construction uniforms displaying the logo of the construction company - still to be done. Construction workers must also be provided with identification tags - still to be done.
Disruption of access routes and daily movement patterns by the construction. Access, traffic and haul roads. |  | The items below have been addressed in the construction tender documents: Unauthorised access to the construction site must be prevented through appropriate fencing and security. When the construction period has ended the implementation of adequate rehabilitation measures to return the landscape and other changes to at least its original state. The Contractor shall be held responsible for the control of all project related traffic, including that of his suppliers, in ensuring that vehicles associated with the project remain on designated routes and within the designated working times.
Impacts on sense of place. Such impacts may arise because of the visual intrusion of project-related infrastructure, as well as noise and traffic impacts during construction. Visual disturbance from wind turbines and solar panels. | Low | Actions under risk management plans for visual impacts, traffic and transport, and noise and vibration have been identified in the draft ESMP.
Dust caused by the construction works and from movement of heavy equipment. During the construction phase, the local community and construction workers would be inconvenienced by the dust generated by the construction works. | Low | Actions under a risk management plan for air emissions in the draft ESMP include requirements relating to dust.
Noise and vibration due to the construction works and from movement of heavy equipment. Movement of heavy machinery on existing local roads may be one of the core problems for the local community during the construction phase. | Low | Actions under risk management plans for visual impacts, traffic and transport, and noise and vibration have been identified in the draft ESMP.
Improper ablution facilities provided | Low | The items below are still to be addressed: Adequate chemical toilets must be provided for all staff. Alternatively, existing ablution facilities on site can be utilised if available. The contractor camp: ensure the necessary ablution facilities are provided, with chemical toilets where such facilities are not available at commencement of construction. Chemical toilets must be empty, kept hygienically clean and secured, they must be emptied / serviced on a regular basis to prevent them overflowing. Adequate toilets and showers must be positioned at the right places.
Socio-cultural differences and conflicts between migrant workers and the local community. Single men predominately occupy the construction camps which could create social conflicts, usually because of cultural differences, alcohol abuse or being away from their wives or partners for extended periods of time. A possible reason for conflict would be the perception among locals that the outsiders are taking up jobs that could have gone to unemployed members of the local community. An influx of unemployed job seekers could also add to the potential for conflict. | Low | The items below are still to be addressed: Construction workers should be clearly identifiable. Overalls should have the logo of the construction company on it and construction workers should wear identification cards. Loitering of outsiders at either the construction site or at the construction camps should not be allowed. Local Police should be requested to assist in this regard. Align awareness campaigns with those of other organisations in the area (i.e. the Local Council). Control of access to construction camp. Cease construction activities before nightfall, if possible. Liaison with police, community policing forum and security stakeholders.
Various social pathologies, such as drug/ alcohol misuse, abuse of woman and children and incidences of sexually transmitted diseases (STI’s) may increase with the influx of job-seekers into the area. | Low | The items below have not yet been considered: Implement HIV/ AIDS, alcohol abuse, drug abuse, and domestic violence prevention and awareness campaigns in the communities. The contractors should ensure the health of its employees and their dependants by adopting rigorous health programmes, which should, at a minimum, include programmes to combat HIV/ AIDS and TB. The contractor should make HIV/ AIDS and STD awareness and prevention programmes a condition of contract for all suppliers and sub-contractors.
Crime is another social pathology that may increase. An inflow of construction workers and job seekers may also be accompanied by an increase in crime. Even if specific instances of crime are not because of the newcomers, they may still be ascribed to them by local communities. | Low | Some of the items below still have to be considered: Regarding safety and security, construction workers should be clearly identifiable - addressed elsewhere. Overalls should have the logo of the construction company on it and construction workers should wear identification cards - addressed elsewhere. The construction site to be fenced and access should be controlled. Loitering of outsiders at either the construction side or at the construction village should not be allowed. Local security companies and Police should be requested to assist in this regard - partly addressed elsewhere. Liaison structures are to be established with local security companies and police to monitor social changes during the construction phase. Liaison should also be established with existing crime control organisations. Control of access to construction camp - addressed elsewhere. Cease construction activities before nightfall, if possible.
Informal settlements. Once construction is concluded and the camp is vacated, it may be illegally occupied. | Low | The construction tender documents require the construction camp to be demolished.
Local economy opportunities and economic empowerment. The construction phase of the project will have temporary positive impacts on the local economy, creating opportunities for formal and informal businesses to benefit from the proposed project. | n/a | This is not a risk to be managed.
Training and skills transfer. The project will provide the opportunity for the local community to participate in training and skills transfer activities. | n/a | This is not a risk to be managed.
Reluctance of beneficiaries to use desalinated water. | Low | Ongoing community education is scheduled as a project activity.
Sustained future operation, management and maintenance of the plants | Medium | Has been considered in planning and design.
Risk of skill loss – skilled staff leaving NamWater employ during / after Pilot Phase (Sustainability) | Low | Broad participation in the project takes place within NamWater, thus the risk is reduced.
Possible unaffordable water tariff for desalinated water Collapse of the South African Rand (and the N$) | High | The following was agreed with NamWater: During the project the current bulk water tariffs will not be increased above the normal inflationary adjustments. After completion of the project, subsidisation of the bulk water tariff will be applied to ensure that the water remains affordable. During the EIA a survey was carried out to establish the magnitude of tariff increases that could be afforded.
Theft of solar panels and other materials | Medium | Site to be fenced and access should be controlled - fencing addressed in design; access control to NamWater operations sites is standard. The remainder of the items are to be attended to once construction starts: Loitering of outsiders at either the construction side or at the construction village should not be allowed. Local security companies and Police should be requested to assist in this regard - to be attended to. Liaison structures are to be established with local security companies and police to monitor social changes during the construction phase. Liaison should also be established with existing crime control organisations.
Visual impact of the plant, solar panels and wind turbine infrastructure. | Low | At Grunau the desalination plant and evaporation ponds will be located over 1km from the nearest households and visual and landscape impacts are unlikely to be significant. At Bethanie the plant will be within the village - reflection from solar panels will be contained by means of screens if the need is identified during/after construction.
Noise impacts form the plant and wind turbines | Low | It has been established that wind power is not cost-effective at the two project sites compared to solar power. Only one small experimental wind turbine will be installed at each site, noise generation will be negligible. The pumps and motors will generate very little noise.
Fire or explosion of plant | Low | Already addressed under environmental risks. This is a very low risk. No fires or explosions have occurred at NamWater plants since the establishment of the entity approximately 20 years ago. Chemicals used at this plant are not flammable. Use of electrical circuit protection devices is standard, as is lightning protection.
Plant down-time (no water provision) | Low | Water will be stored in existing / additional reservoirs to have back-up water for a minimum of 48h so that the problem can be fixed within that time frame. If the problem persists after the 48h, water provision will temporarily switch back to the old water scheme standards.
Water quality changes (+) The project is aimed at improving the quality of water for NW to comply with the new water quality regulations of the Water Resources Management Act of 2013 | Low | Already addressed under project risks.
Local employment and job opportunities. The construction phase of the project will have a positive impact on the local labour market. A positive impact on continued permanent employment will be probable due to the proposed project as the long-term economic viability of the plant will be possible, following the plant expansion. (+) | n/a | This is not a risk to be managed.
Local economy opportunities and economic empowerment. The operational phase of the project will have positive impacts on the local economy, creating opportunities for formal and informal businesses to benefit from the proposed project. (+) | n/a | This is not a risk to be managed.
Improved health. The project will provide the local community with better quality water and this will have a positive impact on the health of the people. (+) | n/a | This is not a risk to be managed.
Savings on current expenses. Due to the better-quality water, medical expenses would be less (dentists) and less frequent need to replace water usage equipment (Geysers, kettles etc.). (+) | n/a | This is not a risk to be managed.
Self-esteem upliftment. With cleaner teeth comes higher self-esteem, less likelihood of depression and social betterment regarding relationships and even job performance. (+) | n/a | This is not a risk to be managed.
Training and skills transfer. The project will provide the opportunity for the local community to participate in training and skills transfer activities. (+) | n/a | This is not a risk to be managed.
Critical Risks Affecting Progress and/or Successful Project Completion (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress or successful completion of project
Identified Risk | Current Level | Steps Identified/Executed to Mitigate Risk
Availability of land for evaporation ponds: Delays in obtaining land rights may lead to project execution delays. | High | An offer by Bethanie Village Council for the sale of land has been accepted by NamWater (outside Project Grant). At Grünau the draft lease agreement between land owner and NamWater is still to be finalised and has already caused some project delay.
Staff training level: The plant may not be optimally operated and maintained. | Low | 1. Select and appoint staff to fill positions identified by Eng. Cons. 2. Identify specific training courses 3. Compile training programme 4. Train staff (including backup staff) 5. Locate staff correctly Above steps are scheduled for execution in Project Year 2.
Staff availability (1. Too few staff members for all shifts, 2. Staff not local, based too far away, long travel time): The plant is not optionally operated and maintained. | Low | 1. Appoint 2 x operators 2. (a) Identify correct base for maintenance staff (b) Locate staff to base(s) Above steps are scheduled for execution in Project Year 2.
Durability of plant materials: Materials are not sufficiently robust to operate in a harsh chemical and natural environment. | Medium | Specify appropriate robust material in Bill of Quantities (BoQ). This has been done in compilation of construction tender documents.
Borehole control: Poor coordination of borehole pumps and plant operation may cause plant failure. | Medium | 1. Identify appropriate borehole automation and control logic 2. Include appropriate borehole automation and control logic in design These steps have been executed in compilation of construction tender documents.
Borehole water quality (Quality of borehole water may vary with time in terms of: (1. Silt content 2. Chemical quality): Pressure is put on plant due to deterioration in quality. | High | 1. (a) Develop management plan for boreholes (b) Continuously apply management plan 2. (a) Monitor borehole water quality regularly (b) Apply appropriate operational adjustments Step 1 (a) to be included in final ESMP due 11 October 2019. Rest of steps to be implemented when plants become operational at beginning of project Year 3.
Insufficient or unsuitable communication facilities or protocols will delay communication of plant status to Keetmanshoop and Windhoek: 1. Remedial action to keep plant operating at the required levels may be delayed. 2. Record of plant performance may be incomplete | Medium | 1. Identify required facilities and protocols 2. Include SCADA for remote monitoring and some control in design 3. Ensure enabled on-site operations teams are in place 4. Ensure continuous functionality of facilities Steps 1 and 2 have been executed in final design and compilation of construction tender documents. Steps 3 and 4 to be executed once plants are operational as from Project Year 3.
Specialized spares may not be available when required, leading to plant failure: Long lead time on specialized spares affect availability | Low | 1. Where possible, design for the use of standardised and commonly available equipment that is simple to install, operate and maintain (i.e. pumps, valves, piping) 2. Ensure critical spares are kept in storage where feasible 3. Ensure contracts are in place for the procurement of specialised equipment that is not kept in storage Step 1 has been executed in final design and compilation of construction tender documents. Steps 2 and 3 to be executed once plants are operational as from Project Year 3.
Irregular calibration of monitoring equipment cause incorrect readings: Incorrect monitoring results compromise effective plant operation and collection of piloting results | Low | 1. Train operations staff to do calibration. 2. Ensure that materials are on site for calibration 3. Establish and apply calibration schedule. 4. Where practical, stock spare instrumentation that were calibrated off-site. Step 1 has been executed in final design and compilation of construction tender documents. Steps 2 and 3 to be executed once plants are operational as from Project Year 3.
Flooding of the plant due to burst pipes, water leakages and rain is a threat to plant infrastructure and human life | Low | 1. Ensure insulation protection (IP) ratings are adequate where equipment is exposed. 2. Install adequate overflows, drainage, water proofing of flooring and protection of electrical equipment. 3. Compile and activate emergency plant shutdown action plans. Steps 1 and 2 have been executed in final design and compilation of construction tender documents. Step 3 to be executed once plants are operational as from Project Year 3.
Chemical safety: Improper handling and storage of hazardous chemicals. | Low | 1. Construct proper handling and storage facilities for hazardous chemical 2. Train staff 3. Ensure staff remain adequately trained Step 1 has been executed in final design and compilation of construction tender documents. Steps 2 and 3 to be executed once plants are operational as from Project Year 3.
Vandalism and theft due to insufficient security measures: 1. Delays in construction 2. Plant cannot operate | Medium | 1. Install reasonable security 2. Schedule meetings with beneficiaries on detrimental effect of theft and vandalism on continuous water supply 3. Conduct the meetings with beneficiaries Step 1 has been executed in final design and compilation of construction tender documents. Steps 2 and 3 to be executed once appointed contractors occupy construction sites.
Bethanie Village Council may continue to use the boreholes that it operates and provide a cheaper (but poorer quality) supply (to 75% of the population): The capacity of the plant may be under-utilised, amounting to an over-designed plant. The information to be collected on its operation, management and maintenance will not be realistic. | High | When the Water Resources Management Act comes into force, the Village Council will be prohibited to provide their own poor quality water. No steps currently required.
Dissatisfaction of beneficiaries at Grünau: Due to groundwater resource limitations, the plant will only supply the same volume as before, which is less than the realistic demand: The beneficiaries may be dissatisfied that the project does not supply them with more water. | Medium | Beneficiaries to be sensitised: 1. That availability of water will remain limited due to groundwater resource capacity 2. The objective of the project is to test the feasibility of groundwater desalination and that the community will benefit by receiving water of good quality. Sensitisation of beneficiaries started during project formulation and is ongoing.
Limited employment opportunities exist for local population in construction and operation/maintenance of the plants: Possible negative impact in terms of community perceptions | Low | 1. Early communication with communities on available job opportunities 2. Contractors to be required to implement a local employment plan Step 1 not yet implemented, but due before start of construction in November 2019. Step 2 is a requirement under the construction tender.
Due to project implementation the cost of bulk water supply will increase: The bulk water supply tariffs may make the water unaffordable to the communities . | Medium | 1. Obtain an undertaking from the EE that during project execution tariffs will remain unchanged, except for normal inflationary adjustment. 2.Sensitise the EE on the need for post-project tariffs to remain affordable by means of adequate subsidisation. Steps 1 and 2 have been implemented.
Inefficient procurement of construction services may occur if the tender amount(s) exceed the threshold for NamWater own handling of the tender: Involvement of the Central Procurement Board may lead to a project delay. | Medium | Obtain exemption from complying with procurement legislation on ground of foreign grant (if required). Procedure to obtain exemption has been investigated.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
All mitigation steps for the risks identified above and scheduled for execution in Project Year 1 have been executed. All mitigation measures undertaken have been successful in reducing the relevant risks.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1] | Environmental Impact Assessment (EIA) to be completed before start of construction. | Draft EIA and draft ESMP completed. | Consult public on EIA and ESMP - 2 to 6 September 2019.
Develop final EIA and ESMP - 9 to 20 September 2019.
Submit final EIA and ESMP to Ministry of Environment and Tourism, provide clarifications, obtain environmental clearance certificate - 24 September to 11 October 2019.
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] Annexures 6 & 7, tables 5 & 6 of project proposal | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] Note: Based on environmental scoping and not on full EIA | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
2 - Access and equity |  |  | The cost of water supply at the two project sites will significantly increase. Inconsiderate upward adjustment of tariffs may make water unaffordable. | 1. Obtain an undertaking from the EE that during project execution tariffs will remain unchanged, except for normal inflationary adjustment. 2.Sensitise the EE on the need for post-project tariffs to remain affordable by means of adequate subsidisation. | During the project the NIE will monitor tariff adjustments for bulk and distribution water supply. Should unrealistic increases be imposed, the NIE will engage the relevant authorities. | n/a | n/a | n/a | n/a
3 – Marginalized and vulnerable Groups |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
4 – Human rights |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
5 – Gender equality and women’s empowerment |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
6 – Core labour rights |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
7 – Indigenous peoples |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
8 – Involuntary resettlement |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
9 – Protection of natural habitats |  |  | No threats were identified after final design. | n/a | n/a | n/a | n/a | n/a | n/a
10 – Conservation of biological diversity |  |  | Final design and EIA indicated that the project will not cause any harm to biological diversity. | n/a | n/a | n/a | n/a | n/a | n/a
11 – Climate change |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
12 – Pollution prevention and resource efficiency |  |  | Possible leakage of brine into soil | The final design provides for construction of sealed evaporation ponds to prevent leakage. Plan and implement a robust monitoring schedule to identify potential leakages from ponds and pipes. | Indicator =Number of leaks. Target = None. | No baseline | The final design provides for construction of sealed evaporation ponds to prevent leakage. | Possible temporary contamination of soil above groundwater level. | Comply with applicable environmental and health legislation
13 – Public health |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
14 – Physical and cultural heritage |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
15 – Lands and soil conservation |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes (Refer to worksheet Risk Assessment)
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | n/a
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | As outlined in the worksheet Risk Assessment
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | As outlined in the worksheet Risk Assessment
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | n/a
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11] |  | n/a
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
No USPs
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None received during the reporting period.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | No, only numbers of male and female beneficiaries at each of the two project sites.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes, there are indicators at outcome level.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Women employees to gain technical knowledge on design and construction of rural desalination plants using renewable power and membrane technology. | Outcome 2: Knowledge of the design, construction and installation of hybrid renewable energy plants to power small desalination plants. | Indicator 2.2: Number of women and children participating in the development and installation of the plants. (Note: Error - Children are not applicable) | Baseline 2.2: Zero | Target 2.2: No target indicated in results framework. | Indicator 2.2: Good EE staff : Project management and execution: 9 male (75%), 3 female (25%) In training/capacity building: 2 male (25%) 6 female (75%) Engineering consultant staff: 3 male (60%) 3 female (40%) Environmental consultant staff: 4 male (44%) 5 female (56%)
A gender balanced group of tertiary institution students to gain hand-on experience in all aspects of plant establishment. | Outcome 3: Knowledge and understanding of operating the plants and of adjusting the treatment train to achieve required quality of water. | Indicator 3.4: Involvement of a gender balanced group of tertiary institution students in all aspects of plant establishment to gain hands-on experience. | Baseline 2.2: Zero | Target 3.4: 5 engineering university students; 2 females and 1 male for Bethanie; 1 female and 1 male for Grünau. | Indicator 3.4: Not applicable yet. Student involvement will be during construction and operation, which is still to start. The requirement to involve students in plant establishment has been included in the construction tender documents.
An equal number of male and female students to be exposed on site to gain awareness of climate change, the objectives, principles and social effects of the project. | Outcome 4.4: Greater awareness among students of increasing climate change resilience through desalination and renewable energy. | Indicator 4.4: Number of tertiary social and environmental students who went on site visits, were involved in surveys and who became aware of and understand the objectives of the project, the principles of desalination, renewable energy, and the associated social effects on the beneficiaries. | Baseline 2.2: Zero | Target 4.4: 6 students at Bethanie and 4 at Grünau, equal number of males and females at each site. | Indicator 4.4: Good. First activity scheduled at start of construction. Students have been identified. NUST students: Male 2 (33%) Female 4 (67%) UNAM students: Male 3 (60%) Female 2 (40%) All students: Male 5 (45%) Female 6 (65%) Total 11
Reduction in skin and scalp afflictions among mothers and their children due to improvement of water quality. | Outcome 5.3: Skin and scalp afflictions such as itching due to hardness of water is reduced. | Indicator 5.3: Percentage of sample population consisting of mothers and their children complaining of afflictions ascribed to water supplied. | Baseline 5.3: To be established by survey of sample population at project inception. | Target 5.3: Complaints by sample population reduced by 50% after first year of piloting. | Indicator 4.5: Poor Survey did not include establishment of baseline - still to be done.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
Acquisition and dissemination of knowledge is the prime objective of the project. Non-discrimination of women is a guiding principle in selection of trainees to acquire knowledge on desalination and renewable energy and in qualified staff involved in project execution.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | 1. Contractual agreement between the NIE and the EE stipulates that: "Where the environmental, social and gender assessment identifies environmental, social or gender risks, produce an environmental and social management plan that accompanies the assessment and that identifies those measures necessary to avoid, minimise, or mitigate the potential environmental, social and gender risks" 2. Project activities 3.4 and 4.5 indicate the requirement for gender balance 3. DRFN's ESP&G policy/manual has been made publicly available on its website 4. The NIE requested the EE to implement the public consultation/communication programme and the appointment of the Programme Public Relations Coordinator and the Gender and Social Expert as respectively proposed in the original project proposal (Environmental and Social Management Plan for Bethanie, Annexure 4, page 106) and in Table 38 on page 105.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | 1. Contractual agreement between the NIE and the EE stipulates that: "Where the environmental, social and gender assessment identifies environmental, social or gender risks, produce an environmental and social management plan that accompanies the assessment and that identifies those measures necessary to avoid, minimise, or mitigate the potential environmental, social and gender risks" 2. Project indicators 2.2, 3.4, 4.4 and 5.3 have gender-responsive elements. Progress with achievement of the indicator targets is indicated in Section 1 of this sheet and in the sheet "Project Indicators".
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | Partially. Arrangements for women's empowerment pertaining to EE qualified staff and trainees taking part in project execution are good. Same applies to EE staff attending training course. Arrangements pertaining to involvement of female beneficiaries in assembly of social data is unsatisfactory.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | The NIE requested the EE to implement the public consultation/communication programme and the appointment of the Programme Public Relations Coordinator and the Gender and Social Expert as respectively proposed in the original project proposal (Environmental and Social Management Plan for Bethanie, Annexure 4, page 106) and in Table 38 on page 105.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None received during the reporting period |  | n/a
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Key Milestones |  | Scheduling |  | Progress to Date | Rating
NIE rating | Project preparation meetings with NamWater |  | 2017-12-07 |  | Completed 12 February 2918 | U
| AF-DRFN Grant Agreement |  | 2018-01-30 |  | Completed 15 January 2018 | HS
| Proposed DRFN-NamWater Grant Agreement |  | 2018-01-30 |  | Completed 30 January 2018 | HS
| Signed DRFN-NamWater Grant Agreement |  | 2018-02-28 |  | Completed 23 May 2018 | U
| Investment of Tranche 1 |  | 2018-02-25 |  | Completed 15 February 2018 | S
| Inception meeting/start of project |  | End March 2018 |  | Completed end July 2018 | U
| Submission of Project Inception Report to AF |  | End August 2018 |  | Submitted 16 August 2018 | HS
| Obtain approval from AF for revised execution and disbursement schedule |  | Not scheduled |  | Approved 7 January 2019 | S
| Monitoring and control of project execution |  | Continuous |  | Ongoing | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Dr Martin B Schneider
| Email: | martin.schneider@drfn.org.na
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Based on 1 to 4 below, overall project implementation is rated as Satisfactory. 1. Project inception was later than initially planned, but still within the directives set by the AF (i.e. within 6 months of receipt of Tranche 1). The reason for late inception was due to the EE having to change/finalise their execution strategy. 2. Since the time that the execution and disbursement schedule was revised in January 2019 (due to late start of project), project execution remained on schedule. 3. Expenditure under Budget A amounted to only 1% of the relevant amount of Tranche 1. The reason is that Tranche 1 is to fund both Year 1 and Year 2 activities, with the latter comprising construction of the plants. Construction accounts for the bulk of project costs. However, expenditure in Year 1 is in line with projections. 4. At the Inception Workshop it was identified that the Project Results Framework had shortcomings relating to measurable indicators and thus realistic targets. The framework was subsequently discussed by the NIE and EE, and changes were identified that would not compromise measurement of the achievement of project outcomes and would provide a more sensible way of measuring the degree of success achieved by the project. However, the AF was not approached for approval of such changes as per the directives contained in ANNEX 7: PROJECT/PROGRAMME IMPLEMENTATION Approved October 2017 and thus the Project Results Framework remains as in the Project Proposal.
| Key Milestones |  | Scheduling |  | Progress to Date | Rating
EE rating | Appointment of engineering consultant |  | 2018-07-02 |  | 2018-08-17 | S
| Concept design of plants |  | 2018-10-31 |  | 2018-11-12 | S
| Preliminary design of plants |  | 2019-06-15 |  | 2019-06-10 | S
| Detail design of plants |  | 2019-07-15 |  | 2019-08-02 | S
| Compilation and issue of RFP for plant construction |  | 2019-08-14 |  | 2019-08-15 | S
| Appointment of environmental engineering consultant |  | 2019-04-02 |  | 2019-05-06 | U
| Draft ESIA for plants |  | 2019-08-09 |  | 2019-08-17 | S
| Draft ESMP for plants |  | 2019-08-09 |  | 2019-08-17 | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | R Likando
| Email: | likandor@namwater.com.na
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Based on 1 to 4 below, overall project execution is rated as Satisfactory. 1. Due to the nature of the project, no targets to be achieved in terms of the results framework arise in Project Year 1. 2. Critical risks are listed and described in the worksheet Risk Assessment. 3. No MTR carried out - this is PPR1 4. The overall rating is S.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc.…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective 1: Acquire knowledge and skills on how to effectively and efficiently desalinate poor quality groundwater on a small scale using RO technology and hybrid renewable energy technology that can be applied to improve the resilience of rural communities against climate change
Outcome 1: Knowledge of the design, construction and installation of small desalination plants using RO technology. | Indicator 1.1: The technical knowledge to plan, design, and construct small-scale desalination plants using RO technology. Indicator 1.2: Number of plants design prepared. | Baseline 1: The existing NamWater knowledge relates to experimental micro-plants using RO technology conducted at (Epukiro Post 3 and Bethanie). No information about the membrane technology operating on renewable resource exists. CuveWaters international project team installed four different types of small-scale groundwater thermal desalination plants in the Omusati Region at Amarika and Akutsima but not operated with renewable energy. | Progress 1: Target 1 is being pursued and will be achieved when construction is complete. Acquisition of the following knowledge under Indicator 1.1 (Target 1.1) has been demonstrated for both plants: 1. Planning 2. Concept design 3. Preliminary design 3. Construction specifications 4. Construction procurement documentation (draft) 10 staff members, 9 from NamWater, 1 from Department of Water Affairs (40% male, 60% female) attended a 4-day course from 1-4 April 2019 on "Desalination with Solar Energy" offered by the European Desalination Society. | Target 1: Demonstration by NamWater that the technical knowledge has been acquired by establishing 2 small-scale desalination plants using RO technology.
Outcome 2: Knowledge of the design, construction and installation of hybrid renewable energy plants to power small desalination plants. | Indicator 2.1: The technical knowledge to plan, design, and install hybrid renewable energy (sun/wind) systems to power small-scale desalination plants. | Baseline 2: The existing NamWater knowledge relates to application of photovoltaics for powering communication equipment and borehole pumps. | Progress 2: Target 2 is being pursued and will only be achieved when construction is complete. Acquisition of the following knowledge under Indicator 1.1 has been demonstrated for both plants: 1. Planning 2. Concept design 3. Preliminary design 3. Construction specifications 4. Construction procurement documentation (draft) | Target 2: Demonstration by NamWater that the technical knowledge has been acquired by establishing two hybrid renewable energy (sun/wind) systems to power small-scale desalination plants.
Concept design, preliminary design and final design completed for plants at Grünau and at Bethanie. Draft construction procurement documentation completed for plants at Grünau and at Bethanie.
| Indicator 2.2: Number of women and children participation in the development and installation of the plants. |  | Indicator 2.2: EE staff : Project management and execution: 9 male (75%), 3 female (25%) In training/capacity building: 2 male (25%) 6 female (75%) Engineering consultant staff: 3 male (60%) 3 female (40%) Environmental consultant team: 4 male (44%) 5 female (56%)
| Indicator 2.3: Number of renewable energy plants units installed. |  | No plants have yet been installed under Indicator 2.3.
Outcome 3: Knowledge and understanding of operating the plants and of adjusting the treatment train to achieve required quality of water. | Indicator 3.1: Sufficient knowledge to commission the small-scale RO desalination plants powered by hybrid renewable energy (sun/wind) systems referred to in Indicator 1.1 above and to execute a reliability run of 3 months after commissioning. | Baseline 3: The existing NamWater knowledge relates to experimental micro-plants using RO technology. | Progress 3.1: No progress towards achieving Target 3.1 - commissioning is to take place after construction, which is scheduled to be completed at end of Project Year 2 | Target 3.1: 2 commissioned desalination plants, powered by hybrid renewable energy.
| Indicator 3.2: Trained operations and maintenance staff. |  | Progress 3.2: Little progress towards achieving Target 3.2 - training is scheduled to take place after construction and commissioning. Requirement for training has been specified in construction tender. | Target 3.2: 5 trained water operators and 1 trained Level 2 water artisan.
| Indicator 3.3: Training, operations and maintenance manuals. |  | Progress 3.3: Little progress towards achieving Target 3.3 - compilation of manuals is scheduled for execution towards end of construction. Specification for manuals has been included in construction tender. | Target 3.3: 1 manual each for training, operations and maintenance.
| Indicator 3.4: Involvement of a gender balanced group of tertiary institution students in all aspects of plant establishment to gain hands-on experience. |  | Progress 3.4: The requirement to involve students in plant establishment has been included in the construction tender documents. | Target 3.4: 5 engineering university students; 2 females and 1 male for Bethanie; 1 female and 1 male for Grünau.
Outcome 4.1: Knowledge of how to optimize the design, construction, operation and maintenance of small RO desalination plants using hybrid power supplies. | Indicator 4.1: 2 optimised desalination plants, powered by hybrid renewable energy plants, yielding water of good quality in sufficient quantities. Calculated cost of bulk water supplied, based on capital and operating cost, broken down to the level of RO plants, power plants and existing infrastructure. A comprehensive set of information. Number of tertiary social and environmental students who went on site visits, and who became aware of and understand the objectives of the project, the principles of desalination, renewable energy, and the associated social effects on the beneficiaries. | Baseline 4.1: The existing NamWater knowledge relates to experimental micro-plants using RO technology. No similar or comparable plants exist. Water presently supplied does not comply with the Namibian quality standards for drinking water. | Progress 4.1: No progress - operation is scheduled to start after commissioning. | Target 4.1: Bulk water delivered from terminal reservoir: • Chemical quality: o Daily measured conductivity compliant with water quality standards for 80% of tests during first year; thereafter compliant for 100% of tests
o Chemical analysis done in Windhoek compliant with water quality standards for 80% of tests during first 6 months, 90% of tests for second 6 months, for next year 100% compliant; analysis initially once per week, with period to be extended as dictated by results.
• Microbiological quality: o Free chlorine daily tested on site always to comply with Standard o Microbiological analysis in Windhoek compliant with water quality standards for 100% of tests; analysis initially once per fortnight, with period to be extended as dictated by results.
• Volume: o Average supply capacity of 460 m3/day at Bethanie and 100 m3/day at Grünau • Continuity of supply: o No interruption of water supply, except for reduction in supply for 24 hours with advanced warning of 2 days in case of major maintenance
Outcome 4.2: Information on the cost of bulk water supply from the two project plants. | Indicator 4.2: Calculated cost of bulk water supplied, based on capital, operational and maintenance cost, broken down to the level of RO plants, power plants and existing infrastructure. | Baseline 4.2: No desalinated water is currently supplied at the two sites, thus there is no baseline. | Progress 4.2: No progress - scheduled to be calculated at ends of first year and second year of plant operation. | Target 4.2: Calculated at ends of first year and second year of piloting, as well as for the two-year period. Total unit cost to be less than 30% of what it would be to import the same volume of good quality water from a reliable source.
Outcome 4.3: Information on the technical and financial feasibility and viability of small-scale RO desalination plants powered by hybrid renewable energy (sun/wind) systems. | Indicator 4.3: A comprehensive set of information. | Baseline 4.3 The existing NamWater information relates to experimental micro-plants using RO technology. No similar or comparable plants exist. | Progress 4.3: Very little progress towards achieving Target 4.3, which is scheduled for completion towards end of project period - design information has been generated, to be used in report. | Target 4.3: A comprehensive report describing the technical and financial feasibility and viability of small-scale RO desalination plants powered by hybrid renewable energy (sun/wind) systems.
Outcome 4.4: Greater awareness among students of increasing climate change resilience through desalination and renewable energy. | Indicator 4.4: Number of tertiary social and environmental students who went on site visits, were involved in surveys and who became aware of and understand the objectives of the project, the principles of desalination, renewable energy, and the associated social effects on the beneficiaries. | Baseline 4.4: No awareness based on practical exposure. | Progress 4.4: First activity scheduled at start of construction. Students have been identified. NUST students: Male 2 (33%) Female 4 (67%) UNAM students: Male 3 (60%) Female 2 (40%) All students: Male 5 (45%) Female 6 (65%) | Target 4.4: 6 students at Bethanie and 4 at Grünau, equal number of males and females at each site.
Objective 2: Positively impact the lives of vulnerable individuals and communities at two project sites, by supplying good quality water, raising awareness of the effects of climate change, promoting judicious use of water and explaining the need for water tariffs.
Outcome 5: Improvement in health of the beneficiaries.
Outcome 5.1: Development of fluorosis in children is halted. | Indicator 5.1: Percentage of children residing at Bethanie and Grünau under the age of 6 months indicated with fluorosis as from end of first year of piloting. | Baseline 5.1: To be established from records at the local clinics. | Progress 5.1: No progress - scheduled for execution at end of first year of supplying desalinated water. (Indicator is impractical). | Target 5.1: Baseline percentage of children under the age of 6 months indicated with fluorosis reduced by 50% in the first 6 months of piloting, and by 100% thereafter.
Outcome 5.2: Gastro-enteritis is reduced, especially among children. | Indicator 5.2: Percentage of beneficiaries at Bethanie and Grünau diagnosed with gastro-enteritis as from inception of piloting. | Baseline 5.2: To be established from records at the local clinics. | Progress 5.2: No progress - scheduled for execution at end of first year of supplying desalinated water. | Target 5.2: Baseline percentage of beneficiaries at Bethanie and Grünau diagnosed with gastro-enteritis reduced by 50% by end of project period.
Outcome 5.3: Skin and scalp afflictions such as itching due to hardness of water is reduced. | Indicator 5.3: Percentage of sample population consisting of mothers and their children complaining of afflictions ascribed to water supplied. | Baseline 5.3: To be established by survey of sample population at project inception. | Progress 5.3: Survey did not include establishment of baseline - still to be done. | Target 5.3: Complaints by sample population reduced by 50% after first year of piloting.
Outcome 5.4: Increase in resilience of beneficiaries to further deterioration of groundwater quality due to climate change. | Indicator 5.4: Correlation between deteriorating groundwater quality and health conditions addressed under Outcome 1 above. | Target 5.4: Targets described relevant to Outcome 1 above. | Progress 5.4: No progress - treated water not yet supplied. | Target 5.4: Zero correlation between groundwater quality deterioration and non-achievement of targets relevant to Outcome 1 above.
Objective 3: Communicate the acquired knowledge and skills to stakeholders in the water sector and thereby promote the mainstreaming of such small-scale desalination technology and systems in the country.
Outcome 6: Awareness by beneficiaries of climate change effects, understanding of the project intervention, acceptance of responsibility to use water judiciously, and the need to pay water tariffs. | Indicator 6.1: Percentage of school learners and teachers at Bethanie and Grünau reached by means of visits to schools to create awareness of climate change effects and the project intervention, and to convey the need use water judiciously and why water tariffs are necessary. | Baseline 6.1: Social stakeholder consultations and engagements were held at Bethanie and Grünau during project formulation; 1 each with officials and general public at each of the project sites. Schools were not visited. | Progress 6.1: No progress - scheduled for execution during construction. | Target 6.1: 80% of all school learners and teachers at the three schools at Bethanie and the school at Grünau to attend visits to schools.
| Indicator 6.2: Number of interactive public meetings at Bethanie and Grünau to create awareness by beneficiaries of climate change effects, an understanding of the project intervention, acceptance of responsibility to use water judiciously, and the need to pay water tariffs. | Baseline 6.2: As above. | Progress 6.2: Two meetings held before construction - 10 June and 22 July 2019. These are in addition to the target meetings. | Target 6.2: 2 interactive public meetings per annum at each of Bethanie and Grünau.
| Indicator 6.3: Number of meetings with community leaders and local officials at Bethanie and Grünau to further strengthen their awareness of climate change effects, an understanding of the project intervention, acceptance of responsibility to use water judiciously, and the need to pay water tariffs; this includes site visits to show progress with plant establishment and subsequently the operation of the plants. | Baseline 6.3: As above. | Progress 6.3: Two meetings held before construction - 11 June and 23 July 2019. These are in addition to the target meetings. | Target 6.3: 2 meetings per annum at each of Bethanie and Grünau
| Indicator 6.4: Distribution of appropriate and site-specific information and learning material to school learners and teachers, and to adults. | Baseline No appropriate material is yet available at the project sites. | Progress 6.4: No progress - scheduled early in Project Year 2. | Target 6.4.1: 1 printed school-level information folder provided to each school learner attending the school visits
Target 6.4.2: 20 printed school-level information folders provided to each school teacher
Target 6.4.3: 1 printed information folder provided to each attendee of public meetings and meetings with officials
Target 6.4.4: 100 printed information folders provided to each clinic and church at the project sites for distribution to the public.
Outcome 7: Stakeholders at regional and national level who are informed of the project results, including the viability and feasibility of small-scale desalination plants powered by hybrid renewable energy as an alternative to importing good quality water over long distances. | Indicator 7.1: Information sharing events with regional and national decision and policy makers in the water supply and environmental sectors. | Baseline 7: No project results are available prior to the start of project execution. | Progress 7.1: No progress - scheduled for second half of project period. | Target 7.1: 1 information sharing event, combined with visits to project sites, during the second half of the project period.
| Indicator 7.2: Technical information sharing events with government officials, consultants, university staff, civil society members active in the water supply and environmental sectors. |  | Progress 7.2.1: No progress - scheduled during construction and during piloting. | Target 7.2.1: 1 information sharing event combined with visits to project sites, during the second half of the project period.
|  |  | Progress 7.2.2: No progress - scheduled in the last year of the project period. | Target 7.2.2: 1 information sharing event presented in Windhoek in the last year of the project period.
| Indicator 7.3: Provision of project information throughout the project period by means of electronic and print media, and presentation of the project at national/international conferences or meetings. |  | Progress 7.3.1: No progress - first programme scheduled at start of construction. | Target 7.3.1: 2 current affairs radio and TV programmes each, one during construction and the other during the piloting period.
|  |  | Progress 7.3.2: Continuous updating. | Target 7.3.2: Websites of EE and NIE continuously updated with project information.
|  |  | Progress 7.3.3: No progress - scheduled for last year of project period. | Target 7.3.3: 1 final project report published on the EE website in last year of project period.
|  |  | Progress 7.2.4: No progress - scheduled for second half of final project year. | Target 7.3.4:1 1 presentation of project at a water conference.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Negative issues relating to EE: Cumbersome administrative and project processes; insufficient commitment to gender related project activities; Government Procurement Policy negatively affects execution schedules on various levels; insufficient stakeholder engagement; insufficient engagement of direct beneficiaries (also see "Risk Register"); lack of transparency on own policies such as on "ethics and business conduct"; too little done relating to publicising the project, especially against the background of having a full PR department available; over-commitment to projects by technical team members due to drought emergency Positive issues relating to EE: Project has full support of CEO and top management; good and easy access to project manager and team members Lessons learned: It is imperative that the technical team members of the EE should be involved in compilation of the project proposal in order that the execution strategy be agreed to beforehand (not done); it is essential that a signed agreement be established between the NIE and the EE to regulate execution of the project (done).
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Project inception and execution delays were fully described in a report submitted to the AF on 19 February 2019. In summary the following: The approved project proposal indicated April 2018 as the intended start date for project execution. It was considered highly desirable that the engineering consultant, who would be one of the most important members of the project team, should also attend the project inception workshop. The implication was that the project inception workshop would be postponed until the consultant had been appointed. However, due to the cumbersome Government procurement process that the EE (as a State-owned enterprise) was now for the first time required to apply, the consultant could not be appointed in time for an inception workshop to be held within the time directives of the AF. The inception workshop thus took place on 16/17 July 2018. Since the accounting cycles of both the NIE and the EE are based on full calendar months, the two parties agreed to consider 01 August 2018 as the official starting date of the project.
At the project inception workshop NamWater presented its final strategy for executing the project. Adoption of this strategy necessitated changes to be made to the execution schedule that was presented in the approved project proposal. Instead of completing both design and construction of the plants in Project Year 1, design was rescheduled to be completed in Year 1 and construction in Year 2. Operation of the plants will thus be conducted in Years 3 - 4, and not in Years 2-4 as originally envisaged. It is considered that the shorter operational period will not detrimentally affect achievement of the project objectives. At the end of Year 1, project execution is on schedule.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | 1. Project risks reassessed and risk matrix updated in July 2019. 2. Project results framework assessed and updated in August 2019. 3. It was identified that due to meteorological conditions the capital cost of generating wind energy at both project sites was approximately 12 times that of solar energy. The concept of a hybrid PV/wind installation to power the desalination plants was thus abandoned. However, due to the nature of the project, a small wind turbine (800 W at Grünau and 1 kW at Bethanie) is included in the design to collect data regarding wind energy on site. When adequate sunlight is not available and there is sufficient wind, the turbines will provide some power to the plant and charge the batteries. 4. Since the primary objective of the project is to gain knowledge, the initial concept designs were changed to allow for more experimentation and data collection. The treatment trains will now include two stages of flocculation, pH pre- and post-correction, anti-scalant dosing, pressure sand filtration, cartridge filtration, reverse osmosis, with various bypass options; online measuring and analytical equipment will be installed and readings will be transmitted by SCADA for recording and analysis.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | All environmental and social safeguard measures that are infrastructure specific have been incorporated in plant design, while measures that are specific to the construction stage have been incorporated in the RFP for construction services. The effectiveness of these measures have not yet been demonstrated since construction is still to start. Safeguard measures that are not infrastructure related have been scheduled, and no unwanted negative impacts have yet arisen.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | This project is principally of a technical nature. In the first project year the detailed EIA/ESMP and the plant designs from concept through preliminary to detail design were done, and the RFP for procurement of construction services was compiled. Gender considerations were addressed in the EIA/ESMP, but plant design up to delivery of treated water into the terminal reservoir and compilation of the RFP can be regarded as gender-neutral. During the Year 1, specific gender considerations influenced the selection of EE staff-in training to be involved in executing the project and of staff members to attend a training course on design of desalination plants (more than 50% of the staff members are women).
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A
What measures are being/could have been put in place to improve project/program results? | N/A
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | N/A
If learning objectives have been established, have they been met? Please describe. | N/A
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | NAM/NIE/Water/2015/1
Implementing Entity | Desert Research Foundation of Namibia (DRFN)
Type of implementing entity | NIE
Country | Namibia
Region | Africa
Sector | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
| Bethanie | Total | 0 | 0 | 0 | Total | 2978 | 2978 | 0 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 51% | 51% | 0% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries (<14 years) | 0% | 0% | 0% | % of Youth beneficiaries | 30% | 30% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
| Grunau | Total | 0 | 0 | 0 | Total | 500 | 500 | 0
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 49% | 49% | 0%
|  | % of Youth beneficiaries (<14 years) | 0% | 0% | 0% | % of Youth beneficiaries | 30% | 30% | 0%
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Water management | 1: No capacity | Public | Local | Water management | 4: High capacity
Output 2.2 Targeted population groups covered by adequate risk reduction systems | Indicator 2.2.1: Percentage of population covered by adequate risk-reduction systems | % of population targeted | % of female population targeted | % of male population targeted | % of children under 14 years targeted | % of population targeted | % of female population targeted | % of male population targeted | % of children under 14 years targeted | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
| Indicator 2.2.2: No. of people affected by climate variability | Total population | Females | Males | Children under 14 years | Total population | Females | Children under 14 years | Children under 14 years | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Bethanie
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0% | 0% | 1: Aware of neither |  | 1740 | 50% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | National | 2: Partially responsive (Lacks most elements) |  | Water management | Regional | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 5: Fully improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.2: No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) | Number of assets | Type |  | Sector | Number of assets | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 2 | Community |  | Water management | 2 | Community |  | Water management
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adaptive capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnerability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strengthened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.