## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 1 August 2019-31 July 2020
| Project Title: | Pilot rural desalination plants using renewable power and membrane technology
| Project Summary: | Namibia relies heavily on groundwater for the supply of water, and the predicted increase in both temperature and rainfall variability due to climate change will increase this reliance. However, in many areas the dissolved solids content of the locally available groundwater exceeds the approved threshold for human consumption. Decreased aquifer recharge due to periods of lower rainfall caused by climate change is likely to cause an increase in total dissolved solids in groundwater, which will exacerbate the water quality situation. Pumping water over long distances from other water sources is not a feasible option for supplying small communities with good quality water. An alternative is to improve the quality of locally abstracted groundwater by applying treatment techniques. These techniques require energy in the form of electricity, but many of the small communities are not coupled to the national electricity grid. It is also considered that the energy needs for treatment should be met by sustainable and environmentally sound resources.
The aim of the proposed project is thus to pilot the treatment by reverse osmosis (RO) of poor quality local groundwater to a level that complies with the national standards for drinking water, using sun and wind energy to power the process. Execution of the project will yield a wide range of information and knowledge on both technical and social aspects of establishing and operating such treatment and power plants. The acquired information, knowledge and skills will then be communicated to stakeholders in the water supply sector in order that the applied technology could be mainstreamed and replicated elsewhere in the country. The project will result in improved resilience of vulnerable communities and groups to climate change impact, specifically to a decrease in chemical water quality of existing groundwater sources. In addition to providing benefits to vulnerable communities in the target areas, the project will also serve to increase the capacity of government agencies to integrate climate change adaptation considerations into water supply planning and policy processes. It is considered essential to pilot two plants in a rural setting, where the water demand of the communities differs by an order of magnitude. This would allow the opportunity to establish how plant size affected aspects such as operation, management and maintenance requirements, the unit cost of water produced, the involvement of beneficiaries; and the interest of stakeholders. The two selected project sites are at Grünau settlement and at Bethanie village, both located in the far south of the country.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | NAM/NIE/Water/2015/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Desert Research Foundation of Namibia (DRFN) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Republic of Namibia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | 1. Bethanie Village, //Karas Region (Southern Namibia) - 36°30'01" S, 17°09'34" E 2. Grünau Settlement, //Karas Region (Southern Namibia) - 27°43'57" S, 18°22'42" E | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 10-13 October 2017 during 30th Adaptation Fund Board Meeting
IE-AFB Agreement Signature Date: |  | 2018-01-15
Start of Project/Programme: |  | 2018-08-01 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Actual Mid-term Review Date (if applicable): |  | Latest date end January 2022 as per project proposal Request for extension of project period is still to be confirmed; date of MTR will then change | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Original Completion Date: |  | 2022-07-31
Revised Completion Date after approval of extension request (if applic) |  | Not applicable yet
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
| Category of condition | Environmental and Social Safeguards
| Condition or Requirement | Environmental Impact Assessment (EIA) to be completed before start of construction.
| Current Status | Condition met and cleared by the AFB Sec
| Planned actions, including a detailed time schedule | Environmental and Social Management Plans are applied and associated monitoring is carried out, to continue as applicable until project completion
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception report: 16 August 2018 Extension request: 08 October 2020 (to be confirmed by NIE at request of AFB Secretariat) | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | www.drfn.org.na | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Dr. Martin Schneider | Dominican Republic
| Email: | martin.schneider@drfn.org.na | Ecuador
| Date: | 2022-07-31 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Mr. Teofilus Nghitila | Equatoral Guinea
| Email: | tnghitila@yahoo.com | Eritrea
| Date: | 2022-07-31 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Dr. Martin Schneider | Fiji
| Email: | martin.schneider@drfn.org.na | Finland
| Date: | 2022-07-31 | France
| Executing Agency |  | Gambia
| Name: | Mr. Romeo Likando | Georgia
| Email: | likandor@namwater.com.na | Germany
| Date: | 2022-07-31 | Ghana
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 31 July 2019 |  |  |  | Financial information PPR 2: cumulative from project start to 31 July 2020 |  |  |  |  | Financial information PPR 3: cumulative from project start to 31 July 2021 |  |  |  | Financial information PPR 4: cumulative from project start to 31 July 2022 |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
NOTE: All expenditure and ROI took place in NAD (N$). For the purpose of the PPR1 all expenditure and ROI amounts were converted to USD (US$) at the exchange rates applicable on the respective days that the Project funds (A+B) and the NIE fee (C) received from the AF were converted to NAD (N$). The exchange rates (N$:US$) applied for reporting are: Funds originating from Project Formulation Grant (received 28 February 2017) All funds: 12,97 Funds originating from Tranche 1 (received 26 January 2018) Project funds (A+B): 11,691 ROI on Project funds (A+B): 11,691 NIE fee (C): 11,84 ROI on NIE fee (C): 11,84 |  |  |  | NOTE: All expenditure and ROI took place in NAD (N$). For the purpose of the PPR2 all expenditure and ROI amounts were converted to USD (US$) at the exchange rates applicable on the respective days that the relevant Project funds (A+B) and the NIE fee (C) received from the AF were converted to NAD (N$). This approach is regarded to be "correct", but since tranches are not invested in separate accounts this requires complicated calculations for conversion to US$, especially in the case of ROI on funds originating from more than one tranche and on ROI on previously generated ROI, as well as in the case where some funds from a tranche remain undisbursed to the EE as at the end of that project year. This approach is not cost-effective and the accuracy that can be achieved for PPR3 onwards is doubtful. The exchange rates used for reporting here are: Funds originating from Project Formulation Grant (received 28 February 2017) All funds: 12,97 Funds originating from Tranche 1 (received 26 January 2018) Project funds (A+B), ROI on (A+B) and ROI on previous ROI: 11,691 NIE fee (C), ROI on (C) and ROI on previous ROI: 11,840 Funds originating from Tranche 2 (received 22 November 2019) Project funds (A+B), ROI on (A+B) and ROI on previous ROI: 14,500 NIE fee (C), ROI on (C) and ROI on previous ROI: 14,500
Estimated cumulative total disbursement from NIE to EE from project as of 28 February 2017 | Item | Amount (US$) |  | Estimated cumulative total disbursement from NIE to EE from project as of 28 February 2017 | Item | Amount (US$) |  |  | Estimated cumulative total disbursement from NIE to EE from project as of 28 February 2017 |  |  |  | Estimated cumulative total disbursement from NIE to EE from project as of 28 February 2017 |  |  |  | Estimated cumulative total disbursement from NIE to EE from project as of 28 February 2017
| Total disbursement | 181428 |  |  | Total disbursement | 181428
| Project formulation grant | 27500 |  |  | Project formulation grant | 27500
| Project funds (A+B) | 153928 |  |  | Project funds (A+B) | 153928
| Project activities cost (A) | 23075 |  |  | Project activities cost (A) | 23075
| Project execution cost (B) | 130853 |  |  | Project execution cost (B) | 130853
Add any comments on AF Grant Funds. (word limit=200) | No comment |  |  | Add any comments on AF Grant Funds. (word limit=200) | Disbursement by NIE to EE in Year 2 |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
The NIE did not disburse any funds to the EE in Project Year 2, since the EE did not submit the required invoices and supportive documentation to the NIE. NamWater after the end of Project Year 2 requested disbursement of all expenditure incurred during that year. The implication is that project activities and project execution in Project Year 2 were temporarily funded from NamWater resources.
Uncommitted amounts not yet disbursed to EE
"Committed amounts" is understood to mean funds that have already been spent by the EE or have been pledged by the EE to in future pay for services rendered under established contacts or agreements. As at the end of Year 2 the NIE has not disbursed any uncommitted funds to the EE. Uncommitted amounts not yet disbursed thus equal the uncommitted amounts shown below:
[5 empty] | Project Costs (A+B) | 3207315
[5 empty] | Project Activity Cost (A) | 2861609
[5 empty] | Project Execution Cost (B) | 345706
INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
| Item | Amount (US$) |  |  | Item | Amount (US$)
| Total Investment Income | 476039.34 |  |  | Total Investment Income | 795382.71
| ROI in Year 1 | 476039.34 |  |  | ROI in Year 1 | 476039.34
| On Project Funds (A+B) | 472622.09 |  |  | On Project Funds (A+B) | 472622.09
| On A | 451161.53 |  |  | On A | 451161.53
| On B | 21460.56 |  |  | On B | 21460.56
| On Management Fee (C) | 3417.25 |  |  | On Management Fee (C) | 3417.25
[5 empty] | ROI in Year 2 | 319343.37
[5 empty] | On Project Funds (A+B) | 315310.47
[5 empty] | On A | 302266.17
[5 empty] | On B | 13044.3
[5 empty] | On Management Fee (C) | 4032.9
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period |  |  |  | List output and corresponding amount spent for the current reporting period |  |  |  |  | List output and corresponding amount spent for the current reporting period |  |  |  | List output and corresponding amount spent for the current reporting period |  |  |  | List output and corresponding amount spent for the current reporting period
NOTE: the NIE should reimburse the project funds with the amounts under ROI on Project Management Fee (C) to supplement Fee (C) and Advance to NIE to supplement Project Management Fee (C) |  |  |  | NOTE: 1. The amounts under A and B are those spent by the EE, but they have not been disbursed by the NIE to the EE 2. The amounts utilised in Project Year 1 under ROI on Project Management Fee (C) to supplement Fee (C) and Advance to NIE to supplement Project Management Fee (C) have not yet been reimbursed to the project
| Item/activity/action | Amount (US$) |  |  | Item/activity/action | Amount (US$) |  |  |  | Item/activity/action | Amount (US$) |  |  | Item/activity/action | Amount (US$) |  |  | Item/activity/action | Amount (US$)
| Total project (A+B+C) | 286029.7419 |  |  | Total project (A+B+C) | 702608.6459
| Project Activity Cost (A) | 22574.0313 |  |  | Project Activity Cost (A) | 541189.0343 |  | 563763.0656
| Comp 1: Develop desal plants | 13619.6219 |  |  | Comp 1: Develop desal plants | 429723.8046
| 1.1 Civil works | 2483.1922 |  |  | 1.1 Civil works | 234061.4148
| 1.2 Water treatment plants | 8277.0507 |  |  | 1.2 Water treatment plants | 62044.8208
| 1.3 M&E works | 2859.379 |  |  | 1.3 M&E works | 133617.5691
| Comp 2: Develop energy plants | 8954.4094 |  |  | Comp 2: Develop energy plants | 100719.6989
| 2.1 Turbines | 2189.6331 |  |  | 2.1 Turbines | 7885.0398
| 2.2 Solar fields | 2575.3143 |  |  | 2.2 Solar fields | 4558.5493
| 2.3 Battery banks | 1070.396 |  |  | 2.3 Battery banks | 63083.6541
| 2.4 Inverters & BOS | 1070.396 |  |  | 2.4 Inverters & BOS | 7197.6734
| 2.5 Electrical & SCADA | 1070.396 |  |  | 2.5 Electrical & SCADA | 3832.4352
| 2.6 Civil: safety & security | 978.2739 |  |  | 2.6 Civil: safety & security | 14162.3471
| 2.7 Professional fees | 0 |  |  | 2.7 Professional fees | 0
| Comp 3: Test, commission, train | 0 |  |  | Comp 3: Test, commission, train | 4596.9549
| Comp 4: Piloting of plants | 0 |  |  | 3.1 Testing | 0
| Comp 5: Supply quality water | 0 |  |  | 3.2 Specialised training | 0
| Comp 6: Sensitise stakeholders | 0 |  |  | 3.3 Produce manuals | 4596.95
| Comp 7: Info & knowledge | 0 |  |  | 3.4 Involve tertiary students | 0
| Project Execution Cost (B) | 127845.5479 |  |  | Comp 4: Piloting of the plants | 6148.5758
| 1. Management and supervision | 24577.8774 |  |  | 4.1: Operate, maintain, improve desalination plants | 0
| 2. Data collection | 333.5899 |  |  | 4.2: Operate, maintain, improve power plants | 0
| 3. Progress meetings/reports | 25749.0369 |  |  | 4.3: Update manuals | 0
| 4. Financials | 1316.9464 |  |  | 4.4: Collect information, record lessons | 6148.58
| 5. Site scientist/engineer | 20861.7073 |  |  | 4.5: Site visits by students | 0
| 6. Capacity building | 55006.39 |  |  | Project Execution Cost (B) | 92053.0709 |  | 219898.6188
| Project Management Fee (C) | 95181.4443 |  |  | 1. Management and supervision | 19203.0909
| 1. Management | 48849.6975 |  |  | 2. Data collection | 4569.2101
| 2. Operations | 2038.6754 |  |  | 3. Progress meetings/reports | 7707.7925
| 3. Office services and supplies | 19800.8406 |  |  | 4. Financials | 9408.3457
| 4. Auditing and consulting | 17118.2308 |  |  | 5. Site scientist/engineer | 1916.6318
| 5. Knowledge dissemination | 7374 |  |  | 6. Capacity building | 49248
| ROI on Project Management Fee (C) to supplement Fee (C) | 3417 |  |  | Project Management Fee (C) | 69366.5407 |  | 204976.7034
| 1. Management | 2533.208 |  |  | 1. Management | 38252.4497
| 2. Operations | 178.0839 |  |  | 2. Operations | 0
| 3. Office services and supplies | 62.1146 |  |  | 3. Office services and supplies | 14945.3931
| 4. Auditing and consulting | 643.5935 |  |  | 4. Auditing and consulting | 10679.3103
| 5. Knowledge dissemination | 0 |  |  | 5. Knowledge dissemination | 5489.3876
| Advance to NIE to supplement Proj. Management Fee (C) | 37011.7184
| 1. Management | 27438.7999
| 2. Operations | 1928.9411
| 3. Office services and supplies | 672.803
| 4. Auditing and consulting | 6971.1744
| 5. Knowledge dissemination | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
NOTE: Planned expenditure under Project Activity Cost (A) consists of the remainder of Tranche 1 for A (= US$ 3 789 485), plus Tranche 2 for A (= US$ zero as per approved revised disbursement schedule). Planned expenditure under Project Execution Cost (B) consists of the remainder of Tranche 1 for B (= US$ 88 142) plus Tranche 2 for B (= US$ 113 688), amounting to US$ 201 830. Planned expenditure under Project Management Cost (C) consists of Tranche 2 for C (= US$ 93 285) minus the advance to be repaid (= US$ 37 012), minus the ROI on C for Year 1(=US$ 3 417) to be repaid, amounting to US$ 52 857. |  |  |  | NOTE: The projected total expenditure for Project Year 3 as presented here has not been updated with information that may have become available since submission of the document PPR2 of 29 September 2020.
List outputs planned and corresponding projected cost for the upcoming reporting period | Item/activity/action | Projected cost (US$) | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | Item/activity/action | Projected cost (US$) | Est. Completion Date |  | List outputs planned and corresponding projected cost for the upcoming reporting period | Item/activity/action | Projected cost (US$) | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | Item/activity/action | Projected cost (US$) | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | Item/activity/action | Projected cost (US$) | Est. Completion Date
| Project (A+B+C) | 4044172.4255 |  |  | Project (A+B+C) | 3223280.2515 | 2023-07-31
| Project Activity Cost (A) | 3789484.9687 |  |  | Project Activity Cost (A) | 2920240.7946 | 2023-07-31 | 3484003.8602
| Comp 1: Develop desal plants | 2270610.3781 | 2020-07-31 |  | Comp 1: Develop desal plants | 2140958.9 | 2021-08-14
| 1.1 Civil works | 868456.8078 | 2020-07-31 |  | 1.1 Civil works | 1255778.4715 | 2021-08-14
| 1.2 Water treatment plants | 1129610.9493 | 2020-07-31 |  | 1.2 Water treatment plants | 272390.7775 | 2021-08-14
| 1.3 M&E works | 272542.621 | 2020-07-31 |  | 1.3 M&E works | 612789.651 | 2021-08-14
| Comp 2: Develop energy plants | 1477199.5906 | 2020-07-31 |  | Comp 2: Develop energy plants | 587192.1316 | 2021-08-14
| 2.1 Turbines | 399072.3669 | 2020-07-31 |  | 2.1 Turbines | 55402.4848 | 2021-08-14
| 2.2 Solar fields | 547301.6857 | 2020-07-31 |  | 2.2 Solar fields | 84780.0556 | 2021-08-14
| 2.3 Battery banks | 311021.604 | 2020-07-31 |  | 2.3 Battery banks | 247776.8574 | 2021-08-14
| 2.4 Inverters & BOS | 58374.604 | 2020-07-31 |  | 2.4 Inverters & BOS | 172446.1389 | 2021-08-14
| 2.5 Electrical & SCADA | 13791.604 | 2020-07-31 |  | 2.5 Electrical & SCADA | 1673.4702 | 2021-08-14
| 2.6 Civil: safety & security | 43606.7261 | 2020-07-31 |  | 2.6 Civil: safety & security | 25113.1246 | 2021-08-14
| 2.7 Professional fees | 104031 | 2020-07-31 |  | 2.7 Professional fees | 0 | 2021-08-14
| Comp 3: Test, commission, train | 19161 | 2020-07-31 |  | Comp 3: Test, commission, train | 32193.9338 | 2021-08-30
| 3.1 Test components and complete systems, etc. | 1916 | 2020-07-31 |  | 3.1 Test components and complete systems, etc. | 7681.9776 | 2021-08-30
| 3.2 Provide specialized training to O&M staff | 8431 | 2020-07-31 |  | 3.2 Provide specialized training to O&M staff | 17558.285 | 2021-08-30
| 3.3 Produce training and maintenance manuals | 5173 | 2020-07-31 |  | 3.3 Produce training and maintenance manuals | 6953.6712 | 2021-08-30
| 3.4 Involve tertiary institution students, etc. | 3641 | 2020-07-31 |  | 3.4 Involve tertiary institution students, etc. | 0 | 2021-08-30
| Comp 4: Piloting of plants | 19321 | 2022-07-31 |  | Comp 4: Piloting of plants | 150486.8822 | 2023-07-31
| 4.1 Operate, maintain and improve the desalination plants | 0 | 2022-07-31 |  | 4.1 Operate, maintain and improve the desalination plants | 47041.6346 | 2023-07-31
| 4.2 Operate, maintain and improve the power plants | 0 | 2022-07-31 |  | 4.2 Operate, maintain and improve the power plants | 103445.2476 | 2023-07-31
| 4.3 Update the training, operations and maintenance manuals | 6000 | 2022-07-31 |  | 4.3 Update the training, operations and maintenance manuals | 0 | 2023-07-31
| 4.4 Collect technical and social information, etc. | 8400 | 2022-07-31 |  | 4.4 Collect technical and social information, etc. | 0 | 2023-07-31
| 4.5 Inform beneficiaries of what plants do and the benefits to be achieved | 4921 | 2022-07-31 |  | 4.5 Inform beneficiaries of what plants do and the benefits to be achieved | 0 | 2023-07-31
| Comp 5: Supply quality water | 0 | 2022-07-31 |  | Comp 5: Supply quality water | 0 | 2023-07-31
| 5.1 Operate, maintain the plants | 0 | 2022-07-31 |  | 5.1 Operate, maintain the plants | 0 | 2023-07-31
| 5.2 Hand over infrastructure to NamWater to ensure continuation of water supply | 0 | 2022-07-31 |  | 5.2 Hand over infrastructure to NamWater to ensure continuation of water supply | 0 | 2023-07-31
| Comp 6: Sensitise stakeholders | 1824 | 2022-07-31 |  | Comp 6: Sensitise stakeholders | 7698.2294 | 2023-07-31
| 6.1 Public meetings to share information | 1059 | 2022-07-31 |  | 6.1 Public meetings to share information | 7698.2294 | 2023-07-31
| 6.2 Information supply to school children | 218 | 2022-07-31 |  | 6.2 Information supply to school children | 0 | 2023-07-31
| 6.3 Impart knowledge and skills to community women | 547 | 2022-07-31 |  | 6.3 Impart knowledge and skills to community women | 0 | 2023-07-31
| Comp 7: Info & knowledge | 1369 | 2022-07-31 |  | Comp 7: Info & knowledge | 1710.7176 | 2023-07-31
| 7.1 Share project experience and lessons learnt | 931 | 2022-07-31 |  | 7.1 Share project experience and lessons learnt | 1710.7176 | 2023-07-31
| 7.2 Distribute technical information | 438 | 2022-07-31 |  | 7.2 Distribute technical information | 0 | 2023-07-31
| Project Execution Cost (B) | 201830.4568 | 2022-07-31 |  | Project Execution Cost (B) | 201830.4568 | 2023-07-31 | 421729.0756
| 1. Management and supervision | 52817.8123 | 2022-07-31 |  | 1. Management and supervision | 52817.8123 | 2023-07-31
| 2. Data collection | 55656.7022 | 2022-07-31 |  | 2. Data collection | 55656.7022 | 2023-07-31
| 3. Progress meetings/reports | 54559.0592 | 2022-07-31 |  | 3. Progress meetings/reports | 54559.0592 | 2023-07-31
| 4. Financials | 26873.2729 | 2022-07-31 |  | 4. Financials | 26873.2729 | 2023-07-31
| 5. Site scientist/engineer | 11923.6101 | 2022-07-31 |  | 5. Site scientist/engineer | 11923.6101 | 2023-07-31
| 6. Capacity building | 0 | n/a |  | 6. Capacity building | 0 | 2023-07-31
| Proj. Management Fee (C) (Note: Planned expenditure for Year 2 as per the Project Proposal is reduced by the advance and the ROI on C to be paid back to the investment account for funds under A+B.) | 52857 | 2022-07-31 |  | Proj. Management Fee C | 101209 | 2023-07-31 | 306185.7034
| 1. Management | 19336 | 2022-07-31 |  | 1. Management | 49308 | 2023-07-31
| 2. Operations | 9068 | 2022-07-31 |  | 2. Operations | 11175 | 2023-07-31
| 3. Office services and supplies | 14714 | 2022-07-31 |  | 3. Office services and supplies | 15449 | 2023-07-31
| 4. Auditing and consulting | 4385 | 2022-07-31 |  | 4. Auditing and consulting | 19923 | 2023-07-31
| 5. Knowledge dissemination | 5354 | 2022-07-31 |  | 5. Knowledge dissemination | 5354 | 2023-07-31
[9 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[9 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[9 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[9 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Level | Steps Taken to Mitigate Risk
Financial risks
Ineffective Financial Management Systems | Low | Financial management arrangements were defined in the grant agreement between NIE and EE and subsequently implemented. The majority of procedures are effective and application continues to be monitored. However, the project accounting function in the EE was dormant for a period of four months and a backlog of project accounting functions arose. Project cost reports by the EE are not presented to the NIE as required. After the NIE via the EE project manager attempted to have the matter rectified, the NIE officially informed the CEO of the EE of this non-compliance with the DRFN-NamWater agreement. The NIE has since received a cost report for Year 2 under the Project Activity Cost (A), but none yet for the Project Execution Cost (B). The possible impact on the project remains low, but the NIE constantly monitors the situation.
Delays in the disbursement of funds, procurement and institutional inefficiencies (e.g. lengthy approval processes) result in delayed delivery of equipment and other services and hence project implementation. | Low | Procedures for submission of disbursement requests by the EE and subsequent disbursement by the NIE were defined in the DRFN-NamWater grant agreement. The EE in Project Year 2 did not submit disbursement requests as required and thus the NIE did not disburse any project funds to the EE. After the NIE via the EE project manager attempted to have the matter rectified, the NIE officially informed the CEO of the EE of this non-compliance with the DRFN-NamWater agreement. This situation did not cause cash flow problems within the EE and did not effect procurement under the project. The situation is slowly being redressed and expenditure in Year 2 under the Project Activity Cost (A) has since been disbursed to the EE. The possible impact on the project remains low, but the NIE constantly monitors the situation.
| Low | Payment of contractor invoices by the EE for construction at Grünau initially did not take place within the time period specified in the construction contract. After the NIE via the EE project manager attempted to have the matter rectified, the NIE officially requested the CEO of the EE to ensure that such payments were made as per the contract. Late payment could potentially have a negative impact on the ability of the contractor to pay suppliers and thus on the execution of work to schedule. The situation was resolved, but the NIE continues to monitor compliance by the EE.
| High | Inefficiencies in the decision-making and approval processes within the EE and in the requirement to apply the Public Procurement Act (Act 15 of 2015) and its regulations have resulted in major project execution delays. Amongst others this caused the award of the construction tender at Bethanie to be cancelled by order of the Public Procurement Review Panel since the tender was awarded outside the bid validity period. This caused a substantial delay in project execution. The tender was only readvertised approximately 19 weeks later, in part due to the effect of Covid-19 restrictions imposed by Government. The risk of execution delays due to slow procedures continues to exist and requires constant attention from the NIE. Both the risk probability and the risk impact turned out to be very high.
Fluctuations in exchange rate (USD: NAD) which could affect the funding available for implementation and lead to budgetary constraints. | Low | The change in NAD-USD exchange rate from the time of budget compilation to receipt of Tranche 1 resulted in a loss of approximately 10% of the project budget in NAD. Since Tranche 1 comprises 82,5% of the total Project Grant, the exchange loss amounted to 8.3% of the total project budget. However, investment of Tranche 1, coupled to a change in project execution schedule that delayed spending of the bulk of the Project Activities Cost (A), has yielded a return on investment that has fully recovered the exchange rate loss on Tranche 1. During Year 2 the exchange rate risk remained low until the effects of Covid-19 on 24 February 2020 started to drastically increase the NAD:USD exchange rate. The NIE on 24 March 2020 analysed the risk of insufficient project funds for construction at Bethanie. It was found that under the foreseen worst case scenario of a N$ 22 : US$ 1 exchange rate there would still be sufficient funds to undertake the construction as planned.
The EE, however, decided to postpone re-advertisement of the tender as a risk mitigation measure. It turned out that the risk did not manifest since the increase in exchange rate turned at N$ 19.11 : US$ 1 and currently stands below N$ 17 : US$ 1. The effect of the steps taken to mitigate the risk caused an extended delay in project execution. On the positive side, the re-advertised construction tender incorporated aspects to manage the volatile exchange rate and therefore to achieve value for money. The exchange rate risk is considered to remain low. The EE also decided on in-house construction of the evaporation ponds at Bethanie to reduce project cost. The NIE considers that this mitigation step gives rise to alternate risks, such as those associated with financial control, and will closely monitor expenditure.
Ineffective management of project funds affects project implementation. | Low | Procurement complies with the NamWater procurement policy and procedures and with the directives of the Public Procurement Act. The NIE is provided with all tender documentation, including bid evaluations and award recommendations, all of which requires a "no objection" from the NIE before the EE can proceed. The NIE requires an annual external financial audit of the EE's financial statements for the project to be provided within two months of the end of each project year. The audit for Year 1 was only received in the last month of Year 2, but this did not affect project implementation. The NIE provides the EE with a quarterly investment report, which also conveys the status of unutilised AF funds and the ROI. The NIE applies proper accounting of AF funds received and disbursed to the EE, and strictly controls utilisation of project funds.
Project risks
Failure to achieve milestones and provide deliverables on time | High | Despite the EE having assigned a dedicated project manager, the combination of cumbersome administrative and project processes and the effect of Covid-19 have resulted in milestones not being achieved as scheduled. The project is already approximately one year behind schedule. With construction at Grünau a delay of approximately 53 days has been experienced - this was principally due to the effect of Government regulations pertaining to Covid-19 and to the negative effect that Covid-19 had on regional and international procurement. The NIE continuously applies project management techniques in an attempt to ensure that an agreed execution schedule is followed. The EE discontinued engagement between the NIE and the EE in the form of quarterly project progress as from February 2020; after the NIE officially informed the CEO of the EE of this non-compliance with the DRFN-NamWater agreement the EE acceded to resume this engagement.
Long distances to the sites result in logistically challenging implementation of project interventions. | Low | Various road safety measures are applied to staff doing site visits. SCADA systems have been incorporated in plant design to allow transfer of plant operations data to the Regional Office and to the Head Office of the EE to cut down on travelling required for monitoring and control of plant operation.
Failure to involve adequate representation of vulnerable communities, particularly women, and therefore failure to create ownership of the project at the community level at project sites. | High | In Year 2 no planned public/community meetings and visits to schools took place due to Government prohibition of public meetings and the closure of schools under the Covid-19 regulations. This will be redressed once restrictions are lifted. To the extent possible, construction at Grünau made use of people from the local community - in the last month of Year 2 a total of 15 local labourers were working on site.
Communities are incapable of managing and maintaining assets and structures built through the project. | Low | The aspect of communities being incapable of managing and maintaining project assets and infrastructure was wrongly identified as a risk in the project proposal. The assets and structures will be managed and maintained by the EE and not by the communities since it is the responsibility of the EE as eventual owner, manager and operator of the plants. Specific measures will, however, be put in place to prevent theft of solar panels which is common throughout Namibia.
Technology transfer with its associated uncertainties | Low | Technology transfer to communities on desalination and renewable energy is not applicable (see block above). Training of EE staff is attended to under scheduled project activities and students have taken part in plant design. The construction tender requires the contractors to accommodate students for transfer of knowledge obtaining hands-on experience - for the Grünau component a training programme was compiled and 5 students are involved in construction.
Operation and maintenance of the plant | Low | Operation and maintenance requirements have been thoroughly considered in the design of the plants. Training of future EE staff to be employed will be carried out during the reliability run after commissioning of the plants.
Water quality | Low | The mitigation measures indicated below will be applied once plants are commissioned: Water will be sampled at specified intervals and sent to the NamWater laboratory for internal or external testing in terms of bacterial and chemical analysis. The results will be made available to the project team to attend to as part of the piloting of the plants. In the event of non-compliance, NamWater is obliged to terminate the operation of the plant and attend to all defect processes before operation may continue. In terms of the Water Resources Management Act, 2013 the specified water quality testing regime must be c:ntinued for the lifetime of the plant. The design of the pilot plants provides for more than adequate monitoring of water quality at various stages of the treatment train. The data will be transferred by SCADA to Windhoek to ensure prompt adjustment in case of deviation from required standards.
Sustainability of the plant | Medium | One of the objectives of the pilot plant is to test the sustainability of the plant. The sustainability will be reviewed during the pilot project and mitigation measures will be recommended to ensure sustainability.
Institutional risks
Low capacity, awareness and acceptance of the need to tackle the impacts of climate change among key stakeholders limit the support for the project and limit likelihood of project outputs being mainstreamed into plans and budgets. | Medium | Activities under a scheduled capacity building programme by the EE have in Year 2 been severely curtailed by the Government regulations pertaining to Covid-19.
Poor coordination with other climate change projects in Namibia limits the potential to learn from and build on the experiences of climate change related projects. | Low | Sharing of information with other actors involved in the execution of climate change projects in Namibia is taking place continuously. This includes the Designated Authority, Government ministries and agencies, State-owned enterprises and local authorities.
Limited capacity of project partners to deliver project outputs. | Low | Engaged project partners all have experience in coordinating, implementing and delivering outputs in their relevant spheres of expertise, as demonstrated by the successful execution of plant design, environmental studies, construction and environmental monitoring to date.
Staff turnover within NamWater, Local Authorities, project partners, consultants and contractors may hamper progress. | Low | Institutional rather than individual relationships have been established between NamWater and Local Authorities and with project partners, limiting the negative impact of staff turnover. The project accounting function within the EE was negatively affected by personnel loss, but is being redressed.
Environmental risks
Non-compliance with the laws and other administrative orders of national and state government. | Low | There is continuous ensurance that all laws and orders are complied with. Environmental clearance certificates for the project at Bethanie and Grünau were obtained after completion of the EIA and ESMP. Groundwater abstraction permits exist. Waste water discharge permits will only be approved by the Policy and Water Administration Division in the Ministry of Agriculture, Water and Land Reform once the ponds have been constructed and Ministry personnel have completed their site inspections. Ponds at Grünau have been completed and those at Bethanie are still to be constructed.
Land acquisition and potential removal of local animals | Low | The EIA found that the identified land is not a sensitive habitat and does not harbour priority species. NamWater purchased the required land at Bethanie from the Village Council and entered into a long-term lease agreement with a private land owner at Grünau. No unintentional removal of local animals will be allowed, and if required consultation should be made with the Ministry of Environment and Tourism - no local animals have been identified for removal at Bethanie and none were removed at Grünau.
Law changes during Construction Phase | Low | Proper communications exist between NamWater and the various competent authorities (MET, MAWF etc.) to ensure that possible law changes are accommodated.
Land and vegetation clearing | Low | It has been established that appointment of a botanical specialist is not required. The requirements below are included in the ESMP and adherence to them is monitored: Clear only the vegetation absolutely necessary for the plant construction and proper operations - this has been specified in the draft ESMP. Only clear vegetation in phases, to minimise erosion and windblown dust - will be adhered to once construction starts. Save the topsoil so that it can be reused later during rehabilitation - - this has been specified in the draft ESMP. Any Protected trees that need to be removed, need a permit from MAWF before this can be done.
Protection of natural systems | Low | The requirements below are included in the ESMP and adherence to them is monitored: Disturbance of vegetation and faunal communities and their habitats is kept to a minimum. Heavy construction vehicles should be kept out of the seasonal and ephemeral stream channels and the movement of construction vehicles should be limited where possible to the existing roads. There are no rivers/oshanas located on the project sites. All earthworks equipment operators shall be informed to cease operating immediately if any artefact is unearthed and to report the finding immediately to the Engineer / ECO and OTC, who in turn shall notify the National Heritage Council.
Pollution of soil and groundwater | Low | Evaporation pond design includes a durable lining to prevent leakage and the ponds have adequate capacity to cater for heavy rainfall events. The requirements below are included in the ESMP and adherence to them is monitored: The Contractor shall ensure that all liquid fuels are stored in tanks or mobile bowsers with lids that are kept firmly shut. All tanks and/or mobile bowsers shall be situated in a bunded area. The Contractor shall ensure that there is adequate fire-fighting equipment at the fuel storage areas.
Access, traffic and haul roads | Low | The Contractor(s) are responsible for the control of all project related traffic, including that of his suppliers, in ensuring that vehicles associated with the project remain on designated routes and within the designated working times - this is monitored. Fencing is included in the construction contracts. Proper maintenance after hand-over is part of routine NamWater activities.
Solid waste management | Low | All solid waste management actions have been addressed in the ESMP and compliance is monitored during construction. This includes provision by the contractor of a sufficient number of rubbish bins with secured lids to prevent animal scavenging. No waste materials, including domestic, organic or construction wastes shall be burnt, dumped or buried on the site.
Hazardous substances | Low | Risk management actions re hazardous substances have been addressed in the ESMP and are executed.
Trenches | Low | Requirements re trenches are addressed in the ESMP and include that trenches shall be demarcated appropriately and securely and regularly monitored to ensure that pedestrians/animals (and vehicular) access to these areas is strictly prohibited.
Erosion, water quality, and storm water | Low | The requirements below are addressed in ESMP and adhered to during construction: The Contractor shall take all reasonable steps to prevent or remediate damage to the environment resulting from the Works in the form of erosion and sedimentation. The Contractor shall immediately remedy any situation that is or has the potential to result in soil erosion, water pollution and sedimentation from the works because of storm water flows. Storm water should be managed appropriately at the culvert crossing where the pipeline is planned to go through underneath the road, so that blockage does not occur.
Leakage of brine into soil and groundwater from ponds (poor design, damage of lining during cleaning, flooding during heavy rain) | Medium | The following mitigation measures have been adopted: Design must include a proper lining to prevent leakage, and adequate capacity for heavy rainfall events - done. Competence of operating staff employed at the plant - staff will be properly trained. Develop a proper and up to date Operation and Maintenance (O&M) manual of procedures with technical guidelines - being done for Grünau, scheduled for execution at Bethanie. Routine and proper environmental monitoring of all aspects of the plant - being done at Grünau, to be done when construction starts at Bethanie. Establish regular reporting procedures on maintenance - to be included in Operations and Maintenance Manuals when they are compiled. Undertake regular inspection and maintenance of all infrastructure to ensure in working order and to assess damaged/deficient equipment, as per the Operation and Maintenance Manual - to be done once plants become operational. Brine peak flow monitoring by monitoring the incidence of overflow at pump stations leading to the ponds and accurate recording of flow metering - design provides instrumentation for monitoring complete treatment train. Monitoring of surrounding boreholes for potential contamination of groundwater from the brine evaporation ponds - not included in ESMP since there are no boreholes in close proximity to the evaporation ponds.
Non-sustainability of water sources being over used | High | The design provides for continuous monitoring of water balance. NamWater is required to utilise boreholes within their recommended abstraction rates and the aquifer within its long-term sustainable yield. Recording of pump and rest water levels is part of standard operating procedure - intervals will be specified in the Operations Manual. Regular assessment of sustainable utilisation is specified in ESMP.
Health hazard to animals entering the pond area | Low | The design provides for proper fencing of the plants and ponds. Construction takes place accordingly.
Collision of birds with wind turbines | Low | It has been established that wind power is not cost-effective at the two project sites compared to solar power. Only one small experimental wind turbine will be installed at each site, with low risk of bird collision.
Potential of birds being attracted to the ponds | Low | The water would be salty but with no hazardous chemicals. The ESIA found that birds avoid water that is not suitable for drinking and that birds will thus not be impacted.
Fire or explosion of plant | Low | This is a very low risk. No fires or explosions have occurred at NamWater plants since the establishment of the entity approximately 20 years ago. Chemicals used at this plant are not flammable. Use of electrical circuit protection devices is standard, as is lightning protection.
Used equipment such as RO filter disposal | Low | Solid waste management actions have been identified under the ESMP. End-of-life plant components are included.
Improper reuse of the brine / salt-by-product | Low | Solid waste management actions have been identified under the ESMP. Salt from evaporation ponds is included.
Social risks
Human rights (e.g. water as a basic need) | Low | Avoid adverse impacts of the project on communities of Indigenous Peoples, or when avoidance is not possible, to minimize and/or compensate for such impacts - no communities of Indigenous People exist that can be negatively affected.
Land acquisition and potential removal of local people | Low | Addressed above under Environmental Risks.
A temporary loss of land and assets to the road servitude or areas to be occupied by project-related surface infrastructure - Indigenous People | Low | There are no communities of Indigenous People that will be affected. The land at Bethanie has been purchased from the Village Council and the land at Grünau is leased from a commercial farmer.
A population influx (due to the presence of a construction workforce, as well as an influx of job-seekers into the area), with a possible concomitant increase in social pathologies and increased pressure on existing infrastructure and services. | Low | The recruitment policy used to employ people on the project must be fair and transparent - done at Grünau. The intention of giving preferential employment to locals is clearly communicated, to discourage an influx of job-seekers from other areas - done. Inform local businesses about the expected influx of construction workers so that they could plan for extra demand - public consultations have taken place, businesses are aware of the project. Ensure that employment procedures/ policy of the contractor is communicated to local stakeholders, local farmers and Local Ward Councillor - done at Grünau, to be done when construction starts at Bethanie. Have clear rules and regulations for access to the construction site to control loitering - addressed in construction tender documents. Consult with the local private security companies and Police to establish standard operating procedures for the control and removal of loiterers at the construction site - done at Grünau, to be done when construction at Bethanie starts. Construction workers should be clearly identifiable by wearing proper construction uniforms displaying the logo of the construction company - done at Grünau, to be done when construction at Bethanie starts. Construction workers must also be provided with identification tags - done at Grünau, to be done when construction starts at Bethanie.
Disruption of access routes and daily movement patterns by the construction. Access, traffic and haul roads. |  | The items below have been addressed in the construction tender documents and are/will be adhered to: Unauthorised access to the construction site must be prevented through appropriate fencing and security. When the construction period has ended the implementation of adequate rehabilitation measures to return the landscape and other changes to at least its original state. The Contractor shall be held responsible for the control of all project related traffic, including that of his suppliers, in ensuring that vehicles associated with the project remain on designated routes and within the designated working times.
Impacts on sense of place. Such impacts may arise because of the visual intrusion of project-related infrastructure, as well as noise and traffic impacts during construction. Visual disturbance from wind turbines and solar panels. | Low | Actions under risk management plans for visual impacts, traffic and transport, and noise and vibration have been identified in the ESMP.
Dust caused by the construction works and from movement of heavy equipment. During the construction phase, the local community and construction workers would be inconvenienced by the dust generated by the construction works. | Low | Actions under a risk management plan for air emissions in the draft ESMP include requirements relating to dust. Dust suppression at Grünau was executed.
Noise and vibration due to the construction works and from movement of heavy equipment. Movement of heavy machinery on existing local roads may be one of the core problems for the local community during the construction phase. | Low | Actions under risk management plans for visual impacts, traffic and transport, and noise and vibration were identified in the ESMP and are carried out at Grünau. At Grünau the plant is far removed from the community, but at Bethanie the risk will be higher, since the plant will be situated within the village.
Improper ablution facilities provided | Low | Adequate chemical toilets must be provided for all staff. Alternatively, existing ablution facilities on site can be utilised if available. The contractor camp: ensure the necessary ablution facilities are provided, with chemical toilets where such facilities are not available at commencement of construction. Chemical toilets must be empty, kept hygienically clean and secured, they must be emptied / serviced on a regular basis to prevent them overflowing. Adequate toilets and showers must be positioned at the right places. All workers at Grünau, the majority of whom are local, are accommodated in the village. Toilet facilities are provided at the construction site as specified.
Socio-cultural differences and conflicts between migrant workers and the local community. Single men predominately occupy the construction camps which could create social conflicts, usually because of cultural differences, alcohol abuse or being away from their wives or partners for extended periods of time. A possible reason for conflict would be the perception among locals that the outsiders are taking up jobs that could have gone to unemployed members of the local community. An influx of unemployed job seekers could also add to the potential for conflict. | Low | The measures below are executed: Construction workers should be clearly identifiable. Overalls should have the logo of the construction company on it and construction workers should wear identification cards. Loitering of outsiders at either the construction site or at the construction camps should not be allowed. Local Police should be requested to assist in this regard. Align awareness campaigns with those of other organisations in the area (i.e. the Local Council). Control of access to construction camp. Cease construction activities before nightfall, if possible. Liaison with police, community policing forum and security stakeholders.
Various social pathologies, such as drug/ alcohol misuse, abuse of woman and children and incidences of sexually transmitted diseases (STI’s) may increase with the influx of job-seekers into the area. | Low | The identified measures below have not been attended to: Implement HIV/ AIDS, alcohol abuse, drug abuse, and domestic violence prevention and awareness campaigns in the communities. The contractors should ensure the health of its employees and their dependants by adopting rigorous health programmes, which should, at a minimum, include programmes to combat HIV/ AIDS and TB. The contractor should make HIV/ AIDS and STD awareness and prevention programmes a condition of contract for all suppliers and sub-contractors.
Crime is another social pathology that may increase. An inflow of construction workers and job seekers may also be accompanied by an increase in crime. Even if specific instances of crime are not because of the newcomers, they may still be ascribed to them by local communities. | Low | The following measures are in place at Grünau: Construction workers should be clearly identifiable. Overalls should have the logo of the construction company on it and construction workers should wear identification cards. The construction site is to be fenced and access should be controlled. Loitering of outsiders at either the construction side or at the construction village should not be allowed. Local security companies and Police should be requested to assist in this regard. Liaison structures are to be established with local security companies and police to monitor social changes during the construction phase. Liaison should also be established with existing crime control organisations. Control of access to construction camp. Cease construction activities before nightfall, if possible. Construction at Grünau is a small operation with approximately 15 workers at maximum. The majority are locals and thus the identified risk in this case is low.
Informal settlements. Once construction is concluded and the camp is vacated, it may be illegally occupied. | Low | The construction tender documents require any construction camp to be demolished. At Grünau there is no camp since most workers are locals and live in the village.
Local economy opportunities and economic empowerment. The construction phase of the project will have temporary positive impacts on the local economy, creating opportunities for formal and informal businesses to benefit from the proposed project. | n/a | This is not a risk to be managed.
Training and skills transfer. The project will provide the opportunity for the local community to participate in training and skills transfer activities. | n/a | This is not a risk to be managed.
Reluctance of beneficiaries to use desalinated water. | Low | Ongoing community education is scheduled as a project activity, but due to assembly restrictions by Government to combat Covid-19 has not been initiated.
Sustained future operation, management and maintenance of the plants | Medium | Has been considered in planning and design.
Risk of skill loss – skilled staff leaving NamWater employ during / after Pilot Phase (Sustainability) | Low | Broad technical participation in the project takes place within NamWater, thus the risk is reduced.
Possible unaffordable water tariff for desalinated water Collapse of the South African Rand (and the N$) | High | The following was agreed with NamWater: During the project the current bulk water tariffs will not be increased above the normal inflationary adjustments. After completion of the project, subsidisation of the bulk water tariff will be applied to ensure that the water remains affordable. During the EIA a survey was carried out to establish the magnitude of tariff increases that could be afforded.
Theft of solar panels and other materials | Medium | Sites are to be fenced and access should be controlled - fencing is addressed in design; access control to NamWater operations sites is standard. The remainder of the measures are attended to once construction starts: Loitering of outsiders at either the construction site or at the construction camp should not be allowed. Local security companies and Police should be requested to assist in this regard. Liaison structures are to be established with local security companies and police to monitor social changes during the construction phase. Liaison should also be established with existing crime control organisations.
Visual impact of the plant, solar panels and wind turbine infrastructure. | Low | At Grunau the desalination plant and evaporation ponds will be located over 1km away from the nearest households; visual and landscape impacts are unlikely to be significant. At Bethanie the plant will be within the village - reflection from solar panels will be contained by means of screens if the need is identified during/after construction.
Noise impacts form the plant and wind turbines | Low | It has been established that wind power is not cost-effective at the two project sites compared to solar power. Only one small experimental wind turbine will be installed at each site, noise generation will be negligible. The pumps and motors will generate very little noise.
Fire or explosion of plant | Low | Already addressed under environmental risks. This is a very low risk. No fires or explosions have occurred at NamWater plants since the establishment of the entity approximately 20 years ago. Chemicals used at this plant are not flammable. Use of electrical circuit protection devices is standard, as is lightning protection.
Plant down-time (no water provision) | Low | Water will be stored in existing / additional reservoirs to have back-up water for a minimum of 48h so that an operations problem can be fixed within that time frame. If the problem persists after the 48h, water provision will temporarily switch back to the old water scheme standards.
Water quality changes (+) The project is aimed at improving the quality of water for NW to comply with the new water quality regulations of the Water Resources Management Act of 2013 | Low | Already addressed under project risks.
Local employment and job opportunities. The construction phase of the project will have a positive impact on the local labour market. A positive impact on continued permanent employment will be probable due to the proposed project as the long-term economic viability of the plant will be possible, following the plant expansion. (+) | n/a | This is not a risk to be managed.
Local economy opportunities and economic empowerment. The operational phase of the project will have positive impacts on the local economy, creating opportunities for formal and informal businesses to benefit from the proposed project. (+) | n/a | This is not a risk to be managed.
Improved health. The project will provide the local community with better quality water and this will have a positive impact on the health of the people. (+) | n/a | This is not a risk to be managed.
Savings on current expenses. Due to the better-quality water, medical expenses would be less (dentists) and less frequent need to replace water usage equipment (Geysers, kettles etc.). (+) | n/a | This is not a risk to be managed.
Self-esteem upliftment. With cleaner teeth comes higher self-esteem, less likelihood of depression and social betterment regarding relationships and even job performance. (+) | n/a | This is not a risk to be managed.
Training and skills transfer. The project will provide the opportunity for the local community to participate in training and skills transfer activities. (+) | n/a | This is not a risk to be managed.
Critical Risks Affecting Progress and/or Successful Project Completion (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress or successful completion of project
Identified Risk | Current Level | Steps Identified/Executed to Mitigate Risk
Availability of land for evaporation ponds: Delays in obtaining land rights may lead to project execution delays. | High | NamWater purchased the required land at Bethanie and entered into a long-term lease agreement for land at Grünau. The risk does not exist any more.
Staff training level: The plant may not be optimally operated and maintained. | Low | 1. Select and appoint staff to fill positions identified by Eng. Cons. 2. Identify specific training courses 3. Compile training programme 4. Train staff (including backup staff) 5. Locate staff correctly Execution of the above measures is in progress.
Staff availability (1. Too few staff members for all shifts, 2. Staff not local, based too far away, long travel time): The plant is not optionally operated and maintained. | Low | 1. Appoint 2 x operators 2. (a) Identify correct base for maintenance staff (b) Locate staff to base(s) Execution of the above measures is in progress.
Durability of plant materials: Materials are not sufficiently robust to operate in a harsh chemical and natural environment. | Medium | Specify appropriate robust material in Bill of Quantities (BoQ). This has been done in compilation of construction tender documents. The risk has been removed within the constraint of cost-effectiveness.
Borehole control: Poor coordination of borehole pumps and plant operation may cause plant failure. | Medium | 1. Identify appropriate borehole automation and control logic 2. Include appropriate borehole automation and control logic in design These steps have been executed in compilation of construction tender documents.
Borehole water quality (Quality of borehole water may vary with time in terms of: (1. Silt content 2. Chemical quality): Pressure is put on plant due to deterioration in quality. | High | 1. (a) Develop management plan for boreholes (b) Continuously apply management plan 2. (a) Monitor borehole water quality regularly (b) Apply appropriate operational adjustments Step 1 (a) is included in ESMP. Rest of steps to be implemented when plants become operational.
Insufficient or unsuitable communication facilities or protocols will delay communication of plant status to Keetmanshoop and Windhoek: 1. Remedial action to keep plant operating at the required levels may be delayed. 2. Record of plant performance may be incomplete | Medium | Measures 1 and 2 have been executed in final design and compilation of construction tender documents. Measures 3 and 4 to be executed once plants become operational. 1. Identify required facilities and protocols 2. Include SCADA for remote monitoring and some control in design 3. Ensure enabled on-site operations teams are in place 4. Ensure continuous functionality of facilities
Specialized spares may not be available when required, leading to plant failure: Long lead time on specialized spares affect availability | Low | Measures 1 and 2 have been executed in final design and compilation of construction tender documents. Measure 3 is still to be executed. 1. Where possible, design for the use of standardised and commonly available equipment that is simple to install, operate and maintain (i.e. pumps, valves, piping) 2. Ensure critical spares are kept in storage where feasible 3. Ensure contracts are in place for the procurement of specialised equipment that is not kept in storage Steps 2 and 3 to be executed once plants are operational as from Project Year 3.
Irregular calibration of monitoring equipment cause incorrect readings: Incorrect monitoring results compromise effective plant operation and collection of piloting results | Low | Measure 1 has been executed in final design and compilation of construction tender documents. Measures 2 and 3 are to be executed once plants become operational. 1. Train operations staff to do calibration. 2. Ensure that materials are on site for calibration 3. Establish and apply calibration schedule. 4. Where practical, stock spare instrumentation that were calibrated off-site.
Flooding of the plant due to burst pipes, water leakages and rain is a threat to plant infrastructure and human life | Low | Measures 1 and 2 have been executed in final design and compilation of construction tender documents. Measure 3 to be executed once plants are operational. 1. Ensure insulation protection (IP) ratings are adequate where equipment is exposed. 2. Install adequate overflows, drainage, water proofing of flooring and protection of electrical equipment. 3. Compile and activate emergency plant shutdown action plans.
Chemical safety: Improper handling and storage of hazardous chemicals. | Low | Measure 1 has been executed in final design and compilation of construction tender documents. Measures 2 and 3are to be executed once plants are operational. 1. Construct proper handling and storage facilities for hazardous chemical 2. Train staff 3. Ensure staff remain adequately trained
Vandalism and theft due to insufficient security measures: 1. Delays in construction 2. Plant cannot operate | Medium | Measure 1 has been executed in final design and compilation of construction tender documents. Measures 2 and 3 could not be executed at Grünau due to restriction on gathering of people under measures to combat Covid-19. Should the restrictions be relaxed, the measures will be undertaken at Bethanie. 1. Install reasonable security 2. Schedule meetings with beneficiaries on detrimental effect of theft and vandalism on continuous water supply 3. Conduct the meetings with beneficiaries
Bethanie Village Council may continue to use the boreholes that it operates and provide a cheaper (but poorer quality) supply (to 75% of the population): The capacity of the plant may be under-utilised, amounting to an over-designed plant. The information to be collected on its operation, management and maintenance will not be realistic. | High | When the Water Resources Management Act comes into force, the Village Council will be prohibited to provide their own poor quality water. The risk remains high.
Dissatisfaction of beneficiaries at Grünau: Due to groundwater resource limitations, the plant will only supply the same volume as before, which is less than the realistic demand: The beneficiaries may be dissatisfied that the project does not supply them with more water. | Medium | Beneficiaries to be sensitised: 1. That availability of water will remain limited due to groundwater resource capacity 2. The objective of the project is to test the feasibility of groundwater desalination and that the community will benefit by receiving water of good quality. Sensitisation of beneficiaries started during project formulation, but was discontinued due to restrictions on public gathering in view of Covid-19.
Limited employment opportunities exist for local population in construction and operation/maintenance of the plants: Possible negative impact in terms of community perceptions | Low | The measures below were executed at Grünau and will also be applied at Bethanie. 1. Early communication with communities on available job opportunities 2. Contractors to be required to implement a local employment plan
Due to project implementation the cost of bulk water supply will increase: The bulk water supply tariffs may make the water unaffordable to the communities . | Medium | Measures 1 and 2 below have been executed. 1. Obtain an undertaking from the EE that during project execution tariffs will remain unchanged, except for normal inflationary adjustment. 2.Sensitise the EE on the need for post-project tariffs to remain affordable by means of adequate subsidisation.
Inefficient procurement of construction services may occur if the tender amount(s) exceed the threshold for NamWater own handling of the tender: Involvement of the Central Procurement Board may lead to a project delay. | Medium | Exemption from complying with procurement legislation on ground of foreign grant was obtained.
Outbreak of Covid-19 pandemic that affects all aspects of project implementation: Devastating impact on local economy, with associated decrease in value of N$ compared to major currencies leading to higher project cost. Negative effect on supply chains, leading to delays in procurement of instrumentation and equipment under the Grünau construction tender. Prohibition on tender advertisement under the Public Procurement Act for a period of approximately one month, leading to a delay in procurement of construction services for the Bethanie plant. | High | The following measures were employed to mitigate the effect: Exchange rate - described above. Project delays - attempts were and are made to increase execution efficiency once Covid-19 related restrictions are lifted piecemeal.
Enforced working from home for approximately one month, negatively impacting project execution due to a general "Covid paralysis". Prohibition on public gatherings, preventing interaction with local communities and beneficiaries. Prohibition on travelling, requiring special permit and delaying construction at Grünau.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Risk mitigation measures employed and their effect are described in the table above. In the majority of cases the risk has been reduced and in some cases the risk has been removed completely. None of the risks have resulted in foreseen non-achievement of the project objectives. Delays in project execution will inevitably lead to late completion of the project.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1] | Environmental Impact Assessment (EIA) to be completed before start of construction. | Completed one EIA and one ESMP for each of Bethanie and Grünau. Submitted EIAs and ESMPs to Ministry of Environment and Tourism (MET) on 18 November 2019, with request for Environmental Clearance Certificates (ECCs) to be issued. ECCs issued by MET on 18 December 2019. EIAs and EMPs provided to AF on 07 January 2020. | All conditions have been complied with.
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] Annexures 6 & 7, tables 5 & 6 of project proposal | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] Note: Based on environmental scoping and not on full EIA | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
2 - Access and equity |  |  | The cost of water supply at the two project sites will significantly increase. Inconsiderate upward adjustment of tariffs may make water unaffordable. | 1. During project execution keep tariffs unchanged, except for normal inflationary adjustment. 2.Post-project tariffs to remain affordable by means of adequate subsidisation. | 1 and 2. Bulk water tariffs at Bethanie and Grünau. | Pre-project bulk water tariffs at: Bethanie: N$ 13.15/m3 Grünau: N$ 15,60/m3 Year 1 bulk water tariffs at: Bethanie: N$ 13.80/m3 Grünau: N$ 16,40/m3 % increase in tariff at both Bethanie and Grünau = 5%, which was normal inflationary adjustment Year 2 adjustments: None | 1. Obtained an undertaking from the EE that during project execution tariffs will remain unchanged, except for normal inflationary adjustment. 2.Sensitised the EE on the need for post-project tariffs to remain affordable by means of adequate subsidisation. | No residual impact to date. Monitoring is continued. | n/a
3 – Marginalized and vulnerable Groups |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
4 – Human rights |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
5 – Gender equality and women’s empowerment |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
6 – Core labour rights |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
7 – Indigenous peoples |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
8 – Involuntary resettlement |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
9 – Protection of natural habitats |  |  | No threats were identified after EIA and final design. | n/a | n/a | n/a | n/a | n/a | n/a
10 – Conservation of biological diversity |  |  | Final design and EIA indicated that the project will not cause any harm to biological diversity. | n/a | n/a | n/a | n/a | n/a | n/a
11 – Climate change |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
12 – Pollution prevention and resource efficiency |  |  | Possible leakage or spillage of brine into soil | The final design provides for construction of sealed evaporation ponds to prevent leakage. Plan and implement a robust monitoring schedule to identify potential leakages from ponds and pipes. | Indicator =Number of leaks. Target = None. | No baseline | The final design provides for construction of sealed evaporation ponds to prevent leakage. Sizes of pond sufficient to prevent spillage, even in event of unusually intense rain. | Impact may be temporary contamination of soil above groundwater level. | Should contamination occur, remedial action will comply with applicable environmental and health legislation
13 – Public health |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
14 – Physical and cultural heritage |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
15 – Lands and soil conservation |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes (Refer to worksheet Risk Assessment)
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | n/a
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | As outlined in the worksheet Risk Assessment under Environmental Risks and under Social Risks
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Compliance Monitoring Programme issued to contractor at Grünau prior to start of construction. Compliance monitoring being executed during Grünau construction. Compiled ESM Audit Report for Grünau for February to August 2020. Continue to implement ESMP at Grünau and continue implementation monitoring until project completion. Implement ESMP at Bethanie and do implementation monitoring when construction starts.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | n/a
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11] |  | n/a
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
No USPs
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None received during the reporting period.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | No, only numbers of male and female beneficiaries at each of the two project sites.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes, there are indicators at outcome level.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good) | 0.44444
Women employees to gain technical knowledge on design and construction of rural desalination plants using renewable power and membrane technology. | Outcome 2: Knowledge of the design, construction and installation of hybrid renewable energy plants to power small desalination plants. | Indicator 2.2: Number of women and children participating in the development and installation of the plants. (Note: Error - Children are not applicable) | Baseline 2.2: Zero | Target 2.2: No target indicated in results framework. | Indicator 2.2: Good EE staff : Project management and execution: 9 male (75%), 3 female (25%) In training/capacity building: 2 male (25%) 6 female (75%) Engineering consultant staff: 3 male (60%) 2 female (40%) Environmental consultant staff: 4 male (44%) 5 female (56%) Contractor staff for Grünau construction: Male 100% Female 0% Temporary local labourers and security staff recruited for Grünau construction: 15, all male (100%)
A gender balanced group of tertiary institution students to gain hand-on experience in all aspects of plant establishment. | Outcome 3: Knowledge and understanding of operating the plants and of adjusting the treatment train to achieve required quality of water. | Indicator 3.4: Involvement of a gender balanced group of tertiary institution students in all aspects of plant establishment to gain hands-on experience. | Baseline 2.2: Zero | Target 3.4: 5 engineering university students; 2 females and 1 male for Bethanie; 1 female and 1 male for Grünau. | Indicator 3.4: Good Trade students assigned to Grunau Project: 3 female (60%) 2 male (40%)
An equal number of male and female students to be exposed on site to gain awareness of climate change, the objectives, principles and social effects of the project. | Outcome 4.4: Greater awareness among students of increasing climate change resilience through desalination and renewable energy. | Indicator 4.4: Number of tertiary social and environmental students who went on site visits, were involved in surveys and who became aware of and understand the objectives of the project, the principles of desalination, renewable energy, and the associated social effects on the beneficiaries. | Baseline 2.2: Zero | Target 4.4: 6 students at Bethanie and 4 at Grünau, equal number of males and females at each site. | Indicator 4.4: Good. First activity to take place once travel and assembly restrictions under Covid-19 have been lifted. Students have been identified. NUST students: Male 2 (33%) Female 4 (67%) UNAM students: Male 3 (60%) Female 2 (40%) All students: Male 5 (45%) Female 6 (65%) Total 11
Reduction in skin and scalp afflictions among mothers and their children due to improvement of water quality. | Outcome 5.3: Skin and scalp afflictions such as itching due to hardness of water is reduced. | Indicator 5.3: Percentage of sample population consisting of mothers and their children complaining of afflictions ascribed to water supplied. | Baseline 5.3: To be established by survey of sample population at project inception. | Target 5.3: Complaints by sample population reduced by 50% after first year of piloting. | Indicator 4.5: Poor Survey did not include establishment of baseline and has still not been done due to Covid-19 restrictions on travel and assembly of people.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
Acquisition and dissemination of knowledge is the prime objective of the project. Non-discrimination of women is a guiding principle in selection of trainees to acquire knowledge on desalination and renewable energy and in qualified staff involved in project execution. |  | Good for qualified professional staff. Good for EE trainee staff. Good for tertiary and trade students. Poor for contractor staff for Grünau construction. Poor for temporary local labourers and security staff at Grünau construction site.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | 1. Contractual agreement between the NIE and the EE stipulates that: "Where the environmental, social and gender assessment identifies environmental, social or gender risks, produce an environmental and social management plan that accompanies the assessment and that identifies those measures necessary to avoid, minimise, or mitigate the potential environmental, social and gender risks" 2. Project activities 3.4 and 4.5 indicate the requirement for gender balance 3. DRFN's ESP&G policy/manual has been made publicly available on its website 4. The NIE requested the EE to implement the public consultation/communication programme and the appointment of the Programme Public Relations Coordinator and the Gender and Social Expert as respectively proposed in the original project proposal (Environmental and Social Management Plan for Bethanie, Annexure 4, page 106) and in Table 38 on page 105.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | 1. Contractual agreement between the NIE and the EE stipulates that: "Where the environmental, social and gender assessment identifies environmental, social or gender risks, produce an environmental and social management plan that accompanies the assessment and that identifies those measures necessary to avoid, minimise, or mitigate the potential environmental, social and gender risks" 2. Project indicators 2.2, 3.4, 4.4 and 5.3 have gender-responsive elements. Progress with achievement of the indicator targets is indicated in Section 1 of this sheet and in the sheet "Project Indicators".
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | Partially. Arrangements for women's empowerment pertaining to EE qualified staff and trainees taking part in project execution are good. Same applies to EE staff attending training course. Arrangements pertaining to involvement of female beneficiaries in assembly of social data is unsatisfactory.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | The NIE requested the EE to implement the public consultation/communication programme and the appointment of the Programme Public Relations Coordinator and the Gender and Social Expert as respectively proposed in the original project proposal (Environmental and Social Management Plan for Bethanie, Annexure 4, page 106) and in Table 38 on page 105.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None received during the reporting period |  | n/a
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Component 1: Development of pilot desalination plants at Bethanie and Grünau |  | Outcome 2 | Completion on 31 July 2020 (end of Year 2) |  | Grünau: behind schedule by 2.5 months > Contractor appointed 13 January 2020 > Site hand-over 20 February 2020 > Construction in progress, completion foreseen mid-October 2020 > Estimated delay due to Covid-19 of 55 days Bethanie: behind schedule by estimated 13 months > Contractor not yet appointed by end of Year 2 | Grünau: U Bethanie: HU
| Component 2: Development of pilot hybrid renewable energy plants at Bethanie and Grünau |  | Outcome 2 | Completion on 31 July 2020 (end of Year 2) |  | Grünau: behind schedule by 2.5 months > Contractor appointed 13 January 2020 > Site hand-over 20 February 2020 > Construction in progress, completion foreseen mid-October 2020 > Estimated delay due to Covid-19 of 55 days Bethanie: behind schedule by estimated 13 months > Contractor not yet appointed by end of Year 2 | Grünau: U Bethanie: HU
| Component 3: Testing and commissioning of plants & training of staff and students |  | Outcome 2 | Completion on 31 July 2020 (end of Year 2) |  | Grünau: behind schedule by approximately 3 months > Testing and commissioning now scheduled for mid-October 2020 > Reliability run by contractor scheduled for mid-October 2020 to mid-January 2021 > Training is ahead of schedule Bethanie: behind schedule by approximately 13.5 months > Testing and commissioning now scheduled for mid-September 2021 > Reliability run by contractor scheduled for mid-September 2021 to mid-December 2021 > Training could not start since there is no infrastructure | Grünau: U Bethanie: HU
| Component 4: Piloting of the plants at Bethanie and Grünau |  | Outcome 2 | Execution 01 August 2020 to 31 July 2022 (Year 1 and Year 2) |  | As above | Grünau: U Bethanie: HU
| Component 5: Supply good quality water to the communities at the two project sites during piloting of the plants |  | Outcome 4 | Execution 01 August 2020 to 31 July 2022 (Year 1 and Year 2) |  | As above | Grünau: U Bethanie: HU
| Component 6: Sensitise project beneficiaries and local stakeholders at Bethanie and Grünau |  | Outcome 3 | Execution throughout project period |  | No activities carried out since completion of EIAs > At Grünau closure of schools and restrictions on travel and assembly of people due to Covid-19 have prevented execution of activities > At Bethanie, delay in start of construction precluded execution of activities | U
| Component 7: Information and knowledge dissemination |  | Outcome 3 | Execution primarily during Year 3 and Year 4 of project |  | Virtually no activities required during Year 2 | n/a
[6 empty] | Overall Rating | U
Please Provide the Name and Contact information of person(s) responsible for completeling the Rating section
| Name: | Dr Martin B Schneider
| Email: | martin.schneider@drfn.org.na
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Rating justification In the project proposal it was indicated that project execution was expected to start in April 2018, be completed in March 2022, with an execution period of four years. As part of the project, the plants at Bethanie and Grünau would be designed and constructed in Project Year 1 and the operational piloting of the plants would take place in Project Years 2, 3 and 4. At the inception workshop NamWater indicated that design and construction would in fact require two years and requested that the high-level execution schedule be changed to reflect two years for plant establishment and two years for plant operation. The DRFN approached the AF for approval to change the schedule presented in the project proposal and the NamWater request was approved. The approved high-level execution plan to be adhered to now entails that the project start date is 01 August 2018, that plant establishment should be completed by the end of Project Year 2 in July 2020, that the plants should be operated during the subsequent two Project Years and that execution of all other project activities should be completed by the end of Project Year 4 in July 2022. The plant at Grünau is expected to be completed approximately 2.5 months later and that at Bethanie approximately 13 months later than required under the high-level execution plan. The implication is that part of this 4-year project, which has been in execution for 2 years, is already more than 1 year behind schedule. Inefficiencies in the decision-making and approval processes within the EE and the requirement to apply the Public Procurement Act (Act 15 of 2015) and its regulations have resulted in major project execution delays. Amongst others this caused the award of the construction tender at Bethanie to be cancelled by order of the Public Procurement Review Panel since the tender was awarded outside the bid validity period. This caused a substantial delay in project execution. The tender was only readvertised approximately 19 weeks later, in part due to the real effect of Covid-19 restrictions imposed by Government and also to a perceived state of “Covid paralysis” that took hold of Government and public entities. The technical work done to date has been of a high standard. It is considered that achievement of Objective 1 of the project (to acquire knowledge and skills on how to effectively and efficiently desalinate poor quality groundwater on a small scale using RO technology and hybrid renewable energy technology ….) is being achieved. Objective 2 (to positively impact the lives of vulnerable individuals and communities at two project sites …) can be pursued once Component 1 has been completed and nothing prevents Objective 3 (to communicate the acquired knowledge and skills to stakeholders in the water supply sector …) to be achieved. Recommendations for next steps The major factor to be considered now is whether the two plants can be run for a sufficiently long period before the end of the 4-year project to obtain the desired operations data. By the date of the resubmission of this document on 23 October 2020: 1. The NIE and the EE had agreed that a request would be submitted to the AFB Secretariat for a project extension of 1 year to allow Objective 4 to be achieved. 2. No steps to prevent further delays due to application of the Public Procurement Act (Act 15 of 2015) and its regulations are required since the new construction tender for mechanical and electrical works at Bethanie had been awarded and the construction site had been handed over to the contractor. 3. The plant at Grünau had been completed and inaugurated. Execution of Component 4 at this site has started and no specific steps are required to ensure that the activities can continue. 4. The EE is endeavoring to remove inefficiencies in their activities and to comply with set requirements as per the NIE-EE funding agreement. No further steps are currently required over and above the continued application of sound project management practices at both the implementation and execution levels.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | ESIA and ESMP approved and Environmental Clearance Certificate issued |  | Outcome 2 | 2019-11-11 |  | Achieved 19 December 2019 | S
| Tenders advertised for construction at both sites |  | Outcome 2 | 2019-08-08 |  | Achieved 15 August 2019 | S
| Contractor appointed for construction at Grünau |  | Outcome 2 | 2019-11-25 |  | Achieved 13 January 2020 | U
| Contractor appointed for construction at Bethanie |  | Outcome 2 | 2019-11-25 |  | Achieved 07 September 2020 | U
| Construction of works starts at Grünau |  | Outcome 2 | 2020-01-20 |  | Achieved 28 January 2020 | S
| Construction of works starts at Bethanie |  | Outcome 2 | 2020-01-30 |  | Foreseen for 01 October 2020 | U
| Do testing & commissioning of works at Grünau |  | Outcome 2 | 2020-07-31 |  | Foreseen for 14 October 2020 | U
| Do testing & commissioning of works at Bethanie |  | Outcome 2 | 2020-07-31 |  | Foreseen for 30 August 2021 | U
| Start operation and piloting of plants at Grünau |  | Outcome 2 | 2020-07-31 |  | Foreseen for 14 October 2020 | U
| Start operation and piloting of plants at Bethanie |  | Outcome 2 | 2020-07-31 |  | Foreseen for 30 August 2021 | U
[6 empty] | Overall Rating | U
Please Provide the Name and Contact information of person(s) responsible for completeling the Rating section
| Name: | Mr. R Likando
| Email: | likandor@namwater.com.na
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Based on 1 to 4 below, overall project execution is rated as Unsatisfactory in terms of execution within initially committed and agreed timelines but the attainment of project objectives is not affected. 1. Due to the nature of the project, no targets to be achieved in terms of the results framework arise in Project Year 2. 2. Critical risks are listed and described in the worksheet Risk Assessment. additionally, the following factors contributed immensely on delay of scheduled project activities: (a) poor performance of appointed ESIA consultant and subsequent delay in obtaining environmental clearances for both sites since award of tenders was on a pre-condition of approval of the ESIA, ESMP and granting of environmental clearance by the Ministry of Environment, Forestry and Tourism, (b) impact of COVID-19 restrictions on delivery of goods and services due to supply chain disruptions, (c) cancellation of tender award for construction services at Bethanie in compliance with the order of the Review Panel issued in February 2020, (d) negotiations and settlement on land rights at all project sites. 3. No MTR carried out - this is PPR2. 4. The overall rating is U but the initially agreed project objectives are still to be achieved.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc.…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective 1: Acquire knowledge and skills on how to effectively and efficiently desalinate poor quality groundwater on a small scale using RO technology and hybrid renewable energy technology that can be applied to improve the resilience of rural communities against climate change
Outcome 1: Knowledge of the design, construction and installation of small desalination plants using RO technology. | Indicator 1.1: The technical knowledge to plan, design, and construct small-scale desalination plants using RO technology. Indicator 1.2: Number of plants design prepared. | Baseline 1: The existing NamWater knowledge relates to experimental micro-plants using RO technology conducted at (Epukiro Post 3 and Bethanie). No information about the membrane technology operating on renewable resource exists. CuveWaters international project team installed four different types of small-scale groundwater thermal desalination plants in the Omusati Region at Amarika and Akutsima but not operated with renewable energy. | Progress 1: Target 1 is being pursued and will be achieved when construction is complete. Construction site establishment at Grünau took place in mid-March 2020 and plant commissioning is currently scheduled for mid-October 2020 after approximately 53 days of delay was experienced due to Covid-19 lockdown. Award of the construction tender for Bethanie was cancelled in March 2020. The tender was re-advertised with closing date 07 August 2020. Acquisition of the following knowledge under Indicator 1.1 (Target 1.1) has been demonstrated for both desalination plants: 1. Planning 2. Concept design 3. Preliminary design 3. Construction specifications 4. Construction procurement documentation 5. Technical and financial evaluation of bids At Grünau knowledge was acquired on construction/installatiof the civil, mechanical and electrical elements of the treatment plant. | Target 1.1: (Achievement in progress) Demonstration by NamWater that the technical knowledge has been acquired by establishing 2 small-scale desalination plants using RO technology. Target 1.2: (Achieved) Complete design of two plants
Outcome 2: Knowledge of the design, construction and installation of hybrid renewable energy plants to power small desalination plants. | Indicator 2.1: The technical knowledge to plan, design, and install hybrid renewable energy (sun/wind) systems to power small-scale desalination plants. | Baseline 2: The existing NamWater knowledge relates to application of photovoltaics for powering communication equipment and borehole pumps. | Progress 2.1: Target 2 is being pursued and will be achieved when construction is complete. Construction site establishment at Grünau took place in mid-March 2020 and plant commissioning is currently scheduled for mid-October 2020 after approximately 53 days of delay was experienced due to Covid-19 lockdown. Award of the construction tender for Bethanie was cancelled in March 2020. The tender was re-advertised with closing date 07 August 2020. Acquisition of the following knowledge under Indicator 1.1 (Target 1.1) has been demonstrated for both plants: 1. Planning 2. Concept design 3. Preliminary design 3. Construction specifications 4. Construction procurement documentation 5. Technical and financial evaluation of bids At Grünau knowledge was acquired on construction/installatiof the civil, mechanical and electrical elements of the power plant. | Target 2.1: (Achievement in progress) Demonstration by NamWater that the technical knowledge has been acquired by establishing two hybrid renewable energy (sun/wind) systems to power small-scale desalination plants.
| Indicator 2.2: Number of women and children participation in the development and installation of the plants. |  | Indicator 2.2: EE staff : Project management and execution: 9 male (75%), 3 female (25%) In training/capacity building: 2 male (25%) 6 female (75%) Engineering consultant staff: 3 male (60%) 2 female (40%) Environmental consultant team: 4 male (44%) 5 female (56%) Contractor staff for Grünau construction: Male 100% Female 0% | Target 2.2: (No target set)
| Indicator 2.3: Number of renewable energy plants units installed. |  | Indicator 2.3: No installation has yet been completed. Installation of one is in progress, to be completed early October 2020. | Target 2.3: 2 energy plants to be installed
Outcome 3: Knowledge and understanding of operating the plants and of adjusting the treatment train to achieve required quality of water. | Indicator 3.1: Sufficient knowledge to commission the small-scale RO desalination plants powered by hybrid renewable energy (sun/wind) systems referred to in Indicator 1.1 above and to execute a reliability run of 3 months after commissioning. | Baseline 3: The existing NamWater knowledge relates to experimental micro-plants using RO technology. | Progress 3.1: Operation is to start after construction and commissioning of the plants. Construction at Grünau is scheduled for completion in early October 2020. Construction at Bethanie has not yet started. | Target 3.1: Two commissioned desalination plants, powered by hybrid renewable energy (that have demonstrated the ability to produce blended desalinated water).
| Indicator 3.2: Trained operations and maintenance staff. |  | Progress 3.2: Little progress towards achieving Target 3.2 - training is scheduled to take place during the 3-month reliability run after construction and commissioning. Requirement for training has been specified in the construction tender. | Target 3.2: 5 trained water operators and 1 trained Level 2 water artisan.
| Indicator 3.3: Training, operations and maintenance manuals. |  | Progress 3.3: Little progress towards achieving Target 3.3 - compilation of manuals is scheduled for execution towards end of construction. Specification for manuals has been included in construction tender. | Target 3.3: 1 manual each for training, operations and maintenance. | Trade students assigned to Grunau Project: 3 female (60%) 2 male (40%)
| Indicator 3.4: Involvement of a gender balanced group of tertiary institution students in all aspects of plant establishment to gain hands-on experience. |  | Progress 3.4: 5 male and 6 female university students have been identified who will become involved once Covid-19 restrictions are lifted. 5 trade students are taking part in construction of the Grünau plant. | Target 3.4: 5 engineering university students; 2 females and 1 male for Bethanie; 1 female and 1 male for Grünau. |  | In training/capacity building: 2 male (25%) 6 female (75%)
Outcome 4.1: Knowledge of how to optimize the design, construction, operation and maintenance of small RO desalination plants using hybrid power supplies. | Indicator 4.1: 2 optimised desalination plants, powered by hybrid renewable energy plants, yielding water of good quality in sufficient quantities. Calculated cost of bulk water supplied, based on capital and operating cost, broken down to the level of RO plants, power plants and existing infrastructure. A comprehensive set of information. Number of tertiary social and environmental students who went on site visits, and who became aware of and understand the objectives of the project, the principles of desalination, renewable energy, and the associated social effects on the beneficiaries. | Baseline 4.1: The existing NamWater knowledge relates to experimental micro-plants using RO technology. No similar or comparable plants exist. Water presently supplied does not comply with the Namibian quality standards for drinking water. | Progress 4.1: No progress - operation is scheduled to start after commissioning. | Target 4.1: Bulk water delivered from terminal reservoir: • Chemical quality: o Daily measured conductivity compliant with water quality standards for 80% of tests during first year; thereafter compliant for 100% of tests
o Chemical analysis done in Windhoek compliant with water quality standards for 80% of tests during first 6 months, 90% of tests for second 6 months, for next year 100% compliant; analysis initially once per week, with period to be extended as dictated by results.
• Microbiological quality: o Free chlorine daily tested on site always to comply with Standard o Microbiological analysis in Windhoek compliant with water quality standards for 100% of tests; analysis initially once per fortnight, with period to be extended as dictated by results.
• Volume: o Average supply capacity of 460 m3/day at Bethanie and 100 m3/day at Grünau • Continuity of supply: o No interruption of water supply, except for reduction in supply for 24 hours with advanced warning of 2 days in case of major maintenance
Outcome 4.2: Information on the cost of bulk water supply from the two project plants. | Indicator 4.2: Calculated cost of bulk water supplied, based on capital, operational and maintenance cost, broken down to the level of RO plants, power plants and existing infrastructure. | Baseline 4.2: No desalinated water is currently supplied at the two sites, thus there is no baseline. | Progress 4.2: No progress - scheduled to be calculated at ends of first year and second year of plant operation. | Target 4.2: Calculated at ends of first year and second year of piloting, as well as for the two-year period. Total unit cost to be less than 30% of what it would be to import the same volume of good quality water from a reliable source.
Outcome 4.3: Information on the technical and financial feasibility and viability of small-scale RO desalination plants powered by hybrid renewable energy (sun/wind) systems. | Indicator 4.3: A comprehensive set of information. | Baseline 4.3 The existing NamWater information relates to experimental micro-plants using RO technology. No similar or comparable plants exist. | Progress 4.3: Good progress has been made with generation of technical information relating to design and construction, as well as with information on construction costs. Technical and financial information pertaining to operation and maintenance can only be collected once the schemes have been commissioned. | Target 4.3: A comprehensive report describing the technical and financial feasibility and viability of small-scale RO desalination plants powered by hybrid renewable energy (sun/wind) systems.
Outcome 4.4: Greater awareness among students of increasing climate change resilience through desalination and renewable energy. | Indicator 4.4: Number of tertiary social and environmental students who went on site visits, were involved in surveys and who became aware of and understand the objectives of the project, the principles of desalination, renewable energy, and the associated social effects on the beneficiaries. | Baseline 4.4: No awareness based on practical exposure. | Progress 4.4: First activities postponed due to Covid-19 restrictions on travel and assembly of people; to start once restrictions are lifted. Students have been identified. NUST students: Male 2 (33%) Female 4 (67%) UNAM students: Male 3 (60%) Female 2 (40%) All students: Male 5 (45%) Female 6 (65%) | Target 4.4: 6 students at Bethanie and 4 at Grünau, equal number of males and females at each site.
Objective 2: Positively impact the lives of vulnerable individuals and communities at two project sites, by supplying good quality water, raising awareness of the effects of climate change, promoting judicious use of water and explaining the need for water tariffs.
Outcome 5: Improvement in health of the beneficiaries.
Outcome 5.1: Development of fluorosis in children is halted. | Indicator 5.1: Percentage of children residing at Bethanie and Grünau under the age of 6 months indicated with fluorosis as from end of first year of piloting. | Baseline 5.1: To be established from records at the local clinics. | Progress 5.1: No progress - scheduled for assessment at end of first year of supplying desalinated water. (Indicator is impractical). | Target 5.1: Baseline percentage of children under the age of 6 months indicated with fluorosis reduced by 50% in the first 6 months of piloting, and by 100% thereafter.
Outcome 5.2: Gastro-enteritis is reduced, especially among children. | Indicator 5.2: Percentage of beneficiaries at Bethanie and Grünau diagnosed with gastro-enteritis as from inception of piloting. | Baseline 5.2: To be established from records at the local clinics. | Progress 5.2: No progress - scheduled for assessment at end of first year of supplying desalinated water. | Target 5.2: Baseline percentage of beneficiaries at Bethanie and Grünau diagnosed with gastro-enteritis reduced by 50% by end of project period.
Outcome 5.3: Skin and scalp afflictions such as itching due to hardness of water is reduced. | Indicator 5.3: Percentage of sample population consisting of mothers and their children complaining of afflictions ascribed to water supplied. | Baseline 5.3: To be established by survey of sample population when travel and assembly restrictions under Coveid-19 are lifted. | Progress 5.3: Survey did not include establishment of baseline - still to be done. | Target 5.3: Complaints by sample population reduced by 50% after first year of piloting.
Outcome 5.4: Increase in resilience of beneficiaries to further deterioration of groundwater quality due to climate change. | Indicator 5.4: Correlation between deteriorating groundwater quality and health conditions addressed under Outcome 1 above. | Target 5.4: Targets described relevant to Outcome 5.1 above. | Progress 5.4: No progress - treated water not yet supplied. | Target 5.4: Zero correlation between groundwater quality deterioration and non-achievement of targets relevant to Outcome 1 above.
Objective 3: Communicate the acquired knowledge and skills to stakeholders in the water sector and thereby promote the mainstreaming of such small-scale desalination technology and systems in the country.
Outcome 6: Awareness by beneficiaries of climate change effects, understanding of the project intervention, acceptance of responsibility to use water judiciously, and the need to pay water tariffs. | Indicator 6.1: Percentage of school learners and teachers at Bethanie and Grünau reached by means of visits to schools to create awareness of climate change effects and the project intervention, and to convey the need use water judiciously and why water tariffs are necessary. | Baseline 6.1: Social stakeholder consultations and engagements were held at Bethanie and Grünau during project formulation; 1 each with officials and general public at each of the project sites. Schools were not visited. | Progress 6.1: No progress - scheduled for execution during construction but cannot be undertaken until Covid-19 restrictions are lifted. Schools are closed and restrictions exist on travel and assembly of people. | Target 6.1: 80% of all school learners and teachers at the three schools at Bethanie and the school at Grünau to attend visits to schools.
| Indicator 6.2: Number of interactive public meetings at Bethanie and Grünau to create awareness by beneficiaries of climate change effects, an understanding of the project intervention, acceptance of responsibility to use water judiciously, and the need to pay water tariffs. | Baseline 6.2: As above. | Progress 6.2: Two meetings held before construction - 10 June and 22 July 2019. These are in addition to the target meetings. | Target 6.2: 2 interactive public meetings per annum at each of Bethanie and Grünau.
| Indicator 6.3: Number of meetings with community leaders and local officials at Bethanie and Grünau to further strengthen their awareness of climate change effects, an understanding of the project intervention, acceptance of responsibility to use water judiciously, and the need to pay water tariffs; this includes site visits to show progress with plant establishment and subsequently the operation of the plants. | Baseline 6.3: As above. | Progress 6.3: Two meetings were held before construction - 11 June and 23 July 2019. These are in addition to the target meetings. No annual meetings were held due to restrictions under measures to combat Covid-19. | Target 6.3: 2 meetings per annum at each of Bethanie and Grünau
| Indicator 6.4: Distribution of appropriate and site-specific information and learning material to school learners and teachers, and to adults. | Baseline No appropriate material is yet available at the project sites. | Progress 6.4: No progress. | Target 6.4.1: 1 printed school-level information folder provided to each school learner attending the school visits
Target 6.4.2: 20 printed school-level information folders provided to each school teacher
Target 6.4.3: 1 printed information folder provided to each attendee of public meetings and meetings with officials
Target 6.4.4: 100 printed information folders provided to each clinic and church at the project sites for distribution to the public.
Outcome 7: Stakeholders at regional and national level who are informed of the project results, including the viability and feasibility of small-scale desalination plants powered by hybrid renewable energy as an alternative to importing good quality water over long distances. | Indicator 7.1: Information sharing events with regional and national decision and policy makers in the water supply and environmental sectors. | Baseline 7: No project results are available prior to the start of project execution. | Progress 7.1: No progress - scheduled for second half of project period. | Target 7.1: 1 information sharing event, combined with visits to project sites, during the second half of the project period.
| Indicator 7.2: Technical information sharing events with government officials, consultants, university staff, civil society members active in the water supply and environmental sectors. |  | Progress 7.2.1: No progress - Scheduled for second half of project period. Will be delayed until restrictions under Covid-19 on travel and assembly of people are lifted. | Target 7.2.1: 1 information sharing event combined with visits to project sites, during the second half of the project period.
|  |  | Progress 7.2.2: No progress - scheduled for the last year of the project period. | Target 7.2.2: 1 information sharing event presented in Windhoek in the last year of the project period.
| Indicator 7.3: Provision of project information throughout the project period by means of electronic and print media, and presentation of the project at national/international conferences or meetings. |  | Progress 7.3.1: No progress - prevented by government regulations to combat the spread of Covid-19 | Target 7.3.1: 2 current affairs radio and TV programmes each, one during construction and the other during the piloting period.
|  |  | Progress 7.3.2: Continuous updating delayed. | Target 7.3.2: Websites of EE and NIE continuously updated with project information.
|  |  | Progress 7.3.3: No progress, except for information collection - publication scheduled for last year of project period. | Target 7.3.3: 1 final project report published on the EE website in last year of project period.
|  |  | Progress 7.2.4: No progress - scheduled for second half of final project year. | Target 7.3.4:1 1 presentation of project at a water conference.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Negative: Project execution has fallen behind schedule due to the delays that are extensively described below. Positive: It is considered that the technical work done to date is of a high standard and that the EE has already acquired extensive knowledge and skills through involvement in the design and construction of the plants. The training programme for staff-in -training, tertiary students and trade students is regarded as successful. Lessons learned: It is imperative that the technical team members of the EE should be involved in compilation of the project proposal in order that the execution strategy be agreed to beforehand (not done). It is also essential that a signed agreement be established between the NIE and the EE to regulate execution of the project (done).
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Summary of delays Project execution has experienced various delays. The approved project proposal indicated that the project would start in April 2018 and have a duration of 4 years. Components 1 to 3 (establishment and commissioning of two plants) would be carried out in Year 1, Components 4 and 5 (pilot operation of the plants and the supply of water) would run through Years 2 to 4, and activities under Components 6 and 7 would take place throughout the project. At the project inception workshop (which only took place in July 2018) the EE presented its final strategy for executing the project. Adoption of this strategy necessitated changes to be made to both the execution schedule and the projected annual cash flows under the Project Activities Cost (A) that were presented in the approved project proposal. The EE requested that Components 1 to 3 should be rescheduled for completion in Year 2, in contrast to the initially envisaged completion in Year 1. The project duration would remain 4 years, with the implication that pilot operation of the plants and the supply of water would be reduced from 3 years to 2 years. The AF approved the requested changes.
Currently, at the end of Year 2, further execution delays have accumulated. Completion of Component 3 at Grünau is expected to be 3 months late and that at Bethanie to be 13.5 months late. If the project period remains 4 years, the implication is that the originally foreseen period of 3 years for pilot operation of the plants and the supply of water will now be reduced to 1 year 9 months at Grünau and to 10 months at Bethanie. The effect of these delays on achievement of the project objectives and the possible need to extend the project period still have to be assessed.
Causes of delays Factors causing or contributing to delays are the following:  The technical units of the EE that would be responsible for project execution had not been involved or consulted adequately during compilation of the project proposal and thus there was a lack of project ownership at the outset.  The execution strategy for the project had not been established prior to approval of the project.  Prior to approval of the project the technical resources of the EE were already under strain due to a large number of projects under execution or identified for execution.  The EE as a large State-owned entity is subject to bureaucracy, cumbersome administrative and project processes, slow decision making and inefficiencies in the approval processes.  The requirement to apply the Public Procurement Act (Act 15 of 2015) and its regulations have caused project execution delays.  The outbreak of the Covid-19 pandemic and the associated combat measures imposed affect all aspects of project implementation.
Examples of delays Execution strategy and high-level execution schedule: It took 4 months to produce an execution strategy and 8 months to establish a high-level execution schedule. By the time the schedule was produced, the project was in the 4th month of intended project execution as per the approved project proposal. The NIE requested the EE on 16 November 2017 to produce a strategy for project execution and a more detailed execution plan than the one in the project proposal. This information was only provided 4 months later on 13 March 2018. The schedule provided for completion of construction in March 2020, i.e. at the end of Year 1 of the project period. However, at the inception workshop in mid-July 2018 the EE indicated that construction would only be completed in July 2020. The accordingly adjusted high-level schedule subsequently became the approved project schedule.
Grant agreement between NIE and EE: The NIE submitted a first draft agreement to the EE on 30 January 2018. It took approximately 4 months before the final agreement was signed. Project inception workshop: Based on the date of the inception workshop, execution of the project started 4 months later than indicated in the approved project proposal. However, the late scheduling of the workshop did not delay execution of the project. The proposed start date for project execution was April 2018, but execution activities already started in March 2018 with compilation of the Terms of Reference (ToR) for the appointment of engineering consultants for preliminary and final design of the plants. It was considered highly desirable that the engineering consultant, who would be an important member of the project team, should also attend the project inception workshop. It was thus decided to postpone the project inception workshop until after appointment of the consultant, which was anticipated for end of June 2018. However, the AF directs that the inception workshop must take place within 6 months of receipt of the first tranche, which happened on 25 January 2018. When it became clear that the consultant would not be appointed before this period ran out, the workshop was held on 16/17 July 2018.
Appointment of consulting engineer: From the time that the EE provided the first draft Terms of Reference for the appointment of consulting engineers it took 4.5 months until the letter of award was issued to the successful tenderer. The period from tender closure to tender award alone was 4 months. Appointment of environmental consultant: From the time that the EE received the first draft Terms of Reference for the appointment of environmental consultants it took 11 months until the letter of award was issued to the successful tenderer. The period from tender closure to tender award alone was 5 months. This included a temporary stoppage of the bid evaluation process of a month due to an irregularity by one of the tenderers. Bethanie construction tender process: The initial process to appoint a contractor for construction of the plant at Bethanie failed. From the time that the tender was first advertised to the appointment of a contractor after re-advertisement took approximately 13 months.
The tender was first advertised on 15 August 2019. One of the tenderers requested an official review of the technical bid evaluation report and the matter went to the Public Procurement Review Panel. Award of the tender was cancelled by the panel’s order since the tender had been awarded outside the bid validity period. From the panel’s order it took 1 month to cancel the tender and another approximately 4 months to re-advertise the construction tender. Some of this delay can be ascribed to Covid-19. Covid-19: The Covid-19 pandemic detrimentally affected project implementation. It caused a disruption of supply chains, leading to delays of an estimated 53 days in procurement of instrumentation and equipment under the Grünau construction tender. Government placed a prohibition on tender advertisement under the Public Procurement Act for a period of approximately one month, leading to a delay in procurement of construction services for the Bethanie plant. Everybody rendering non-essential services had to work from home for a period of approximately 1 month and restrictions were placed on assembly of people and on travelling. This negatively affected office activities by the EE and temporarily interrupted civil works at Bethanie.
Breakdown of NIE-EE management activities: For a period of approximately 6 months (as from January 2020 to the end of Project Year 2 in July 2020) the NIE was not afforded the opportunity to fully exercise its implementation management activities and to ensure that project execution remained on track. This is considered to have led to a number of execution activities going astray and to associated project delays. The grant agreement between the NIE and the EE provides for project performance/planning meetings to take place within the first two weeks of each project quarter. At these meetings progress and expenditure in the previous quarter is reviewed, the detail execution schedule and the projected cash flow for the next quarter is discussed, risk management is assessed, disbursement requests by the EE are consolidated, and matters that may affect project execution are discussed and decisions made. The last quarterly progress/performance meeting took place on 22 November 2019. All attempts by the NIE to have the required meetings proved unsuccessful and as a result the quarterly meetings for Quarter 3 and Quarter 4 of Project Year 2 did not take place. As a result the EE decided on certain risk management approaches without discussing them with the NIE, which have led to further delays.
Measures taken to reduce delays: The majority of the causes of delays are inherent to the system within which the EE operates and thus cannot be removed or changed by the NIE. The same applies to Covid-19 and the measures imposed by Government to combat the spread of the disease. What the NIE has done is:  Prior to project inception ensured that the project would be assigned to the most experienced project manager at the EE.  Ensured that the EE staff to be involved in project execution were aware of the nature, scope, objectives, targets and execution deadlines of the project by having a number of pre-project planning and preparation meetings with them.  Visited the CEO of the EE to explain the importance of successfully completing the project as per the project proposal.  Ensured that all activities to be carried out by the NIE (e.g. comment on and “no objection” to terms of terms of reference, tender documents, proposed award of tenders, etc.) are carried out as expediently as possible to ensure that the NIE does not cause any delay in the subsequent activities by the EE.  Went beyond what could be considered the responsibility of the NIE in assisting the EE with activities to carried out by them that could have an effect on project progress.
 In the agreement with the EE provided for regular progress/performance meetings to take place to ensure adherence to project schedules and to discuss matters that could affect project execution and attempted to ensure that the meetings did take place.  Impressed on the EE to carry out identified mitigation actions to ensure that risks of project delays are mitigated.  Went to great lengths to ensure that payments to the contractor at Grünau were made as specified in the construction tender to ensure that procurement could continue without interruption.  Made every attempt to get the EE to keep to the detailed execution schedules.  Towards the end of Project Year 2, in an attempt to motivate the EE to improve their performance and to get the project on track again, wrote a letter to the CEO of the EE. The letter conveyed that the EE was non-compliant with various of their obligations under the grant agreement with the NIE and stated that failure to remedy the indicated instances of non-compliance entitled the NIE to eventually suspend or cancel the agreement and thereby the project.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Measures undertaken are described above under "Measures taken to reduce delay"
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | All environmental and social safeguard measures that are infrastructure specific have been incorporated in plant design, while measures that are specific to the construction stage have been incorporated in the construction tenders. The effectiveness of these measures have been demonstrated during construction of the Grünau plant. Measures relating to plant operation are applicable only after commissioning has taken place. Safeguard measures that are not infrastructure related have been scheduled, and no unwanted negative impacts have yet arisen.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | This project is principally of a technical nature. Gender considerations were addressed in the EIA/ESMP, but the design and construction of the plants can be regarded as gender-neutral. To date, specific gender considerations influenced the selection of EE staff-in training, to be involved in executing the project and of staff members to attend a training course on design of desalination plants (more than 50% of the staff members are women). The same applies to selection of tertiary students and trade students involved.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The project has not yet reached the midpoint of execution and it is too early to answer the question..
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The concept is sound, namely treating poor quality groundwater to a level suitable for human consumption while using renewable energy sources for both borehole water abstraction and for the treatment process. The crucial factors that will determine the potential for replication is the cost of the treated water compared to the cost of importing good quality water over long distances and the level of expertise required to operate and maintain the plants. The financial viability will differ from one locality to another. The capital cost at the two sites is already known, but the total unit cost of water will only be available after completion of pilot operation. The required level of training of the operators and maintenance staff will also be clear at that stage.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc.) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | General: Implementation of a project that pilots new approaches is time consuming and the time estimated in the project proposal should not be under-estimated. Positive: In such projects it is essential to make use of existing external sources of expertise and the EE should not attempt to reinvent the wheel. Negative: The principle members of the project team that will execute the project should be involved in the design of the project and in compiling the project proposal. With projects carried out by government or State-owned entities there should be a high-ranking project sponsor or project champion who can ensure that the project receives the required level of priority and who can intervene when things go wrong. It should be kept in mind that the NIE has no control over the utilisation of human resources of the EE and can only apply high-level project management techniques in implementing the project.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The concept is sound, namely treating poor quality groundwater to a level suitable for human consumption while using renewable energy sources for both borehole water abstraction and for the treatment process. The crucial factors that will determine the potential for replication is the cost of the treated water compared to the cost of importing good quality water over long distances and the level of expertise required to operate and maintain the plants. The financial viability will differ from one locality to another. The capital cost at the two sites is already known, but the total unit cost of water will only be available after completion of pilot operation. The required level of training of the operators and maintenance staff will also be clear at that stage.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The project has not yet reached the midpoint of execution and it is too early to answer the question..
What measures are/have been put in place to ensure sustainability of the project/program results? | The EE is the national supplier of bulk water. All infrastructure established under the project will become the property of the EE after completion of the project and the EE has undertaken to continue management, operation and maintenance of the plants.
What measures are being/could have been put in place to improve project/program results? | The project has not yet reached the midpoint of execution and it is too early to answer the question..
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Design of the plants was carried out by a joint venture of engineering consultants with experience in RO and generation of sun/wind power, with oversight and guidance provided by EE staff who have knowledge and experience of establishment, operation and maintenance of water treatment and supply infrastructure.
If learning objectives have been established, have they been met? Please describe. | The project has not yet reached the midpoint of execution and it is too early to answer the question..
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | There have been no difficulties in accessing existing technical information.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | The project has not yet reached the midpoint of execution and it is too early to answer the question..

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | NAM/NIE/Water/2015/1
Implementing Entity | Desert Research Foundation of Namibia (DRFN)
Type of implementing entity | NIE
Country | Namibia
Region | Africa
Sector | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
| Bethanie | Total | 0 | 0 | 0 | Total | 2978 | 2978 | 0 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 51% | 51% | 0% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries (<14 years) | 0% | 0% | 0% | % of Youth beneficiaries | 30% | 30% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
| Grunau | Total | 0 | 0 | 0 | Total | 500 | 500 | 0
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 49% | 49% | 0%
|  | % of Youth beneficiaries (<14 years) | 0% | 0% | 0% | % of Youth beneficiaries | 30% | 30% | 0%
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Water management | 1: No capacity | Public | Local | Water management | 4: High capacity
Output 2.2 Targeted population groups covered by adequate risk reduction systems | Indicator 2.2.1: Percentage of population covered by adequate risk-reduction systems | % of population targeted | % of female population targeted | % of male population targeted | % of children under 14 years targeted | % of population targeted | % of female population targeted | % of male population targeted | % of children under 14 years targeted | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
| Indicator 2.2.2: No. of people affected by climate variability | Total population | Females | Males | Children under 14 years | Total population | Females | Males | Children under 14 years | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | 2978 | 1459 | 1518 | 893 | 2978 | 1459 | 1518 | 893
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0% | 0% | 1: Aware of neither |  | 1740 | 50% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | National | 2: Partially responsive (Lacks most elements) |  | Water management | Regional | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 5: Fully improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.2: No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) | Number of assets | Type |  | Sector | Number of assets | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 2 | Community |  | Water management | 2 | Community |  | Water management
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adaptive capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnerability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strengthened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste