## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 2019-2020
| Project Title: | Adaptation to the Impacts of Climate Change on Peru’s Coastal Marine Ecosystem and Fisheries
| Project Summary: | The main challenge consists in increasing the resilience of the coastal marine ecosystems and the coastal communities (particularly the artisanal fishing communities) to climate change impacts. The main beneficiaries of this project are the artisanal fishing communities, whose livelihoods largely depends on the status of the coastal marine ecosystems, which are already subject to a number of non-climatic threats.The overall objective of the project is to reduce the vulnerability of coastal communities to impacts of climate change on the coastal marine ecosystems and fishery resources.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Peruvian Trust Fund for National Parks and Protected Areas - Profonanpe | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | NIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Perú | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Máncora, Los Órganos, El Ñuro y Cabo Blanco (04°05 - 04°15'S) Don Martin Island to Punta Salinas (11 ° 01'S - 11 ° 19'S), and includes Végueta, Huacho and Carquín | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2015-10-09
IE-AFB Agreement Signature Date: |  | 2016-05-01 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2018-05-17 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | May 2020
| Original Completion Date: | September 2022
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | José Zavala Huambachano | Dominican Republic
| Email: | coordinador.pamc@acomerpescado.gob.pe | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Rosa Morales Saravia | Equatoral Guinea
| Email: | rmorales@minam.gob.pe | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Omar Corilloclla Terbullino | Fiji
| Email: | ocorilloclla@profonanpe.org.pe | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Felix Fabian Puente de la Vega Chumbe | Georgia
| Email: | fpuentedelavega@acomerpescado.gob.pe | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Dimitri Gutiérrez Aguilar | Grenada
| Email: | dgutierrez@imarpe.gob.pe | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [April 30th, 2019] |  |  |  |  | Financial information: cumulative from project start to [April 30th, 2020] | [5 empty] | Financial information: cumulative from project start to [April 30th, 2021]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS | [5 empty] | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? | [5 empty] | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [1/05/2016] | 2979902.3305 |  |  |  | Estimated cumulative total disbursement as of [1/05/2016] |  | 2979902.3305 |  |  |  | Estimated cumulative total disbursement as of [30/04/2021] |  | 4679999.3305
Add any comments on AF Grant Funds. (word limit=200) |  |  |  |  | Add any comments on AF Grant Funds. (word limit=200) | [5 empty] | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | The grant has been disbursed in a current account that in Peru doesn´t generate incomes. |  |  |  | INVESTMENT INCOME |  | The grant has been disbursed in a current account that in Peru doesn´t generate incomes. |  |  |  | INVESTMENT INCOME |  | The grant has been disbursed in a current account that in Peru doesn´t generate incomes.
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant | [5 empty] | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA | [5 empty] | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION |  | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION |  | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION |  | AMOUNT
| Project Output | Activity programmed in the Annual Operation Plan (AOP) 2018/2019 |  |  |  |  | Project Output | Activity programmed in the Annual Operation Plan (AOP) 2019/2020 |  |  |  |  | Project Output | Activity programmed in the Annual Operation Plan (AOP) 2020/2021
| OUTPUT 1.1.1. Adoption of sustainable fishing methods to tackle non-selective fishing gear based on EAF principles directed to target species vulnerable to climate change | 1.1.1.1. Implementation of a conversion pilot from fishing gillnets to long-lines for tuna yellowfin in the Mancora pilot area | 0 |  |  |  | OUTPUT 1.1.1. Adoption of sustainable fishing methods to tackle non-selective fishing gear based on EAF principles directed to target species vulnerable to climate change | 1.1.1.1. Implementation of a conversion pilot from fishing gillnets to long-lines for tuna yellowfin in the Mancora pilot area | 126.01 |  |  |  | OUTPUT 1.1.1. Adoption of sustainable fishing methods to tackle non-selective fishing gear based on EAF principles directed to target species vulnerable to climate change | 1.1.1.1. Implementation of a conversion pilot from fishing gillnets to long-lines for tuna yellowfin in the Mancora pilot area | 11483.1
|  | 1.1.1.2. Following-up of anchovy fishing gears adoption in the Huacho pilot area | [5 empty] | 1.1.1.2. Following-up of anchovy fishing gears adoption in the Huacho pilot area | 1008.04 |  |  |  |  | 1.1.1.2. Following-up of anchovy fishing gears adoption in the Huacho pilot area | 15982.43
|  | 1.1.1.3. Research of the adoption of anchovy fishing gears adoption in the Huacho pilot area | [5 empty] | 1.1.1.3. Research of the adoption of anchovy fishing gears adoption in the Huacho pilot area | 271.96 |  |  |  |  | 1.1.1.3. Research of the adoption of anchovy fishing gears adoption in the Huacho pilot area | 25193.67
| OUTPUT 1.1.2. Restoration and co-management of natural banks | 1.1.2.1 Restoration of Peruvian scallops natural banks in the Huacho pilot area | 1253.57 |  |  |  | OUTPUT 1.1.2. Restoration and co-management of natural banks | 1.1.2.1. Restoration of Peruvian scallops natural banks in the Huacho pilot area | 75737.16 |  |  |  | OUTPUT 1.1.2. Restoration and co-management of natural banks | 1.1.2.1. Restoration of Peruvian scallops natural banks in the Huacho pilot area | 2750
| OUTPUT 1.2.1 Planning and development of sustainable aquaculture through smallscale concessions | 1.2.1.1. Farming of Peruvian scallops in Huacho and oysters in Mancora | 15619.6 |  |  |  |  | 1.1.2.2.Co-management of Peruvian scallops natural banks in the Huacho pilot area | 8572.02 |  |  |  |  | 1.1.2.2.Co-management of Peruvian scallops natural banks in the Huacho pilot area | 0
| OUTPUT 1.2.5. Production of bio-fertilizers from fishery and aquaculture residues | 1.2.5.1 Feasibility study of bioproducts | 2483.63 |  |  |  |  | 1.1.2.3. Fishery Ecological Risk Assessment, focusing on artisanal fisheries in Mancora and Huacho | 823.4 |  |  |  |  | 1.1.2.3. Fishery Ecological Risk Assessment, focusing on artisanal fisheries in Mancora and Huacho | 60530.97
| OUTPUT 2.1.1. Development of a climatic and an oceanographic surveillance system. | 2.1.1.1. Gliders acquisition | 32954.08 |  |  |  | OUTPUT 1.2.1. Planning and development of sustainable aquaculture through smallscale concessions | 1.2.1.1. Farming of Peruvian scallops in Huacho and oysters in Mancora | 2750 |  |  |  | OUTPUT 1.2.1. Planning and development of sustainable aquaculture through smallscale concessions | 1.2.1.1. Farming of Peruvian scallops in Huacho and oysters in Mancora | 0
| OUTPUT 2.1.2. Establishment of marine environment surveillance programs in pilot areas in coordination with local stakeholders | 2.1.2.1. Mancora pilot area monitoring (bentos research) | 752.3 |  |  |  |  | 1.2.1.2. Farming of oyster in Mancora | 5330.1 |  |  |  |  | 1.2.1.2. Farming of oyster in Mancora | 7163.49
|  | 2.1.2.2. Huacho pilot area monitoring (line-base study) | 19868.68 |  |  |  |  | 1.2.1.4.Aquaponic farming in the Huacho pilot area | 7537.96 |  |  |  |  | 1.2.1.4.Aquaponic farming in the Huacho pilot area | 2591.26
|  | 2.1.2.3. Mancora pilot area monitoring (line-base study) | 18170.85 |  |  |  | OUTPUT 1.2.2. Creation of ecotourism companies | 1.2.2.2.Formulation of the local tourism development plan for Mancora and Huacho | 4000 |  |  |  | OUTPUT 1.2.2. Creation of ecotourism companies | 1.2.2.2.Formulation of the local tourism development plan for Mancora and Huacho | 0
[7 empty] | OUTPUT 1.2.3. Improving marketing capacities for sustainable artisanal fisheries | 1.2.3.1. Capacity building in production fishery derivatives for direct human consumption | 17753.93 |  |  |  |  | 1.2.2.3. Implementation of a gastronomic circuit in Máncora and Huacho | 0
[8 empty] | 1.2.3.2 Mejorar gestión efectiva de las actividades implementadas por el proyecto | 1206.24 |  |  |  |  | 1.2.2.4. Development of artisan products with marine inputs | 0
[7 empty] | OUTPUT 1.2.5. Production of bio-fertilizers from fishery and aquaculture residues | 1.2.5.1. Estudio para la evaluación de los insumos para bioproductos | 21625.55 |  |  |  |  | 1.2.2.5. Experiential fishing development | 0
|  | 2.1.2.4. Mancora and Huacho pilot areas monitoring (equipment) | 0 |  |  |  |  | 1.2.5.2. Implementation of an artisanal pilot plant, inception of activities and quality assessment of the final products in the pilot areas | 1000 |  |  |  | OUTPUT 1.2.3. Improving marketing capacities for sustainable artisanal fisheries | 1.2.3.1. Capacity building in production fishery derivatives for direct human consumption | 44001.92
| OUTPUT 2.1.3. Development of a modeling and prediction system at local scales. | 2.1.3.1.Research visits and Climate Change Modeling | 3241.6 |  |  |  | OUTPUT 2.1.1. Development of a climatic and an oceanographic surveillance system. | 2.1.1.1. Gliders acquisition | 361163 |  |  |  |  | 1.2.3.2 Mejorar gestión efectiva de las actividades implementadas por el proyecto | 32921.34
| OUTPUT 3.1.1. Development and implementation of a Knowledge Management Strategy (KMS) | 3.1.1.1. Design and implementation of a knowledge management strategy and lessons learned | 307.07 |  |  |  |  | 2.1.1.2. Gliders training and deployment in the pilot areas | 0 |  |  |  | OUTPUT 1.2.5. Production of bio-fertilizers from fishery and aquaculture residues | 1.2.5.1. Estudio para la evaluación de los insumos para bioproductos | 0
| OUTPUT 3.2.1. Training and sensitizing of beneficiaries on key topics such as formalization, entrepreneurship, normative and fishing gear | 3.2.1.1. Training workshops for fishermen | 0 |  |  |  |  | 2.1.1.3. System and oceanographic data quality control implemented and automated according to IODE standards | 6984.62 |  |  |  |  | 1.2.5.2. Implementation of an artisanal pilot plant, inception of activities and quality assessment of the final products in the pilot areas | 0
| OUTPUT 3.2.2. Design and implementation of early warning systems through a participatory process at local and regional scales | 3.2.2.1. Design of Early Warning Systems for Mancora and Huacho | 0 |  |  |  | OUTPUT 2.1.2. Establishment of marine environment surveillance programs in pilot areas in coordination with local stakeholders | 2.1.2.1. Mancora pilot area monitoring (bentos research) | 0 |  |  |  | OUTPUT 2.1.1. Development of a climatic and an oceanographic surveillance system. | 2.1.1.1. Gliders acquisition | 683585
| OUTPUT 4.1.1. Support of the cross-sector working group for the promotion of common actions addressing coastal ecosystems’ resilience to climate change impacts. | 4.1.1.1.Intersectoral plan formulation | 0 |  |  |  |  | 2.1.2.2. Huacho pilot area monitoring (line-base study) | 8500 |  |  |  |  | 2.1.1.2. Gliders training and deployment in the pilot areas | 110132.52
| OUTPUT 4.1.2. Development of regulations and proposals for co-management in coastal marine areas | 4.1.2.1. Socioeconomic and legal analysis oriented to regulations and legal proposals on climate change adaptation | 0 |  |  |  |  | 2.1.2.3. Mancora pilot area monitoring (line-base study) | 12000 |  |  |  |  | 2.1.1.3. System and oceanographic data quality control implemented and automated according to IODE standards | 5061.86
| OUTPUT 4.1.3. Development of regulation to implement incentives for the participation of artisanal fishermen, adopting sustainable practices, in the National Direct Human Consumption Program. | 4.1.3.1.Formulation of a technical document to support the promotion of hydrobiological resources for direct human consumption. | 307.07 |  |  |  |  | 2.1.2.4. Mancora and Huacho pilot areas monitoring (equipment) | 123674.69 |  |  |  | OUTPUT 2.1.2. Establishment of marine environment surveillance programs in pilot areas in coordination with local stakeholders | 2.1.2.1. Mancora pilot area monitoring (bentos research) | 0
| Project Execution Cost (PEC) | Project Coordinator | 50960.72 |  |  |  |  | 2.1.2.5. Installation and recovery of sensors for monitoring pilot areas | 249.56 |  |  |  |  | 2.1.2.2. Huacho pilot area monitoring (line-base study) | 11000
|  | Local Coordinator | 14524.57 |  |  |  |  | 2.1.2.6. Design and initial experiences of participatory environmental monitoring in the pilot areas | 0 |  |  |  |  | 2.1.2.3. Mancora pilot area monitoring (line-base study) | 0
|  | Administrative assistant | 908.49 |  |  |  | OUTPUT 2.1.3. Development of a modeling and prediction system at local scales. | 2.1.3.1.Research visits and Climate Change Modeling | 21824.63 |  |  |  |  | 2.1.2.4. Mancora and Huacho pilot areas monitoring (equipment) | 0
|  | Procurement specialist | 8933.73 |  |  |  | OUTPUT 2.1.4. Capacity building in the monitoring and development of new science-based tools such as Ecological Risk Assessments (ERA) for climate change targeting IMARPE, decision makers and academia | 2.1.4.1. Research and training on new science-based tools such as Ecological Risk Assessment (ERA) for climate change | 25660 |  |  |  |  | 2.1.2.5. Installation and recovery of sensors for monitoring pilot areas | 0
|  | Design of the monitoring and evaluation system | 154.35 |  |  |  |  | 2.1.4.2. Vulnerability and ecological risk assessment (ERA) workshops associated with climate change in pilot areas | 4707.94 |  |  |  |  | 2.1.2.6. Design and initial experiences of participatory environmental monitoring in the pilot areas | 15950
|  | Inception workshop | 9298.68 |  |  |  |  | 2.1.4.3.Research in oceanographic modeling, vulnerability, ecological risk and, benthos | 17520 |  |  |  | OUTPUT 2.1.3. Development of a modeling and prediction system at local scales. | 2.1.3.1.Research visits and Climate Change Modeling | 109728.95
| TOTAL PROJECT COST (TPC) |  | 94958.45 |  |  |  | OUTPUT 3.1.1. Development and implementation of a Knowledge Management Strategy (KMS) | 3.1.1.1. Design and implementation of a knowledge management strategy and lessons learned | 10790.65 |  |  |  | OUTPUT 2.1.4. Capacity building in the monitoring and development of new science-based tools such as Ecological Risk Assessments (ERA) for climate change targeting IMARPE, decision makers and academia | 2.1.4.1. Research and training on new science-based tools such as Ecological Risk Assessment (ERA) for climate change | 54628.45
| PROJECT EXECUTION COST (PEC) |  | 84780.54 |  |  |  |  | 3.1.1.2. Formulation of a sectoral strategy proposal for fishing and aquaculture issues face to climate change aligned with the Nationally Determined Contributions (NDC) | 533.65 |  |  |  |  | 2.1.4.2. Vulnerability and ecological risk assessment (ERA) workshops associated with climate change in pilot areas | 0
| TOTAL (TPC + PEC) |  | 179738.99 |  |  |  | OUTPUT 3.2.1. Training and sensitizing of beneficiaries on key topics such as formalization, entrepreneurship, normative and fishing gear | 3.2.1.1. Training workshops for fishermen | 0 |  |  |  |  | 2.1.4.3.Research in oceanographic modeling, vulnerability, ecological risk and, benthos | 20460
[7 empty] | OUTPUT 3.2.2. Design and implementation of early warning systems through a participatory process at local and regional scales | 3.2.2.1. Design of Early Warning Systems for Mancora and Huacho | 0 |  |  |  | OUTPUT 3.1.1. Development and implementation of a Knowledge Management Strategy (KMS) | 3.1.1.1. Design and implementation of a knowledge management strategy and lessons learned | 10000
PLANNED EXPENDITURE SCHEDULE | [6 empty] | OUTPUT 4.1.1. Support of the cross-sector working group for the promotion of common actions addressing coastal ecosystems’ resilience to climate change impacts. | 4.1.1.1.Intersectoral plan formulation | 0 |  |  |  |  | 3.1.1.2. Formulation of a sectoral strategy proposal for fishing and aquaculture issues face to climate change aligned with the Nationally Determined Contributions (NDC) | 5105.4
[14 empty] | 3.1.1.3. Implementation and Monitoring of the EGC | 2980.34
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION |  | PROJECTED COST | Est. Completion Date |  |  |  | 4.1.1.2. Working Group conformed by PRODUCE and MINAM to develop marine spatial planning and Environmental Territorial Planning pilot, in Huacho | 0 |  |  |  | OUTPUT 3.2.1. Training and sensitizing of beneficiaries on key topics such as formalization, entrepreneurship, normative and fishing gear | 3.2.1.1. Training workshops for fishermen | 0
[7 empty] | OUTPUT 4.1.2. Development of regulations and proposals for co-management in coastal marine areas | 4.1.2.1. Socioeconomic and legal analysis oriented to regulations and legal proposals on climate change adaptation | 0 |  |  |  |  | 3.2.1.2. Training for institutions | 0
[7 empty] | OUTPUT 4.1.3. Development of regulation to implement incentives for the participation of artisanal fishermen, adopting sustainable practices, in the National Direct Human Consumption Program. | 4.1.3.1.Formulation of a technical document to support the promotion of hydrobiological resources for direct human consumption. | 0 |  |  |  |  | 3.2.1.3. Development of discussion spaces for the exchange of successful experiences | 0
[7 empty] | Project Execution Cost (PEC) | Project Coordinator | 55103.8 |  |  |  |  | 3.2.1.4. Workshop to identify the role of women in fishing and aquaculture activities and their adaptation to climate change | 0
| Project Output | Activity programmed in the Annual Operation Plan (AOP) 2019/2020 | [5 empty] | Local Coordinator | 23715.4 |  |  |  | OUTPUT 3.2.2. Design and implementation of early warning systems through a participatory process at local and regional scales | 3.2.2.1. Design of Early Warning Systems for Mancora and Huacho | 4500
[8 empty] | Administrative assistant | 13073.53 |  |  |  |  | 3.2.2.2. Equipment for the Design of the SAT for coastal marine areas through a participatory process in Máncora | 0
| OUTPUT 1.1.1. Adoption of sustainable fishing methods to tackle non-selective fishing gear based on EAF principles directed to target species vulnerable to climate change | 1.1.1.1. Implementation of a conversion pilot from fishing gillnets to pole and line and/or long-lines for tuna yellowfin in the Mancora pilot area | 78100 | December 2020 |  |  |  | Procurement specialist | 19089.15 |  |  |  | OUTPUT 4.1.1. Support of the cross-sector working group for the promotion of common actions addressing coastal ecosystems’ resilience to climate change impacts. | 4.1.1.1.Intersectoral plan formulation | 0
|  | 1.1.1.2. Following-up of anchovy fishing gears adoption in the Huacho pilot area | 98800 | January 2020 |  |  |  | Diseño del sistema de monitoreo y evaluación y elaboración de la línea base | 1069.35 |  |  |  |  | 4.1.1.2. Working Group conformed by PRODUCE and MINAM to develop marine spatial planning and Environmental Territorial Planning pilot, in Huacho | 0
|  | 1.1.1.3. Adoption of selective gillnets fishing gears to target coastal resources in the Huacho pilot area | 46000 | March 2020 |  |  |  | Monitoreo de salvaguardas sociales y ambientales | 7437.47 |  |  |  | OUTPUT 4.1.2. Development of regulations and proposals for co-management in coastal marine areas | 4.1.2.1. Socioeconomic and legal analysis oriented to regulations and legal proposals on climate change adaptation | 0
| OUTPUT 1.1.2. Restoration and co-management of natural banks | 1.1.2.1. Re-stock of Peruvian scallops natural banks in the Huacho pilot area | 88800 | May 2020 |  |  | TOTAL PROJECT COST (TPC) |  | 741351.11 |  |  |  | OUTPUT 4.1.3. Development of regulation to implement incentives for the participation of artisanal fishermen, adopting sustainable practices, in the National Direct Human Consumption Program. | 4.1.3.1.Formulation of a technical document to support the promotion of hydrobiological resources for direct human consumption. | 0
|  | 1.1.2.2.Co-management of Peruvian scallops natural banks in the Huacho pilot area | 62400 | May 2020 |  |  | PROJECT EXECUTION COST (PEC) |  | 119488.7 |  |  |  | Project Execution Cost (PEC) | 5.1.1.1. Project Coordinator | 47190.23
|  | 1.1.2.3. Fishery Ecological Risk Assessment, focusing on artisanal fisheries in Mancora and Huacho | 105780 | February 2020 |  |  | TOTAL (TPC + PEC) |  | 860839.81 |  |  |  |  | 5.1.1.2. Local Coordinator | 20118.15
| OUTPUT 1.2.1 Planning and development of sustainable aquaculture through smallscale concessions | 1.2.1.1. Farming of Peruvian scallops in Huacho | 130650 | May 2020 | [9 empty] | 5.1.1.3. Administrative assistant | 9745.74
|  | 1.2.1.2. Farming of oyster in Mancora | 81900 | May 2020 | PLANNED EXPENDITURE SCHEDULE | [8 empty] | 5.1.1.4. Procurement specialist | 17690.55
|  | 1.2.1.4.Aquaponic farming in the Huacho pilot area | 104600 | May 2020 | List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION |  | PROJECTED COST | Est. Completion Date |  |  |  | 5.1.2.3. Monitoring of social and environmental safeguards | 27288.72
| OUTPUT 1.2.2. Creation of ecotourism enterprises | 1.2.2.2.Formulation of the local tourism development plan for Mancora and Huacho | 30000 | October 2019 |  |  | Project Output | Activity programmed in the Annual Operation Plan (AOP) 2020 | [5 empty] | 5.1.2.4. Monitoring and evaluation | 3663.9
| OUTPUT 1.2.3 Improvement of market power capacities for sustainable artisanal fisheries | 1.2.3.1. Capacity building in production fishery derivatives for direct human consumption | 166900 | May 2020 |  |  | OUTPUT 1.1.1. Adoption of sustainable fishing methods to tackle non-selective fishing gear based on EAF principles directed to target species vulnerable to climate change | 1.1.1.1. Implementation of a conversion pilot from fishing gillnets to pole and line and/or long-lines for tuna yellowfin in the Mancora pilot area | 71627.98 | October 2020 |  |  | TOTAL PROJECT COST (TPC) |  | 1235750.7
| OUTPUT 1.2.5. Production of bio-fertilizers from fishery and aquaculture residues | 1.2.5.2. Implementation of an artisanal pilot plant, inception of activities and quality assessment of the final products in the pilot areas | 6000 | May 2020 |  |  |  | 1.1.1.2. Following-up of anchovy fishing gears adoption in the Huacho pilot area | 82800 | November 2020 |  |  | PROJECT EXECUTION COST (PEC) |  | 125697.29
| OUTPUT 2.1.1. Development of a climatic and an oceanographic surveillance system. | 2.1.1.1. Gliders acquisition | 960000 | December 2019 |  |  |  | 1.1.1.3. Adoption of selective gillnets fishing gears to target coastal resources in the Huacho pilot area | 73737 | December 2020 |  |  | TOTAL (TPC + PEC) |  | 1361447.99
|  | 2.1.1.2. Gliders training and deployment in the pilot areas | 140000 | April 2020 |  |  | OUTPUT 1.1.2. Restoration and co-management of natural banks | 1.1.2.1. Re-stock of Peruvian scallops natural banks in the Huacho pilot area | 62502 | December 2020
|  | 2.1.1.3. System and oceanographic data quality control implemented and automated according to IODE standards | 26000 | May 2020 |  |  |  | 1.1.2.2.Co-management of Peruvian scallops natural banks in the Huacho pilot area | 28757.02 | November 2020 | PLANNED EXPENDITURE SCHEDULE |  |  | POA 2021
| OUTPUT 2.1.2. Establishment of marine environment surveillance programs in pilot areas in coordination with local stakeholders | 2.1.2.2.Base-line in the Huacho pilot area | 5000 | May 2020 |  |  |  | 1.1.2.3. Fishery Ecological Risk Assessment, focusing on artisanal fisheries in Mancora and Huacho | 63716 | July 2020 | List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION |  | PROJECTED COST | Est. Completion Date
|  | 2.1.2.5. Installation and recovery of sensors for monitoring pilot areas | 36000 | May 2020 |  |  | OUTPUT 1.2.1 Planning and development of sustainable aquaculture through smallscale concessions | 1.2.1.1. Farming of Peruvian scallops in Huacho | 21185 | May 2020 |  |  | Project Output | Activity programmed in the Annual Operation Plan (AOP) 2021
|  | 2.1.2.6. Design and initial experiences of participatory environmental monitoring in the pilot areas | 42600 | May 2020 |  |  |  | 1.2.1.2. Farming of oyster in Mancora | 135961.02 | December 2020 |  |  | OUTPUT 1.1.1. Adoption of sustainable fishing methods to tackle non-selective fishing gear based on EAF principles directed to target species vulnerable to climate change | 1.1.1.1. Implementation of a conversion pilot from fishing gillnets to pole and line and/or long-lines for tuna yellowfin in the Mancora pilot area | 57950 | December 2021
| OUTPUT 2.1.3. Development of a modeling and prediction system at local scales. | 2.1.3.1. Research visits and climate change modeling | 135650 | May 2020 |  |  |  | 1.2.1.4.Aquaponic farming in the Huacho pilot area | 90427 | December 2020 |  |  |  | 1.1.1.2. Following-up of anchovy fishing gears adoption in the Huacho pilot area | 84672 | December 2021
| OUTPUT 2.1.4. Building capacity on monitoring and development of new science based tools such as Ecological Risk Assessments (ERA) for climate change directed to IMARPE, decision makers and academia. | 2.1.4.1. Research and training on new science-based tools such as Ecological Risk Assessment (ERA) for climate change | 80000 | January 2020 |  |  | OUTPUT 1.2.2. Creation of ecotourism enterprises | 1.2.2.2.Formulation of the local tourism development plan for Mancora and Huacho | 18000 | July 2020 |  |  |  | 1.1.1.3. Adoption of selective gillnets fishing gears to target coastal resources in the Huacho pilot area | 77910 | December 2021
|  | 2.1.4.2. Vulnerability and ecological risk assessment (ERA) workshops associated with climate change in pilot areas | 9530 | May 2020 |  |  |  | 1.2.2.3. Implementación de circuito gastronómico en Máncora y Huacho | 26000 | November 2020 |  |  | OUTPUT 1.1.2. Restoration and co-management of natural banks | 1.1.2.1. Re-stock of Peruvian scallops natural banks in the Huacho pilot area | 100500 | November 2021
|  | 2.1.4.3.Research in oceanographic modeling, vulnerability, ecological risk and, benthos | 38400 | May 2020 |  |  |  | 1.2.2.4. Desarrollo de productos artesanales con insumos marinos | 74128.5 | November 2020 |  |  |  | 1.1.2.2.Co-management of Peruvian scallops natural banks in the Huacho pilot area | 23400.16 | July 2021
| OUTPUT 3.1.1. Development and implementation of a Knowledge Management Strategy (KMS) | 3.1.1.1. Design and implementation of a knowledge management strategy and lessons learned | 17600 | October 2019 |  |  |  | 1.2.2.5. Desarrollo de pesca vivencial | 93143 | October 2020 |  |  |  | 1.1.2.3. Fishery Ecological Risk Assessment, focusing on artisanal fisheries in Mancora and Huacho | 23469 | April 2021
|  | 3.1.1.2. Formulation of a sectoral strategy proposal for fishing and aquaculture issues face to climate change aligned with the Nationally Determined Contributions (NDC) | 26500 | May 2020 |  |  | OUTPUT 1.2.3 Improvement of market power capacities for sustainable artisanal fisheries | 1.2.3.1. Capacity building in production fishery derivatives for direct human consumption | 101472 | October 2020 |  |  | OUTPUT 1.2.1 Planning and development of sustainable aquaculture through smallscale concessions | 1.2.1.1. Farming of Peruvian scallops in Huacho and oysters in Mancora | 0
| OUTPUT 3.2.2. Design and implementation of early warning systems through a participatory process at local and regional scales | 3.2.2.1. Design of Early Warning Systems for Mancora and Huacho | 32400 | May 2020 |  |  |  | 1.2.3.2 Mejorar gestión efectiva de las actividades implementadas por el proyecto | 44032 | December 2020 |  |  |  | 1.2.1.2. Farming of oyster in Mancora | 171647.77 | August 2021
| OUTPUT 4.1.1. Support of the cross-sector working group for the promotion of common actions addressing coastal ecosystems’ resilience to climate change impacts. | 4.1.1.1.Intersectoral plan formulation | 26250 | May 2020 |  |  | OUTPUT 1.2.4 Inicio de procesos de certificación para pesquerías | 1.2.4.1. Implementación de un sistema de trazabilidad para pescadores artesanales de las áreas piloto de proyecto | 11887 | September 2020 |  |  |  | 1.2.1.4.Aquaponic farming in the Huacho pilot area | 71560 | December 2021
|  | 4.1.1.2. Working Group conformed by PRODUCE and MINAM to develop marine spatial planning and Environmental Territorial Planning pilot, in Huacho | 5000 | May 2020 |  |  | OUTPUT 1.2.5. Production of bio-fertilizers from fishery and aquaculture residues | 1.2.5.1. Estudio para la evaluación de los insumos para bioproductos | 5965 | January 2020 |  |  | OUTPUT 1.2.2. Creation of ecotourism enterprises | 1.2.2.2.Formulation of the local tourism development plan for Mancora and Huacho | 98956 | December 2021
| OUTPUT 4.1.3. Development of regulation to implement incentives for the participation of artisanal fishermen, adopting sustainable practices, in the National Direct Human Consumption Program. | Tarea 4.1.3.1. Formulation of a guide to carry out an assessment on the adoption of sustainable practices related to artisanal fishery products for Direct Human Consumption. | 35200 | May 2020 |  |  |  | 1.2.5.2. Implementation of an artisanal pilot plant, inception of activities and quality assessment of the final products in the pilot areas | 135227 | October 2020 |  |  |  | 1.2.2.3. Implementación de circuito gastronómico en Máncora y Huacho | 100957 | March 2021
| Project Execution Cost (PEC) | Project Coordinator | 57131.74 | May 2020 |  |  | OUTPUT 2.1.1. Development of a climatic and an oceanographic surveillance system. | 2.1.1.1. Gliders acquisition | 951093 | March 2020 |  |  |  | 1.2.2.4. Desarrollo de productos artesanales con insumos marinos | 0
|  | Local Coordinator | 24310.56 | May 2020 |  |  |  | 2.1.1.2. Gliders training and deployment in the pilot areas | 115500 | February 2020 |  |  |  | 1.2.2.5. Desarrollo de pesca vivencial | 0
|  | Administrative assistant | 16354.66 | May 2020 |  |  |  | 2.1.1.3. System and oceanographic data quality control implemented and automated according to IODE standards | 5919.72 | June 2020 |  |  | OUTPUT 1.2.3 Improvement of market power capacities for sustainable artisanal fisheries | 1.2.3.1. Capacity building in production fishery derivatives for direct human consumption | 193240 | August 2021
|  | Procurement specialist | 16811.18 | May 2020 |  |  | OUTPUT 2.1.2. Establishment of marine environment surveillance programs in pilot areas in coordination with local stakeholders | 2.1.2.2.Base-line in the Huacho pilot area | 11000 | May 2020 |  |  |  | 1.2.3.2 Mejorar gestión efectiva de las actividades implementadas por el proyecto | 59002.86 | December 2021
|  | Safeguards and gender monitoring | 32499 | May 2020 |  |  |  | 2.1.2.3. Linea base en la zona de Mancora | 3500 | January 2020 |  |  | OUTPUT 1.2.4 Inicio de procesos de certificación para pesquerías | 1.2.4.1. Implementación de un sistema de trazabilidad para pescadores artesanales de las áreas piloto de proyecto | 0
| TOTAL PROJECT COST (TPC) |  | 2616060 |  |  |  |  | 2.1.2.4. Monitoreo de la zona de Huacho y Mancora | 64960 | February 2020 |  |  | OUTPUT 1.2.5. Production of bio-fertilizers from fishery and aquaculture residues | 1.2.5.1. Estudio para la evaluación de los insumos para bioproductos | 0
| PROJECT EXECUTION COST (PEC) |  | 147107.14 |  |  |  |  | 2.1.2.5. Installation and recovery of sensors for monitoring pilot areas | 39000 | July 2020 |  |  |  | 1.2.5.2. Implementation of an artisanal pilot plant, inception of activities and quality assessment of the final products in the pilot areas | 158305 | December 2021
| TOTAL (TPC+PEC) |  | 2763167.14 |  |  |  |  | 2.1.2.6. Design and initial experiences of participatory environmental monitoring in the pilot areas | 25250 | September 2020 |  |  | OUTPUT 2.1.1. Development of a climatic and an oceanographic surveillance system. | 2.1.1.1. Gliders acquisition | 23750 | June 2021
[7 empty] | OUTPUT 2.1.3. Development of a modeling and prediction system at local scales. | 2.1.3.1. Research visits and climate change modeling | 119323.98 | November 2020 |  |  |  | 2.1.1.2. Gliders training and deployment in the pilot areas | 18556 | December 2021
[7 empty] | OUTPUT 2.1.4. Building capacity on monitoring and development of new science based tools such as Ecological Risk Assessments (ERA) for climate change directed to IMARPE, decision makers and academia. | 2.1.4.1. Research and training on new science-based tools such as Ecological Risk Assessment (ERA) for climate change | 117435.78 | August 2020 |  |  |  | 2.1.1.3. System and oceanographic data quality control implemented and automated according to IODE standards | 15400 | February 2021
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) | The project doesn't have co-financing | [6 empty] | 2.1.4.2. Vulnerability and ecological risk assessment (ERA) workshops associated with climate change in pilot areas | 0 |  |  |  | OUTPUT 2.1.2. Establishment of marine environment surveillance programs in pilot areas in coordination with local stakeholders | 2.1.2.2.Base-line in the Huacho pilot area | 0
How much of the total co-financing as committed in the Project Document has actually been realized? | [7 empty] | 2.1.4.3.Research in oceanographic modeling, vulnerability, ecological risk and, benthos | 29414 | October 2020 |  |  |  | 2.1.2.3. Linea base en la zona de Mancora | 0
[7 empty] | OUTPUT 3.1.1. Development and implementation of a Knowledge Management Strategy (KMS) | 3.1.1.1. Design and implementation of a knowledge management strategy and lessons learned | 33487 | November 2020 |  |  |  | 2.1.2.4. Monitoreo de la zona de Huacho y Mancora | 0
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | [7 empty] | 3.1.1.2. Formulation of a sectoral strategy proposal for fishing and aquaculture issues face to climate change aligned with the Nationally Determined Contributions (NDC) | 19750 | December 2020 |  |  |  | 2.1.2.5. Installation and recovery of sensors for monitoring pilot areas | 40000 | February 2021
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | [7 empty] | 3.1.1.3. Implementación y Seguimiento de la EGC | 33500 | December 2020 |  |  |  | 2.1.2.6. Design and initial experiences of participatory environmental monitoring in the pilot areas | 86500 | August 2021
[8 empty] | 3.1.1.4. Implementación y seguimiento de la Estrategia Sectorial en áreas piloto | 2000 | January 2020 |  |  | OUTPUT 2.1.3. Development of a modeling and prediction system at local scales. | 2.1.3.1. Research visits and climate change modeling | 67226.66 | December 2021
[8 empty] | 3.1.1.5. Desarrollo de medios de difusión / comunicación | 9500 | May 2020 |  |  | OUTPUT 2.1.4. Building capacity on monitoring and development of new science based tools such as Ecological Risk Assessments (ERA) for climate change directed to IMARPE, decision makers and academia. | 2.1.4.1. Research and training on new science-based tools such as Ecological Risk Assessment (ERA) for climate change | 17500 | February 2021
[7 empty] | OUTPUT 3.2.1. Training and sensitizing of beneficiaries on key topics such as formalization, entrepreneurship, normative and fishing gear | 3.2.1.1. Capacitación a pescadores artesanales | 6000 | June 2020 |  |  |  | 2.1.4.2. Vulnerability and ecological risk assessment (ERA) workshops associated with climate change in pilot areas | 0
[8 empty] | 3.2.1.2. Capacitación a instituciones | 27000 | December 2020 |  |  |  | 2.1.4.3.Research in oceanographic modeling, vulnerability, ecological risk and, benthos | 33000 | August 2021
[8 empty] | 3.2.1.3. Desarrollo de los espacios de debate para el intercambio de experiencias existosas | 3295 | November 2020 |  |  | OUTPUT 3.1.1. Development and implementation of a Knowledge Management Strategy (KMS) | 3.1.1.1. Design and implementation of a knowledge management strategy and lessons learned | 0
[8 empty] | 3.2.1.4. Taller para identificar el rol de la mujer en las actividades pesqueras acuícolas | 2000 | May 2020 |  |  |  | 3.1.1.2. Formulation of a sectoral strategy proposal for fishing and aquaculture issues face to climate change aligned with the Nationally Determined Contributions (NDC) | 19750 | June 2021
[7 empty] | OUTPUT 3.2.2. Design and implementation of early warning systems through a participatory process at local and regional scales | 3.2.2.1. Design of Early Warning Systems for Mancora and Huacho | 38500 | November 2020 |  |  |  | 3.1.1.3. Implementación y Seguimiento de la EGC | 84300 | December 2021
[7 empty] | OUTPUT 4.1.1. Support of the cross-sector working group for the promotion of common actions addressing coastal ecosystems’ resilience to climate change impacts. | 4.1.1.1.Intersectoral plan formulation | 16650 | May 2020 |  |  |  | 3.1.1.4. Implementación y seguimiento de la Estrategia Sectorial en áreas piloto | 0
[8 empty] | 4.1.1.2. Working Group conformed by PRODUCE and MINAM to develop marine spatial planning and Environmental Territorial Planning pilot, in Huacho | 0 |  |  |  |  | 3.1.1.5. Desarrollo de medios de difusión / comunicación | 0
[7 empty] | OUTPUT 4.1.3. Development of regulation to implement incentives for the participation of artisanal fishermen, adopting sustainable practices, in the National Direct Human Consumption Program. | Tarea 4.1.3.1. Formulation of a guide to carry out an assessment on the adoption of sustainable practices related to artisanal fishery products for Direct Human Consumption. | 40845 | June 2020 |  |  | OUTPUT 3.2.1. Training and sensitizing of beneficiaries on key topics such as formalization, entrepreneurship, normative and fishing gear | 3.2.1.1. Capacitación a pescadores artesanales | 0
[7 empty] | Project Execution Cost (PEC) | Project Coordinator | 57131.74 |  |  |  |  | 3.2.1.2. Capacitación a instituciones | 33500 | December 2021
[5 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  | Local Coordinator | 24310.56 |  |  |  |  | 3.2.1.3. Desarrollo de los espacios de debate para el intercambio de experiencias existosas | 15000 | September 2021
[8 empty] | Administrative assistant | 16354.66 |  |  |  |  | 3.2.1.4. Taller para identificar el rol de la mujer en las actividades pesqueras acuícolas | 0
[8 empty] | Procurement specialist | 16811.18 |  |  |  | OUTPUT 3.2.2. Design and implementation of early warning systems through a participatory process at local and regional scales | 3.2.2.1. Design of Early Warning Systems for Mancora and Huacho | 30000 | May 2021
[8 empty] | Safeguards and gender monitoring | 43789 |  |  |  |  | 3.2.2.2 | 12000 | December 2021
[7 empty] | TOTAL PROJECT COST (TPC) |  | 2855491 |  |  |  | OUTPUT 4.1.1. Support of the cross-sector working group for the promotion of common actions addressing coastal ecosystems’ resilience to climate change impacts. | 4.1.1.1.Intersectoral plan formulation | 34000 | July 2021
[7 empty] | PROJECT EXECUTION COST (PEC) |  | 158397.14 |  |  |  |  | 4.1.1.2. Working Group conformed by PRODUCE and MINAM to develop marine spatial planning and Environmental Territorial Planning pilot, in Huacho | 0
[7 empty] | TOTAL (TPC+PEC) |  | 3013888.14 |  |  |  | OUTPUT 4.1.2. Development of regulations and proposals for co-management in coastal marine areas | 4.1.2.1. Preparation of a normative proposal aimed at incorporating the concepts of co-management in the management of the artisanal fishery | 74000 | December 2021
[13 empty] | OUTPUT 4.1.3. Development of regulation to implement incentives for the participation of artisanal fishermen, adopting sustainable practices, in the National Direct Human Consumption Program. | 4.1.3.1. Formulation of a guide to carry out an assessment on the adoption of sustainable practices related to artisanal fishery products for Direct Human Consumption. | 49600 | December 2021
[13 empty] | Project Execution Cost (PEC) | Project Coordinator | 57131.74 | December 2021
[5 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  | The project doesn't have co-financing |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  | Local Coordinator | 24310.56 | December 2021
[14 empty] | Administrative assistant | 16354.66 | December 2021
[5 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | [8 empty] | Procurement specialist | 16811.18 | December 2021
[5 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | [8 empty] | Safeguards and gender monitoring | 47411.5136 | July 2021
[6 empty] | NOTE | In December 2019, the Annual Operating Budget 2020 was approved (January - December). | [5 empty] | TOTAL PROJECT COST (TPC) |  | 1875652.45
[13 empty] | PROJECT EXECUTION COST (PEC) |  | 162019.6536
[13 empty] | TOTAL (TPC+PEC) |  | 2037672.1036
[11 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  | The project doesn't have co-financing
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
[12 empty] | NOTE | In December 2020, the Annual Operating Budget 2021 was approved (January - December).
[8 empty] | January 2020 | January
[8 empty] | February 2020 | February | 2020
[8 empty] | March 2020 | March | 2020
[8 empty] | April 2020 | April | 2020
[8 empty] | May 2020 | May | 2020
[8 empty] | June 2020 | June | 2020
[8 empty] | July 2020 | July | 2020
[8 empty] | August 2020 | August | 2020
[8 empty] | September 2020 | September | 2020
[8 empty] | October 2020 | October | 2020 |  |  |  | January 2021 | January
[8 empty] | November 2020 | November | 2020 |  |  |  | February 2021 | February | 2021
[8 empty] | December 2020 | December | 2020 |  |  |  | March 2021 | March | 2021
[10 empty] | 2020 |  |  |  | April 2021 | April | 2021
[14 empty] | May 2021 | May | 2021
[14 empty] | June 2021 | June | 2021
[14 empty] | July 2021 | July | 2021
[14 empty] | August 2021 | August | 2021
[14 empty] | September 2021 | September | 2021
[14 empty] | October 2021 | October | 2021
[14 empty] | November 2021 | November | 2021
[14 empty] | December 2021 | December | 2021
2021

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Regulatory
Climate change adaptation has not been incorporated in the policies, strategies, and plans of the Ministry of Production (PRODUCE) nor local governments. | PRODUCE through its General Directorate of Environmental Fisheries and Aquaculture Affairs (DGAAMPA) is establishing measures to implement the sectoral NDCs identified and approved to date. | The proposal for a Sectoral Strategy on Fisheries and Aquaculture to deal with Climate Change has been formulated, aligning the implementation of the NDC, which was carried out with different agents involved from the pilot areas (district and provincial municipalities) and state institutions (IMARPE , PRODUCE)
Insufficient regulation proposing environmental friendly fishing practices and the sustainable use of ecosystems. | There is fishing regulation with recommendations and measures related to the use of friendly fishing gear and sustainable use of resources. However, it is not explicitly regulated and its monitoring is still limited. Therefore, the risk remains. | So far, 3 conservation agreements have been signed, between the Huacho fishermen's associations and SERNANP, for the sustainable use of the marine resources in the Don Martin Island. The signing of the conservation agreement with the Los Órganos OSPA is also ongoing, which contemplates the efficient use of resources and environmental monitoring of the area.
Weak enforcement and lack of compliance with regulation; various gray areas in the interaction between artisanal and industrial fishing. | Considering that the factors determining this risk are of a legal, social, economic and cultural nature, there is still no evidence of articulation of efforts in an integral manner, therefore the risk remains. | The study of ecological risk to the fisheries has been completed, which will provide a scientific basis for the formulation of legal regulatory norms on artisanal fishing. The Governance Improvement Consultancy is in the procurement phase, This service will support the arrangements to guarantee the sustainability of the other activities that previously started, which have already developed the stages of diagnosis and identification of beneficiaries. Based on this, the Governance consultancy will optimize the intervention with the beneficiaries and improve coordination with local actors, beneficiaries and entities of the fishing sector.
Financial
There may be insufficient financial resources for the sustainability of the project activities once the grant financing the project is spent. | Considering that the activities related to the adaptation measures planned under component 1, have not yet begun, this risk remains. | Until the reporting date, there is a project document to be submitted to the PNIPA fund related to sustainable fishing gear (carried out within the framework of the consultancy of identification of competitive funds); Likewise, it will begin in the formulation of four project proposals for aquaculture activities, in order to give sustainability to the project activities, which have been identified with project beneficiaries and stakeholders, based on complementary needs to the project activities. Likewise, coordination has been carried out with projects from other cooperating sources (EBAMAR project, PAN III Project) that also have work areas that converge with those of the project, in order to give continuity to various activities such as sustainable tourism, participatory monitoring, among other.
Political
Artisanal fishing has not been included into national development policies; the focus of the sector has been directed to industrial fishing and exports | In 2018, PRODUCE promulgated the Legislative Decree No. 1392, which establishes the formalization system of the artisanal fishing activity (SIFORPA). It has also initiated the formulation of a national training program for artisanal fishermen. | The work to formalize the OSPAS continued, there are 80 formalized fishermen with a fishing sailor's license or card ("Carné de marinero de pesca") in the two pilot areas so far, as well as 8 OSPAS with renewal of the updated board and registration with SUNARP. These have been important steps for the fishermen, because thanks to the obtaining of these cards, they comply with the formalization requirements and have been able to obtain benefits from the state in the context of COVID 19 (like FONDEPES loans).
Operational
Few or lack of coordination instances for the key stakeholders involved does not ensure the adequate prioritization of project activities. | The regulations are still insufficient, however, the project will contribute with interventions that allow improving the participation of users in decision making. | So far, spaces for dialogue have been coordinated between OSPAS and local and regional governments, as public and private entities. This will be reinforced with the implementation of the governance component, the primary function of which is to facilitate and promote these spaces for dialogue.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The COVID 19 pandemic and its impacts on coastal communities in the pilot areas of the project represent a risk for the fulfillment of project activities and objectives. | Although the quarantine has ended and economic activities, especially artisanal fishing, are gradually reactivating, the impacts on the economic health and income of the direct beneficiaries of the project are significant and it is expected that they will continue for a longer time. | In this context, the reprogramming of the AOP 2021 has been chosen in order to realize a reduction of the planned ammounts for travel and workshops. In addition,the following is proposed: 1.- Accelerate all activities that were paralyzed or delayed as a result of the pandemic. 2.- Accelerate the calls and contracts of the thematic packages in a way that allows improving the technical execution of the project. 3.- Develop the activities within the norms for pandemic control at the national level, following established protocols and the use of adequate equipment by both project staff and beneficiaries. 4.- Evaluate the possibility of a temporary extension for the implementation of project activities. Support in productive fishing activities such as the direct commercialization of the fish in "A comer pescado" fairs in the pilot area of Huacho and Máncora, as well as support in the search for new forms of commercialization online, for groups of artisan women. Some project activities has been implemented through online workshops, which has helped to reduce the risk of contagion of the COVID19 disease, as well as support the technological inclusion of the fishing communities. Ecomonic recovery is also being supported through project activities such as the activation of responsible tourism and the production of biofertilizers.
To implement some of the activities of component 1, it is necessary to previously obtain permits or authorizations from the competent sectors. This is the case of the activities related to the adoption of sustainable fishing gear and the promotion of sustainable aquaculture. The terms in which these authorizations would obtain could mean a delay in the start-up of these activities, as well as in the development of other activities that depend on these, such as the one related to commercialization (output 1.2.3). | although the quarantine has ended and economic activities, especially artisanal fishing, are gradually reactivating, the impacts on the economic health and income of the direct beneficiaries of the project are significant and it is expected that they will Currently the activity of production of oysters will need permits, and Los Organos´s association have a partial authorization for the use of the acuatic area. We are supporting the association to finish the formalization for the use of the area. | They are being supported in the individual training of fishermen, as well as the renewal of boards of directors, to be able to require permits for aquaculture concessions. They are being supported in the constitution of MYPES so that they can establish more beneficial marketing agreements. This process is being developed as part of the aquaponics and biofertilizer activities. The formalization of the OSPAS, (80 fishermen formalized with a fishing sailor's license in the two pilot zones, as well as 8 OSPAS with renewal of the updated board and obtaining registration with SUNARP) represent important steps for fishermen because thanks to the obtaining of these cards, they meet the formalization requirements and have been able to obtain state benefits in the COVID 19 context. In the consulting of Ostra´s production, we will support to Organos´s Association with board of directors update and change of productive activity to Aquaculture, and finally to present the necessary documentation to complete the process of obtaining an aquatic concession (form, environmental impact statement, DICAPI authorization, etc.).
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The inclusion of online training sessions has managed to include the communities in the project activities avoiding contagion, as well as the support for the reactivation of tourism in the Mancora area and the "A comer pescado" fairs, which support that these communities can recover economically from the impact caused by the pandemic.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity |  |  | Resistance of beneficiaries due to saturation of activities | M.E.1. Technical assistance for the organizational reorganization of the OSPAs and other forms of associativity of the beneficiaries | Number of OSPAs and other forms of association of fishermen, aquaculture producers, commercial handlers, artisans, tour operators, among other beneficiaries (both men and women), who have current registration in the Public registers as a legal entity. Number of OSPAs and other forms of associativity of fishermen, aquaculturists, commercial handlers, artisans, tour operators, among other beneficiaries, who have current registration in the entity that regulates their activity. (dissagregated by men and women) | 0 | A total of 9 associations in the pilot areas of Huacho and Máncora have their board of directors registered and updated in Public Records There are a total of 7 OSPAS with associates with a fisherman's license, MAN card and a fisherman's certificate. | It was not possible to comply with the formalization of all the OSPAS with which it works. | Sustainability agreements are made with other entities to continue the formalization process.
Resistance of beneficiaries due to complexity of the requirement in the development of activities, especially compliance with formal requirements for signing agreements
Resistance of beneficiaries due to concentration of beneficiaries, especially when a single group concentrates and encompasses several activities
Resistance of beneficiaries due to discredit in the social and political environment
|  |  | Resistance of beneficiaries due to patriarchal cultural patterns and social context | M.E.5. Prevention of child labor and gender violence through joint actions with DEMUNA, CEM and other similar programs. | Risk level of the event that generates the conditions for child labor or gender violence within the framework of the project Number of preventive actions carried out in conjunction with DEMUNA, CEM and other similar programs Number of cases of child labor due to project intervention with social assistance and made available to DEMUNA Number of cases of gender violence due to project intervention with social and legal assistance, and made available to the CEM | 0 | No events were registered regarding this topic | It is not possible to give professional to the cases presented | Request support from the relevant entities to deal with these cases
|  |  | Conflicts of interest due to increased competencies of beneficiaries, when intervening in other productive activities outside the regular (fishing), causing conflicts with other productive groups. | M.E.3. Support for the commercialization of marine products from the new responsible fishing practices | Number of commercial agreements managed in collaboration with OSPA and other forms of fishermen associations, aquaculture producers, commercial handlers, artisans, tour operators, among other beneficiaries (dissagregated by men and women) Number of trade agreements managed in collaboration with civil society organizations Level of compliance with the commitments of the trade agreements | 0 | There is a commercial agreement for the sale of fish in the pilot zone of Mancora, with the women traders of Caleta del Ñuro at the "A comer pescado" fairs None 1/1
|  |  | Conflict of interest due to pre-existing, latent or crisis tensions, related to previous conflicts due to agreements not fulfilled by other institutions in the intervention zones. | M.E.4.Preparation and signing of an institutional agreement with defined and articulated responsibilities for the social and economic sustainability of artisanal tuna fishing and other related initiatives | Number of institutional agreements signed that have defined and articulated responsibilities for the social and economic sustainability of artisanal tuna fishing and other related initiatives Number of socialization workshops with fishermen, aquaculture producers, merchant handlers, artisans, tour operators, among other beneficiaries (both men and women) and key actors about the institutional agreements signed that have defined and articulated responsibilities for the social and economic sustainability of artisanal tuna fishing and other related initiatives. | 0 | It has 3 conservation agreements signed between Ospas of Huacho and SERNANP There is also, in the signing process, 1 conservation agreement in the pilot zone of Mancora, between the OSPA of Cabo Blanco and the municipality of El Alto. In process, also the signing of a cooperation agreement between AMARTEMM and the municipality of Vegueta 1 meeting was held for each agreement promoted | At the time of execution of project, it is not possible to sign or establish the agreements. | Establish working committees at the end of the project to finalize these agreements.
Conflict of interest due to differences between user and administrators
Conflict of interest due to overlapping of responsibilities
|  |  | Conflict of interest due to exclusion of areas / resources | M.E.6. Compensation to artisanal fishermen directly affected by a possible restriction. | Risk level of the event that generates the conditions for the eventual restriction of access to areas / resources Level of access to the development of income-generating initiatives, such as the production of biofertilizers, ecotourism, etc. promoted by the project, by fishermen, aquaculture producers, commercial handlers, artisans, tour operators (men and women), among others registered by direct impact with eventual restriction of access to areas /resources. | 0 | No events were registered regarding this topic 3/4 , It is working with all active Ospas of the two pilot areas in all productive activities implemented in the project | New conflicts are generated for access to resources related to the project activity. | Work with zone management committees to adequately deal with these conflicts and empower them to mediate conflicts.
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights |  |  | Children and teenagers in non-training work activities for new ventures | M.E.5. Prevention of child labor and gender violence through joint actions with DEMUNA, CEM and other similar programs. | Risk level of the event that generates the conditions for child labor or gender violence within the framework of the project Number of preventive actions carried out in conjunction with DEMUNA, CEM and other similar programs Number of cases of child labor due to project intervention with social assistance and made available to DEMUNA Number of cases of gender violence due to project intervention with social and legal assistance, and made available to the CEM | 0 | No events were registered regarding this topic | It is not possible to give professional to the cases presented | Request support from the relevant entities to deal with these cases
7 – Indigenous peoples
8 – Involuntary resettlement |  |  | Reduction of income from new fishing techniques and new productive ventures | M.E.2. Financing the cost of the pilot's sustainable fishing gear | Number of artisanal fishermen (shipowners) with sustainable fishing gear financed and installed Number of artisanal vessels with sustainable fishing gear in use | a) To be determined b) 0 | 127 fishermen in the process of installing sustainable fishing gear 30 vessels identified and in the process of installing sustainable fishing gear | Misuse of fishing gear by fishermen. | Supervision by IMARPE for proper use of fishing gear after project completion.
|  |  | Cross-cutting mitigation measures | M.T.1.Construction of the Local Work Plan (LWP) in each pilot site with the beneficiaries and key stakeholders of the project | Number of participants in the LWP development and monitoring workshops Level of representation of fishermen, aquaculture producers, merchant handlers, artisans, tour operators, among other beneficiaries (women and men) and key project stakeholders who participate in the LWP development and monitoring workshops Number of replicas of the LWP elaboration and monitoring workshops in the communities and together with fishermen, aquaculture producers, commercial handlers, artisans, tour operators (considering women and men), among other beneficiaries and key actors who participated in the elaboration | 0 | The LWP formulation process has not started yet
|  |  |  | M.T.2. Effective coordination of each project activity with the beneficiaries and key actors | Level of compliance with the commitments made in the coordination meetings of the project activities included in the LWP Number of complaints about lack of knowledge of the progress of the project activities included in the LWP | 0 | The LWP formulation process has not started yet | Compliance level is low at the end of the project. | Manage agreements with other projects or NGOs to comply with them.
|  |  |  | M.T.3. Involvement in spaces for dialogue and confidence building of the beneficiaries and key actors of the project | Frequency of meetings of the spaces for dialogue and trust building Level of convening power of dialogue spaces and trust building Level of involvement of fishermen, aquaculture producers, commercial handlers, artisans, tour operators, among other beneficiaries (men and women) and key project actors who participate in the dialogue and trust-building spaces | 0 | At least 1 meeting a week in each pilot zone, to coordinate activities. 3/4 ,3/4, participants actively collaborate in meetings, workshops, as well as they include us in their governance spaces
|  |  |  | M.T.4. Targeting of beneficiaries in each pilot site | Number of fishermen, aquaculture producers, commercial handlers, artisans, tour operators, among others, who are beneficiaries of the project in each pilot site |  | There are 128 beneficiaries in Mancora There are 288 beneficiaries in Huacho
|  |  |  | M.T.5. Capacity building of the beneficiaries for the adoption of new responsible fishing practices, new undertakings of complementary activities and mechanisms for the conservation of species | Degree of knowledge of fishermen, aquaculturists, commercial handlers, artisans, tour operators, among other beneficiaries, about the traditional and complementary productive activities that are improved and developed with the project Level of formalization (individual) of fishermen, aquaculture producers, commercial handlers, artisans, tour operators, among other beneficiaries of traditional and complementary productive activities that are improved and developed with the project | 0 | 3/4, Most of the beneficiaries we work with know about the adaptation measures that have been implemented. There are more than 80 fishermen with a fishing sailor's license
|  |  |  | M.T.6. Implementation of communication strategy / plan at the three levels of intervention, with emphasis on the pilot sites | Level of involvement of fishermen, aquaculture producres, commercial handlers, artisans, tour operators, among other beneficiaries and key project actors in communication activities Number of environmental education and communication campaigns and resources on the key issues of the project | 0 | 1/2 , the implementation of communication activities is in process Workshops regarding these issues have not been implemented yet, but they are in the process of implementing participatory monitoring.
9 – Protection of natural habitats |  |  | R5. Decline in the population of some species | (M.10.) Develop research aimed at generating information on the real impact of aquaculture on benthic species and implement the derived recommendations. | Number of investigations carried out. | 0 | There is 1 postgraduate thesis on climate vulnerability assessment (EVC) of the impacts of climate change on key species of the Peruvian tropical ecosystem. There is also 1 investigation on ecological risk to fisheries
|  |  |  | (M.11.) Develop capacities of local actors on techniques and methodologies for monitoring species. | Number of local actors trained. Percentage (%) increase in the grade obtained from the evaluations carried out before and after the training sessions. | 0 | An environmental monitoring system is being implemented with the support of a mobile application to record oceanographic data and incidents, but it is still in the initial implementation process. These data are not yet available because the training process has not started.
10 – Conservation of biological diversity |  |  | R1.Mortality of marine vertebrates (mainly turtles and seabirds) due to incidental capture in fishing gear. | (M.1.) Establish a monitoring program on board (verification at sea of the correct development of sustainable fishing methods) to monitor the incidental capture of marine vertebrates (mammals, birds and sea turtles), which will contribute to making recommendations to improve the fishing practice and thus reduce the incidental capture of the species and the associated mortality. | Number of fishing trips per vessel with observers on board. Catch per Unit of Effort (CPUE). Mortality by species. Number of individuals released (alive) by species. | 0 | An environmental monitoring system is being implemented with the support of a mobile application to register oceanographic data and incidents, but it is still in the initial implementation process. | The app does not have logistical support at the end of the project. | Signing of sustainability commitments with IMARPE and other public and private institutions.
|  |  |  | (M.2.) Train and sensitize artisanal fishermen in the identification of marine vertebrates and threatened local species; as well as the use of recovery, rehabilitation and release techniques for incidentally captured species. | Number of artisanal fishermen trained. Percentage (%) increase in the grade obtained from the evaluations carried out before and after the training sessions. | 0 | This monitoring system will also train fishermen on species identification and bycatch
|  |  | R2. Mortality of natural scallops predators | (M.3.) Design a protocol for the implementation of surveillance, prevention and control measures against COVID-19, for activities derived from on-board monitoring. | Protocol for activities derived from on-board monitoring, prepared. | 0 | There are report cards on symptoms related to COVID 19, which are reported at the time of field trips and trainings
|  |  |  | (M.4.) Design a protocol for the implementation of surveillance, prevention and control measures against COVID-19, for conducting training workshops. | Protocol for conducting training workshops. | 0 | There are report cards on symptoms related to COVID 19, which are reported at the time of field trips and trainings
11 – Climate change
12 – Pollution prevention and resource efficiency |  |  | R3. Pollution of seawater by the generation of solid and oily residues, originating from the aquaculture activity developed in the pilot sites of the project | (M.5.) Prepare the Environmental Management Instrument, corresponding to the activity to be carried out. | Current Environmental Management Instrument | 0 | The process has not started yet | The management tool needs to be constantly updated. | Obtain support from NGOs to update this instrument.
|  |  |  | (M.6.) Prepare and implement a solid and oily waste management plan, which must be part of the management plan for the fishing area or concession; taking into account the Guidelines for the surveillance of the health of workers at risk of exposure to COVID-19; prioritizing the use of sustainable alternatives. | Number of management plans prepared, approved and implemented by the beneficiaries. | 0 | So far, no plans have been made for the concession of the aquaculture zone, but activities related to the use of fishing gear are being carried out, in which the adequate disposal of solid and oily waste is considered. | Despite having the plan, the activities established in it are not being fulfilled. | Establish sanctions for consulting firms that carry out field work to report this data.
|  |  |  | (M.7.) Carry out periodic reviews of the engines of the vessels to avoid spillage of oils or lubricants, a measure that must be included in the management plan of the fishing area or concession. | Number of management plans for fishing areas or concessions (containing a solid and oily waste management plan), approved by the competent authority. | 0 | So far, no plans have been made for the concession of the aquaculture zone, but activities related to the use of fishing gear are being carried out, in which the proper disposal of solid and oily waste is considered. | Despite having the plan, the activities established in it are not being fulfilled. | Establish sanctions for consulting firms that carry out field work to report this data.
|  |  |  | (M.8.) Consider within the project component on capacity building, training modules on solid waste management and the adverse effects on local fauna; as well as good aquaculture practices. | Number of artisanal fishermen trained. Percentage (%) increase in the grade obtained from the evaluations carried out before and after the training sessions. | 0 | The start of training for the different activities is in process
|  |  |  | (M.9.) Supervise the proper development of aquaculture activity. | Number of supervisions carried out. | 0 | The aquaculture activities (aquaponics) are in the process of implementing greenhouses.
|  |  | R4. Pollution of the marine environment by residues from the implementation of the protocols for the surveillance, prevention and control measure against COVID-19 in the activity. | (M.6.) Prepare and implement a solid and oily waste management plan, which must be part of the management plan for the fishing area or concession; taking into account the Guidelines for the surveillance of the health of workers at risk of exposure to COVID-19; prioritizing the use of sustainable alternatives. | Number of management plans prepared, approved and implemented by the beneficiaries. | 0 | So far no plans have been made for the concession of an aquaculture zone, but activities related to the use of fishing gear are being carried out, in which the adequate disposal of solid and oily waste is considered.
|  |  | R5. Decline in the population of some species | (M.10.) Develop research aimed at generating information on the real impact of aquaculture on benthic species and implement the derived recommendations. | Number of investigations carried out. | 0 | There is 1 postgraduate thesis on climate vulnerability assessment (EVC) of the impacts of climate change on key species of the Peruvian tropical ecosystem. There is also 1 investigation on ecological risk to fisheries
|  |  |  | (M.11.) Develop capacities of local actors on techniques and methodologies for monitoring species. | Number of local actors trained. Percentage (%) increase in the grade obtained from the evaluations carried out before and after the training sessions. | 0 | An environmental monitoring system is being implemented with the support of a mobile application to record oceanographic data and incidents, but it is still in the initial implementation process. These data are not yet available because the training process has not started.
|  |  | R6. Pollution of seawater by the generation of solid and oily waste from the ecotourism activity carried out in the project pilot sites | (M.6.) Prepare and implement a solid and oily waste management plan, which must be part of the management plan for the fishing area or concession; taking into account the Guidelines for the surveillance of the health of workers at risk of exposure to COVID-19; prioritizing the use of sustainable alternatives. | Number of management plans prepared, approved and implemented by the beneficiaries. | 0 | Tourism activities are about to begin, and initiatives at sea will include the revision of the vessels.
|  |  |  | (M.7.) Carry out periodic reviews of the engines of the vessels to avoid spillage of oils or lubricants, a measure that must be included in the management plan of the fishing area or concession. | Number of management plans for fishing areas or concessions (containing a solid and oily waste management plan), approved by the competent authority. | 0 | Tourism activities are about to begin, and initiatives at sea will include the revision of the vessels.
|  |  |  | (M.12.) Develop training for beneficiaries on solid waste management. | Number of artisanal fishermen trained. Percentage (%) increase in the grade obtained from the evaluations carried out before and after the training sessions. | 0 | Tourism activities are about to start, and initiatives at sea will include training on solid waste management.
|  |  | R7. Displacement or abandonment of the habitat of marine vertebrates (mammals, birds and turtles) due to the noise of the boats and human presence in the places where the sightings are made | (M.13.Prepare codes of conduct of good practices for the observation of marine fauna, which must be implemented by the ecotourism companies formed. | Good practice code of conduct prepared and implemented. | 0 | The process has not started yet
|  |  |  | (M.14.) Sign agreements or commitments with the beneficiaries to comply with good observation practices. | Number of agreements | 0 | There are 2 conservation agreements with SERNANP, in Huacho, which contemplates the care of coastal marine ecosystems | The signing of conservation agreements in the pilot areas is paralyzed. | Coordinate with other projects or public entities to support the signing of conservation agreements with OSPAS.
|  |  |  | (M.15.) Develop environmental awareness campaigns and capacity building on good ecotourism practices, aimed at the direct beneficiaries of the activity. | Number of people trained. Percentage (%) increase in the grade obtained from the evaluations carried out before and after the training sessions. | 0 | Tourism activities are about to start, and initiatives at sea will include training on good ecotourism practices
|  |  |  | (M.16.) Promote compliance with legal regulations related to the tourist operation, such as Supreme Decree No. 006-2011-MTC - Regulation of Aquatic Tourist Transportation. | Number of supervisions carried out. | 0 | The process has not started yet
|  |  |  | (M.17.) Supervise the proper development of the ecotourism operation of the beneficiaries. | Number of supervisions carried out. | 0 | Tourism activities are about to start, and initiatives at sea will include training on good ecotourism practices | The tourist activity is carried out in an inadequate way due to little supervision of the entities involved. | Apoyo a MINAM y MINCETUR para asegurar que las actividades turisticas se desarrollen adecuadamente.
|  |  | R8. Pollution by the emission of odors during the conversion of fishing and aquaculture residues | (M.18.)Use appropriate techniques for the conversion of fishing and aquaculture waste. | Number of trained participants. Percentage (%) increase in the grade obtained from the evaluations carried out before and after the training sessions. Number of supervisions carried out. | 0 | 80 women have been trained in the production of biofertilizers No data has yet been registered on the impact of training
|  |  | R9. Soil and habitats contamination of guano birds | (M.19.) Evacuate all solid waste generated outside the protected natural area (Don Martín islet), taking into account the Guidelines for monitoring the health of workers at risk of exposure to COVID-19. | Amount of solid waste evacuated. | 0 | There are output formats, which are completed at each entrance to the Island | The waste generated and evacuated by the project activities is not registered. | Establish sanctions for consulting firms that carry out field work to report this data.
|  |  | R10. Displacement or abandonment of guano bird habitats | (M.20.) Coordinate with the RNSIIPG (SERNANP) staff the location and time of entry to the Don Martín islet. | Authorization to enter the protected natural area. | 0 | There is preliminary coordination with SERNANP for consultants to enter the Island. So far, 12 entries have been made to Don Martin Island
13 – Public health
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes, regarding current events(Pandemic), these are being included in the new social and environmental risk mitigation meassures and these had been monitored since March 2020
Have unanticipated ESP risks been identified during the reporting period? |  | Yes, a new update of the social and environmental risks was made through a consultancy, to which the possible social and environmental risks related to the pandemic are being added .
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | The principle of public health was activated, due to the pandemic since it has significantly affected the fishing communities of the PA, for which the project is providing support with personal protection equipment for the associations in order to reduce the spread of the virus .
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The implementing entity participated in the revision, approval and no objection of the governance consulting. The inclusion of this consulting will ensure to comply of social and environment safeguards, through of the inclusion of mitigation meassures in the activities planned to implement. These activities were consulted with project participants.
Have the implementation arrangements been effective during the reporting period? |  | The activities before mentioned will ensure the good development of productives activities and to mitigate of social and environment risk. Also, social and environmental safeguards services are recently being implemented, however the main limitation is the COVID19 restrictions in the pilot areas. Progress has been made in the planning work and there has been the collaboration of the user areas.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | We have updated ESP, what has been inplemented through of our colaborators in the field work, they used forms for monitoring the social and environment safeguards.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes, now the use of forms facilitates the monitoring and compliance of mitigation measures in the field work, also makes it easier the processing of the data obtained.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
A letter was received from the Chancay fishermen's association, requesting support for obtaining the fishermen license. |  | Support was provided for obtaining the fisherman license issued for DICAPI Chancay. The copy of the means of verification can be found below.
Grievance and suggestion format |  |  |  |  | Resolucion
Note on L35: CIMOBP: This principle was not actived
Note on L40: CIMOBP: This principle was not actived
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | No
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
COMPONENT 1: Implementation of interventions in pilot strategic areas to improve resilience of target coastal communities and key coastal marine ecosystems to climate change and variability-induced stress. | Objective | % of women of de individuals linked to the artisanal fishing activity adopting adaptation measures to climate | 0 | 20% | Good . Currently, there is a participation of 18% of women of the total beneficiaries, and it is projected to have more in the year 2021 -2022
COMPONENT 3: Capacity building and knowledge management system for implementing the EBA and the EAF, and for the dissemination of project’s lessons learned, targeting government officials, academia, local communities and other stakeholders | Objective | % of women with improved capacity | 0 | 80% | Good. It has started the training in the different productive activities and consulting about Early warning system (SAT) and knownledge management. There is a participation of 130 women(32.5%), considering a total of 400 (participants)
OUTPUT 1.2.2. Creation of ecotourism enterprises | Output | # of women association that incorporates ecotourism as a complementary economic activity | 0 | 1 | Good. A handcraft women association (AMARTEMM) are being supported also has started with the ecotourism bussiness initiatives with the participation of women ; also we will support to Ñuro women's association, who works in marine gastronomy
OUTPUT 1.2.3 Improvement of market power capacities for sustainable artisanal fisheries | Output | # of trade agreements managed in partnership with a women association | 0 | 1 | Good. In 2020 , we have started with participation of the women association "El Ñuro" with the sale of fish in the fair "A Comer Pescado" .
OUTPUT 1.2.5. Production of biofertilizers from fishery and aquaculture residues | Output | # women´s associations linked to artisanal fishing activity, generate bioproducts from fishing and aquaculture residues | 0 | 2 | Good. We have formed work groups of women in order to start with the implementation of the biofertilizers production plant in the two pilot areas.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | Work meetings have been held to review the products of the Social and Environmental Safeguards consultancies, sending contributions and suggestions.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes. Gender approach has been included in the terms of reference.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | The project includes three activities related to the inclusion of women in productive activities (exclusive), which has generated interest in them. Therefore, it has been possible to organize them to form productive associations, thus supporting their social and economic empowerment, this has been achieved by the constant support between the consultants and the project coordinating team, which has members with experience and knowledge in I work with a gender focus. Likewise, within the governance consultancy, the participation and support of a specialist on the subject has been contemplated, which will further reinforce the social empowerment of these associations.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | Yes, the active participation of women in the productive activities of the two pilot areas has been achieved
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Despite the COVID 19 pandemic, they have been able to partially comply with the GP, using new means and support in the pilot areas.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No complaints have been reported
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Project component 1 |  |  | S |  | MS: The progress reflected in its indicators is not the expected (31% y 20% for Outcomes 1.1 and 1.2 respectively), but Profonanpe: 1) provided support to establish thematic packages in order to improve the excecution and 2)Accompanied and participated in the selection process of those services. It is also important to mention some outstanding aspects in relation to the execution under this component: 1) Although the location and characteristics of the Natural Bank have been identified, which include the restoration actions, these activities have not taken place yet. 2) The progress under outcome 1.2 is related to the thematic packages, which have recently started to implement (i.e: aquaponics, tourism, bioproducts). | MS
| Project component 2 |  |  | S |  | S: The progress reflected in its indicators is the expected (80%), considering the project has passed the mid-term Some outstanding aspects in relation to the execution under this component: the project is having significant contribution to strengten institutional capacities related to AF outcome 2; like the training of IMARPE professionals, professionals from other institutions in SAT design and Articulation Plan | S
| Project component 3 |  | Outcome 3 | S |  | MS: The progress reflected in its indicators is not the expected (38%), but Profonanpe provided support to establish and approve the thematic packages in order to improve the execution. Some outstanding aspects in relation to the execution under this component by the executing entities: 1) the knowledge management system that has been designed and it is about to be implemented 2) 45 people among professionals and fishermen of the target population are being trained in several topics regarding sustainable fishing and commercialization, and there are two early warning systems developed. But the replication strategies should be in a certain level of development by now. | MS
| Project component 4 |  | Outcome 7 | S |  | U: Few action was taken in the reporting period, it was provided the support to stablish and approve the thematic package for the improvement of the governance Also, coordinations between DGPARPA and DGAAMPA have been made in order to move forward in this component. | U
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Pamela Reyes Neyra y Omar Corilloclla
| Email: | preyes@profonanpe.org.pe / ocorilloclla@profonanpe.org.pe
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Profonanpe provided support for updating indicators and goals of the results framework of the project, which was submitted to the Adaptation Fund, and it received the approval in June 2020. In order to improve the project execution and to ease procurement processes, Profonanpe also provided support in the development of seven clustering of activities or thematic packages of consultancies for the main project services, which terms of reference have been approved and the majority of the consultancies are in implementation. Also, as implementing entity, there were arranged with the project coordinator and the representative of National Designated Entity (MINAM) some meetings that address the bottlenecks identifed in the implementation as well as the following of the level of implementation. To date, the mid term evaluation of the project is in course and is it is expected to finish in July (There was the participation and collaboration of the key actors and partners of the project). The evaluation report will be sent to the AF as soon as it is received and approved. Regarding the project execution, it has to be considered that the project had a slow start since the design to the inception date (May2018), in addition to that, the first project coordinator resigned from his position (November 2018) and it caused a delay in project activities.The current project coordinator was hired in February 2019 and he developed the Project Implementation Plan (PIP), jointly with PRODUCE and IMARPE proffesionals.In relation to this, the project team, Produce, IMARPE and Profonanpe, as mentioned before developed the strategy of clustering or packaging of the main project activities, by 7 key topics and its terms of reference, in order to improve the execution of activities for the project remaining time. It is important to notice that by now, these packages are in the implementation (i.e:Aqcuaponics, bioproducts and tourism) or the hiring stage. Also, since january 2020, it was approved an Annual Operational Plan with January-December period, in order to improve the project tracking. Regarding Environmental and social safeguard, 2 consultancies were implemented, so the risks and mitigation measures initially identified were updated, in the same way the grievance mechanism was developed, and now all of them are in implementation. In the scope of component 2, some of the important progress were the development of vulnerability assessment of socio ecological and species in Talara, as well as an Evaluation of ecological risk to the fishery, also training of IMARPE professionals, professionals from other institutions in SAT design and Articulation Plan. In the 3rd component the main progress were made in the development of the 2 SAT.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 1.1 |  | Outcome 5 | S |  | Selective fishing gears and restoration of a scallop natural bed are being implemented to improve the resilience of coastal marine ecosystems to climate change | S
| Outcome 1.2 |  | Outcome 6 | S |  | Interventions in two pilot strategic areas are being implemented to improve diversification of livelihoods (aquaponics, oyster culture, biofertilizers, ecotoourism and commercialization) | S
| Outcome 2.1 |  | Outcome 2 | S |  | Three oceanographic gliders have been acquired as a marine environment surveillance system, climate vulnerability analysis of tropical species and socio-ecological vulnerability assessement of small-scale fishing communities have been carried out. Oceanographic scenarios are being modelled at regional and local scales. | HS
| Outcome 3.1 |  | Outcome 3 | S |  | The Knowledge management strategy design is available Implementation of a proposal for a Sectorial and Subnational Articulation Plan for adaptation measures in the planning and budget instruments and budgetary programs of the Fishing and Aquaculture Sub Sector of the Ministry of Production | MS
| Outcome 3.2 |  | Outcome 3 | S |  | Implementation of the Early Warning System Design for harmful algal blooms, sulfurous plums and marine heat waves as hazards associated with climate change for the coastal marine zone of Huacho and Mancora Budget was committed for the governance themathic package | MS
| Ourcome 4.1 |  | Outcome 7 | S |  | Coordinations between DGPARPA and DGAAMPA have been made in order to move forward in this component. It made possible the programming of four activities in the POA 2021, related to: 1) upport for intersectoral actions for the implementation of the Fisheries and Aquaculture NDCs, 2) Policy proposal to incorporate the ecological risk assessment in regulations for Fisheries and Aqcuaculture; 3) Comprehensive evaluation of the PNACP | U
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dimitri Gutierrez (Imarpe) and Sharon Dale (Produce)
| Email: | dgutierrez@imarpe.gob.pe/ sdale@produce.gob.pe
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Justification from Imarpe: Positive progress: Merging activities in six thematic packages (natural scallop bed restoration, aquaponics, oyster culture, commercialization, biofertilizers and ecotourism) allowed to start main interventions for diversification of livelihoods, international calls allowed to contract high-level experts for vulnerability assessments of species and fishing communities. The initial activities of the interventions have been positively received by the stakeholders and field work has begun, making important progress (organization and training of beneficiaries, implementation of infrastructure, etc.). Negative progress: Covid pandemic restricted field surveys, trips of experts to Peru, workshops with stakeholders, limited presential capacity building with fishers and delayed equipment acquisition, extending execution of consultancies. Some bureaucratic procedures were stopped or slowed down because of the pandemic. Recommendations: Promote extensive use of virtual workshops with fishers, and outreach of outcomes related to vulnerability studies and modelling scnearios, among decision makers and stakeholders. Implement the glider technology already acquired by IMARPE for monitoring and research surveys. Make efforts to streamline inter-institutional articulation in order to improve times in the coordination and execution of the different tasks. Extend the period of the project in order to accomplish project goals, and ensure scaffolding of fishers Justification from Produce: Positive aspects: 1. High participation of public institutions at the three levels of government: national, regional and local in programmed activities. 2 project beneficiaries continued to actively participate in virtual activities. Negative aspects: 1. Delay in the execution of activities due to the COVID 19 pandemic 2. The time lag in the programming and execution of the project, motivated appropriate and neccesary adjustments to the planned stage of activities, to achieve the expected results.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings. |  |  | 2
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance. |  |  | 1
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs. |  |  | 2
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs. |  |  | 1
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies
Note on F8: Pamela Patricia Reyes Neyra: Outcomes 5 and 6
Note on F9: Pamela Patricia Reyes Neyra: Outcomes 1 and 2
Note on D25: Pamela Patricia Reyes Neyra: Rated by Imarpe
Note on D26: Pamela Patricia Reyes Neyra: Rated by Imarpe
Note on D27: Pamela Patricia Reyes Neyra: Rated by Imarpe
Note on D28: Pamela Patricia Reyes Neyra: Rated by Produce
Note on D29: Pamela Patricia Reyes Neyra: Rated by Produce
Note on D30: Pamela Patricia Reyes Neyra: Rated by Produce

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator adjusted | Baseline | Progress since inception | Target for Project End | Explanation of the progress to date | 0.44828
Objective/Component 1 | # of persons in PA linked to the artisanal fisheries adopting climate change adaptation measures that improve their livelihoods and the resilience of the ecosystem | 0 | 41% | 700 | Progress has been made in the milestones: Identification of beneficiaries, Beneficiaries by activity and Beneficiary commitments to the reporting date. It is estimated that 400 beneficiaries are at different levels of commitments, however 290 have a significant level of progress. With this last number, the percentage of completion was estimated. | 0.41429
| % of women of the individuals linked to the artisanal fishing activity adopting adaptation measures to climate change | 0 | 32.5% | 20% | It is estimated from the number of identified women out of the total number of identified beneficiaries, at the reporting date it is estimated 130 women.
Outcome 1.1. / Output 1.1.1 | # of vessels in PAs adopting selective fishing gear | 0% | 31.47% | At least 30 vessels | Identification of formal vessels and start-up in the activities of gillnets (7 with field operations), purse seines (3 with field operations) and angling (30 identified). | 0.33333
Outcome 1.1. / Output 1.1.2 | # of natural banks re-stocked | 0 | 20.83% | 1 natural bank of Peruvian scallop in Don Martin Island | Characterization and location of the natural bank and installation of the catchment system. The procurement of materials and equipment for field work is in process. In addition, training for project beneficiaries is also in process.
| # of natural banks co-managed | 0 | 42.5% | 1 natural bank of Peruvian scallop under co-management principles | Fisheries ecological risk assessment and a conservation agreement have been developed between fishermen's associations and the entity in charge of protected areas, SERNANP.
Outcome 1.2. / Output 1.2.1 | # of artisanal fishermen associations and women linked to the artisanal fishing activity, developing sustainable aquaculture reporting profits | 0 | 24.17% | At least two associations of fishermen and one of women linked to fishing activity develop sustainable aquaculture activities that report profits. | It represents progress in identifying areas as well as the formalization and training of women beneficiaries in the Aquaponics activity in Huacho. 25 women have been identified.
| # of projects with business plans | 0 | 0% | 3 business plan | It depends on the progress of the aquaculture activities.
Outcome 1.2./ Output 1.2.2 | # of fishers associations participating in sustainable tourism ventures reporting complementary income | 1 | 13.22% | At least 2 fishers associations | Progress in the estimation of the number of beneficiaries identified and their formalization, as well as the formation of provincial working groups for the formulation of Tourism Development Plans (PDTL). There are 67 identified beneficiaries and 19 artisan women supported in updating their formalization.
| # of women association that incorporates sustainable tourism as a complementary economic activity | 0 | 13.22% | At least 1 women association | It has been estimated the number of beneficiaries identified and their formalization. There are 19 artisan women supported in the updating of their formalization.
Outcome 1.2./ Output 1.2.3 | % of fishers reporting increased income per fishing ton sold. (from a total of 300 fishers in Máncora). | 0 | 30% | 20% of artisanal fishers increase their revenue per ton sold | The progress represents the identification and prioritization of beneficiaries in the pilot areas.
| # of trade agreements between SOAFs and middlemen / final consumer (i.e. restaurant, supermarket | 0 | 22.5% | At least one trade agreement | Identification of improvements in the marketing of prioritized products in both pilot areas.
| # of trade agreements managed in partnership with a women association | 0 | 0% | At least one trade agreement | It depends on the marketing improvements, these are in the initial process of implementation (coordination with competent institutions and local authorities).
Outcome 1.2./ Output 1.2.4 | # of fishing units incorporated in a catches traceability system applying sustainable fishing gear | 0 | 12.5% | 33 fishing units | Initial experiences of traceability systems with two vessels in the pilot area of ​​Mancora, with the installation of cameras on board, formalization and issuance of QR code for the commercialization of hydrobiological resources.
Outcome 1.2./ Output 1.2.5 | # of women's associations linked to artisanal fishing activity, generate biofertilizers from fishing and aquaculture residues | 0 | 47.92% | At least two women's associations | A feasibility study has been made, identification and formalization of women beneficiaries as well as the installation of a module prototype. There are three women's associations in the towns of Los Organos, El Ñuro (Mancora pilot area) and Carquin in Huacho.
Objective /Component 2 | No. of modern systems for environment surveillance and prediction implemented | 0 | 79.87% | 1 modern system | Describes the progress of the outputs that make up the component.
Outcome 2.1 / Output 2.1.1. | # of marine autonomous gliders in operation | 1 | 87.5% | 3 Glider marine autonomous gliders in operation | It only remains to conclude with the start-up for the planning of the deployments.
| # of platforms for oceanographic data dissemination in almost real-time implemented | 0 | 87.5% | 1 platforms for oceanographic data dissemination in almost real-time implemented | Advances in training and information systematization.
| # of high-resolution oceanographic data management systems of the project implemented |  | 75% | 1 system | Advances show the training for the implementation of the Implemented and Automated Oceanographic Data Quality System and Control (IODE).
Outcome 2.1 / Output 2.1.2. | # of bio-oceanographic baseline evaluations for each AP | 0 | 100% | 1 bio-oceanographic baseline evaluation for each AP | It has been made the field work, the systematization of the historical information, the analysis of the information and the presentation of the final report.
| # sensors and data loggers for high-frequency observation of SST and conductivity | 0 | 50% | 3 sensors and data loggers for high-frequency observation of SST and conductivity | The acquisition of the equipment is in the tender process.
| Quality environmental and red tides monitoring program with local stakeholders | 0 | 64.58% | 1 operational monitoring program of environmental quality (DO, pH, harmful algal blooms) at selected points and on a seasonal basis | It represents the progress in the acquisition of oceanographic equipment.
| Ecosystem resilience monitoring program designed with other stakeholders and including fishermen as observers | 0 | 50% | 1 proposal developed for an ecosystem resilience monitoring program | A Participatory Monitoring System has been designed, and its implementation is in process in both pilot zones. Also in the terminal phase is the Evaluation of the Coastline in both pilot areas.
Outcome 2.1 / Output 2.1.3. | # of oceanographic scenarios under optimistic and pessimistic IPCC greenhouse gas concentration trajectories (RCP 8.5 and RCP 3-PD) | 0 | 50% | 2 scenarios developed (optimistic and pessimistic) | The hiring of a specialist has been developed for the simulation of oceanographic scenarios in the pilot areas of Huacho and Máncora using regional models.
| # of catch potential scenarios of key resources under IPCC greenhouse gas concentration trajectories RCP 8.5 and RCP 3-PD | 0 | 50% | 2 scenarios developed (optimistic and pessimistic) | Specialists work in process, as well as research stays abroad.
Outcome 2.1 / Output 2.1.4. | # of trained scientists at IMARPE and academia and/or other centres |  | 66.67% | At least 15 trained scientists in IMARPE, and a similar number in academia and/or other centres. | At least 10 trained professionals
| # of workshops and seminars for decision-makers |  | 50% | 4 workshops / seminars directed to decision-makers within the framework of the project | Two webinars have been held about species vulnerability and socioecology.
| # of undergraduate and graduate thesis developed related to project outcomes (baseline studies, aquaculture impact, ERAs, etc.), | 0 | 87.5% | At least 6 theses incorporating issues related to project | 1 thesis completed, and five about to be completed.
Objective / Component 3 | No. stakeholders with improved capacity in order to reduce vulnerability to climate chang | 0% | 25% | At least 10 fishery associations and 6 public institutions (PRODUCE, IMARPE, MINAM, SERNANP, local governments) | It represents the percentage of progress of the training related to project activities to IMARPE, PRODUCE, SERNANP MINAM institutions as well as regional and local authorities.
| % of women with improved capacity | 17% | 16.67% | 80 % of women with improved capacity | Approximately 40 women at different levels with improved capacities have been identified.
Outcome 3.1 / Output 3.1.1 | # of tools to support the processes of production, storage, update, circulation and knowledge (re)use | 0 | 50% | Formal communication, storage, classification and distribution systems of the information generated | The EGC Knowledge Management Strategy has been designed and is being implemented.
| # of documented lessons by users type | 0 | 0% | As part of the learning process there are identified at least 2 replication strategies for scale up (technical and management) by characterized user type (governmental, non-governmental, private, beneficiaries) | It depends on the EGC implementation, which is recently in implementation
| # of replication strategies for scale-up |  | 0% |  | It depends on the EGC implementation, which is recently in implementation
| # of sectoral public management instruments that include project adaptation measures aligned with the NDCs | 0 | 85.42% | 01 Sectoral Strategy proposal on fisheries and aquaculture aligned with the NDCs | Consulting is in its final phase
Outcome 3.2 / Output 3.2.1 | # of artisanal fishers and other key agents trained in issues related to Component 1: fishing sustainable methods, self-organization, legal formalization, entrepreneurship, fisheries certification, marketing, | 0 | 66.67% | 30% of the target population trained | It shows the progress in the programming of activities and training for artisanal fishermen, as part of the activities and consultancies of the project, such as Early Warning Systems and Knowledge Management strategies. It is estimated a number of 40 people involved in total.
| # of debate spaces for sharing successful experiences | 0 | 0% | 3 network-wide debates for beneficiaries at each PA to generate synergies and share learning | It depends on the EGC implementation, which is recently in implementation
Outcome 3.2 / Output 3.2.2 | # early warning systems associated to environmental variables | 0 | 61.67% | Two early warning systems developed with a set of reference levels and indicators associated to environmental variables to identify and timely evaluate the emergence of short-term deviations for taking appropriate action | Design consultancy for the SAT Early Warning System is in final process, the implementation is planned.
Objective / Component 4 | No. regulations or instruments proposals to promote resiliency of ecosystems and communities to climate change | 0 | 2.812% | At least 4 regulations or instruments proposals to promote resiliency of ecosystems and communities to climate change | It describes the progress of the activities or outputs that make up the component.
Outcome 4.1 / Output 4.1.1 | # of cross-sector management proposals addressing coastal marine issues related to climate change. | 0 | 6.25% | One cross-sector draft plan incorporating coastal and marine environments in climate change adaptation strategies and instruments for defining sector policies related to Integrated Management of Coastal Marine Areas | Consultancy for intersectoral articulation is recently in process.
| # of economic ecological zoning proposals in PA. | 0 | 0% | 1 zoning proposal have been developed in coordination with the MINAM (Territorial Ordination Office) | It depends on the progress of the intersectoral articulation service.
Outcome 4.1 / Output 4.1.2 | # of proposals for the update and/or development of the current fisheries normativity and regulations, with focus on co-management | 0 | 1.25% | At least one normativity or guideline is incorporated for co-management at the sectorial and regional level | Consultancy call is in process.
Outcome 4.1 / Output 4.1.3 | # of regulations and/or administrative procedures for the implementation of incentives approved | 0 | 3.75% | 1 regulation incorporated to promote artisanal fishing products for Direct Human Consumption, applying sustainable fishing methods, in the national and regional laws and regulations | It is in the consultative process of integral evaluation of the National Program To eat Fish of the Ministry of Production.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The pandemic imposed restrictions on project activities and project beneficiaries. Administrative processes continue to be a limiting factor for project execution.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The suspension of the calls for consultancies in 2020 significantly delayed the execution of the project. Negotiations were made with the parts of the project to accelerate the processes and at the end of 2020 the calls for the thematic packages are resumed. To date, we have hired 5 thematic packages. DGPARPA of the Ministry of Production states that it does not have competencies to develop the activities of the component 4 of the project. In a higher level internal coordination in PRODUCE, adjustments to the responsibilities between DGPARPA and DGAAMPA were determined, in order to develop the component 4 activities.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | The regrouping of activities for the competition and award is an important change, in addition to the fact that a consultancy aimed at strengthening Governance in order to complement the activities established in component 4 is being included here.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | With the start of consultations for the implementation of the 5 activities of component 1, the Environmental and Social Safeguards Management Plan - PGAS has been updated and consultants have been trained for its implementation, as well as the establishment of the respective information flow. Measures are being implemented to avoid negative impacts, such as: 1.- Technical assistance for the organizational cleanup of the OSPAs and other forms of associativity of the beneficiaries 2.- Financing the cost of the pilot's sustainable fishing gear 3.- Support for the commercialization of marine products from the new responsible fishing practices, participation in the fairs of the National Program to Eat Fish "A comer pescado". 4.- Strengthening the capacities of the beneficiaries for the adoption of new responsible fishing practices, new undertakings of complementary activities and mechanisms for the conservation of species.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | We have worked with a group of women in the pilot area of ​​Huacho in the framework of the consultancy on the implementation of an aquaponic module, we are also working with a group of women in Los Organos, El Ñuro and Carquin for the implementation of modules of waste treatment in fishing and aquaculture, and training sessions and an internship have been developed. These activities have had the prior identification of basic selection criteria such as that they are directly or indirectly related to the artisanal fishing activity and that they have residence in the area, counting on a favorable response and a growing interest and commitment.It is important to mention that the indicated activities are designed for work exclusively with women and whose impact results will allow to visualize their participation in the community and contribute to their empowerment. Currently, the formalization aspects are being worked on, which will allow consolidating the mechanisms of collaboration and trust with the project.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The repopulation activities of the scallop species have begun on Don Martin Island, where despite the fact that this activity does not consider the identification of direct beneficiaries, for the use of the repopulated resource, there have been coordination with the Management Committee of the ANP Natural Protected Area, and training meetings with a group of fishermen who are part of this committee in order to inform and be part of the initiative. In relation to administrative aspects, it is necessary to indicate that some limitations occurred in relation to the requirements that SERNANP was requesting to grant permission to carry out activities in the ANP, these were overcome in coordination carried out in the technical secretariat of the project Work has begun with women in both pilot sites, related to the Aquaponic cultivation module in Huacho and the waste treatment modules in fishing and aquaculture in El Ñuro and Los Organos in Piura and Carquin in Huacho, where training activities are carried out. with the group of women involved. These activities have been accelerated from the hiring of consultancies for the development of these activities, establishing a coordinated work with the project's field articulators. In the activities to promote sustainable tourism, there was a significant participation of beneficiaries in the call for expressions of interest of project initiatives that have been selected in each pilot area, this as a consequence of: i) a communication strategy in networks and advertising on a web microsite designed by the consulting team, ii) a coordinated work of the project coordinators with the professionals responsible in the field of the consulting team. In addition, work is being carried out on the beginning of the process of formulating the Local Tourism Development plan, which has, from the beginning, with the active participation of local authorities. The prioritization of resources, fisheries and beneficiaries for intervention in marketing improvements has made it possible to identify critical routes for implementation, counting on the participation according to competencies of various institutions both at local, regional and national levels.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Although we are in an initial stage of the implementation of the activity of improvement of capacities in the commercialization and initiation of certification, this activity is related to the result of other activities and the traceability work of the productive chain constitutes a key element for scaling and replicability at the end of the project.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | This grant was important to enhance key actors knowledge in the implementation of the Adaptation Fund's and Profonanpe's ESP and Gender policies. The workshop participants could recognize the importance of applying environmental and social safeguards and gender approach for a good project performance. It is considred that this type of grants effectively contribute to strenghten capacities environmental and social safeguards and gender of the new policies at that time, and complement with the AF current project in the successful implementation of the policies mentioned before. Another good aspect is that this fund was a good complement to a GCF readiness funds that were aligned to the topics mentioned before.
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | The grant was used in 2017 for training of Profonanpe’s technical staff, project coordination teams and a pool of specialists in environmental and social safeguards and gender approach, to carry out the implementation of the Fund’s Environmental and Social Policy (ESP) and the Gender Policy in programs and projects. - A workshop was held in the city of Lima between 6 and 8 of September 2017. A total of forty people including Profonanpe’s technical staff, project coordination teams and a selected pool of specialists in environmental and social safeguards and gender approach participated in this workshop that sought to enhance participants’ knowledge in the effective implementation of the Adaptation Fund’s ESP and Gender Policy in programmes and projects, as well as Profonanpe’s environmental, social and gender policies. In the framework of the workshop, there were developed some excersises thar required the elaboration of a checklist for screening projects against environmental and social risks, project cases and PowerPoint presentations tha were shared with participants. At the end of the workshop an evaluation survey was carried out, as well as photographs, a social media release on Profonanpe's social media and the workshop report were developed. Also with this grant it was possible to publish Profonanpe´s environmental, social and gender policies in its institutional web site.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | To date, the following can be identified:: Positive lessons: - Consider previous actions for the implementation of adaptation measures in local actors and beneficiaries.. - Involve local actors and beneficiaries in project activities from the early stages. - Promoting and training in the use of virtual spaces and platforms is key to developing capacities in a pandemic context.. - The design of the Sectorial Articulation Plan has made it possible to identify the link between the planned actions and progress of the project with the Nationally Determined Contributions approved by the Ministry of Production PRODUCE, allowing articulation with the directions and involved areas of PRODUCE and MINAM. Negative lessons: - - The adaptation measures must be formulated as results of the project, considering the real technical and administrative scope, if there are external factors to the measures that are not under the project's control, there is a high risk for their implementation.. - It is necessary to formulate the theory of change for the project as well as the corresponding indicators in the design phase, as well as their review, update and validation at the beginning by the team and executing partners.. - It is necessary to have a governance arrangement for the project that minimizes administrative requirements and simplifies its processes, especially when it involves the participation of more than one executing institution involved. -It is necessary that the design considers the administrative procedures that are part of each of the institutions that are part of the project. The project processes that involve the review or approval of more than one institution translate into complex and bureaucratic procedures that limit the execution of the project.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | There is a high biological and social connectivity in the coastal marine ecosystems, considering this, it is expected that the implementation and achievement of the impact results of the adaptation measures promoted by the project will be supported by governance arrangements for their sustainability, and may replicate, there are actions such as: - Conservation agreements between the beneficiaries and public entities or local authorities. - Framework agreements between beneficiaries and local authorities for the development of productive activities such as tourism. - Alliances with other similar projects so that they can grant continuity to the intervention.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The progress that have been made in the formalization of the groups of beneficiaries and the support in the commercialization of hydrobiological resources:: Identification and coordination with groups of beneficiaries in sustainable tourism initiatives in the pilot sites. Support in the formalization and generation of capacities with the beneficiaries of the waste treatment modules in fishing and aquaculture. Technical and scientific support for the generation of capacities for the improvement of fishing gear in the pilot sites..
What measures are/have been put in place to ensure sustainability of the project/program results? | There is a consultancy that addresses all the issues of improving the governance of the activities and adaptation measures of the project.
What measures are being/could have been put in place to improve project/program results? | Field coordinators work in each pilot site of the project, whose main functions are to coordinate with local actors, consultants, and beneficiaries. There is direct coordination between the coordinators of the project and the operators of each consultancy in each pilot site.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | We have the design of the Knowledge Management Strategy for which workshops were held in the pilot areas. Workshops and meetings have also been held with professionals and fishermen to identify the vulnerability of species in the Mancora pilot area.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | The analyzes carried out in the species and socio-ecological vulnerability assessments were disseminated through a webinar organized by IMARPE and the project on the Facebook live platform (June 2021).
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
Products | Hyperlinks
APOYO EN LA INVESTIGACIÓN PARA LA CULMINACIÓN DEL LEVANTAMIENTO DE INFORMACIÓN DE LOS CRUCEROS Y PROSPECCIONES PARA INCORPORACION A LA DATA DEL CENTRO DE DATOS OCEANOGRÁFICOS | https://drive.google.com/file/d/1K1vpJM3BidkeuSLpdGmZwozdVG5PoR0L/view?usp=sharing
REPOBLAMIENTO DE UN BANCO NATURAL DE CONCHA DE ABANICO (primer producto) | https://drive.google.com/drive/folders/1hIRrjmmGfgzeGIPewE2Guat46HH03WpA?usp=sharing
IMPLEMENTACION DE UN CULTIVO ACUAPONICO (primer producto) | https://drive.google.com/drive/folders/1SXPZRSY5HZFDW2DY3EUiYpHvBW8bkVDA?usp=sharing
PROMOCION DEL TURISMO SOSTENIBLE (primer producto) | https://drive.google.com/drive/folders/1Srb_lHk_PWJOsOhRcfzuZz1kpV5ilTq0?usp=sharing
COMERCIALIZACION Y PREEVALUACION (producto 2) | https://drive.google.com/drive/folders/11ZPyh_4BBx0r-oI7QqtGYDX4YDMgK9nr?usp=sharing
CONSULTORIA PARA EL MEJORAMIENTO Y ASISTENCIA TECNICA EN REDES DE ENMALLE DE RECURSOS COSTEROS EN HUACHO | https://drive.google.com/drive/folders/1oRlFS9VOe-nmgGfvCQu4LDPueG81igF9?usp=sharing
Asistencia de investigación para el análisis de la vulnerabilidad socioecológica de comunidades pesqueras artesanales de la zona piloto de Máncora frente al cambio climático | https://drive.google.com/file/d/1qZ5IsDLlOXjaOFxTxfEhKLGlEIjRJd3Z/view?usp=sharing
EVALUACION DE LA LINEA DE COSTA (producto 5) | https://drive.google.com/drive/folders/1Wi6-NJTeXLtlZjGDZjWDHc6vRVBwBH4Y?usp=sharing
Evaluación de vulnerabilidad climática (EVC) de los impactos del cambio climático sobre especies clave del ecosistema tropical peruano (final). | https://drive.google.com/file/d/1e7b7JDOUWABeGE2_WzNMaOp0CByj1p0v/view?usp=sharing
Estudios del ambiente en zonas marinas y costeras con datos provenientes de despliegues de vehículos autónomos submarinos (producto 7). | https://drive.google.com/file/d/1vbnNSsAGgYDoJd-MJwRdStGJ_ikQRY1p/view?usp=sharing
Modelado estadístico de especies en zonas marinas y costeras de las áreas piloto de Huacho y Máncora (producto 7). | https://drive.google.com/file/d/1nmXLpucjY0BXvtrvFb71EN3ORegXpLZX/view?usp=sharing
Evaluación de la Vulnerabilidad Climática (EVC) de especies del ecosistema tropical peruano (producto 8). | https://drive.google.com/file/d/1kRCuVrbeii_VRDPZqw6zAmINtm6ZmKD6/view?usp=sharing
Asistencia para estudio de impacto del cambio climatico sobre comunidades bentonicas | https://drive.google.com/file/d/1d4_PhOCb7OVnmMvQ32Dq0E6EerEMvVb-/view?usp=sharing
MODELADO ESTADÍSTICO DE ESPECIES EN ZONAS MARINAS Y COSTERAS DE LAS ÁREAS PILOTO DE HUACHO Y MÁNCORA (producto 7). | https://drive.google.com/file/d/1Phh4lsQ69dKmHC9RlZITwqzSVe6kGv3A/view?usp=sharing
Servicio de evaluacion de riesgo ecologico asociado a pesquerias artesanales seleccionadas | https://drive.google.com/file/d/1Nzaxtq7XCBtk-HoZoYu8keSFSYa4eZuv/view?usp=sharing
Asistencia tecnica para implementacion de las salvaguardas sociales y el enfoque de genero en el proyecto (parcial). | https://drive.google.com/file/d/1LKJ7SuMgGtwLSFiqFDvrfVtkmeAn3AfJ/view?usp=sharing
Fotografias del proyecto | https://drive.google.com/drive/folders/1DwAL_vaW8YMOAb_DEcQg9aLX7Yx9I0Er?usp=sharing
Linea de base, version final | https://drive.google.com/file/d/1xR2Te-fGm_jeRaOXk87UuhQyJsfu8sCI/view?usp=sharing
If learning objectives have been established, have they been met? Please describe. | Learning objectives have not been established, however, the development and systematization of lessons learned from the project are planned as part of the implementation of the EGC knowledge management strategy.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Although there is data and information generated by IMARPE, it was identified that this is not in compatible public formats, it is not in detail at a local scale, aspects that have made it difficult to establish thresholds in the impacts identified for the design of the SAT.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | In the context of COVID, the use of virtual platforms for coordination with project beneficiaries is being innovated, as well as the replacement of face-to-face workshops and meetings.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | Profonanpe
Type of implementing entity | NIE
Country | Peru
Region | Latin America and Caribbean
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at Year 3
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 3541 | 741 | 2800 | Total | 3541 | 741 | 2800 | Total | 2000 | 400 | 1600
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 36% | 20% | 40% | % of female beneficiaries | 0.6% | 3% | 0.8% | % of female beneficiaries | 6.5% | 32.5% | 8.125%
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at Year 3
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Coastal flooding |  | Total | 60 | Coastal flooding | 4: Effective | Total | 60 | Coastal flooding | 4: Effective | Total | 400 | Coastal flooding | 4: Effective
|  | % of female targeted | 0% |  |  | % of female targeted | 20% |  |  | % of female targeted | 15% |  |  | % of female targeted | 68%
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Coastal management | Regional | 3: Risk and vulnterability assessments completed or updated | 1 | Coastal management | Regional | 1: No plans conducted or updated | 1 | Coastal management | Regional | 3: Risk and vulnterability assessments completed or updated | 3 | Coastal management | Regional | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding
|  | 0 | 1: Risk knowledge | Geographical coverage | Local | 2 | 1: Risk knowledge | Geographical coverage | Local | 0 | 1: Risk knowledge | Geographical coverage | Local | 2 | 1: Risk knowledge | Geographical coverage | Local
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 5 |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 5
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 2 | 2: Monitoring and warning service | Geographical coverage | Local | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 0 | 2: Monitoring and warning service | Geographical coverage | Local
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 5 |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding
|  | 0 | 3: Dissemination and communication | Geographical coverage | Local | 2 | 3: Dissemination and communication | Geographical coverage | Local | 0 | 3: Dissemination and communication | Geographical coverage | Local | 0 | 3: Dissemination and communication | Geographical coverage | Local
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 5 |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding
|  | 0 | 4: Response capability | Geographical coverage | Local | 2 | 4: Response capability | Geographical coverage | Local | 0 | 4: Response capability | Geographical coverage | Local | 0 | 4: Response capability | Geographical coverage | Local
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 5 |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at Year 3
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 30 | Coastal management | 3: Medium capacity | Total | 30 | Coastal management | 4: High capacity | Total | 30 | Coastal management | 4: High capacity | Total | 45 | Coastal management | 2: Low capacity
|  | % of female targeted | 17% |  |  | % of female targeted | 20% |  |  | % of female targeted | 17% |  |  | % of female targeted | 33.33%
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 30 | 17% | Public |  | 30 | 20% | Public |  | 30 | 20% | Public |  | 45 | 33.33% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Coastal management | 3: Medium capacity | Public | National | Coastal management | 4: High capacity | Public | National | Coastal management | 3: Medium capacity | Public | National | Coastal management | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at Year 3
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% |  |  |  |  | 4: Mostly aware |  |  |  | 4: Mostly aware |  | 11 | 33.33% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Performance at Year 3
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
[6 empty] | Coasts | 1 | ha rehabilitated | 4: Effective | Coasts |  | ha rehabilitated | 1: Ineffective | Coasts | 1 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at Year 3
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 |  |  |  | 5 | Physical capital | Coastal management | Community-based adaptation | 0 | Physical capital | Coastal management | Community-based adaptation | 4 | Physical capital | Coastal management | Community-based adaptation
|  | 0 |  |  |  | 7 | Social capital | Coastal management | Community-based adaptation | 0 | Social capital | Coastal management | Community-based adaptation | 9 | Social capital | Coastal management | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
0
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at year 3
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
2: Most not integrated
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 |  |  |  | 4 | Coastal management | National | Other policy | 0 | Coastal management | National | Other policy | 0 | Coastal management | National | Other policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at Year 3
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
Note on I23: Cynthia Mirella Cespedes Madalengoitia: to be determined
Note on J23: Cynthia Mirella Cespedes Madalengoitia: to be determined
Note on K23: Cynthia Mirella Cespedes Madalengoitia: to be determined
Note on M23: Cynthia Mirella Cespedes Madalengoitia: to be determined
Note on N23: Cynthia Mirella Cespedes Madalengoitia: to be determined
Note on O23: Cynthia Mirella Cespedes Madalengoitia: to be determined
Note on I27: Cynthia Mirella Cespedes Madalengoitia: this number refers to direct beneficiaries
Note on M27: Cynthia Mirella Cespedes Madalengoitia: this number refers to direct beneficiaries (9)
Note on P30: User: Evaluation of ecological risk to the fishery Vulnerability Assessment of species in Talara Socio-ecological Vulnerability Assessment in Talara
Note on K39: Cynthia Mirella Cespedes Madalengoitia: Thiis include ENSO, algae blooms and sulphidic plums
Note on P40: User: 1 at Mancora pilot site 1 at Huacho pilot site
Note on Q54: User: 15 professionals in Articulation Plan 15 professionals and 15 fishermen in SAT design
Note on Q55: User: 15 identified women
Note on J57: Cynthia Mirella Cespedes Madalengoitia: the 30 trained belongs to public (15) and private sector (15)
Note on N57: Cynthia Mirella Cespedes Madalengoitia: the 30 trained belongs to public (15) and private sector (15)
Note on P57: User: 15 professionals in Articulation Plan 15 professionals and 15 fishermen in SAT design
Note on Q57: User: 15 identified women
Note on H67: Cynthia Mirella Cespedes Madalengoitia: According to the Results Framework, the target for this indicator is at least 10 fishery associations and 6 public institutions. In the next reporting period, we will determine the total number of people trained
Note on L67: User: The Knowledge Management Strategy has been designed, however its implementation would allow reporting the progress of the number of associations and institutions aware of it.
Note on P67: User: OSPAs: 2 Huacho, 1 Carquin, 1 Vegueta, 1 Cabo Blanco, 1 Los Organos and 1 Mancora. Institutions: PRODUCE, IMARPE, PROV HUAURA MUNICIPALITY, PIURA PROVINCIAL MUNICIPALITY
Note on Q67: User: 15 women out of a total of 45 people
Note on M94: User: The location and characteristics of the Natural Bank have been identified, including the restoration actions, although these have not taken place yet.
Note on Q94: User: The location and characteristics of the Natural Bank have been identified, including the restoration actions, although these activities have not taken place yet.
Note on C109: Cynthia Mirella Cespedes Madalengoitia: no es posible reportar este indicador
Note on H118: Cynthia Mirella Cespedes Madalengoitia: alineado al resultado 1.2 se cuentan la planta de bioproductos y las 2 concesiones de acuicultura (ostras y concha de abanico) 2 de acuaponía
Note on K118: Cynthia Mirella Cespedes Madalengoitia: the project uses the ecosystem-based adaptation approach
Note on P118: User: 3 Bioproducts modules (2 emancora and 1 in Huacho) 1 Aquaponics Module 1 Oyster Farming (pending)
Note on H119: Cynthia Mirella Cespedes Madalengoitia: 2 asociaciones de mujeres de acuaponía 2 asociaciones de pescadores y 1 de mujeres en turismo 2 asociaciones para acuicultura = 7
Note on P119: User: 1 association of women in Aquaponics (pending) 3 associations of women in Bipodructos 6 associations of men and women in Tourism 1 oyster farming association (pending)
Note on H121: Cynthia Mirella Cespedes Madalengoitia: The target is 700 individuals as beneficiaries of component 1. At this time we can not determine how many families belong because it is possible that some beneficiaries belong to the same household. In the next reporting period we can have this information
Note on I121: Cynthia Mirella Cespedes Madalengoitia: It is very difficult to obtain this value in the sector because there is a cultural factor, the fisherman is very jealous with the information and there is a high distrust
Note on Q121: User: It is very difficult to obtain this value in the sector because there is a cultural factor, the fisherman is very jealous with the information and there is a high distrust
Note on K133: Cynthia Mirella Cespedes Madalengoitia: Fishing and aquaculture policy
Note on O133: Cynthia Mirella Cespedes Madalengoitia: Fishing and aquaculture policy
Note on S133: User: Fishing and aquaculture policy