## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 2019-2020
| Project Title: | Adaptation to the Impacts of Climate Change on Peru’s Coastal Marine Ecosystem and Fisheries
| Project Summary: | The main challenge consists in increasing the resilience of the coastal marine ecosystems and the coastal communities (particularly the artisanal fishing communities) to climate change impacts. The main beneficiaries of this project are the artisanal fishing communities, whose livelihoods largely depends on the status of the coastal marine ecosystems, which are already subject to a number of non-climatic threats.The overall objective of the project is to reduce the vulnerability of coastal communities to impacts of climate change on the coastal marine ecosystems and fishery resources.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Peruvian Trust Fund for National Parks and Protected Areas - Profonanpe | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | NIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Perú | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Máncora, Los Órganos, El Ñuro y Cabo Blanco (04°05 - 04°15'S) Don Martin Island to Punta Salinas (11 ° 01'S - 11 ° 19'S), and includes Végueta, Huacho and Carquín | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2015-10-09
IE-AFB Agreement Signature Date: |  | 2016-05-01 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2018-05-17 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | May 2020
| Original Completion Date: | September 2022
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | José Zavala Huambachano | Dominican Republic
| Email: | coordinador.pamc@acomerpescado.gob.pe | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Laura Secada Daly | Equatoral Guinea
| Email: | lsecada@minam.gob.pe | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Omar Corilloclla Terbullino | Fiji
| Email: | ocorilloclla@profonanpe.org.pe | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Felix Fabian Puente de la Vega Chumbe | Georgia
| Email: | fpuentedelavega@acomerpescado.gob.pe | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Dimitri Gutiérrez Aguilar | Grenada
| Email: | dgutierrez@imarpe.gob.pe | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [April 30th, 2019] |  |  |  |  | Financial information: cumulative from project start to [April 30th, 2020]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [1/05/2016] | 2979902.3305 |  |  |  | Estimated cumulative total disbursement as of [1/05/2016] |  | 2979902.3305
Add any comments on AF Grant Funds. (word limit=200) |  |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | The grant has been disbursed in a current account that in Peru doesn´t generate incomes. |  |  |  | INVESTMENT INCOME |  | The grant has been disbursed in a current account that in Peru doesn´t generate incomes.
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION |  | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION |  | AMOUNT
| Project Output | Activity programmed in the Annual Operation Plan (AOP) 2018/2019 |  |  |  |  | Project Output | Activity programmed in the Annual Operation Plan (AOP) 2019/2020
| OUTPUT 1.1.1. Adoption of sustainable fishing methods to tackle non-selective fishing gear based on EAF principles directed to target species vulnerable to climate change | 1.1.1.1. Implementation of a conversion pilot from fishing gillnets to long-lines for tuna yellowfin in the Mancora pilot area | 0 |  |  |  | OUTPUT 1.1.1. Adoption of sustainable fishing methods to tackle non-selective fishing gear based on EAF principles directed to target species vulnerable to climate change | 1.1.1.1. Implementation of a conversion pilot from fishing gillnets to long-lines for tuna yellowfin in the Mancora pilot area | 126.01
|  | 1.1.1.2. Following-up of anchovy fishing gears adoption in the Huacho pilot area | [5 empty] | 1.1.1.2. Following-up of anchovy fishing gears adoption in the Huacho pilot area | 1008.04
|  | 1.1.1.3. Research of the adoption of anchovy fishing gears adoption in the Huacho pilot area | [5 empty] | 1.1.1.3. Research of the adoption of anchovy fishing gears adoption in the Huacho pilot area | 271.96
| OUTPUT 1.1.2. Restoration and co-management of natural banks | 1.1.2.1 Restoration of Peruvian scallops natural banks in the Huacho pilot area | 1253.57 |  |  |  | OUTPUT 1.1.2. Restoration and co-management of natural banks | 1.1.2.1. Restoration of Peruvian scallops natural banks in the Huacho pilot area | 75737.16
| OUTPUT 1.2.1 Planning and development of sustainable aquaculture through smallscale concessions | 1.2.1.1. Farming of Peruvian scallops in Huacho and oysters in Mancora | 15619.6 |  |  |  |  | 1.1.2.2.Co-management of Peruvian scallops natural banks in the Huacho pilot area | 8572.02
| OUTPUT 1.2.5. Production of bio-fertilizers from fishery and aquaculture residues | 1.2.5.1 Feasibility study of bioproducts | 2483.63 |  |  |  |  | 1.1.2.3. Fishery Ecological Risk Assessment, focusing on artisanal fisheries in Mancora and Huacho | 823.4
| OUTPUT 2.1.1. Development of a climatic and an oceanographic surveillance system. | 2.1.1.1. Gliders acquisition | 32954.08 |  |  |  | OUTPUT 1.2.1. Planning and development of sustainable aquaculture through smallscale concessions | 1.2.1.1. Farming of Peruvian scallops in Huacho and oysters in Mancora | 2750
| OUTPUT 2.1.2. Establishment of marine environment surveillance programs in pilot areas in coordination with local stakeholders | 2.1.2.1. Mancora pilot area monitoring (bentos research) | 752.3 |  |  |  |  | 1.2.1.2. Farming of oyster in Mancora | 5330.1
|  | 2.1.2.2. Huacho pilot area monitoring (line-base study) | 19868.68 |  |  |  |  | 1.2.1.4.Aquaponic farming in the Huacho pilot area | 7537.96
|  | 2.1.2.3. Mancora pilot area monitoring (line-base study) | 18170.85 |  |  |  | OUTPUT 1.2.2. Creation of ecotourism companies | 1.2.2.2.Formulation of the local tourism development plan for Mancora and Huacho | 4000
|  | 2.1.2.4. Mancora and Huacho pilot areas monitoring (equipment) | 0 |  |  |  | OUTPUT 1.2.3. Improving marketing capacities for sustainable artisanal fisheries | 1.2.3.1. Capacity building in production fishery derivatives for direct human consumption | 17753.93
| OUTPUT 2.1.3. Development of a modeling and prediction system at local scales. | 2.1.3.1.Research visits and Climate Change Modeling | 3241.6 |  |  |  |  | 1.2.3.2 Mejorar gestión efectiva de las actividades implementadas por el proyecto | 1206.24
| OUTPUT 3.1.1. Development and implementation of a Knowledge Management Strategy (KMS) | 3.1.1.1. Design and implementation of a knowledge management strategy and lessons learned | 307.07 |  |  |  | OUTPUT 1.2.5. Production of bio-fertilizers from fishery and aquaculture residues | 1.2.5.1. Estudio para la evaluación de los insumos para bioproductos | 21625.55
| OUTPUT 3.2.1. Training and sensitizing of beneficiaries on key topics such as formalization, entrepreneurship, normative and fishing gear | 3.2.1.1. Training workshops for fishermen | 0 |  |  |  |  | 1.2.5.2. Implementation of an artisanal pilot plant, inception of activities and quality assessment of the final products in the pilot areas | 1000
| OUTPUT 3.2.2. Design and implementation of early warning systems through a participatory process at local and regional scales | 3.2.2.1. Design of Early Warning Systems for Mancora and Huacho | 0 |  |  |  | OUTPUT 2.1.1. Development of a climatic and an oceanographic surveillance system. | 2.1.1.1. Gliders acquisition | 361163
| OUTPUT 4.1.1. Support of the cross-sector working group for the promotion of common actions addressing coastal ecosystems’ resilience to climate change impacts. | 4.1.1.1.Intersectoral plan formulation | 0 |  |  |  |  | 2.1.1.2. Gliders training and deployment in the pilot areas | 0
| OUTPUT 4.1.2. Development of regulations and proposals for co-management in coastal marine areas | 4.1.2.1. Socioeconomic and legal analysis oriented to regulations and legal proposals on climate change adaptation | 0 |  |  |  |  | 2.1.1.3. System and oceanographic data quality control implemented and automated according to IODE standards | 6984.62
| OUTPUT 4.1.3. Development of regulation to implement incentives for the participation of artisanal fishermen, adopting sustainable practices, in the National Direct Human Consumption Program. | 4.1.3.1.Formulation of a technical document to support the promotion of hydrobiological resources for direct human consumption. | 307.07 |  |  |  | OUTPUT 2.1.2. Establishment of marine environment surveillance programs in pilot areas in coordination with local stakeholders | 2.1.2.1. Mancora pilot area monitoring (bentos research) | 0
| Project Execution Cost (PEC) | Project Coordinator | 50960.72 |  |  |  |  | 2.1.2.2. Huacho pilot area monitoring (line-base study) | 8500
|  | Local Coordinator | 14524.57 |  |  |  |  | 2.1.2.3. Mancora pilot area monitoring (line-base study) | 12000
|  | Administrative assistant | 908.49 |  |  |  |  | 2.1.2.4. Mancora and Huacho pilot areas monitoring (equipment) | 123674.69
|  | Procurement specialist | 8933.73 |  |  |  |  | 2.1.2.5. Installation and recovery of sensors for monitoring pilot areas | 249.56
|  | Design of the monitoring and evaluation system | 154.35 |  |  |  |  | 2.1.2.6. Design and initial experiences of participatory environmental monitoring in the pilot areas | 0
|  | Inception workshop | 9298.68 |  |  |  | OUTPUT 2.1.3. Development of a modeling and prediction system at local scales. | 2.1.3.1.Research visits and Climate Change Modeling | 21824.63
| TOTAL PROJECT COST (TPC) |  | 94958.45 |  |  |  | OUTPUT 2.1.4. Capacity building in the monitoring and development of new science-based tools such as Ecological Risk Assessments (ERA) for climate change targeting IMARPE, decision makers and academia | 2.1.4.1. Research and training on new science-based tools such as Ecological Risk Assessment (ERA) for climate change | 25660
| PROJECT EXECUTION COST (PEC) |  | 84780.54 |  |  |  |  | 2.1.4.2. Vulnerability and ecological risk assessment (ERA) workshops associated with climate change in pilot areas | 4707.94
| TOTAL (TPC + PEC) |  | 179738.99 |  |  |  |  | 2.1.4.3.Research in oceanographic modeling, vulnerability, ecological risk and, benthos | 17520
[7 empty] | OUTPUT 3.1.1. Development and implementation of a Knowledge Management Strategy (KMS) | 3.1.1.1. Design and implementation of a knowledge management strategy and lessons learned | 10790.65
PLANNED EXPENDITURE SCHEDULE | [7 empty] | 3.1.1.2. Formulation of a sectoral strategy proposal for fishing and aquaculture issues face to climate change aligned with the Nationally Determined Contributions (NDC) | 533.65
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION |  | PROJECTED COST | Est. Completion Date |  |  | OUTPUT 3.2.1. Training and sensitizing of beneficiaries on key topics such as formalization, entrepreneurship, normative and fishing gear | 3.2.1.1. Training workshops for fishermen | 0
| Project Output | Activity programmed in the Annual Operation Plan (AOP) 2019/2020 |  |  |  |  | OUTPUT 3.2.2. Design and implementation of early warning systems through a participatory process at local and regional scales | 3.2.2.1. Design of Early Warning Systems for Mancora and Huacho | 0
| OUTPUT 1.1.1. Adoption of sustainable fishing methods to tackle non-selective fishing gear based on EAF principles directed to target species vulnerable to climate change | 1.1.1.1. Implementation of a conversion pilot from fishing gillnets to pole and line and/or long-lines for tuna yellowfin in the Mancora pilot area | 78100 | December 2020 |  |  | OUTPUT 4.1.1. Support of the cross-sector working group for the promotion of common actions addressing coastal ecosystems’ resilience to climate change impacts. | 4.1.1.1.Intersectoral plan formulation | 0
|  | 1.1.1.2. Following-up of anchovy fishing gears adoption in the Huacho pilot area | 98800 | January 2020 |  |  |  | 4.1.1.2. Working Group conformed by PRODUCE and MINAM to develop marine spatial planning and Environmental Territorial Planning pilot, in Huacho | 0
|  | 1.1.1.3. Adoption of selective gillnets fishing gears to target coastal resources in the Huacho pilot area | 46000 | March 2020 |  |  | OUTPUT 4.1.2. Development of regulations and proposals for co-management in coastal marine areas | 4.1.2.1. Socioeconomic and legal analysis oriented to regulations and legal proposals on climate change adaptation | 0
| OUTPUT 1.1.2. Restoration and co-management of natural banks | 1.1.2.1. Re-stock of Peruvian scallops natural banks in the Huacho pilot area | 88800 | May 2020 |  |  | OUTPUT 4.1.3. Development of regulation to implement incentives for the participation of artisanal fishermen, adopting sustainable practices, in the National Direct Human Consumption Program. | 4.1.3.1.Formulation of a technical document to support the promotion of hydrobiological resources for direct human consumption. | 0
|  | 1.1.2.2.Co-management of Peruvian scallops natural banks in the Huacho pilot area | 62400 | May 2020 |  |  | Project Execution Cost (PEC) | Project Coordinator | 55103.8
|  | 1.1.2.3. Fishery Ecological Risk Assessment, focusing on artisanal fisheries in Mancora and Huacho | 105780 | February 2020 |  |  |  | Local Coordinator | 23715.4
| OUTPUT 1.2.1 Planning and development of sustainable aquaculture through smallscale concessions | 1.2.1.1. Farming of Peruvian scallops in Huacho | 130650 | May 2020 |  |  |  | Administrative assistant | 13073.53
|  | 1.2.1.2. Farming of oyster in Mancora | 81900 | May 2020 |  |  |  | Procurement specialist | 19089.15
|  | 1.2.1.4.Aquaponic farming in the Huacho pilot area | 104600 | May 2020 |  |  |  | Diseño del sistema de monitoreo y evaluación y elaboración de la línea base | 1069.35
| OUTPUT 1.2.2. Creation of ecotourism enterprises | 1.2.2.2.Formulation of the local tourism development plan for Mancora and Huacho | 30000 | October 2019 |  |  |  | Monitoreo de salvaguardas sociales y ambientales | 7437.47
| OUTPUT 1.2.3 Improvement of market power capacities for sustainable artisanal fisheries | 1.2.3.1. Capacity building in production fishery derivatives for direct human consumption | 166900 | May 2020 |  |  | TOTAL PROJECT COST (TPC) |  | 741351.11
| OUTPUT 1.2.5. Production of bio-fertilizers from fishery and aquaculture residues | 1.2.5.2. Implementation of an artisanal pilot plant, inception of activities and quality assessment of the final products in the pilot areas | 6000 | May 2020 |  |  | PROJECT EXECUTION COST (PEC) |  | 119488.7
| OUTPUT 2.1.1. Development of a climatic and an oceanographic surveillance system. | 2.1.1.1. Gliders acquisition | 960000 | December 2019 |  |  | TOTAL (TPC + PEC) |  | 860839.81
|  | 2.1.1.2. Gliders training and deployment in the pilot areas | 140000 | April 2020
|  | 2.1.1.3. System and oceanographic data quality control implemented and automated according to IODE standards | 26000 | May 2020 | PLANNED EXPENDITURE SCHEDULE
| OUTPUT 2.1.2. Establishment of marine environment surveillance programs in pilot areas in coordination with local stakeholders | 2.1.2.2.Base-line in the Huacho pilot area | 5000 | May 2020 | List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION |  | PROJECTED COST | Est. Completion Date
|  | 2.1.2.5. Installation and recovery of sensors for monitoring pilot areas | 36000 | May 2020 |  |  | Project Output | Activity programmed in the Annual Operation Plan (AOP) 2020
|  | 2.1.2.6. Design and initial experiences of participatory environmental monitoring in the pilot areas | 42600 | May 2020 |  |  | OUTPUT 1.1.1. Adoption of sustainable fishing methods to tackle non-selective fishing gear based on EAF principles directed to target species vulnerable to climate change | 1.1.1.1. Implementation of a conversion pilot from fishing gillnets to pole and line and/or long-lines for tuna yellowfin in the Mancora pilot area | 71627.98 | October 2020
| OUTPUT 2.1.3. Development of a modeling and prediction system at local scales. | 2.1.3.1. Research visits and climate change modeling | 135650 | May 2020 |  |  |  | 1.1.1.2. Following-up of anchovy fishing gears adoption in the Huacho pilot area | 82800 | November 2020
| OUTPUT 2.1.4. Building capacity on monitoring and development of new science based tools such as Ecological Risk Assessments (ERA) for climate change directed to IMARPE, decision makers and academia. | 2.1.4.1. Research and training on new science-based tools such as Ecological Risk Assessment (ERA) for climate change | 80000 | January 2020 |  |  |  | 1.1.1.3. Adoption of selective gillnets fishing gears to target coastal resources in the Huacho pilot area | 73737 | December 2020
|  | 2.1.4.2. Vulnerability and ecological risk assessment (ERA) workshops associated with climate change in pilot areas | 9530 | May 2020 |  |  | OUTPUT 1.1.2. Restoration and co-management of natural banks | 1.1.2.1. Re-stock of Peruvian scallops natural banks in the Huacho pilot area | 62502 | December 2020
|  | 2.1.4.3.Research in oceanographic modeling, vulnerability, ecological risk and, benthos | 38400 | May 2020 |  |  |  | 1.1.2.2.Co-management of Peruvian scallops natural banks in the Huacho pilot area | 28757.02 | November 2020
| OUTPUT 3.1.1. Development and implementation of a Knowledge Management Strategy (KMS) | 3.1.1.1. Design and implementation of a knowledge management strategy and lessons learned | 17600 | October 2019 |  |  |  | 1.1.2.3. Fishery Ecological Risk Assessment, focusing on artisanal fisheries in Mancora and Huacho | 63716 | July 2020
|  | 3.1.1.2. Formulation of a sectoral strategy proposal for fishing and aquaculture issues face to climate change aligned with the Nationally Determined Contributions (NDC) | 26500 | May 2020 |  |  | OUTPUT 1.2.1 Planning and development of sustainable aquaculture through smallscale concessions | 1.2.1.1. Farming of Peruvian scallops in Huacho | 21185 | May 2020
| OUTPUT 3.2.2. Design and implementation of early warning systems through a participatory process at local and regional scales | 3.2.2.1. Design of Early Warning Systems for Mancora and Huacho | 32400 | May 2020 |  |  |  | 1.2.1.2. Farming of oyster in Mancora | 135961.02 | December 2020
| OUTPUT 4.1.1. Support of the cross-sector working group for the promotion of common actions addressing coastal ecosystems’ resilience to climate change impacts. | 4.1.1.1.Intersectoral plan formulation | 26250 | May 2020 |  |  |  | 1.2.1.4.Aquaponic farming in the Huacho pilot area | 90427 | December 2020
|  | 4.1.1.2. Working Group conformed by PRODUCE and MINAM to develop marine spatial planning and Environmental Territorial Planning pilot, in Huacho | 5000 | May 2020 |  |  | OUTPUT 1.2.2. Creation of ecotourism enterprises | 1.2.2.2.Formulation of the local tourism development plan for Mancora and Huacho | 18000 | July 2020
| OUTPUT 4.1.3. Development of regulation to implement incentives for the participation of artisanal fishermen, adopting sustainable practices, in the National Direct Human Consumption Program. | Tarea 4.1.3.1. Formulation of a guide to carry out an assessment on the adoption of sustainable practices related to artisanal fishery products for Direct Human Consumption. | 35200 | May 2020 |  |  |  | 1.2.2.3. Implementación de circuito gastronómico en Máncora y Huacho | 26000 | November 2020
| Project Execution Cost (PEC) | Project Coordinator | 57131.74 | May 2020 |  |  |  | 1.2.2.4. Desarrollo de productos artesanales con insumos marinos | 74128.5 | November 2020
|  | Local Coordinator | 24310.56 | May 2020 |  |  |  | 1.2.2.5. Desarrollo de pesca vivencial | 93143 | October 2020
|  | Administrative assistant | 16354.66 | May 2020 |  |  | OUTPUT 1.2.3 Improvement of market power capacities for sustainable artisanal fisheries | 1.2.3.1. Capacity building in production fishery derivatives for direct human consumption | 101472 | October 2020
|  | Procurement specialist | 16811.18 | May 2020 |  |  |  | 1.2.3.2 Mejorar gestión efectiva de las actividades implementadas por el proyecto | 44032 | December 2020
|  | Safeguards and gender monitoring | 32499 | May 2020 |  |  | OUTPUT 1.2.4 Inicio de procesos de certificación para pesquerías | 1.2.4.1. Implementación de un sistema de trazabilidad para pescadores artesanales de las áreas piloto de proyecto | 11887 | September 2020
| TOTAL PROJECT COST (TPC) |  | 2616060 |  |  |  | OUTPUT 1.2.5. Production of bio-fertilizers from fishery and aquaculture residues | 1.2.5.1. Estudio para la evaluación de los insumos para bioproductos | 5965 | January 2020
| PROJECT EXECUTION COST (PEC) |  | 147107.14 |  |  |  |  | 1.2.5.2. Implementation of an artisanal pilot plant, inception of activities and quality assessment of the final products in the pilot areas | 135227 | October 2020
| TOTAL (TPC+PEC) |  | 2763167.14 |  |  |  | OUTPUT 2.1.1. Development of a climatic and an oceanographic surveillance system. | 2.1.1.1. Gliders acquisition | 951093 | March 2020
[8 empty] | 2.1.1.2. Gliders training and deployment in the pilot areas | 115500 | February 2020
[8 empty] | 2.1.1.3. System and oceanographic data quality control implemented and automated according to IODE standards | 5919.72 | June 2020
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) | The project doesn't have co-financing | [5 empty] | OUTPUT 2.1.2. Establishment of marine environment surveillance programs in pilot areas in coordination with local stakeholders | 2.1.2.2.Base-line in the Huacho pilot area | 11000 | May 2020
How much of the total co-financing as committed in the Project Document has actually been realized? | [7 empty] | 2.1.2.3. Linea base en la zona de Mancora | 3500 | January 2020
[8 empty] | 2.1.2.4. Monitoreo de la zona de Huacho y Mancora | 64960 | February 2020
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | [7 empty] | 2.1.2.5. Installation and recovery of sensors for monitoring pilot areas | 39000 | July 2020
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | [7 empty] | 2.1.2.6. Design and initial experiences of participatory environmental monitoring in the pilot areas | 25250 | September 2020
[7 empty] | OUTPUT 2.1.3. Development of a modeling and prediction system at local scales. | 2.1.3.1. Research visits and climate change modeling | 119323.98 | November 2020
[7 empty] | OUTPUT 2.1.4. Building capacity on monitoring and development of new science based tools such as Ecological Risk Assessments (ERA) for climate change directed to IMARPE, decision makers and academia. | 2.1.4.1. Research and training on new science-based tools such as Ecological Risk Assessment (ERA) for climate change | 117435.78 | August 2020
[8 empty] | 2.1.4.2. Vulnerability and ecological risk assessment (ERA) workshops associated with climate change in pilot areas | 0
[8 empty] | 2.1.4.3.Research in oceanographic modeling, vulnerability, ecological risk and, benthos | 29414 | October 2020
[7 empty] | OUTPUT 3.1.1. Development and implementation of a Knowledge Management Strategy (KMS) | 3.1.1.1. Design and implementation of a knowledge management strategy and lessons learned | 33487 | November 2020
[8 empty] | 3.1.1.2. Formulation of a sectoral strategy proposal for fishing and aquaculture issues face to climate change aligned with the Nationally Determined Contributions (NDC) | 19750 | December 2020
[8 empty] | 3.1.1.3. Implementación y Seguimiento de la EGC | 33500 | December 2020
[8 empty] | 3.1.1.4. Implementación y seguimiento de la Estrategia Sectorial en áreas piloto | 2000 | January 2020
[8 empty] | 3.1.1.5. Desarrollo de medios de difusión / comunicación | 9500 | May 2020
[7 empty] | OUTPUT 3.2.1. Training and sensitizing of beneficiaries on key topics such as formalization, entrepreneurship, normative and fishing gear | 3.2.1.1. Capacitación a pescadores artesanales | 6000 | June 2020
[8 empty] | 3.2.1.2. Capacitación a instituciones | 27000 | December 2020
[8 empty] | 3.2.1.3. Desarrollo de los espacios de debate para el intercambio de experiencias existosas | 3295 | November 2020
[8 empty] | 3.2.1.4. Taller para identificar el rol de la mujer en las actividades pesqueras acuícolas | 2000 | May 2020
[7 empty] | OUTPUT 3.2.2. Design and implementation of early warning systems through a participatory process at local and regional scales | 3.2.2.1. Design of Early Warning Systems for Mancora and Huacho | 38500 | November 2020
[7 empty] | OUTPUT 4.1.1. Support of the cross-sector working group for the promotion of common actions addressing coastal ecosystems’ resilience to climate change impacts. | 4.1.1.1.Intersectoral plan formulation | 16650 | May 2020
[8 empty] | 4.1.1.2. Working Group conformed by PRODUCE and MINAM to develop marine spatial planning and Environmental Territorial Planning pilot, in Huacho | 0
[7 empty] | OUTPUT 4.1.3. Development of regulation to implement incentives for the participation of artisanal fishermen, adopting sustainable practices, in the National Direct Human Consumption Program. | Tarea 4.1.3.1. Formulation of a guide to carry out an assessment on the adoption of sustainable practices related to artisanal fishery products for Direct Human Consumption. | 40845 | June 2020
[7 empty] | Project Execution Cost (PEC) | Project Coordinator | 57131.74
[5 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  | Local Coordinator | 24310.56
[8 empty] | Administrative assistant | 16354.66
[8 empty] | Procurement specialist | 16811.18
[8 empty] | Safeguards and gender monitoring | 43789
[7 empty] | TOTAL PROJECT COST (TPC) |  | 2855491
[7 empty] | PROJECT EXECUTION COST (PEC) |  | 158397.14
[7 empty] | TOTAL (TPC+PEC) |  | 3013888.14
[5 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  | The project doesn't have co-financing
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
[6 empty] | NOTE | In December 2019, the Annual Operating Budget 2020 was approved (January - December).
[8 empty] | January 2020 | January
[8 empty] | February 2020 | February | 2020
[8 empty] | March 2020 | March | 2020
[8 empty] | April 2020 | April | 2020
[8 empty] | May 2020 | May | 2020
[8 empty] | June 2020 | June | 2020
[8 empty] | July 2020 | July | 2020
[8 empty] | August 2020 | August | 2020
[8 empty] | September 2020 | September | 2020
[8 empty] | October 2020 | October | 2020
[8 empty] | November 2020 | November | 2020
[8 empty] | December 2020 | December | 2020
2020

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Regulatory
Climate change adaptation has not been incorporated in the policies, strategies, and plans of the Ministry of Production (PRODUCE) nor local governments. | PRODUCE through its General Directorate of Environmental Fisheries and Aquaculture Affairs (DGAAMPA) is establishing measures to implement the sectoral NDCs identified and approved to date. | A consultancy has been convened to formulate a proposal for the sectoral and sub-national articulation plan of the adaptation measures of the project, aligned with the nationally determined contributions (NDC) in the planning documents, budget and budgetary programs of the Fishing Sub-sector and aquaculture. Coordination with projects that have similar objectives, have been developed and coincidences have been identified. It would allow the intervention to be given sustainability.
Insufficient regulation proposing environmental friendly fishing practices and the sustainable use of ecosystems. | There is fishing regulation with recommendations and measures related to the use of friendly fishing gear and sustainable use of resources. However, it is not explicitly regulated and its monitoring is still limited. Therefore, the risk remains. | A conservation agreement has been signed between SERNANP and an association of fishermen in Huacho, which contemplates the sustainable use and management of the resource on Don Martin Island, with the support of the project.
Weak enforcement and lack of compliance with regulation; various gray areas in the interaction between artisanal and industrial fishing. | Considering that the factors determining this risk are of a legal, social, economic and cultural nature, there is still no evidence of articulation of efforts in an integral manner, therefore the risk remains. | In the third component of the project a knowdlege management system has been designed in order to systematize all kind of knowledge generated in the areas of intervention. It is urgent to move forward to the next implementation stage, specially because of the context of the COVID-19. The design of the grouped activities has considered a Governance package, which includes activities from the component 1, 3 and 4 , which will contribute to mitigate this risk.
Financial
There may be insufficient financial resources for the sustainability of the project activities once the grant financing the project is spent. | Considering that the activities related to the adaptation measures planned under component 1, have not yet begun, this risk remains. | Coordinations were made with other similar projects in the scope of intervention, in order to identify sustainability mechanisms for the activities. A consultancy for the identification of competitive funds for one of the activities related to fishing gear in Component 1 is under development. Likewise, there is the hiring of field coordinators in each pilot area, whose main function is to coordinate actions with the beneficiaries, local actors and consultants, in order to improve the technical execution of the project.
Political
Artisanal fishing has not been included into national development policies; the focus of the sector has been directed to industrial fishing and exports | In 2018, PRODUCE promulgated the Legislative Decree No. 1392, which establishes the formalization system of the artisanal fishing activity (SIFORPA). It has also initiated the formulation of a national training program for artisanal fishermen. | The initial work of the field articulators was aimed at supporting the formalization of the fishermen in the pilot areas. In the Huacho area there are 128 files for the formalization of fishing permits, while in Mancora the formalization is still pending with 7 fishermen's organizations in the four localities of intervention.
Operational
Few or lack of coordination instances for the key stakeholders involved does not ensure the adequate prioritization of project activities. | The regulations are still insufficient, however, the project will contribute with interventions that allow improving the participation of users in decision making. | The project will support the development of the bases that allow the emission of norms and / or regulations aimed at improving the participation of the actors stakeholders (Component 4)
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The COVID 19 pandemic and its impacts on coastal communities in the pilot areas of the project represent a risk for the fulfillment of project activities and objectives. | Although the quarantine has ended and economic activities, especially artisanal fishing, are gradually reactivating, the impacts on the economic health and income of the direct beneficiaries of the project are significant and it is expected that they will continue for a longer time. | In this context, the reprogramming of the AOP 2020 has been chosen in order to realize a reduction of the planned ammounts for travel and workshops. In addition,the following is proposed: 1.- Accelerate all activities that were paralyzed or delayed as a result of the pandemic. 2.- Accelerate the calls and contracts of the thematic packages in a way that allows improving the technical execution of the project. 3.- Develop the activities within the norms for pandemic control at the national level, following established protocols and the use of adequate equipment by both project staff and beneficiaries. 4.- Evaluate the possibility of a temporary extension for the implementation of project activities.
To implement some of the activities of component 1, it is necessary to previously obtain permits or authorizations from the competent sectors. This is the case of the activities related to the adoption of sustainable fishing gear and the promotion of sustainable aquaculture. The terms in which these authorizations would obtain could mean a delay in the start-up of these activities, as well as in the development of other activities that depend on these, such as the one related to commercialization (output 1.2.3). | As part of the processes for obtaining permits from aquaculture concessions, it is necessary for the associations to have all the documentation related to fishing permits and the renewal of boards of directors, many of the associations do not have this documentation. | They are being supported in the individual training of fishermen, as well as the renewal of boards of directors, to be able to require permits for aquaculture concessions. They will also be supported in the constitution of MYPES so that they can establish more beneficial marketing agreements.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
In relation to the risk that the social and economic impacts of the pandemic represents, the implementation of the project should be seen as a clear opportunity to contribute to the recovery of these coastal communities, and establish the necessary adjustments in the project in order to make it easier to overcome the current crisis with increasing resilience and the possibility of any other in the future.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity |  |  | Resistance from specific artisanal fisheries or groups within those areas to the proposed measures | Realizacion de mas talleres y reuniones de coordinacion con las asociaciones de pescadores, asi como se incluyo el apoyo tecnico en la zona. | Numero de talleres y reuniones con asociaciones de pescadores. | 0 | En el marco del desarrollo de la implementacion de las medidas de adaptacion, se han realizado talleres tanto de diagnostico (EGC,bioproductos,comercializacion) validacion de propuestas (bioproductos) y coordinaciones para inicio de implementacion en las areas pilotos.
|  |  | Conflicting interests among stakeholders regarding the rights and access to the use of natural resources. | implementar condiciones habilitantes para implementacion de acuerdo de co-manejo | Numero de asociaciones que firman acuerdo de conservacion con SERNANP Numero de asociaciones formalizadas. | 0 | Hasta la fecha, se logró firmar el acuerdo de conservacion entre una asociacion de pescadores y SERNANP, lo que es el primer paso para el establecimiento de los acuerdos de co-manejo en el AP Huacho. Asi tambien se les apoyo en la formalizacion para la firma de este acuerdo de conservacion.
|  |  | Interinstitutional or internal conflicts between the entity that administrates the artisanal fishing dock and the sectorial authority, due to the lack of definition in the responsibilities for the experiential tuna fishing activity | Implementar mesas de diaologo y coordinacion para el establecimiento de responsabilidades para la pesca experimental del atun. | Tipo de entidades participantes en los talleres | 0 | Se inicio la consultoria EREAF, la cual contempla talleres y reuniones con intercambio de opiniones entre actores de diferentes entidades, lo cual ayudara a establecer posibles medidas para la pesca experimental del Atun .
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights |  |  | Children working on adaptation activities proposed in the pilot sites | No mitigation measure had to be implemented in the reporting period | Number of cases of children working in productive activities | 0
7 – Indigenous peoples
8 – Involuntary resettlement |  |  | Reduction of artisanal fishermen family income due to adoption of new fishing gears | No mitigation measure had to be implemented in the reporting period | a) Family income per month b) Number of commercialization agreements suscribed with fishermen | a) To be determined b) 0
9 – Protection of natural habitats
10 – Conservation of biological diversity |  |  | Mortality of marine vertebrates (mainly birds and sea turtles) by incidental capture in fishing gears. | No mitigation measure had to be implemented in the reporting period | a) Number of trained fishermen in rehabilitation and release techniques b) Number of individuals released alive | 0
|  |  | Change in the benthic species composition due to aquaculture infrastructure installation (bottom pens). | No mitigation measure had to be implemented in the reporting period | Number of environmental monitoring in the area | 0
|  |  | Marine vertebrates’ displacement or habitat abandonment (mammals, birds and turtles) due to vessels’ sound and human presence where sightings are held. | No mitigation measure had to be implemented in the reporting period | Number of environmental monitoring in the area | 0
|  |  | Incidental capture of juvenile tuna fishes or use of juvenile anchovies as baits due to tuna fishing pilots with pole and line and hand-line (experiential fishing) | No mitigation measure had to be implemented in the reporting period | Number of live bait production modules in the pilot area | 0
11 – Climate change
12 – Pollution prevention and resource efficiency |  |  | Seawater pollution by solid and oily waste generation from aquaculture activities. | No mitigation measure had to be implemented in the reporting period. | a) Environmental Impact Statement approved b) Number of waste management reports | 0
|  |  | Seawater pollution by solid and oily waste generation from ecotourism activities (e.g. wildlife sightings and experiential tuna fishing). | No mitigation measure had to be implemented in the reporting period. | a) Number of women and men trained in solid and liquid waste management in tourism activities b) Number of waste management reports | 0
|  |  | Solid waste and effluents generation during the process of bio-fertilizer production | No mitigation measure had to be implemented in the reporting period. | a) Number of women and men trained in solid and liquid waste management for the production of bioproducts b) Number of waste management reports | 0
|  |  | Soil pollution due to leakage of effluents during the process of bio-fertilizer production | No mitigation measure had to be implemented in the reporting period. |  | 0
13 – Public health
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes, regarding current events(Pandemic), these are being included in the new social and environmental risk mitigation meassures.
Have unanticipated ESP risks been identified during the reporting period? |  | Yes, a new update of the social and environmental risks was made through a consultancy, to which the possible social and environmental risks related to the pandemic are being added.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | The principle of public health was activated, due to the pandemic since it has significantly affected the fishing communities of the PA, for which the project is providing support with personal protection equipment for the associations in order to reduce the spread of the virus .
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Work meetings have been held to review the products of the Social and Environmental Safeguards consultancies, sending contributions and suggestions.
Have the implementation arrangements been effective during the reporting period? |  | Yes, safeguards measures were included in the terms of reference of consultancies formulated during the reporting period.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Social and environmental safeguards consultancies began to be implemented, which will update the risks initially identified and validate the mitigation measures proposed with the target audience.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes, the support of the social safeguards specialist helped to have a more fluid coordination with the associations, as well as the presence of the field support.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Social safeguards services and recently the environmental safeguards service are being implemented, however the main limitation is the COVID19 restrictions in the pilot areas. Progress has been made in the planning work and there has been the collaboration of the user areas.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
A letter was received from the Chancay fishermen's association, requesting to participate in the project activities. |  | The fishermen's association of Chancay was considered part of the target audience
A letter is received from the Huacho fishermen's association requesting support in the disinfection of their boats. |  | Support was provided for the desinfection of their boats
A letter is received from the fishermen's association to request support to cover the counterpart to obtain a competitive fund |  | They cannot be offered the counterpart for not being considered in the AOP.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | No
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
COMPONENT 1: Implementation of interventions in pilot strategic areas to improve resilience of target coastal communities and key coastal marine ecosystems to climate change and variability-induced stress. | Objective | % of women adopting climate change adaptation measures | 0 | 80% | Poor. It has been proposed to the Secretariat the adjustment to this indicator (see project indicators sheet)
COMPONENT 3: Capacity building and knowledge management system for implementing the EBA and the EAF, and for the dissemination of project’s lessons learned, targeting government officials, academia, local communities and other stakeholders | Objective | % of women with improved capacity | 0 | 80% | Poor. In 2018 a scientific workshop for IMARPE was carried out. From a total of 31 participants, only 6 were women.
OUTPUT 1.2.2. Creation of ecotourism enterprises | Output | # of women association that incorporates ecotourism as a complementary economic activity | 0 | 1 | Poor. Field activities hasn´t started yet.
OUTPUT 1.2.3 Improvement of market power capacities for sustainable artisanal fisheries | Output | # of trade agreements managed in partnership with a women association | 0 | 1 | Poor. Field activities hasn´t started yet.
OUTPUT 1.2.5. Production of biofertilizers from fishery and aquaculture residues | Output | # of women associations producing biofertilizers | 0 | 2 | Poor. This activity is in its initial phase (formulation of feasibility study).
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | Work meetings have been held to review the products of the Social and Environmental Safeguards consultancies, sending contributions and suggestions.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes. Gender approach has been included in the terms of reference.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | A professional specialized on gender and climate change from PRODUCE's General Direction of Environmental, Fishery and Aquaculture Affairs (DGAAMPA), is participating in project implementation, specifically in activities of component 3.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | Yes. Gender approach has been included in the terms of reference.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Social safeguards services and recently the environmental safeguards service are being implemented, however the main limitation is the COVID19 restrictions in the pilot areas. Progress has been made in the planning work and there has been the collaboration of the user areas or EE.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
The grievance mechanism specific for the project is being designed and will be disseminated among project beneficiaries during the third reporting period.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Project component 1 |  |  | S |  | MS: The progress reflected in its indicators is not the expected, but Profonanpe provided support to establish thematic packages in order to improve the excecution. | MS
| Project component 2 |  |  | S |  | S: The progress reflected in its indicators is the expected, considering the project is almost in the mid-term | S
| Project component 3 |  | Outcome 3 | S |  | MS: The progress reflected in its indicators is not the expected, but Profonanpe provided support to establish thematic packages in order to improve the execution | MS
| Project component 4 |  | Outcome 7 | S |  | HU: No action was taken in the reporting period, it only was the support to stablish the thematic package for the improvement of the governance | HU
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Pamela Reyes Neyra y Omar Corilloclla
| Email: | preyes@profonanpe.org.pe / ocorilloclla@profonanpe.org.pe
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Profonanpe provided support for updating indicators and goals of the results framework of the project, which was submitted to the Adaptation Fund for approval. In order to improve the project execution and to ease procurement processes, Profonanpe also provided support in the development of seven clustering of activities or thematic packages for the main project services.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 2.1 |  | Outcome 1 | S |  | MS: The progress reflected in its indicators is the expected (45%), considering the project is almost in the mid-term, but with still with modest overall relevance. | MS
| Outcome 3.2 |  | Outcome 1 | S |  | U: There is not progress showed in its indicators | U
| Outcome 2.1 |  | Outcome 2 | S |  | S: The progress reflected in its indicators is the expected (45%), also considering the project is almost in the mid-term and that the project is having significant contribution to strengten institutional capacities related to AF outcome 2. | S
| Component 3 |  | Outcome 3 | S |  | MU: The progress showed in its indicators is below the one expected for the period. The progress considered is related to the knowledge management system that is being designed. | MU
| Outcome 1.1 |  | Outcome 5 | S |  | MU: The progress showed in its indicators is below the one expected for the period. | MU
| Outcome 1.2 |  | Outcome 6 | S |  | MU:The progress showed in its indicators is below the one expected for the period. | MU
| Component 4 |  | Outcome 7 | S |  | HU: No action was taken in the reporting period | HU
[6 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Pamela Reyes Neyra y Omar Corilloclla
| Email: | preyes@profonanpe.org.pe / ocorilloclla@profonanpe.org.pe
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
It has to be considered that the project had a slow start since the design to the inception date (May2018), in addition to that, the first project coordinator resigned from his position (November 2018) and it caused a delay in project activities.The new project coordinator was hired (February 2019) and he had the initial task to complete the Project Implementation Plan (PIP), which was completed jointly with PRODUCE and IMARPE proffesionals.In relation to this,it was developed the clustering or regrouping of activities of the projects, by topics and its terms of reference. It is an strategy that seeks to improve the execution of activities for the project remaining time, because it is expected to improve the procurement of the main equipment and services. Also, for the 2020, it was approved an Annual Operational Plan with January-December period, in order to improve the project tracking.Regarding Environmental and social safeguard, 2 consultancies began to be implemented, so the risks and mitigation measures initially identified will be updated for the next period, also the grievance mechanism is in development. In the scope of component 2, IMARPE requested the acquisition of the gliders and this process took place in the reporting period. This high-tech equipment will upgrade the research capacities of IMARPE.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies
Note on F8: Pamela Patricia Reyes Neyra: Outcomes 5 and 6
Note on F9: Pamela Patricia Reyes Neyra: Outcomes 1 and 2
Note on D29: Pamela Patricia Reyes Neyra: Indicator output 1.1.2

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator adjusted | Baseline | Progress since inception | Target for Project End
Objective/Component 1 | # of persons in PA linked to the artisanal fisheries adopting climate change adaptation measures that improve their livelihoods and the resilience of the ecosystem | 0 | 20% | 700
| % of women of the individuals linked to the artisanal fishing activity adopting adaptation measures to climate change | 0 | 17.19% | 20%
Outcome 1.1. / Output 1.1.1 | # of vessels in PAs adopting selective fishing gear | 0% | 0% | At least 30 vessels
Outcome 1.1. / Output 1.1.2 | # of natural banks re-stocked | 0 | 20% | 1 natural bank of Peruvian scallop in Don Martin Island
| # of natural banks co-managed | 0 | 12.5% | 1 natural bank of Peruvian scallop under co-management principles
Outcome 1.2. / Output 1.2.1 | # of artisanal fishermen associations and women linked to the artisanal fishing activity, developing sustainable aquaculture reporting profits | 0 | 25% | At least two associations of fishermen and one of women linked to fishing activity develop sustainable aquaculture activities that report profits.
0
| # of projects with business plans | 0 | 0% | 3 business plan
Outcome 1.2./ Output 1.2.2 | # of fishers associations participating in sustainable tourism ventures reporting complementary income | 1 | 0% | At least 2 fishers associations
| # of women association that incorporates sustainable tourism as a complementary economic activity | 0 | 25% | At least 1 women association
Outcome 1.2./ Output 1.2.3 | % of fishers reporting increased income per fishing ton sold. (from a total of 300 fishers in Máncora). | 0 | 25% | 20% of artisanal fishers increase their revenue per ton sold
| # of trade agreements between SOAFs and middlemen / final consumer (i.e. restaurant, supermarket | 0 | 0% | At least one trade agreement
| # of trade agreements managed in partnership with a women association | 0 | 0% | At least one trade agreement
Outcome 1.2./ Output 1.2.4 | # of fishing units incorporated in a catches traceability system applying sustainable fishing gear | 0 | 0% | 33 fishing units
Outcome 1.2./ Output 1.2.5 | # of women's associations linked to artisanal fishing activity, generate biofertilizers from fishing and aquaculture residues | 0 | 20% | At least two women's associations
Objective /Component 2 | No. of modern systems for environment surveillance and prediction implemented | 0 | 45% | 1 modern system
Outcome 2.1 / Output 2.1.1. | # of marine autonomous gliders in operation | 1 | 80% | 3 Glider
| # of platforms for oceanographic data dissemination in almost real-time implemented | 0 | 33.33% | 1 plataform
| # of high-resolution oceanographic data management systems of the project implemented |  | 33.33% | 1 system
Outcome 2.1 / Output 2.1.2. | # of bio-oceanographic baseline evaluations for each AP | 0 | 75% | 1 bio-oceanographic baseline evaluation for each AP
| Quality environmental and red tides monitoring program with local stakeholders | 0 | 16.67% | 1 operational monitoring program of environmental quality (DO, pH, harmful algal blooms) at selected points and on a seasonal basis
| Ecosystem resilience monitoring program designed with other stakeholders and including fishermen as observers | 0 | 33.33% | 1 proposal developed for an ecosystem resilience monitoring program
Outcome 2.1 / Output 2.1.3. | # of oceanographic scenarios under optimistic and pessimistic IPCC greenhouse gas concentration trajectories (RCP 8.5 and RCP 3-PD) | 0 | 33.33% | 2 scenarios developed (optimistic and pessimistic)
| # of catch potential scenarios of key resources under IPCC greenhouse gas concentration trajectories RCP 8.5 and RCP 3-PD | 0 | 0% | 2 scenarios developed (optimistic and pessimistic)
Outcome 2.1 / Output 2.1.4. | # of trained scientists at IMARPE and academia and/or other centres |  | 60% | At least 15 trained scientists in IMARPE, and a similar number in academia and/or other centres.
| # of workshops and seminars for decision-makers |  | 50% | 4 workshops / seminars directed to decision-makers within the framework of the project
| # of undergraduate and graduate thesis developed related to project outcomes (baseline studies, aquaculture impact, ERAs, etc.), | 0 | 30% | At least 6 theses incorporating issues related to project
Objective / Component 3 | No. stakeholders with improved capacity in order to reduce vulnerability to climate chang | 0% | 20% | At least 10 fishery associations and 6 public institutions (PRODUCE, IMARPE, MINAM, SERNANP, local governments)
| % of women with improved capacity | 17% | 20% | 80 % of women with improved capacity
Outcome 3.1 / Output 3.1.1 | # of tools to support the processes of production, storage, update, circulation and knowledge (re)use | 0 | 8.333% | Formal communication, storage, classification and distribution systems of the information generated
| # of documented lessons by users type | 0 |  | As part of the learning process there are identified at least 2 replication strategies for scale up (technical and management) by characterized user type (governmental, non-governmental, private, beneficiaries)
# of replication strategies for scale-up
| # of sectoral public management instruments that include project adaptation measures aligned with the NDCs | 0 |  | 01 Sectoral Strategy proposal on fisheries and aquaculture aligned with the NDCs
Outcome 3.2 / Output 3.2.1 | # of artisanal fishers and other key agents trained in issues related to Component 1: fishing sustainable methods, self-organization, legal formalization, entrepreneurship, fisheries certification, marketing, | 0 | 0% | 30% of the target population trained
| # of debate spaces for sharing successful experiences | 0 | 0% | 3 network-wide debates for beneficiaries at each PA to generate synergies and share learning
Outcome 3.2 / Output 3.2.2 | # early warning systems associated to environmental variables | 0 | 0% | Two early warning systems developed with a set of reference levels and indicators associated to environmental variables to identify and timely evaluate the emergence of short-term deviations for taking appropriate action
Objective / Component 4 | No. regulations or instruments proposals to promote resiliency of ecosystems and communities to climate change | 0 | 0% | At least 4 regulations or instruments proposals to promote resiliency of ecosystems and communities to climate change
Outcome 4.1 / Output 4.1.1 | # of cross-sector management proposals addressing coastal marine issues related to climate change. | 0 | 0% | One cross-sector draft plan incorporating coastal and marine environments in climate change adaptation strategies and instruments for defining sector policies related to Integrated Management of Coastal Marine Areas
| # of economic ecological zoning proposals in PA. | 0 | 0% | 1 zoning proposal have been developed in coordination with the MINAM (Territorial Ordination Office)
Outcome 4.1 / Output 4.1.2 | # of proposals for the update and/or development of the current fisheries normativity and regulations, with focus on co-management | 0 | 0% | At least one normativity or guideline is incorporated for co-management at the sectorial and regional level
Outcome 4.1 / Output 4.1.3 | # of regulations and/or administrative procedures for the implementation of incentives approved | 0 | 0% | 1 regulation incorporated to promote artisanal fishing products for Direct Human Consumption, applying sustainable fishing methods, in the national and regional laws and regulations

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | In December 2019, in order to improve the technical and budget monitoring and monitoring of the project, a 2020 calendar AOP was approved, canceling the 2019-2020 AOP approved in June 2019. The grouping of activities has been proposed as the appropriate strategy to improve the execution of the project and the fulfillment of its objectives, however the flow of procedure is constituting a bottleneck for its execution and implementation.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The delays in the flow of procedures are maintained, this constitutes an important limitation. The effects of the pandemic on the development of the planned activities are causing delays that are expected to affect the project significantly.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | The regrouping of activities for the competition and award is an important change, in addition to the fact that a consultancy aimed at strengthening Governance in order to complement the activities established in component 4 is being included here.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Although the implementation of environmental and social safeguards is still limited due to the fact that adaptation measures for Component 1 have not started, in the context of the pandemic, project beneficiaries have been treated with personal protective equipment and materials from cleaning. They have coordinated with them to avoid environmental contamination as a consequence of the use of disposable equipment.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | The work carried out by the women field articulators is essential for the development of activities in the pilot areas, this raised to collect updated information from the areas, coordinate the activities of other consultations and maintain a presence of the project in the area and with the beneficiaries.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Adaptation measures have not been implemented yet in the areas.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Adaptation measures have not been implemented yet in the areas.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The acquisition of high-tech equipment allows IMARPE to be at the forefront of oceanographic research at a national and international level.
What measures are/have been put in place to ensure sustainability of the project/program results? | The grouping of activities includes in each service the design of the sustainability mechanisms of the intervention. The equipment purchased is being awarded in session in use to the user areas of the project.
What measures are being/could have been put in place to improve project/program results? | The hiring of field articulators is in process to guarantee these coordination.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | We have the design of the Knowledge Management Strategy for which workshops were held in the pilot areas. Workshops and meetings have also been held with professionals and fishermen to identify the vulnerability of species in the Mancora pilot area.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | The systematization of the information of the baseline is already in its final phase and the design of participatory monitoring is planned, however, communication channels and dissemination of this information have not been implemented yet.
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
Products | Hyperlinks
Estrategía, Análisis, y Optimización de Información proporcionados por el despliegue de un glider Slocum-G2 en relación con el sistema hidrodinámico frente a la costa norte del perú | https://drive.google.com/file/d/1jCT4pTD9I1UaQrTf3CjXT2rSf6U_V9j7/view?usp=sharing
Asistencia Técnica para la identificación y definición de áreas para el repoblamiento y cultivo de concha de abanico en la zona piloto de Huacho | https://drive.google.com/file/d/1o9cpnmxhMI21VDBsoPAujKnD0mlmRYh8/view?usp=sharing
Modelado oceanográfico de zonas marinas y costeras | https://drive.google.com/file/d/1VlF40cJNnA3cv8JqUPifJBptf2XxudB0/view?usp=sharing
Elaboración de un estudio de factibilidad de la actividad de conversión de residuos pesqueros y acuícolas en bio productos en las zonas piloto de las ciudades de Huacho y Mancora. | https://drive.google.com/file/d/1vsAnFPGywXtflKg5RqYzae4jsb5NOdk2/view?usp=sharing
Consultoría para Asistencia técnica para la identificación y definición de áreas para el cultivo de ostra en la zona piloto de Máncora | https://drive.google.com/file/d/1VQqvDHu9opfZFPyW-69p9cBEw7Rn6oq-/view?usp=sharing
Asistencia de investigación para el análisis de la vulnerabilidad socioecológica de comunidades pesqueras artesanales de la zona piloto de Máncora frente al cambio climático | https://drive.google.com/file/d/1qZ5IsDLlOXjaOFxTxfEhKLGlEIjRJd3Z/view?usp=sharing
Asistencia para el levantamiento de información de los cruceros y prospecciones para incorporación a la data del centro de datos oceanográficos (parcial) | https://drive.google.com/file/d/1IjPRcS8I93IGe5i8speAeeRLDGXAZ5kF/view?usp=sharing
Modelado atmosférico de zonas marinas y costeras de las áreas piloto de Huacho y Máncora (parcial) | https://drive.google.com/file/d/1QDDcwNCp1nT2se2ygxR9-fwgAX3e9okA/view?usp=sharing
Evaluación de vulnerabilidad climática (EVC) de los impactos del cambio climático sobre especies clave del ecosistema tropical peruano (parcial). | https://drive.google.com/file/d/1xwwZ6-TZtcS7j73kjUjsIvDqsgMxG9KB/view?usp=sharing
Estudios del ambiente en zonas marinas y costeras con datos provenientes de despliegues de vehículos autónomos submarinos (parcial). | https://drive.google.com/file/d/1u1wyBiQah9GO2IJsqWZ5rS3qDIbsvoJH/view?usp=sharing
Modelado estadístico de especies en zonas marinas y costeras de las áreas piloto de Huacho y Máncora (parcial). | https://drive.google.com/file/d/11fzewNSVWIB05KqusuICquFGmrQVv_Vw/view?usp=sharing
Evaluación de la Vulnerabilidad Climática (EVC) de especies del ecosistema tropical peruano (parcial). | https://drive.google.com/file/d/1ZXM9SMs-WZgF1PXqKgtw4kzqZTXrKkJ0/view?usp=sharing
Asitencia tecnica y acompañamiento para acciones de desarrollo productivo, empresarial y comercial, dirigido a pescadores artesanales en el area piloto de Huacho | https://drive.google.com/file/d/1jw9YucPmF9JMis8mi2ZjXFbrTDagIgeR/view?usp=sharing
Asistencia para estudio de impacto del cambio climatico sobre comunidades bentonicas | https://drive.google.com/file/d/1d4_PhOCb7OVnmMvQ32Dq0E6EerEMvVb-/view?usp=sharing
Servicio especializado para el diseño de la estrategia de gestión del conocimiento del proyecto | https://drive.google.com/file/d/1w326Snf2oVLd7e4S1rDeo94VIW1o_zlf/view?usp=sharing
Servicio de evaluacion de riesgo ecologico asociado a pesquerias artesanales seleccionadas | https://drive.google.com/file/d/1Nzaxtq7XCBtk-HoZoYu8keSFSYa4eZuv/view?usp=sharing
Asistencia tecnica para implementacion de las salvaguardas sociales y el enfoque de genero en el proyecto (parcial). | https://drive.google.com/file/d/1LKJ7SuMgGtwLSFiqFDvrfVtkmeAn3AfJ/view?usp=sharing
Fotografias del proyecto | https://drive.google.com/drive/folders/1DwAL_vaW8YMOAb_DEcQg9aLX7Yx9I0Er?usp=sharing
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | In the context of COVID, the use of virtual platforms for coordination with project beneficiaries is being innovated, as well as the replacement of face-to-face workshops and meetings.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | Profonanpe
Type of implementing entity | NIE
Country | Peru
Region | Latin America and Caribbean
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 3541 | 741 | 2800 | Total | 3541 | 741 | 2800 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 36% | 20% | 40% | % of female beneficiaries | 0.6% | 3% | 0.8% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Coastal flooding |  | Total | 60 | Coastal flooding | 4: Effective | Total | 60 | Coastal flooding | 4: Effective | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 20% |  |  | % of female targeted | 15% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Coastal management | Regional | 3: Risk and vulnterability assessments completed or updated | 1 | Coastal management | Regional | 1: No plans conducted or updated | 1 | Coastal management | Regional | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Local | 2 | 1: Risk knowledge | Geographical coverage | Local | 0 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 5 |  |  | Number of municipalities | 0 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 2 | 2: Monitoring and warning service | Geographical coverage | Local | 0 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 5 |  |  | Number of municipalities | 0 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Local | 2 | 3: Dissemination and communication | Geographical coverage | Local | 0 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 5 |  |  | Number of municipalities | 0 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 4: Response capability | Geographical coverage | Local | 2 | 4: Response capability | Geographical coverage | Local | 0 | 4: Response capability | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 5 |  |  | Number of municipalities | 0 |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 30 | Coastal management | 3: Medium capacity | Total | 30 | Coastal management | 4: High capacity | Total | 30 | Coastal management | 4: High capacity | Total
|  | % of female targeted | 17% |  |  | % of female targeted | 20% |  |  | % of female targeted | 17% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 30 | 17% | Public |  | 30 | 20% | Public |  | 30 | 20% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Coastal management | 3: Medium capacity | Public | National | Coastal management | 4: High capacity | Public | National | Coastal management | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% |  |  |  |  | 4: Mostly aware |  |  |  | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
[6 empty] | Coasts | 1 | ha rehabilitated | 4: Effective | Coasts |  | ha rehabilitated | 1: Ineffective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 |  |  |  | 5 | Physical capital | Coastal management | Community-based adaptation | 0 | Physical capital | Coastal management | Community-based adaptation
|  | 0 |  |  |  | 7 | Social capital | Coastal management | Community-based adaptation | 0 | Social capital | Coastal management | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
0
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 |  |  |  | 4 | Coastal management | National | Other policy | 0 | Coastal management | National | Other policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
Note on I23: Cynthia Mirella Cespedes Madalengoitia: to be determined
Note on J23: Cynthia Mirella Cespedes Madalengoitia: to be determined
Note on K23: Cynthia Mirella Cespedes Madalengoitia: to be determined
Note on M23: Cynthia Mirella Cespedes Madalengoitia: to be determined
Note on N23: Cynthia Mirella Cespedes Madalengoitia: to be determined
Note on O23: Cynthia Mirella Cespedes Madalengoitia: to be determined
Note on I27: Cynthia Mirella Cespedes Madalengoitia: this number refers to direct beneficiaries
Note on M27: Cynthia Mirella Cespedes Madalengoitia: this number refers to direct beneficiaries (9)
Note on K39: Cynthia Mirella Cespedes Madalengoitia: Thiis include ENSO, algae blooms and sulphidic plums
Note on J57: Cynthia Mirella Cespedes Madalengoitia: the 30 trained belongs to public (15) and private sector (15)
Note on N57: Cynthia Mirella Cespedes Madalengoitia: the 30 trained belongs to public (15) and private sector (15)
Note on H67: Cynthia Mirella Cespedes Madalengoitia: According to the Results Framework, the target for this indicator is at least 10 fishery associations and 6 public institutions. In the next reporting period, we will determine the total number of people trained
Note on L67: User: The Knowledge Management Strategy has been designed, however its implementation would allow reporting the progress of the number of associations and institutions aware of it.
Note on M94: User: The location and characteristics of the Natural Bank have been identified, including the restoration actions, although these have not taken place yet.
Note on C109: Cynthia Mirella Cespedes Madalengoitia: no es posible reportar este indicador
Note on H118: Cynthia Mirella Cespedes Madalengoitia: alineado al resultado 1.2 se cuentan la planta de bioproductos y las 2 concesiones de acuicultura (ostras y concha de abanico) 2 de acuaponía
Note on K118: Cynthia Mirella Cespedes Madalengoitia: the project uses the ecosystem-based adaptation approach
Note on H119: Cynthia Mirella Cespedes Madalengoitia: 2 asociaciones de mujeres de acuaponía 2 asociaciones de pescadores y 1 de mujeres en turismo 2 asociaciones para acuicultura = 7
Note on H121: Cynthia Mirella Cespedes Madalengoitia: The target is 700 individuals as beneficiaries of component 1. At this time we can not determine how many families belong because it is possible that some beneficiaries belong to the same household. In the next reporting period we can have this information
Note on I121: Cynthia Mirella Cespedes Madalengoitia: It is very difficult to obtain this value in the sector because there is a cultural factor, the fisherman is very jealous with the information and there is a high distrust
Note on K133: Cynthia Mirella Cespedes Madalengoitia: Fishing and aquaculture policy
Note on O133: Cynthia Mirella Cespedes Madalengoitia: Fishing and aquaculture policy