## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 30 August 2019 - 29 August 2020
| Project Title: | The Agricultural Climate Resilience Enhancement Initiative (ACREI)
| Project Summary: | The Agricultural Climate Resilience Enhancement Initiative (ACREI) is a US$ 6.8 million project funded by the Adaptation Fund and implemented by the World Meteorological Organization (WMO) in partnership with the Food and Agriculture Organization (FAO) and the Intergovernmental Authority on Development (IGAD) Climate Prediction and Applications Centre (ICPAC). The ACREI project is the first regional project funded by the Adaptation Funded through its Pilot Programme for Regional Projects. The program targets Ethiopia, Kenya and Uganda and supports community adaption practice, climate proofing of extension systems and climate informed decision making. The project outcomes are: - Outcome 1. Sustainably enhanced agricultural productivity, production, livelihood diversification and income levels among targeted communities. - Outcome 2. Enhanced technical capacity of development and extension actors (national, sub-national, private sector, NGOs, CBOs) to support community level climate adaptation strategies - Outcome 3. Improved climate informed decision making in regional, national and sub-national institutions The goal of the initiative is to develop and implement adaptation strategies and measures that will strengthen the resilience of vulnerable smallholder farmers, agro-pastoralists and pastoralists in the Horn of Africa to climate variability and change. The overall objective of ACREI is improved adaptive capacity and resilience to current climate variability and change among targeted farmers, agro-pastoralists and pastoralist communities. The goals of the ACREI project are in line with the IGAD Drought Disaster Resilience and Sustainability Initiative (IDDRSI) programme, and with the overall vision of the African Ministerial Conference on Meteorology (AMCOMET), the inter-governmental body for the development of meteorology and its applications in Africa.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AFR/MIE/Food/2015/2 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | The World Meteorological Organization (WMO) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity (MIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Ethiopia, Kenya and Uganda | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Ethiopia - Kersa Woreda, East Hererghe Zone & Mieso Woreda, West Hererghe Zone Kenya - Taita Taveta County Uganda - Sembabule District & Isingiro District | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2017-03-17
IE-AFB Agreement Signature Date: |  | 2017-06-20 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2018-08-30 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | TBA - Since project was planned as a 3-year project.
TBC
| Original Completion Date: | 29 August 2021 (based on 3 year duration after inception)
Revised Completion Date after approval of |  | N/A
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
| Condition or Requirement | N/A
| Current Status | N/A
| Planned actions, including a detailed time schedule | N/A
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Project Inception Workshop Report (submitted to Adaptation Fund on 29 October 2018) Project brief by WMO (PDF available) Project fliers by ICPAC (PDF available) Project story by Adaptation Fund: https://www.adaptation-fund.org/adaptation-fund-project-story-regional-project-in-ethiopia-kenya-and-uganda/ Regional projects video by Adaptation Fund: https://youtu.be/UWUgHC-Av4c News stories/publications Year 1: - WMO: https://public.wmo.int/en/media/news/new-initiative-boost-smallholders’-climate-resilience-horn-of-africa - FAO: http://www.fao.org/africa/news/detail-news/en/c/1151587/ - ICPAC: http://icpac.net/wp-content/uploads/PR_ACREI---Strengthening-the-resilience-of-vulnerable-smallholder-farmers_2018-09-05_Final_Clean-AMCOMET.pdf - IGAD Center for Pastoral Areas and Livestock Development (ICPALD): https://icpald.org/new-initiative-to-boost-smallholders-climate-resilience-in-the-horn-of-africa/ News stories/ publications Year 2 - https://www.icpac.net/news/enhancing-climate-advisories-resilience-east-africa/ - https://www.icpac.net/news/communicating-climate-change-east-africa/ - https://www.icpac.net/news/journalists-share-experiences-weather-and-climate-reporting/ - https://public.wmo.int/en/enhancing-climate-advisories-resilience-east-africa - https://www.nrc.no/expert-deployment/2016/2019/radio-programming-boosts-climate-change-adaptation/ - Various project reports published on ICPAC ACREI website below. - Publication on ACREI baseline methodology: https://doi.org/10.1007/978-3-030-22759-3_67-1 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://public.wmo.int/en/projects/agricultural-climate-resilience-enhancement-initiative-acrei-0 | Democratic Republic of the Congo
https://www.icpac.net/our-projects/acrei/
https://www.adaptation-fund.org/project/agricultural-climate-resilience-enhancement-initiative-acrei-ethiopia-kenya-uganda/
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Sebastian Grey, World Meteorological Organization (WMO), Sub-regional Office for Eastern and Southern Africa | Dominican Republic
| Email: | SGrey@wmo.int | Ecuador
| Date: | 2019-10-28 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | H.E. Mr. Kare Chawicha Debessa, State Minister, Ministry of Environment and Forest (at time of project approval) | Equatoral Guinea
| Email: | eenvironment@gmail.com | Eritrea
| Date: | 2017-02-01 | Estonia
| Name: | Mr. Charles T. Sunkuli, Principal Secretary, State Department of Environment & Regional Development Authorities, Ministry of Environment and Forestry, Kenya (at time of project approval) | Equatoral Guinea
| Email: | psoffice@environment.go.ke | Eritrea
| Date: | 2017-02-03 | Estonia
| Name: | Mr. Keith Muhakanizi, Permanent Secretary / Secretary to the Treasury, Ministry of Finance, Planning and Economic Development | Equatoral Guinea
| Email: | finance@finance.go.ug | Eritrea
| Date: | 2017-01-16 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Jean-Paul Gaudechoux, Senior Programme Manager, WMO | Fiji
| Email: | jpgaudechoux@wmo.int | Finland
| Date: | 2019-10-28 | France
| Executing Agency |  | Gambia
| Name: | Cyril Ferrand, Resilience Team Leader, Food and Agriculture Organization of the United Nations (FAO), FAO Sub-Regional Resilience Team for Eastern Africa, Nairobi, Kenya | Georgia
| Email: | Cyril.Ferrand@fao.org | Germany
| Date: | 2019-10-28 | Ghana
| Executing Agency |  | Greece
| Name: | Dr. Guleid Artan, Intergovernmental Authority on Development (IGAD) Climate Prediction and Applications Centre (ICPAC), Nairobi, Kenya | Grenada
| Email: | gartan@icpac.net | Guatemala
| Date: | 2019-10-28 | Guinea
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information: cumulative from project start to 29 August 2019 |  |  |  |  | Financial information: cumulative from project start to 29 August 2020 |  |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 29 August 2019 |  | 2064394 |  |  | Estimated cumulative total disbursement as of 29 August 2020 |  | 5983831 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) |  | Grant funds were well received and disbursements made to the Executing Entities, with FAO receiving their project funds in November 2018 and ICPAC receiving theirs in February 2019. The IE and EEs are utilising the project execution costs as indicated in the project document. One issue that has arisen is in regards to currency fluctuations. Funds received from Adaptation Fund are registered and maintained in CHF (in accordance to WMO financial regulations), with disbursements being made to partners in USD. However, it has been noted that currency exchange fluctuations between the USD and CHF can still have slight impacts on project funds. Between the time of the receipt of funds from the Adaptation Fund and disbursements being made to implementing partners, USD/CHF currency exchange fluctuations occured which negatively affected one executing entity's disbursement amount. The trust funds are being monitored and a plan put in place to ensure this does not occur for subsequent disbursements. To mitigate further currency fluctuation effects, future disbursements to partners are aimed to be conducted as quickly as possible after receipt of funds from the Adaptation Fund. Note that the initial delay between receipt of funds from Adaptation Fund and disbursements being made to partners was due to events outside WMO control and have been communicated to the Adapation Fund. Disbursed to FAO (including EE fees and execution costs) - US$1,250,261 Disbursed to ICPAC (including EE fees and execution costs) - US$377,807 Total disbursed to EEs = US$1,628,068 WMO expenditure (execution costs and activities) - US$355,261 WMO IE fees - US$81,065 Total up to end of August 2019 - US$2,064,394 Balance unspent and unobligated as at end of August - US$1,335,606 The disbursement schedules for the executing entities are as follows: ICPAC: Year 1: US$377,807.00 (already disbursed) Year 2: US$352,807.00 Year 3: US$317,806.00 Total: US$1,048,420 FAO: Year 1: US$1,250,261 (already disbursed) Year 2: US$3,077,067 Year 3: US$335,466.00 Total: US$4,662,794 The remaining balance from the first tranche, will be carried forward to committments to executing entities contracts for their Year 2 activities. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  | Disbursed to FAO (including EE fees and execution costs) - $4,327,328 Disbursed to ICPAC (including EE fees and execution costs) - $730,614 Total disbursed to EEs = $5,057,942 (82.6% of funds received from AF have been disbursed to EEs) WMO expenditure (activities & execution costs) - $736,292 (This includes LoAs with other institutions: IIRR - $101,908 disbursed (+US$25,423 obligation); AFAAS - $74,817 disbursed; Ethiopia National Meteorological Authority - $18,000 disbursed; Uganda National Meteorological Authority - $18,000 disbursed)) WMO IE fees - $189,597 Total up to end of August 2020 - $5,983,831 (97.8% of funds received from AF) Balance unspent as at end of August 2020 ≈ $136,169 (2.2% of AF grant). This remaining balance will be carried forward to committments to outstanding payments for LoAs and to executing entities contracts for their Year 3 activities. Although most funds have been disbursed to Executing Enitities as per WMOs agreements with them, their expenditure of these funds in Year 2 was much lower than expected due to the COVID situations impact on activities. Given the status of activities as a result of the COVID situation, there will be need for an extension of the project. WMO is not requesting any disbursement of funds from Adaptation Fund at this stage. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
:
INVESTMENT INCOME |  | 2375.87 |  |  | INVESTMENT INCOME |  | 3357 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
Component 1 | Output 1.1 | 1.1.1 - 10 day training at sub-national level of Agric and Met staff on Participatory planning approaches | 40559 |  | Component 1 | Output 1.1 | 1.1.1 - 10 day training at sub-national level of Agric and Met staff on Participatory planning approaches | 63227
|  | 1.1.2 - Community sensitization, mobilization and launching of the community adaptation planning processes. | 15666.37 |  |  |  | 1.1.2 - Community sensitization, mobilization and launching of the community adaptation planning processes. | 16838
|  | 1.1.3 - Context analysis and stocktaking at community level | 3385.95 |  |  |  | 1.1.3 - Context analysis and stocktaking at community level | 11139
|  | 1.1.4 - Seasonal short term adaptation planning of 1-2 days in each target community | 80.8 |  |  |  | 1.1.4 - Seasonal short term adaptation planning of 1-2 days in each target community | 7371
|  | 1.1.5 - Longer term adaptation planning over a period of seven to ten days in each community | 11076.4 | Scheduled as a Year 2 activity, though some preparatory activities have begun. |  |  | 1.1.5 - Longer term adaptation planning over a period of seven to ten days in each community | 51803
|  | 1.1.6 - Validation of community adaptation plans | 0 | Year 2 activity |  |  | 1.1.6 - Validation of community adaptation plans | 17185
| Output 1.2 | 1.2.1 - Baseline and endline data collection | 36538.65 |  |  | Output 1.2 | 1.2.1 - Baseline and endline data collection | 83907
|  | 1.2.2 - 4-week training of facilitators (ToFs) courses on the APFS approach | 133262.83 |  |  |  | 1.2.2 - 4-week training of facilitators (ToFs) courses on the APFS approach | 169923
|  | 1.2.3 - Community Ground working will be undertaken in each target community | 2134.44 |  |  |  | 1.2.3 - Community Ground working will be undertaken in each target community | 11065
|  | 1.2.4 - Facilitation of participatory learning in APFS group trough groups meeting on weekly basis over appr 1.5 years period | 42084.01 |  |  |  | 1.2.4 - Facilitation of participatory learning in APFS group trough groups meeting on weekly basis over appr 1.5 years period | 45327
|  | 1.2.5 - Provision of learning materials package/grants to APFS groups | 0 | Year 2 activity |  |  | 1.2.5 - Provision of learning materials package/grants to APFS groups | 6111
| Output 1.3 | 1.3.1 - Training of communities in village savings systems (VSLA/VICOBA) and financial management and support for establishment of community savings and banking schemes. | 0 | Year 2 activity |  | Output 1.3 | 1.3.1 - Training of communities in village savings systems (VSLA/VICOBA) and financial management and support for establishment of community savings and banking schemes. | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
|  | 1.3.2 - Support to development of community adaptation investment proposal in target communities. | 33001.71 | Scheduled as a Year 2 activity, though some preparatory activities have begun. |  |  | 1.3.2 - Support to development of community adaptation investment proposal in target communities. | 73150
|  | 1.3.3 - Technical review and screening of proposals through multi-sectoral proposal review group | 0 | Year 2 activity |  |  | 1.3.3 - Technical review and screening of proposals through multi-sectoral proposal review group | 0 |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
|  | 1.3.4 - Community investment grant financing | 78138.33 | Scheduled as a Year 2 activity, though some preparatory activities have begun. |  |  | 1.3.4 - Community investment grant financing | 73057 |  | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
|  | 1.3.5 - Technical backstopping and monitoring of beneficiary community investment project implementation. | 285228.07 | Scheduled as a Year 2 activity, though some preparatory activities have begun. |  |  | 1.3.5 - Technical backstopping and monitoring of beneficiary community investment project implementation. | 198304
| Output 1.4 | 1.4.1 - Within country community exchange visits | 0 | Year 2 activity |  | Output 1.4 | 1.4.1 - Within country community exchange visits | 0
|  | 1.4.2 - Community and site participation in project review processes | 0 | Year 2 activity |  |  | 1.4.2 - Community and site participation in project review processes | 1425
|  | 1.4.3 - Participation in field days and agriculture shows/fairs but target communities | 0 | Year 2 activity |  |  | 1.4.3 - Participation in field days and agriculture shows/fairs but target communities | 2049
|  | 1.4.4 - Knowledge exchange coalitions for climate change adaptation | 58532.38 | Scheduled as a Year 2 activity, though some preparatory activities have begun. |  |  | 1.4.4 - Knowledge exchange coalitions for climate change adaptation | 60680
Component 2 | Output 2.1 | 2.1.1 - Conduct stakeholder mapping and capacity needs assessment on integration of climate change in extension programmes at sub-national level. | 3784.88 |  | Component 2 | Output 2.1 | 2.1.1 - Conduct stakeholder mapping and capacity needs assessment on integration of climate change in extension programmes at sub-national level. | 56095
|  | 2.1.2 - Development of a capacity development plan to integrate climate change in extension programmes at sub-national level. | 0 |  |  |  | 2.1.2 - Development of a capacity development plan to integrate climate change in extension programmes at sub-national level. | 24957
| Output 2.2 | 2.2.1 - Stocktaking and identification of actors | 0 |  |  | Output 2.2 | 2.2.1 - Stocktaking and identification of actors | 0
|  | 2.2.2 - Review/Update FS training manuals on climate change adaptation best practices. | 0 |  |  |  | 2.2.2 - Review/Update FS training manuals on climate change adaptation best practices. | 86253
|  | 2.2.3 - Workshop to validate the climate training curriculum and modules among key stakeholders followed by printing and dissemination of the curriculum | 0 | Year 2 activity |  |  | 2.2.3 - Workshop to validate the climate training curriculum and modules among key stakeholders followed by printing and dissemination of the curriculum | 68427
|  | 2.2.4 - National and sub-national training of extension actors on climate sensitive extension services. | 103142.14 |  |  |  | 2.2.4 - National and sub-national training of extension actors on climate sensitive extension services. | 129284 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
| Output 2.3 | 2.3.1 - Establishment of a knowledge and experience sharing platform following review of existing information systems | 95180.98 |  |  | Output 2.3 | 2.3.1 - Establishment of a knowledge and experience sharing platform following review of existing information systems | 106403
|  | 2.3.2 - Dissemination of timely information on climate impacts and weather forecasts through selected community radio, social media and print channels. | 0 |  |  |  | 2.3.2 - Dissemination of timely information on climate impacts and weather forecasts through selected community radio, social media and print channels. | 35213 |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
|  | 2.3.3 - Formation of dialogue groups for information exchange on climate adaptation. | 0 | Year 2 activity |  |  | 2.3.3 - Formation of dialogue groups for information exchange on climate adaptation. | 3081 |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
| Output 2.4 | 2.4.1 - Awareness creation workshops among FS support actors | 27725.25 | Scheduled as a Year 2 activity, though some preparatory activities have begun. |  | Output 2.4 | 2.4.1 - Awareness creation workshops among FS support actors | 74225
|  | 2.4.2 - Development of a generic climate module for FS practice on climate change adaptation and ecosystem resilience strategies. | 0 |  |  |  | 2.4.2 - Development of a generic climate module for FS practice on climate change adaptation and ecosystem resilience strategies. | 0 |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
|  | 2.4.3 - Refresher training of practicing Field School Master trainers in the region on the climate module and adaptation strategies | 5194 | Scheduled as a Year 2 activity, though some preparatory activities have begun. |  |  | 2.4.3 - Refresher training of practicing Field School Master trainers in the region on the climate module and adaptation strategies | 8535
|  | 2.4.4 - Lobbying and advocacy for climate sensitive FS | 4872.2 |  |  |  | 2.4.4 - Lobbying and advocacy for climate sensitive FS | 1094 |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Component 3 | Output 3.1 | 3.1.1 - Improved tailored seasonal climate forecasts and climate change projections | 47861 |  | Component 3 | Output 3.1 | 3.1.1 - Improved tailored seasonal climate forecasts and climate change projections | 116793
|  | 3.1.2 - Training and capacity building in downscaling techniques and communication of uncertainties | 19577 |  |  |  | 3.1.2 - Training and capacity building in downscaling techniques and communication of uncertainties | 29373
|  | 3.1.3 - High resolution forecast downscaling to farming community level | 2459 |  |  |  | 3.1.3 - High resolution forecast downscaling to farming community level | 0
|  | 3.1.4 - Establishment of historical climate baseline statistics, trends and historical and future climate change hotspots (areas of concern) for selected communities | 11031.51 |  |  |  | 3.1.4 - Establishment of historical climate baseline statistics, trends and historical and future climate change hotspots (areas of concern) for selected communities | 11032
| Output 3.2 | 3.2.1 - Database for intermediaries and famer users established | 4142.76 |  |  | Output 3.2 | 3.2.1 - Database for intermediaries and famer users established | 0
|  | 3.2.2 - Existing feedback mechanisms reviewed | 4586 |  |  |  | 3.2.2 - Existing feedback mechanisms reviewed | 5354
|  | 3.2.3 - A cost effective communication and feedback channel designed, tested and validated | 0 |  |  |  | 3.2.3 - A cost effective communication and feedback channel designed, tested and validated | 21170
| Output 3.3 | 3.3.1 - Seasonal agriculture planners regularly produced through national participatory planning workshops | 32005.5 |  |  | Output 3.3 | 3.3.1 - Seasonal agriculture planners regularly produced through national participatory planning workshops | 45903
|  | 3.3.2 - Continuous monitoring and evaluation | 58401.38 |  |  |  | 3.3.2 - Continuous monitoring and evaluation | 62353
|  | 3.3.3 - Identified intermediaries trained in PICSA and PSP approaches | 11253 |  |  |  | 3.3.3 - Identified intermediaries trained in PICSA and PSP approaches | 16464
|  | 3.3.4 - Capacity for agro-met divisions at NMHS and ICPAC strengthened | 8224.45 |  |  |  | 3.3.4 - Capacity for agro-met divisions at NMHS and ICPAC strengthened | 90460
|  | 3.3.5 - Advocacy and effective communication of project outcomes | 7050.77 |  |  |  | 3.3.5 - Advocacy and effective communication of project outcomes | 55902
| Output 3.4 | 3.4.1 - Documentation and dissemination of good practices and lessons learned on the use of climate information in agricultural decision making | 1314.6 |  |  | Output 3.4 | 3.4.1 - Documentation and dissemination of good practices and lessons learned on the use of climate information in agricultural decision making | 1230
|  | 3.4.2 - Conducting regional and national learning forums | 30590 |  |  |  | 3.4.2 - Conducting regional and national learning forums | 51906
|  | 3.4.3 - Improved regional food and nutrition security assessment coordination including capacity building on attribution of food insecurity to various climate related hazards. | 0 |  |  |  | 3.4.3 - Improved regional food and nutrition security assessment coordination including capacity building on attribution of food insecurity to various climate related hazards. | 0
|  | 3.4.4 - Publication of key findings in peer-reviewed journals | 0 | Year 2 activity |  |  | 3.4.4 - Publication of key findings in peer-reviewed journals | 0
|  | Execution costs | 363288.03 |  |  |  | Execution costs | 507224
|  | TOTAL | 1581373.39 |  |  |  | TOTAL | 2501292
PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
Component 1 | Output 1.1 | 1.1.1 - 10 day training at sub-national level of Agric and Met staff on Participatory planning approaches | 6316 | October 2019 (activity largely complete) | Component 1 | Output 1.1 | 1.1.1 - 10 day training at sub-national level of Agric and Met staff on Participatory planning approaches | 0 | Complete
|  | 1.1.2 - Community sensitization, mobilization and launching of the community adaptation planning processes. | 833.63 | October 2019 (activity largely complete) |  |  | 1.1.2 - Community sensitization, mobilization and launching of the community adaptation planning processes. | 0 | Complete
|  | 1.1.3 - Context analysis and stocktaking at community level | 11614.05 | 2019-12-01 |  |  | 1.1.3 - Context analysis and stocktaking at community level | 3860 | Largely complete
|  | 1.1.4 - Seasonal short term adaptation planning of 1-2 days in each target community | 9919.2 | Seasonal and annual activity - ongoing up to end of project. |  |  | 1.1.4 - Seasonal short term adaptation planning of 1-2 days in each target community | 2629 | Seasonal and annual activity - ongoing up to end of project.
|  | 1.1.5 - longer term adaptation planning over a period of seven to ten days in each community | 42127.6 | 2020-02-01 |  |  | 1.1.5 - longer term adaptation planning over a period of seven to ten days in each community | 1401 | Largely complete
|  | 1.1.6 - Validation of community adaptation plans | 27000 | 2020-03-01 |  |  | 1.1.6 - Validation of community adaptation plans | 9815 | 2020-12-01
| Output 1.2 | 1.2.1 - Baseline and endline data collection | 119461.35 | Baseline survey complete. Funds will be carried forward for regular monitoring and endline survey. |  | Output 1.2 | 1.2.1 - Baseline and endline data collection | 72093 | Baseline survey complete. Funds carried forward are being used for regular monitoring and for endline survey.
|  | 1.2.2 - 4-week training of facilitators (ToFs) courses on the APFS approach | 123237.17 | 2019-12-01 |  |  | 1.2.2 - 4-week training of facilitators (ToFs) courses on the APFS approach | 86577 | 2021-08-01
|  | 1.2.3 - Community Ground working will be undertaken in each target community | 16615.56 | October 2019 (activity largely complete) |  |  | 1.2.3 - Community Ground working will be undertaken in each target community | 7685 | Largely complete - Will be used for regular community interactions.
|  | 1.2.4 - Facilitation of participatory learning in APFS group trough groups meeting on weekly basis over appr 1.5 years period | 38915.99 | Seasonal and annual activity - December 2020 |  |  | 1.2.4 - Facilitation of participatory learning in APFS group trough groups meeting on weekly basis over appr 1.5 years period | 35673 | Delayed by COVID - August 2021
|  | 1.2.5 - Provision of learning materials package/grants to APFS groups | 27000 | 2020-02-01 |  |  | 1.2.5 - Provision of learning materials package/grants to APFS groups | 20889 | Delayed by COVID - December 2020
| Output 1.3 | 1.3.1 - Training of communities in village savings systems (VSLA/VICOBA) and financial management and support for establishment of community savings and banking schemes. | 24000 | 2020-06-01 |  | Output 1.3 | 1.3.1 - Training of communities in village savings systems (VSLA/VICOBA) and financial management and support for establishment of community savings and banking schemes. | 24000 | Delayed by COVID - June 2021
|  | 1.3.2 - Support to development of community adaptation investment proposal in target communities. | 61998.29 | 2020-02-01 |  |  | 1.3.2 - Support to development of community adaptation investment proposal in target communities. | 21850 | 2020-12-01
|  | 1.3.3 - Technical review and screening of proposals through multi-sectoral proposal review group | 30000 | 2020-03-01 |  |  | 1.3.3 - Technical review and screening of proposals through multi-sectoral proposal review group | 30000 | 2020-12-01
|  | 1.3.4 - Community investment grant financing | 1692861.67 | 2020-08-01 |  |  | 1.3.4 - Community investment grant financing | 1697943 | Delayed by COVID - August 2021
|  | 1.3.5 - Technical backstopping and monitoring of beneficiary community investment project implementation. | 62030.93 | Ongoing through to end of project |  |  | 1.3.5 - Technical backstopping and monitoring of beneficiary community investment project implementation. | 148955 | Ongoing through to end of project
| Output 1.4 | 1.4.1 - Within country community exchange visits | 26250 | 2020-11-01 |  | Output 1.4 | 1.4.1 - Within country community exchange visits | 26250 | Delayed by COVID - August 2021
|  | 1.4.2 - Community and site participation in project review processes | 3000 | 2020-08-01 |  |  | 1.4.2 - Community and site participation in project review processes | 1575 | Delayed by COVID - August 2021
|  | 1.4.3 - Participation in field days and agriculture shows/fairs but target communities | 18240 | Seasonal and annual activity |  |  | 1.4.3 - Participation in field days and agriculture shows/fairs but target communities | 15951 | Seasonal and annual activity
|  | 1.4.4 - Knowledge exchange coalitions for climate change adaptation | 0 | Ongoing through to end of project |  |  | 1.4.4 - Knowledge exchange coalitions for climate change adaptation | 0
Component 2 | Output 2.1 | 2.1.1 - Conduct stakeholder mapping and capacity needs assessment on integration of climate change in extension programmes at sub-national level. | 51257.12 | 2019-12-01 | Component 2 | Output 2.1 | 2.1.1 - Conduct stakeholder mapping and capacity needs assessment on integration of climate change in extension programmes at sub-national level. | 0 | Complete
|  | 2.1.2 - Development of a capacity development plan to integrate climate change in extension programmes at sub-national level. | 30000 | 2020-01-01 |  |  | 2.1.2 - Development of a capacity development plan to integrate climate change in extension programmes at sub-national level. | 3043 | Largely complete
| Output 2.2 | 2.2.1 - Stocktaking and identification of actors | 0 | Ongoing - No cost |  | Output 2.2 | 2.2.1 - Stocktaking and identification of actors | 0 | Ongoing - No cost
|  | 2.2.2 - Review/Update FS training manuals on climate change adaptation best practices. | 87000 | 2019-12-01 |  |  | 2.2.2 - Review/Update FS training manuals on climate change adaptation best practices. | 0 | Complete
|  | 2.2.3 - Workshop to validate the climate training curriculum and modules among key stakeholders followed by printing and dissemination of the curriculum | 68103 | 2020-03-01 |  |  | 2.2.3 - Workshop to validate the climate training curriculum and modules among key stakeholders followed by printing and dissemination of the curriculum | 0 | Complete.
|  | 2.2.4 - National and sub-national training of extension actors on climate sensitive extension services. | 171657.86 | Initally budgeted under Year 1, however for the rational flow of project activities this has been agreed to be moved to Year 2 activity - August 2020 |  |  | 2.2.4 - National and sub-national training of extension actors on climate sensitive extension services. | 145516 | Delayed by COVID - August 2021
| Output 2.3 | 2.3.1 - Establishment of a knowledge and experience sharing platform following review of existing information systems | 168649.02 | 2020-08-01 |  | Output 2.3 | 2.3.1 - Establishment of a knowledge and experience sharing platform following review of existing information systems | 157427 | Ongoing
|  | 2.3.2 - Dissemination of timely information on climate impacts and weather forecasts through selected community radio, social media and print channels. | 63000 | Initially budgeted under Year 1, however, in consultation with the National Meteorological and Hydrological Services (NMHSs) this has now been planned to be utilised in Year 2 and 3. |  |  | 2.3.2 - Dissemination of timely information on climate impacts and weather forecasts through selected community radio, social media and print channels. | 27787 | LoAs with National Meteorological services in all 3 countries signed and funds disbursed to 2 of the 3. Remaining funds here are for the disbursement to the 3rd NMS and for WMO support to their activities.
|  | 2.3.3 - Formation of dialogue groups for information exchange on climate adaptation. | 36368 | 2020-08-01 |  |  | 2.3.3 - Formation of dialogue groups for information exchange on climate adaptation. | 33287 | 2021-08-01
| Output 2.4 | 2.4.1 - Awareness creation workshops among FS support actors | 68274.75 | 2020-03-01 |  | Output 2.4 | 2.4.1 - Awareness creation workshops among FS support actors | 21775 | 2021-03-01
|  | 2.4.2 - Development of a generic climate module for FS practice on climate change adaptation and ecosystem resilience strategies. | 74320 | 2020-05-01 |  |  | 2.4.2 - Development of a generic climate module for FS practice on climate change adaptation and ecosystem resilience strategies. | 74320 | Delayed due to unavailability of identified consultant - December 2020
|  | 2.4.3 - Refresher training of practicing Field School Master trainers in the region on the climate module and adaptation strategies | 101685 | 2020-08-01 |  |  | 2.4.3 - Refresher training of practicing Field School Master trainers in the region on the climate module and adaptation strategies | 98344 | 2021-03-01
|  | 2.4.4 - Lobbying and advocacy for climate sensitive FS | 22970.8 | Ongoing annual activity |  |  | 2.4.4 - Lobbying and advocacy for climate sensitive FS | 26749 | Ongoing annual activity
Component 3 | Output 3.1 | 3.1.1 - Improved tailored seasonal climate forecasts and climate change projections | 72139 | Seasonal activity | Component 3 | Output 3.1 | 3.1.1 - Improved tailored seasonal climate forecasts and climate change projections | 3207 | Ongoing - Seasonal activity
|  | 3.1.2 - Training and capacity building in downscaling techniques and communication of uncertainties | 20423 | Seasonal and annual activity |  |  | 3.1.2 - Training and capacity building in downscaling techniques and communication of uncertainties | 10627 | Ongoing - Seasonal activity
|  | 3.1.3 - High resolution forecast downscaling to farming community level | 17541 | Seasonal and annual activity |  |  | 3.1.3 - High resolution forecast downscaling to farming community level | 20000 | Ongoing up to end of project.
|  | 3.1.4 - Establishment of historical climate baseline statistics, trends and historical and future climate change hotspots (areas of concern) for selected communities | 8968.49 | 2020-05-01 |  |  | 3.1.4 - Establishment of historical climate baseline statistics, trends and historical and future climate change hotspots (areas of concern) for selected communities | 8968 | Historical analysis complete. Future CC scenario analysis workshop delayed by COVID - May 2021
| Output 3.2 | 3.2.1 - Database for intermediaries and famer users established | 10857.24 | 2020-08-01 |  | Output 3.2 | 3.2.1 - Database for intermediaries and famer users established | 15000 | Ongoing - December 2020
|  | 3.2.2 - Existing feedback mechanisms reviewed | 5414 | 2020-06-01 |  |  | 3.2.2 - Existing feedback mechanisms reviewed | 4646 | Mostly complete - remaining funds to be carried forward for follow up surveys and finalising reports.
|  | 3.2.3 - A cost effective communication and feedback channel designed, tested and validated | 25000 | 2020-08-01 |  |  | 3.2.3 - A cost effective communication and feedback channel designed, tested and validated | 3830 | Ongoing up to end of project.
| Output 3.3 | 3.3.1 - Seasonal agriculture planners regularly produced through national participatory planning workshops | 47994.5 | Seasonal and annual activity |  | Output 3.3 | 3.3.1 - Seasonal agriculture planners regularly produced through national participatory planning workshops | 34097 | Ongoing up to end of project.
|  | 3.3.2 - Continuous monitoring and evaluation | 1598.62 | Ongoing activity up to end of project. |  |  | 3.3.2 - Continuous monitoring and evaluation | 0 | Ongoing up to end of project.
|  | 3.3.3 - Identified intermediaries trained in PICSA and PSP approaches | 18747 | 2020-05-01 |  |  | 3.3.3 - Identified intermediaries trained in PICSA and PSP approaches | 13536 | Ongoing up to end of project.
|  | 3.3.4 - Capacity for agro-met divisions at NMHS and ICPAC strengthened | 91775.55 | Annual activity up to end of project. AWS procurement targetted for Year 2. |  |  | 3.3.4 - Capacity for agro-met divisions at NMHS and ICPAC strengthened | 9540 | Annual activity up to end of project. AWS procurement in process (PO issued).
|  | 3.3.5 - Advocacy and effective communication of project outcomes | 104949.23 | Ongoing activity up to end of project. |  |  | 3.3.5 - Advocacy and effective communication of project outcomes | 56098 | Ongoing up to end of project.
| Output 3.4 | 3.4.1 - Documentation and dissemination of good practices and lessons learned on the use of climate information in agricultural decision making | 18685.4 | Ongoing activity up to end of project. |  | Output 3.4 | 3.4.1 - Documentation and dissemination of good practices and lessons learned on the use of climate information in agricultural decision making | 18770 | Ongoing up to end of project.
|  | 3.4.2 - Conducting regional and national learning forums | 49410 | Ongoing activity up to end of project. |  |  | 3.4.2 - Conducting regional and national learning forums | 28094 | Ongoing up to end of project.
|  | 3.4.3 - Improved regional food and nutrition security assessment coordination including capacity building on attribution of food insecurity to various climate related hazards. | 40000 | Ongoing activity up to end of project. |  |  | 3.4.3 - Improved regional food and nutrition security assessment coordination including capacity building on attribution of food insecurity to various climate related hazards. | 40000 | Ongoing up to end of project.
|  | 3.4.4 - Publication of key findings in peer-reviewed journals | 5000 | Ongoing through Year 2 and Year 3. Three papers currently being written. |  |  | 3.4.4 - Publication of key findings in peer-reviewed journals | 5000 | Ongoing up to end of project.
|  | Execution costs | 159423.97 | Ongoing up to end of project. |  |  | Execution costs | 138776 | Ongoing up to end of project.
|  | TOTAL | 3982633.99 |  |  |  | TOTAL | 3205583
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? |  | N/A |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  | N/A
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Different pace of project implementation for each country may delay overall project implementation and affect regional activities. | Low | Project structures have been formed at regional (PMT) and national level (PAG) to ensure the project moves at required pace and any key issues are raised and addressed as quickly as possible to enable implementation to proceed.
Uneven speed of implementation and expenditure rate among the three main partners may hamper overall project performance | Medium | Project structures have been formed at regional (Project Management Team (PMT)) and national level (Project Advisory Group (PAG)) to ensure the project moves at required pace and any key issues are raised and addressed as quickly as possible to enable implementation to proceed. Partners are meeting regularly to jointly plan and implement activities.
Irregularities with regards to relationships between executing and implementing bodies | Low | Standard WMO procedures have been used for partner agreements, including the use of Letters of Agreement, UN-to-UN agreements and Implementing Arrangements. WMO reporting requirements are being used for all partners to ensure project status information is regularly updated.
Sub-national governments prioritize alternative implementation frameworks. | Low | Partners have conducted inception missions to, and engaged local authorities in, all three countries at both national and sub-national level. All relevant stakeholders are aware of the project and are taking the project as a key initiative to build resilience and adaptive capacity in the project target locations.
Political uncertainties affect project implementation. | Low | Monitoring of the political and security context in all project target areas in partnership with key stakeholders is ongoing.
Limited awareness and stakeholder involvement on the project | Low | Partners have conducted inception missions to, and engaged local authorities in, all three countries at both national and sub-national level. All relevant stakeholders are aware of the project and are taking the project as a key initiative to build resilience and adaptive capacity in the project target locations.
Occurrence of a major natural disaster in the project areas. | Medium | Project partners continue to monitor the environmental context for any major hazard occurences, particularly in relation to climate hazards, of which the project goal is exactly to cushion and reduce the impacts of climate hazards.
Intercommunity differences regarding adaptation planning priorities in each community. | Low | Community based approaches will be used in all target communities. In particular, a community managed disaster risk reduction approach will be used and combined with participatory climate services approaches. Trainings on participatory approaches have been conducted for local stakeholders as part of the project.
Bias in awarding adaptation proposals. | Low | The project partners will jointly develop adaptation proposal review criteria in partnership with local authorities. The criteria will be developed based on lessons from FAO as well as small grants facilities (SGF) in other Adaptation Fund projects (e.g. South African National Biodiversity Institute (SANBI) project in South Africa).
Movement of trained staff to other sectors or outside the project areas. | Medium | A combination of strategies are being used to mitigate the potential of this risk occuring and reduce the magnitude of impact if it were to occur, including: 1 - Working with farmers directly through the farmer field school approach. 2 - Working with a wide variety of actors, including local organisations where possible, to ensure capacity remains in the project locations. 3 - Development of products that can be used beyond the project lifespan - e.g. training manuals. 4 - Working closely with the local government institutions responsible for agriculture and natural resources management.
Political influence affects adoption of lessons learned into national and regional adaptation strategies. | Low | Advocacy and stakeholder consultation, engagement and senistisation will be conducted throughout project implementation. Policy makers at sub-national level have been engaged and sensitised on the project, as well as being supported to participate in regional climate and food security fora, thus improving appreciation of the projects approach to climate resilience.
Governments continue to prioritize emergency initiatives over development initiatives. | Low | Advocacy and stakeholder consultation, engagement and sensitisation will be conducted throughout project implementation. Policy makers at sub-national level have been engaged and sensitised on the project, as well as being supported to participate in regional climate and food security fora, hence improving appreciation of the resilience building approach being used in the ACREI project.
Weak downscaling capacity to support the project. | Low | Building downscaling capacity is a key part of project implementation - ICPAC has ensured that all participating NMHSs from ACREI project countries are regularly involved in the seasonal forecast generation exercise at regional level, joint downscaling of the forecasts to sub-national level and conducting targetted training ahead of each season.
Limited coordination with other ongoing adaptation initiatives in the target countries. | Low | A review of ongoing initiatives has already been conducted. Consultation and engagement with stakeholders to ensure alignment and additionality to other programmes. In Kenya for example, good synergies have been found with ongoing government and development partner projects and programmes such as the Agriculture Sector development Support Programme (ASDSP) and the DFID funded WISER Coastal Project. Joint workshops have been held and a common approach to programming is being encouraged in consultation with the Taita Taveta CEC for Agriculture, Livestock, Fisheries and Irrigation.
Delays in recruitment or appointment of critical staff for the project. | Low | TORs for key staff developed and vacancy announcements were floated before official project commencement. The use of inhouse expertise among project partners and appointment of focal people from national institutions has been used as a strategy. All relevant staff are now onboard and supporting the project.
Instability in currencies, market prices and availability of project inputs | Medium | Funds received from Adaptation Fund are registered and maintained in CHF (in accordance to WMO financial regulations), with disbursements being made to partners in USD. However, it has been noted that currency exchange fluctuations between the USD and CHF can still have slight impacts on project funds. In Year 1, USD/CHF currency exchange fluctuations occured which negatively affected one executing entity's disbursement amount. To mitigate further currency fluctuation effects, future disbursements to partners are aimed to be conducted as quickly as possible after receipt of funds from the Adaptation Fund. Note that the initial delay between receipt of funds from Adaptation Fund and disbursements being made to partners for Year 1 was due to events outside WMO control and have been communicated to the Adapation Fund.
General financial risks | Low | WMO, FAO and ICPAC financial management procedures are being used to manage financial risks in all project activities and transactions.
Delays in financial disbursements | Low | The use of standard LoAs and UN-to-UN agreements to engage partners and ensure quick disbursement of funds.
Misuse of community financial grants at local level | Medium | Use of recognised community grant mechanisms based on FAO experience on such (e.g. grants mechanisms for Agropastoral Field Schools and the "Njaa Marufuku Kenya". This will be closely monitored in Year 2, when comunity grants begin.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The outbreak of the Covid-19 pandemic at national, regional and global level. | High | Some workshops and activities have been conducted online, particularly those related to Component 3 on seasonal climate advisories. When gatherings have been necessary, these are conducted with limited numbers and observing any local COVID-19 regulations for gatherings. FAO have developed global guidelines on running FFS in times of COVID, and these have been shared with the country implementing teams.
Desert Locust upsurge (particularly Ethiopia) | Low | FAO and Government have conducted extensive areal and ground spraying of swarms.
Intermittent security concerns in Ethiopia | Medium | Working with local partners who have regular access to project locations.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The risk mitigation measures employed were related to the COVID pandemic. - Workshops and activities that could be conducted online were replanned and conducted using virtual conferencing platforms, although with shorter duration, limited participation in some cases. - Advocacy and awareness raising on the project has continued to be conducted online, including writing news stories and documentation of good practices. - When gatherings have been necessary, these are conducted with limited numbers and observing any local COVID-19 regulations for gatherings. For desert locust: FAO and Government have conducted extensive areal and ground spraying of swarms.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1] | No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law | Yes | No | Lack of compliance with local and national laws in project activities. | Avoidance: The final project design will be compliant with all relevant regional and national laws following extensive consultation with national and regional stakeholders. Avoidance: No adaptation investments (USPs or any project activities) will be conducted if they do not comply with local, national and international laws. | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | The final project design was made to be compliant with all relevant regional and national laws following extensive consultation with national and regional stakeholders. | The final project design was made to be compliant with all relevant regional and national laws following extensive consultation with national and regional stakeholders. Any measures related with adherence to local and national laws will be implemented in Year 2 and Year 3 following identification of USPs. | None at the moment. | None at the moment.
2 - Access and equity | Yes | No | Lack of equity in access to project resources and activities. | Management, mitigation and avoidance: Given that the project will involve the development of shared community resources the project team will ensure that any activities or developments do not negatively affect current user rights to shared natural resources as well as ensuring equitable benefits from adaptation investments and other project activities. Any activities involving shared resources will be conducted in the context of the Voluntary Guidelines on the Responsible Governance of Tenure of Land, Fisheries and Forests in the Context of National Food Security (VGGT) and the relevant national laws. | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | From the baseline survey: - There is diparity between mens and womens ownership of resilience assets. Ensuring gender equity in access to project resources will be a major area of focus during project implementation. - One project site in Uganda, being a refugee host community, has high disparity between host community households and refugee households in terms of access to assets, trainings, adaptation practices and agricultural income. | - A conflict sensitivity review of the ACREI project was conducted by FAO with the main reccomendation being that "conflict-sensitive programming could cause significant positive shifts in peace and conflict dynamics and trends, and have a positive impact on food and nutrition security". Conflict sensitive programming will be integrated in various aspects of the project beginning in Year 2, particularly the community adaptation planning. - Further measures will be implemented in Year 2 and Year 3. | None at the moment. | None at the moment.
3 – Marginalized and vulnerable Groups | Yes | No | Exclusion of marginalised and vulnerable groups from project activities. | Management, mitigation & avoidance: The project will specifically target the most vulnerable and food insecure members of society in the target communities. Management: Ensure participation of all relevant stakeholders in project activities without discrimination and with aim to ensure fair and equitable access to project benefits including for women and men as well as marginalized groups. Management: Utilise proven community based adaptation planning methodologies that take into account the needs of different socio-economic groups in the community. Management, mitigation & avoidance: Conduct comprehensive community level consultations in the target districts, including with vulnerable groups, female headed households and key informants such as traditional forecast providers. Management: Aim to ensure that project activities target and support the most vulnerable to become more resilient to climate change including women, women headed households, children and the youth. | Minutes/ reports of consultations with local authorities on communityselection. | From the baseline survey: - There is diparity between mens and womens ownership of resilience assets. Ensuring gender equity in access to project resources will be a major area of focus during project implementation. - One project site in Uganda, being a refugee host community, has high disparity between host community households and refugee households in terms of access to assets, trainings, adaptation practices and agricultural income. - Knowledge on the gendered impacts of climate hazards and climate change is low. Awareness on this aspect will be supported through the community based planning pocesses and various trainings. | - Identification of target communities has been undertaken in conjunction with local authorities in all countries based on agreed upon criteria related to climate vulnerability, history of being affected by climate related events, income and food security classification, and presence (or rather lack) of large scale agricultural adaptation support. - One selected project location in Uganda is a refugee host community, therefore contributing to targetting of the most vulnerable. - Training of Ministry of Agriculture and National Meteorological and Hydrological Services (NMHS) staff on participatory planning approaches began in August 2019. This is expected to enhance sensitivity on the needs of different socio-economic groups in the community in relation to project activities. - Further measures will be implemented in Year 2 and Year 3. | None at the moment. | None at the moment.
4 – Human rights | No | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 – Gender equality and women’s empowerment | Yes | No | Lack of gender equity and women’s empowerment in project implementation and outcomes. | Management, mitigation & avoidance: - Baseline with sex disaggregated data and gender specific questions - Use participatory tools for gender sensitive community consultation and the FAO Self-evaluation and Holistic Assessment to Climate Resilience of Farmers and Pastoralists (SHARP). - Use tools developed by FAO and partners for integrating gender in climate-smart agriculture (http://www.fao.org/3/a-i5299e.pdf and http://www.fao.org/3/a-az917e.pdf). - Aim for 50% participation of women in project activities and 50% of project direct beneficiaries to be women, while also targeting specific project activities at women or women groups (for example the integrated savings and lending). - Foster equal participation of men and women in institutions and decision-making processes related to the project. | Participation of men and women in project activities and structures (see project LogFrame). | - There is disparity between mens and womens ownership of resilience assets. Ensuring gender equity in access to project resources will be a major area of focus during project implementation. - Knowledge on the gendered impacts of climate hazards and climate change is low. Awarenes on this aspect will be supported through the community based plannin pocesses and various trainings. - Womens participation in project activities and leadership positions varies from location to location and activity to activity. See the GP Compliance sheet for more details on gender issues arising in the project. | - The baseline survey has incorporated sex-dissagregated data and has useful information on the climate change adaptation needs and constraints of both men and women. Interesting findings have emerged regarding controll over assets by men and women, knowledge on climate change adaptation and ability to adapt to climate change. - Engagement of FAO Country Office gender focal points in project planning meetings and in review of documents to ensure incorporation of gender aspects. - Farmers field school groups incoporate both men and women, both as members and as group leaders. In some cases the 50% target is exceeded, however in other cases it is not always possible. The partners continue to strive for greater participation of women in such activities as well as identifying any barriers to their participation so project activities can be adjust to account. - All workshops and trainings have incorporated both men and women as participants and as facilitators/ trainers, with the need for gender balance and having women in key roles highlighted. | None at the moment. | None at the moment.
6 – Core labour rights | No | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 – Indigenous peoples | No | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 – Involuntary resettlement | No | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 – Protection of natural habitats | Yes | No | Damage to natural habitats (as a result of project activities). | Avoidance: The project partners, through broad stakeholder consultation and engagement, will ensure that adaptation investments do not encroach onto protected areas, buffer zones and natural habitats. Avoidance, management & mitigation: Climate change adaptation investments will be screened for negative impact on adjacent ecosystems and natural habitats. | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | Population growth, resources scarcity, land degradation, low productivity (both livestock and crops), overgrazing, deforestation, invasive species and market fluctuations among others affect the project locations. Adaptation investments/ USPs and specific basleine information related to them are yet to be identified through community based approaches in Year 2 of the project. | Measures will be implemented largely in Year 2/3 when USPs are identified and begun. | None at the moment. | None at the moment.
10 – Conservation of biological diversity | Yes | No | Biodiversity loss (as a result of project activities). | Management & mitigation: A climate-smart agriculture approach will be utilised to ensure that the project does not in any way contribute to biodiversity loss. Through the climate-smart agriculture approach the project will in fact improve biodiversity in crop and livestock production as a means of improving agro-ecosystem resilience to climate change and weather variability. The climate smart agricultural approach will improve biodiversity due to diversification of livelihoods, crops and livestock breeds and introduction of improved agroforestry species. Management, avoidance and mitigation: The project will foster capacity building and farmer to farmer learning so as to enhance responsible and effective governance of natural resources including land, pasture, water, soils and forests. Avoidance: The project will not involve or entertain introduction of invasive species or new pests and diseases into the project sites and any actions that may result in these will be appropriately screened and subjected to the relevant national and international laws and guidelines. | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | Population growth, resources scarcity, land degradation, low productivity (both livestock and crops), overgrazing, deforestation, invasive species and market fluctuations among others affect the project locations. Adaptation investments/ USPs and specific basleine information related to them are yet to be identified through community based approaches in Year 2 of the project. | Measures will be implemented largely in Year 2/3 when USPs are identified and begun. | None at the moment. | None at the moment.
11 – Climate change | No | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 – Pollution prevention and resource efficiency | Yes | No | Pollution and lack of efficiency in use of natural resources. | Management, avoidance & mitigation: The project will where possible, promote techniques such as Integrated Pest and Disease Management (IPDM) as a pillar of sustainable agriculture, reduce reliance on pesticides and avoid adverse impacts from chemical use on the health and safety of farming communities, consumers and the environment. Management: The climate-smart agriculture practices promoted through the project will also reduce soil erosion and hence reduce water pollution. Management: As part of the climate-smart agriculture approach to be used in the project, maximising efficiency in the use of natural resources will play a major role in supporting improved productivity and food security as well as supporting climate change adaptation. Management, mitigation & avoidance: Mitigation benefits will also be realised by reducing emission’s intensity, reducing waste by improving the timing and application of inputs, and ultimately increasing crop and livestock productivity per unit of inputs (and emissions). | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | Population growth, resources scarcity, land degradation, low productivity (both livestock and crops), overgrazing, deforestation, invasive species and market fluctuations among others affect the project locations. Adaptation investments/ USPs and specific basleine information related to them are yet to be identified through community based approaches in Year 2 of the project. | Measures will be implemented largely in Year 2/3 when USPs are identified and begun. | None at the moment. | None at the moment.
13 – Public health | No | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 – Physical and cultural heritage | No | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 – Lands and soil conservation | Yes | No | Land and soil degradation | Management & mitigation: The project will promote improved agricultural practices such as soil and water conservation practices (like minimum or zero tillage, contour ridging, increased use of organic manure). Water harvesting and irrigation, bush fallowing, agro-forestry, diversified agriculture including apiculture and plantation agriculture; and rotational grazing, programmed reseeding of degraded rangelands among pastoral and agro-pastoral communities, etc. will be encouraged and promoted by the project. | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | Population growth, resources scarcity, land degradation, low productivity (both livestock and crops), overgrazing, deforestation, invasive species and market fluctuations among others affect the project locations. Adaptation investments/ USPs and specific basleine information related to them are yet to be identified through community based approaches in Year 2 of the project. | Measures will be implemented largely in Year 2/3 when USPs are identified and begun. | None at the moment. | None at the moment.
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Monitoring of ESP risks is ongoing as part of project activities.
Have unanticipated ESP risks been identified during the reporting period? |  | None at the moment.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant? |  | Yes
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | N/A - These will be implemented largely when USPs are identified and begun. The major focus of the IE has been on 1) ensuring partners are fully aware of the ESP; 2) ensuring that the adaptation investment criteria integrate screening for environmental and social risks.
Have the implementation arrangements been effective during the reporting period? |  | Yes, awareness on the ESP has been raised among EEs and the means of screening for environmental and social risks in the adaptation invetments identified.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | N/A - These will be implemented largely when USPs are identified and begun.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | N/A - These will be implemented largely when USPs are identified and begun.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8] |  | Yes
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | The capacity for ESMP at the IE and the EEs is adequate based on their experience implementing similar projects and programmes. The Food and Agriculture Organization (FAO) which is responsible for the community-related and and adaptation grants components of the project have Environmental and Social Management Guidelines as well as principles for sustainable food and agriculture systems which aim to balance economic, social and environmental dimensions of sustainability in agriculture and food systems, and provide a basis for developing policies, regulations and incentives to guide the transition to sustainability, while promoting resilience through an adaptive response to shocks and opportunities. In terms of roles and responsibilities, WMO as the IE, will through the project manager ensure that partners are aware of the Adaptation Funds Environmental and Social Policy and take actions to ensure it is implemented. FAO as the excuting entity responsible for implementing the USPs and other community-level activities, will be the primary means through which ESP issues are implemented. All relevant human resources have been engaged either directly on the project or as technical support already within the partner organizations. Additional resources will be engaged and responsibilities defined as required to support ESMP implementation. This includes engaging WMO, FAO and ICPAC technical staff at national, regional and HQ levels with expertise on aspects such as gender, conflict sensitive programming and accountability. For Year 2: - 1) WMO made presentations on ESP issues at project meetings in all 3 countries to ensure partners were aware of this - 2) The adaptation investment (USP) template was designed to integrate a screening for environmental and social issues. Outstanding arrangements for compliance with Adaptation Fund ESMP include: - 1) Technical multi-stakeholder committees reviewing USPs will consider the potential of each investment for negative environmental and social impacts, based on the checklist/screening developed. - 2) Validation (disclosure) of the identified adaptation investments (through meetings with local leadership and communities). These arrangements will be conducted in accordance with AF Guidance on USPs (https://www.adaptation-fund.org/wp-content/uploads/2019/04/AFB.B.32-33.7_Compliance-with-ESP_Update-of-PPR_and_Guidance-for-USPs_revised-1.pdf) In terms of dealing with ESP risks, the heirarchy will be 1) avoidance, and 2) management of negative environmental and social impacts. Adaptation investments with potential for large scale adverse environmental and social impacts (either at the project site or its surroundings) will not be conducted.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | The community adaptation planning process, in which USPs are to be formulated, is still being undertaken. Only, Ethiopia has submitted USPs for review. The IE and EEs will ensure that all ESP issues are analysed and appropriately incoprorated into the ESMP submitted with the initial project proposal.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP] | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing.
USP 2: [name the USP] | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing.
USP 3: [name the USP] | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing.
USP 4: [name the USP] | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing.
USP 5: [name the USP] | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing. | N/A - USP identification ongoing.
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts? |  | Yes | The farmer field school groups and their structures provide the main channel for grievances. Partner staff contacts have been shared among stakeholders.
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None to date. |  | None to date.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Gender considerations were taken into account during project formulation including highlighting the following aspects for ensuring integration of gender equity and womens empowerment in project implementation and outcomes: 1) Baseline with sex disaggregated data and gender specific questions. 2) Use of participatory tools for gender sensitive community consultation and the FAO Self-evaluation and Holistic Assessment to Climate Resilience of Farmers and Pastoralists (SHARP). 3) Use tools developed by FAO and partners for integrating gender in climate-smart agriculture (http://www.fao.org/3/a-i5299e.pdf and http://www.fao.org/3/a-az917e.pdf). 4) Aim for 50% participation of women in project activities and 50% of project direct beneficiaries to be women, while also targeting specific project activities at women or women groups (for example the integrated savings and lending). 5) Foster equal participation of men and women in institutions and decision-making processes related to the project.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes. The results framework includes indicators at Objective, Outcome and Output level which either refer to targets for womens participation or to gender dissagregated data.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Number of APFS groups in place and applying climate change adaptation knowledge. (target for 50% women) | Output | % women | 0 | 50% | Good
Number of extension actors (% female) who demonstrate an increase in knowledge and skills on climate-sensitive extension methodologies | Output | % women | 0 | 50% | To be measured at endline.
Percentage change in household incomes disaggregated by gender of household heads | Outcome | % women | 0 | 50% | To be measured at endline.
No. of staff trained to respond to, and mitigate impact of, climate-related events (by gender). | Outcome | % women | 0 | 50% | Satisfactory
Percentage of extension workers (male and female) who are integrating adaptation strategies in their work at the community level | Outcome | % women | 0 | 50% | To be measured at endline.
9000 APFS household members/direct and targeted beneficiaries (min. 50% female) | Objective | % women | 0 | 50% | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
N/A - to be completed for final PPR as per guidance. |  | N/A - to be completed for final PPR as per guidance notes.
N/A - to be completed for final PPR as per guidance. |  | N/A - to be completed for final PPR as per guidance notes.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Implementing Entity and Executing Enities, have all made efforts to comply with the key concepts of the AF Gender Policy, including gender equity, gender mainstreaming, gender responsiveness, gender sensitivity and women's empowerment. In particular the following aspects have been put in place to ensure compliance with the AF gender policy: 1 - Ensuring that the household baseline incorporated sex disaggregated data and gender specific questions. 2 - Encouraging project partners/ executing entities to hold gender sensitive consultations and assessments, for example holding seperate focus group discussions for men and women, therefore allowing womens views to be better captured without being overshadowed by men. 3 - Ensuring that the Regional Inception Workshop had participation of both men and women. 4 - Ensuring that gender issues were discussed at Inception and during workplanning - for example, the question of how activities are designed so as not to discourage full participation of women arose during the inception.
Have the implementation arrangements at the IE been effective during the reporting period? |  | The implementation arrangements for Gender Policy compliance have been effective. Discussions on gender issues were held during project inception and work planning, with the following outcomes and agreements: 1) all partners to consider the specific needs and constraints of womens participation in project activities; 2) track gender indicators in all activities; 3) aim for equal participation of women in project activities and activity leadership structures; and 4) capture sex-dissagregated data for the baseline and other assessments and activities. This has laid the foundation for effective Gender Policy implementation in the project.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | Food and Agriculture Organization (FAO) of the United Nations: - The baseline survey has incorporated sex-dissagregated data and has useful information on the climate change adaptation needs and constraints of both men and women. - The baseline survey also had questions on the climate-related needs, challenges and impacts in relation to men and women. Interesting findings have emerged regarding control over assets by men and women, knowledge on climate change adaptation and ability to adapt to climate change. - Engagement of FAO Country Office gender focal points, where available, in project planning meetings and on review of documents to ensure incorporation of gender aspects. - Continuous sensitisation on participation of both men and women when sending activity invitations; project focal persons are encouraged to be a mix of both men and women; and overall continuous awareness raising on the need for womensparticipation throughout all the project activities. - Workshops and trainings have involved both men and women as participants and as facilitators/ trainers. - Examples of gender participation in Year 2: Farmers field school (FFS) groups incorporate both men and women, and a concerted effort has been made to ensure equal participation of women in these groups and their leadership structures. In Ethiopia, the leadership of the first 10 FFS groups was 32% women, and FFS membership was required to have 50:50 ratio of men and women. In Uganda, the FFs groups are comprised of 61% women and the leadership of the groups is 58% women, with some groups being womens' groups. In Kenya, women make up 60% of FFS membership and 50% of FFS chairpersonship. Community engagement meetings in Uganda involved over 70% women.
IGAD Climate Predictions and Applications Centre (ICPAC): - Continuous sensitisation on participation of both men and women when identifying participants for project activities; project focal persons are encouraged to be a mix of both men and women; and overall continuous awareness raising on the need for womens participation throughout all the project activities. - All trainings have incorporated both men and women as participants and as facilitators/ trainers.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | The implementation arrangements for Gender Policy compliance have been effective in some cases but not in others. Womens participation in project activities, as well as their engagement in leadership and training roles has been mixed. In some cases womens participation is higher than the targetted 50% and in other cases womens participation has been lower than the targetted 50%. The effectiveness of the EEs efforts has also varied from country-to-country and activity to activity.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No major capacity gaps affecting Gender Policy compliance have been identified at the IE or the EEs. The capacity for adherence to the Gender Policy is adequate among the IE and EEs. Overall, it is not always possible to meet the targets for womens participation and engagement; however the EEs will continue to emphasise this aspect among stakeholders. However, the EEs will continue to engage with the stakeholders on the importance of gender issues and the participation of both men and women.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1] |  | Yes |  | The farmer field school groups and their structures provide the main channel for grievances. Partner staff contacts have been shared among stakeholders.
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
N/A-No Grievances related to Genders matters were received during the reporting period but suggestions related to gender participation and involvement are highlighted during meetings |  | N/A
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity (WMO): | Overall project management and coordination: 1. Second disbursements to executing entities; 2. National and regional project implementation structures regularly meeting. |  |  | 1. Second disbursements to executing entities made 2. At least two Project Management Team (PMT) meetings held and at least one national project advisory group meeting per country held. |  | 1) Both executing entities received their year two disbursements in the first quarter of 2020, bringing disbursement rate to over 90%. 2) The project management team (PMT) at regional level is meeting regularly, with two formal meetings being held in the last year. Despite COVID affecting the ability to hold in-person meetings, the PMT held an online meeting in June 2020. All three countries have held national project advisory group (PAG) meetings in the year, including an online one for Kenya. | Satisfactory (S)
| Component 1 |  | Outcome 6 | 1. 60 FFS groups formed and FFS learning and exchange begun 2. 30 communities engaged on community adaptation planning and community adaptation investments identified and implementation begun |  | 1. 62 FFS groups were formed and supported with registration and identification of learning enterprises. FFS learning in Ethiopia is ongoing. FFS learning in Uganda and Kenya could not begin in March 2020 as scheduled due to the impact of the COVID pandemic. 2. Community adaptation planning has been conducted across all ACREI communities and the specific investments to be funded are in the process of being elaborated based on a template developed jointly by the partners, which also integrates ESP aspects. Community adaptation investments for Ethiopia are under review by the project team. Kenya is in the process of validating the identified investments. Uganda is in process of identifying the investments to be funded. | Marginally Satisfactory (MS)
| Component 2 |  | Outcome 2 | 1. Three (3) stakeholder mapping, capacity needs assessments & capacity development plans on integrating climate change in extension in project locations 2. One regional writeshop conducted and one regional APFS manual on climate change adaptation produced 3. Trainings for extension actors & field school facilitators on climate change adaptation conducted 4. LoAs with national meteorological services in place to improve climate information communication in project locations. 5. Knowledge sharing platform for information on climate change adaptation in place. 6. A generic climate information module for FS practice developed. |  | 1. Stakeholder mapping, capacity assessments and capacity development plans under Output 2.1 were completed through an LoA with the African Forum for Agricultural Advisory Sefvices (AFAAS). 2. The climate change manual for farmer field schools was developed through a partnership with the International Institute of Rural Reconstruction (IIRR), with a writeshop conducted in October 2019 and a technical team reviewing and refining the manual in August 2020. 3. Trainings under Component 2 for extenson actors could not be conducted due to the COVID situation. 4. LoAs have been signed with the 3 respective national meteorological authorities and funds transfers made to 2 of them for their actrivities. This work links with that under Component 3. 5. Various knowledge sharing platforms are being used, including Whatsapp groups, Telegram Groups, WMO and ICPAC project websites, and virtual experience sharing. 6. The generic climate module was delayed as the consultant identified for this work became unavailable. | Satisfactory (S)
| Component 3 |  | Outcome 2 | 1. Five sub-national units/ districts receiving localised seasonal climate information. 2. Seven government institutions and three NGOs/CBOs reciving climate information. 3. FFS groups to begin receiving climate information in Year 2. 4. Policy makers from all ACREI sub-locations supported to participate in regional climate outlook fora. 5. At least 2 good practices and or papers documented. |  | 1. All 5 ACREI project locations are receiving support for seasonal climate advisory development and dissemination. 2. Various government departments and institutions are involved in coproduction of seasonal advisories and have the information 3. Farmer representatives are being involved in seasonal advisory development and tasked with sharing the information in their communities. Registration of FFS group contacts and learning times have been gathered to inform options for direct sharing of climate information. 4. Policy makers were continued to be supported to participate in regional climate Outlook Forums, although after the onset of the COVID pandemic this was not possible. 5. Two good practices have been documented (one on the seasonal advisory process (PSP) which is to be featured in the ICPAC coproduction manual to which ACREI has also contributed and another on media engagement for climate information communication). | Satisfactory (S)
[6 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Sebastian Grey, ACREI Project Officer, WMO Office for Eastern and Southern Africa
| Email: | sgrey@wmo.int
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project is proceeding generally well, with the major issue affecting progress in Year 2 being the emergence of the COVID pandemic. This has affected activities and expenditure by the EEs, particularly FAO whose activities are mostly field and community based. In terms of institutional arrangement, the project management team (PMT) at regional level is meeting regularly and all countries are holding national project advisory group (PAG) meetings. During the COVID period some of these meetings were held online, including one PMT meeting and one Kenya PAG meeting. Baseline survey, stakeholder sensitisation and community identification (10 communities per country) were completed in Year 1. Year 2 focused on identifying the community adaptation needs and narrowing down to the specific adaptation investments to be funded by the project. It was expected that some investments would be funded in Year 2 however, this has been delayed mostly due to limited possibility for community engagements as a result of COVID. Sixty-two (out of a target of 60) farmer field school groups have been formed, however field school learning which was due to begin in March 2020, was affected by restrictions on travel and gatherings that came about as a result of the COVID pandemic. Stakeholder mapping, capacity assessments of extension actors on climate change adaptation and development of capacity development plans for extension actors in project locations were succesfully completed in partnership with the African Forum for Agricultural Advisory Services (AFAAS). The development of a module on climate change adaptation for Farmers Field Schools was also completed in partnership with the International Institute for Rural Reconstruction (IIRR), although national validation workshops could not be held and a smaller team was instead constituted to validate the manual. The activity on the development of a generic module on climate information was intended to be conducted in Year 2, and although some preliminary work has been conducted by FAO, a suitable consultant to undertake the assignment had not been engaged (the one initially identified became unavailable). The trainings of extension actors based on the above assessments and manuals were delayed. Under Component 3, all ACREI locations are receiving support for seasonal participatory climate advisory development for each important season, includign translation into local languages. Even during the COVID period, the seasonal advisory workshops have shifted online, and have been conducted and advisories produced, though not without challenges e.g. reduced duration, limited participation of farmers. This is being conducted in collaboration with the national meteorological services. A regional training on the PICSA methodlogy, initially scehduled for March 2020, had to be postponed due to the COVID pandemic. Local media (particularly local radio stations) have being successfully engaged to support wider distribution of climate information in project target locations in Kenya and Uganda. Media engagement and training in Ethiopia was affected by the COVID situation. The main next steps include: 1) Implementing community adaptation investments; 2) Implementing and documenting field school learning in Kenya and Uganda; 3) Conducting trainings that were affected by COVID (e.g. extension actors trainings, PICSA training; 4) Continued advocacy and documentation of good practices.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator (FAO): | Component 1 |  | Outcome 6 | 1. 60 FFS groups formed and FFS learning and exchange begun 2. 30 communities engaged on community adaptation planning and community adaptation investments identified and implementation begun |  | 1. 62 FFS groups were formed and supported with registration and identification of learning enterprises. FFS learning in Ethiopia is ongoing. FFS learning in Uganda and Kenya could not begin in March 2020 as scheduled due to the impact of the COVID pandemic. 2. Community adaptation planning has been conducted across all ACREI communities and the specific investments to be funded are in the process of being elaborated based on a template developed jointly by the partners, which also integrates ESP aspects. Community adaptation investments for Ethiopia are under review by the project team. Kenya is in the process of validating the identified investments. Uganda is in process of identifying the investments to be funded. | Marginally Satisfactory (MS)
| Component 2 |  | Outcome 2 | 1. Three (3) stakeholder mapping, capacity needs assessments & capacity development plans on integrating climate change in extension in project locations 2. One regional writeshop conducted and one regional APFS manual on climate change adaptation produced 3. Trainings for extension actors & field school facilitators on climate change adaptation conducted 4. LoAs with national meteorological services in place to improve climate information communication in project locations. 5. Knowledge sharing platform for information on climate change adaptation in place. 6. A generic climate information module for FS practice developed. |  | 1. Stakeholder mapping, capacity assessments and capacity development plans under Output 2.1 were completed through an LoA with the African Forum for Agricultural Advisory Sefvices (AFAAS). 2. The climate change manual for farmer field schools was developed through a partnership with the International Institute of Rural Reconstruction (IIRR), with a writeshop conducted in October 2019 and a technical team reviewing and refining the manual in August 2020. 3. Trainings under Component 2 for extenson actors could not be conducted due to the COVID situation. 4. LoAs have been signed with the 3 respective national meteorological authorities and funds transfers made to 2 of them for their actrivities. This work links with that under Component 3. 5. Various knowledge sharing platforms are being used, including Whatsapp groups, Telegram Groups, WMO and ICPAC project websites, and virtual experience sharing. 6. The generic climate module was delayed as the consultant identified for this work became unavailable. | Satisfactory (S)
[6 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Deborah Duveskog, Agriculture and Resilience Officer, FAO sub-regional office, Resilience Team, Nairobi
| Email: | deborah.duveskog@fao.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project is proceeding generally well, with the major issue affecting progress in Year 2 being the emergence of the COVID pandemic. This has affected nature and magnitude of field activities and thus expenditures by FAO whose activities are mostly field and community based. Year 2 focused on identifying the community adaptation needs and narrowing down to the specific adaptation investments to be funded by the project. It was expected that some investments would be funded in Year 2 however, this has been delayed mostly due to limited possibility for community engagements as a result of COVID. Sixty-two (out of a target of 60) farmer field school groups have been formed, however field school learning which was due to begin in March 2020, was affected by restrictions on travel and gatherings that came about as a result of the COVID pandemic. In Ethiopia movement restrictions have further been enhanced by intermittent security concerns. Stakeholder mapping, capacity assessments of extension actors on climate change adaptation and development of capacity development plans for extension actors in project locations were successfully completed in partnership with the African Forum for Agricultural Advisory Services (AFAAS). The development of a module on climate change adaptation for Farmers Field Schools was also completed in partnership with the International Institute for Rural Reconstruction (IIRR), although national validation workshops could not be held and a smaller team was instead constituted to validate the manual. The activity on the development of a generic module on climate information was intended to be conducted in Year 2, and although some preliminary work has been conducted by FAO, a suitable consultant to undertake the assignment had not been engaged (the one initially identified became unavailable). The trainings of extension actors based on the above assessments and manuals were delayed.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator (ICPAC): | Component 3 |  | Outcome 2 | 1. Five sub-national units/ districts receiving localised seasonal climate information. |  | All the targeted ACREI sub-national units (five) are receiving localised seasonal climate advisories and they comprise East and West Haraghe Zones in Ethiopia, Taita Taveta County in Kenya and Sembabule and Isingiro Districts in Uganda. The forecast based coproduction processes involved the National Meteorological and Hydrological Services (the key stakeholders mandated to produce climate information at national level and lower levels), the local government authorities, government departments responsible for agriculture and livestock, farmers, partners among others. The NMHSs from the three countries are further disseminating downscaled monthly and weekly forecast updates to the season forecast given prior to the commencement of the season. Local media has been engaged in Kenya and Uganda as key partners in enhancing access, use, and uptake of climate information through mainstreaming climate information in their programming, an approach called Seasonal Media Action Plan (S-MAP). In Ethiopia, this has not been undertaken due to COVID. For SMAP training to be effective, an initial face to face training of journalist on climate information is very key. Historical climate data analysis has also been conducted for all ACREI locations identifying key climatic baselines such as average onset and cessation dates, dry spell occurence, average season length and other agrometeorological parameters, as well as their changes over time. Climate change projections work has started and is expected to be ready for sharing in the first quarter of 2021. | Satisfactory
|  |  | Outcome 2 | 2. Six government institutions (2 per country) and three NGOs/CBOs (one per country) receiving climate information. |  | In all the countries, government institutions responsible for agriculture and livestock, disaster management, health, forestry, veterinary services, water, environment and tourism, NGOs/CBOs have been continuously engaged in ACREI coproduction workshops and are receiving localised climate information. Thus the targets have been exceeded in all three countries. | Satisfactory
|  |  | Outcome 2 | 3. FFS groups to begin receiving climate information in Year 2 |  | In our coproduction workshops, farmer representatives from ACREI target locations are our key stakeholders and therefore have been continuously involved in all seasonal participatory advisory development exercises, with aim to ensure farmers have first-hand information and also gain a better understanding of the forecasts and the overall advisory generation process. FFS groups, which were formed in under component 2 receive these advisories through various dissemination approaches that the project has adopted, for instance through local radio and brochures translated to local languages. However, a limited or no participation of farmer representatives in the coproduction sessions and the shorter virtual time was the main challenge. | Marginally satisfactory (MS)
|  |  | Outcome 2 | 4. Seasonal advisories developed and distributed in all three countries for each important season. |  | Forecast based advisories were developed in all three countries for OND and MAM for Kenya and Uganda sites and for JJAS for Ethiopia following their key planting seasons. Advisories generated are being disseminated through various channels including print, radio and Whatsapp. Weekly/decadal forecasts updates are also being provided via Whatsapp and radio in Kenya and Uganda and via email in Ethiopia. Advisories were translated into Kiswahili in Kenya and Luganda and Runyankore in Uganda for wider reach and understanding. JJAS 2020 advisories in Ethiopia were provided in English and it is envisioned that the subsequent ones will be translated to Oromifa working closely with NMA. | Satisfactory
|  |  | Outcome 2 | 5. Policy makers from all ACREI sub-locations supported to participate in regional climate outlook fora. |  | Through the Greater Horn of Africa Climate Outlook Forums (GHACOFs), Policy makers from all ACREI project sites were supported where key dialogue and discourse on climate risks and climate risk management measures for the Eastern Africa region are held. Policy briefs on historical climate baselines for Uganda and Ethiopia are at advanced stage and will be shared to all stakeholders in the first quarter of 2021. Policy briefs on climate change projects for the project sites will also be shared in 2021. These products are envisaged to contribute to policy dialogue on climate change and ensure greater recognition of climate hazards and climate change among sub-national policy makers. However, lack of face to face interactions has been the major challenge. | Marginally satisfactory (MS)
[6 empty] | Overall Rating | Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Abdi Jama, IGAD Climate Prediction and Applications Centre (ICPAC)
| Email: | ajama@icpac.net; abdi.jama@igad.int
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Component 3 of the project is generally proceeding well, with the exemption of a few activities that were put on hold due to COVID 19 pandemic. Virtual engagement was one mitigative measure that was employed for most of component 3 activities. However, online approach have its limitations, for instance, it excluded participation of some of the key stakeholders like farmers in the coproduction process due to internet and technical challenges. A face to face engagement is most ideal for such workshops. As a result of these mitigative measures, all ACREI locations are receiving support for seasonal participatory climate advisory development for each important season, including translation into local languages. This is being conducted in collaboration with the national meteorological services of Ethiopia, Kenya and Uganda, being the institutions mandated to give climate information services at national and sub-national levels. One of the training on Participatory Integrated Climate Services for Agriculture (PICSA) which had been scheduled in March 2020, in Entebbe, Uganda, was postponed indefinitely due to the COVID 19 pandemic. This was necessary as most of the training sessions involves field visits and site demonstrations. Local media (particularly local radio stations) have been successfully engaged to support wider distribution of climate information in project target locations in Kenya and Uganda. More engagement is still needed in Uganda to make it more effective. Media engagement and training in Ethiopia was affected by the COVID situation and is being planned for 2021. Overall, there has been improved climate informed decision making in regional, national and sub-national institutions and the general rating for the component is satisfactory. The main next steps include: Holding PICSA training when the COVID 19 situation allows, preparation and validation of climate change projection for project sites, and continued implementation of key component 3 activities and supporting activities of component 1 and 2 for the final project year.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective | Number of beneficiaries received support for increased adaptive capacity to mitigate and respond to effects of climate change. | 0 | To be measured at endline | 45,000 direct beneficiaries through participation in CMDRR or as beneficiaries of investment grants. 9000 APFS household members/direct and targeted beneficiaries (min. 50% female) 40,000 indirect recipients of weather and climate information
| Percentage of targeted population with sustained climate-resilient alternative livelihoods. | 20% of direct target population implementing identified adaptation practices | To be measured at endline | 60% of direct target population with climate resilience livelihoods Alternative asset creation improved among 50% of target population.
| Percentage change in income (number, types and levels) among target population during periods affected by climate variability | US$193.5 (agricultural income averaged across the project locations from baseline survey) | To be measured at endline | A 40% increase in number, types, and/or levels among 80% of direct beneficiaries.
| Change in quality of climate related advisory to target population by the extension service. | Partially effective/ useful | To be measured at endline | Minimum 40% increase in satisfaction rates among direct and indirect beneficiaries with climate advisory services prior to the last extreme weather event.
Outcome 1 | Percentage change in crop/livestock yields among targeted households | See baseline report for yields of various crop and livestock products | To be measured at endline | 30% increase in crop/ livestock yields
| Percentage change in productivity of land, crop and livestock resources among targeted communities. | See baseline report for yields of various crop and livestock products | To be measured at endline | At least 50% increase
| Percentage of households adopting new or scaling up existing climate adaptation practices (including indigenous knowledge) | 0 | To be measured at endline | At least 30% adoption
| Percentage change in household incomes disaggregated by gender of household heads | US$193.5 (agricultural income averaged across the project locations from baseline survey) | To be measured at endline | At least by 50%
Outcome 2 | Number and type of targeted institutions with increased capacity to minimize exposure to climate variability risks | 0 | To be measured at endline | 30 institutions
| Percentage of extension workers (male and female) who are integrating adaptation strategies in their work at the community level | Assessments ongoing | Activity targeted for Year 2 | 80%
| Percentage of direct target population with reduced risk to climate variability and extremes | 0 | To be measured at endline | 70%
| No. of staff trained to respond to, and mitigate impact of, climate –related events (by gender). | 0 | To be measured at endline | 100 staff trained
Outcome 3 | Harmonized climate change response strategies for the region developed | 0 | To be assessed during final evaluation | Harmonised GHA Climate Change Strategy
| Percentage change in national budgets allocated to climate adaptation activities | 0 | To be assessed during final evaluation | 15% increase
| Percentage of households using tailored seasonal climate forecasts to plan their activities or enterprises | 0 (Households access some weather information, however tailored seasonal forecasts will be introduced through the project) | To be measured at endline | 70% increase
Output 1.1 | Number of community level adaptation action plans produced | 0 | Community adapotation planning conducted in all communities | 30 Community Adaptation Plans
| Number of staff trained in participatory community mobilization and planning processes. | 0 | Total: 137 Ethiopia: 31 Kenya: 33 Uganda: 73 | 60 staff trained
Output 1.2 | Number of participatory technology developments sites/structures linked to climate change adaptation | 0 | Ongoing | 60 PTDs documented
| Number of field days conducted by APFS on climate change adaptation | 0 | Ongoing | At least 60 field days
| Number of APFS groups in place and applying climate change adaptation knowledge. | 0 | Total: 62 groups Ethiopia: 20 groups, Kenya: 22 groups, Uganda: 20 groups | 60 groups in place applying adaptation practices
Output 1.3 | Number of communities trained in climate change adaptation proposal development | 0 | 30 communities trained and supported. | 30 communities trained.
| Number of community adaptation proposals developed | 0 | Ongoing | 30 community adaptation proposals submitted
| Percentage of approved, climate adaptation proposals, funded and implemented | 0 | Year 2 & 3 activity | At least 80% of submitted proposals funded and implemented.
Output 1.4 | Number of intra-country FS visits conducted | 0 | Delayed | 60 Visits
| Number of inter-country FS visits conducted | 0 | Delayed | 3 Visits
| Number of visibility and exposure events attended by target community members | 0 | Delayed | 6 events
Output 2.1 | No of national stakeholder mapping and capacity needs assessments undertaken | 0 | 3 stakeholder mapping & capacity needs assessments conducted (partnership with AFAAS) | 3
| No. of capacity development plans in place | 0 | 3 capacity development plans produced (partnership with AFAAS) | 3
Output 2.2 | Number of training manuals on climate adaptation strategies reviewed, modified and validated | 0 | One regional APFS manual produced (partnership with IIRR) | Updated APFS modules available in 3 countries
| Number of extensions actors (% female) who demonstrate an increase in knowledge and skills on climate-sensitive extension methodologies | 0 | To be measured at endline | 100 extension actors.
Output 2.3 | A knowledge and experience sharing platform for extension actors on climate proofing methodologies established | 0 | WMO and ICPAC websites curently being used, along with Whatsapp and Telegram Groups. Physical platform through PSP workshops & GHACOF also used. | ACREI Knowledge platform linked to existing platforms
| Number of community outreach forums on adaptation to climate change held and linked to the FS. | 0 | Delayed | 30 Community outreach forums
| Number of media-based partnerships developed for disseminating climate change adaptation information | 0 | Ethiopia: 0 Kenya: 3 radio stations Uganda: 0 (NB. This work is supported under Component 3 of ACREI) | At least 6 media partnerships
Output 2.4 | Proportion of identified FS service providers integrating climate related information in their FS implementation | 0 | To be measured at endline | At least 60%
| A generic climate module for FS practice developed | 0 | Delayed | 1 generic climate module
| Number of FS climate change adaptation issue papers developed | 0 | 1 paper published on ACREI baseline methodology | 3 issue papers
Output 3.1 | Number of livelihood zones with specific climate information generated and disseminated | 0 | 5 out of 5 ACREI districts | 5 Sub national units
| Number of target sub-national institutions provided with seasonal and/or enterprise-specific climate information | 0 | At least two government institutions and one NGO/ CBO per country | At least 6 government extension institution and 1 NGO or CBO receiving downscaled forecasts from Met agencies.
Output 3.2 | Number of FS with localized climate monitoring systems | 0 | Farmer representatives are included in the seasonal advisory development process and tasked with sharing information in their communities. Contact details and meeting times for all 60 FFS groups have been registered for exploring direct climate information dissemination. FFS rain gauge procurement also underway, under Component 1. | 60 FS groups by end of project
Output 3.3 | Number of National Agricultural Planners produced | 0 | Seasonal agroclimatic advisories produced as per indicator below. Three (3) historical climate data analysis conducted for all project locations identifying key climatic parameters such as average onset and cessation dates. | At least 4 seasonal planners developed per country
| Number of agro-climate advisories disseminated | 0 | 9 (four in Kenya for each of the main rainy seasons in 2019 and 2020, three in Uganda for JJA 2019, MAM2020 & OND2020) and two for Ethiopia for the JJA 2019 and 2020 season ) | At least 4
Output 3.4 | Number of good practices developed | 0 | Two (2) regional good practices developed - PSP process & S-MAP/ Media engagement | 6 (2 per country)
| Number of policy dialogues on climate change adaptation conducted | 0 | 3 (two at regional level and one at national level) | At least 4 ( national policy dialogue per country and 1 regional policy)
| Number of updates on food and nutrition security developed for advocacy and response | 0 | Being conducted by FSNWG which is led by ICPAC. ICPAC supports participants from ACREI sites to engage in seasonal meetings. | 24 monthly updates

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | - In Kenya where a sub-national meteorological officer is available at the County level (i.e. Kenya has a County Director of Meteorology present in the project location), this sub-national presence has facilitated the downscaling and dissemination of climate information and agroclimatic advisories. The project team is still working with the national staff in Uganda and Ethiopia to support local level generation and dissemination of climate information. Positive developments are that 1) in Uganda the National Meteorological Authority (UNMA) has begun a decentralisation process with deployment of staff to districts; and 2) In Ethiopia, the national level NMHS staff have prioritised ACREI locations for production of localised advisories and forecasts including in local languages. - The engagement of media as a stakeholder on the dissemination of climate information in Taita Taveta County, Kenya has yielded extremely positive results. Media partners have accepted this role and there has been a huge increase in information and programmes on weather, climate, and climate hazards targetting the County. Similar partnerships have been initiated in Uganda. The Ethiopia media engagement was affected by COVID. - Mainstreaming of agriculture and resilience issues in local media could be a cost efficient option for agricultural extension.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The delay in Year 2 is largely as a result of the COVID pandemic, which occured at a time when key aspects of the project were meant to be undertaken. The measures taken to reduce the delays included the following: - Where possible, some workshops and activities that were meant to be conducted in person, were replanned and conducted online using virtual conferencing platforms, although with shorter duration and limited participation in some cases. - Advocacy and awareness raising on the project has continued to be conducted online, including writing news stories and documentation of good practices. - When gatherings have been necessary, these are conducted with limited numbers and observing any local COVID-19 regulations for gatherings. - Working with locally based implementing partners.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No changes have been made to project Outputs in Year 2. The main aspect of change relates to delays in various activities as a result of the COVID pandemic but not to the project design.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | For the activities undertaken to date, the environmental and social safeguards have been adequate and as yet no negative impacts have emerged. However, the project involves USPs which are yet to be implemented.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | The project partners have undertaken the following measures in relation to gender considerations in the ACREI project: - Baseline survey tools were reviewed by FAO gender experts and had inclusion of sex-dissagregated data, questions on control and ownership of household assets, and questions on impacts of climate change and climate hazards on different household members. - Aiming for 50% participation of men and women in all trainings and project activities (including as participants and trainers). - Aim for 50% participation of women in project activities and 50% of project direct beneficiaries to be women, while also targeting specific project activities at women or women groups (for example the integrated savings and lending). - Foster equal participation of men and women in institutions and decision-making processes related to the project. Some lessons emerging from Year 2 relating to gender include the following: - Some activities tend to have greater participation of women than men while others tend to have greater participation of men. For example, local trainings often have good participation of women, however, trainings involving travel outside the community often have greater participation of men. - Womens participation in project activities and leadership positions varies from location to location and activity to activity. It is not always possible to ensure equal participation of men and women, however efforts for such are being made. To track these issues and their change over time, the endline survey for the project will include questions dissagregated by gender as well as gender specific questions on impacts of project activities. At present indicators related to gender, focusing on womens participation and empowerment, include the following: - Number of APFS groups in place and applying climate change adaptation knowledge. (target for 50% women) - Number of extension actors (% female) who demonstrate an increase in knowledge and skills on climate-sensitive extension methodologies - Percentage change in household incomes disaggregated by gender of household heads - Number of staff trained to respond to, and mitigate impact of, climate-related events (by gender). - Percentage of extension workers (male and female) who are integrating adaptation strategies in their work at the community level - 9000 APFS household members/direct and targeted beneficiaries (minimum 50% female)
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A
What measures are being/could have been put in place to improve project/program results? | N/A
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | N/A
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | N/A
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | N/A
If learning objectives have been established, have they been met? Please describe. | N/A
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | N/A
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | AFR/MIE/Food/2015/2
Implementing Entity | World Meteorological Organization (WMO)
Type of implementing entity | MIE
Country | Ethiopia, Kenya & Uganda
Region | Africa
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 94000 | 54000 | 40000 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 40000 | Drought | 2: Partially effective | Total | 40000 | Drought | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 100 | Agriculture | 2: Low capacity | Total | 100 | Agriculture | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 100 | 50% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 20% |  | Agriculture |  | 60 |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 40000 | 50% | 3: Partially aware |  | 40000 | 50% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Food security | Regional | 3: Moderately responsive (Some defined elements) |  | Food security | Regional | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
Community
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 10800 | 50% | 4: High improvement |  | 10800 | 50% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 6480 | 50% | From 30% to 40% | Agricultural-related | 6480 | 50% | From 30% to 40% | Agricultural-related
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies | Agriculture | Community-based adaptation | 30 | Adaptation strategies | Agriculture | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 10800 | Agricultural-related |  | 193.5 | 10800 | Agricultural-related |  | 40%
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Agriculture | Local | Other policy | 3 | Agriculture | Local | Other policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 2: Partially not enforced (Most elements not implemented) |  | 2: Partially effective | 3 | 3: Partially enforced (Some elements implemented) |  | 4: Effective