## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 30 August 2018 - 29 August 2019
| Project Title: | Agricultural Climate Resilience Enhancement Initiative (ACREI)
| Project Summary: | The Agricultural Climate Resilience Enhancement Initiative (ACREI) is a US$ 6.8 million project funded by the Adaptation Fund and implemented by the World Meteorological Organization (WMO) in partnership with the Food and Agriculture Organization (FAO) and the Intergovernmental Authority on Development (IGAD) Climate Prediction and Applications Centre (ICPAC). The ACREI project is the first regional project funded by the Adaptation Funded through its Pilot Programme for Regional Projects. The program targets Ethiopia, Kenya and Uganda and supports community adaption practice, climate proofing of extension systems and climate informed decision making. The project outcomes are: - Outcome 1. Sustainably enhanced agricultural productivity, production, livelihood diversification and income levels among targeted communities. - Outcome 2. Enhanced technical capacity of development and extension actors (national, sub-national, private sector, NGOs, CBOs) to support community level climate adaptation strategies - Outcome 3. Improved climate informed decision making in regional, national and sub-national institutions The goal of the initiative is to develop and implement adaptation strategies and measures that will strengthen the resilience of vulnerable smallholder farmers, agro-pastoralists and pastoralists in the Horn of Africa to climate variability and change. The overall objective of ACREI is improved adaptive capacity and resilience to current climate variability and change among targeted farmers, agro-pastoralists and pastoralist communities. The goals of the ACREI project are in line with the IGAD Drought Disaster Resilience and Sustainability Initiative (IDDRSI) programme, and with the overall vision of the African Ministerial Conference on Meteorology (AMCOMET), the inter-governmental body for the development of meteorology and its applications in Africa.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AFR/MIE/Food/2015/2 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | The World Meteorological Organization (WMO) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity (MIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Ethiopia, Kenya and Uganda | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Ethiopia - Kersa Woreda, East Hererghe Zone & Mieso Woreda, West Hererghe Zone Kenya - Taita Taveta County Uganda - Sembabule District & Isingiro District | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2017-03-17
IE-AFB Agreement Signature Date: |  | 2017-06-20 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2018-08-30 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | TBA - Since project was planned as a 3-year project.
| Terminal Evaluation Date: | TBC
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Project Inception Workshop Report (submitted to Adaptation Fund) Project brief by WMO (PDF available) Project fliers by ICPAC (PDF available) Project story by Adaptation Fund: https://www.adaptation-fund.org/adaptation-fund-project-story-regional-project-in-ethiopia-kenya-and-uganda/ Regional projects video by Adaptation Fund: https://youtu.be/UWUgHC-Av4c Various news stories: - WMO: https://public.wmo.int/en/media/news/new-initiative-boost-smallholders’-climate-resilience-horn-of-africa - FAO: http://www.fao.org/africa/news/detail-news/en/c/1151587/ - ICPAC: http://icpac.net/wp-content/uploads/PR_ACREI---Strengthening-the-resilience-of-vulnerable-smallholder-farmers_2018-09-05_Final_Clean-AMCOMET.pdf - IGAD Center for Pastoral Areas and Livestock Development (ICPALD): https://icpald.org/new-initiative-to-boost-smallholders-climate-resilience-in-the-horn-of-africa/ | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | - https://public.wmo.int/en/projects/agricultural-climate-resilience-enhancement-initiative - https://www.adaptation-fund.org/project/agricultural-climate-resilience-enhancement-initiative-acrei-ethiopia-kenya-uganda/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
Project Manager/Coordinator |  |  | Dominica
| Name: | Sebastian Grey, World Meteorological Organization (WMO), Sub-regional Office for Eastern and Southern Africa | Dominican Republic
| Email: | SGrey@wmo.int | Ecuador
| Date: | 2019-10-28 | Egypt
| Government DA Ethiopia |  | El Salvador
| Name: | H.E. Mr. Kare Chawicha Debessa, State Minister, Ministry of Environment and Forest (at time of project approval) | Equatoral Guinea
| Email: | eenvironment@gmail.com | Eritrea
| Date: | 2017-02-01 | Estonia
| Government DA Kenya |  | El Salvador
| Name: | Mr. Charles T. Sunkuli, Principal Secretary, State Department of Environment & Regional Development Authorities, Ministry of Environment and Forestry, Kenya (at time of project approval) | Equatoral Guinea
| Email: | psoffice@environment.go.ke | Eritrea
| Date: | 2017-02-03 | Estonia
| Government DA Uganda |  | El Salvador
| Name: | Mr. Keith Muhakanizi, Permanent Secretary / Secretary to the Treasury, Ministry of Finance, Planning and Economic Development | Equatoral Guinea
| Email: | finance@finance.go.ug | Eritrea
| Date: | 2017-01-16 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Jean-Paul Gaudechoux, Senior Programme Manager, WMO | Fiji
| Email: | jpgaudechoux@wmo.int | Finland
| Date: | 2019-10-28 | France
| Executing Agency |  | Gambia
| Name: | Cyril Ferrand, Resilience Team Leader, Food and Agriculture Organization of the United Nations (FAO), FAO Sub-Regional Resilience Team for Eastern Africa, Nairobi, Kenya | Georgia
| Email: | Cyril.Ferrand@fao.org | Germany
| Date: | 2019-10-28 | Ghana
| Executing Agency |  | Greece
| Name: | Dr. Guleid Artan, Intergovernmental Authority on Development (IGAD) Climate Prediction and Applications Centre (ICPAC), Nairobi, Kenya | Grenada
| Email: | gartan@icpac.net | Guatemala
| Date: | 2019-10-28 | Guinea
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 29 August 2019
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 29 August 2019 |  | 2064394
Add any comments on AF Grant Funds. (word limit=200) |  | Grant funds were well received and disbursements made to the Executing Entities, with FAO receiving their project funds in November 2018 and ICPAC receiving theirs in February 2019. The IE and EEs are utilising the project execution costs as indicated in the project document. One issue that has arisen is in regards to currency fluctuations. Funds received from Adaptation Fund are registered and maintained in CHF (in accordance to WMO financial regulations), with disbursements being made to partners in USD. However, it has been noted that currency exchange fluctuations between the USD and CHF can still have slight impacts on project funds. Between the time of the receipt of funds from the Adaptation Fund and disbursements being made to implementing partners, USD/CHF currency exchange fluctuations occured which negatively affected one executing entity's disbursement amount. The trust funds are being monitored and a plan put in place to ensure this does not occur for subsequent disbursements. To mitigate further currency fluctuation effects, future disbursements to partners are aimed to be conducted as quickly as possible after receipt of funds from the Adaptation Fund. Note that the initial delay between receipt of funds from Adaptation Fund and disbursements being made to partners was due to events outside WMO control and have been communicated to the Adapation Fund. Disbursed to FAO (including EE fees and execution costs) - US$1,250,261 Disbursed to ICPAC (including EE fees and execution costs) - US$377,807 Total disbursed to EEs = US$1,628,068 WMO expenditure (execution costs and activities) - US$355,261 WMO IE fees - US$81,065 Total up to end of August 2019 - US$2,064,394 Balance unspent and unobligated as at end of August - US$1,335,606 The disbursement schedules for the executing entities are as follows: ICPAC: Year 1: US$377,807.00 (already disbursed) Year 2: US$352,807.00 Year 3: US$317,806.00 Total: US$1,048,420 FAO: Year 1: US$1,250,261 (already disbursed) Year 2: US$3,077,067 Year 3: US$335,466.00 Total: US$4,662,794 The remaining balance from the first tranche, will be carried forward to committments to executing entities contracts for their Year 2 activities.
INVESTMENT INCOME |  | 2375.87
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT
Component 1 | Output 1.1 | 1.1.1 - 10 day training at sub-national level of Agric and Met staff on Participatory planning approaches | 40559
|  | 1.1.2 - Community sensitization, mobilization and launching of the community adaptation planning processes. | 15666.37
|  | 1.1.3 - Context analysis and stocktaking at community level | 3385.95
|  | 1.1.4 - Seasonal short term adaptation planning of 1-2 days in each target community | 80.8
|  | 1.1.5 - Longer term adaptation planning over a period of seven to ten days in each community | 11076.4 | Scheduled as a Year 2 activity, though some preparatory activities have begun.
|  | 1.1.6 - Validation of community adaptation plans | 0 | Year 2 activity
| Output 1.2 | 1.2.1 - Baseline and endline data collection | 36538.65
|  | 1.2.2 - 4-week training of facilitators (ToFs) courses on the APFS approach | 133262.83
|  | 1.2.3 - Community Ground working will be undertaken in each target community | 2134.44
|  | 1.2.4 - Facilitation of participatory learning in APFS group trough groups meeting on weekly basis over appr 1.5 years period | 42084.01
|  | 1.2.5 - Provision of learning materials package/grants to APFS groups | 0 | Year 2 activity
| Output 1.3 | 1.3.1 - Training of communities in village savings systems (VSLA/VICOBA) and financial management and support for establishment of community savings and banking schemes. | 0 | Year 2 activity
|  | 1.3.2 - Support to development of community adaptation investment proposal in target communities. | 33001.71 | Scheduled as a Year 2 activity, though some preparatory activities have begun.
|  | 1.3.3 - Technical review and screening of proposals through multi-sectoral proposal review group | 0 | Year 2 activity
|  | 1.3.4 - Community investment grant financing | 78138.33 | Scheduled as a Year 2 activity, though some preparatory activities have begun.
|  | 1.3.5 - Technical backstopping and monitoring of beneficiary community investment project implementation. | 285228.07 | Scheduled as a Year 2 activity, though some preparatory activities have begun.
| Output 1.4 | 1.4.1 - Within country community exchange visits | 0 | Year 2 activity
|  | 1.4.2 - Community and site participation in project review processes | 0 | Year 2 activity
|  | 1.4.3 - Participation in field days and agriculture shows/fairs but target communities | 0 | Year 2 activity
|  | 1.4.4 - Knowledge exchange coalitions for climate change adaptation | 58532.38 | Scheduled as a Year 2 activity, though some preparatory activities have begun.
Component 2 | Output 2.1 | 2.1.1 - Conduct stakeholder mapping and capacity needs assessment on integration of climate change in extension programmes at sub-national level. | 3784.88
|  | 2.1.2 - Development of a capacity development plan to integrate climate change in extension programmes at sub-national level. | 0
| Output 2.2 | 2.2.1 - Stocktaking and identification of actors | 0
|  | 2.2.2 - Review/Update FS training manuals on climate change adaptation best practices. | 0
|  | 2.2.3 - Workshop to validate the climate training curriculum and modules among key stakeholders followed by printing and dissemination of the curriculum | 0 | Year 2 activity
|  | 2.2.4 - National and sub-national training of extension actors on climate sensitive extension services. | 103142.14
| Output 2.3 | 2.3.1 - Establishment of a knowledge and experience sharing platform following review of existing information systems | 95180.98
|  | 2.3.2 - Dissemination of timely information on climate impacts and weather forecasts through selected community radio, social media and print channels. | 0
|  | 2.3.3 - Formation of dialogue groups for information exchange on climate adaptation. | 0 | Year 2 activity
| Output 2.4 | 2.4.1 - Awareness creation workshops among FS support actors | 27725.25 | Scheduled as a Year 2 activity, though some preparatory activities have begun.
|  | 2.4.2 - Development of a generic climate module for FS practice on climate change adaptation and ecosystem resilience strategies. | 0
|  | 2.4.3 - Refresher training of practicing Field School Master trainers in the region on the climate module and adaptation strategies | 5194 | Scheduled as a Year 2 activity, though some preparatory activities have begun.
|  | 2.4.4 - Lobbying and advocacy for climate sensitive FS | 4872.2
Component 3 | Output 3.1 | 3.1.1 - Improved tailored seasonal climate forecasts and climate change projections | 47861
|  | 3.1.2 - Training and capacity building in downscaling techniques and communication of uncertainties | 19577
|  | 3.1.3 - High resolution forecast downscaling to farming community level | 2459
|  | 3.1.4 - Establishment of historical climate baseline statistics, trends and historical and future climate change hotspots (areas of concern) for selected communities | 11031.51
| Output 3.2 | 3.2.1 - Database for intermediaries and famer users established | 4142.76
|  | 3.2.2 - Existing feedback mechanisms reviewed | 4586
|  | 3.2.3 - A cost effective communication and feedback channel designed, tested and validated | 0
| Output 3.3 | 3.3.1 - Seasonal agriculture planners regularly produced through national participatory planning workshops | 32005.5
|  | 3.3.2 - Continuous monitoring and evaluation | 58401.38
|  | 3.3.3 - Identified intermediaries trained in PICSA and PSP approaches | 11253
|  | 3.3.4 - Capacity for agro-met divisions at NMHS and ICPAC strengthened | 8224.45
|  | 3.3.5 - Advocacy and effective communication of project outcomes | 7050.77
| Output 3.4 | 3.4.1 - Documentation and dissemination of good practices and lessons learned on the use of climate information in agricultural decision making | 1314.6
|  | 3.4.2 - Conducting regional and national learning forums | 30590
|  | 3.4.3 - Improved regional food and nutrition security assessment coordination including capacity building on attribution of food insecurity to various climate related hazards. | 0
|  | 3.4.4 - Publication of key findings in peer-reviewed journals | 0 | Year 2 activity
|  | Execution costs | 363288.03
|  | TOTAL | 1581373.39
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
Component 1 | Output 1.1 | 1.1.1 - 10 day training at sub-national level of Agric and Met staff on Participatory planning approaches | 6316 | October 2019 (activity largely complete)
|  | 1.1.2 - Community sensitization, mobilization and launching of the community adaptation planning processes. | 833.63 | October 2019 (activity largely complete)
|  | 1.1.3 - Context analysis and stocktaking at community level | 11614.05 | 2019-12-01
|  | 1.1.4 - Seasonal short term adaptation planning of 1-2 days in each target community | 9919.2 | Seasonal and annual activity - ongoing up to end of project.
|  | 1.1.5 - longer term adaptation planning over a period of seven to ten days in each community | 42127.6 | 2020-02-01
|  | 1.1.6 - Validation of community adaptation plans | 27000 | 2020-03-01
| Output 1.2 | 1.2.1 - Baseline and endline data collection | 119461.35 | Baseline survey complete. Funds will be carried forward for regular monitoring and endline survey.
|  | 1.2.2 - 4-week training of facilitators (ToFs) courses on the APFS approach | 123237.17 | 2019-12-01
|  | 1.2.3 - Community Ground working will be undertaken in each target community | 16615.56 | October 2019 (activity largely complete)
|  | 1.2.4 - Facilitation of participatory learning in APFS group trough groups meeting on weekly basis over appr 1.5 years period | 38915.99 | Seasonal and annual activity - December 2020
|  | 1.2.5 - Provision of learning materials package/grants to APFS groups | 27000 | 2020-02-01
| Output 1.3 | 1.3.1 - Training of communities in village savings systems (VSLA/VICOBA) and financial management and support for establishment of community savings and banking schemes. | 24000 | 2020-06-01
|  | 1.3.2 - Support to development of community adaptation investment proposal in target communities. | 61998.29 | 2020-02-01
|  | 1.3.3 - Technical review and screening of proposals through multi-sectoral proposal review group | 30000 | 2020-03-01
|  | 1.3.4 - Community investment grant financing | 1692861.67 | 2020-08-01
|  | 1.3.5 - Technical backstopping and monitoring of beneficiary community investment project implementation. | 62030.93 | Ongoing through to end of project
| Output 1.4 | 1.4.1 - Within country community exchange visits | 26250 | 2020-11-01
|  | 1.4.2 - Community and site participation in project review processes | 3000 | 2020-08-01
|  | 1.4.3 - Participation in field days and agriculture shows/fairs but target communities | 18240 | Seasonal and annual activity
|  | 1.4.4 - Knowledge exchange coalitions for climate change adaptation | 0 | Ongoing through to end of project
Component 2 | Output 2.1 | 2.1.1 - Conduct stakeholder mapping and capacity needs assessment on integration of climate change in extension programmes at sub-national level. | 51257.12 | 2019-12-01
|  | 2.1.2 - Development of a capacity development plan to integrate climate change in extension programmes at sub-national level. | 30000 | 2020-01-01
| Output 2.2 | 2.2.1 - Stocktaking and identification of actors | 0 | Ongoing - No cost
|  | 2.2.2 - Review/Update FS training manuals on climate change adaptation best practices. | 87000 | 2019-12-01
|  | 2.2.3 - Workshop to validate the climate training curriculum and modules among key stakeholders followed by printing and dissemination of the curriculum | 68103 | 2020-03-01
|  | 2.2.4 - National and sub-national training of extension actors on climate sensitive extension services. | 171657.86 | Initally budgeted under Year 1, however for the rational flow of project activities this has been agreed to be moved to Year 2 activity - August 2020
| Output 2.3 | 2.3.1 - Establishment of a knowledge and experience sharing platform following review of existing information systems | 168649.02 | 2020-08-01
|  | 2.3.2 - Dissemination of timely information on climate impacts and weather forecasts through selected community radio, social media and print channels. | 63000 | Initially budgeted under Year 1, however, in consultation with the National Meteorological and Hydrological Services (NMHSs) this has now been planned to be utilised in Year 2 and 3.
|  | 2.3.3 - Formation of dialogue groups for information exchange on climate adaptation. | 36368 | 2020-08-01
| Output 2.4 | 2.4.1 - Awareness creation workshops among FS support actors | 68274.75 | 2020-03-01
|  | 2.4.2 - Development of a generic climate module for FS practice on climate change adaptation and ecosystem resilience strategies. | 74320 | 2020-05-01
|  | 2.4.3 - Refresher training of practicing Field School Master trainers in the region on the climate module and adaptation strategies | 101685 | 2020-08-01
|  | 2.4.4 - Lobbying and advocacy for climate sensitive FS | 22970.8 | Ongoing annual activity
Component 3 | Output 3.1 | 3.1.1 - Improved tailored seasonal climate forecasts and climate change projections | 72139 | Seasonal activity
|  | 3.1.2 - Training and capacity building in downscaling techniques and communication of uncertainties | 20423 | Seasonal and annual activity
|  | 3.1.3 - High resolution forecast downscaling to farming community level | 17541 | Seasonal and annual activity
|  | 3.1.4 - Establishment of historical climate baseline statistics, trends and historical and future climate change hotspots (areas of concern) for selected communities | 8968.49 | 2020-05-01
| Output 3.2 | 3.2.1 - Database for intermediaries and famer users established | 10857.24 | 2020-08-01
|  | 3.2.2 - Existing feedback mechanisms reviewed | 5414 | 2020-06-01
|  | 3.2.3 - A cost effective communication and feedback channel designed, tested and validated | 25000 | 2020-08-01
| Output 3.3 | 3.3.1 - Seasonal agriculture planners regularly produced through national participatory planning workshops | 47994.5 | Seasonal and annual activity
|  | 3.3.2 - Continuous monitoring and evaluation | 1598.62 | Ongoing activity up to end of project.
|  | 3.3.3 - Identified intermediaries trained in PICSA and PSP approaches | 18747 | 2020-05-01
|  | 3.3.4 - Capacity for agro-met divisions at NMHS and ICPAC strengthened | 91775.55 | Annual activity up to end of project. AWS procurement targetted for Year 2.
|  | 3.3.5 - Advocacy and effective communication of project outcomes | 104949.23 | Ongoing activity up to end of project.
| Output 3.4 | 3.4.1 - Documentation and dissemination of good practices and lessons learned on the use of climate information in agricultural decision making | 18685.4 | Ongoing activity up to end of project.
|  | 3.4.2 - Conducting regional and national learning forums | 49410 | Ongoing activity up to end of project.
|  | 3.4.3 - Improved regional food and nutrition security assessment coordination including capacity building on attribution of food insecurity to various climate related hazards. | 40000 | Ongoing activity up to end of project.
|  | 3.4.4 - Publication of key findings in peer-reviewed journals | 5000 | Ongoing through Year 2 and Year 3. Three papers currently being written.
|  | Execution costs | 159423.97 | Ongoing up to end of project.
|  | TOTAL | 3982633.99
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? |  | N/A
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  | Although no formal cofinancing was indicated, the project partners have engaged with other organisations conducting similar work in the target locations and have in some cases combined activities or leveraged on other funds to ensure project activities reach the most people. Examples include the following: 1 - Regional training on remote sensing for agricultural meteorology was conducted within the framework of ACREI targeting the ACREI country National Meteorological and Hydrological Services (NMHSs). A WMO partner organization, EUMETSAT, was engaged to support the participation of NMHS staff from outside of the ACREI countries, ensuring all 13 countries under ICPAC could be involved in this capacity building activity that was primarily conducted within the framework of the ACREI project. 2 - Participatory scenario planning being conducted ahead of each rainfall season in ACREI target locations has brought on board various stakeholders to support participants and farmers in their specific locations of work thus enabling wider reach of the climate information and advisories being generated under ACREI. In Kenya for example, synergies have been built with the Government of Kenya's Agriculture Sector Development Support Programme (ASDSP) and the DFID funded WISER Coastal Project to ensure coordination and wider impact of ACREI activities.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Different pace of project implementation for each country may delay overall project implementation and affect regional activities. | Low | Project structures have been formed at regional (PMT) and national level (PAG) to ensure the project moves at required pace and any key issues are raised and addressed as quickly as possible to enable implementation to proceed.
Uneven speed of implementation and expenditure rate among the three main partners may hamper overall project performance | Medium | Project structures have been formed at regional (Project Management Team (PMT)) and national level (Project Advisory Group (PAG)) to ensure the project moves at required pace and any key issues are raised and addressed as quickly as possible to enable implementation to proceed. Partners are meeting regularly to jointly plan and implement activities.
Irregularities with regards to relationships between executing and implementing bodies | Low | Standard WMO procedures have been used for partner agreements, including the use of Letters of Agreement, UN-to-UN agreements and Implementing Arrangements. WMO reporting requirements are being used for all partners to ensure project status information is regularly updated.
Sub-national governments prioritize alternative implementation frameworks. | Low | Partners have conducted inception missions to, and engaged local authorities in, all three countries at both national and sub-national level. All relevant stakeholders are aware of the project and are taking the project as a key initiative to build resilience and adaptive capacity in the project target locations.
Political uncertainties affect project implementation. | Low | Monitoring of the political and security context in all project target areas in partnership with key stakeholders is ongoing.
Limited awareness and stakeholder involvement on the project | Low | Partners have conducted inception missions to, and engaged local authorities in, all three countries at both national and sub-national level. All relevant stakeholders are aware of the project and are taking the project as a key initiative to build resilience and adaptive capacity in the project target locations.
Occurrence of a major natural disaster in the project areas. | Medium | Project partners continue to monitor the environmental context for any major hazard occurences, particularly in relation to climate hazards, of which the project goal is exactly to cushion and reduce the impacts of climate hazards.
Intercommunity differences regarding adaptation planning priorities in each community. | Low | Community based approaches will be used in all target communities. In particular, a community managed disaster risk reduction approach will be used and combined with participatory climate services approaches. Trainings on participatory approaches have been conducted for local stakeholders as part of the project.
Bias in awarding adaptation proposals. | Low | The project partners will jointly develop adaptation proposal review criteria in partnership with local authorities. The criteria will be developed based on lessons from FAO as well as small grants facilities (SGF) in other Adaptation Fund projects (e.g. South African National Biodiversity Institute (SANBI) project in South Africa).
Movement of trained staff to other sectors or outside the project areas. | Medium | A combination of strategies are being used to mitigate the potential of this risk occuring and reduce the magnitude of impact if it were to occur, including: 1 - Working with farmers directly through the farmer field school approach. 2 - Working with a wide variety of actors, including local organisations where possible, to ensure capacity remains in the project locations. 3 - Development of products that can be used beyond the project lifespan - e.g. training manuals. 4 - Working closely with the local government institutions responsible for agriculture and natural resources management.
Political influence affects adoption of lessons learned into national and regional adaptation strategies. | Low | Advocacy and stakeholder consultation, engagement and senistisation will be conducted throughout project implementation. Policy makers at sub-national level have been engaged and sensitised on the project, as well as being supported to participate in regional climate and food security fora, thus improving appreciation of the projects approach to climate resilience.
Governments continue to prioritize emergency initiatives over development initiatives. | Low | Advocacy and stakeholder consultation, engagement and sensitisation will be conducted throughout project implementation. Policy makers at sub-national level have been engaged and sensitised on the project, as well as being supported to participate in regional climate and food security fora, hence improving appreciation of the resilience building approach being used in the ACREI project.
Weak downscaling capacity to support the project. | Low | Building downscaling capacity is a key part of project implementation - ICPAC has ensured that all participating NMHSs from ACREI project countries are regularly involved in the seasonal forecast generation exercise at regional level, joint downscaling of the forecasts to sub-national level and conducting targetted training ahead of each season.
Limited coordination with other ongoing adaptation initiatives in the target countries. | Low | A review of ongoing initiatives has already been conducted. Consultation and engagement with stakeholders to ensure alignment and additionality to other programmes. In Kenya for example, good synergies have been found with ongoing government and development partner projects and programmes such as the Agriculture Sector development Support Programme (ASDSP) and the DFID funded WISER Coastal Project. Joint workshops have been held and a common approach to programming is being encouraged in consultation with the Taita Taveta CEC for Agriculture, Livestock, Fisheries and Irrigation.
Delays in recruitment or appointment of critical staff for the project. | Low | TORs for key staff developed and vacancy announcements were floated before official project commencement. The use of inhouse expertise among project partners and appointment of focal people from national institutions has been used as a strategy. All relevant staff are now onboard and supporting the project.
Instability in currencies, market prices and availability of project inputs | Medium | Funds received from Adaptation Fund are registered and maintained in CHF (in accordance to WMO financial regulations), with disbursements being made to partners in USD. However, it has been noted that currency exchange fluctuations between the USD and CHF can still have slight impacts on project funds. Between the time of the receipt of funds from the Adaptation Fund and disbursements being made to implementing partners, USD/CHF currency exchange fluctuations occured which negatively affected one executing entity's disbursement amount. The trust funds are being monitored and a plan put in place to ensure this does not occur for subsequent disbursements. To mitigate further currency fluctuation effects, future disbursements to partners are aimed to be conducted as quickly as possible after receipt of funds from the Adaptation Fund. Note that the initial delay between receipt of funds from Adaptation Fund and disbursements being made to partners was due to events outside WMO control and have been communicated to the Adapation Fund.
General financial risks | Low | WMO, FAO and ICPAC financial management procedures are being used to manage financial risks in all project activities and transactions.
Delays in financial disbursements | Low | The use of standard LoAs and UN-to-UN agreements to engage partners and ensure quick disbursement of funds.
Misuse of community financial grants at local level | Medium | Use of recognised community grant mechanisms based on FAO experience on such (e.g. grants mechanisms for Agropastoral Field Schools and the "Njaa Marufuku Kenya". This will be closely monitored in Year 2, when comunity grants begin.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
None at the moment. | N/A | N/A
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Risk mitigation measures as indicated above were employed, ensuring that the likelihood of occurrence of any risks remained the same or lower than at the time of project submission and did not affect project implementation. No major risks occured during the reporting period and no major issues have arisen. The management of risks has been facilitated through close and open lines of communications with project stakeholders as well as regular interaction among project partners at regional and national level.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1] | Under AF Board Decision for approval of ACREI project funding (Decision B.29/27), no ESP-related conditions were applied. However project partners have committed in the project document that: "Where identified adaptation investments are deemed to have potential negative environmental and social impacts, these will be subjected to further Environmental and Social Impact screening and analysis including the development of Environmental and Social Management Plans (ESMPs) and where required by law, Environmental Impact Assessments (IEAs). Adaptation investments with potential for large scale adverse environmental and social impacts (either at the project site or its surroundings) will not be conducted." | N/A | N/A - USPs and any associated ESMP where required will be identified and implemented beginning in Year 2.
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law | Yes | No | Lack of compliance with local and national laws in project activities. | Avoidance: The final project design will be compliant with all relevant regional and national laws following extensive consultation with national and regional stakeholders. Avoidance: No adaptation investments (USPs or any project activities) will be conducted if they do not comply with local, national and international laws. | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | The final project design was made to be compliant with all relevant regional and national laws following extensive consultation with national and regional stakeholders. | The final project design was made to be compliant with all relevant regional and national laws following extensive consultation with national and regional stakeholders. Any measures related with adherence to local and national laws will be implemented in Year 2 and Year 3 following identification of USPs. | None at the moment. | None at the moment.
2 - Access and equity | Yes | No | Lack of equity in access to project resources and activities. | Management, mitigation and avoidance: Given that the project will involve the development of shared community resources the project team will ensure that any activities or developments do not negatively affect current user rights to shared natural resources as well as ensuring equitable benefits from adaptation investments and other project activities. Any activities involving shared resources will be conducted in the context of the Voluntary Guidelines on the Responsible Governance of Tenure of Land, Fisheries and Forests in the Context of National Food Security (VGGT) and the relevant national laws. | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | From the baseline survey: - There is diparity between mens and womens ownership of resilience assets. Ensuring gender equity in access to project resources will be a major area of focus during project implementation. - One project site in Uganda, being a refugee host community, has high disparity between host community households and refugee households in terms of access to assets, trainings, adaptation practices and agricultural income. | - A conflict sensitivity review of the ACREI project was conducted by FAO with the main reccomendation being that "conflict-sensitive programming could cause significant positive shifts in peace and conflict dynamics and trends, and have a positive impact on food and nutrition security". Conflict sensitive programming will be integrated in various aspects of the project beginning in Year 2, particularly the community adaptation planning. - Further measures will be implemented in Year 2 and Year 3. | None at the moment. | None at the moment.
3 – Marginalized and vulnerable Groups | Yes | No | Exclusion of marginalised and vulnerable groups from project activities. | Management, mitigation & avoidance: The project will specifically target the most vulnerable and food insecure members of society in the target communities. Management: Ensure participation of all relevant stakeholders in project activities without discrimination and with aim to ensure fair and equitable access to project benefits including for women and men as well as marginalized groups. Management: Utilise proven community based adaptation planning methodologies that take into account the needs of different socio-economic groups in the community. Management, mitigation & avoidance: Conduct comprehensive community level consultations in the target districts, including with vulnerable groups, female headed households and key informants such as traditional forecast providers. Management: Aim to ensure that project activities target and support the most vulnerable to become more resilient to climate change including women, women headed households, children and the youth. | Minutes/ reports of consultations with local authorities on communityselection. | From the baseline survey: - There is diparity between mens and womens ownership of resilience assets. Ensuring gender equity in access to project resources will be a major area of focus during project implementation. - One project site in Uganda, being a refugee host community, has high disparity between host community households and refugee households in terms of access to assets, trainings, adaptation practices and agricultural income. - Knowledge on the gendered impacts of climate hazards and climate change is low. Awareness on this aspect will be supported through the community based planning pocesses and various trainings. | - Identification of target communities has been undertaken in conjunction with local authorities in all countries based on agreed upon criteria related to climate vulnerability, history of being affected by climate related events, income and food security classification, and presence (or rather lack) of large scale agricultural adaptation support. - One selected project location in Uganda is a refugee host community, therefore contributing to targetting of the most vulnerable. - Training of Ministry of Agriculture and National Meteorological and Hydrological Services (NMHS) staff on participatory planning approaches began in August 2019. This is expected to enhance sensitivity on the needs of different socio-economic groups in the community in relation to project activities. - Further measures will be implemented in Year 2 and Year 3. | None at the moment. | None at the moment.
4 – Human rights | No | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 – Gender equality and women’s empowerment | Yes | No | Lack of gender equity and women’s empowerment in project implementation and outcomes. | Management, mitigation & avoidance: - Baseline with sex disaggregated data and gender specific questions - Use participatory tools for gender sensitive community consultation and the FAO Self-evaluation and Holistic Assessment to Climate Resilience of Farmers and Pastoralists (SHARP). - Use tools developed by FAO and partners for integrating gender in climate-smart agriculture (http://www.fao.org/3/a-i5299e.pdf and http://www.fao.org/3/a-az917e.pdf). - Aim for 50% participation of women in project activities and 50% of project direct beneficiaries to be women, while also targeting specific project activities at women or women groups (for example the integrated savings and lending). - Foster equal participation of men and women in institutions and decision-making processes related to the project. | Participation of men and women in project activities and structures (see project LogFrame). | - There is disparity between mens and womens ownership of resilience assets. Ensuring gender equity in access to project resources will be a major area of focus during project implementation. - Knowledge on the gendered impacts of climate hazards and climate change is low. Awarenes on this aspect will be supported through the community based plannin pocesses and various trainings. - Womens participation in project activities and leadership positions varies from location to location and activity to activity. See the GP Compliance sheet for more details on gender issues arising in the project. | - The baseline survey has incorporated sex-dissagregated data and has useful information on the climate change adaptation needs and constraints of both men and women. Interesting findings have emerged regarding controll over assets by men and women, knowledge on climate change adaptation and ability to adapt to climate change. - Engagement of FAO Country Office gender focal points in project planning meetings and in review of documents to ensure incorporation of gender aspects. - Farmers field school groups incoporate both men and women, both as members and as group leaders. In some cases the 50% target is exceeded, however in other cases it is not always possible. The partners continue to strive for greater participation of women in such activities as well as identifying any barriers to their participation so project activities can be adjust to account. - All workshops and trainings have incorporated both men and women as participants and as facilitators/ trainers, with the need for gender balance and having women in key roles highlighted. | None | N/A
6 – Core labour rights | No | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 – Indigenous peoples | No | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 – Involuntary resettlement | No | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 – Protection of natural habitats | Yes | No | Damage to natural habitats (as a result of project activities). | Avoidance: The project partners, through broad stakeholder consultation and engagement, will ensure that adaptation investments do not encroach onto protected areas, buffer zones and natural habitats. Avoidance, management & mitigation: Climate change adaptation investments will be screened for negative impact on adjacent ecosystems and natural habitats. | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | Population growth, resources scarcity, land degradation, low productivity (both livestock and crops), overgrazing, deforestation, invasive species and market fluctuations among others affect the project locations. Adaptation investments/ USPs and specific basleine information related to them are yet to be identified through community based approaches in Year 2 of the project. | Measures will be implemented largely in Year 2 when USPs are identified and begun. | None at the moment. | None at the moment.
10 – Conservation of biological diversity | Yes | No | Biodiversity loss (as a result of project activities). | Management & mitigation: A climate-smart agriculture approach will be utilised to ensure that the project does not in any way contribute to biodiversity loss. Through the climate-smart agriculture approach the project will in fact improve biodiversity in crop and livestock production as a means of improving agro-ecosystem resilience to climate change and weather variability. The climate smart agricultural approach will improve biodiversity due to diversification of livelihoods, crops and livestock breeds and introduction of improved agroforestry species. Management, avoidance and mitigation: The project will foster capacity building and farmer to farmer learning so as to enhance responsible and effective governance of natural resources including land, pasture, water, soils and forests. Avoidance: The project will not involve or entertain introduction of invasive species or new pests and diseases into the project sites and any actions that may result in these will be appropriately screened and subjected to the relevant national and international laws and guidelines. | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | Population growth, resources scarcity, land degradation, low productivity (both livestock and crops), overgrazing, deforestation, invasive species and market fluctuations among others affect the project locations. Adaptation investments/ USPs and specific basleine information related to them are yet to be identified through community based approaches in Year 2 of the project. | Measures will be implemented largely in Year 2 when USPs are identified and begun. | None at the moment. | None at the moment.
11 – Climate change | No | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 – Pollution prevention and resource efficiency | Yes | No | Pollution and lack of efficiency in use of natural resources. | Management, avoidance & mitigation: The project will where possible, promote techniques such as Integrated Pest and Disease Management (IPDM) as a pillar of sustainable agriculture, reduce reliance on pesticides and avoid adverse impacts from chemical use on the health and safety of farming communities, consumers and the environment. Management: The climate-smart agriculture practices promoted through the project will also reduce soil erosion and hence reduce water pollution. Management: As part of the climate-smart agriculture approach to be used in the project, maximising efficiency in the use of natural resources will play a major role in supporting improved productivity and food security as well as supporting climate change adaptation. Management, mitigation & avoidance: Mitigation benefits will also be realised by reducing emission’s intensity, reducing waste by improving the timing and application of inputs, and ultimately increasing crop and livestock productivity per unit of inputs (and emissions). | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | Population growth, resources scarcity, land degradation, low productivity (both livestock and crops), overgrazing, deforestation, invasive species and market fluctuations among others affect the project locations. Adaptation investments/ USPs and specific basleine information related to them are yet to be identified through community based approaches in Year 2 of the project. | Measures will be implemented largely in Year 2 when USPs are identified and begun. | None at the moment. | None at the moment.
13 – Public health | No | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 – Physical and cultural heritage | No | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 – Lands and soil conservation | Yes | No | Land and soil degradation | Management & mitigation: The project will promote improved agricultural practices such as soil and water conservation practices (like minimum or zero tillage, contour ridging, increased use of organic manure). Water harvesting and irrigation, bush fallowing, agro-forestry, diversified agriculture including apiculture and plantation agriculture; and rotational grazing, programmed reseeding of degraded rangelands among pastoral and agro-pastoral communities, etc. will be encouraged and promoted by the project. | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | Population growth, resources scarcity, land degradation, low productivity (both livestock and crops), overgrazing, deforestation, invasive species and market fluctuations among others affect the project locations. Adaptation investments/ USPs and specific basleine information related to them are yet to be identified through community based approaches in Year 2 of the project. | Measures will be implemented largely in Year 2 when USPs are identified and begun. | None at the moment. | None at the moment.
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Monitoring of ESP risks is ongoing as part of project activities.
Have unanticipated ESP risks been identified during the reporting period? |  | Community based adaptation action planning will be conducted in Year 2, which will include aspects of identification of environmental and social risks related to the yet to be identified USPs.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant? |  | Yes
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | N/A - These will be implemented largely in Year 2 when USPs are identified and begun.
Have the implementation arrangements been effective during the reporting period? |  | N/A - These will be implemented largely in Year 2 when USPs are identified and begun.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | N/A - These will be implemented largely in Year 2 when USPs are identified and begun.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | N/A - These will be implemented largely in Year 2 when USPs are identified and begun.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10] |  | Partially
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | The capacity for ESMP at the IE and the EEs is adequate based on their experience implementing similar projects and programmes. The Food and Agriculture Organization (FAO) which is responsible for the community-related and and adaptation grants components of the project have Environmental and Social Management Guidelines as well as principles for sustainable food and agriculture systems which aim to balance economic, social and environmental dimensions of sustainability in agriculture and food systems, and provide a basis for developing policies, regulations and incentives to guide the transition to sustainability, while promoting resilience through an adaptive response to shocks and opportunities. In terms of roles and responsibilities, WMO as the IE, will through the project manager ensure that partners are aware of the Adaptation Funds Environmental and Social Policy and take actions to ensure it is implemented. FAO as the excuting entity responsible for implementing the USPs and other community-level activities, will be the primary means through which ESP issues are implemented. All relevant human resources have been engaged either directly on the project or as technical support already within the partner organizations. Additional resources will be engaged and responsibilities defined as required to support ESMP implementation. This includes engaging WMO, FAO and ICPAC technical staff at national, regional and HQ levels with expertise on aspects such as gender, conflict sensitive programming and accountability. As examples: - 1) FAO gender focal points have been involved in ensuring gender considerations are included in project activities. - 2) FAO experts on conflict sensitive programming have reviewed ACREI activities and provided guidance on enhancing conflict sensitivity during project implementation. Outstanding arrangements for compliance with Adaptation Fund ESMP include: - 1) The IE will make presentations on environmental and social policy at suitable partner meetings in all three countries. - 2) Field implementation teams are to hold discussions on environmental and social impacts (both positive and negative) when developing community adaptation plans. - 3) The adaptation investment (USP) development guidance will include a checklist/ screening for environmental and social issues, including gender. - 4) Technical multi-stakeholder committees reviewing USPs will also consider the potential of each investment for negative environmental and social impacts. - 5). Aadequate disclosure of the identified adaptation investments (through meetings with local leadership and communities). - 6) Sharing of a known locally appropriate grievance mechanism (through effective feedback channels) in each of the target communities for allowing registering of ESMP-related complaints. - 7) Continued sensitization and awareness raising on environmental and social impacts (positive and negative) during project activities. These arrangements will be conducted in accordance with AF Guidance on USPs (https://www.adaptation-fund.org/wp-content/uploads/2019/04/AFB.B.32-33.7_Compliance-with-ESP_Update-of-PPR_and_Guidance-for-USPs_revised-1.pdf) In terms of dealing with ESP risks, the heirarchy will be 1) avoidance, and 2) management of negative environmental and social impacts. Adaptation investments with potential for large scale adverse environmental and social impacts (either at the project site or its surroundings) will not be conducted.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11] |  | The community adaptation planning process, in which USPs are to be formulated, is scheduled to be undertaken in Year 2. The IE and EEs will ensure that all ESP issues are analysed and appropriately incoprorated into the ESMP submitted with the initial project proposal. The IE has also gathered lessons from other Adaptation Fund projects including the SANBI Small Grants facility project and its "Risk dashboard Guideline Document To Inform Detection and Management of Environmental and Social Risks in Projects and programmes funded by the Adaptation Fund".
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP] | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2.
USP 2: [name the USP] | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2.
USP 3: [name the USP] | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2.
USP 4: [name the USP] | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2.
USP 5: [name the USP] | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2. | N/A - USPs will be identified and implemented in Year 2.
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts? |  | Partially
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Given that the project contains USPs, the grievance mechanism will be fully implemented as the USPs are identified and implemented. As indicated in the project document, key aspects of the grievence mechanism will include the following: 1) Disclosure for any adaptation investments with potential negative environmental and social impacts and the plans for their management. 2) Introduction of a mechanism for stakeholders to communicate and get feedback on any problems regarding project implementation including problems related to environmental and social impacts. The farmer field school groups and their leadership provide the main channel for grievances related to enviroenmental and social impacts of the project as well as gender and other matters. In addition, partner staff have shared contact details and open channels for communication exist between the project partners and stakeholders from national to local level. To date no grievences have been received. |  | Given that the project contains USPs, the grievance mechanism will be fully implemented as the USPs are identified and implemented. To date no grievences have been received.

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Gender considerations were taken into account during project formulation including highlighting the following aspects for ensuring integration of gender equity and womens empowerment in project implementation and outcomes: 1) Baseline with sex disaggregated data and gender specific questions. 2) Use of participatory tools for gender sensitive community consultation and the FAO Self-evaluation and Holistic Assessment to Climate Resilience of Farmers and Pastoralists (SHARP). 3) Use tools developed by FAO and partners for integrating gender in climate-smart agriculture (http://www.fao.org/3/a-i5299e.pdf and http://www.fao.org/3/a-az917e.pdf). 4) Aim for 50% participation of women in project activities and 50% of project direct beneficiaries to be women, while also targeting specific project activities at women or women groups (for example the integrated savings and lending). 5) Foster equal participation of men and women in institutions and decision-making processes related to the project.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes. The results framework includes indicators at Objective, Outcome and Output level which either refer to targets for womens participation or to gender dissagregated data.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Number of APFS groups in place and applying climate change adaptation knowledge. (target for 50% women) | Output | % women | 0 | 50% | Satisfactory
Number of extension actors (% female) who demonstrate an increase in knowledge and skills on climate-sensitive extension methodologies | Output | % women | 0 | 50% | To be measured at endline.
Percentage change in household incomes disaggregated by gender of household heads | Outcome | % women | 0 | 50% | To be measured at endline.
No. of staff trained to respond to, and mitigate impact of, climate-related events (by gender). | Outcome | % women | 0 | 50% | Year 2 activity
Percentage of extension workers (male and female) who are integrating adaptation strategies in their work at the community level | Outcome | % women | 0 | 50% | To be measured at endline.
9000 APFS household members/direct and targeted beneficiaries (min. 50% female) | Objective | % women | 0 | 50% | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
N/A - to be completed for final PPR as per guidance. |  | N/A - to be completed for final PPR as per guidance notes.
N/A - to be completed for final PPR as per guidance. |  | N/A - to be completed for final PPR as per guidance notes.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Implementing Entity and Executing Enities, have all made efforts to comply with the key concepts of the AF Gender Policy, including gender equity, gender mainstreaming, gender responsiveness, gender sensitivity and women's empowerment. In particular the following aspects have been put in place to ensure compliance with the AF gender policy: 1 - Ensuring that the household baseline incorporated sex disaggregated data and gender specific questions. 2 - Encouraging project partners/ executing entities to hold gender sensitive consultations and assessments, for example holding seperate focus group discussions for men and women, therefore allowing womens views to be better captured without being overshadowed by men. 3 - Ensuring that the Regional Inception Workshop had participation of both men and women. 4 - Ensuring that gender issues were discussed at Inception and during workplanning - for example, the question of how activities are designed so as not to discourage full participation of women arose during the inception.
Have the implementation arrangements at the IE been effective during the reporting period? |  | The implementation arrangements for Gender Policy compliance have been effective. Discussions on gender issues were held during project inception and work planning, with the following outcomes and agreements: 1) all partners to consider the specific needs and constraints of womens participation in project activities; 2) track gender indicators in all activities; 3) aim for equal participation of women in project activities and activity leadership structures; and 4) capture sex-dissagregated data for the baseline and other assessments and activities. This has laid the foundation for effective Gender Policy implementation in the project.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | Food and Agriculture Organization (FAO) of the United Nations: - The baseline survey has incorporated sex-dissagregated data and has useful information on the climate change adaptation needs and constraints of both men and women. - The baseline survey has also had question incoporated on the climate-related needs, challenges and impacts oin relation to men and women. Interesting findings have emerged regarding control over assets by men and women, knowledge on climate change adaptation and ability to adapt to climate change. - Engagement of FAO Country Office gender focal points, where available, in project planning meetings and on review of documents to ensure incorporation of gender aspects. - Continuous sensitisation on participation of both men and women when sending activity invitations; project focal persons are encouraged to be a mix of both men and women; and overall continuous awareness raising on the need for womensparticipation throughout all the project activities. - Workshops and trainings have involved both men and women as participants and as facilitators/ trainers. In Uganda, trainings on participatory planning approaches involved 46% women. In Kenya, however farmer field school facilitator trainings incorporated just 15% women and this is an area for future improvement. - Farmers field school (FFS) groups incorporate both men and women, and a concerted effort has been made to ensure equal participation of women in these groups and their leadership structures. In Ethiopia, the leadership of FFS groups is 32% women. In Uganda, the FFs groups are comprised of 61% women and the leadership of the groups is 58% women.
IGAD Climate Predictions and Applications Centre (ICPAC): - Continuous sensitisation on participation of both men and women when identifying participants for project activities; project focal persons are encouraged to be a mix of both men and women; and overall continuous awareness raising on the need for womens participation throughout all the project activities. - All trainings have incorporated both men and women as participants and as facilitators/ trainers. Information specific to men and women has been gathered through this method. - Assessments involving focus group discussions have been structured to cater for separate discussions with men and women. The facilitators of the focus group discussions were equally male and female (1:1 ratio). - Fifty seven percent of participants of the participatory scenario planning (PSP) exercise held in Kenya for the March-April-May 2019 season in Taita Taveta, Kenya were female, however the percentage reduced to 34% during the October-November-December (OND) PSP exercise. Percentages are expected to vary from workshop to workshop and place to place, however ICPAC continues to emphasise the participation of women and their leadership roles in project activities. - Twenty six percent of the participants in the media training in Taita Taveta, Kenya were female.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | The implementation arrangements for Gender Policy compliance have been effective in some cases but not in others. Womens participation in project activities, as well as their engagement in leadership and training roles has been mixed. In some cases womens participation is higher than the targetted 50% and in other cases womens participation has been lower than the targetted 50%. The effectiveness of the EEs efforts has also varied from country-to-country and activity to activity. Overall, it is not always possible to meet the targets for womens participation and engagement in leadership roles; however the EEs will continue to emphasise this aspect among stakeholders.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | At the moment no major capacity gaps affecting Gender Policy compliance have been identified at the IE or the EEs. The capacity for adherence to the Gender Policy is adequate among the IE and EEs. However, it is not always possible to meet the targets for womens' participation and engagement in leadership roles; and there seems to be a gap when it comes to the availability of female technical staff in the target locations. However, the EEs will continue to engage with the stakeholders on the importance of gender issues and the participation of both men and women.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8] |  | Partially The farmer field school groups and their leadership structures provide the main channel for grievances related to gender and other matters. Given that the project contains USPs, the grievance mechanism related to gender equality and womens empowerment will be fully implemented as the USPs are identified and implemented.
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances relating to gender matters have been received in the reporting period. |  | No grievances relating to gender matters have been received in the reporting period.
However, at the inception workshop, stakeholders emphasised that gender issues need to be carefully considered when planning trainings and other project activities. For example, stakeholders indicated that in some cases all day long and/or month-long trainings and activities may not be conducive for women’s participation. It was suggested that trainings be broken down into sessions of short duration. |  | This issue was raised at the project inception workshop, where the IE and EEs were present and thus could immediately take note of the issue for action. This issue was accepted by all project partners as being of critical importance and agreed that beginning with the baseline survey, efforts would be made to ensure consieration of the needs and challenges of women, through the measures indicated in the project document and others to be identified with support of institutional gender focal points where available.

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Overall project management and coordination: 1. Regional inception workshop; 2. Disbursements to executing entities; 3. Stakeholder sensitisation in all three countries; 4. Communities for adaptation actions identified; 5. Project implementation structures at regional, national and sub-national level in place. |  | Stakeholder engagement and sensitisation, and project implementation structures in place by end of 2018. Target was to begin activities by the first rainy season of 2019 (i.e. March-April-May 2019 season). |  | 1) Regional inception workshop held 30-31 August 2018. 2) Agreements signed and disbursements made to both executing entities (FAO and ICPAC) to enable them to implement their activities - FAO in November 2018 and ICPAC in February 2019. 3) Joint partner inception missions have been held to all 3 project countries, and meetings held with key stakeholders. 4) Locations for community based activities have been identified in partnership with local authorities and stakeholders. 5) Project implementation structures have been put in place at regional, national and sub-national level with agreed upon terms of reference (TORs). The project management team (PMT) at regional level is meeting regularly and all three countries have held national project advisory group (PAG) meetings. | Satisfactory (S)
| Component 1: 1. Household baseline survey complete in all target locations. 2. Community sensitisation and mobilisation conducted. 3. 60 field school groups in place. 4. 60 extension staff trained on participatory mobilization and planning approaches |  | 1. Baseline survey complete and reports available. 2. 10 communities for community based activities identified in consultation with local authorities, and sensitisation and community engagement begun. 3. 30 field school groups in place by end of Year 1, 10 in each country (i.e. half of project target) 4. One training conducted per country on participatory community mobilization and planning approaches |  | 1. The baseline survey has been completed in all three countries and draft reports are available. 2. Community sensitisation and mobilisation was successfully conducted in all three countries. This involved first engaging the local authorities on the identification of 10 communities per country, conducting joint scoping missions and collection of community characteristics and livelihood information. 3. Twenty eight (28) field school groups were in place by the end of Year 1. This includes 10 groups in Ethiopia and 18 groups in Uganda. The groups have an average of 32 members in Ethiopia, and between 20-35 members each in Uganda. This is in line with the initial project targets to have a total of 1800 field school group members being supported by the project. The remaining 32 groups will be formed in Year 2. 4. Three trainings (one per country) were conducted involving a total of over 130 participants drawn from government departments, NGOs and CBOs thus surpassing the initial target of having 60 government staff trained across the three countries. | Satisfactory (S)
| Component 2: 1. Stakeholder mapping and capacity needs assessments conducted for all 3 countries (Activity 2.1.1). 2. Capacity development plans for all three countries available on integration of climate change in extension practices (Activity 2.1.2). 3. Updated agropastoral field school manuals on climate change available in the 3 countries (Activity 2.2.2 and 2.2.3). 4. Generic module on climate information available by end of Year 2 (Activity 2.4.2). |  | Consultants/ service providers/ implementing partners identified and contracts issued for activities under Outputs 2.1, 2.2 and 2.4 by end of August 2019. As per the project document and budget these activities were meant to be done through either consultancies or contracts with a suitable actor. |  | Contracts for activities 2.1.1 and 2.1.2; and 2.2.2 and 2.2.3 (capacity assessments and capacity development plans on integrating climate change in agricultural extension; and farmer field school modules on climate change adaptation) were issued in August 2019 and the activities have begun. Activity 2.4.2 (Generic module on climate information) will be conducted by a consultant in Year 2, a delay that was due to the need to ensure adequate integration of the Participatory Integrated Climate Services for Agriculture (PICSA) methodology. Trainings of extension agents based on the above assessments and modules will be conducted in Year 2. | Satisfactory (S)
| Component 3: 1. Five sub-national units/ districts receiving localised seasonal climate information. 2. Six government institutions, 1 NGO/CBO receiving downscaled climate information. 3. 30 farmer field school groups receiving localised climate information by end of Year 2. 4. One seasonal planner/ advisory developed and distributed per country per year. 5. Two policy dialogues on climate information conducted in each country and one regional policy dialogue. |  | 1. Five sub-national units/ districts receiving localised seasonal climate information. 2. Seven government institutions and threeNGOs/CBOs reciving climate information. 3. FFS groups to begin receiving climate information in Year 2. 4. Seasonal advisories developed in all three countries for each important season. 5. Policy makers from all ACREI sub-locations supported to participate in regional climate outlook fora. |  | 1. Four out of five sub-national units are receiving localised seasonal climate information, with sites in Ethiopia and kenya also recicing support to translate the advisories into local languages (Kiswahili in Kenya and Oromifa and Ahmaric in Ethiopia). Three out of five of these sub-national units (in Ethiopia and Kenya)are also receiving weekly and 10-day forecasts through support of the ACREI project. 2. At least two government institutions in each country (ministries responsible for disasters, health, agriculture and livestock, health, veterinary services, waterand tourism) and one NGOs/CBOs are receiving climate information. In Kenya alone, seven government institutions and three NGOs/CBOs (Red Cross, World Vision and Wild Life Works) are receiving climate information through the ACREI project. In addition, media partners have been identified to support dissemination of the information to boader stakeholders in the project locations. This has resulted in the development of a Climate Information Media Action Plan in Kenya, which identifies the different media partners and their roles in dissemination of climate. Other countries will be supported to develop similar media partnerships in year 2. All countries will be expected to hold climate programmes hosted by identified media partners in each important season. 3. FFS groups are to begin receiving climate information in Year 2, however farmer representatives from ACREI target locations have been involved in seasonal participatory advisory development exercises. 4. Seasonal advisories are being developed in all three countries for each important season. 5. Policy makers from all ACREI sub-locations have been supported to participate in regional climate outlook fora (specifcially the Greater Horn of Africa Climate Outlook Fora - GHACOF). Policy brief generated from the climate baselines has been shared at the county parliament in Taita Taveta; County Climate coordination group created in Taita Taveta as a result of ACREI engagement with policy makers. | Satisfactory (S)
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Sebastian Grey, ACREI Project Officer, WMO Office for Eastern and Southern Africa
| Email: | sgrey@wmo.int
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project is proceeding well without major issues. It is expected that by the end of Year 2 major activities will be on schedule in line with milestones in the LogFrame, particularly for community-based activities under Component 1 and capacity building activities under Component 2. The project management team (PMT) at regional level is meeting regularly and all countries have held national project advisory group (PAG) meetings. Coordination between the implementing entity and executing entities has been good with regular meetings being held to ensure integration between project Components as well as at the different spatial scales (regional to local level). The inception workshop and joint partner sensitisation missions enhanced understanding on the role of national partners, including the national meteorological and hydrological services (NMHSs) and the ministries responsible for agriculture in the respective countries. National stakeholders have welcomed and committed their support to what is considered an innovative project for the region. Completion of baseline data collection and report writing (which will provide benchmarks to measure project impacts), community identification (10 per country for on-the-ground adaptation actions), and stakeholder sensitization, have been conducted and have laid the foundation for implementation of the project. The community and stakeholder trainings on adaptation action planning began towards the end of August, and will continue into the first quarter of Year 2. Note that the majority of Component 1 activities were scheduled for Year 2, particularly the community adaptation planning and the implementation of community adaptation grants, and this will be a major focus of the project going forward. Capacity assessments, stakeholder mapping, and updating of training materials have begun, with organisations having been contracted to conduct these activities. One activity on the development of a generic module on climate information will be undertaken by a consultant in Year 2. These assessments and manuals will enable various capacity building trainings in Year 2, including training of extension actors and farmer field school facilitators on climate change adaptation and climate information. Although the training of extension actors was initially budgeted under Year 1, the EEs and stakeholders agreed that these would best be conducted in Year 2 once the capacity assessments and various manuals are complete. Four out of five ACREI locations are being supported with seasonal participatory advisory development (including translation into local languages) for each important season (only one district in Uganda did not receive this support in Year 1). This is being conducted in collaboration with the national NMHSs, and have included participation of broad stakeholders. In Year 2 efforts will be made to ensure all 5 ACREI project locations receive participatory seasonal advisory development support, despite any distance hindrances. Local media (particularly local radio stations) have being successfully engaged to support wider distribution of climate information in project target locations. Main next steps include: 1) Finalising assessments and modules under Compnent 2; 2) ensuring both project sites in Uganda receive support for seasonal participatory advisory development; and 3) community adaptation planning and field school support.
| Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Overall project management and coordination: 1. Regonal inception workshop; 2. Disbursements to executing entities; 3. Stakeholder sensitisation in all three countries; 4. Communities for adaptation actions identified; 5. Project implementation structures at regional, national and sub-national level in place. |  | Iception workshop held, EE dibursements made, stakeholder engagement and sensitisation, and project implementation structures in place by end of 2018 so major activies could start before the first rainy season of 2019 (i.e. March-April-May 2019 season). |  | 1. Regional inception workshop held 30-31 August 2018. 2. Disbursements have been made to both executing entities (FAO and ICPAC) to enable them to implement their activities - FAO in November 2018 and ICPAC in February 2019. 3. Joint partner inception missions have been held to all 3 project countries, and meetings held with key stakeholders. 4. Locations for community based activities have been identified in partnership with local authorities and stakeholders. 5. Project implementation structures have been put in place at regional, national and sub-national level with agreed upon terms of reference (TORs). The project management team (PMT) at regional level is meeting regularly and all three countries have held national project advisory group (PAG) meetings. 6. Coordination between the implementing entity and executing entities has been good with regular meetings being held between the three. 7. The role of the national partners including the meteorological and hydrological services (NMHSs) and the ministries responsible for agriculture in the respective countries, has been enhanced following the project inception and the national stakeholders sensitisation missions. | Satisfactory (S)
| Component 1: 1. Household baseline survey complete in all target locations. 2. Community sensitisation and mobilisation conducted. 3. 60 field school groups in place. 4. 60 extension staff trained on participatory mobilization and planning approaches |  | 1. Baseline survey complete and reports available. 2. 10 communities for community based activities identified in consultation with local authorities, and sensitisation and community engagement begun. 3. 30 field school groups in place, 10 in each country (i.e. half of project target) 4. One training conducted per country on participatory community mobilization and planning approaches |  | 1. The baseline survey has been completed in all three countries and draft reports are available. 2. Community sensitisation and mobilisation was successfully conducted in all three countries. 3. Twenty-eight field school groups involving an average of 30 members each were in place by the end of Year 1. 4. Three trainings have been conducted (one per country) on partiocipatory comunity mobilisation and planning. These trainings have involved a total of over 130 participants drawn from government departnerts, NGOs and CBOs thus surpassing the initial target of having 60 government staff trained across the three countries. | Satisfactory (S)
| Component 2: 1. Stakeholder mapping and capacity needs assessments conducted for all 3 countries (Activity 2.1.1). 2. Capacity development plans for all three countries available on integration of climate change in extension practices (Activity 2.1.2). 3. Updated agropastoral field school manuals on climate change available in the 3 countries (Activity 2.2.2 and 2.2.3). 4. Generic module on climate information available by end of Year 2 (Activity 2.4.2). |  | Consultants/ service providers/ implementing partners identified and contracts issued for activities under Outputs 2.1, 2.2 and 2.4 by end of August 2019. As per the project document and budget these activities were meant to be conducted through either consultancies or contracts with a suitable actor. |  | Contracts / Implementing Arrangements for activities 2.1.1 and 2.1.2; and 2.2.2 and 2.2.3 (capacity assessments and capacity development plans on integrating climate change in agricultural extension; and farmer field school modules on climate change adaptation) were issued in August 2019 and the implementing partners have now begun work on the activities. Activity 2.4.2 (Generic module on climate information) will be conducted by a consultant in Year 2, a delay that was due to the need to ensure adequate integration of the Participatory Integrated Climate Services for Agriculture (PICSA) methodology. Trainings of extension agents based on the above assessments and modules will be conducted in Year 2. | Satisfactory (S)
| Component 3: 1. Five sub-national units/ districts receiving localised seasonal climate information. 2. Six government institutions, 1 NGO/CBO reciving downscaled climate information. 3. 30 farmer field school groups receiving localised climate information by end of Year 2. 4. One seasonal planner/ advisory developed and distributed per country per year. 5. Two policy dialogues on climate information conducted in each country and one regional policy dialogue. |  | 1. Five sub-national units/ districts receiving localised seasonal climate information. 2. Seven government institutions and three NGOs/CBOs reciving climate information. 3. FFS groups to begin receiving climate information in Year 2. 5. Policy makers from all ACREI sub-locations supported to participate in regional climate outlook fora. Dialogues with policy makers conducted in Kenya resulting in the formation of the county climate change coordination group. |  | 1. Four out of five sub-national units/ districts are receiving localised seasonal climate information. Three out of five of these sub-national units (in Ethiopia and Kenya)are also receiving weekly and 10-day forecasts through support of the ACREI project. 2. Across the three countries various government institutions and NGOs are receiving climate information and this aspect is already exceeding the initial targets set for the project. 3. FFS groups are to begin receiving climate information in Year 2, however farmer representatives from ACREI target locations have been involved in seasonal participatory advisry development exercises. 4. Seasonal advisories are being developed in all three countries for each main rainfall season. Trainings and support to institutionalisation of the seaonal advisory development process have also begun. 5. Policy makers from all ACREI sub-locations supported to participate in regional climate outlook fora. A policy brief generated from climate baselines has been shared at the county parliament in Taita Taveta, which is an extremely positive result; a County Climate Coordination Group has been created in Taita Taveta County, Kenya as a result of ACREI engagement with policy makers. | Satisfactory (S)
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Jean-Paul Gaudechoux, Senior Programme Manager, WMO
| Email: | jpgaudechoux@wmo.int
| Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other - Food and Agriculture Organization of the United Nations (FAO), Executing Entity | Component 1: 1. Household baseline survey complete in all target locations. |  | 1. Baseline survey complete and reports available. |  | The baseline survey has been completed in all project locations, with over 2,500 households surveyed. The draft baseline reports have been produced and the information and data gathered will provide a strong basis from which to measure project progress and impacts; and is already providing useful information on needs, challenges and opportunities related to the project target communities and agricultural climate resilience. | Highly satisfactory (HS)
| 2. Community sensitisation and mobilisation conducted. |  | 2. 10 communities for community based activities identified in consultation with local authorities, and sensitisation and community engagement begun. |  | Locations for comunity based activities have been identified across all three countries in consultation with local authorities. In Kenya a combination of sub-locations and wards have been identified, in Ethiopia Kebeles have been selected as the level for community based work, and in Uganda where a watershed approach will be used, a combination of villages and parishes have been selected. Field missions to the communities have been undertaken, beginning with the baseline surveys, and sensitisation has been conducted for stakeholders at national, sub-national and local levels. | Satisfactory (S)
| 3. 60 field school groups in place. |  | 3. 30 field school groups in place, 10 in each country (i.e. half of project target by end of Year 1) |  | Twenty eight (28) farmer field school groups are in place across the three countries. This includes 10 groups in Ethiopia and 18 groups in Uganda. The groups have an average of 32 members in Ethiopia, and between 20-35 members each in Uganda, placing the group membership in line with the initial targets to have a total of 1800 field school group members being supported by the project. Field school groups in Kenya are still under formation, however all are expected to be in place by the end of December 2019. | Satisfactory (S)
| 4. 60 extension staff trained on participatory mobilization and planning approaches. |  | 4. One training conducted per country on participatory community mobilization and planning approaches |  | One training has been conducted in each country on participatory community mobilisation and planning approaches and farmer field school facilitation. The trainings targeted local government staff, local agricultural extension staff, NGO and CBO staff, and some comunity members. In total 137 people have been trained (Ethiopia - 31; Kenya - 33; Uganda - 73) with 45 being women. | Satisfactory (S)
| Component 2: 1. Stakeholder mapping and capacity needs assessments conducted for all 3 countries (Activity 2.1.1). 2. Capacity development plans for all three countries available on integration of climate change in extension practices (Activity 2.1.2). 3. Updated agropastoral field school manuals on climate change available in the 3 countries (Activity 2.2.2 and 2.2.3). |  | Consultants/ service providers/ implementing partners identified and contracts issued for activities under Outputs 2.1, 2.2 and 2.4 by end of August 2019. As per the project document and budget these activities were meant to be done through either consultancies or contracts with suitable actors. |  | The capacity needs assessments and capacity development plans for the three countries (Activity 2.1.1 and 2.1.2), are currently being developed, with the contract between WMO and the institution undertaking these activities has been signed in August 2019. The updated agropastoral field school manuals on climate change (Activity 2.2.2 and 2.2.3) are also currently under development with the contract between WMO and the actor undertaking this work having also been signed in August 2019. The activities have since begun with the capcity needs assessment and capacity development plans expected to be complete by January 2020 and the field school manual on climate adaptation practices expected to be complete by March 2020. These activities are budgeted for under WMO but are reported here for consistency with the project framework. The development of a generic module on climate information will be undertaken by a consultant in Year 2. The delay in in this activity was due to the need to ensure adequate integration of the Participatory Integrated Climate Services for Agriculture (PICSA) methodology for which capacity building exercises are planned for the first quarter of Year 2. These assessments and manuals are all expected to be completed in time to feed into field school learning and the training of extension actors targetted under Component 2 of the project. | Satisfactory (S)
| 4. At least two media-based partnerships formed per country (national level and sub-national level) |  | Media partners identified and plans developed for media-based climate information dissemination. |  | This has been supported by ICPAC work under Component 3 of the project. Assessments have been conducted in all three countries and possible media partners identified. These are mostly radio stations. In Year two and year three the partnerships will be solidified with all countries expected to have climate related radio programmes with the identified media partners in each important season. | Satisfactory (S)
| 5. Generic module on climate information available by end of Year 2 (Activity 2.4.2). |  | A consultant identified and contract issued for activities under Output 2.4 by end of August 2019. As per the project document and budget the manual development was menat to be conducted with aid of a consultant. |  | The contract for activity 2.4.2 is pending identification of a suitable consultant. Terms of reference have been drafted and it is expected that a consultant will have been identified and engaged by December 2019 and the activity completed in time to feed into farmer field school learning in Year 2. The manual is expected to be applicable beyond just the project locations, thus contributing to broader impact of ACREI. | Marginally satisfactory (MS)
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Deborah Duveskog, Community Resilience Officer, FAO RTEA, Nairobi, Kenya
| Email: | Deborah.Duveskog@fao.org
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. The project has started well and the overall trend has been positive. National stakeholders including the ministries responsible for agriculture, have welcomed the start of the project and have committed their support to its success. In Ethiopia, the Oromia Regional Bureau of Agriculture, under whch the project locations fall, have signed an LoA with FAO to support project implementation. In Uganda and Kenya, the local authorities have idnetified local level focal points to support the FAO Components of ACREI implementation. Project Outcomes under Components 1 and 2, related to households adopting new or scaling up existing climate adaptation practices (including indigenous knowledge); increases in sources and/or amounts of agricultural income; and increases in agricultural productivity, are expected to be met though too early to be measured at this stage. The baseline survey provides a strong basis from which to measure project progress and impacts; and is already providing useful information on needs, challenges and opportunities related to the project target communities and agricultural climate resilience. Local authorities have played an active role in the identification of the communities for adaptation activities and this is sure to also support sustainability of the actions in the target communities. The community adaptation grants to be implemented in Year 2 of the project will be a main channel through which these Outcomes are realised. The farmer field schools currently under formation (28 of a target of 60 formed) will also provide a channel through which these Outcomes are realised. While trainings for extension actors provide further support to realisation of the project Outcomes. The assessments and manuals are all expected to be completed in time to feed into field school learning and the training of extension actors targetted under Component 2 of the project. 2. Detail critical risks that have affected progress. No major risks have affected project progress to date. As detailed in the ESP Compliance section there were some requests made for changes in location of some project activities. Both requests were still within the initially identified project counties/ districts/ zones for the project and were deemed to be acceptable. One was a request for change of project location in Ethiopia due to reasons related to acessibility. An official request letter was sent by The Oromia Regional Bureau for Agriculture to FAO requesting a change from Golaoda, East Haraghe to Kersa, East Harage, which was forwarded to the Adaptation Fund, through WMO. The request was accepted since the new woreda was still in the same initially identified project Zone and the request was deemed to be justifiable and early enough not to affect project activities or budget. The bringing to the attention of the issue at an early stage was well appreciated by the project partners, and continued open communication on any challenges or issues welcomed. Another request involved having the project not concentrate on only two sub-counties in Taita Taveta County, Kenya, as had initially been agreed between the project partners and local authorities. The County Government through the County Executive Committee for Agriculture, Livestock, Fisheries and Irrigation requested for additional communities from a third sub-county to be included to enhance project reach and also have better comparison of project impacts in different parts of the county. After some discussion with the Taita Taveta County Executive for Agriculture, Livestock, Fisheries and Irrigation, the request was accepted given that it did not have significant implications for project implementation, communities in the previously identified sub-counties could still be kept in the project, and the addition would provide good comparison of adaptation options due to its slightly differing climate. The request for the inclusion of the additional sub-county at an early stage was well apprecieted by the project partners. 3. Outline response to MTR undertaken this reporting period. N/A 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words N/A
| Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other - Intergovernmental Authority on Development (IGAD) Climate Prediction and Applications Centre (ICPAC), Executing Entity | 1. Five sub-national units/ districts receiving localised seasonal climate information. |  | 1. Five sub-national units/ districts receiving localised seasonal climate information. |  | Four out of five ACREI sub-national units are receiving localised seasonal climate information. This includes East and West Haraghe Zones in Ethiopia, Tata Taveta County in Kenya and Sembabule District in Uganda. The seasonal advisory processes have involved the national meteorological and hydrological services (the key stakeholders mandated to produce climate information at national level), the local government authorities, government departments responsible for agriculture, and farmers among others. Only Isingiro District in Uganda could not have a participatory advisory development exercise conducted due to challenges associated with distance betwene the two target districts in Uganda. The sites in Kenya and Ethiopia are also disseminating downscaled monthly and weekly updates to the season forecast. However, the project partners and the national stakeholders will be discussing the options to ensure the production of participatory seasonal advisory development in both project districts of Uganda. Historical climate data analysis has also been conducted for all ACREI locations identifying key climatic parameters such as average onset and cessation dates, dry spell occurence, average season length and other agrometeorological parameters, as well as their changes over time. | Satisfactory (S)
| 2. Six government institutions, 1 NGO/CBO reciving downscaled climate information. |  | 2. Six government institutions (2 per country) and three NGOs/CBOs (one per country) receiving climate information. |  | In each country at least two government institutions (ministries handling disasters, health, agriculture and livestock, health, veterinary services, water and tourism) and one NGO/ CBO are receiving localised climate information as a result of the ACREI project. The targets have been exceeded in all three countries, with for example, seven government institutions and three NGOs/CBOs (red cross, world vision and Wild Life Works) in Kenya receiving climate information through the ACREI project. | Highly Satisfactory (HS)
| 3. 30 farmer field school groups receiving localised climate information by end of Year 2. |  | 3. FFS groups to begin receiving climate information in Year 2. |  | FFS groups will begin receiving climate information in Year 2, however farmer representatives from ACREI target locations have been involved in all seasonal participatory advisory development exercises, with aim to ensure farmers have first hand information and also gain a better understanding of the processes. | Satisfactory (S)
| 4. One seasonal planner/ advisory developed and distributed per country per year. |  | 4. Seasonal advisories developed and distributed in all three countries for each important season. |  | Seasonal advisories are being developed in all three countries for each important season. They are being disseminated through various channels including print, radio and Whatsapp. Weekly/decadal forecasts are also being provided via Whatsapp and radio in Kenya and via email to key intermediaries in Ethiopia. Efforts to also ensure production of 10-day forecasts for the ACREI project locations in Uganda are also being made. Updated forecasts and advisories are also being produced in Kenya, to support farmers being constantly aware of any changes to the seasonal weather foreacst and hence better plan their production activities. In Kenya, the OND 2019 forecast was also translated into Kiswahili for wider reach and understanding, while in Ethiopia the JJA 2019 seasonal forecast was translated into Oromifa, the most widely used local language in the target locations. | Satisfactory (S)
| 5. Two policy dialogues on climate information conducted in each country and one regional policy dialogue. |  | 5. Policy makers from all ACREI sub-locations supported to participate in regional climate outlook fora. |  | Policy makers from all ACREI sub-locations supported to participate in regional climate outlook fora, where key dalogue on climate risks and climate risk management measures for the Eastern Africa region are held. A policy brief generated from the historical climate data analysis (climate baseline) has been shared at the County Parliament in Taita Taveta, something that is sure to contribute to policy dialogue on climate change and ensure greater recognition of climate hazards and climate change among county policy makers. In addition, a County Climate Coordination Group has been created in Taita Taveta as a result of ACREI engagement with policy makers. | Satisfactory (S)
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Abdi Jama, IGAD Climate Prediction and Applications Centre (ICPAC)
| Email: | ajama@icpac.net
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. The project has started well and there is high anticipation from stakeholders and broader development actors in the region to see the results of what is considered to be an innovative project for the Horn of Africa. National Meteorological and Hydrological Services whom ICPAC works with in the climate information activities have expressed support for the project and have been a key part of the activities being implemented at national level related to climate information generation and dissemination at the local level in the three target countries. Project Outcomes under Component 3, related to number/ percentage of households using tailored seasonal climate forecasts to plan their activities or enterprises; and improvement in the quality of advisories are on track to be achieved based on the above progress on outputs and milestones. ACREI supported the staff to participate in the development of a harmonized climate change response strategies for the ICPAC region. Because of the distance between the two districts in Uganda, facilitating participatory scenario planning (PSPs) in both districts was limited by budgetary constraints. Downscaling of climate information to sub-national level was done for the first time in Ethiopia and Uganda, and it is hoped that this will be institutionalised through ACREI support. Uganda is the only site where updated downscaled climate information is not given on a monthly or weekly basis. Participation of farmers in the coproduction of seasonal climate information and generation of seasonal advisories has led to an increase in the number of households using tailored seasonal climate forecasts to plan their activities or enterprises. Overall there has been improved climate informed decision making in regional, national and sub-national institutions. In addition, media partners have been identified to support dissemination of the information to broader stakeholders in the project locations. This has resulted in the development of a Climate Information Media Action Plan in Kenya, which identifies the different media partners and their roles in dissemination of climate information. A surge of climate related reporting in the project location in Kenya has occured due to these actions. Other countries will be supported to develop similar media partnerships in year 2. All countries will be expected to hold climate programmes hosted by identified media partners in each important season. So far from the initial work conducted in Kenya, there has been a greater than expected interest from both local and national radio and television stations and coverage of climate issues in Taita Taveta County has increased greatly. 2. Detail critical risks that have affected progress. Funds from WMO were disbursed in February 2019. This slightly delayed disbursement led to limited time to implement all planned activities for the first year, however despite this ICPAC managed to begin implementing activities ahead of the March-April-May 2019 season. Good progress is being made and the overall trend is positive. Isingiro District in Uganda could not have a participatory advisory development exercise conducted due to challenges associated with distance between the two target districts in Uganda (hence only 4 out of the 5 ACREI project locations received seasonal participatory agroclimatic advisory support). However, the project partners and the national stakeholders are discussing the options to ensure the production of participatory seasonal advisories in both project districts of Uganda for the next season. 3. Outline response to MTR undertaken this reporting period. N/A 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words N/A
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective | Number of beneficiaries received support for increased adaptive capacity to mitigate and respond to effects of climate change. | 0 | To be measured at endline | 45,000 direct beneficiaries through participation in CMDRR or as beneficiaries of investment grants. 9000 APFS household members/direct and targeted beneficiaries (min. 50% female) 40,000 indirect recipients of weather and climate information
| Percentage of targeted population with sustained climate-resilient alternative livelihoods. | 20% of direct target population implementing identified adaptation practices | To be measured at endline | 60% of direct target population with climate resilience livelihoods Alternative asset creation improved among 50% of target population.
| Percentage change in income (number, types and levels) among target population during periods affected by climate variability | US$193.5 (agricultural income averaged across the project locations from baseline survey) | To be measured at endline | A 40% increase in number, types, and/or levels among 80% of direct beneficiaries.
| Change in quality of climate related advisory to target population by the extension service. | Partially effective/ useful | To be measured at endline | Minimum 40% increase in satisfaction rates among direct and indirect beneficiaries with climate advisory services prior to the last extreme weather event.
Outcome 1 | Percentage change in crop/livestock yields among targeted households | See baseline report for yields of various crop and livestock products | To be measured at endline | 30% increase in crop/ livestock yields
| Percentage change in productivity of land, crop and livestock resources among targeted communities. | See baseline report for yields of various crop and livestock products | To be measured at endline | At least 50% increase
| Percentage of households adopting new or scaling up existing climate adaptation practices (including indigenous knowledge) | 0 | To be measured at endline | At least 30% adoption
| Percentage change in household incomes disaggregated by gender of household heads | US$193.5 (agricultural income averaged across the project locations from baseline survey) | To be measured at endline | At least by 50%
Outcome 2 | Number and type of targeted institutions with increased capacity to minimize exposure to climate variability risks | 0 | Activity targeted for Year 2 | 30 institutions
| Percentage of extension workers (male and female) who are integrating adaptation strategies in their work at the community level | Assessments ongoing | Activity targeted for Year 2 | 80%
| Percentage of direct target population with reduced risk to climate variability and extremes | 0 | To be measured at endline | 70%
| No. of staff trained to respond to, and mitigate impact of, climate –related events (by gender). | 0 | Activity targeted for Year 2 | 100 staff trained
Outcome 3 | Harmonized climate change response strategies for the region developed | 0 | To be measured at endline | Harmonised GHA Climate Change Strategy
| Percentage change in national budgets allocated to climate adaptation activities | 0 | To be measured at endline | 15% increase
| Percentage of households using tailored seasonal climate forecasts to plan their activities or enterprises | 0 (Households access some weather information, however tailored seasonal forecasts will be introduced through the project) | To be measured at endline | 70% increase
Output 1.1 | Number of community level adaptation action plans produced | 0 | Year 2 activity | 30 Community Adaptation Plans
| Number of staff trained in participatory community mobilization and planning processes. | 0 | Total: 137 Ethiopia: 31 Kenya: 33 Uganda: 73 | 60 staff trained
Output 1.2 | Number of participatory technology developments sites/structures linked to climate change adaptation | 0 | Year 2 activity (through farmer field schools) | 60 PTDs documented
| Number of field days conducted by APFS on climate change adaptation | 0 | Year 2 activity (through farmer field schools) | At least 60 field days
| Number of APFS groups in place and applying climate change adaptation knowledge. | 0 | Total: 28 groups Ethiopia: 10 groups Kenya: 0 groups Uganda: 18 groups | 60 groups in place applying adaptation practices
Output 1.3 | Number of communities trained in climate change adaptation proposal development | 0 | Year 2 activity | 30 communities trained.
| Number of community adaptation proposals developed | 0 | Year 2 activity | 30 community adaptation proposals submitted
| Percentage of approved, climate adaptation proposals, funded and implemented | 0 | Year 2 & 3 activity | At least 80% of submitted proposals funded and implemented.
Output 1.4 | Number of intra-country FS visits conducted | 0 | Year 2 activity | 60 Visits
| Number of inter-country FS visits conducted | 0 | Year 2 activity | 3 Visits
| Number of visibility and exposure events attended by target community members | 0 | Year 2 activity | 6 events
Output 2.1 | No of national stakeholder mapping and capacity needs assessments undertaken | 0 | Activity ongoing | 3
| No. of capacity development plans in place | 0 | Activity ongoing | 3
Output 2.2 | Number of training manuals on climate adaptation strategies reviewed, modified and validated | 0 | Activity ongoing | Updated APFS modules available in 3 countries
| Number of extensions actors (% female) who demonstrate an increase in knowledge and skills on climate-sensitive extension methodologies | 0 | Year 2 activity | 100 extension actors.
Output 2.3 | A knowledge and experience sharing platform for extension actors on climate proofing methodologies established | 0 | Platform identification and development underway. | ACREI Knowledge platform linked to existing platforms
| Number of community outreach forums on adaptation to climate change held and linked to the FS. | 0 | Year 2 & 3 activity | 30 Community outreach forums
| Number of media-based partnerships developed for disseminating climate change adaptation information | 0 | Ethiopia: 0 Kenya: 3 radio stations Uganda: 0 (NB. This work is supported under Component 3 of ACREI) | At least 6 media partnerships
Output 2.4 | Proportion of identified FS service providers integrating climate related information in their FS implementation | 0 | To be measured at endline | At least 60%
| A generic climate module for FS practice developed | 0 | Year 2 activity | 1 generic climate module
| Number of FS climate change adaptation issue papers developed | 0 | 0 (3 papers curently being written) | 3 issue papers
Output 3.1 | Number of livelihood zones with specific climate information generated and disseminated | 0 | 4 out of 5 ACREI districts | 5 Sub national units
| Number of target sub-national institutions provided with seasonal and/or enterprise-specific climate information | 0 | At least two government institutions and one NGO/ CBO per country | At least 6 government extension institution and 1 NGO or CBO receiving downscaled forecasts from Met agencies.
Output 3.2 | Number of FS with localized climate monitoring systems | 0 | Year 2 activity, although farmer representatives were included in the seasonal outlook forum | 60 FS groups by end of project
Output 3.3 | Number of National Agricultural Planners produced | 0 | Seasonal agroclimatic advisories produced as per indicator below. Historical climate data analysis conducted for all 3 countries identifying key climatic parameters such as average onset and cessation dates. | At least 4 seasonal planners developed per country
| Number of agro-climate advisories disseminated | 0 | 4 (two in Kenya for each of the main rainy seasons in 2019, one in Uganda and one in Ethiopia for the June-July0August season) | At least 4
Output 3.4 | Number of good practices developed | 0 | Year 2 & 3 activity | 6 (2 per country)
| Number of policy dialogues on climate change adaptation conducted | 0 | 3 (two at regional level and one at national level) | At least 4 ( national policy dialogue per country and 1 regional policy)
| Number of updates on food and nutrition security developed for advocacy and response | 0 | Year 2 & 3 activity | 24 monthly updates

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | - Being the first regional Adaptation Fund project the modalities for inception at regional and national level required good thought and planning. Of note is that having a regional inception workshop contributed to enhanced and common knowledge of project partners, stakeholders, and focal people from participating institutions and countries. However, this did not necessarily eliminate the need for national inception workshops, with Ethiopia deciding to also have a national inception workshop with all key national stakeholders. - Being a multi country and multistakeholder project, coordination at both regional and national levels among project partners and stakeholders is crucial for project success. The establishment of project structures at regional, national and sub-national level has thus been undertaken to ensure integration from regional to local level. - The project is country driven and involves consultation, engagement and agreement with various national and sub-national stakeholders. These engagements sometimes take time and can result in delays, however they are necessary to ensure sustainability, ownership and ultimate success of the project. - In Kenya where a sub-national meteorological officer is available at the County level (i.e. Kenya has a County Director of Meteorology present in the project location), this sub-national presence has facilitated the downscaling and dissemination of climate information and agroclimatic advisories. The project team is still working with the national staff in Uganda and Ethiopia to support local level generation and dissemination of climate information. Positive developments are that 1) in Uganda the National Meteorological Authority (UNMA) has begun a decentralisation process with deployment of staff to districts; and 2) In Ethiopia, the national level NMHS staff have prioritised ACREI locations for production of localised advisories and forecasts including in local languages. - The engagement of media as a stakeholder on the dissemination of climate information in Taita Taveta County, Kenya has yielded extremely positive results. Media partners have accepted this role and there has been a huge increase in information and programmes on weather, climate, and climate hazards targetting the County. Similar partnerships are expected to be built in Uganda and Ethiopia, and this aspect of the project has been identified as having potential for documentation as a good/ best practice. - The facilitation of the involvement of sub-national agricultural technical staff and policy makers in the regional fora related to climate change and food security in Eastern Africa has been extremely valuable in terms of 1) allowing sub-national agricultural techical staff and policy makers to gain a better underatanding of the regional climate forecasting and food security issues; 2) allowing cross-country exchange of knowledge, experiences and challenges; and 3) allowing local voices to be heard at the regional/ international level. These have increased stakeholder knowledge and engagement on ACREI (and ACREI related issues) from local to regional level.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There was a delay in project inception largely due to the following three factors: - The untimely death of the WMO Representative for Eastern and Southern Africa, who was also the project development lead, left a huge gap in the office. This necessitated the recruitment of a new WMO Representative as well as the recruitment of the project specific staff. These recruitments took longer than usual due to loss of the WMO Representative. - The need to ensure that key stakeholders in the project fully understood their roles in the project prior to inception. - A regional inception workshop was not formally budgeted for in the project proposal. The measures taken to reduce the delays included the following: - TORs for project staff were developed and VAs floated as early as possible so staff could be on board at project inception. Internal administrative procedures related to project implementation were begun while awaiting recruitment of project staff. - Regular dialogue among the project partners and key stakeholders (including government departments) on the project, the next steps and the likely inception date. - A suitable platform for project inception was sought at one of the partners regional events, rather than having a standalone inception. Since the initial delay, progress has been steady and proceeded well with only minor delays to some activites.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | No changes have been made to project Outputs at the moment. The training of extension actors, initially scheduled for Year 1, has been moved to Year two in consultation with EEs and stakeholders, who agreed that the trainings would best be conducted in Year 2 once the capacity assessments and various training manuals are complete. Regarding activities for which costs reflected in the Year 1 PPR yet were initially budgeted as Year 2 activities: - 1) For Activity 1.3.4 (Community investment grant financing), the preparatory activities have included an LoA with the Oromia Regional Bureau for Agriculture in Ethiopia to support community mobilisation and community engagement-related aspects in the lead up to community adaptation planning. This began in Year 1 and will carry forward to Year 2 of the project. - 2) For other activities budgeted for Year 2 for which expenditure has been registered in Year 1. This expenditure has included costs for preparatory activities, or costs for which committments overlap between Year 1 and Year 2. These include costs such as those for field staff, regional technical support, knowledge management, farmer field school experts, and initial missions. Regarding activities which were initially budgeted under Year 1, for the reasons indicated below they have been either moved or extended through to Year 2: - 1) Activity 2.2.4 (National and sub-national training of extension actors on climate sensitive extension services) - it was realised and agreed that this activity was best implemented once assessments, manuals and guides being developed to inform such trainings were completed. Undertaking this activity in Year 2 allows for adequate integration of the climate change capacity needs findings (Activity 2.1.1 and 2.2.2) and use of the field school climate change module (being developed under Activity 2.2.3). - 2) Activity 2.3.2 (Dissemination of timely information on climate impacts and weather forecasts) - climate information dissemination has begun and is being implemented for all major rainfall seasons with support of partner activities under Component 3. However, climate information dissemination will be conducted seasonally over the entire duration of the project hence the need to spread these activities across the remaining project Years and not just Year 1. The County Government through the County Executive Committee for Agriculture, Livestock, Fisheries and Irrigation requested for additional communities from a third sub-county to be included to enhance project reach and also have better comparison of project impacts in different parts of the county. The request was accepted given that it did not have significant implications for project implementation, communities in the previously identified sub-counties could still be kept in the project, and the addition would provide good comparison of adaptation options due its its slightly differing climate. The request for the inclusion of the additional sub-county at an early stage was well apprecieted by the project partners. Another request came from the local authorities in Ethiopia to change one initially identified project woreda to another in the same Zone. Specifically the request was for a change from Golaoda Woreda, East Haraghe to Kersa Woreda, East Haraghe. Ethiopia was the only country of the three countries covered by the ACREI project which had identified a project location to this specificity and project implementation would still be in the initially identified project zone of East Haraghe, but in a different district, i.e. Kersa Woreda. The request was communicated to the Adaptation Fund and accepted since the new woreda was still in the same initially identified project Zone and the request deemed to be justifiable and early enough not to affect project activities or budget. The early comunication of the request was well appreciated by the project partners, and continued open communication on any challenges or issues welcomed.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | For the activities undertaken to date, the environmental and social safeguards have been adequate and as yet no negative impacts have emerged. However, the project involves USPs which are planned for development and implementation in Year 2. Only then can an accurate assessment on the effectiveness of the environmental and social safeguard measures be provided.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | The project partners have undertaken the following measures in relation to gender considerations in the ACREI project: - Baseline survey tools were reviewed by FAO gender experts and had inclusion of sex-dissagregated data, questions on control and ownership of household assets, and questions on impacts of climate change and climate hazards on different household members. - Aiming for 50% participation of men and women in all trainings and project activities (including as participants and trainers). - Aim for 50% participation of women in project activities and 50% of project direct beneficiaries to be women, while also targeting specific project activities at women or women groups (for example the integrated savings and lending). - Foster equal participation of men and women in institutions and decision-making processes related to the project. Some lessons emerging from the project relating to gender include the following: - Contrary to common knowledge baseline surveys in ACREI target communities revealed the perception that women are not affected greatly by climate change, and all household members are equally affected. This points to a need for greater awareness raising on the impacts of climate change on women. - The knowledge of climate change and climate change adaptation strategies was found to be lower among women headed households than male headed households. Given the vulnerability of women and women headed households to climate change and food insecurity, this highlights the need for awareness raising and capacity building targetted at women and women headed households on issues of climate change and climate change adaptation. - Despite household assets being one of the main contributors to resilience to climate change, these resources were found to be prdominantly controlled by men. There is need to ensure women and men equally own and control assets which contribute to their resilience to climate change. - Womens participation in project activities and leadership positions varies from location to location and activity to activity. It is not always possible to ensure equal participation of men and women, however efforts for such are being made. To track these issues and their change over time, the endline survey for the project will include questions dissagregated by gender as well as gender specific questions on impacts of project activities. At present indicators related to gender, focusing on womens participation and empowerment, include the following: - Number of APFS groups in place and applying climate change adaptation knowledge. (target for 50% women) - Number of extension actors (% female) who demonstrate an increase in knowledge and skills on climate-sensitive extension methodologies - Percentage change in household incomes disaggregated by gender of household heads - Number of staff trained to respond to, and mitigate impact of, climate-related events (by gender). - Percentage of extension workers (male and female) who are integrating adaptation strategies in their work at the community level - 9000 APFS household members/direct and targeted beneficiaries (minimum 50% female)
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A - to be filled at project completion.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A - to be filled at project completion.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A - to be filled at project completion.
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A - to be filled at project completion.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A - to be filled at project completion.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A - to be filled at project completion.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A - to be filled at project completion.
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A - to be filled at project completion.
What measures are being/could have been put in place to improve project/program results? | N/A - to be filled at project completion.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | N/A - to be filled at project completion.
If learning objectives have been established, have they been met? Please describe. | N/A - to be filled at project completion.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A - to be filled at project completion.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A - to be filled at project completion.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | AFR/MIE/Food/2015/2
Implementing Entity | World Meteorological Organization (WMO)
Type of implementing entity | MIE
Country | Ethiopia, Kenya & Uganda
Region | Africa
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 94000 | 54000 | 40000 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 40000 | Drought | 2: Partially effective | Total | 40000 | Drought | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 100 | Agriculture | 2: Low capacity | Total | 100 | Agriculture | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 100 | 50% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 20% |  | Agriculture |  | 60 |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 40000 | 50% | 3: Partially aware |  | 40000 | 50% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Food security | Regional | 3: Moderately responsive (Some defined elements) |  | Food security | Regional | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
Community
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 10800 | 50% | 4: High improvement |  | 10800 | 50% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 6480 | 50% | From 30% to 40% | Agricultural-related | 6480 | 50% | From 30% to 40% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies | Agriculture | Community-based adaptation | 30 | Adaptation strategies | Agriculture | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 10800 | Agricultural-related |  | 193.5 | 10800 | Agricultural-related |  | 40%
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Agriculture | Local | Other policy | 3 | Agriculture | Local | Other policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 2: Partially not enforced (Most elements not implemented) |  | 2: Partially effective | 3 | 3: Partially enforced (Some elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia, Kenya & Uganda
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.