## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 30 August 2021 - 29 August 2022
| Project Title: | The Agricultural Climate Resilience Enhancement Initiative (ACREI)
| Project Summary: | The Agricultural Climate Resilience Enhancement Initiative (ACREI) is a US$ 6.8 million project funded by the Adaptation Fund and implemented by the World Meteorological Organization (WMO) in partnership with the Food and Agriculture Organization (FAO) and the Intergovernmental Authority on Development (IGAD) Climate Prediction and Applications Centre (ICPAC). The ACREI project is the first regional project funded by the Adaptation Funded through its Pilot Programme for Regional Projects. The program targets Ethiopia, Kenya and Uganda and supports community adaption practice, climate proofing of extension systems and climate informed decision making. The project outcomes are: - Outcome 1. Sustainably enhanced agricultural productivity, production, livelihood diversification and income levels among targeted communities. - Outcome 2. Enhanced technical capacity of development and extension actors (national, sub-national, private sector, NGOs, CBOs) to support community level climate adaptation strategies - Outcome 3. Improved climate informed decision making in regional, national and sub-national institutions The goal of the initiative is to develop and implement adaptation strategies and measures that will strengthen the resilience of vulnerable smallholder farmers, agro-pastoralists and pastoralists in the Horn of Africa to climate variability and change. The overall objective of ACREI is improved adaptive capacity and resilience to current climate variability and change among targeted farmers, agro-pastoralists and pastoralist communities. The goals of the ACREI project are in line with the IGAD Drought Disaster Resilience and Sustainability Initiative (IDDRSI) programme, and with the overall vision of the African Ministerial Conference on Meteorology (AMCOMET), the inter-governmental body for the development of meteorology and its applications in Africa.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AFR/MIE/Food/2015/2 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | The World Meteorological Organization (WMO) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity (MIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Ethiopia, Kenya and Uganda | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Ethiopia - Kersa Woreda, East Hererghe Zone & Mieso Woreda, West Hererghe Zone Kenya - Taita Taveta County Uganda - Sembabule District & Isingiro District | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2017-03-17
IE-AFB Agreement Signature Date: |  | 2017-06-20 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2018-08-30 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | NA - Since project was planned as a 3-year project.
TBC
| Original Completion Date: | 2022-08-29
Revised Completion Date after approval of |  | 2024-02-29
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
| Condition or Requirement | N/A
| Current Status | N/A
| Planned actions, including a detailed time schedule | N/A
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Project Inception Workshop Report (submitted to Adaptation Fund on 29 October 2018) Project 1-year no-cost extension request due to COVID (submitted on 6 January 2021) Project no-cost extension (14 March 2022) | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://public.wmo.int/en/projects/agricultural-climate-resilience-enhancement-initiative-acrei-0 | Democratic Republic of the Congo
https://www.icpac.net/our-projects/acrei/
https://www.adaptation-fund.org/project/agricultural-climate-resilience-enhancement-initiative-acrei-ethiopia-kenya-uganda/
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Sebastian Grey, World Meteorological Organization (WMO), Office for Eastern and Southern Africa | Dominican Republic
| Email: | SGrey@wmo.int | Ecuador
| Date: | 2019-10-28 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | H.E. Mr. Kare Chawicha Debessa, State Minister, Ministry of Environment and Forest (at time of project approval) | Equatoral Guinea
| Email: | eenvironment@gmail.com | Eritrea
| Date: | 2017-02-01 | Estonia
| Name: | Mr. Charles T. Sunkuli, Principal Secretary, State Department of Environment & Regional Development Authorities, Ministry of Environment and Forestry, Kenya (at time of project approval) | Equatoral Guinea
| Email: | psoffice@environment.go.ke | Eritrea
| Date: | 2017-02-03 | Estonia
| Name: | Mr. Keith Muhakanizi, Permanent Secretary / Secretary to the Treasury, Ministry of Finance, Planning and Economic Development | Equatoral Guinea
| Email: | finance@finance.go.ug | Eritrea
| Date: | 2017-01-16 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Jean-Paul Gaudechoux, Senior Programme Manager, WMO | Fiji
| Email: | jpgaudechoux@wmo.int | Finland
| Date: | 2019-10-28 | France
| Executing Agency |  | Gambia
| Name: | Cyril Ferrand, Resilience Team Leader, Food and Agriculture Organization of the United Nations (FAO), FAO Sub-Regional Resilience Team for Eastern Africa, Nairobi, Kenya | Georgia
| Email: | Cyril.Ferrand@fao.org | Germany
| Date: | 2019-10-28 | Ghana
| Executing Agency |  | Greece
| Name: | Dr. Guleid Artan, Intergovernmental Authority on Development (IGAD) Climate Prediction and Applications Centre (ICPAC), Nairobi, Kenya | Grenada
| Email: | gartan@icpac.net | Guatemala
| Date: | 2019-10-28 | Guinea
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information: cumulative from project start to 29 August 2019 |  |  |  |  | Financial information: cumulative from project start to 29 August 2020 |  |  |  |  | Financial information: cumulative from project start to 29 August 2021 |  |  |  |  | Financial information: cumulative from project start to 29 August 2022 |  |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 29 August 2019 |  | 2064394 |  |  | Estimated cumulative total disbursement as of 29 August 2020 |  | 5893831 |  |  | Estimated cumulative total disbursement as of 29 August 2021 |  | 6107079 |  |  | Estimated cumulative total disbursement as of 29 August 2022 |  | 6424885 |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) |  | Grant funds were well received and disbursements made to the Executing Entities, with FAO receiving their project funds in November 2018 and ICPAC receiving theirs in February 2019. The IE and EEs are utilising the project execution costs as indicated in the project document. One issue that has arisen is in regards to currency fluctuations. Funds received from Adaptation Fund are registered and maintained in CHF (in accordance to WMO financial regulations), with disbursements being made to partners in USD. However, it has been noted that currency exchange fluctuations between the USD and CHF can still have slight impacts on project funds. Between the time of the receipt of funds from the Adaptation Fund and disbursements being made to implementing partners, USD/CHF currency exchange fluctuations occured which negatively affected one executing entity's disbursement amount. The trust funds are being monitored and a plan put in place to ensure this does not occur for subsequent disbursements. To mitigate further currency fluctuation effects, future disbursements to partners are aimed to be conducted as quickly as possible after receipt of funds from the Adaptation Fund. Note that the initial delay between receipt of funds from Adaptation Fund and disbursements being made to partners was due to events outside WMO control and have been communicated to the Adapation Fund. Disbursed to FAO (including EE fees and execution costs) - US$1,250,261 Disbursed to ICPAC (including EE fees and execution costs) - US$377,807 Total disbursed to EEs = US$1,628,068 WMO expenditure (execution costs and activities) - US$355,261 WMO IE fees - US$81,065 Total up to end of August 2019 - US$2,064,394 Balance unspent and unobligated as at end of August - US$1,335,606 The disbursement schedules for the executing entities are as follows: ICPAC: Year 1: US$377,807.00 (already disbursed) Year 2: US$352,807.00 Year 3: US$317,806.00 Total: US$1,048,420 FAO: Year 1: US$1,250,261 (already disbursed) Year 2: US$3,077,067 Year 3: US$335,466.00 Total: US$4,662,794 The remaining balance from the first tranche, will be carried forward to committments to executing entities contracts for their Year 2 activities. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  | Disbursed to FAO (including EE fees and execution costs) - $4,327,328 Disbursed to ICPAC (including EE fees and execution costs) - $730,614 Total disbursed to EEs = $5,057,942 (82.6% of funds received from AF have been disbursed to EEs) WMO expenditure (activities & execution costs) - $736,292 (This includes LoAs with other institutions: IIRR - $101,908 disbursed (+US$25,423 obligation); AFAAS - $74,817 disbursed; Ethiopia National Meteorological Authority - $18,000 disbursed; Uganda National Meteorological Authority - $18,000 disbursed)) WMO IE fees - $189,597 Total up to end of August 2020 - $5,893,831 (97.8% of funds received from AF) Balance unspent as at end of August 2020 ≈ $136,169 (2.2% of AF grant). This remaining balance will be carried forward to committments to outstanding payments for LoAs and to executing entities contracts for their Year 3 activities. Although most funds have been disbursed to Executing Enitities as per WMOs agreements with them, their expenditure of these funds in Year 2 was much lower than expected due to the COVID situations impact on activities. Given the status of activities as a result of the COVID situation, there will be need for an extension of the project. WMO is not requesting any disbursement of funds from Adaptation Fund at this stage. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  | Disbursed to FAO (including EE fees and execution costs) - $4,327,328 (unchanged from PPR2) - Total contract value $4,636,794 Disbursed to ICPAC (including EE fees and execution costs) - $730,614 (unchanged from PPR2) - Total contract value $1,048,420 Total disbursed to EEs = $5,057,942 (82.6% of funds received from AF have been disbursed to EEs) of total contracted value of $5,685,214 WMO expenditure (activities & execution costs) - $807,596 (This includes LoAs with other institutions: IIRR - $127,339 disbursed; AFAAS - $74,817 disbursed; Ethiopia National Meteorological Authority - $18,000 disbursed (+$5,650 disbursed in October 2021); Uganda National Meteorological Authority - $18,000 disbursed (+ additional $5,800 pending disbursement) Kenya Meteorological Department (KMD) - 18,000 disbursed) Total disbursed / committed - $6,107,079 (99% of funds received from AF) Balance undisbursed and uncommitted as at end of August 2021 ≈ $12,921 (1% of funds received from AF to date). NB: This does not include funds for EE third disbursements, which are also contracted and still expected to be fully utilised. Although most funds have been disbursed to Executing Enitities as per WMOs agreements with them, their expenditure of these funds in Year 2 and 3 was still much lower than planned, mostly due to COVID-related impacts on activities. There was a significant decrease in expenditure once the COVID pandemic set in. Henmce, expenditure data below has been split into two columns, one for actual expenditure and one for disbursements / committments to date. WMO and FAO undertook a revision of the FAO contract to account for currency fluctuations that affected the first disbursement to FAO. The activities have not changed and the budget adjustments, amounting to a reduction of FAOs budget by $66,500, were not over the threshold to warrant a material change request. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  | Disbursed to FAO (including EE fees and execution costs) - $4,327,328 (unchanged from PPR3) - Total contract value $4,636,794. Disbursed to ICPAC (including EE fees and execution costs) - $1,048,420 - Total contract value $1,048,420 (100% of contract funds disbursed) Total disbursed to EEs = $5,375,748 (79.1% of funds received from AF have been disbursed to EEs) of total contracted value of $5,685,214. FAOs final disbursement is expected to be in February 2023. WMO expenditure (activities, LoAs, execution costs) - $814,660 Total disbursed / committed - $6,424,885 (95% of funds received from AF) Balance undisbursed and uncommitted as at end of August 2022 ≈ $375,885 (5% of funds received from AF to date). This includes FAOs third & final disbursement, which is expected to be done in February 2023. Although most funds have been disbursed to Executing Enitities as per WMOs agreements with them, actual data is tracked seperately. The expenditure data below has been split into two columns, one for actual expenditure and one for disbursements / committments to date. |  |  | Add any comments on AF Grant Funds. (word limit=200)
[7 empty] | : |  |  |  |  | : |  |  |  |  | :
INVESTMENT INCOME |  | 2375.87 |  |  | INVESTMENT INCOME |  | 3357 |  |  | INVESTMENT INCOME |  | 3400 |  |  | INVESTMENT INCOME |  | 2867 |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  | Cummulative from project start |  | EXPENDITURE DATA |  |  | Cummulative from project start |  | EXPENDITURE DATA |  |  | Cummulative from project start |  | EXPENDITURE DATA |  |  | Cummulative from project start |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT (actual expenditure) | Disbursed or committed | List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT (actual expenditure) | Disbursed or committed | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
Component 1 | Output 1.1 | 1.1.1 - 10 day training at sub-national level of Agric and Met staff on Participatory planning approaches | 40559 |  | Component 1 | Output 1.1 | 1.1.1 - 10 day training at sub-national level of Agric and Met staff on Participatory planning approaches | 63227 |  | Component 1 | Output 1.1 | 1.1.1 - 10 day training at sub-national level of Agric and Met staff on Participatory planning approaches | 66346 | 46875 | Component 1 | Output 1.1 | 1.1.1 - 10 day training at sub-national level of Agric and Met staff on Participatory planning approaches | 89555 | 46875
|  | 1.1.2 - Community sensitization, mobilization and launching of the community adaptation planning processes. | 15666.37 |  |  |  | 1.1.2 - Community sensitization, mobilization and launching of the community adaptation planning processes. | 16838 |  |  |  | 1.1.2 - Community sensitization, mobilization and launching of the community adaptation planning processes. | 15442 | 16500 |  |  | 1.1.2 - Community sensitization, mobilization and launching of the community adaptation planning processes. | 15442 | 16500
|  | 1.1.3 - Context analysis and stocktaking at community level | 3385.95 |  |  |  | 1.1.3 - Context analysis and stocktaking at community level | 11139 |  |  |  | 1.1.3 - Context analysis and stocktaking at community level | 11140 | 15000 |  |  | 1.1.3 - Context analysis and stocktaking at community level | 11360 | 15000
|  | 1.1.4 - Seasonal short term adaptation planning of 1-2 days in each target community | 80.8 |  |  |  | 1.1.4 - Seasonal short term adaptation planning of 1-2 days in each target community | 7371 |  |  |  | 1.1.4 - Seasonal short term adaptation planning of 1-2 days in each target community | 9894 | 10000 |  |  | 1.1.4 - Seasonal short term adaptation planning of 1-2 days in each target community | 10473 | 10000
|  | 1.1.5 - Longer term adaptation planning over a period of seven to ten days in each community | 11076.4 | Scheduled as a Year 2 activity, though some preparatory activities have begun. |  |  | 1.1.5 - Longer term adaptation planning over a period of seven to ten days in each community | 51803 |  |  |  | 1.1.5 - Longer term adaptation planning over a period of seven to ten days in each community | 56243 | 53204 |  |  | 1.1.5 - Longer term adaptation planning over a period of seven to ten days in each community | 70677 | 53204
|  | 1.1.6 - Validation of community adaptation plans | 0 | Year 2 activity |  |  | 1.1.6 - Validation of community adaptation plans | 17185 |  |  |  | 1.1.6 - Validation of community adaptation plans | 18466 | 27000 |  |  | 1.1.6 - Validation of community adaptation plans | 22202 | 27000
| Output 1.2 | 1.2.1 - Baseline and endline data collection | 36538.65 |  |  | Output 1.2 | 1.2.1 - Baseline and endline data collection | 83907 |  |  | Output 1.2 | 1.2.1 - Baseline and endline data collection | 95571 | 157200 |  | Output 1.2 | 1.2.1 - Baseline and endline data collection | 89472 | 157200
|  | 1.2.2 - 4-week training of facilitators (ToFs) courses on the APFS approach | 133262.83 |  |  |  | 1.2.2 - 4-week training of facilitators (ToFs) courses on the APFS approach | 169923 |  |  |  | 1.2.2 - 4-week training of facilitators (ToFs) courses on the APFS approach | 197213 | 256500 |  |  | 1.2.2 - 4-week training of facilitators (ToFs) courses on the APFS approach | 177032 | 256500
|  | 1.2.3 - Community Ground working will be undertaken in each target community | 2134.44 |  |  |  | 1.2.3 - Community Ground working will be undertaken in each target community | 11065 |  |  |  | 1.2.3 - Community Ground working will be undertaken in each target community | 7292 | 18750 |  |  | 1.2.3 - Community Ground working will be undertaken in each target community | 11462 | 18750
|  | 1.2.4 - Facilitation of participatory learning in APFS group trough groups meeting on weekly basis over appr 1.5 years period | 42084.01 |  |  |  | 1.2.4 - Facilitation of participatory learning in APFS group trough groups meeting on weekly basis over appr 1.5 years period | 45327 |  |  |  | 1.2.4 - Facilitation of participatory learning in APFS group trough groups meeting on weekly basis over appr 1.5 years period | 45649 | 81000 |  |  | 1.2.4 - Facilitation of participatory learning in APFS group trough groups meeting on weekly basis over appr 1.5 years period | 68191 | 81000
|  | 1.2.5 - Provision of learning materials package/grants to APFS groups | 0 | Year 2 activity |  |  | 1.2.5 - Provision of learning materials package/grants to APFS groups | 6111 |  |  |  | 1.2.5 - Provision of learning materials package/grants to APFS groups | 9469 | 27000 |  |  | 1.2.5 - Provision of learning materials package/grants to APFS groups | 19366 | 27000
| Output 1.3 | 1.3.1 - Training of communities in village savings systems (VSLA/VICOBA) and financial management and support for establishment of community savings and banking schemes. | 0 | Year 2 activity |  | Output 1.3 | 1.3.1 - Training of communities in village savings systems (VSLA/VICOBA) and financial management and support for establishment of community savings and banking schemes. | 0 |  |  | Output 1.3 | 1.3.1 - Training of communities in village savings systems (VSLA/VICOBA) and financial management and support for establishment of community savings and banking schemes. | 1982 | 24000 |  | Output 1.3 | 1.3.1 - Training of communities in village savings systems (VSLA/VICOBA) and financial management and support for establishment of community savings and banking schemes. | 4575 | 24000 |  | TOTAL | 0
|  | 1.3.2 - Support to development of community adaptation investment proposal in target communities. | 33001.71 | Scheduled as a Year 2 activity, though some preparatory activities have begun. |  |  | 1.3.2 - Support to development of community adaptation investment proposal in target communities. | 73150 |  |  |  | 1.3.2 - Support to development of community adaptation investment proposal in target communities. | 72298 | 95000 |  |  | 1.3.2 - Support to development of community adaptation investment proposal in target communities. | 91059 | 95000
|  | 1.3.3 - Technical review and screening of proposals through multi-sectoral proposal review group | 0 | Year 2 activity |  |  | 1.3.3 - Technical review and screening of proposals through multi-sectoral proposal review group | 0 |  |  |  | 1.3.3 - Technical review and screening of proposals through multi-sectoral proposal review group | 14094 | 30000 |  |  | 1.3.3 - Technical review and screening of proposals through multi-sectoral proposal review group | 13689 | 30000 | PLANNED EXPENDITURE SCHEDULE
|  | 1.3.4 - Community investment grant financing | 78138.33 | Scheduled as a Year 2 activity, though some preparatory activities have begun. |  |  | 1.3.4 - Community investment grant financing | 73057 |  |  |  | 1.3.4 - Community investment grant financing | 204789 | 1771000 |  |  | 1.3.4 - Community investment grant financing | 755994 | 1771000 | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
|  | 1.3.5 - Technical backstopping and monitoring of beneficiary community investment project implementation. | 285228.07 | Scheduled as a Year 2 activity, though some preparatory activities have begun. |  |  | 1.3.5 - Technical backstopping and monitoring of beneficiary community investment project implementation. | 198304 |  |  |  | 1.3.5 - Technical backstopping and monitoring of beneficiary community investment project implementation. | 331076 | 347259 |  |  | 1.3.5 - Technical backstopping and monitoring of beneficiary community investment project implementation. | 322713 | 347259
| Output 1.4 | 1.4.1 - Within country community exchange visits | 0 | Year 2 activity |  | Output 1.4 | 1.4.1 - Within country community exchange visits | 0 |  |  | Output 1.4 | 1.4.1 - Within country community exchange visits | 0 | 26250 |  | Output 1.4 | 1.4.1 - Within country community exchange visits | 18408 | 26250
|  | 1.4.2 - Community and site participation in project review processes | 0 | Year 2 activity |  |  | 1.4.2 - Community and site participation in project review processes | 1425 |  |  |  | 1.4.2 - Community and site participation in project review processes | 3405 | 2999 |  |  | 1.4.2 - Community and site participation in project review processes | 1425 | 2999
|  | 1.4.3 - Participation in field days and agriculture shows/fairs but target communities | 0 | Year 2 activity |  |  | 1.4.3 - Participation in field days and agriculture shows/fairs but target communities | 2049 |  |  |  | 1.4.3 - Participation in field days and agriculture shows/fairs but target communities | 5070 | 18240 |  |  | 1.4.3 - Participation in field days and agriculture shows/fairs but target communities | 17429 | 18240
|  | 1.4.4 - Knowledge exchange coalitions for climate change adaptation | 58532.38 | Scheduled as a Year 2 activity, though some preparatory activities have begun. |  |  | 1.4.4 - Knowledge exchange coalitions for climate change adaptation | 60680 |  |  |  | 1.4.4 - Knowledge exchange coalitions for climate change adaptation | 60680 | 35000 |  |  | 1.4.4 - Knowledge exchange coalitions for climate change adaptation | 53213 | 35000
Component 2 | Output 2.1 | 2.1.1 - Conduct stakeholder mapping and capacity needs assessment on integration of climate change in extension programmes at sub-national level. | 3784.88 |  | Component 2 | Output 2.1 | 2.1.1 - Conduct stakeholder mapping and capacity needs assessment on integration of climate change in extension programmes at sub-national level. | 56095 |  | Component 2 | Output 2.1 | 2.1.1 - Conduct stakeholder mapping and capacity needs assessment on integration of climate change in extension programmes at sub-national level. | 58298.6037 | 58298.6037 | Component 2 | Output 2.1 | 2.1.1 - Conduct stakeholder mapping and capacity needs assessment on integration of climate change in extension programmes at sub-national level. | 58298.6037 | 58298.6037
|  | 2.1.2 - Development of a capacity development plan to integrate climate change in extension programmes at sub-national level. | 0 |  |  |  | 2.1.2 - Development of a capacity development plan to integrate climate change in extension programmes at sub-national level. | 24957 |  |  |  | 2.1.2 - Development of a capacity development plan to integrate climate change in extension programmes at sub-national level. | 25937.7014 | 25937.7014 |  |  | 2.1.2 - Development of a capacity development plan to integrate climate change in extension programmes at sub-national level. | 25937.7014 | 25937.7014
| Output 2.2 | 2.2.1 - Stocktaking and identification of actors | 0 |  |  | Output 2.2 | 2.2.1 - Stocktaking and identification of actors | 0 |  |  | Output 2.2 | 2.2.1 - Stocktaking and identification of actors | 0 | 0 |  | Output 2.2 | 2.2.1 - Stocktaking and identification of actors | 0 | 0
|  | 2.2.2 - Review/Update FS training manuals on climate change adaptation best practices. | 0 |  |  |  | 2.2.2 - Review/Update FS training manuals on climate change adaptation best practices. | 86253 |  |  |  | 2.2.2 - Review/Update FS training manuals on climate change adaptation best practices. | 89004 | 89004 |  |  | 2.2.2 - Review/Update FS training manuals on climate change adaptation best practices. | 89004 | 89004
|  | 2.2.3 - Workshop to validate the climate training curriculum and modules among key stakeholders followed by printing and dissemination of the curriculum | 0 | Year 2 activity |  |  | 2.2.3 - Workshop to validate the climate training curriculum and modules among key stakeholders followed by printing and dissemination of the curriculum | 68427 |  |  |  | 2.2.3 - Workshop to validate the climate training curriculum and modules among key stakeholders followed by printing and dissemination of the curriculum | 44059 | 44059 |  |  | 2.2.3 - Workshop to validate the climate training curriculum and modules among key stakeholders followed by printing and dissemination of the curriculum | 44059 | 44059
|  | 2.2.4 - National and sub-national training of extension actors on climate sensitive extension services. | 103142.14 |  |  |  | 2.2.4 - National and sub-national training of extension actors on climate sensitive extension services. | 129284 |  |  |  | 2.2.4 - National and sub-national training of extension actors on climate sensitive extension services. | 142587 | 274800 |  |  | 2.2.4 - National and sub-national training of extension actors on climate sensitive extension services. | 256987 | 274800 |  | TOTAL | 0
| Output 2.3 | 2.3.1 - Establishment of a knowledge and experience sharing platform following review of existing information systems | 95180.98 |  |  | Output 2.3 | 2.3.1 - Establishment of a knowledge and experience sharing platform following review of existing information systems | 106403 |  |  | Output 2.3 | 2.3.1 - Establishment of a knowledge and experience sharing platform following review of existing information systems | 126165 | 263830 |  | Output 2.3 | 2.3.1 - Establishment of a knowledge and experience sharing platform following review of existing information systems | 141834 | 263830
|  | 2.3.2 - Dissemination of timely information on climate impacts and weather forecasts through selected community radio, social media and print channels. | 0 |  |  |  | 2.3.2 - Dissemination of timely information on climate impacts and weather forecasts through selected community radio, social media and print channels. | 35213 |  |  |  | 2.3.2 - Dissemination of timely information on climate impacts and weather forecasts through selected community radio, social media and print channels. | 36171 | 54426 |  |  | 2.3.2 - Dissemination of timely information on climate impacts and weather forecasts through selected community radio, social media and print channels. | 52079 | 54426 | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
|  | 2.3.3 - Formation of dialogue groups for information exchange on climate adaptation. | 0 | Year 2 activity |  |  | 2.3.3 - Formation of dialogue groups for information exchange on climate adaptation. | 3081 |  |  |  | 2.3.3 - Formation of dialogue groups for information exchange on climate adaptation. | 3168 | 36368 |  |  | 2.3.3 - Formation of dialogue groups for information exchange on climate adaptation. | 5392 | 36368 | How much of the total co-financing as committed in the Project Document has actually been realized?
| Output 2.4 | 2.4.1 - Awareness creation workshops among FS support actors | 27725.25 | Scheduled as a Year 2 activity, though some preparatory activities have begun. |  | Output 2.4 | 2.4.1 - Awareness creation workshops among FS support actors | 74225 |  |  | Output 2.4 | 2.4.1 - Awareness creation workshops among FS support actors | 59655 | 96000 |  | Output 2.4 | 2.4.1 - Awareness creation workshops among FS support actors | 101570 | 96000
|  | 2.4.2 - Development of a generic climate module for FS practice on climate change adaptation and ecosystem resilience strategies. | 0 |  |  |  | 2.4.2 - Development of a generic climate module for FS practice on climate change adaptation and ecosystem resilience strategies. | 0 |  |  |  | 2.4.2 - Development of a generic climate module for FS practice on climate change adaptation and ecosystem resilience strategies. | 28954 | 74320 |  |  | 2.4.2 - Development of a generic climate module for FS practice on climate change adaptation and ecosystem resilience strategies. | 29810 | 74320 | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
|  | 2.4.3 - Refresher training of practicing Field School Master trainers in the region on the climate module and adaptation strategies | 5194 | Scheduled as a Year 2 activity, though some preparatory activities have begun. |  |  | 2.4.3 - Refresher training of practicing Field School Master trainers in the region on the climate module and adaptation strategies | 8535 |  |  |  | 2.4.3 - Refresher training of practicing Field School Master trainers in the region on the climate module and adaptation strategies | 11639 | 106879 |  |  | 2.4.3 - Refresher training of practicing Field School Master trainers in the region on the climate module and adaptation strategies | 45456 | 106879
|  | 2.4.4 - Lobbying and advocacy for climate sensitive FS | 4872.2 |  |  |  | 2.4.4 - Lobbying and advocacy for climate sensitive FS | 1094 |  |  |  | 2.4.4 - Lobbying and advocacy for climate sensitive FS | 1094 | 27843 |  |  | 2.4.4 - Lobbying and advocacy for climate sensitive FS | 11889 | 27843 | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Component 3 | Output 3.1 | 3.1.1 - Improved tailored seasonal climate forecasts and climate change projections | 47861 |  | Component 3 | Output 3.1 | 3.1.1 - Improved tailored seasonal climate forecasts and climate change projections | 116793 |  | Component 3 | Output 3.1 | 3.1.1 - Improved tailored seasonal climate forecasts and climate change projections | 169879.97 | 120000 | Component 3 | Output 3.1 | 3.1.1 - Improved tailored seasonal climate forecasts and climate change projections | 209468 | 180000
|  | 3.1.2 - Training and capacity building in downscaling techniques and communication of uncertainties | 19577 |  |  |  | 3.1.2 - Training and capacity building in downscaling techniques and communication of uncertainties | 29373 |  |  |  | 3.1.2 - Training and capacity building in downscaling techniques and communication of uncertainties | 29372.8 | 40000 |  |  | 3.1.2 - Training and capacity building in downscaling techniques and communication of uncertainties | 37616 | 40000
|  | 3.1.3 - High resolution forecast downscaling to farming community level | 2459 |  |  |  | 3.1.3 - High resolution forecast downscaling to farming community level | 0 |  |  |  | 3.1.3 - High resolution forecast downscaling to farming community level | 0 | 20000 |  |  | 3.1.3 - High resolution forecast downscaling to farming community level | 0 | 30000
|  | 3.1.4 - Establishment of historical climate baseline statistics, trends and historical and future climate change hotspots (areas of concern) for selected communities | 11031.51 |  |  |  | 3.1.4 - Establishment of historical climate baseline statistics, trends and historical and future climate change hotspots (areas of concern) for selected communities | 11032 |  |  |  | 3.1.4 - Establishment of historical climate baseline statistics, trends and historical and future climate change hotspots (areas of concern) for selected communities | 11031.5 | 20000 |  |  | 3.1.4 - Establishment of historical climate baseline statistics, trends and historical and future climate change hotspots (areas of concern) for selected communities | 11031.5 | 20000
| Output 3.2 | 3.2.1 - Database for intermediaries and famer users established | 4142.76 |  |  | Output 3.2 | 3.2.1 - Database for intermediaries and famer users established | 0 |  |  | Output 3.2 | 3.2.1 - Database for intermediaries and famer users established | 0 | 15000 |  | Output 3.2 | 3.2.1 - Database for intermediaries and famer users established | 0 | 15000
|  | 3.2.2 - Existing feedback mechanisms reviewed | 4586 |  |  |  | 3.2.2 - Existing feedback mechanisms reviewed | 5354 |  |  |  | 3.2.2 - Existing feedback mechanisms reviewed | 5353.76 | 10000 |  |  | 3.2.2 - Existing feedback mechanisms reviewed | 5353.76 | 10000
|  | 3.2.3 - A cost effective communication and feedback channel designed, tested and validated | 0 |  |  |  | 3.2.3 - A cost effective communication and feedback channel designed, tested and validated | 21170 |  |  |  | 3.2.3 - A cost effective communication and feedback channel designed, tested and validated | 23904.7 | 25000 |  |  | 3.2.3 - A cost effective communication and feedback channel designed, tested and validated | 37048.7 | 35000
| Output 3.3 | 3.3.1 - Seasonal agriculture planners regularly produced through national participatory planning workshops | 32005.5 |  |  | Output 3.3 | 3.3.1 - Seasonal agriculture planners regularly produced through national participatory planning workshops | 45903 |  |  | Output 3.3 | 3.3.1 - Seasonal agriculture planners regularly produced through national participatory planning workshops | 55886.49 | 80000 |  | Output 3.3 | 3.3.1 - Seasonal agriculture planners regularly produced through national participatory planning workshops | 89882.25 | 120000
|  | 3.3.2 - Continuous monitoring and evaluation | 58401.38 |  |  |  | 3.3.2 - Continuous monitoring and evaluation | 62353 |  |  |  | 3.3.2 - Continuous monitoring and evaluation | 64803.44 | 84803.44 |  |  | 3.3.2 - Continuous monitoring and evaluation | 140076.44 | 94803.44
|  | 3.3.3 - Identified intermediaries trained in PICSA and PSP approaches | 11253 |  |  |  | 3.3.3 - Identified intermediaries trained in PICSA and PSP approaches | 16464 |  |  |  | 3.3.3 - Identified intermediaries trained in PICSA and PSP approaches | 16463.5 | 30000 |  |  | 3.3.3 - Identified intermediaries trained in PICSA and PSP approaches | 23766.5 | 40000
|  | 3.3.4 - Capacity for agro-met divisions at NMHS and ICPAC strengthened | 8224.45 |  |  |  | 3.3.4 - Capacity for agro-met divisions at NMHS and ICPAC strengthened | 90460 |  |  |  | 3.3.4 - Capacity for agro-met divisions at NMHS and ICPAC strengthened | 63616.96 | 95383.46 |  |  | 3.3.4 - Capacity for agro-met divisions at NMHS and ICPAC strengthened | 68233.5 | 115383.46
|  | 3.3.5 - Advocacy and effective communication of project outcomes | 7050.77 |  |  |  | 3.3.5 - Advocacy and effective communication of project outcomes | 55902 |  |  |  | 3.3.5 - Advocacy and effective communication of project outcomes | 56337.84 | 112000 |  |  | 3.3.5 - Advocacy and effective communication of project outcomes | 93609.83 | 168000
| Output 3.4 | 3.4.1 - Documentation and dissemination of good practices and lessons learned on the use of climate information in agricultural decision making | 1314.6 |  |  | Output 3.4 | 3.4.1 - Documentation and dissemination of good practices and lessons learned on the use of climate information in agricultural decision making | 1230 |  |  | Output 3.4 | 3.4.1 - Documentation and dissemination of good practices and lessons learned on the use of climate information in agricultural decision making | 1230.42 | 20000 |  | Output 3.4 | 3.4.1 - Documentation and dissemination of good practices and lessons learned on the use of climate information in agricultural decision making | 32703.42 | 40000
|  | 3.4.2 - Conducting regional and national learning forums | 30590 |  |  |  | 3.4.2 - Conducting regional and national learning forums | 51906 |  |  |  | 3.4.2 - Conducting regional and national learning forums | 54305.5 | 80000 |  |  | 3.4.2 - Conducting regional and national learning forums | 102989.5 | 110000
|  | 3.4.3 - Improved regional food and nutrition security assessment coordination including capacity building on attribution of food insecurity to various climate related hazards. | 0 |  |  |  | 3.4.3 - Improved regional food and nutrition security assessment coordination including capacity building on attribution of food insecurity to various climate related hazards. | 0 |  |  |  | 3.4.3 - Improved regional food and nutrition security assessment coordination including capacity building on attribution of food insecurity to various climate related hazards. | 0 | 40000 |  |  | 3.4.3 - Improved regional food and nutrition security assessment coordination including capacity building on attribution of food insecurity to various climate related hazards. | 0 | 60000
|  | 3.4.4 - Publication of key findings in peer-reviewed journals | 0 | Year 2 activity |  |  | 3.4.4 - Publication of key findings in peer-reviewed journals | 0 |  |  |  | 3.4.4 - Publication of key findings in peer-reviewed journals | 0 | 5000 |  |  | 3.4.4 - Publication of key findings in peer-reviewed journals | 1670.37 | 10000
|  | Execution costs | 363288.03 |  |  |  | Execution costs | 507224 |  |  |  | Execution costs | 608880.16 | 616962 |  |  | Execution costs | 608880 | 643768
[12 empty] | Project support costs | 250334 | 482388 |  |  | Project support costs | 376403 | 482388
|  | TOTAL | 1581373.39 |  |  |  | TOTAL | 2501292 |  |  |  | TOTAL | 3264252.345 | 6107079.205 |  |  | TOTAL | 4564786.075 | 6424885.205
PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED (Actual) COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED (Actual) COST | Est. Completion Date
Component 1 | Output 1.1 | 1.1.1 - 10 day training at sub-national level of Agric and Met staff on Participatory planning approaches | 6316 | October 2019 (activity largely complete) | Component 1 | Output 1.1 | 1.1.1 - 10 day training at sub-national level of Agric and Met staff on Participatory planning approaches | 0 | Complete | Component 1 | Output 1.1 | 1.1.1 - 10 day training at sub-national level of Agric and Met staff on Participatory planning approaches | 0 | Complete | Component 1 | Output 1.1 | 1.1.1 - 10 day training at sub-national level of Agric and Met staff on Participatory planning approaches | 0 | Complete
|  | 1.1.2 - Community sensitization, mobilization and launching of the community adaptation planning processes. | 833.63 | October 2019 (activity largely complete) |  |  | 1.1.2 - Community sensitization, mobilization and launching of the community adaptation planning processes. | 0 | Complete |  |  | 1.1.2 - Community sensitization, mobilization and launching of the community adaptation planning processes. | 0 | Complete |  |  | 1.1.2 - Community sensitization, mobilization and launching of the community adaptation planning processes. | 0 | Complete
|  | 1.1.3 - Context analysis and stocktaking at community level | 11614.05 | 2019-12-01 |  |  | 1.1.3 - Context analysis and stocktaking at community level | 3860 | Largely complete |  |  | 1.1.3 - Context analysis and stocktaking at community level | 3860 | Largely complete. |  |  | 1.1.3 - Context analysis and stocktaking at community level | 3640 | Largely complete.
|  | 1.1.4 - Seasonal short term adaptation planning of 1-2 days in each target community | 9919.2 | Seasonal and annual activity - ongoing up to end of project. |  |  | 1.1.4 - Seasonal short term adaptation planning of 1-2 days in each target community | 2629 | Seasonal and annual activity - ongoing up to end of project. |  |  | 1.1.4 - Seasonal short term adaptation planning of 1-2 days in each target community | 106 | Largely complete |  |  | 1.1.4 - Seasonal short term adaptation planning of 1-2 days in each target community | 0 | Largely complete
|  | 1.1.5 - longer term adaptation planning over a period of seven to ten days in each community | 42127.6 | 2020-02-01 |  |  | 1.1.5 - longer term adaptation planning over a period of seven to ten days in each community | 1401 | Largely complete |  |  | 1.1.5 - longer term adaptation planning over a period of seven to ten days in each community | 0 | Complete |  |  | 1.1.5 - longer term adaptation planning over a period of seven to ten days in each community | 0 | Complete
|  | 1.1.6 - Validation of community adaptation plans | 27000 | 2020-03-01 |  |  | 1.1.6 - Validation of community adaptation plans | 9815 | 2020-12-01 |  |  | 1.1.6 - Validation of community adaptation plans | 8534 | Only Uganda remaining. December 2021. |  |  | 1.1.6 - Validation of community adaptation plans | 4798 | Largely complete.
| Output 1.2 | 1.2.1 - Baseline and endline data collection | 119461.35 | Baseline survey complete. Funds will be carried forward for regular monitoring and endline survey. |  | Output 1.2 | 1.2.1 - Baseline and endline data collection | 72093 | Baseline survey complete. Funds carried forward are being used for regular monitoring and for endline survey. |  | Output 1.2 | 1.2.1 - Baseline and endline data collection | 60429 | Baseline survey complete. Funds carried forward are being used for regular monitoring and for endline survey. |  | Output 1.2 | 1.2.1 - Baseline and endline data collection | 67728 | Baseline survey complete. Funds carried forward are being used for regular monitoring and for endline survey.
|  | 1.2.2 - 4-week training of facilitators (ToFs) courses on the APFS approach | 123237.17 | 2019-12-01 |  |  | 1.2.2 - 4-week training of facilitators (ToFs) courses on the APFS approach | 86577 | 2021-08-01 |  |  | 1.2.2 - 4-week training of facilitators (ToFs) courses on the APFS approach | 59287 | Largely complete - funds carried forward for follow up trainings. |  |  | 1.2.2 - 4-week training of facilitators (ToFs) courses on the APFS approach | 79468 | Largely complete - funds carried forward for follow up trainings.
|  | 1.2.3 - Community Ground working will be undertaken in each target community | 16615.56 | October 2019 (activity largely complete) |  |  | 1.2.3 - Community Ground working will be undertaken in each target community | 7685 | Largely complete - Will be used for regular community interactions. |  |  | 1.2.3 - Community Ground working will be undertaken in each target community | 11458 | Largely complete - Will be used for regular community interactions. |  |  | 1.2.3 - Community Ground working will be undertaken in each target community | 7288 | Largely complete - being used for regular community interactions.
|  | 1.2.4 - Facilitation of participatory learning in APFS group trough groups meeting on weekly basis over appr 1.5 years period | 38915.99 | Seasonal and annual activity - December 2020 |  |  | 1.2.4 - Facilitation of participatory learning in APFS group trough groups meeting on weekly basis over appr 1.5 years period | 35673 | Delayed by COVID - August 2021 |  |  | 1.2.4 - Facilitation of participatory learning in APFS group trough groups meeting on weekly basis over appr 1.5 years period | 35351 | Ongoing May 2022. |  |  | 1.2.4 - Facilitation of participatory learning in APFS group trough groups meeting on weekly basis over appr 1.5 years period | 12809 | Largely complete - carried forward for monitoring and community engagements
|  | 1.2.5 - Provision of learning materials package/grants to APFS groups | 27000 | 2020-02-01 |  |  | 1.2.5 - Provision of learning materials package/grants to APFS groups | 20889 | Delayed by COVID - December 2020 |  |  | 1.2.5 - Provision of learning materials package/grants to APFS groups | 17531 | Ongoing December 2021. |  |  | 1.2.5 - Provision of learning materials package/grants to APFS groups | 7634 | 2023-12-01
| Output 1.3 | 1.3.1 - Training of communities in village savings systems (VSLA/VICOBA) and financial management and support for establishment of community savings and banking schemes. | 24000 | 2020-06-01 |  | Output 1.3 | 1.3.1 - Training of communities in village savings systems (VSLA/VICOBA) and financial management and support for establishment of community savings and banking schemes. | 24000 | Delayed by COVID - June 2021 |  | Output 1.3 | 1.3.1 - Training of communities in village savings systems (VSLA/VICOBA) and financial management and support for establishment of community savings and banking schemes. | 22018 | Delayed by COVID - June 2021 |  | Output 1.3 | 1.3.1 - Training of communities in village savings systems (VSLA/VICOBA) and financial management and support for establishment of community savings and banking schemes. | 19425 | Begun
|  | 1.3.2 - Support to development of community adaptation investment proposal in target communities. | 61998.29 | 2020-02-01 |  |  | 1.3.2 - Support to development of community adaptation investment proposal in target communities. | 21850 | 2020-12-01 |  |  | 1.3.2 - Support to development of community adaptation investment proposal in target communities. | 22702 | 2021-12-01 |  |  | 1.3.2 - Support to development of community adaptation investment proposal in target communities. | 3941 | Largely complete - carried forward for monitoring and community engagements
|  | 1.3.3 - Technical review and screening of proposals through multi-sectoral proposal review group | 30000 | 2020-03-01 |  |  | 1.3.3 - Technical review and screening of proposals through multi-sectoral proposal review group | 30000 | 2020-12-01 |  |  | 1.3.3 - Technical review and screening of proposals through multi-sectoral proposal review group | 15906 | 2021-12-02 |  |  | 1.3.3 - Technical review and screening of proposals through multi-sectoral proposal review group | 16311 | Largely complete - carried forward for monitoring and community engagements
|  | 1.3.4 - Community investment grant financing | 1692861.67 | 2020-08-01 |  |  | 1.3.4 - Community investment grant financing | 1697943 | Delayed by COVID - August 2021 |  |  | 1.3.4 - Community investment grant financing | 1566211 | 2022-08-01 |  |  | 1.3.4 - Community investment grant financing | 1015006 | 2023-12-01
|  | 1.3.5 - Technical backstopping and monitoring of beneficiary community investment project implementation. | 62030.93 | Ongoing through to end of project |  |  | 1.3.5 - Technical backstopping and monitoring of beneficiary community investment project implementation. | 148955 | Ongoing through to end of project |  |  | 1.3.5 - Technical backstopping and monitoring of beneficiary community investment project implementation. | 16183 | Ongoing through to end of project |  |  | 1.3.5 - Technical backstopping and monitoring of beneficiary community investment project implementation. | 24546 | Ongoing through to end of project
| Output 1.4 | 1.4.1 - Within country community exchange visits | 26250 | 2020-11-01 |  | Output 1.4 | 1.4.1 - Within country community exchange visits | 26250 | Delayed by COVID - August 2021 |  | Output 1.4 | 1.4.1 - Within country community exchange visits | 26250 | Delayed by COVID - August 2022 |  | Output 1.4 | 1.4.1 - Within country community exchange visits | 7842 | Ongoing
|  | 1.4.2 - Community and site participation in project review processes | 3000 | 2020-08-01 |  |  | 1.4.2 - Community and site participation in project review processes | 1575 | Delayed by COVID - August 2021 |  |  | 1.4.2 - Community and site participation in project review processes | 2595 | Mostly Uganda. December 2021. |  |  | 1.4.2 - Community and site participation in project review processes | 1574 | Largely complete - carried forward for monitoring and community engagements
|  | 1.4.3 - Participation in field days and agriculture shows/fairs but target communities | 18240 | Seasonal and annual activity |  |  | 1.4.3 - Participation in field days and agriculture shows/fairs but target communities | 15951 | Seasonal and annual activity |  |  | 1.4.3 - Participation in field days and agriculture shows/fairs but target communities | 12930 | Seasonal and annual activity |  |  | 1.4.3 - Participation in field days and agriculture shows/fairs but target communities | 811 | Seasonal and annual activity.
|  | 1.4.4 - Knowledge exchange coalitions for climate change adaptation | 0 | Ongoing through to end of project |  |  | 1.4.4 - Knowledge exchange coalitions for climate change adaptation | 0 |  |  |  | 1.4.4 - Knowledge exchange coalitions for climate change adaptation | 0 |  |  |  | 1.4.4 - Knowledge exchange coalitions for climate change adaptation | 0
Component 2 | Output 2.1 | 2.1.1 - Conduct stakeholder mapping and capacity needs assessment on integration of climate change in extension programmes at sub-national level. | 51257.12 | 2019-12-01 | Component 2 | Output 2.1 | 2.1.1 - Conduct stakeholder mapping and capacity needs assessment on integration of climate change in extension programmes at sub-national level. | 0 | Complete | Component 2 | Output 2.1 | 2.1.1 - Conduct stakeholder mapping and capacity needs assessment on integration of climate change in extension programmes at sub-national level. | 0 | Complete | Component 2 | Output 2.1 | 2.1.1 - Conduct stakeholder mapping and capacity needs assessment on integration of climate change in extension programmes at sub-national level. | 0 | Complete
|  | 2.1.2 - Development of a capacity development plan to integrate climate change in extension programmes at sub-national level. | 30000 | 2020-01-01 |  |  | 2.1.2 - Development of a capacity development plan to integrate climate change in extension programmes at sub-national level. | 3043 | Largely complete |  |  | 2.1.2 - Development of a capacity development plan to integrate climate change in extension programmes at sub-national level. | 2062.2986 | Largely complete. Carried forward for follow ups. |  |  | 2.1.2 - Development of a capacity development plan to integrate climate change in extension programmes at sub-national level. | 0 | Largely complete. Carried forward for follow ups.
| Output 2.2 | 2.2.1 - Stocktaking and identification of actors | 0 | Ongoing - No cost |  | Output 2.2 | 2.2.1 - Stocktaking and identification of actors | 0 | Ongoing - No cost |  | Output 2.2 | 2.2.1 - Stocktaking and identification of actors | 0 | Ongoing - No cost |  | Output 2.2 | 2.2.1 - Stocktaking and identification of actors | 0 | Ongoing - No cost
|  | 2.2.2 - Review/Update FS training manuals on climate change adaptation best practices. | 87000 | 2019-12-01 |  |  | 2.2.2 - Review/Update FS training manuals on climate change adaptation best practices. | 0 | Complete |  |  | 2.2.2 - Review/Update FS training manuals on climate change adaptation best practices. | 0 | Complete |  |  | 2.2.2 - Review/Update FS training manuals on climate change adaptation best practices. | 0 | Complete
|  | 2.2.3 - Workshop to validate the climate training curriculum and modules among key stakeholders followed by printing and dissemination of the curriculum | 68103 | 2020-03-01 |  |  | 2.2.3 - Workshop to validate the climate training curriculum and modules among key stakeholders followed by printing and dissemination of the curriculum | 0 | Complete. |  |  | 2.2.3 - Workshop to validate the climate training curriculum and modules among key stakeholders followed by printing and dissemination of the curriculum | 24044 | Largely complete. Funds being used for follow up activities. |  |  | 2.2.3 - Workshop to validate the climate training curriculum and modules among key stakeholders followed by printing and dissemination of the curriculum | 0 | Largely complete. Funds being used for follow up activities.
|  | 2.2.4 - National and sub-national training of extension actors on climate sensitive extension services. | 171657.86 | Initally budgeted under Year 1, however for the rational flow of project activities this has been agreed to be moved to Year 2 activity - August 2020 |  |  | 2.2.4 - National and sub-national training of extension actors on climate sensitive extension services. | 145516 | Delayed by COVID - August 2021 |  |  | 2.2.4 - National and sub-national training of extension actors on climate sensitive extension services. | 132213 | Delayed by COVID - May 2022 |  |  | 2.2.4 - National and sub-national training of extension actors on climate sensitive extension services. | 17813 | Funds to be used for follow up trainings. April 2023.
| Output 2.3 | 2.3.1 - Establishment of a knowledge and experience sharing platform following review of existing information systems | 168649.02 | 2020-08-01 |  | Output 2.3 | 2.3.1 - Establishment of a knowledge and experience sharing platform following review of existing information systems | 157427 | Ongoing |  | Output 2.3 | 2.3.1 - Establishment of a knowledge and experience sharing platform following review of existing information systems | 137665 | Ongoing |  | Output 2.3 | 2.3.1 - Establishment of a knowledge and experience sharing platform following review of existing information systems | 121996 | Ongoing. December 2023
|  | 2.3.2 - Dissemination of timely information on climate impacts and weather forecasts through selected community radio, social media and print channels. | 63000 | Initially budgeted under Year 1, however, in consultation with the National Meteorological and Hydrological Services (NMHSs) this has now been planned to be utilised in Year 2 and 3. |  |  | 2.3.2 - Dissemination of timely information on climate impacts and weather forecasts through selected community radio, social media and print channels. | 27787 | LoAs with National Meteorological services in all 3 countries signed and funds disbursed to 2 of the 3. Remaining funds here are for the disbursement to the 3rd NMS and for WMO support to their activities. |  |  | 2.3.2 - Dissemination of timely information on climate impacts and weather forecasts through selected community radio, social media and print channels. | 26829 | LoAs with National Meteorological Services in all 3 countries signed and funds disbursed to all 3. Remaining funds here are either committed or will be used by WMO to support their activities (support missions). |  |  | 2.3.2 - Dissemination of timely information on climate impacts and weather forecasts through selected community radio, social media and print channels. | 2347 | LoAs with National Meteorological Services in all 3 countries signed and funds disbursed to all 3. Remaining funds here are either committed or will be used by WMO to support their activities.
|  | 2.3.3 - Formation of dialogue groups for information exchange on climate adaptation. | 36368 | 2020-08-01 |  |  | 2.3.3 - Formation of dialogue groups for information exchange on climate adaptation. | 33287 | 2021-08-01 |  |  | 2.3.3 - Formation of dialogue groups for information exchange on climate adaptation. | 33200 | 2022-08-01 |  |  | 2.3.3 - Formation of dialogue groups for information exchange on climate adaptation. | 30976 | Delayed.
| Output 2.4 | 2.4.1 - Awareness creation workshops among FS support actors | 68274.75 | 2020-03-01 |  | Output 2.4 | 2.4.1 - Awareness creation workshops among FS support actors | 21775 | 2021-03-01 |  | Output 2.4 | 2.4.1 - Awareness creation workshops among FS support actors | 36345 | 2022-03-01 |  | Output 2.4 | 2.4.1 - Awareness creation workshops among FS support actors | 0 | Largely complete
|  | 2.4.2 - Development of a generic climate module for FS practice on climate change adaptation and ecosystem resilience strategies. | 74320 | 2020-05-01 |  |  | 2.4.2 - Development of a generic climate module for FS practice on climate change adaptation and ecosystem resilience strategies. | 74320 | Delayed due to unavailability of identified consultant - December 2020 |  |  | 2.4.2 - Development of a generic climate module for FS practice on climate change adaptation and ecosystem resilience strategies. | 74320 | Delayed due to unavailability of identified consultant - December 2020 |  |  | 2.4.2 - Development of a generic climate module for FS practice on climate change adaptation and ecosystem resilience strategies. | 44510 | Activity conducted. Funds will be used for review and validation.
|  | 2.4.3 - Refresher training of practicing Field School Master trainers in the region on the climate module and adaptation strategies | 101685 | 2020-08-01 |  |  | 2.4.3 - Refresher training of practicing Field School Master trainers in the region on the climate module and adaptation strategies | 98344 | 2021-03-01 |  |  | 2.4.3 - Refresher training of practicing Field School Master trainers in the region on the climate module and adaptation strategies | 95240 | 2022-03-01 |  |  | 2.4.3 - Refresher training of practicing Field School Master trainers in the region on the climate module and adaptation strategies | 61423 | Funds to be used for follow up trainings. April 2023.
|  | 2.4.4 - Lobbying and advocacy for climate sensitive FS | 22970.8 | Ongoing annual activity |  |  | 2.4.4 - Lobbying and advocacy for climate sensitive FS | 26749 | Ongoing annual activity |  |  | 2.4.4 - Lobbying and advocacy for climate sensitive FS | 26749 | Ongoing annual activity |  |  | 2.4.4 - Lobbying and advocacy for climate sensitive FS | 15954 | Ongoing annual activity
Component 3 | Output 3.1 | 3.1.1 - Improved tailored seasonal climate forecasts and climate change projections | 72139 | Seasonal activity | Component 3 | Output 3.1 | 3.1.1 - Improved tailored seasonal climate forecasts and climate change projections | 3207 | Ongoing - Seasonal activity | Component 3 | Output 3.1 | 3.1.1 - Improved tailored seasonal climate forecasts and climate change projections | 10120.03 | Ongoing - Seasonal activity | Component 3 | Output 3.1 | 3.1.1 - Improved tailored seasonal climate forecasts and climate change projections | 0 | Ongoing - Seasonal activity
|  | 3.1.2 - Training and capacity building in downscaling techniques and communication of uncertainties | 20423 | Seasonal and annual activity |  |  | 3.1.2 - Training and capacity building in downscaling techniques and communication of uncertainties | 10627 | Ongoing - Seasonal activity |  |  | 3.1.2 - Training and capacity building in downscaling techniques and communication of uncertainties | 10627.2 | Ongoing - Seasonal activity |  |  | 3.1.2 - Training and capacity building in downscaling techniques and communication of uncertainties | 2384 | Ongoing - Seasonal activity
|  | 3.1.3 - High resolution forecast downscaling to farming community level | 17541 | Seasonal and annual activity |  |  | 3.1.3 - High resolution forecast downscaling to farming community level | 20000 | Ongoing up to end of project. |  |  | 3.1.3 - High resolution forecast downscaling to farming community level | 20000 | Ongoing up to end of project. |  |  | 3.1.3 - High resolution forecast downscaling to farming community level | 30000 | Ongoing up to end of project.
|  | 3.1.4 - Establishment of historical climate baseline statistics, trends and historical and future climate change hotspots (areas of concern) for selected communities | 8968.49 | 2020-05-01 |  |  | 3.1.4 - Establishment of historical climate baseline statistics, trends and historical and future climate change hotspots (areas of concern) for selected communities | 8968 | Historical analysis complete. Future CC scenario analysis workshop delayed by COVID - May 2021 |  |  | 3.1.4 - Establishment of historical climate baseline statistics, trends and historical and future climate change hotspots (areas of concern) for selected communities | 8968.5 | Historical analysis complete. Future CC scenario analysis workshop delayed by COVID - May 2021 |  |  | 3.1.4 - Establishment of historical climate baseline statistics, trends and historical and future climate change hotspots (areas of concern) for selected communities | 8968.5 | Historical analysis complete. Future CC scenario analysis complete, report and pending.
| Output 3.2 | 3.2.1 - Database for intermediaries and famer users established | 10857.24 | 2020-08-01 |  | Output 3.2 | 3.2.1 - Database for intermediaries and famer users established | 15000 | Ongoing - December 2020 |  | Output 3.2 | 3.2.1 - Database for intermediaries and famer users established | 15000 | Ongoing - December 2021 |  | Output 3.2 | 3.2.1 - Database for intermediaries and famer users established | 15000 | Ongoing
|  | 3.2.2 - Existing feedback mechanisms reviewed | 5414 | 2020-06-01 |  |  | 3.2.2 - Existing feedback mechanisms reviewed | 4646 | Mostly complete - remaining funds to be carried forward for follow up surveys and finalising reports. |  |  | 3.2.2 - Existing feedback mechanisms reviewed | 4646.24 | Mostly complete - remaining funds to be carried forward for follow up surveys and finalising reports. |  |  | 3.2.2 - Existing feedback mechanisms reviewed | 4646.24 | Mostly complete - remaining funds to be carried forward for follow up surveys and finalising reports.
|  | 3.2.3 - A cost effective communication and feedback channel designed, tested and validated | 25000 | 2020-08-01 |  |  | 3.2.3 - A cost effective communication and feedback channel designed, tested and validated | 3830 | Ongoing up to end of project. |  |  | 3.2.3 - A cost effective communication and feedback channel designed, tested and validated | 11095.3 | Ongoing up to end of project. |  |  | 3.2.3 - A cost effective communication and feedback channel designed, tested and validated | 0 | Ongoing up to end of project.
| Output 3.3 | 3.3.1 - Seasonal agriculture planners regularly produced through national participatory planning workshops | 47994.5 | Seasonal and annual activity |  | Output 3.3 | 3.3.1 - Seasonal agriculture planners regularly produced through national participatory planning workshops | 34097 | Ongoing up to end of project. |  | Output 3.3 | 3.3.1 - Seasonal agriculture planners regularly produced through national participatory planning workshops | 24113.51 | Ongoing up to end of project. |  | Output 3.3 | 3.3.1 - Seasonal agriculture planners regularly produced through national participatory planning workshops | 30117.75 | Ongoing up to end of project.
|  | 3.3.2 - Continuous monitoring and evaluation | 1598.62 | Ongoing activity up to end of project. |  |  | 3.3.2 - Continuous monitoring and evaluation | 0 | Ongoing up to end of project. |  |  | 3.3.2 - Continuous monitoring and evaluation | 0 | Ongoing up to end of project. |  |  | 3.3.2 - Continuous monitoring and evaluation | 0 | Ongoing up to end of project.
|  | 3.3.3 - Identified intermediaries trained in PICSA and PSP approaches | 18747 | 2020-05-01 |  |  | 3.3.3 - Identified intermediaries trained in PICSA and PSP approaches | 13536 | Ongoing up to end of project. |  |  | 3.3.3 - Identified intermediaries trained in PICSA and PSP approaches | 23536.5 | PICSA training delayed significantly due to COVID travel restrictions. |  |  | 3.3.3 - Identified intermediaries trained in PICSA and PSP approaches | 16233.5 | PICSA training now April 2023
|  | 3.3.4 - Capacity for agro-met divisions at NMHS and ICPAC strengthened | 91775.55 | Annual activity up to end of project. AWS procurement targetted for Year 2. |  |  | 3.3.4 - Capacity for agro-met divisions at NMHS and ICPAC strengthened | 9540 | Annual activity up to end of project. AWS procurement in process (PO issued). |  |  | 3.3.4 - Capacity for agro-met divisions at NMHS and ICPAC strengthened | 36383.04 | Annual activity up to end of project. AWS procured and installation set for Q42021. |  |  | 3.3.4 - Capacity for agro-met divisions at NMHS and ICPAC strengthened | 47149.96 | Annual activity up to end of project.
|  | 3.3.5 - Advocacy and effective communication of project outcomes | 104949.23 | Ongoing activity up to end of project. |  |  | 3.3.5 - Advocacy and effective communication of project outcomes | 56098 | Ongoing up to end of project. |  |  | 3.3.5 - Advocacy and effective communication of project outcomes | 55662.16 | Ongoing up to end of project. |  |  | 3.3.5 - Advocacy and effective communication of project outcomes | 74390.17 | Ongoing up to end of project.
| Output 3.4 | 3.4.1 - Documentation and dissemination of good practices and lessons learned on the use of climate information in agricultural decision making | 18685.4 | Ongoing activity up to end of project. |  | Output 3.4 | 3.4.1 - Documentation and dissemination of good practices and lessons learned on the use of climate information in agricultural decision making | 18770 | Ongoing up to end of project. |  | Output 3.4 | 3.4.1 - Documentation and dissemination of good practices and lessons learned on the use of climate information in agricultural decision making | 18769.58 | Ongoing up to end of project. |  | Output 3.4 | 3.4.1 - Documentation and dissemination of good practices and lessons learned on the use of climate information in agricultural decision making | 7296.58 | Ongoing up to end of project.
|  | 3.4.2 - Conducting regional and national learning forums | 49410 | Ongoing activity up to end of project. |  |  | 3.4.2 - Conducting regional and national learning forums | 28094 | Ongoing up to end of project. |  |  | 3.4.2 - Conducting regional and national learning forums | 25694.5 | Ongoing up to end of project. Affected by COVID. |  |  | 3.4.2 - Conducting regional and national learning forums | 7010.5 | Ongoing up to end of project.
|  | 3.4.3 - Improved regional food and nutrition security assessment coordination including capacity building on attribution of food insecurity to various climate related hazards. | 40000 | Ongoing activity up to end of project. |  |  | 3.4.3 - Improved regional food and nutrition security assessment coordination including capacity building on attribution of food insecurity to various climate related hazards. | 40000 | Ongoing up to end of project. |  |  | 3.4.3 - Improved regional food and nutrition security assessment coordination including capacity building on attribution of food insecurity to various climate related hazards. | 40000 | Ongoing up to end of project. Affected by COVID. |  |  | 3.4.3 - Improved regional food and nutrition security assessment coordination including capacity building on attribution of food insecurity to various climate related hazards. | 60000 | Ongoing up to end of project.
|  | 3.4.4 - Publication of key findings in peer-reviewed journals | 5000 | Ongoing through Year 2 and Year 3. Three papers currently being written. |  |  | 3.4.4 - Publication of key findings in peer-reviewed journals | 5000 | Ongoing up to end of project. |  |  | 3.4.4 - Publication of key findings in peer-reviewed journals | 5000 | Publications being worked on some at minimal or no cost. |  |  | 3.4.4 - Publication of key findings in peer-reviewed journals | 8329.63 | Publications being worked on some at minimal or no cost.
|  | Execution costs | 159423.97 | Ongoing up to end of project. |  |  | Execution costs | 138776 | Ongoing up to end of project. |  |  | Execution costs | 37119.84 | Ongoing up to end of project. |  |  | Execution costs | 34888 | Ongoing up to end of project.
[12 empty] | Project support costs | 239000 |  |  |  | Project support costs | 105985
|  | TOTAL | 3982633.99 |  |  |  | TOTAL | 3205583 |  |  |  | TOTAL | 3055754.6986 |  |  |  | TOTAL | 2020239.13
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? |  | N/A |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  | N/A |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  | N/A |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  | N/A
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Different pace of project implementation for each country may delay overall project implementation and affect regional activities. | Low | Project structures have been formed at regional (PMT) and national level (PAG) to ensure the project moves at required pace and any key issues are raised and addressed as quickly as possible to enable implementation to proceed.
Uneven speed of implementation and expenditure rate among the three main partners may hamper overall project performance | Medium | Project structures have been formed at regional (Project Management Team (PMT)) and national level (Project Advisory Group (PAG)) to ensure the project moves at required pace and any key issues are raised and addressed as quickly as possible to enable implementation to proceed. Partners are meeting regularly to jointly plan and implement activities.
Irregularities with regards to relationships between executing and implementing bodies | Low | Standard WMO procedures have been used for partner agreements, including the use of Letters of Agreement, UN-to-UN agreements and Implementing Arrangements. WMO reporting requirements are being used for all partners to ensure project status information is regularly updated.
Sub-national governments prioritize alternative implementation frameworks. | Low | Partners have conducted inception missions to, and engaged local authorities in, all three countries at both national and sub-national level. All relevant stakeholders are aware of the project and are taking the project as a key initiative to build resilience and adaptive capacity in the project target locations.
Political uncertainties affect project implementation. | Low | Monitoring of the political and security context in all project target areas in partnership with key stakeholders is ongoing.
Limited awareness and stakeholder involvement on the project | Low | Partners have conducted inception missions to, and engaged local authorities in, all three countries at both national and sub-national level. All relevant stakeholders are aware of the project and are taking the project as a key initiative to build resilience and adaptive capacity in the project target locations.
Occurrence of a major natural disaster in the project areas. | Medium | Project partners continue to monitor the environmental context for any major hazard occurences, particularly in relation to climate hazards, of which the project goal is exactly to cushion and reduce the impacts of climate hazards.
Intercommunity differences regarding adaptation planning priorities in each community. | Low | Community based approaches will be used in all target communities. In particular, a community managed disaster risk reduction approach will be used and combined with participatory climate services approaches. Trainings on participatory approaches have been conducted for local stakeholders as part of the project.
Bias in awarding adaptation proposals. | Low | The project partners will jointly develop adaptation proposal review criteria in partnership with local authorities. The criteria will be developed based on lessons from FAO as well as small grants facilities (SGF) in other Adaptation Fund projects (e.g. South African National Biodiversity Institute (SANBI) project in South Africa).
Movement of trained staff to other sectors or outside the project areas. | Medium | A combination of strategies are being used to mitigate the potential of this risk occuring and reduce the magnitude of impact if it were to occur, including: 1 - Working with farmers directly through the farmer field school approach. 2 - Working with a wide variety of actors, including local organisations where possible, to ensure capacity remains in the project locations. 3 - Development of products that can be used beyond the project lifespan - e.g. training manuals. 4 - Working closely with the local government institutions responsible for agriculture and natural resources management.
Political influence affects adoption of lessons learned into national and regional adaptation strategies. | Low | Advocacy and stakeholder consultation, engagement and senistisation will be conducted throughout project implementation. Policy makers at sub-national level have been engaged and sensitised on the project, as well as being supported to participate in regional climate and food security fora, thus improving appreciation of the projects approach to climate resilience.
Governments continue to prioritize emergency initiatives over development initiatives. | Low | Advocacy and stakeholder consultation, engagement and sensitisation will be conducted throughout project implementation. Policy makers at sub-national level have been engaged and sensitised on the project, as well as being supported to participate in regional climate and food security fora, hence improving appreciation of the resilience building approach being used in the ACREI project.
Weak downscaling capacity to support the project. | Low | Building downscaling capacity is a key part of project implementation - ICPAC has ensured that all participating NMHSs from ACREI project countries are regularly involved in the seasonal forecast generation exercise at regional level, joint downscaling of the forecasts to sub-national level and conducting targetted training ahead of each season.
Limited coordination with other ongoing adaptation initiatives in the target countries. | Low | A review of ongoing initiatives has already been conducted. Consultation and engagement with stakeholders to ensure alignment and additionality to other programmes. In Kenya for example, good synergies have been found with ongoing government and development partner projects and programmes such as the Agriculture Sector development Support Programme (ASDSP) and the DFID funded WISER Coastal Project. Joint workshops have been held and a common approach to programming is being encouraged in consultation with the Taita Taveta CEC for Agriculture, Livestock, Fisheries and Irrigation.
Delays in recruitment or appointment of critical staff for the project. | Low | TORs for key staff developed and vacancy announcements were floated before official project commencement. The use of inhouse expertise among project partners and appointment of focal people from national institutions has been used as a strategy. All relevant staff are now onboard and supporting the project.
Instability in currencies, market prices and availability of project inputs | Medium | Funds received from Adaptation Fund are registered and maintained in CHF (in accordance to WMO financial regulations), with disbursements being made to partners in USD. However, it has been noted that currency exchange fluctuations between the USD and CHF can still have slight impacts on project funds. In Year 1, USD/CHF currency exchange fluctuations occured which negatively affected one executing entity's disbursement amount. To mitigate further currency fluctuation effects, future disbursements to partners are aimed to be conducted as quickly as possible after receipt of funds from the Adaptation Fund. Note that the initial delay between receipt of funds from Adaptation Fund and disbursements being made to partners for Year 1 was due to events outside WMO control and have been communicated to the Adapation Fund.
General financial risks | Low | WMO, FAO and ICPAC financial management procedures are being used to manage financial risks in all project activities and transactions.
Delays in financial disbursements | Low | The use of standard LoAs and UN-to-UN agreements to engage partners and ensure quick disbursement of funds.
Misuse of community financial grants at local level | Medium | Use of recognised community grant mechanisms based on FAO experience on such (e.g. grants mechanisms for Agropastoral Field Schools and the "Njaa Marufuku Kenya". This will be closely monitored in Year 2, when comunity grants begin.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The outbreak of the Covid-19 pandemic at national, regional and global level. | Low | In the last reporting period activities returned to being largely in-person. Remote/ hybrid workshops are still maintained as an option.
Intermittent insecurity concerns in Ethiopia. | Medium | Partners have continued to work through and with local partners, including government departments, who have regular access to project locations. For example, regional bureaus for agriculture. Despite this, the Ethiopia component has fallen behind.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Risks were managed as per previous reporting period and in line with risk mitigation measures noted above. In-person activities have once again become the norm following the end of the COVID pandemic.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
| Was the ESP risks identification complete at the time of funding approval? [1] | No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
| ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
| 1 - Compliance with the law | Yes | No | Lack of compliance with local and national laws in project activities. | Avoidance: Screening activities for compliance with the law. | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | The final project design was made to be compliant with all relevant regional and national laws following extensive consultation with national and regional stakeholders. | All adaptation investments identified to date have been screened for compliance with the law. | None at the moment. | None at the moment.
| 2 - Access and equity | Yes | No | Lack of equity in access to project resources and activities. | Management, mitigation and avoidance: Screening of activities for equity in participation and access to project resources - Using participatory methods in project activities. | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | From the baseline survey: - There is disparity between mens and womens ownership of resilience assets. Ensuring gender equity in access to project resources will be a major area of focus during project implementation. - One project site in Uganda, being a refugee host community, has high disparity between host community households and refugee households in terms of access to assets, trainings, adaptation practices and agricultural income. | - Disclosure of project activities (USPs) with communities and local authorities has been conducted - Farmer field school groups are structured to be diverse and include members from different backgrounds, with some being womens'groups - Selected farmer field school groups in Uganda incoporate vulnerable groups in the form of refugees - Trainings throughout the reporting period have incorporated men and women. - Participatory approaches continue to be used in Year 4 of the project, building on the trainings of Ministry of Agriculture and National Meteorological and Hydrological Services (NMHS) staff on participatory planning that was conducted in Year 1 and 2. | None at the moment. | None at the moment.
| 3 – Marginalized and vulnerable Groups | Yes | No | Exclusion of marginalised and vulnerable groups from project activities. | Management, mitigation & avoidance: Targetting the most vulnerable and food insecure members of society in the target communities. Management: Ensure participation of all relevant stakeholders in project activities without discrimination and with aim to ensure fair and equitable access to project benefits including for women and men as well as marginalized groups. Management: Continue to use proven community based adaptation planning methods that take into account the needs of different socio-economic groups in the community.. | Minutes/ reports of consultations with local authorities on community selection. | From the baseline survey: - There is diparity between mens and womens ownership of resilience assets. Ensuring gender equity in access to project resources will be a major area of focus during project implementation. - One project site in Uganda, being a refugee host community, has high disparity between host community households and refugee households in terms of access to assets, trainings, adaptation practices and agricultural income. - Knowledge on the gendered impacts of climate hazards and climate change is low. Awareness on this aspect will be supported through the community based planning pocesses and various trainings. | - Participatory approaches continue to be used in Year 4 of the project, building on the trainings of Ministry of Agriculture and National Meteorological and Hydrological Services (NMHS) staff on participatory planning that was conducted in Year 1 and 2. - Selected farmer field school groups in Uganda incoporate vulnerable groups in the form of refugees | None at the moment. | None at the moment.
| 4 – Human rights | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 5 – Gender equality and women’s empowerment | Yes | No | Lack of gender equity and women’s empowerment in project implementation and outcomes. | Management, mitigation & avoidance: - Encouraged 50% participation of women in project activities e.g. farmer field school groups - Foster equal participation of men and women in institutions and decision-making processes related to the project. - EEs to capture sex-dissagregated data for project activities and trainings | Participation of men and women in project activities and structures (see project LogFrame). | - There is disparity between mens and womens ownership of resilience assets. Ensuring gender equity in access to project resources will be a major area of focus during project implementation. - Knowledge on the gendered impacts of climate hazards and climate change is low. Awarenes on this aspect will be supported through the community based plannin pocesses and various trainings. - Womens participation in project activities and leadership positions varies from location to location and activity to activity. See the GP Compliance sheet for more details on gender issues arising in the project. | This has built on actions taken in Years 1 and 2 of the project, including the following: - The baseline survey incorporated sex-dissagregated data - Farmers field school groups incoporate both men and women (although the 50% target was not always met), and in some cases the groups are womens'only groups. - All workshops and trainings in Year 4 have incorporated both men and women as participants and as facilitators/ trainers, with the need for gender balance and having women in key roles highlighted. - The project celebrated International Womens' Day 2021 with a story highlighting the role of women in weather and climate reporting. | None at the moment. | None at the moment.
| 6 – Core labour rights | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 7 – Indigenous peoples | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 8 – Involuntary resettlement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 9 – Protection of natural habitats | Yes | No | Damage to natural habitats (as a result of project activities). | Avoidance: Adaptation investment proposals to include screening for encroachment and damage to protected areas, buffer zones and natural habitats. | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | Population growth, resources scarcity, land degradation, low productivity (both livestock and crops), overgrazing, deforestation, invasive species and market fluctuations among others affect the project locations. Adaptation investments/ USPs and specific basleine information related to them are yet to be identified through community based approaches in Year 2 of the project. | Screening of USPs for potential damage and encroachment onto natural habitats. To date no USPs have been found to encroach into natural habitats, buffer zones or protected areas. | None at the moment. | None at the moment.
| 10 – Conservation of biological diversity | Yes | No | Biodiversity loss (as a result of project activities). | Management & mitigation: The climate-smart agriculture approach to be used in farmer field schools. Management, avoidance and mitigation: Farmer field school groups sensitised on issues of biodiversity and its importance. Avoidance: Adaptation investments to be screened against potential to cause biodiversity loss. | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | Population growth, resources scarcity, land degradation, low productivity (both livestock and crops), overgrazing, deforestation, invasive species and market fluctuations among others affect the project locations. Adaptation investments/ USPs and specific basleine information related to them are yet to be identified through community based approaches in Year 2 of the project. | - In Year 4 all USPs identified to date were screened for potential impact on biodiversity of plants and animals. - Seeds promoted in the farmer field schools have been locally sourced. - Farmer field school groups were supported to experiment with a wide variety of seeds nand sensitised on crop diversity as a resilience measure. | None at the moment. | None at the moment.
| 11 – Climate change | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 12 – Pollution prevention and resource efficiency | Yes | No | Pollution and lack of efficiency in use of natural resources. | Management, avoidance & mitigation: The adaptation investments prepared during Year 4 are to be screened against potential to cause pollution. Management: The climate-smart agriculture approach to be promoted in all adaptation invetsments and in farmer field school groups. | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | Population growth, resources scarcity, land degradation, low productivity (both livestock and crops), overgrazing, deforestation, invasive species and market fluctuations among others affect the project locations. Adaptation investments/ USPs and specific basleine information related to them are yet to be identified through community based approaches in Year 2 of the project. | - The adaptation investments prepared during Year 4 were screened against potential to cause pollution - CSA approach is integrated into all project activities - Field days for farmer field school groups displayed and promoted efficient agricultural technologies. | None at the moment. | None at the moment.
| 13 – Public health | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 14 – Physical and cultural heritage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 15 – Lands and soil conservation | Yes | No | Land and soil degradation | Management & mitigation: Farmer field school groups to be sensitised on issues of land and soil conservation in accordance with the climate smart approach. Adaptation investments to be screened for potential negative impact on land and soil resources. | - Minutes/ reports of community adaptation action planning processes and consultations with local authorities. - The community adaptation action plans and the community adaptation investments (i.e. the USPs) themselves. | Population growth, resources scarcity, land degradation, low productivity (both livestock and crops), overgrazing, deforestation, invasive species and market fluctuations among others affect the project locations. Adaptation investments/ USPs and specific baseline information related to them are yet to be identified through community based approaches in Year 2 of the project. | - The adaptation investments prepared during Year 4 were screened for potential for land and soil degradation. The screening found that the investments highly follow a sustainable land management and soil conservation approach. - Farmer field school groups were sensitised on issues of land and soil conservation for resilience and improved productivity | None at the moment. | None at the moment.
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
| Has monitoring for unanticipated ESP risks been carried out? |  | Monitoring of ESP risks is ongoing as part of project activities.
| Have unanticipated ESP risks been identified during the reporting period? |  | None at the moment.
| If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
| Is the categorisation according to ESP standards still relevant? |  | Yes
| If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
| What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | WMO has 1) ensured that EEs are fully aware of the ESP through raising this in meetings and making presentations on the ESP for partners; 2) guided the EEs to integrate ESP principles into their activities (e.g. through drafting or reviewing ESP screening checklists).
| Have the implementation arrangements been effective during the reporting period? |  | Yes, awareness on the ESP has been raised among the EEs and the means of screening for environmental and social risks in the adaptation investments elaborated.
| What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | FAO - Integrated ESP checklist and screening into adaptation investments proposal format for Uganda and Kenya. Staff are monitoring ESP issues during field activities. All USPs developed todate have been screened according to a checklist based on AF ESP. Conducting validation exercises with communities and local authorities. ICPAC - Focusing on gender and inclusive participation in their activities. Had awareness raising related to women and climate e.g. promoting women journalists in weather and climate reporting on International Women’s Day.
| Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes, to date they have been effective: 1) Awareness has been raised among partners and stakeholders on environmental and social risks; 2) the template for the adaptation investments has integrated questions and screening on all the adaptation fund ESP principles; and 3) adaptation investment proposals prepared to date have been screened for environmental and social impacts.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
| Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8] |  | Yes
| Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | The capacity for ESMP at the IE and the EEs is adequate based on their experience implementing similar projects and programmes. The Food and Agriculture Organization (FAO) which is responsible for the community-related and and adaptation grants components of the project have Environmental and Social Management Guidelines as well as principles for sustainable food and agriculture systems which aim to balance economic, social and environmental dimensions of sustainability in agriculture and food systems, and provide a basis for developing policies, regulations and incentives to guide the transition to sustainability, while promoting resilience through an adaptive response to shocks and opportunities. In terms of roles and responsibilities, WMO as the IE, has ensured that partners are aware of the Adaptation Funds Environmental and Social Policy and supported EEs to take actions to ensure it is implemented (ths was communicated from Year 1 to present). FAO as the excuting entity responsible for implementing the USPs and other community-level activities, has been the primary means through which ESP issues are implemented. All relevant human resources have been engaged either directly on the project or as technical support already within the partner organizations. Key aspects undertaken in Year 4 include: - 1) Adaptation investments in Uganda were screened by local implementing partners and local government staff (environment officers) for potential negative environmental and social impacts. Outstanding arrangements for compliance with Adaptation Fund ESMP include: - 1) Continued monitoring and technical backstopping to identify any emerging issues as adaptation investments are implemented. These arrangements are being conducted in accordance with AF Guidance on USPs (https://www.adaptation-fund.org/wp-content/uploads/2019/04/AFB.B.32-33.7_Compliance-with-ESP_Update-of-PPR_and_Guidance-for-USPs_revised-1.pdf)
| Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | Each adaptation investment integrates an ESMP based on the 15 ESP criteria of the Adaptation Fund.
| List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
1 | Baraka (Kersa) climate-smart agriculture for drought and climate variability | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Baraka | See link to sub-project document
2 | Bulbulu Negya (Kersa) climate-smart agriculture for drought and climate variability | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Bulbulu Negaya | See link to sub-project document
3 | Baha Kosum Negya (Kersa) climate-smart agriculture for drought and climate variability | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Baha Kosum | See link to sub-project document
4 | Gale Mirga (Kersa) climate-smart agriculture for drought and climate variability | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Gale Mirga | See link to sub-project document
5 | Gewachu (Kersa) climate-smart agriculture for drought and climate variability | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Gewachu | See link to sub-project document
6 | Asgemse (Meiso) climate-smart agriculture for drought and climate variability | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Asgemse | See link to sub-project document
7 | Harkonca (Meiso) climate-smart agriculture for drought and climate variability | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Harconca | See link to sub-project document
8 | Oda Keneni (Meiso) climate-smart agriculture for drought and climate variability | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Oda Keneni | See link to sub-project document
9 | Torbeyo (Meiso) climate-smart agriculture for drought and climate variability | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Torbeyo | See link to sub-project document
10 | Gorbo (Meiso) climate-smart agriculture for drought and climate variability | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Gorbo | See link to sub-project document
11 | Tausa (Voi) Galla goat support | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Tausa | See link to sub-project document
12 | Mbololo/ Mraru (Voi) Galla goat support | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Mraru | See link to sub-project document
13 | Ndome (Voi) Galla goat support | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Ndome | See link to sub-project document
14 | Ghazi (voi) rock weir for water harvesting for crops and livestock | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Ghazi | See link to sub-project document
15 | Chumvuni (Taveta) - Galla Goat support | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Chumvuni | See link to sub-project document
16 | Mahandakini (Taveta) - sunflower seed support and oil press | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Mahandakini | See link to sub-project document
17 | Mata (Taveta) - Water canal intake and lining | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Mata | See link to sub-project document
18 | Kighombo-Marumbenyi (Mwatate) - water tanks and kitchen garden with multi storey bags and vegetable seeds | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Kighombo-Marumbenyi | See link to sub-project document
19 | Mengo/ Msau (Mwatate) - Water canal intake and lining | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Msau | See link to sub-project document
20 | Mwachawaza (Mwatate) irrigation/ water distribution support | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Mwachawaza | See link to sub-project document
21 | Rong’e nyika (Mwatate) check dam construction on Mafuri river | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Rong’e nyika | See link to sub-project document
22 | Ishozi (Isingiro) underground water tank project | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Ishozi Bakayara | See link to sub-project document
23 | Kakunyu (Isingiro) valley dam rehabilitation | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Kakunyu Tweyombeke | See link to sub-project document
24 | Katojo Bakayara (Isingiro) water storage for vegetable production | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Katojo Bakayara | See link to sub-project document
25 | Rubirizi-Kazinga (Isingiro) Water & NRM project | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Rubiriza Kazinga | See link to sub-project document
26 | Ruhimbo Tukwatanise (Isingiro) Water & NRM project | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Ruhimbo Tukwatanise | See link to sub-project document
27 | Nakasenyi, Nakasenyi (Ssembabule) rain water harvesting (15) | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Nakasenyi | See link to sub-project document
28 | Kabaale, Nakasenyi (Ssembabule) Valley Tank | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Kabaale | See link to sub-project document
29 | Kampala, Lwemiyaga (Ssembabule) Valley Tank | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Kampala | See link to sub-project document
30 | Lwemibu, Lwemiyaga (Ssembabule) Rainwater Harvesting (15) | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Lwemibu | See link to sub-project document
31 | Ntete, Lwemiyaga (Ssembabule) Rainwater Harvesting (15) | Yes | See link to sub-project document | Yes | Yes - consultation with technical staff and communities | Yes - risks and impacts assessed according to the 15 AF criteria including gender. Targets also broken down by gender where possible. | Ntete | See link to sub-project document
32
33
34
SECTION 6: GRIEVANCES
| Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts? |  | Yes | The farmer field school groups and their structures provide the main channel for grievances. Partner staff contacts have been shared among stakeholders.
| List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
| None to date. |  | None to date.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Gender considerations were taken into account during project formulation including highlighting the following aspects for ensuring integration of gender equity and womens empowerment in project implementation and outcomes: 1) Baseline with sex disaggregated data and gender specific questions. 2) Use of participatory tools for gender sensitive community consultation and the FAO Self-evaluation and Holistic Assessment to Climate Resilience of Farmers and Pastoralists (SHARP). 3) Use tools developed by FAO and partners for integrating gender in climate-smart agriculture (http://www.fao.org/3/a-i5299e.pdf and http://www.fao.org/3/a-az917e.pdf). 4) Aim for 50% participation of women in project activities and 50% of project direct beneficiaries to be women, while also targeting specific project activities at women or women groups (for example the integrated savings and lending). 5) Foster equal participation of men and women in institutions and decision-making processes related to the project.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes. The results framework includes indicators at Objective, Outcome and Output level which either refer to targets for womens participation or to gender dissagregated data.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Number of APFS groups in place and applying climate change adaptation knowledge. (target for 50% women) | Output 1.2 | % women | 0 | 50% | Good
Number of extension actors (% female) who demonstrate an increase in knowledge and skills on climate-sensitive extension methodologies | Output 2.2 | % women | 0 | 50% | To be measured at endline.
Percentage change in household incomes disaggregated by gender of household heads | Outcome 1 | % women | 0 | 50% | To be measured at endline.
No. of staff trained to respond to, and mitigate impact of, climate-related events (by gender). | Outcome 2 | % women | 0 | 50% | Satisfactory
Percentage of extension workers (male and female) who are integrating adaptation strategies in their work at the community level | Outcome 2 | % women | 0 | 50% | To be measured at endline.
9000 APFS household members/direct and targeted beneficiaries (min. 50% female) | Objective | % women | 0 | 50% | Good
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
N/A - to be completed for final PPR as per guidance. |  | N/A - to be completed for final PPR as per guidance notes.
N/A - to be completed for final PPR as per guidance. |  | N/A - to be completed for final PPR as per guidance notes.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Implementing Entity and Executing Enities, have all made efforts to comply with the key concepts of the AF Gender Policy, including gender equity, gender mainstreaming, gender responsiveness, gender sensitivity and women's empowerment. In particular the following aspects have been put in place to ensure compliance with the AF gender policy: 1 - Requesting partners to report on gender policy compliance. 2 - Encouraging project partners/ executing entities to hold gender sensitive consultations and assessments, for example holding seperate focus group discussions for men and women, therefore allowing womens views to be better captured without being overshadowed by men.
Have the implementation arrangements at the IE been effective during the reporting period? |  | The implementation arrangements for Gender Policy compliance have been effective. Discussions during the inception workshop laid the platform for effective integration of gender issues in the project. Ensuring partners continue to integrate and report on gender isues has been a key role for the IE.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | Food and Agriculture Organization (FAO) of the United Nations: - Continuous sensitisation on participation of both men and women when sending activity invitations; and overall continuous awareness raising on the need for womens participation throughout all the project activities. - Workshops and trainings have involved both men and women as participants and as facilitators/ trainers. - Examples of gender participation in Year 3: Farmers field school (FFS) groups in Isingiro Uganda are currently comprised of approximately 75% women. In Kenya, women make up 60% of FFS membership and 50% of FFS chairpersonship. Community engagement meetings in Uganda involved over 70% women. In Uganda, FFS learning activities are scheduled according to gender-based work outside the field to enable women’s participation.
IGAD Climate Predictions and Applications Centre (ICPAC): - Continuous sensitisation on participation of both men and women when identifying participants for project activities; and overall continuous awareness raising on the need for womens participation throughout all the project activities. - All trainings have incorporated both men and women as participants and as facilitators/ trainers. - Published story for International Womens' Day highlighting the role of women in weather and climate reporting
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | The implementation arrangements for Gender Policy compliance have been effective in some cases but not in others. Womens participation in project activities, as well as their engagement in leadership and training roles has been mixed. In some cases womens participation is higher than the targetted 50% and in other cases womens participation has been lower than the targetted 50%. The effectiveness of the EEs efforts has also varied from country-to-country and activity to activity.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No major capacity gaps affecting Gender Policy compliance have been identified at the IE or the EEs. The capacity for adherence to the Gender Policy is adequate among the IE and EEs. Overall, it is not always possible to meet the targets for womens participation and engagement; however, the EEs will continue to engage with the stakeholders on the importance of gender issues and the participation of both men and women.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1] |  | Yes |  | The farmer field school groups and their structures provide the main channel for grievances. Partner staff contacts have been shared among stakeholders.
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
N/A-No Grievances related to Genders matters were received during the reporting period but suggestions related to gender participation and involvement are highlighted during meetings |  | N/A
Yes
No
Partially

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective | Number of beneficiaries received support for increased adaptive capacity to mitigate and respond to effects of climate change. | 0 | To be measured at endline | 45,000 direct beneficiaries through participation in CMDRR or as beneficiaries of investment grants. 9000 APFS household members/direct and targeted beneficiaries (min. 50% female) 40,000 indirect recipients of weather and climate information
| Percentage of targeted population with sustained climate-resilient alternative livelihoods. | 20% of direct target population implementing identified adaptation practices | To be measured at endline | 60% of direct target population with climate resilience livelihoods Alternative asset creation improved among 50% of target population.
| Percentage change in income (number, types and levels) among target population during periods affected by climate variability | US$193.5 (agricultural income averaged across the project locations from baseline survey) | To be measured at endline | A 40% increase in number, types, and/or levels among 80% of direct beneficiaries.
| Change in quality of climate related advisory to target population by the extension service. | Partially effective/ useful | To be measured at endline | Minimum 40% increase in satisfaction rates among direct and indirect beneficiaries with climate advisory services prior to the last extreme weather event.
Outcome 1 | Percentage change in crop/livestock yields among targeted households | See baseline report for yields of various crop and livestock products | To be measured at endline | 30% increase in crop/ livestock yields
| Percentage change in productivity of land, crop and livestock resources among targeted communities. | See baseline report for yields of various crop and livestock products | To be measured at endline | At least 50% increase
| Percentage of households adopting new or scaling up existing climate adaptation practices (including indigenous knowledge) | 0 | To be measured at endline | At least 30% adoption
| Percentage change in household incomes disaggregated by gender of household heads | US$193.5 (agricultural income averaged across the project locations from baseline survey) | To be measured at endline | At least 50% increase
Outcome 2 | Number and type of targeted institutions with increased capacity to minimize exposure to climate variability risks | 0 | To be measured at endline | 30 institutions
| Percentage of extension workers (male and female) who are integrating adaptation strategies in their work at the community level | Assessments ongoing | To be measured at endline | 80%
| Percentage of direct target population with reduced risk to climate variability and extremes | 0 | To be measured at endline | 70%
| No. of staff trained to respond to, and mitigate impact of, climate –related events (by gender). | 0 | To be measured at endline | 100 staff trained
Outcome 3 | Harmonized climate change response strategies for the region developed | 0 | To be assessed during final evaluation | Harmonised GHA Climate Change Strategy
| Percentage change in national budgets allocated to climate adaptation activities | 0 | To be assessed during final evaluation | 15% increase
| Percentage of households using tailored seasonal climate forecasts to plan their activities or enterprises | 0 (Households access some weather information, however tailored seasonal forecasts will be introduced through the project) | To be measured at endline | 70% increase
Output 1.1 | Number of community level adaptation action plans produced | 0 | Community adaptation planning conducted in all 30 communities | 30 Community Adaptation Plans
| Number of staff trained in participatory community mobilization and planning processes. | 0 | Total: 137 Ethiopia: 31 (16% women) Kenya: 33 (15% women) Uganda: 76 + 73 (40% women) | 60 staff trained
Output 1.2 | Number of participatory technology developments sites/structures linked to climate change adaptation | 0 | Linked to FFS learning (total 62): Uganda - 20 Kenya - 22 Ethiopia - 20 | 60 PTDs documented
| Number of field days conducted by APFS on climate change adaptation | 0 | Total: 29 Ethiopia - 6 Kenya - 18 Uganda - 5 | At least 60 field days
| Number of APFS groups in place and applying climate change adaptation knowledge. | 0 | Total: 62 groups Ethiopia: 20 groups, Kenya: 22 groups, Uganda: 20 groups | 60 groups in place applying adaptation practices
Output 1.3 | Number of communities trained in climate change adaptation proposal development | 0 | 30 communities trained and supported. | 30 communities trained.
| Number of community adaptation proposals developed | 0 | Total: 31 elaborated & submitted Ethiopia: 10 Kenya: 11 Uganda: 10 | 30 community adaptation proposals submitted
| Percentage of approved, climate adaptation proposals, funded and implemented | 0 | 31 proposals approved; 9 completed; 12 in advanced stages of implementation; 10 beginning | At least 80% of submitted proposals funded and implemented.
Output 1.4 | Number of intra-country FS visits conducted | 0 | Total: 13 Ethiopia: 0 Kenya: 8 Uganda: 5 | 60 Visits
| Number of inter-country FS visits conducted | 0 | Planned for 2023 | 3 Visits
| Number of visibility and exposure events attended by target community members | 0 | Planned for 2023/24 | 6 events
Output 2.1 | No of national stakeholder mapping and capacity needs assessments undertaken | 0 | 3 stakeholder mapping & capacity needs assessments completed (partnership with AFAAS) | 3
| No. of capacity development plans in place | 0 | 3 capacity development plans produced (partnership with AFAAS) | 3
Output 2.2 | Number of training manuals on climate adaptation strategies reviewed, modified and validated | 0 | One regional APFS manual produced (partnership with IIRR) | Updated APFS modules available in 3 countries
| Number of extensions actors (% female) who demonstrate an increase in knowledge and skills on climate-sensitive extension methodologies | 0 | To be measured at endline | 100 extension actors.
Output 2.3 | A knowledge and experience sharing platform for extension actors on climate proofing methodologies established | 0 | WMO and ICPAC websites curently being used, along with Whatsapp and Telegram Groups. Physical platform through PSP workshops & GHACOF also used. | ACREI Knowledge platform linked to existing platforms
| Number of community outreach forums on adaptation to climate change held and linked to the FS. | 0 | Planned for 2023/24 | 30 Community outreach forums
| Number of media-based partnerships developed for disseminating climate change adaptation information | 0 | Ethiopia: 1 radio station Kenya: 5 radio stations, 3 other media Uganda: 6 radio stations, 3 other media (This is supported under Component 3) | At least 6 media partnerships
Output 2.4 | Proportion of identified FS service providers integrating climate related information in their FS implementation | 0 | To be measured at endline | At least 60%
| A generic climate module for FS practice developed | 0 | 1 draft generic module produced (draft under review) | 1 generic climate module
| Number of FS climate change adaptation issue papers developed | 0 | 1 paper published on ACREI baseline methodology 2nd paper prepared (led by AFAAS) on extension actors climate change capacity in Uganda but not accepted for publication; 3rd paper prepared by ICPAC on climate information communication channels but not accepted for publication. | 3 issue papers
Output 3.1 | Number of livelihood zones with specific climate information generated and disseminated | 0 | 5 out of 5 ACREI districts are consistently receiving downscaled climate advisories | 5 Sub national units
| Number of target sub-national institutions provided with seasonal and/or enterprise-specific climate information | 0 | At least two government institutions and one NGO/ CBO per country | At least 6 government extension institution and 1 NGO or CBO receiving downscaled forecasts from Met agencies.
Output 3.2 | Number of FS groups reporting timely receipt of climate advisories | 0 | To be measured at endline. Currently 62 groups have been formed and are being provided with climate information. | 60 FS groups
| Number of FS with localized climate monitoring systems | 0 | 62 FFS groups provided with low cost rain gauges and receiving support on integration of climate information and climate adaptation into their activities. Farmer representatives are included in the seasonal advisory development process and tasked with sharing information in their communities. Contact details and meeting times for all 62 FFS groups have been registered for exploring direct climate information dissemination. | 60 FS groups by end of project
Output 3.3 | Number of National Agricultural Planners produced | 0 | Seasonal agroclimatic advisories produced as per indicator below. Three (3) historical climate data analysis conducted for all project locations identifying key climatic parameters such as average onset and cessation dates. | At least 4 seasonal planners developed per country
| Number of agro-climate advisories disseminated | 0 | 19 (8 in Kenya for each of the main rainy seasons in 2019, 2020, 2021 & 2022; 7 in Uganda for JJA2019, MAM2020, OND2020, MAM2021, OND2021, MAM2022, OND2022; and 4 for Ethiopia for the JJA 2019, 2020, 2021 & 2022 seasons) | At least 4
Output 3.4 | Number of good practices developed | 0 | 4 good practices documented to date: 1) PSP process used in ACREI; 2) Seasonal Media Action Plan; 3) RIMA methodology used in ACREI baseline; 4) Zoom Mashinani farmer engagement; | 6 (2 per country)
| Number of policy dialogues on climate change adaptation conducted | 0 | 3 (1 regional policy dialogue pending) | At least 4 ( national policy dialogue per country and 1 regional policy)
| Number of updates on food and nutrition security developed for advocacy and response | 0 | Being conducted by FSNWG which is led by ICPAC. ICPAC supports participants from ACREI sites to engage in seasonal meetings. | 24 monthly updates

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity (WMO): | Overall project management and coordination |  |  | 1. Second disbursements to executing entities made 2. At least two Project Management Team (PMT) meetings held and at least one national project advisory group meeting per country held. 3. Partner agreements amendended in line with no-cost extension of the project |  | 1. ICPAC received their 3rd and final disbursement for the project, while FAOs final disbursement is expected to be done in early 2023. EE expenditure of disbursed funds also picked up in the last year. 2. The project management team (PMT) at regional level is meeting regularly, with the last meeting being in mid-2022. The second meeting for the year has been delayed but will be scheduled for early 2023. | Satisfactory (S)
| Component 1 |  | Outcome 6 | 1. 60 Farmer Field School (FFS) groups formed and FFS learning and exchange conducted 2. 30 communities engaged on community adaptation planning and community adaptation investments identified and implementation begun |  | 1. 62 FFS groups were formed and supported with registration and identification of learning enterprises. FFS learning in all countries has proceeded well, with good results. FFS groups in Kenya completed learning cycle and held graduation ceremonies combined with field days per sub-county to contribute to learning, exchange, advocacy and awareness raising. Uganda FFS learning has also begun across the 2 target districts despite some initial delays. (Highly satisfactory for FFS activities) 2. Major progress was made in implementing the adaptation investments and as of report submission 9 adaptation investments in Kenya have been implemented (stories on some of the investments have been published by local media) and Uganda is at an advanced stage. Ethiopia has fallen behind on this aspect, though they were initially ahead of the other two countries on the adaptation investment identification. | Satisfactory (S)
| Component 2 |  | Outcome 2 | 1. Three (3) stakeholder mapping, capacity needs assessments & capacity development plans on integrating climate change in extension in project locations 2. One regional writeshop conducted and one regional FFS manual on climate change adaptation produced 3. Trainings for extension actors & field school facilitators on climate change adaptation conducted 4. LoAs with national meteorological services in place to improve climate information communication in project locations. 5. Knowledge sharing platform for information on climate change adaptation in place. 6. A generic climate information module for FFS practice developed. 7. Three issue papers developed on climate change in agriculture. 8. Media based partnerships (6) for outreach and climate information dissemination to the 30 target communities developed. |  | 1. Stakeholder mapping, capacity assessments and capacity development plans under Output 2.1 were completed through an LoA with the African Forum for Agricultural Advisory Services (AFAAS). 2. The production of the climate change manual for farmer field schools was completed through a partnership with the International Institute of Rural Reconstruction (IIRR). The manual has potential for use beyond just ACREI project. 3. Training of extension actors and field school facilitators was done for each country. A regional PICSA training will be held in 2023. 4. LoAs have been signed with the 3 respective national meteorological services and funds transfers made to all 3 for their activities. The NMHSs have been conducting various activities to enhance climate services delivery to the target communities. This work links with that under Component 3, including installation and commissiong of the automatic weather stations. 5. Various knowledge sharing platforms are being used, including Whatsapp groups, Telegram Groups, WMO and ICPAC project websites, and virtual experience sharing. 6. The draft generic climate module has been prepared through a consultant recruited by FAO, however, it still needs some revisions to be considered for broader dissemination. 7. Three draft papers have been prepared, however only one was published. 1 paper published on ACREI baseline methodology. A 2nd paper was prepared (led by AFAAS) on extension actors climate change capacity in Uganda but was not accepted for publication. A 3rd paper was also prepared by ICPAC on climate information communication channels but was not accepted for publication. Efforts to publish these are continuing. 8. Media partnerships have been developed in all 3 countries under Component 3 of the project and exceed the number initially targetted. Outreach to communities is ongoing including through media partners and support to the NMHSs. Results of media partnership vary across the 3 countries, with Kenya showing best results. | Satisfactory (S)
| Component 3 |  | Outcome 2 | 1. Five sub-national units/ districts receiving localised seasonal climate information. 2.At least two government institutions and one NGO/ CBO per country receiving local climate advisories. 3. FFS groups to begin receiving climate information and be supported with local rainfall monitoring equipment. 4. Policy makers from all ACREI sub-locations supported to participate in regional climate outlook fora. 5. At least 2 good practices and or papers documented. 6. Procure and install automatic weather stations and associated IT equipment for national meteorological services |  | 1. All 5 ACREI project locations are receiving support for seasonal climate advisory development and dissemination. This shifted back to in-person events in the lst reporting period and was combined with broader policy dialogue. Media engagement continued, including provision of podcast kits to aid sharing of climate change related stories. 2. Various government departments and local institutions are involved in coproduction of seasonal advisories and receive the information and advisories produced. 3. Low-cost raingauges were procured for all FFS groups in the project, however, there is need to examine issues around their use, robustness/ quality and sustainability. 4. In 2022, policy dialogues were integrated into the seasonal participatory advisory workshops so that broader discussions around adaptation policy could be held. A regional policy dialogue workshop is still to be held. 5. Four good practices have been documented to date: 1) PSP process used in ACREI; 2) Seasonal Media Action Plan for engagement of media in climate information dissemination; 3) RIMA methodology used in ACREI baseline; 4) Zoom Mashinani farmer engagement. These have been documented through stories on partner websites and there is need to better package and share the good practices. It is expected that with teh rollout of the community adaptation practices, more stories and good practices will emerge. 6. Three automatic weather stations were installed in the target countries and will be commissioned once troubleshooting on some sensors is complete. The procurement of the associated IT equipment has progressed and delivery for all three countries is pending customs protocols. | Satisfactory (S)
[6 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Sebastian Grey, Project Officer, WMO Office for Eastern and Southern Africa
| Email: | sgrey@wmo.int
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Progress and expenditure picked up over the last reporting period as travel and activities mostly returned to pre-COVID levels, with partners able to hold various in-person activities. In terms of adaptation investments under Component 1 of the project, this was the main area of delay in previous years and is now back on track. In Kenya and Uganda the community adaptaton investments are completed or at advanced stages of completion. Ethiopia which was initially ahead on this aspect has had some adnministrative delays and effort is ongoing to ensure rollout of the idnetified adaptation actions. 62 (out of a target of 60) farmer field school groups conducted seasonal learning focusing on climate-resilient enterprises identified by the groups themselves. FFS groups in all countries managed to hold some field days and learning visits as well as some gorups having graduated. Stakeholder mapping, capacity assessments and development of capacity development plans for extension actors on climate adaptation in project locations were successfully completed in partnership with the African Forum for Agricultural Advisory Services (AFAAS). The development of a module on climate change adaptation for Farmers Field Schools was also completed in partnership with the International Institute for Rural Reconstruction (IIRR). The generic module on climate information prepared in the project still requires review and validation before wider sharing. Sub-national extension actor training and support continued, and the next major aspect for extension capacity building will be the PICSA training scheduled for March 2023. Under Component 3, all ACREI locations are receiving support for participatory climate advisory development for each important season, including translation into local languages, in collaboration with the national meteorological services. Seasonal participatory advisory workshops held in year 4 were modified to include policy dialogue, an aspect that had been initially derailed due to the COVID pandmic. A regional training on the PICSA methodology (initially March 2020) has now been reprogrammed for March 2023 after reengagement of the training service provider (contract issued as of report writing). Local media (particularly radio stations) have being engaged to support wider distribution of climate information in target locations. Three automatic weather stations have been installed in the project locations, although repair of one wind sensor and one temperature sensor cable are being done before official commissioning. The NMHSs of the three participating countries were all provided with LoAs to enhance climate information dissemination aspects and have been using these funds to support engagement with farmers and communities targetted under ACREI. IT equipment was also procured for the NMHSs to enhance their data and analytical capacity - these are in process of being delivered to the countries. The participatory climate services work done by ICPAC and partners under Component 3 has continued to set an example and in 2022, the ACREI site in Kenya was identified as a learning location for another large climate services project being implemented in Eastern Africa with funding from the European Commission. The next steps include: 1) Completing implementation of the community adaptation investments - highest priority for the project; 2) Repair of the two sensors for the installed automatic weather stations & delivery of procured IT equipment for the NMHSs; 3) conducting regional policy workshop under Component 3; 4) continued advocacy and documentation of good practices.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator (FAO): | Component 1 |  | Outcome 6 | 1. 60 FFS groups formed and FFS learning and exchange conducted 2. 30 communities engaged on community adaptation planning and community adaptation investments identified and implementation begun |  | 1. As per previous report, 62 FFS groups were formed and supported with registration, identification of learning enterprises and seasonal learning on climate resiliente practices. Many good lessons and stories have emerged as a result of the FFS activities, including the linkages with the aspect of increasing knowledge on adaptation and climate information. FFS groups have been supported to enhance their knowledge on climate resilisnte agriculture. All groups completed learning cycle except 10 groups in Ethiopia who will continue one more season. 2. Community adaptation planning has fully been conducted across all ACREI communities and the specific investments to be funded have been identified in All three countries. Kenya has completed implementation of 9 out of 10 investment adaptation actions. Uganda implementation is ongoing but at advanced stages. Details of the adaptation investments have been included in the ESP compliance section where all the adaptation investments have been listed. This work is ongoing and is the current focus of project activities at the moment. Ethiopia, which was initially ahead in the identification of the adaptation investments, fell behind on implementation largely due to the administrative requirements for their implementation as well as country situation. This is being addressed by the FAO team. | Satisfactory (S)
| Component 2 |  | Outcome 2 | 1. Three (3) stakeholder mapping, capacity needs assessments & capacity development plans on integrating climate change in extension in project locations 2. One regional writeshop conducted and one regional APFS manual on climate change adaptation produced 3. Trainings for extension actors & field school facilitators on climate change adaptation conducted 4. LoAs with national meteorological services in place to improve climate information communication in project locations. 5. Knowledge sharing platform for information on climate change adaptation in place. 6. A generic climate information module for FS practice developed. 7. Three issue papers developed on climate change in agriculture. 8. Media based partnerships (6) for outreach and climate information dissemination to the 30 target communities developed. |  | 1. Stakeholder mapping, capacity assessments and capacity development plans under Output 2.1 were completed through an LoA with the African Forum for Agricultural Advisory Services (AFAAS) in previous reporting periods. 2. The production of the climate change manual for farmer field schools was completed through a partnership with the International Institute of Rural Reconstruction (IIRR) in one of the previous reporting periods. The manual has potential for use beyond just ACREI project. 3. Regional trainings for extension actors are being reserved for use in early 2023. In the emantime national trainings have been done linking with the farmer field school activities. 4. The NMHSs continue to engage in climate services enhanecement in the ACREI locations through the LoAs provided to them and linking with the seasonal participatory climate advisory processes supported by ICPAC and FAO under Component 3. 5. Various knowledge sharing platforms continue to be used, including Whatsapp groups, Telegram Groups, WMO and ICPAC project websites, and virtual and in-person experience sharing. 6. The draft generic climate module has been prepared through a consultant recruited by FAO, however has not been finalised. 7. Three draft papers have been prepared, however only one has been published. Two other papers were submitted to journals but not accepted and require revision before resubmission or exploration of alternative publication opportunities. 8. Media partnerships have been developed in all 3 countries under Component 3 of the project and exceed the number initially targetted. | Satisfactory (S)
[6 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Deborah Duveskog, Agriculture and Resilience Officer, FAO sub-regional office, Resilience Team, Nairobi
| Email: | deborah.duveskog@fao.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Year 4 focused on implementation of the community adaptation investments that had been delayed partly due to COVID in previous years but also due to administrative delays in administering the grants. In Kenya and Uganda the community adaptaton investments are completed or at advanced stages of completion. In these countries the grants are largely related to water for adaptation (e.g. houshold or community water harvesting combined with vegetable production support). Significant progress was made on the farmer field school aspects of the project, with 62 farmer field school groups undertaking learning across all the countries, exceeding the target of 60 planned. The learning has been documented and some good practices have emerged. FAO supported the groups with learning inputs as well as facilitators. Some FFS group graduations and field days were also held. Low-cost raingauges were also procured for all FFS groups, however field monitoring has uncovered issues around proper use and quality of the gauges. Stakeholder mapping, capacity assessments of extension actors on climate change adaptation and development of capacity development plans for extension actors in project locations were successfully completed in previous reporting periods in partnership with the African Forum for Agricultural Advisory Services (AFAAS). The development of a module on climate change adaptation for Farmers Field Schools was also completed in a previous reporting period in partnership with the International Institute for Rural Reconstruction (IIRR), although national validation workshops could not be held and a smaller team was instead constituted to validate the manual. The development of a generic module on climate information was begun by a consultant hired by FAO, however the draft is not yet finalised due sto some gaps in content and adjustments needed in the format to ensure alignment with the farmer field school approach. Training of extension actors has been conducted at national level rather than regional, however a regional extension actor training linked to the PICSA approach is still planned. Overall, FAO has shifted focus to ensure that the community adaptation grants are administered and has seen good progress on this in Kenya and Uganda. Support to Ethiopia to reach similar levels of implementation are ongoing.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator (ICPAC): | Component 3 |  | Outcome 2 | 1. Five sub-national units/ districts receiving localised seasonal climate information. |  | All the targeted ACREI sub-national units (five) continue to receive localised seasonal climate advisories and updates. The forecast based coproduction processes involves the National Meteorological and Hydrological Services (the key stakeholders mandated to produce climate information at national and lower levels), the local government authorities, government departments responsible for agriculture and livestock, farmers, NGOs, CBOs, partners among others. These activities were conducted in-person in all project sites, following the end of the COVID pandemic. In the last reporting period, the seasonal advisories were combined with policy dialogue workshops involving sub-nationals and in some cases national policy makers from environment and climate management, water, livestock and agriculture sectors as well as media in the target locations. A regional policy dialogue is expected to be held in 2023. Local media, have continued to be engaged in climate services dissemination and this aspect has been exemplary in Kenya, where many of the journalists who have been trained and engaged under ACREI have taken up the role in their broader work and activities. Historical climate data analysis has also been conducted for all ACREI locations identifying key climatic baselines such as average onset and cessation dates, dry spell occurence, average season length and other agrometeorological parameters, as well as their changes over time. The climate change projections analysis has been done and the report is being dfinalized. | Satisfactory (S)
|  |  | Outcome 2 | 2. Six government institutions (2 per country) and three NGOs/CBOs (one per country) receiving climate information. |  | The targets here have been reached in all countries, with engagement of various government and non-government organizations. Ensuring sustainability through linkages with other projects and initiatives is being explored. | Satisfactory (S)
|  |  | Outcome 2 | 3. FFS groups to begin receiving climate information in Year 2 |  | FFS groups were supported through training activities for farmers and the farmer field school facilitators, who have also been added to distribution lists (e.g. Whatsapp Groups) for receipt of forecast information and advisories. Receipt of climate information is also through brochures, radio and participation of selected farmers in seasonal advisory development workshops, the latter of which ensures that the farmers have first hand knowledge of the forecast and also contdibute to development of the advisories. | Satisfactory (S)
|  |  | Outcome 2 | 4. Seasonal advisories developed and distributed in all three countries for each important season. |  | Forecast based advisories continue to be developed in all three countries for all important agricultural seasons, namley OND and MAM for Kenya and Uganda sites and JJAS for Ethiopia. The advisories are codeveloped with farmers and stakeholders and are disseminated through brochures, radio (via the media partners) and Whatsapp. Weekly/monthly forecasts updates are also being provided via Whatsapp and radio in Kenya and Uganda and via email in Ethiopia. Advisories are translated into local languages, Oromifa in Ethiopia, Kiswahili in Kenya, and Luganda and Runyankore in Uganda for wider reach and understanding. Translations is led by the NMHSs with input from ICPAC. | Satisfactory (S)
|  |  | Outcome 2 | 5. Policy makers from all ACREI sub-locations supported to participate in regional climate outlook fora. |  | Polciy makers have previously been supported to participate (either in-person or virtually) in the Greater Horn of Africa Climate Outlook Forums (GHACOFs), which is a WMO recognized regional User Interface Platform (UIP). In 2022, ICPAC integrated policy dialogue into the seasonal participatory advisory development workshops, where key issues around adaptation policy and practice were discussed in relation to climate services. | Satisfactory (S)
|  |  | Outcome 2 | 6. Procure and install automatic weather stations and associated IT equipment for national meteorological services |  | Procurement of automatic weather stations was done by WMO and equipment installed in all 3 countries by the NMHSs. Some troubleshooting is still being done on the AWSs (e.g. damaged wind sensor in Ethiopia, and one damaged cable for the temperature and humidity senro in Kenya), however the AWSs are funtional and data is being transmitted. IT equipment (high specification desktops) has been procured and should be delivered in early 2023, which will enable receipt of the AWS data, and use by the NMHs for data analysis or communication of forecasts and advisories. About 12 Podcast kits (4 per site) were procured and distrbuted to the best performed local journalists to enable them to record view of farmers during field visit. | Satisfactory (S)
[6 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Abdi Fidar, IGAD Climate Prediction and Applications Centre (ICPAC)
| Email: | abdi.fidar@igad.int
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | 2022 saw a full return to in-person activities as the COVID pandemic came to an end. All seasonal climate advisory workshops were held in-person and were integrated with further media engagement and broader adaptation policy dialogues in all project locations, in collaboration with the national meteorological services of Ethiopia, Kenya and Uganda. The climate services aspect of the project has been strong and stakeholders are generally pleased with this aspect of the project. The main next steps include: Issue contract and hold PICSA training (as of this report the cntract has been issued and dates agree for week of 20th March); holding a regional policy dialogue workshop; repair of the faulty AWS wind sensor and cable for Ethiopia and Kenya respecitvely; delivery of the IT equipment and looking at other opportunities for publication of papers and documentation of case studies and learning. Discussions on scaling up the climate services aspects will also be key. Overall, the general rating for Component 3 is satisfactory.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | - Low cost raingauges were procured for farmer field schools in the previous year, and have emerged as a key learning point for future projects. Monitoring found the raingauges to be an aspect of pride for farmers, however there are still challenges with taking regular recordings, security of the gauges and quality of the gauges under direct sun.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Year 4 saw a return to normalcy for most project activities that had been affected by teh COVID pandemic. Travel nationally and internationaly has become possible and the project partners held various in-person workshops and activities in Year 4. Service providers for regional trainings (particulary the PICSA training that was postponed multiple times due to COVID restrictions) have been reengaged and these are expected to be conducted soon. FAO have continued to work with locally based implementing partners, including government departments. Focus by FAO has been on implementing the adaptation actions component of the project, which is now poceding well in Kenya and on track in Uganda but still delayed in Ethiopia.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No major changes have been made to project Outputs in Year 4.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | For the activities undertaken to date, the environmental and social safeguards have been adequate and as yet no negative impacts have emerged. USPs in all 3 countries have undergone screening for environmental and social impacts and all adaptation investments have sections with questions on issues related to do with ESP and a table / checklist for summarising any issues and mitigation measures according to the 15 Adaptation Fund ESP categories.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | During the reporting period, the main aspect of gender considerations focused on targeting 50% participation of women in project activities. In previous years, effort was also placed on ensuring women were equal members and leaders in farmer field school groups; targeting women in specific activities (e.g. womens journalists) and ensuring design of the adaptation investments took acount of womens needs. In the upcoming year, it is expected to get a better picture of project benefits for women, in addition to understanding participation issues. The main lesson as in previous reports is that some activities tend to have greater participation of women than men while others tend to have greater participation of men. Local trainings often have good participation of women, however, trainings involving travel outside the community often have greater participation of men. The overwhelming household roles of women sometimes hinder their participation in project activities that are conducted far from home. Women'participation also varies from place to place.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Community proposed adaptation investments require comprehensive technical assessment before implementation and hence sufficient time has to be allocated for this. Also for engineering type of interventions (water structures etc) specialist skills beyond government technical offices are often required thus increasing costs related to assessments. Farmers have much local knowledge and when empowered with technical support through for example the FFS approach, and financial resources can take a lead in enhancing their own climate resilience Farmer groups and associations (like the farmer field school groups in the project) play a key role in enhancing adaptation and resilience of farmers - they support one another socially, technically and financially
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The ACREI site in Kenya (Taita Taveta) was visited for a learning mission by a multicountry team from another large climate services project (CLIMSA) being implemented in Eastern Africa. As per previous report, the key areas for learning and potential scale up included: - Seasonal participatory advisory dialogues to support farmers to plan for the upcoming season, based on a combination of scientific weather informaiton and local knowledge. ACREI site in Taita Taveta has already been used as a learning site by other - Manuals developed under the project have applicability beyond the current project locations and even in other countries and regions e.g., The Climate Change Adaptation Guide for farmer Field Schools - Seasonal media action plan (SMAP) methodology for engagement of media in the communication of weather and climate information and advisories - Climate sensitive farmer field schools approach, which has enabled farmers to learn about the resilience strategies they can use in the face of local weather and climate hazards. - Sensitising and supporting farmers and farmer field schools groups on the importance of local climate information, including supporting them with low cost raingauges and training on their use. - The partnership approach that the project demonstrates has proven successful and necessary i.e., partnership from regional to sub-national level, linking organizations involved in climate services to those involved in supporting adaptation actions on the ground. Through other funding sources, the project partners are exploring digital climate services and enhancement of extension worker capacity building based on capacity needs assessments conducted under ACREI.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Community adaptation investments have begun being implemented and at this point the lessons that can be highlighted are: 1 - Importance of identifying locally suitable and resilient crop varieties and livestock to enhance physical and financial resilience. 2 - Apart from on-farm measures to enhance resilience, market linkages and support across the entire value chain are needed to enhance incomes. 3- Climate resilience is by nature cross sectoral and needs to allow for combination of crop, livestock and ecosystem serivces work, and the particular combination of such action needs to be community specific thus calling for participatory approaches allowing for a wide technical scope of interventions. 4 - Involving local organisations as implementing partners in concrete adaptation investments yields benefits in terms of ownership and sustainability 5 - Physical adaptation measure stake time for implementation as well as for results to be seen and this has to be catered for in project development.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Community adaptation investments are still in process of being implemented, however, many of the identified adaptation investments of ACREI have great potential for scale up and replicability. For example applied solutions related to trees on farm, intergrated farming (multi-crop), local poultry solutions, hardy livestock breeds, pasture conservation and hay making, preservation of farm products etc.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The following aspects can be highlighted at this point as being highly successful: 1. The participatory climate services aspect of the project including seasonal participatory advisories and the engagemenmt of media partners in climate information communication. farmers and stakeholders now hear first hand the seasonal forecast and play a key role in co-producing the advisories for agriculture and livestock sectors in their communities. 2. The climate sensitive farmer field school learning, which has succesfully engaged farmers on different climate resilient learning enterprises. To date there are 62 farmer field school groups being supported under the project, which have proven an excellent platform for linking technical and meterological knowledge. Low-cost raingauges have been disributed to approximatly 50 of these groups and some are already reporting back readings to the national meteorological and hydrological services. 3. Farmers support to access, understand and coproduce climate services.
What measures are/have been put in place to ensure sustainability of the project/program results? | To date sustainability has been hinged on the following: - Capacity building of extension agents and local CBO staff on climate adaptation and the methodologies being used in the project. - Capacity building national meteorological and hydrological services staff on the co-production methologies used in the project - Developing manuals that can be used beyond the project lifetimee.g. Climate Change Adaptation Guide for farmer Field Schools - Supporting long term climate data gathering through meteorological equipment procurement for farmers and national meteorological and hydrological services - Working closely with government departments and agencies, such as the national meteorlogical and hydrological services and departments of agricultural extension/ Ministries of Agriculture, and having them lead on key activities once initial capacity building has been conducted. - Where possible LoAs have been made with local CBOs, farmers associations, government departments and other organizations undertaking related work - Supporting sales/ market linkages for farmer produce where possible. e.g. Potato tuber market linkages for farmer field school groups in Ethiopia. Including savings and loans modalities with target communities to build up their financial assets.
What measures are being/could have been put in place to improve project/program results? | - Better internal coordination of the EEs on the understanding of the administrative requirements for various aspects of project implementation could have expedited some aspects or prepared the project team for some delays. This is particularly so for the adaptation investments aspect of the project for which the internal administrative requirements were much stricter than initially understood. - The diverse capacities and context of communities in different countries and locations means that the adaptation investment implementation modality needs to be tailored and cannot be implemented in one way across all countries and locations. The relevant EE has had to take account of this in implementing this aspect of the project.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | - The project team has integrated exisitng methodologies into many activities then enhanced them by tailoring to the local context - examples include the use of the Participatory Scenario Planning (PSP) methodology to enable farmers to co-produce seasonal climate advisories. - Building on the global expertise of the MIE and EEs in various aspects of project implementation e.g. developing specifications for meteorological equipment based on global standards, capacity building on climate downscaling, engagement of media in the comunication of weather and climate information. - Use of local climate data sets for some limate analysis - use of global and regional climate data sets to feed into seasonal climate outlooks - Use of existing manuals, guidelines and methodologies for some activities e.g. INSTAT methodology for historical climate data analysis - The Global and sub-regional FFS platforms with its continous release of new evidence, studies and guidance and manuals have been used to improve FFS practice in the project.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Yes, information is made available to different stakeholders through different means: • Printing of seasonal climate advisories for wide distribution in target communities • Local radio stations and journalists • Whatsapp groups formed in each country to share climate information among technical experts and local extension agents • Whatsapp groups formed for farmer field school facilitators to share progress, successes and challenges (specifcally Kenya) • All completed documents published on EE websites • Targetted peer-reviewed publications - paper on baseline methodology successfully published; one undergoing review and a third needing revisions before submission for publication • Advocacy and awareness raising events by project partners
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | Various project stories, technical reports, videos, case studies, best practices and conference presentations have been prepared to date and are largely available on the partner websites.
If learning objectives have been established, have they been met? Please describe. | Learning is integrated into the project through trainings and knowledge management. This includes the farmer field school activities which are based on farmer-to-farmer experiential learning and have incorporated farmer exchange visits and field days. Online learning and exchange has also been conducted related to the communication of climate services. various trainings have been conducted for the national meteorological and hydrological services, extension agents and partners. use of messaging apps for sharing information and creating communities of practice has also been integral.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | There have been no significant challenges in accessing data or knowledge related to project implementation. Climate data has been provided by the national meteorological and hydrological services where available, while global databases have been used to supplement and enhance spatial scale of the analysis.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Learning is a key aspect in the farmer field school component of the project and will contribute directly to the outcomes. Increased knowledge and capacity of extension agents and national meteorological and hydrological services is also a major aspect that will contribute to project outcomes and sustainability.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | The following innovations featured prominently in the project: - Coproduction of seasonal climate advisories with farmers, extension agents and climate experts - Seasonal media action plan (SMAP) methodology developed by ICPAC for engagement of media in the communication of weather and climate information and advisories - Climate sensitive farmer field schools approach, which has enabled farmers to learn about the resilience strategies they can use in the face of local weather and climate hazards. - Sensitising and supporting farmers and farmer field schools groups on the importance of local climate information, including supporting them with low cost raingauges and training on their use. - The partnership approach that the project demonstrates i.e., partnership from regional to sub-national level, linking organizations involved in climate services to those involved in supporting adaptation actions on the ground.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative? | No
If you answered yes above, kindly specify the name of the Fund/Organization. | N/A
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | AFR/MIE/Food/2015/2
Implementing Entity | World Meteorological Organization (WMO)
Type of implementing entity | MIE
Country | Ethiopia, Kenya & Uganda
Region | Africa
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 54000 | 54000 | 40000 | Total | 69500 | 9500 | 60000 (approximation) | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 50% | 60% | 50% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0 | 0 | 0 | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 40000 | Drought | 2: Partially effective | Total | 40000 | Drought | 4: Effective | Total | 60000 | - Seasonal forecast - Likelihhod of below or above normal rains (droughts/ floods) - Season onset, length and cessation - Intra-seasonal warnings | 3: Moderately effective | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted | 50 |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 100 | Agriculture | 2: Low capacity | Total | 100 | Agriculture | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 100 | 50% | Public |  | 137 | Ethiopia: 15% Kenya: 15% Uganda: 40% | Public - Extension actors + some CBO staff
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 20% |  | Agriculture |  | 60 |  | Agriculture |  | Endline survey planned for final year |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 40000 | 50% | 3: Partially aware |  | 40000 | 50% | 4: Mostly aware |  | Endline survey planned for final year | Endline survey planned for final year | Endline survey planned for final year
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Food security | Regional | 3: Moderately responsive (Some defined elements) |  | Food security | Regional | 4: Mostly responsive (Most defined elements) |  | Food security | Regional | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
Community
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 10800 | 50% | 4: High improvement |  | 10800 | 50% | 4: High improvement |  | 0 | 0 | 0
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 6480 | 50% | From 30% to 40% | Agricultural-related | 6480 | 50% | From 30% to 40% | Agricultural-related | 1900 | 60% | Endline survey planned for final year | Agricultural-related
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies | Agriculture | Community-based adaptation | 30 | Adaptation strategies | Agriculture | Community-based adaptation | 0 | Adaptation strategies | Agriculture | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 10800 | Agricultural-related |  | 193.5 | 10800 | Agricultural-related |  | 40% | 0 | Agricultultural-related |  | Endline survey planned for final year
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Agriculture | Local | Other policy | 3 | Agriculture | Local | Other policy | 1 - PSPs | Agriculture | Local | Other policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 2: Partially not enforced (Most elements not implemented) |  | 2: Partially effective | 3 | 3: Partially enforced (Some elements implemented) |  | 4: Effective | 3 - PSPs, Climate-sensitive farmer field schools, SMAP | 4: Enforced (Most elements implemented) |  | 4: Effective