## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | November 17th, 2021 to November 17th, 2022
| Project Title: | Promoting Climate-Smart Agriculture in West Africa (Benin, Burkina Faso, Ghana, Niger, Togo)
| Project Summary: | The Regional Project « Promoting Climate-Smart Agriculture in West Africa » aims to reduce the vulnerability of farmers and pastoralists to increase climatic risk, which undermines the level of food security, income generation, and the supporting ecosystem services of poor communities. The specific objectives of the project are: i) Strengthen knowledge and technical capacity through regional and local interactions for the promotion of agriculture practices resilient to the adverse effects of climate change; ii) Scaling up best practices related to climate change adaptation in agriculture and pastoralism at local and regional level; iii) Share knowledge and disseminate lessons learned on resilient agricultural best practices related to climate-smart agriculture. The oucomes expected by project implementaion are: i) Climate services adapted to the needs of producers are available with the support of national and regional institutions and usable by the producers; ii) Institutional exchanges on agro-meteorological forecasts for agricultural campaigns and provision of information adapted to the level of producers; iii) Climate resilient knowledge and farming practices are strengthened; iv) Capacity building of stakeholders in charge of designing and implementing of projects to promote climate smart-agriculture; v) Strengthening the transboundary collaboration for the adaptation of agriculture to climate change to enhance the national capacity for CSA; vi) Agricultural and livestock practices contribute to the resilience of populations to improve productivity, incomes and carbon sequestration; vii) Knowledge on resilient agriculture best practices related to climate-smart agriculture is strengthened and disseminated; viii) The sharing of experiences and expertise on best practices related to climate-smart agriculture is strengthened.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | 1431-Full-Prop-CSA-WA-14-5-18-clean | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Banque Ouest Africaine de Developpement | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Regional Implenting Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Benin, Burkina Faso, Ghana, Niger and Togo | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Benin (Atacora, Alibori), Burkina Faso (Centre sud, Centre est, Est) , Ghana (Upper west, Norden) , Niger (Tilaberi, Dosso), Togo (Kara, Savanes) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 16 July 2018
IE-AFB Agreement Signature Date: |  | 18, September 2020 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 17 November, 2020 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | September 2022
| Original Completion Date: | May 2024
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
| Category of condition | Environmental and Social Safeguards
| Condition or Requirement | (i) Finalization of the terms of reference of the perimeter committees and fee management structure; (ii) Identification of a list of permitted activities, including inherent risks, and in line with national requirements, according to the 15 principles of the Environmental and Social Policy; (iii) For each Environmental and Social Policy principle, preparation, by project inception, of methodology for the identification of relevant risks during unidentified sub-project identification, and for each participating country, country-specific elements that will be required for risk identification and included in the methodology; (iv) An assessment for each participating country of the personnel and capacity requirements to apply the Environmental and Social Management Plan, and the financial implications reflected in a revised budget, as needed; and (v) Adoption of guidelines for environmentally responsible pesticide use.
(i) Finalization of the terms of reference of the perimeter committees and fee management structure; This condition is yet to be met; The Tender document for the recrutement of the consultant in charge of the additional studies will be prepared by the RPMU and the call for proposal will be launched for the selection of the Cabinet of consultants. This additional studies will allow us to select the 25 sub-projets that will be funded in Compent 2 of this CSA project.
(ii) Identification of a list of permitted activities, including inherent risks, and in line with national requirements, according to the 15 principles of the Environmental and Social Policy; This condition is yet to be met for each sub project. Within the framework of the project implementation, two types of activities have been distinguished: 1) one that will be chosen by the communities for the development of the subprojects, and 2) one that have already been decided in the proposal and which will not be decided by the communities. Also the the Criteria for the selection of sub-projects will be given to the consultant to be recruited (See Page 139 of Full Proposal). In order to ensure that the project minimizes the risk of negative environmental and social impacts from the project, an analysis was conducted to identify potential generic negative impacts and risks (Cf. section II. L of full proposal document) as well as to propose measures that will be taken to avoid, counteract or minimize their occurrence and impact.Table 26: Environmental and Social risks and negative impacts mangement measures (pp 147-150 of Full Proposal) describe the proposed measures, for demonstration purposes. The specific measures will be proposed in the environmental and social management plans of the sub-projects that will be subject to environmental and social impact assessment. Each sub-project will have a specific Environmental and Social Management Plan reflecting the reality of the site, the specific activities to be undertaken and the responsibilities of the stakeholders. The environmental and social management approach in the selection and implementation of sub-projects.
(iii) For each Environmental and Social Policy principle, preparation, by project inception, of methodology for the identification of relevant risks during unidentified sub-project identification, and for each participating country, country-specific elements that will be required for risk identification and included in the methodology; This condition is yet to be met since sub projects have not been selected yet. All this tasks are included in the Scope of Work (SOW) of the consultant. However it key to highlifht that the the project proposal document has already identified the general guidelines that well be used during the sub-projects selection in each country to ensure compliance to this requirement/condition.
(iv) An assessment for each participating country of the personnel and capacity requirements to apply the Environmental and Social Management Plan, and the financial implications reflected in a revised budget, as needed: this willbe done during the complementary studies in order to better identify sites that will be hosted sub-projects,
(v) Adoption of guidelines for environmentally responsible pesticide use. This condition is yet to be met since sub projects have not been selected yet. The development of integrated pest and pesticide management toolbox and good environmental management practice and capacity building of agents for their utilisation as well as the support for the implementation of ESMPs for subprojects and discussion of integrated pest management alternatives to producers are part of activities planned. These will be implemented one the sites and sub-projects are developped/indentified with the support of the consultant.
| Current Status | Condition not met
| Planned actions, including a detailed time schedule | Transmission of tender documents regarding both Meteorological equipements and Field complementary studies in order to receive NON OBJECTION NOTICE (Quarter 2, 2023) Transmission of selection of cbinet for complementary studies fields in order to receive NON OBJECTION NOTICE (January, 2023) 2023 Procurement Plan in order to receive NON OBJECTION NOTICE (March, 2023) Tenders documents regarding Recruitment of national offices for the supervision of the execution of water mobilization infrastructure works (Quarter 2, 2023) Recruitment of a consultant for the compilation of lessons learned from the AIC project (Quarter 2, 2023) Procurement of motorized pumps for sub-projects (Quarter 2, 2023) Construction of 100 runoff collection basins in 5 countries (Benin, Burkina Faso, Ghana, Niger and Togo) (Quarter 2, 2023) Construction of 10 large diameter wells in 5 countries (Benin, Burkina-Faso, Ghana, Niger and Togo) (Quarter 2, 2023) Realization of 04 spreading sills in 05 countries (Benin, Burkina-Faso, Ghana, Niger and Togo) (Quarter 2, 2023) Construction of 80 runoff collection basins (BCER) along the secured transhumance corridors (Quarter 2, 2023) Realization of 20 human powered boreholes along the secured transhumance corridors in 5 countries (Benin, Burkina-Faso, Ghana, Niger and Togo) (Quarter 2, 2023) Development of sites (of the 25 selected sub-projects) for market gardening with solar irrigation and a Californian network Development of irrigation sites (of the 25 selected sub-projects) with spreading sills in 5 countries (Benin, Burkina-Faso, Ghana, Niger and Togo) (Quarter 2, 2023)
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | 1) Executive Summary of Circular Mission AIC-BOAD_May 29 to June 15, 2022; 2) Report_Institutional exchange workshop_CSA Project_FINAL; 3) Mission Report of 2022 Science and Partnership for Africa’s Agriculture Conference (SPAAC), 14 - 16 September 2022 Alisa Hotel, Accra (GHANA); 4) Mission Report for participation at UNFCCC CoP27 Sharm-El-Sheikh (EGYPT); 5) 3A0 FORUM REPORT (Bissau). | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://araa.org/fr/programme/promotion-de-l%E2%80%99agriculture-intelligente-face-au-climat-en-afrique-de-l%E2%80%99ouest-aic | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | M. Jacques-André NDIONE | Dominican Republic
| Email: | jndione@araa.org | Ecuador
| Date: | 2022-03-17 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Wilfried BIAO MONGAZI (BENIN) | Equatoral Guinea
| Email: | wilmongazi@yahoo.fr | Eritrea
Date:
| Name: | Ambroise KAFANDO (BURKINA FASO)
| Email: | ambkafando@gmail.com
Date:
| Name: | Fredua Agyeman (GHANA)
| Email: | Fredua_a@yahoo.com ; Fredua_agyeman@hotmail.com
Date:
| Name: | Dr. Kamaye Maazou (NIGER)
| Email: | kamayemaazou@yahoo.fr
Date:
| Name: | Mme MERY YAOU (TOGO)
| Email: | denv_togo@yahoo.fr ; ymery69@yahoo.fr
Date:
| Implementing Entity |  | Ethiopia
| Name: | M. Ibrahim TRAORE | Fiji
| Email: | itraore@boad.org | Finland
| Date: | 2022-03-17 | France
| Executing Agency |  | Gambia
| Name: | ECOWAS Regional Agency for Agriculture and Food (RAAF) | Georgia
| Email: | osalifou@araa.org et kkonlani@araa.org | Germany
| Date: | 2022-03-17 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [insert date] |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [30/11/2022] | 3000000 |  |  |  | 3000000
Add any comments on AF Grant Funds. (word limit=200) | Following the context of COVID 19, the recruitment of the PMU was delayed and we were able to organize only the project launch workshop. This is why there is a big difference between resource disbursed and consumed |  |  | Add any comments on AF Grant Funds. (word limit=200) | The 2022 budget for the project was implemented at 18.05%. It should be pointed out that the administrative procedures for the full implementation of the budget activities were not completed until the end of the period. And the 2022 activities were renewed over 2023. The amount in US dollars (USD) of uncommitted figures not yet disbursed to executing entities to date is 9 904 000. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1.1. Strengthening agroclimatic and meteorological information | 0 |  |  | Output 1.1.1. Strengthening agroclimatic and meteorological information | 66016.2789
| Output 1.1.2. Institutional exchanges on agro-meteorological forecasts for agricultural | 0 |  |  | Output 1.1.2. Institutional exchanges on agro-meteorological forecasts for agricultural | 0
| Output 1.2.1. Capacity building of stakeholders in charge of designing and implementing of projects to promote climate smart-agriculture | 0 |  |  | Output 1.2.1. Capacity building of stakeholders in charge of designing and implementing of projects to promote climate smart-agriculture | 552.0592
| Output 1.2.2 Strengthening the transboundary collaboration for the adaptation of agriculture to climate change to enhance the national capacity for CSA | 0 |  |  | Output 1.2.2 Strengthening the transboundary collaboration for the adaptation of agriculture to climate change to enhance the national capacity for CSA | 0
| Output 2.1.1. Promotion of integrated techniques and activities related to water management, soil rehabilitation and conservation and livestock mobility to enhance beneficiaries’ resilience | 0 |  |  | Output 2.1.1. Promotion of integrated techniques and activities related to water management, soil rehabilitation and conservation and livestock mobility to enhance beneficiaries’ resilience | 0
| Output 2.1.2 Support for the fields’valorization | 0 |  |  | Output 2.1.2 Support for the fields’valorization | 0
| Output 3.1.1 The sharing of experiences and expertise on best practices related to climate-smart agriculture is strengthened | 0 |  |  | Output 3.1.1 The sharing of experiences and expertise on best practices related to climate-smart agriculture is strengthened | 0
| Execution cost | 122918 |  |  | Execution cost | 203981.1641
| IE Fees | 100000 |  |  | IE Fees | 22979.096
| TOTAL | 222918 |  |  | TOTAL | 293528.5983 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1.1. Strengthening agroclimatic and meteorological information | 180000 | 2022-09-30 |  | Output 1.1.1. Strengthening agroclimatic and meteorological information | 280000 | 2023-09-30
| Output 1.1.2. Institutional exchanges on agro-meteorological forecasts for agricultural | 150000 | 2022-08-31 |  | Output 1.1.2. Institutional exchanges on agro-meteorological forecasts for agricultural | 1149000 | 2023-12-31
| Output 1.2.1. Capacity building of stakeholders in charge of designing and implementing of projects to promote climate smart-agriculture | 35000 | 2022-08-31 |  | Output 1.2.1. Capacity building of stakeholders in charge of designing and implementing of projects to promote climate smart-agriculture
| Output 1.2.2 Strengthening the transboundary collaboration for the adaptation of agriculture to climate change to enhance the national capacity for CSA | 304000 | 2022-10-31 |  | Output 1.2.2 Strengthening the transboundary collaboration for the adaptation of agriculture to climate change to enhance the national capacity for CSA | 3235000 | 2023-10-31
| Output 2.1.1 Promotion of integrated techniques and activities related to water management, soil rehabilitation and conservation and livestock mobility to enhance beneficiaries’ resilience | 550000 | 2022-12-31 |  | Output 2.1.1 Promotion of integrated techniques and activities related to water management, soil rehabilitation and conservation and livestock mobility to enhance beneficiaries’ resilience
| Output 2.1.2 Support for the fields’valorization | 465000 | 2022-12-31 |  | Output 2.1.2 Support for the fields’valorization
| Output 3.1.1 The sharing of experiences and expertise on best practices related to climate-smart agriculture is strengthened | 60000 | 2022-12-31 |  | Output 3.1.1 The sharing of experiences and expertise on best practices related to climate-smart agriculture is strengthened | 180000 | 2023-12-31
| Execution cost | 453900 | 2022-12-31 |  | Execution cost | 512000 | 2023-12-31
| IE Fees | 200000 | 2022-12-31 |  | IE Fees | 454911.3453 | 2023-12-31
| TOTAL | 2397900 |  |  | TOTAL | 5810911.3453 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Financial
Instability in currencies, market prices and availability of project inputs | Low | In the MoUs with AGRHYMET and CIAT, we've included provision to address instability in currencies. As a exeample, we said: "b) If exchange rate fluctuations decrease the value of the Grant to such an extent that this will have consequences for the implementation of the Project, the Implementing organization shall inform RAAF as soon as possible. Exchange rate losses will be charged to the project by reducing the project activities to the extent of the exchange loss. c) If exchange rate fluctuations increase the value of the Grant, the gain shall be treated as disbursed Grant funds and used for Project purposes. Net surplus from conversion into foreign currency shall be subtracted from future disbursements or repaid as unused funds at the end of the Project, unless otherwise agreed between the Parties."
Delay in disbursements | Low | Up to now, we have not been faced such risk. Due to the dealy in implementing field activities, we have sufficient financial resources to consume.
Misuse of financial subsidies at the local level | Low | In the case that up to now, sub-projects are not implmented, no major risk occured. Whatever, after their selection, in collobation with national project management units, a capacity building wrokshop will be organised in order to strenghen their knowledge and practice on financial reporting anad management according to RAAF rules. Funds will be disbursed to beneficiaries only when the annual work and budget program is established and approved by the national project management unit at the country level.
Financial risks on the procedural level | Low | The financial rules and guidelines of BOAD, as implementation entity, are used throughout the implementation of the project to minimize financial risks. This includes the internal and external audit procedures provided for by these rules and guidelines
Political
Political uncertainties affect project implementation | Low | The project target areas are relatively stable politically and all efforts are made to ensure that project activities are conducted with participation of all relevant stakeholders including government departments and local structures so as to aid conflict resolution should any arise.
Political influence affects adoption of lessons learned into national and regional adaptation strategies. | Low | The project partners worked together in a consultative manner with all stakeholders, relevant government departments and institutions to ensure that lessons learned from the project are considered and adequately incorporated in national and regional adaptation strategies. Advocacy on key issues played an important role in uptake of project learning. Up to now, the same dynamics is maintained and reinforced.
Sub-national governments prioritise alternative implementation frameworks. | Low | Lobbying and advocacy have taken place to ensure that all stakeholders including sub-national governments work in a harmonized and coordinated manner. In addition, these sub-national governments/municipalities are members of the Inclusive National Platform for Coordination and Concertation (INCCP), which is the national steering committee of the CSA project at country level.
Mangement and Coordination
Delays in recruitment or appointment of critical staff for the project. | Low | Since january 2023, the Regional management project unit (RMPU) is now complete. From March 2022 up to december 2022, RMPU was not fully operational in the case that the Administrative, financial and procurement officer was not recruited yet.
Different pace of project implementation for each country may delay overall project implementation and affect regional activities. | Low | BOAD with the collaboration of RAAF established already appropriate project management and coordination structures at both regional and national level to monitor, report on and discuss progress on a regular basis and take corrective action where needed to ensure that the project moves at the required pace in all 5 countries. National level implementation plans on an annual basis have been developed to guide in country activities. In addition, the RMPU maintains close communication with country level to identify potential barriers and anticipate solutions. We have regular meetings in a monthly basis with national projects management units.
Uneven speed of implementation and expenditure rate among the three main partners may hamper overall project performance | Medium | Due to the delay in implementing field project activities, the RPMU has adjusted the planning. RAAF has already introduced a request of no cost extesion.
Irregularities in regards to relationships between executing and implementing bodies | Low | Standard and well proven formats are used for fund disbursement between BOAD, RAAF respectively, including formats and standards for reporting and financial accounting.
Limited coordination with other ongoing adaptation initiatives in the target countries | Low | The regional steering committee that has taken place on February, 04th, 2022 gave strong recommandations on building synergies and developing synergies or complementarity with regional and national initiatives. This has been done with GGCA+, ECOWAS Agroecology Programme.
Limited awareness and stakeholder involvement on the project | Low | The project partners have experience in undertaking multi-stakeholder initiatives and aim to ensure that all relevant stakeholders are engaged and involved throughout the project cycle.
Technical
Low capacity of stakeholders to implement the project activities | Medium | The activities of capacity building of stakeholders under the component 1 helped to overcome this obstacle.
The technical practices promoted by the project are confined to the first beneficiaries | Low | The project plans a strong component 3 on dissemination of lessons learned. For 2023 Annual work plan, specific activities are already planned to undertaken and mitigate such risk.
Institutional
Overlap of interventions of public institutions | Low | Clear memorandum of intervention between the project and the different institutions involved in project implementation have taken care of this.
Movement of trained staff to other sectors or outside the project areas. | Medium | Working both with farmers as well as a wide variety of relevant institutions in the project target areas aimed to ensure that capacity remains within the project target areas even when there is some movement of staff.
Strategical and cultural
Intercommunity differences regarding adaptation planning priorities in each community. | Low | During the period under review, we have experienced sud risk. The use of community based approaches to adaptation planning aimed to ultimately ensure that all views are heard and included in the adaptation planning process as well as prioritised based on agreement of the community as a whole.
Reluctance to apply the knowledge and practices for adaptation to climate change cultural barriers in accepting new techniques can be expected. | Low | During the period under review, we have experienced sud risk. The project is intended to provide opportunities for beneficiaries to submit sub-projects on the basis of their need for adaptation while remaining within the project boundaries. Sensitization actions are conducted to facilitate the adaptation of the actions proposed by the project.
Climate
New facets of climate risks emerge during the life of the project | Medium | With regards the MoU signed between RAAF and AGRHYMET, weather and climate forecast are produced by AGRHYMET, and disseminated thanks to various channels, even also local languages.
Low integration of climate, environmental and gender issues in the implementation of the project by the producers | Low | These issues are taken into account in the sub-project selection criteria. Training and awareness activities are programmed to allow sufficient taking into account of climate, environmental, social and gender issues in the implementation of activities on the sites.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Delays in recruitment or appointment of critical staff for the project and/ or Staff changes in both, the Regional Project Management Unit (RPMU) and National Project Management Unit (NPMU) | Low | Staff for the RPMU has been completly recruted and already in place at RAFF Office in Lomé. In addition the staff for the NPMU has been appointed by the Ministers in charge of Agriculture and Environment in each country, and RAFF is in touch with the Cabinet.
During the kick-off meeting, the issue of security in the project implementation sites has been raised. Participants were made aware of the existence of insecure areas in Niger and Burkina Faso that are facing growing civil insecurity | Low | Burkina Faso and Niger proposed new municipalities for the project implementation and new sites meet the criteria retained during the preparation of the project.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
During that period (November 2021-November 2022), no additional risk has been identified, a part from administrative and procurement procedures that are slowing the project implementation, but we need to adapt.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Low integration of environmental and social issues relative to the Adaptation Fund ESP principles in the subprojects ESIA and ESMP. Low capacity to producers for the implementation of environmental and social measures, in accordance with national law and the principles of the Adaptation Fund. | The project will ensure that the ESIAs for subprojects is conducted in accordance to the Adaptation Fund environmental and social policy and national procedures. The project will ensure that the technical and organizational capacities of the beneficiaries are strengthened in order to implement the measures contained in the Environmental and Social Management Plan. The project management unit will ensure that the on-site support by the technical services is effective and beneficial to the perfect implementation of the measures in accordance with the texts in force. | Not available | Not available | Not available | Not available | Not available
2 - Access and equity |  |  | Risk of increase in inequalities between women, men, youth and particularly vulnerable groups. Risk of not full participation of certain groups members in the preparation and the implementation of the subproject. | The project should promote equitable access to project resources by potential beneficiaries, with a focus on women's and youth groups The project will ensure the participation of all stakeholders in project activities without discrimination and in order to ensure fair and equitable access to project benefits including for women and men as well as marginalized groups The project team will ensure that project activities do not adversely affect current user rights to shared natural resources including water and ensure equitable benefits of climate-smart agriculture investments. The project will ensure that when a group of farmers or a farming community is funded, all members of this group or community can participate fully in the activities and benefit from the benefits generated. | Not available | Not available | Not available | Not available | Not available
3 – Marginalized and vulnerable Groups |  |  | Risk of no involvement of marginalized and vulnerable groups in the provision of the resources of the project. | The project will specifically target the most vulnerable and food-insecure groups in the targeted communities. To do this, the project will use the following measures: - ensure that project activities target and help the most vulnerable to become more resilient to climate change, including women, households headed by women, children and youth; - Conducting community-wide outreach in target districts, including vulnerable groups, female-headed households and key informants such as traditional foresight providers; - Establish selection criteria that favor the strong involvement of vulnerable groups. | Not available | Not available | Not available | Not available | Not available
4 – Human rights |  |  | Medium risk related to the health and safety of workers. Low risk of child labor outside the limits of the law. | During construction works, and during their operation, workers are exposed to the risk of accident at work that can go from simple death injuries. It is similarly during the realization on the different technologies on the site with agricultural equipment. In rural areas, children help parents in field activities. Under the project, it is not excluded that children are used to difficult tasks | Not available | Not available | Not available | Not available | Not available
5 – Gender equality and women’s empowerment |  |  | Insufficient taking into account of gender in the implementation of the project | The project should promote gender mainstreaming in different activities. Women and youth must be strongly involved in technical and organizational capacity-building activities to equip them for full participation in planning and decision-making activities. The selection criteria for beneficiaries will have to take gender into account. The project management unit will ensure that at least 50% of direct beneficiaries are women and 50% of all beneficiaries are young people. | Not available | Not available | Not available | Not available | Not available
6 – Core labour rights |  |  | Risk related to the health and safety of workers during infrastructures realization. Risk of child labor outside the limits of the law. | The project management unit will include clear environmental and social clauses in the bidding documents for companies. The project will conduct raise awareness among companies and producers about the provisions of the labour code. The project will raise awareness of beneficiaries on the labor code and children's rights in order to eliminate the worst working conditions of children. | Not available | Not available | Not available | Not available | Not available
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats |  |  | Damage vegetation and wildlife habitat during water infrastructure realization | The management unit will include in the DAO the environmental clauses for the management of vegetation and wildlife habitats that may be found on the sites where water mobilization infrastructures are built. The project will ensure that investments do not encroach on protected areas, buffer zones and natural habitats. Any sub-project having negative interactions with these areas being directly eliminated during the selection phase. | Not available | Not available | Not available | Not available | Not available
10 – Conservation of biological diversity |  |  | Biodiversity loss | The project will strengthen the capacity of farmers in pest management (eg pesticide use) which could be a cause of elimination of certain species. The project recognizes the need to maintain or strengthen biodiversity and ecosystem services and is committed to integrating their sustainable management into climate-smart agriculture practices promoted under this project. Through the climate smart agriculture approach, the project will effectively conserve and enhance biodiversity through assisted natural regulation techniques, grass strips and agroforestry. The project will promote capacity building and farmer-to-farmer learning to strengthen the responsible and efficient management of natural resources, including land, water, soils, pastures and forests. The project will not involve or introduce invasive species or new pests and diseases into project sites and any actions that may result will be properly filtered and subject to relevant national and international laws and guidelines. | Not available | Not available | Not available | Not available | Not available
11 – Climate change
12 – Pollution prevention and resource efficiency |  |  | Risk of misuse of water and risk of conflict between beneficiaries in the use of water from the infrastructures set up by the project. Soil and water pollution. | The project will strengthen the technical and organizational capacities of beneficiary groups for the rational use of water. The project management unit will establish in each beneficiary group a water management committee with clear guidelines. The project will promote integrated pest management (IPM) techniques as a pillar of sustainable agriculture, reduce pesticide dependence and avoid the adverse health effects of chemical use, the safety of farming communities, consumers and the environment.. The project will enroll an experienced pest and pesticide management expert (FAO expert, preferably), to develop and implement a capacity building program for those involved in integrated pest and pesticide management. This Expert will prepare and disseminate an integrated pest management tool box for the use by beneficiaries and technical staff whose technical capacities have been strengthened accordingly. The project promotes the use of organic manure to reduce the use of chemical fertilizers and limit contamination of water in nearby water bodies. Benefits will also be achieved by reducing waste and improving the timing and application of chemical inputs. Climate-smart agricultural practices promoted as part of the project will also reduce soil erosion and thus water pollution. | Not available | Not available | Not available | Not available | Not available
13 – Public health |  |  | Risk of poisoning by inhalation or by consumption of water contaminated by fertilizers or pesticides. Risk of drowning in Runoff Collection basin (BCER). Development of water-related diseases | The project will implement the above measures to limit water and soil pollution to reduce the risk of harm to the health of populations. Capacity building actions on pesticide application, in the event that integrated pest management alternatives prove ineffective in dealing with the problem. If the use of chemical pesticides is needed, the project will ensure that they are WHO class III or U homologous pesticides that are less hazardous to human health. The project will raise awareness, through extension services and site animators (NGOs), on the use of appropriate equipment during phytosanitary treatments and hygiene measures. The project management unit will ensure that BCERs are sized to reduce this risk. The surroundings of the BCERs must be fixed by grass strips or reforestation with appropriate species. The project will inform and sensitize the populations on diseases related to the presence of water (malaria, typhoid fever, amoebic dysentery, etc.); The project will take steps to include the area in the intervention program of the epidemiological surveillance system at the national level. | Not available | Not available | Not available | Not available | Not available
14 – Physical and cultural heritage |  |  | Risk of destruction of the physical heritage during incidental findings | Although the identification of sites takes into account the protection of the physical cultural heritage, incidental findings are not excluded during the implementation of the project. It is the risk of destruction of the physical and cultural heritage during incidental findings | Not available | Not available | Not available | Not available | Not available
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | No.
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | No major new output has been set out in the case the 25 sub-projects will be identified during the second year of the project. We're aware about the compulsory that ESP safeguard measures will be taken in to account.
Have the implementation arrangements been effective during the reporting period? |  | Not yet
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | All needed information have been included in the ToRs for selecting the consultants who should know how to access ESP safaguard and to be in compliance with, both national, BOAD and Adaptation Fund rules and requirements.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Not yet
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Not yet
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | Not yet! TORs for USP are ready but the consultant is no recruted yet, but we're ongoing process to finalize contractualization.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Increasing gender resilience through training empowerment | Objective | o reduce the vulnerability of farmers and pastoralists to climate risk, which is already affecting the level of food security, income generation and ecosystem services of poor communities | 0 | 7,600 households, that to say 53,200 of which 26,600 women (ie. 50%) are direct beneficiaries of site development activities | No field implementation activity has been done during that period
Strengthenin knowledge and capacity through regional and local interations for the promotion of resilient agriculture practices to the adverse effects of climat change | output 1 | Number of beneficiaries informed about climate risk issues through the action of meteorological services | Low regional synergy and complementarity in the production of agro-climatic and meteorological information | At least 60 000 farmers including 50% of women have acces to agro-meteorological information for agricultural planning | A regional workshop meeting on the sharing of experiences on the use of agro-hydro-climatic information and their implications for Agriculture from August 16 to 18, 2022 in Agbélouvé (Lomé, Togo) and which brought together around fifty participants was organized with the support of AGRHYMET.
Strengthenin knowledge and capacity through regional and local interations for the promotion of resilient agriculture practices to the adverse effects of climat change | output 1 | Number of beneficiaries informed about climate risk issues through the action of meteorological services | Low regional synergy and complementarity in the production of agro-climatic and meteorological information | 120 managerial staff and officers of local communities/municipalities (including at least 30% of women) | No field implementation activity has been done during that period
Strengthenin knowledge and capacity through regional and local interations for the promotion of resilient agriculture practices to the adverse effects of climat change | output 1 | Level of technical capacity of regional national and local institutions to promote climate resilient best practices in an CSA approach | Low regional synergy and complementarity in the production of agro-climatic and meteorological information | 250 national technicians (agriculture, water, livestock, environment, forests, and adaptation) including at least 30% of women are trained to promote CSA | No field implementation activity has been done during that period
Climate services adapted to the needs of producers are available with the support of national and regional institutions and can be used by producer | Ootcome 1.1 | Number of beneficiaries informed about climate risk issues through the actions of meteorological services | low access to agrometeorological information for planning agricultural seasons | At least 60 000 producers including 50% of women have access to agrometeorological information adapted for agricultural planning | A regional workshop meeting on the sharing of experiences on the use of agro-hydro-climatic information and their implications for Agriculture from August 16 to 18, 2022 in Agbélouvé (Lomé, Togo) and which brought together around fifty participants was organized with the support of AGRHYMET.
Exchanges with the institutions on agrometeorological forecasts for agricultural campaigns and provision of information adapted to the level of producers | Ootcome 1.1 | Number of producers with access to adapted weather information | Low access to adapted agro meteorological information | At least 60 000 producers, including 50% of women have access to suitable agro-meteorological information | No field implementation activity has been done during that period
Knowledge and practices of climatesmart agriculture are reinforced | output 1.2 | Number of farmers' groups, technical agents, development organizations, associations that have improved their knowledge of the CSA | Lack of CSA training for rural extension services and stakeholders in the project area | At least 400 actors with 50% of women have seen their technical capacity and knowledge strengthened to promote climate resilient CSA practices | No field implementation activity has been done during that period
Strengthening capacity of stakeholders responsible for the design and project implementation to promote a climate smart agriculture | output 1.2 | Number of managers and technicians from national and regional institutions trained | Lack of CSA training for managers and technicians of national and regional institutions | 120 Managerial staff and officers of local communities/municipalities (including at least 30% of women) are trained on the CSA approach and the formulation of micro-projects | No field implementation activity has been done during that period
Strengthening capacity of stakeholders responsible for the design and project implementation to promote a climate smart agriculture | output 1.2 | Number of managers and technicians from national and regional institutions trained | Lack of CSA training for managers and technicians of national and regional institutions | 250 national technicians (agriculture, water, livestock, environment, forests, and adaptation) including 30% of women are trained to promote CSA | No field implementation activity has been done during that period
Strengthening capacity of stakeholders responsible for the design and project implementation to promote a climate smart agriculture | output 1.2 | Number of people and organizations / institutions with enhanced capacity to promote climate smart agriculture | low technical capacity to support producer groups for the development of CSA microprojects and the development of climate resilient practices | 100 representatives of farmers' organizations including 50% of women are trained on the CSA approach | No field implementation activity has been done during that period
Strengthening capacity of stakeholders responsible for the design and project implementation to promote a climate smart agriculture | output 1.2 | Number of people and organizations / institutions with enhanced capacity to promote climate smart agriculture | low technical capacity to support producer groups for the development of CSA microprojects and the development of climate resilient practices | 36,000 people, whose 50% of women, benefited from CSA sensitization in villages / communities | No field implementation activity has been done during that period
Strengthening capacity of stakeholders responsible for the design and project implementation to promote a climate smart agriculture | output 1.2 | Number of people and organizations / institutions with enhanced capacity to promote climate smart agriculture | low technical capacity to support producer groups for the development of CSA microprojects and the development of climate resilient practices | Subprojects have been identified and formulated with the support of Consultants and at least 50% of the beneficiaries are women. | No field implementation activity has been done during that period
Strengthening cross-border collaboration to adapt agriculture to climate change to strengthen CSA's national capacity | output 1.3 | Number of exchange visits organized and number of people trained | Lack of exchange visits and training on adaptation to climate change in agriculture | 250 representatives of groups including 125 women (ie 50% ) who have participated in on-site learning visits for approximately 10,000 members of producer groups | No field implementation activity has been done during that period
Support for the valorization and management of sites | output 2.1 | percentage of beneficiaries with access to quality agricultural inputs | Low access to quality agricultural inputs. | At least 100% of benficiaries (which 50% are women) have access to improved seeds | No field implementation activity has been done during that period
Knowledge Sharing on Resilient Agricultural Best Practices Related to Climate-Smart Agriculture | Component 3 | Number of people accessing information and lessons learned on best climate resilience techniques | Low access to information on climate resilient agricultural best practices | At least 300,000 people of which 50% women benefited from dissemination activities of lessons learned and project knowledge. | No field implementation activity has been done during that period
Knowledge Building and Dissemination of Lessons Learned on Climate Resilient Agricultural Best Practices | output 3.1 | Effectiveness of dissemination channels of lessons learned | Low access to information on climate resilient agricultural best practices in a suitable format | At least 300,000 people of which 50% women benefited from dissemination activities of lessons learned and project knowledge | No field implementation activity has been done during that period
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | poor
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Implementing Entity recommand to Executive Entity to fit with project document targets and commitments.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Not yet in the case field activities are just starting now.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | No more and new arrangements have been set up out of the project document.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | They're not yet effective, in the case field activities are just starting now.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No gap affecting the GP compliance have been identified.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For the reporting period, no grievance has been received in the case that countries field activities are not implemented yet.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity:
| Component 1: Strengthening knowledge and technical capacities through regional and local interactions for the promotion of agricultural practices resilient to the adverse effects of climate change / Outcome 1.1.: Climate services adapted to the needs of producers are available with the support of national and regional institutions and can be used by producers / Outcome 1.2.: Knowledge and practices of climate-smart agriculture are reinforced |  | Outcome 2 | The acquisition of kits comprising direct reading rain gauges, thermometers and air recorders is supposed to be done. A exchange meeting is organized, producers have access to weather information. By the same time farmers groups, technical agents, development organizations and associations have improved their knowlledge on CSA approach and climate resilien best practices. |  | A regional workshop meeting on the sharing of experiences on the use of agro-hydro-climatic information and their implications for Agriculture from August 16 to 18, 2022 in Agbélouvé (Lomé, Togo) and which brought together around fifty participants was organized with the support of AGRHYMET. The tender documents for acquiring the number of kits comprising direct reading rain gauges, thermometers and air recorders have been publisshed. The offers received do not suit us because the prices proposed are largely superior or higher to the budget available and planned for this activity. BOAD has been informed of the unsuccessful nature of this contract and a new call for proposals will be launched at the begining of 2023. | MS
| Component 2: Scaling up best practices related to climate change adaptation in agriculture and pastoralism at the local level / Outcome 2.1.: Promoted best farming and livestock practices are climate resilient and contribute to increased food security |  | Outcome 6 | Sub-projects are not yet selected. TORs for selecting them are now ready and the call of proposals will be done when complementary studies will be realized. The tenders documents for selecting the conslutants are ready, and process will be launched while BOAD provided notice of no objection. No capacity building activities have been implemented for beneficiaries. |  | A call for proposals has been launched after receiving BOAD no objection notice in September 8th, 2023. The slection of the Cabinet who will conduct fields complementary studies is alredy done; we're just waiting for the no objection notice from BOAD and the contract will be signed. | MS
| Component 3: Knowledge Sharing on Resilient Agricultural Best Practices Related to Climate-Smart Agriculture / Outcome 3.1.: Knowledge of resilient agricultural best practices related to climate-smart agriculture is strengthened and disseminated |  | Outcome 8 | Field activities consist on the development of knowledge documents and lessons learned capitalisation. These materials should be disseminated with regards to stakeholders. |  | In the case that no field activities have been implemented, no knowledge documents and lessons learned, have not been disseminated, with regards to stakeholders. But CSA project has been taken to various scientific forum in order to present CSA the project and what we aim to do to for improving community resilience. This is how the CSA project participated in: i) the 2022 Science and Partnership for Africa’s Agriculture Conference (SPAAC), 14-16 September 2022, Accra (GHANA) and UNFCCC CoP27 (UNFCCC), 03-17 November 2022. The CSA Project was represented among the panelist at the following side-events: “Best prac-tices in climate smart agriculture and agroecology: opportunities and challenges for scalling up and contributing to the achievement of West African goals”; “Improving acess to climate services (weather data and climate information) for climate smart agriculture on the one hand and on the other hand moderator of the side-event «Genera-tion of quality data for reliable products to be made available to decision makers for the reduction of risks due to climate change» in the SENEGAL Pavilion. Previously, the project also attended the SENACC (Seminar on Adaptation to Climate Change) from 16 to 19 May 2023, a scientific event on the margins of the 15th session of the Conference of Par-ties (CoP15) the United Nations Convention to Combat Desertification (UNCCD), held in Abidjan, Côte d'Ivoire. The CSA Project made two (02) oral presentations and participated in two (02) panels (“Climate Change, Agricultural System and Land Management: What Adaptation Strategies for Greater Resilience (Agriculture and Land Use)”; “Levers for Increasing Local and Private Sector Involvement in Low Carbon Initiatives (CCA Pri-vate Sector Funding Experience)”). | MS
| Component 4: Project component cost |  | Outcome 7 | No fields activities have been set up at that time. |  | Priroties activities have focused on: i) finalization of institutional arrangements at the national level insofar as the MoUs have been signed with all the Ministries in charge of agriculture of the five (05) beneficiaries; ii) a circular mission to take contact with the administrative authorities and Ministers in charge of agriculture has been conducted May-June 2022 in the five (05) beneficiaries; iii) all five (05) beneficiary countries of the CSA Project have identified their national steering committee members, iv) partnership agreements with regional institutions have been finalized and even signed in the case of the AGRHYMET Regional Center, v) discussions for seting up parternship with CIAT-biodiversity and ILRI (International Livestock Research Institute) and move forawazrd in the case that MoUs are planned to be signed in 2023, and vi) 2023 AWPB has been prepared. | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mr. Ibrahim TRAORE
| Email: | itraore@boad.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The CSA-BOAD project trends should be better at that time. But administrative procedures and bureaucracy are challenging between ECOWAS and BOAD. These "heavy procedures" impactand slow down the project onset implementation; for example, no procurement has been made during that period; that's why the "Procurement sheet"of this PPR, is clean of information. No disbursement has been done also during that period (Nov 2020-Nov 2021). The staff recruitment and unprecedented expectations like COVID-19 lead to some delays. But, in the case administrative progress has been made at the end of 2021, 2022 will be a tipping point in project implementations' activities. One major critical risk is that the RPMU members change for new positions; this can affect the rhythm of implementing activities. Challenges should be classified at both levels, national and regional. With regards to national, sub-projects selection are linked to Consultants fields complementary studies.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Component 1: Strengthening knowledge and technical capacities through regional and local interactions for the promotion of agricultural practices resilient to the adverse effects of climate change / Outcome 1.1.: Climate services adapted to the needs of producers are available with the support of national and regional institutions and can be used by producers / Outcome 1.2.: Knowledge and practices of climate-smart agriculture are reinforced |  | Outcome 1 | The acquisition of kits comprising direct reading rain gauges, thermometers and air recorders is supposed to be done. A exchange meeting is organized, producers have access to weather information. By the same time farmers groups, technical agents, development organizations and associations have improved their knowlledge on CSA approach and climate resilien best practices. |  | A regional workshop meeting on the sharing of experiences on the use of agro-hydro-climatic information and their implications for Agriculture from August 16 to 18, 2022 in Agbélouvé (Lomé, Togo) and which brought together around fifty participants was organized with the support of AGRHYMET. The tender documents for acquiring the number of kits comprising direct reading rain gauges, thermometers and air recorders have been publisshed. The offers received do not suit us because the prices proposed are largely superior or higher to the budget available and planned for this activity. BOAD has been informed of the unsuccessful nature of this contract and a new call for proposals will be launched at the begining of 2023. | MS
| Component 2: Scaling up best practices related to climate change adaptation in agriculture and pastoralism at the local level / Outcome 2.1.: Promoted best farming and livestock practices are climate resilient and contribute to increased food security |  | Outcome 6 | Sub-projects are not yet selected. TORs for selecting them are now ready and the call of proposals will be done when complementary studies will be realized. The tenders documents for selecting the conslutants are ready, and process will be launched while BOAD provided notice of no objection. No capacity building activities have been implemented for beneficiaries. |  | A call for proposals has been launched after receiving BOAD no objection notice in September 8th, 2023. The slection of the Cabinet who will conduct fields complementary studies is alredy done; we're just waiting for the no objection notice from BOAD and the contract will be signed. | MS
| Component 3: Knowledge Sharing on Resilient Agricultural Best Practices Related to Climate-Smart Agriculture / Outcome 3.1.: Knowledge of resilient agricultural best practices related to climate-smart agriculture is strengthened and disseminated |  | Outcome 8 | Field activities consist on the development of knowledge documents and lessons learned capitalisation. These materials should be disseminated with regards to stakeholders. |  | In the case that no field activities have been implemented, no knowledge documents and lessons learned, have not been disseminated, with regards to stakeholders. But CSA project has been taken to various scientific forum in order to present CSA the project and what we aim to do to for improving community resilience. This is how the CSA project participated in: i) the 2022 Science and Partnership for Africa’s Agriculture Conference (SPAAC), 14-16 September 2022, Accra (GHANA) and UNFCCC CoP27 (UNFCCC), 03-17 November 2022. The CSA Project was represented among the panelist at the following side-events: “Best prac-tices in climate smart agriculture and agroecology: opportunities and challenges for scalling up and contributing to the achievement of West African goals”; “Improving acess to climate services (weather data and climate information) for climate smart agriculture on the one hand and on the other hand moderator of the side-event «Genera-tion of quality data for reliable products to be made available to decision makers for the reduction of risks due to climate change» in the SENEGAL Pavilion. Previously, the project also attended the SENACC (Seminar on Adaptation to Climate Change) from 16 to 19 May 2023, a scientific event on the margins of the 15th session of the Conference of Par-ties (CoP15) the United Nations Convention to Combat Desertification (UNCCD), held in Abidjan, Côte d'Ivoire. The CSA Project made two (02) oral presentations and participated in two (02) panels (“Climate Change, Agricultural System and Land Management: What Adaptation Strategies for Greater Resilience (Agriculture and Land Use)”; “Levers for Increasing Local and Private Sector Involvement in Low Carbon Initiatives (CCA Private Sector Funding Experience)”). | MS
| Component 4: Project component cost |  | Outcome 7 | No fields activities have been set up at that time. |  | Priroties activities have focused on: i) finalization of institutional arrangements at the national level insofar as the MoUs have been signed with all the Ministries in charge of agriculture of the five (05) beneficiaries; ii) a circular mission to take contact with the administrative authorities and Ministers in charge of agriculture has been conducted May-June 2022 in the five (05) beneficiaries; iii) all five (05) beneficiary countries of the CSA Project have identified their national steering committee members, iv) partnership agreements with regional institutions have been finalized and even signed in the case of the AGRHYMET Regional Center, v) discussions for seting up parternship with CIAT-biodiversity and ILRI (International Livestock Research Institute) and move forawazrd in the case that MoUs are planned to be signed in 2023, and vi) 2023 AWPB has been prepared. | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | JACQUES ANDRE NDIONE
| Email: | jndione@araa.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
During the reporting period (Nov 2020-Nov 2021), priroties activities have focused on regional arrangements facilitiies, field activities recorded a big delay. Whatever, major achievements are dealing with: i) Preparation of the procedures manual, ii) Elaboration of a memorandum between ECOWAS and the Ministries in charge of Agriculture of the 5 beneficiary countries, iii) Elaboration of the ToR and selection of the consultant for the lifting of the suspensive conditions, iv)Creation of the Steering Committee, v) Establishment of the Management Unit at the regional level, vi) Establishment of the Management Units at the national level , vii) First call/transfer for funds sent by the RAAF to BOAD, viii) Preparation of the inception report and the 2021 PTBA and ix) Transmission of the inception report and the 2021 PTBA to BOAD and the Adaptation Fund. The staff recruitment and unprecedented expectations like COVID-19 lead to some delays. But, in the case administrative progress has been made at the end of 2021, 2022 will be a tipping point in project implementations' activities. One major critical risk is that the RPMU members change for new positions; this can affect the rhythm of implementing activities. Challenges should be classified at both levels, national and regional. With regards to national, sub-projects selection are linked to Consultants fields complementary studies.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | Component 1: Strengthening knowledge and technical capacities through regional and local interactions for the promotion of agricultural practices resilient to the adverse effects of climate change / Outcome 1.1.: Climate services adapted to the needs of producers are available with the support of national and regional institutions and can be used by producers / Outcome 1.2.: Knowledge and practices of climate-smart agriculture are reinforced |  | Outcome 1 | The acquisition of kits comprising direct reading rain gauges, thermometers and air recorders is supposed to be done. A exchange meeting is organized, producers have access to weather information. By the same time farmers groups, technical agents, development organizations and associations have improved their knowlledge on CSA approach and climate resilien best practices. |  | A regional workshop meeting on the sharing of experiences on the use of agro-hydro-climatic information and their implications for Agriculture from August 16 to 18, 2022 in Agbélouvé (Lomé, Togo) and which brought together around fifty participants was organized with the support of AGRHYMET. The tender documents for acquiring the number of kits comprising direct reading rain gauges, thermometers and air recorders have been publisshed. The offers received do not suit us because the prices proposed are largely superior or higher to the budget available and planned for this activity. BOAD has been informed of the unsuccessful nature of this contract and a new call for proposals will be launched at the begining of 2023. | MS
| Component 2: Scaling up best practices related to climate change adaptation in agriculture and pastoralism at the local level / Outcome 2.1.: Promoted best farming and livestock practices are climate resilient and contribute to increased food security |  | Outcome 6 | Sub-projects are not yet selected. TORs for selecting them are now ready and the call of proposals will be done when complementary studies will be realized. The tenders documents for selecting the conslutants are ready, and process will be launched while BOAD provided notice of no objection. No capacity building activities have been implemented for beneficiaries. |  | A call for proposals has been launched after receiving BOAD no objection notice in September 8th, 2023. The slection of the Cabinet who will conduct fields complementary studies is alredy done; we're just waiting for the no objection notice from BOAD and the contract will be signed. | MS
| Component 3: Knowledge Sharing on Resilient Agricultural Best Practices Related to Climate-Smart Agriculture / Outcome 3.1.: Knowledge of resilient agricultural best practices related to climate-smart agriculture is strengthened and disseminated |  | Outcome 8 | Field activities consist on the development of knowledge documents and lessons learned capitalisation. These materials should be disseminated with regards to stakeholders. |  | In the case that no field activities have been implemented, no knowledge documents and lessons learned, have not been disseminated, with regards to stakeholders. But CSA project has been taken to various scientific forum in order to present CSA the project and what we aim to do to for improving community resilience. This is how the CSA project participated in: i) the 2022 Science and Partnership for Africa’s Agriculture Conference (SPAAC), 14-16 September 2022, Accra (GHANA) and UNFCCC CoP27 (UNFCCC), 03-17 November 2022. The CSA Project was represented among the panelist at the following side-events: “Best prac-tices in climate smart agriculture and agroecology: opportunities and challenges for scalling up and contributing to the achievement of West African goals”; “Improving acess to climate services (weather data and climate information) for climate smart agriculture on the one hand and on the other hand moderator of the side-event «Genera-tion of quality data for reliable products to be made available to decision makers for the reduction of risks due to climate change» in the SENEGAL Pavilion. Previously, the project also attended the SENACC (Seminar on Adaptation to Climate Change) from 16 to 19 May 2023, a scientific event on the margins of the 15th session of the Conference of Par-ties (CoP15) the United Nations Convention to Combat Desertification (UNCCD), held in Abidjan, Côte d'Ivoire. The CSA Project made two (02) oral presentations and participated in two (02) panels (“Climate Change, Agricultural System and Land Management: What Adaptation Strategies for Greater Resilience (Agriculture and Land Use)”; “Levers for Increasing Local and Private Sector Involvement in Low Carbon Initiatives (CCA Private Sector Funding Experience)”). | MS
| Component 4: Project component cost |  | Outcome 7 | No fields activities have been set up at that time. |  | Priroties activities have focused on: i) finalization of institutional arrangements at the national level insofar as the MoUs have been signed with all the Ministries in charge of agriculture of the five (05) beneficiaries; ii) a circular mission to take contact with the administrative authorities and Ministers in charge of agriculture has been conducted May-June 2022 in the five (05) beneficiaries; iii) all five (05) beneficiary countries of the CSA Project have identified their national steering committee members, iv) partnership agreements with regional institutions have been finalized and even signed in the case of the AGRHYMET Regional Center, v) discussions for seting up parternship with CIAT-biodiversity and ILRI (International Livestock Research Institute) and move forawazrd in the case that MoUs are planned to be signed in 2023, and vi) 2023 AWPB has been prepared. | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | TRAORE IBRAHIM
| Email: | itraore@boad.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Project trends should be better at this time. Because the project team is now complete. BOAD asked ECOWAS to prioritize the lifting of the conditions precedent. We hope that ECOWAS will perform in the next 4 months. We know that 2023 will be a tipping point in project implementation activities. An acceleration plan has been drawn up and submitted to the Secretariat of the Adaptation Fund.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
OBJECTIVE | Number of people improving their resilience and their living condition | 0 | No big porgress has been done yet | 7,600 households, that to say 53,200 of which 26,600 women (ie. 50%) are direct beneficiaries of site development activities 3,000 breeders are beneficiaries of activities to improve the mobility of transhumant livestock
COMPONENT 1: Strengthening knowledge and technical capacity through regional and local interactions for the promotion of resilient agriculture practices to the adverse effects of climate change | Number of beneficiaries informed about the issues on climate risks through meteorological services | Low synergy and complementarity in the production of agro-climatic and regional meteriological information. | A regional workshop meeting on the sharing of experiences on the use of agro-hydro-climatic information and their implications for Agriculture from August 16 to 18, 2022 in Agbélouvé (Lomé, Togo) and which brought together around fifty participants was organized with the support of AGRHYMET. The tender documents for acquiring the number of kits comprising direct reading rain gauges, thermometers and air recorders have been publisshed. The offers received do not suit us because the prices proposed are largely superior or higher to the budget available and planned for this activity. BOAD has been informed of the unsuccessful nature of this contract and a new call for proposals will be launched at the begining of 2023. | 60000 farmers, of which 50% are women, have access to agro-meteorological information for the agricultural planning
| Level of technical capacity of regional, national and local institutions to promote best practices in climate change resilience under an IFA approach | To be determined through baseline study | A delay has been noted in the case that this activity is included in CIAT MoU that has been discussed. Due to some administrive procedures, discussions were so long but finally both parties agreed on essential issues and implementation are planned for 2023. | 120 Managerial staff and officers of local communities/municipalities (including at least 30% of women) are trained on the CSA approach and the formulation of micro-projects - 250 national technicians (agriculture, water, livestock, environment, forests, and adaptation) including at least 30% of women are trained to promote CSA - 50 NGOs / Associations are trained on the CSA approach and the identification, formulation on climate smart agriculture projects on climate change
| Percentage of beneficiaries adopting climate-friendly agricultural practices | To be determined through baseline study | A delay has been noted in the case that this activity is included in CIAT MoU that has been discussed. Due to some administrive procedures, discussions were so long but finally both parties agreed on essential issues and implementation are planned for 2023. | 120 Managerial staff and officers of local communities/municipalities (including at least 30% of women) are trained on the CSA approach and the formulation of micro-projects - 250 national technicians (agriculture, water, livestock, environment, forests, and adaptation) including at least 30% of women are trained to promote CSA - 50 NGOs / Associations are trained on the CSA approach and the identification, formulation on climate smart agriculture projects on climate change
| Number of beneficiaries at the local level whose capacities are strengthened to address climate risks with appropriate responses | To be determined through baseline study | A delay has been noted in the case that this activity is included in CIAT MoU that has been discussed. Due to some administrive procedures, discussions were so long but finally both parties agreed on essential issues and implementation are planned for 2023. | 100 representatives of farmers' organizations including at least 50% of women are trained on the CSA approach - 36,000 people, includin 50% of women, benefited from CSA sensitization in villages / communities - 250 representatives of groups including 125 women (ie. 50%) who have participated in on-site learning visits for approximately - 10,000 members of producer groups -12 community development plans were strengthened for the promotion of CSA in Burkina Faso, Niger, Benin, Togo and Ghana
| Number of improved or implemented community plans or policies that incorporate the IFA approach | To be determined through baseline study | A delay has been noted in the case that this activity is included in CIAT MoU that has been discussed. Due to some administrive procedures, discussions were so long but finally both parties agreed on essential issues and implementation are planned for 2023. | 250 representatives of groups including 125 women (ie. 50%) who have participated in on-site learning visits for approximately - 10,000 members of producer groups -12 community development plans were strengthened for the promotion of CSA in Burkina Faso, Niger, Benin, Togo and Ghana
OUTCOME 1.1. Climate services adapted to the needs of producers are available with the support of national and regional institutions and can be used by producers | Number of beneficiaries informed on climate issues through meteorological | Poor access to agro-meteorological information for planning agricultural seasons | A regional workshop meeting on the sharing of experiences on the use of agro-hydro-climatic information and their implications for Agriculture from August 16 to 18, 2022 in Agbélouvé (Lomé, Togo) and which brought together around fifty participants was organized with the support of AGRHYMET. The tender documents for acquiring the number of kits comprising direct reading rain gauges, thermometers and air recorders have been publisshed. The offers received do not suit us because the prices proposed are largely superior or higher to the budget available and planned for this activity. BOAD has been informed of the unsuccessful nature of this contract and a new call for proposals will be launched at the begining of 2023. | At least 60,000 producers, 50% of whom are women, have access to agro-meteorological
ACTIVITITY 1.1.1. Strengthening agroclimatic and meteorological information | Number kits comprising direct reading rain gauges, thermometers and air recorders acquired | Low local weather monitoring network Old or defective equipment Obsolete data and unsuitable for agricultural planning The information on available maps is out of date | The tender documents for acquiring the number of kits comprising direct reading rain gauges, thermometers and air recorders have been publisshed. The offers received do not suit us because the prices proposed are largely superior or higher to the budget available and planned for this activity. BOAD has been informed of the unsuccessful nature of this contract and a new call for proposals will be launched at the begining of 2023. | 600 kits comprising direct reading rain gauges, thermometers and air recorders are installed Local data is collected and processed Adapted agro climatic maps are produced and disseminated Local geo-referenced maps on agro-ecological zones and land uses are local and produced
ACTIVITITY 1.1.2. Exchanges with the institutions on agro-meteorological forecasts for agricultural campaigns and provision of information adapted to the level of producers | Improvement the knowledge of many groups of farmers, agents, and technicians | Lack of training in ICA for rural extension services and practitioners in the project area | A delay has been noted in the case that this activity is included in CIAT MoU that has been discussed. Due to some administrive procedures, discussions were so long but finally both parties agreed on essential issues and implementation are planned for 2023. | 400 actors with 50% of women have seen their technical capacity and knowledge strengthened to promote climate resilient CSA practices + 1 exchange visit and learning in the field is organized per year for the benefit of farmers groups and technical services between the different regions of the different intervention countries to strengthen regional technical collaboration for the promotion of climate smart agriculture
ACTIVITITY 1.2.1. Strengthening capacity of stakeholders responsible for the design and project implementation to promote a climate smart agriculture | Number of managers and technicians from national and regional institutions trained | Lack of CSA training for managers and technicians of national and regional institutions | A delay has been noted in the case that this activity is included in CIAT MoU that has been discussed. Due to some administrive procedures, discussions were so long but finally both parties agreed on essential issues and implementation are planned for 2023. | 120 Managerial staff and officers of local communities/municipalities (including at least 30% of women) are trained on the CSA approach and the formulation of micro-projects + 250 national technicians (agriculture, water, livestock, environment, forests, and adaptation) including 30% of women are trained to promote CSA
ACTIVITITY 1.2.1. Strengthening capacity of stakeholders responsible for the design and project implementation to promote a climate smart agriculture | Number of individuals and organisations/institutions with increased capacity to promote a climate-smart agriculture | Low technical capacity to support producer groups for the development of CSA micro-projects and the development of climate resilient practices | A delay has been noted in the case that this activity is included in CIAT MoU that has been discussed. Due to some administrive procedures, discussions were so long but finally both parties agreed on essential issues and implementation are planned for 2023. | 50 NGOs / Associations are trained on the CSA approach and the identification, formulation on climate smart agriculture projects on climate change + 100 representatives of farmers' organizations including 50% of women are trained on the CSA approach + 36,000 people, whose 50% of women, benefited from CSA sensitization in villages / communities + Subprojects have been identified and formulated with the support of Consultants and at least 50% of the beneficiaries are women.
ACTIVITITY 1.2.2. Strengthening cross-border collaboration to adapt agriculture to climate change to strengthen CSA's national capacity | Number of organised exchange visit and number of trained people | Lack of exchange visits and training on adaptation to climate change in agriculture | A delay has been noted in the case that this activity is included in CIAT MoU that has been discussed. Due to some administrive procedures, discussions were so long but finally both parties agreed on essential issues and implementation are planned for 2023. | 1 exchange visit and learning in the field is organized annually for the benefit of groups of farmers and technical services between regions and countries involved in the project 250 representatives of groups including 125 women (ie 50% ) who have participated in on-site learning visits for approximately 10,000 members of producer groups Operationalization of a framework for exchange and sharing of experiences, and consultation on resilience techniques to climate change in agriculture between the neighboring administrative regions of Burkina Faso, Niger, Benin, Togo and Ghana.
ACTIVITITY 1.2.2. Strengthening cross-border collaboration to adapt agriculture to climate change to strengthen CSA's national capacity | Number of organised exchange visit and number of trained people | Low integration of climate-smart agriculture into local and national development plans | A delay has been noted in the case that this activity is included in CIAT MoU that has been discussed. Due to some administrive procedures, discussions were so long but finally both parties agreed on essential issues and implementation are planned for 2023. | 12 community development plans were strengthened for the promotion of CSA in Burkina Faso, Niger, Benin, Togo and Ghana.
2.1. Promoted best farming and livestock practices are climate resilient and contribute to increased food security | Percentage of adoption of CSA practices | 0 | No porgress has been done yet. In fact the selection of the Consultant for conducting field complementary studies is done. Contract will be signed in January 2023. | 80% of direct beneficiaries have adopted CSA practices
ACTIVITITY: 2.1.1. Promotion of integrated techniques and activities related to water management, rehabilitation and conservation | Number of hectares of land restored | Low soil productivity | No porgress has been done yet. In fact the selection of the Consultant for conducting field complementary studies is done. Contract will be signed in January 2023. | 2 500 ha of restored soil with the techniques of: filter bunds, stone bunds, grass strips, zaï-tassa techniques, half-moons, mulching, organic manure and Natural Assisted regeneration for maize, sorghum and millet developpement
ACTIVITITY: 2.1.1. Promotion of integrated techniques and activities related to water management, rehabilitation and conservation | Rate of yield improvement to support food security and improve beneficiaries' living conditions | Low agricultural yield | No porgress has been done yet. In fact the selection of the Consultant for conducting field complementary studies is done. Contract will be signed in January 2023. | Improvement of at least 80% of agricultural yields in the project intervention sites
ACTIVITITY 2.1.1. Promotion of integrated techniques and activities related to water management, rehabilitation and conservation | Kilometre of transhumance corridors secure cross-border | Recurrent conflicts between farmers and pastoralists | No porgress has been done yet. In fact the selection of the Consultant for conducting field complementary studies is done. Contract will be signed in January 2023. | 1,000 km of corridors or cross-border transhumance tracks
ACTIVITITY 2.1.1. Promotion of integrated techniques and activities related to water management, rehabilitation and conservation | Number of water points and boreholes constructed | Insufficient water points for livestock | No porgress has been done yet. In fact the selection of the Consultant for conducting field complementary studies is done. Contract will be signed in January 2023. | 100 water points (80 BCER and 20 human-powered boreholes) were installed along secure transhumance corridors + Reduction of conflicts between breeders and agricultures
ACTIVITITY 2.1.2: Support for the valorization and management of sites | Percentage of beneficiaries with access to quality agricultural inputs | Low access to quality agricultural inputs. | No porgress has been done yet. In fact the selection of the Consultant for conducting field complementary studies is done. Contract will be signed in January 2023. | 100% of benficiaries (which 50% are women) have access to improved seeds; 80% of beneficiary producers have access to organic fertilizer and / or quality fertilizers; 75% of beneficiary producers make use of alternatives to integrated pest management through on-site support and sensitization; 100% of producers benefit from technical support and advice for the implementation of resilient and sustainable measures related to agriculture, environment, water, pest management, livestock, etc.
COMPONENT 3: Knowledge Sharing on Resilient Agricultural Best Practices Related to Climate-Smart Agriculture | Number of people with access to information and lessons learned on the best climate resilience technics | Types of documents learned on lessons learned | No porgress has been done yet with regards to field activities. CSA project has been taken to various scientific forum in order to present CSA the project and what we aim to do to for improving community resilience. This is how the CSA project participated in: i) the 2022 Science and Partnership for Africa’s Agriculture Conference (SPAAC), 14-16 September 2022, Accra (GHANA) and UNFCCC CoP27 (UNFCCC), 03-17 November 2022. The CSA Project was represented among the panelist at the following side-events: “Best prac-tices in climate smart agriculture and agroecology: opportunities and challenges for scalling up and contributing to the achievement of West African goals”; “Improving acess to climate services (weather data and climate information) for climate smart agriculture on the one hand and on the other hand moderator of the side-event «Genera-tion of quality data for reliable products to be made available to decision makers for the reduction of risks due to climate change» in the SENEGAL Pavilion. Previously, the project also attended the SENACC (Seminar on Adaptation to Climate Change) from 16 to 19 May 2023, a scientific event on the margins of the 15th session of the Conference of Par-ties (CoP15) the United Nations Convention to Combat Desertification (UNCCD), held in Abidjan, Côte d'Ivoire. The CSA Project made two (02) oral presentations and participated in two (02) panels (“Climate Change, Agricultural System and Land Management: What Adaptation Strategies for Greater Resilience (Agriculture and Land Use)”; “Levers for Increasing Local and Private Sector Involvement in Low Carbon Initiatives (CCA Private Sector Funding Experience)”). | 300,000 people of which 50% women benefited from dissemination activities of lessons learned and project knowledge.
OUTCOME 3.1: Knowledge of resilient agricultural best practices related to climate-smart agriculture is strengthened and disseminated | Number of documents on the knowledge and lessons disseminated in aformat appropriete for each stakeholder | Types of documents learned on lessons learned | No porgress has been done yet with regards to field activities. CSA project has been taken to various scientific forum in order to present CSA the project and what we aim to do to for improving community resilience. This is how the CSA project participated in: i) the 2022 Science and Partnership for Africa’s Agriculture Conference (SPAAC), 14-16 September 2022, Accra (GHANA) and UNFCCC CoP27 (UNFCCC), 03-17 November 2022. The CSA Project was represented among the panelist at the following side-events: “Best prac-tices in climate smart agriculture and agroecology: opportunities and challenges for scalling up and contributing to the achievement of West African goals”; “Improving acess to climate services (weather data and climate information) for climate smart agriculture on the one hand and on the other hand moderator of the side-event «Genera-tion of quality data for reliable products to be made available to decision makers for the reduction of risks due to climate change» in the SENEGAL Pavilion. Previously, the project also attended the SENACC (Seminar on Adaptation to Climate Change) from 16 to 19 May 2023, a scientific event on the margins of the 15th session of the Conference of Par-ties (CoP15) the United Nations Convention to Combat Desertification (UNCCD), held in Abidjan, Côte d'Ivoire. The CSA Project made two (02) oral presentations and participated in two (02) panels (“Climate Change, Agricultural System and Land Management: What Adaptation Strategies for Greater Resilience (Agriculture and Land Use)”; “Levers for Increasing Local and Private Sector Involvement in Low Carbon Initiatives (CCA Private Sector Funding Experience)”). | A good practice manual, a lessons learned document, A catalog of best practices and techniques related to climate change adaptation in agriculture are disseminated
ACTIVITITY 3.1.1: Knowledge Building and Dissemination of Lessons Learned on Climate Resilient Agricultural Best Practices | Number of knowledge documents and lessons broadcast | Low access to information on climate resilient agricultural best practices in a suitable format | No porgress has been done yet with regards to field activities. CSA project has been taken to various scientific forum in order to present CSA the project and what we aim to do to for improving community resilience. This is how the CSA project participated in: i) the 2022 Science and Partnership for Africa’s Agriculture Conference (SPAAC), 14-16 September 2022, Accra (GHANA) and UNFCCC CoP27 (UNFCCC), 03-17 November 2022. The CSA Project was represented among the panelist at the following side-events: “Best prac-tices in climate smart agriculture and agroecology: opportunities and challenges for scalling up and contributing to the achievement of West African goals”; “Improving acess to climate services (weather data and climate information) for climate smart agriculture on the one hand and on the other hand moderator of the side-event «Genera-tion of quality data for reliable products to be made available to decision makers for the reduction of risks due to climate change» in the SENEGAL Pavilion. Previously, the project also attended the SENACC (Seminar on Adaptation to Climate Change) from 16 to 19 May 2023, a scientific event on the margins of the 15th session of the Conference of Par-ties (CoP15) the United Nations Convention to Combat Desertification (UNCCD), held in Abidjan, Côte d'Ivoire. The CSA Project made two (02) oral presentations and participated in two (02) panels (“Climate Change, Agricultural System and Land Management: What Adaptation Strategies for Greater Resilience (Agriculture and Land Use)”; “Levers for Increasing Local and Private Sector Involvement in Low Carbon Initiatives (CCA Private Sector Funding Experience)”). | Lessons learned are documented. A website created and operational. Development and dissemination of a manual of good practice about agriculture climate-smart in a smart format understandable at local, national and regional levels. Regional newsletters and national newspapers are produced and available for the general public. A catalogue of best practices and techniques related to adaptation for climate change in agriculture is disseminated in a format appropriate for each potential stakeholder (government and technical services, producer organisations, local communities

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | With regards to 2022 implementation year activities, lessons learned are various, but let us say the challenge for the CSA project was to restore confidence between beneficiairies countries and RAAF, including BOAD due to the big delay. That's why it's good to organize a circular mission, presenting to administratrive and ministerial authorities the project who is now going on implementation field activities. Signing MoUs with all beneficiairies countries and RAAF, was a great achievement. In the case that sor me prerequisite shloud be filled, regarding fields complementary studies, for better successful and to be in compliance with AF conditions, all procurement process have been filled. On the other hand, the RPMU (Regional Project management unit) concentrate on the organization of regional activities that don't depend on procurement, with the support of AGRHYMET and CIAT. Fruitful discussions are concluded thanks to MoUs, and things are moving smoothly in the right direction. In addition, it was also to talk about the CSA project and we aim to do for improving communities' resilience. That's why CSA project participated in : i) "Forum 3AO" (Alliance pour l'Agroécologie en Afrique de l'Ouest, Bissau, 10-13 December 2022) and ii) the 2022 Science and Partnership for Africa’s Agriculture Conference (SPAAC), 14-16 September 2022, Accra (GHANA) and UNFCCC CoP27 (UNFCCC), 03-17 November 2022. The CSA Project was represented among the panelist at the following side-events: “Best practices in climate smart agriculture and agroecology: opportunities and challenges for scalling up and contributing to the achievement of West African goals”; “Improving acess to climate services (weather data and climate information) for climate smart agriculture on the one hand and on the other hand moderator of the side-event «Generation of quality data for reliable products to be made available to decision makers for the reduction of risks due to climate change» in the SENEGAL Pavilion. Previously, the project also attended the SENACC (Seminar on Adaptation to Climate Change) from 16 to 19 May 2023, a scientific event on the margins of the 15th session of the Conference of Par-ties (CoP15) the United Nations Convention to Combat Desertification (UNCCD), held in Abidjan, Côte d'Ivoire. The CSA Project made two (02) oral presentations and participated in two (02) panels (“Climate Change, Agricultural System and Land Management: What Adaptation Strategies for Greater Resilience (Agriculture and Land Use)”; “Levers for Increasing Local and Private Sector Involvement in Low Carbon Initiatives (CCA Private Sector Funding Experience)”). Last but not least, the tender documents for acquiring the number of kits comprising direct reading rain gauges, thermometers and air recorders have been publisshed. The offers received do not suit us because the prices proposed are largely superior or higher to the budget available and planned for this activity. BOAD has been informed of the unsuccessful nature of this contract and a new call for proposals will be launched at the begining of 2023. This lag between what has been planned (120 000 USD) and the real price on the market. Adjustements are already made with countries in order to identify enabling conditions for successful acheivement. Finally, all milestones and deliverables done in 2022, are good steps for moving forward in the right direction.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Some delays remained but thanks to support of BOAD, solutions have been found for all of them. In fact the main constraints are admi,istratives and procurement procedures, at internal level. We have fruitful discussions and we hope that, our Administrative understanbd better that we need to accelerate procedures for better achieivements.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | Changes undertaken are mainly: i) a better schedule in planning activities, ii) all pre-requisite conditions to work with countries are scarcely done and National coordination teams are set up already, iii) AGRHYMET and CGIAR CIAT-BIODIVERSITY are involved in planning process; ILRI will do the same with reagrds to Livestock activities.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Fo that period (November 2021-November 2022), no more activity with regards to environmental and social safeguard measures were taken… We limit ourselves to the content of the approved document up to now.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Fo that period (November 2021-November 2022), no major steps or more activity with regards to gender issue was taken… We limit ourselves to the content of the approved document up to now, in the case that no field activity were implemented. In addition, we've agreeded with our partners like AGRHYMET and CGIAR CIAT-BIODIVERSITY, that gender issue is a compulsory, and they obligation to fully feel all indicators related to gender with regards to the project.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | 1431-Full-Prop-CSA-WA-14-5-18-clean
Implementing Entity | BOAD
Type of implementing entity | RIE
Country | Togo
Region | Africa
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 153720 | 53200 | 100520 | Total |  |  |  | Total
|  | % of female beneficiaries |  | 0% |  | % of female beneficiaries |  | 50% |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 2: Partially effective | Total | 60000 | Drought | 2: Partially effective | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Agriculture | 1: No capacity | Total | 250 | Agriculture | 2: Low capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 30% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 120 | 30% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Food security | 1: No capacity | Public | Regional | Food security | 2: Low capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 0 | National | Food security | 1: No capacity | 50 | National | Food Security | 2: Low capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  |  |  | Agriculture |  |  |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 60000 | 50% | 2: Partially not aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 0 | 40% to 60% | 1: Aware of neither |  | 50 | 40% to 60% | 2: Partially not aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | handbooks | National |  | 12 | Handbooks | National
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Agriculture | Regional | 1: Non responsive (Lacks all elements ) |  | Agriculture | Regional | 2: Partially responsive (Lacks most elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital |  | Strengthening infrastructure | 500 | Physical capital |  | Strengthening infrastructure
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Food Security | Regional | Innovation replicated |  | Food Security | Regional | Innovation replicated
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  |  | Food Security | No innovative practices | 1: Ineffective |  | Food Security | Undertaking innovative practices | 2: Partially effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  | 1: Ineffective |  | Innovative practice |  | 2: Partially effective