## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | January 22nd 2020 - December 31st 2020
| Project Title: | Reducing climate vulnerability and flood risk in coastal urban and semi urban areas in cities in Latin America
| Project Summary: | Adaptation to climate change in coastal cities is a main challenge for both countries (Ecuador and Chile) as coastal areas are more exposed and vulnerable to the negative effects of climate change and the impacts of weather-related disasters. The project objective is to reduce vulnerability to climate-related floods, mud flows and landslides in the three coastal cities by mainstreaming a risk-based approach to adaptation, building collaboration and networking, and developong a culture of adaptation. To achieve this objective, the most prevalent risks were considered in each of the three cities. In the case of the Chilean populations, these are mudflows, while for Esmeraldas floods and landslides were considered. The lessons learned from this initiative are projected to be useful for the entire region of Latin America and the Caribbean. The project has three components: Component 1 focus on priority actions to increase resilience in the three cities. Four outcomes will be generated by mainstreaming DRR into local planning, building infrastructure which incorporate climate-related variables, improving climate monitoring, and strengthening the existing early warning and response systems. Component 2 focus on strengthening the capacities of local government officers and communities, as well as fortifying connections between communities and local and national government. Two outcomes will be generated by developing an online training course on risk-based adaptation for municipal and government officers and technical staff and implementing communication and education strategies to increase local awareness and contribute to build cultural memory. The online course will be open to professionals from other coastal cities of Latin America and the Caribbean. Component 3 focus on nurturing the project´s communities of practice and to document and disseminate the lessons. The backbone of the regional project are the communities of practice that allow the development of collective learning on specific topics. Five communities of practice will be developed.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Development Bank of Latin America (CAF) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Regional Implementing Entity (RIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Chile and Ecuador | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Cities of Antofagasta and Taltal in Chile and Esmeraldas in Ecuador | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | July 16th 2018
IE-AFB Agreement Signature Date: |  | December 11th 2018 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | January 22nd 2020 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | July 22nd 2022
January 22nd 2025
Original Completion Date:
Revised Completion Date after approval of |  | N/A
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | N/A | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | N/A | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Nury Bermudez | Dominican Republic
| Email: | nury.bermudez@undp.org | Ecuador
| Date: | 2019-07-04 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Diego Teca | Equatoral Guinea
| Email: | diego.teca@ambiente.gob.ec | Eritrea
| Date: | 2021-01-08 | Estonia
| Name: | Carolina Urmeneta
| Email: | curmeneta@mma.gob.cl
| Date: | 2020-01-22
| Implementing Entity |  | Ethiopia
| Name: | Carolina Cortes | Fiji
| Email: | acortes@caf.com | Finland
| Date: | 2018-12-11 | France
| Executing Agency |  | Gambia
| Name: | Mónica Andrade | Georgia
| Email: | monica.andrade@undp.org | Germany
| Date: | 2019-07-04 | Ghana
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to December, 31st 2020 |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [December, 31 2020] | 1181487 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | To date, the remaining value to be disbursed to the executing entity in the next 4 years is USD 11,698,513. The second dibursment of $2'625.641 will be made once the PPR and procurement plan has been approved by the Project Board |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 7766.09 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1. Stormwater management plan for Antofagasta | 27764.5134
| 1.2. Green infrastructure plan for Esmeraldas | 67283.2494
| 2.1. Mudflow control infrastructure in Antofagasta | 16931.4621
| 2.2. Landslide mitigation works in Esmeraldas | 23190.0409
| 3.1. Weather radar in Esmeraldas and a storm detection system in Antofagasta | 48375.0876
| 3.2. Increased number of meteorological stations in Antofagasta, Taltal and Esmeraldas | 5746.0339
| 4.1. Enhanced public warning system in Antofagasta and Taltal | 15980.1927
| 4.2. Pilot flood warning system in Esmeraldas | 22019.8113
| 4.3. Evacuation route maps and signals in Antofagasta, Taltal and Esmeraldas | 17530.3546
| 5.1. Course on risk-based adaptation in coastal cities | 34755.6387
| 6.1. Public communication and education strategies for Antofagasta, Taltal and Esmeraldas. | 38255.6995
| 6.2. Narrators´ initiative initiated | 32053.1473
| 7.1. Electronic platform to facilitate communication among stakeholders and dissemination of lessons and best practice | 18792.1212
| 7.2. Lessons and best practice documented and disseminated | 50007.8224
| Project Execution cost | 33494.85
Project/Programme Cycle Management Fee charged by the Implementing Entity
| TOTAL | 452180.025 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1. Stormwater management plan for Antofagasta | 377910.9457 | 2022-03-01
| 1.2. Green infrastructure plan for Esmeraldas | 120548.0312 | 2021-10-01
| 2.1. Mudflow control infrastructure in Antofagasta | 267588.4157
| 2.2. Landslide mitigation works in Esmeraldas | 244000 | dec-21
| 3.1. Weather radar in Esmeraldas and a storm detection system in Antofagasta | 455895.4612 | dec-21
| 3.2. Increased number of meteorological stations in Antofagasta, Taltal and Esmeraldas | 161000 | dec-21
| 4.1. Enhanced public warning system in Antofagasta and Taltal | 30000 | 2022-03-01
| 4.2. Pilot flood warning system in Esmeraldas | 98000 | 2021-05-01
| 4.3. Evacuation route maps and signals in Antofagasta, Taltal and Esmeraldas | 104506.1412 | 2022-03-01
| 5.1. Course on risk-based adaptation in coastal cities | 192000 | aug-21
| 6.1. Public communication and education strategies for Antofagasta, Taltal and Esmeraldas. | 142017.7262 | 2021-09-01
| 6.2. Narrators´ initiative initiated | 64000 | 2021-11-01
| 7.1. Electronic platform to facilitate communication among stakeholders and dissemination of lessons and best practice | 77534.8812 | dec-21
| 7.2. Lessons and best practice documented and disseminated | 79039.1112 | dec-21
| Project Execution cost | 193123.22 | dec-21
| Project/Programme Cycle Management Fee charged by the Implementing Entity |  | dec-21
| TOTAL | 2607163.9334 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Change of central government in Chile. New president and congress will take office in 2018 | N/A | The project was formally launched in January 2020 with a new central government. The project has been presented to the new authorities and is supported by them for its implementation
Change of municipal governments in Antofagasta and Taltal. The new authorities will take office in December 2020. | Moderate | Elections postponed to April 2021 due to COVID. Once the local authorities are positioned, the project will be presented for support
Change of municipal and provincial governments in Esmeraldas. The new authorities will take office in 2019 | N/A | The project was formally launched in January 2020 with a new local government. The project has been presented to the new authorities and is supported by them for its implementation
Support withdrawal from local counterparts, taking into account the change of Governments. | Low | Meetings with key local government authorities to ensure support during implementation Commitment of institutions to designate technical focal points to ensure project continuity
The change of Governments could eventually lead to staff re-structuration, meaning that there could possibly be a knowledge gap between the newcomers. | Moderate | Commitment of institutions to designate technical focal points to ensure project continuity In case there is new staff, meetings will be held to share the progress of the project Periodic activity progress and budgetary implementation reports will be carried out by the project
Lower economic activity in both countries and impact of April´s earthquake in Ecuador | Moderate | The impact of the April 2016 earthquake in Ecuador has been overcome; however, a significant reduction in economic activity in both countries resulting from COVID-19 has been shown. Within the framework of the project implementation, partner institutions have been supported for the implementation of activities to reduce the risk in case of climate disasters within project intervention areas
Grant not being delivered and/or not being delivered on time. | High | CAF cash flow will allow to respond to disbursements in case of delays
Increase in budget due to costs miscalculations, and/or due to overprices during project implementation. | Medium | The project was developed 5 years ago, budget changes are needed. A budget modification request is been analyzed by CAF and UNDP to be sent to the AF shortly.
GADPE has no experience with meteorological monitoring | High | GADPE is provided with limited technical staff, who do not have a specialization in hydro-meteorological monitoring. A consultancy has been hired to improve climate monitoring in Esmeraldas, which incorporates a management model including training the provincial government staff
Baseline studies are not up to date | Low | Changes were made to the baselines of the population composition in project intervention zones in Antofagasta (migration). The baseline is being updated and contact will be made with IOM and UNHCR to generate synergies in the activities to be developed.
Inaccuracy in radar and storm detection system implementation | Moderate | Technical advice and support are available by the competent national body (DMC - Chile, INAMHI - Ecuador). Regular advisory meetings on meteorology issues
Misuse of the online platform created to share best practices between coastal cities. | Low | The Project Communication Strategy (under development) will contain the guidelines for the correct use of the web platform. Once the strategy is available, the web platform will be developed
Lack of understanding of the project, and hence opposition from the local inhabitants. | Moderate | The only activity under this risk is the Cerro Gatazo landslide mitigation works in Esmeraldas. Cerro Gatazo is an informal settlements, discussions have been take place with local governement and neighborhood leaders. Data collection is difficult to perform for fear of contagion of the population. Informative workshops have been held for local beneficiaries on the activities that the project will develop
Effect of El Niño / La Niña in precipitation and local weather conditions. | Low | Monitoring current collected weather information from the project intervention area
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Authorities and technical staff of government institutions prioritize health emergency activities by COVID-19 | Moderate | Two strategic partners in Ecuador ( Municipal GAD in Esmeraldas and SNGRE) in compliance with their competences are directly addressing the health emergency, which has made it difficult to coordinate project actions. Coordination with central and local government institutions, scheduling meetings that enable the fulfillment of project activities
It has been difficult to make an approach with project beneficiaries due to COVID restrictions | High | Performing virtual events (workshops, webinars) when is possible Execution of face-to-face workshops following guidelines established by the central government
Governments return to strict isolation measures | High | Activities planned in 2021 will be done using virtual modality, as it is possible.
Frequent changes of authorities in project member government institutions. | High | In Ecuador, there have been changes of authorities in all the project partner institutions throughout 2020. For example, in INHAMI, there was a change of the Executive Director; in the Ministry of Environment and Water, the Minister, the Undersecretary of Environment and Water and the Provincial Director of Environment of Esmeraldas were changed. In Chile, there have been no changes Commitment of institutions to designate technical focal points to ensure project continuity In case there is new staff, meetings will be held to share the progress of the project Periodic activity progress and budgetary implementation reports will be carried out by the project
Project Unit professionals and/or focal points have the possibility of getting sick by COVID | Moderate | Focal point support technicians must be established so they can be replaced in case of sick leave Project personnel carry out their activities in virtual mode to avoid contagion.
Change of Regional Government Authorities in Antofagasta in May 2021 | Moderate | Once the local authorities are positioned, the project will be presented to be provided with their support
Change of central government authorities in Ecuador in May 2021 | Moderate | The new authorities will take office on 24/05/2021. Once the central government authorities have been positioned, the project will be presented to be provided with their support
Activities that have not been considered in the Project Document and that are necessary to achieve the objectives of the project. | Moderate | Various activities have been identified that were not planned in the project document (Partial Plan on Gatazo hill, Hydro-meteorological Data Quality Control of the Esmeraldas River basin, Regional Communication Strategy) Budget adjustments have been made to develop these identified activities that are necessary to achieve the proposed objectives of the project
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
During the first year of implementation of the project, several risk situations identified in the Project Document have been presented mainly related to the change of authorities and technical specialists within the partner institutions, as well as an incorrect calculation of the monetary values estimated in the Project Document for certain activities. With regard to the change in rotation of authorities and technical personnel, the measures implemented to overcome this situation have focused on requesting the designation of main and alternate focal points in the institutions, which allow to continue with the implementation of the project despite the absence of any of these. In addition, periodic project progress reports are sent to partner institutions so that there is a written record of the activities that are implemented within the project. In the case of the appointment of new authorities, project presentations, objectives and progress status have been made. All these measures have made it possible to move forward with activities without further delays. Regarding activities with an outdated budget estimate in relation to what is laid out in the Project Document, budgetary adjustments have been made as far as possible to meet the results required by the project. The measures implemented have successfully allowed to overcome the risks that have come about and thus continue with the implementation of the project.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Risk: Insufficient alignment with laws and technical standards, especially related to implementation of concrete infrastructure works and climate monitoring under Component 1, Outcome 2 and Outcome 3. Impact: Grey and green infrastructure implementation could not get the Environmental Registry - Ecuador or the Environmental Impact Declaration – DIA for Chile | Gray and green infrastructure works not yet in place Safeguard measures identified in the Project Document: Activity 5. Interventions in Chile have to comply with technical standards, environmental permits and construction code regulations. Activity 6. Interventions in Ecuador have to comply with technical standards, environmental permits and construction code regulations. | Updated studies for implementation of grey and green infrastructure Environmental permit application submitted | 0 updated studies 0 environmental permit application processed | In the next year, the studies for the gray and green infrastructure works will be updated. Once the studies have been updated, all the necessary documentation will be presented to obtain the environmental permits in accordance with the regulations Up to date, as a mitigation measure, the Cerro Gatazo (Esmeraldas) Partial Plan is being carried out to determine land tenure in the area where the green and gray infrastructure project will be executed. In Antofagasta the Rainwater Master Plan is updated | The study carried out of land tenure does not allow to know the owners, thus making it difficult to execute the intervention. (Ecuador) Chile (N/A) | Alternative legal mechanisms are sought to clarify land tenure in the mitigation zone in Cerro Gatazo
2 - Access and equity |  |  | Risk: Possible interruption of water supply, energy services or roads / streets accessibility. The beneficiary might have no access to project benefits because of inexistent mechanism to ensure participation of communities, marginalized, vulnerable groups, and stakeholder and local authorities. Impact 1: If the community is not properly communicated and involved in the process of updating the plan, their local knowledge in their surrounding area such as “Campamentos” or in the ravine routes will not be taken into account. Impact 2: If the community does not participate in the process of preparing the green-infrastructure plan for Esmeraldas, the community will not be informed of risks of residing on hill and will repeat and conceive it as a possible settlement place. Impact 3: If the community is not properly communicated and involved in the process of updating the designs of the infrastructure, their local knowledge in their surrounding area such as “Campamentos” or in the ravine routes will not be taken into account. Impact 4: Do not exist conditions to approve the declaration and preserve the protected forest Impact 5: Impossibility to install the radar and meteorological stations in the best location reached. Radar and meteorological stations without maintenance could not operate properly or not lasting the expected lifetime. Community members could harm or steal the monitoring instruments. Impact 6: If the community does not participate or comment the evacuation maps and procedures for Antofagasta and Taltal, they will not help with their local knowledge and own situation. Also, it is important that they are aware of all the ideas and must agree with the plan. If not, human lives could be in danger. Impact 7: Unable to help their community in an emergency situation. Impact 8: Insufficient information available to update the evacuation maps. Human lives could be in danger. Impact 9: Lack of sustainability of the action and population still in danger. Impact 10: If the community is not able to participate in localization of the banners they may be unused increasing the possibility of accidentally Impact 11: The use of the electronic platform may be limited if the community or community - social leaders does not empower themselves to use it. Impact 12: Technical Staff with lack of knowledge would cause misunderstanding of the disaster risk reduction and adaptation subject and create some difficulties on the implementation phase. Impact 13: Trainers without real capacities to manage disaster risk reduction and adaptation issues in their daily working. Impact 14: Technical staff from the local government without real capacities to manage disaster risk reduction and adaptation issues in their daily working. Impact 15: Technical staff of Esmeraldas local government without proper knowledge about green infrastructure or eco-engineering measures to cope with adaptation measures in the future. Impact 16: Local stakeholders no deeply into green infrastructure or eco engineering would cause lack of sustainability of the actions. Impact 17: Not participation of the social community in the communities of practice. The heterogeneity could be lost. Impact 18: The use of the electronic platform may be limited if the community or community - social leaders does not empower themselves to use it. Impact 19: Not awareness of the community in general of the lessons and best practices of the project. | Safeguard measures identified in the Project Document: Activity 1 - 2 - 3 - 4 - 8: The Local Social Specialist for Chile and Ecuador respectively will prepare a “Communication and Participatory Strategy” that will contain all the activities and how the local community should be involved . Activity 4: The process of including climate change considerations will used comprehensive methodology to fulfill the main objective, of mitigate the population living at risk. Activity 6: The Local Social Specialist for Ecuador will communicate about the Grievance mechanism available. The procedure and forms will be accessible to all actors directly involved in the actions. Also the Operational contractor shall: • Re-Identify the vulnerable groups in the area of influence before the implementation of the project and organize a consultation meeting with the direct beneficiaries and affected groups. • If there is any possibility of interruption of the basic services caused such as water shortage or energy disruptions, the operational contractor team shall make communication to the community affected. • The operational contractor team shall be responsible for the coordination action related with traffic and temporary closure of traffic. In accordance with communities, routes and schedules of access to the Gatazo operational area can be planned. • Fences or barriers and pedestrian pathways are required to be installed. • Receive inquires, suggestions from beneficiaries and communities involved during the consultancy process and if needed the proceed with the grievance mechanism. Activity 8: Trainings and participatory strategy put in place by the local specialist for social issues during the whole implementation. Media Specialist works in behavioral insights messages to explain the importance of this action for the population own safety. Activity 9 - 10 - 11- 12 - 13 - 14 - 15 - 19: The study to identify the location must analyze different places based on a criteria matrix, such as: accessibility, security, no disturb landscape or other telecom instruments among others. The project will ensure that the government has technician in the area and train them to used and maintain the radar. The community need to be informed clearly, a campaign would be implemented by the Media Specialist to reach different target of population. Activity 16 - 18 - 21: A comprehensive information strategy in place to involve the whole community in the evacuation maps. The process will be conducted by the Local Social Specialist based on the “Communication and Participatory Strategy” Activity 17 - 20 - 22 - 23 - 25: Real involvement of the community in the different phases of the process, based on the Communication and Participatory Strategy. Activity 24: The Local Social Specialists shall be aware that the socialization and presentation of the maps is relevant for their use. The “Communication and Participatory Strategy” shall include workshop to define the localization of the maps. Activity 26 - 35 - 36 - 37: The Regional Media Specialist in the “Communication and Participatory Strategy” shall include the development of the regional electronic platform. Activity 27: The Project Board and the Project Manager of the project will require them to participate in the Courses. The courses will be mandatory for all technical staff in both countries. Activity 28: Motivate the trainers to actively participate in the training prepared for them about green infrastructure and disaster risk reduction strategies. Activity 29: Understand the final beneficiaries of this courses, this one means the personnel from the local governments. Before implementing the courses, a survey will be conducted to understand their knowledge, expertise and behaves. The courses will be prepared based on a comprehensive analysis of this database. Also, the timetable of the classes will be analysis thoroughly to fine the best and productive usage time. Activity 31:Motivate the technical staff to actively participate in the training prepared for them about green infrastructure and eco-engineering. Prepare a comprehensive Course Plan with the best technician on eco-engineering, with experience in tropical areas and with native vegetable species. Activity 32: The whole process about the green infrastructure plan need the involvement of key local stakeholders during the implementation. The Local Social Specialist for Esmeraldas shall be aware that the socialization and presentation of the plans and be part of the “Communication and Participatory Strategy”. | Number of Communication and Participatory Strategies Number of Technical report of location for equipment installation Number of training workshops for the technical staff of the institutions in charge of the stations Percentage of project technical staff who have taken the regional risk-based adaptation course Number of grievances received related to access to basic services | 0 Communication and Participatory Strategy 0 Technical report of location for equipment installation 0 training workshops for the technical staff of the institutions in charge of the stations 0% project technical staff who have taken the regional risk-based adaptation course 0 grievances received related to access to basic services | Online and attended workshops have been held with the beneficiaries and stakeholders to gather their contributions and involve in the project Ten workshops were held with key actors and project beneficiaries: - Three workshops for the Early - Warning System - Two workshops for the Partial Land Use and Tenure Plan - Two Workshops for the Green Infrastructure Plan The Grievance mechanism has been socialized to the beneficiaries in workshops | Not identified | Not identified
3 – Marginalized and vulnerable Groups |  |  | Risk: The project might impede an access to basic services such as clean air, energy and housing, safe may be affected. This referred to Component 1. Impact: Claims, non-conformity and possible interruption of works may occur. | This risk is activated once the grey and green infrastructure works are carried out in Esmeraldas. In this reporting period, no safeguard measures have been required. Safeguard measures identified in the PRODOC: Activity 6: The Local Social Specialist for Ecuador will communicate about the Grievance mechanism available. The procedure and forms will be accessible to all actors directly involved in the actions. Also the Operational contractor shall: • Re-Identify the vulnerable groups in the area of influence before the implementation of the project and organize a consultation meeting with the direct beneficiaries and affected groups. • The operational contractor team shall be responsible for the coordination action related with traffic and temporary closure of traffic. In accordance with communities, routes and schedules of access to the Gatazo operational area can be planned. • Fences or barriers and pedestrian pathways are required to be installed. • Receive inquires, suggestions from beneficiaries and communities involved during the consultancy process and if needed by the grievance mechanism. | Number of grievances received related to problems of access to basic services | 0 grievances received related to problems of access to basic services | In this reporting period, no safeguard measures have been required | Not identified | Not identified
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | Risk: Either women or men has unequal opportunities to participate taking into account their working schedules or lifestyles, this referred to in Component 1, Component 2 and Component 3. Impact 1: Only one gender could assist to the course. The gender perspective could be lost, is women cannot assist, children assistance also could be put in risk. Impact 2: Only one gender could assist to the communities of practice. The gender perspective could be lost, if women cannot participate. | The project has promoted equal opportunities for both women and men by taking into account schedules, lifestyle and responsibilities. Safeguard measures identified in the PRODOC: Activity 33: The Local Social Specialist for Esmeraldas shall be aware that the socialization and presentation of the plans should the in schedules that women can attend and be part of the “Communication and Participatory Strategy”. Activity 34: The Local Social Specialist for Chile shall be aware that the socialization and presentation of the plans should the in schedules that women can attend and be part of the “Communication and Participatory Strategy”. Activity 35: The Local Social Specialist for Chile and Ecuador shall be aware that the socialization and presentation of the plans should the in schedules that women can attend and be part of the “Communication and Participatory Strategy”. | Percentage of women's participation in events held by the project | 0% of event attendees have been women | In all the events carried out by the project in the reporting period, all the conditions have been taken to ensure that the participation of men and women is equal. Schedules, lifestyles and responsibilities that may affect the participation of men and women have been considered | Not identified | Not identified
6 – Core labour rights |  |  | Risk: Insufficient alignment with core labour rights, especially related to implementation of concrete infrastructure works and climate monitoring under Component 1, Outcome 2 and Outcome 3 Impact: Persons and workers in the surroundings areas could be injured or affected. | In this reporting period, no safeguard measures have been required. Safeguard measures identified in the PRODOC: Activity 5 - 6: The operational contractor team in Chile and Ecuador shall be responsible for the control of the entire works and implement specific mitigation measures to cope with casualties during construction. • Consider the identified hazards including those that may originate from outside the workplace that are capable of adversely affecting the health and safety of persons under the control of the organization within the workplace. • Applied control related to risk assessment • Follow an accident investigation form. • Recognize extra hours of work, in compliance with the labour regulation of each country. • Be aware of the equipment that the workers use during the infrastructure works. • Take into consideration the medical care emergency kit at the infrastructure works. • Keep in mind the medical check provided at the beginning of the works. • Construction workers must also be provided with identification tags. • Comply with the national legislation – Labour Codes of Ecuador and Chile • Ensure that employment procedures/ policy of the operational contractor is communicated to local stakeholders. • The intention of giving preferential employment to locals is clearly communicated, to discourage an influx of job-seekers from other areas. | Number of grievances received related to problems of violation of labour rights | 0 grievances received | All the procurement process have followed the UNDP Financial Regulations and Rules (2012) as well as a sustainable procurement process including core labour rights. The winning consultants in the different processes must comply with the labor law of each country. | Not identified | Not identified
7 – Indigenous people |  |  | Risk: Indigenous beneficiary families not being adequately informed and engaged to access the range of project benefits. Impact 1: Not use of the information developed. Impact 2: Not participation of the indigenous community in the Narrator’s initiative. The heterogeneity perspective could be lost, is the indigenous community cannot assist. Impact 3: Not participation of the indigenous community in the communities of practice. The heterogeneity could be lost perspective could be lost, is the indigenous community cannot assist. | The project has promoted equal opportunities, incluiding indigenous people and afro-ecuadorina by taking into account working schedules, lifestyle, or languages. This referred to in Component 2. Safeguard measures identified in the PRODOC: Activity 30: The Regional Media Specialist in the “Communication and Participatory Strategy” shall include the development of the regional electronic platform. Activity 33 - 35 - 37: The Local Social Specialist for Esmeraldas shall be aware that the socialization and presentation of the plans should the in schedules that Chachis can attend and be part of the “Communication and Participatory Strategy”. | Communication and participation strategy guarantees participation of indigenous groups | 0 Communication and participation strategies developed | In all the events carried out by the project in the reporting period, all the conditions have been taken to ensure that the participation of indigenous people and afro ecuadorians. Schedules, lifestyles and responsibilities that may affect their participation have been considered | Not identified | Not identified
8 – Involuntary resettlement |  |  | Risk: Temporary physical relocation for the nearest families leaving informal settlements in the proximity of the intervention in Cerro El Gatazo – Esmeraldas, basically related with the removal of mud and soil to stabilize the hill. Impact: Claims, nonconformity and possible interruption of the works could occur. | This risk is activated once the grey and green infrastructure works are carried out in Esmeraldas. In this reporting period, no safeguard measures have been required. Safeguard measures identified in the PRODOC: Activity 6: The Local Social Specialist for Ecuador will prepare a “Communication and Participatory Strategy” that will contain all the Activities and how the local community should participate during their development. Implementation of the activities related with the Landslide mitigation infrastructure in Cerro Gatazo - Ecuador, the Operational contractor shall: • Re-Identify the vulnerable groups in the area of influence before the implementation of the project and organize a consultation meeting with the direct beneficiaries and affected groups. • If there is any possibility of the need of possible temporary resettlements this shall be presented as a Plan to the Project Board. • Receive complaints, inquires, suggestions from beneficiaries and communities involved during the consultancy process and if needed by the grievance mechanism. • The GADE team shall be responsible for the coordination action related to the temporary resettlements. • The GADE team shall be responsible for the temporary localization during the project | Number of grievances received related to problems of access to basic services | 0 grievances received | In this reporting period, no safeguard measures have been required | Not identified | Not identified
9 – Protection of natural habitats
10 – Conservation of biological diversity |  |  | Risk: The introduction of non-endemic species for the stabilization of Cerro Gatazo in Esmeraldas may pose a risk for the project. (such decision will come when USP intervention are completely developed) Impact: Introducing non-endemic species could damage the natural biodiversity, even though it is an area already intervened. | In this reporting period, no safeguard measures have been required. Safeguard measures identified in the PRODOC: Activity 2: A study will be undertaken prior to the selection of which species will be used on the implications of introducing different species. Activity 7: The operational contractor has to develop the revegetation in accordance with the Green Infrastructure Plan approved by the Project Board previously. The species that are going to be used should be in the Green Infrastructure Plan. Based on the findings of study, the choice of native species will be appealed. | Technical report on the selection of species to be used for reforestation | 0 Technical reports | In this reporting period, no safeguard measures have been required. However, preliminary meetings have been held with the Forest Restoration Project of the Ministry of Environment and Water to analyze the species to be used. Also, at the moment the Green Infraestructure Plan is being developed | Not identified | Not identified
11 – Climate change |  |  | Risk: There is no a risk of significant or unjustified increase in greenhouse gas emissions, considering that the project preliminary will not produce more than 1 MM ton /CO2eq during its lifespan. However, for the sake of the project and the compliance of the E&SP this will be attended with a Carbon Footprint recognized tool. This will be classified as risk. Impact 1: The contribution of GHG emissions directly affects the adaptation of Antofagasta, Taltal and Chile. Impact 2: The contribution of GHG emissions directly affects the adaptation of Esmeraldas and Ecuador. | This risk is activated once the grey infrastructure works are carried out in Esmeraldas and Antofagasta. In this reporting period, no safeguard measures have been required Safeguard measures identified in the PRODOC: Activity 5 - 6: Carbon Footprint shall be presented Monitoring system of the GHG emissions shall be presented Approval of Carbon Footprint and the Monitoring system of the GHG | Monitoring system of the GHG emissions developed | 0 Monitoring system of the GHG emissions | In this reporting period, no safeguard measures have been required. In the next year the plans for the implementation of grey infrastructure will be updated. | Not identified | Not identified
12 – Pollution prevention and resource efficiency |  |  | Risk: The project may be implemented in a way that does not meet applicable standards for minimizing material resource use, the production of wastes, and the release of pollutants. Impact 1: The generation of wastes and pollutants during the construction works will pollute the surrounding area of Antofagasta. Impact 2: Health diseases affecting the population of the surroundings and workers. The generation of wastes and pollutants during the construction works will pollute the urban area of Esmeraldas. As environmental impact of gabion retaining walls is basically the slight increment the of greenhouse emissions taking into account the transport of materials. Impact 3: Impossibility to install the radar and meteorological stations in the best location reached. Impact 4: Radar and meteorological stations without maintenance could not operate properly or not lasting the expected lifetime. Impact 5: Community members could harm or steal the monitoring instruments. Impact 6: Impossibility to install the meteorological stations and the storm detection system in the best location reached. Impact 7: Meteorological stations and the storm detection system without maintenance could not operate properly or not lasting the expected lifetime. | This risk is activated once the grey infrastructure works are carried out in Esmeraldas and Antofagasta as well as the installation of meteorological instruments and early warning systems. In this reporting period, no safeguard measures have been required Safeguard measures identified in the PRODOC: Activity 5: A construction plan shall be presented to the Project Board. A specific monitoring procedure for the construction works shall be presented to the Project Board. The operational contractor shall implement a monitoring plan to control: • Water consumption. • Fuel consumption. • Type of fuel consumption • Raw material consumption. • Energy consumption. • Solid waste generation. • Wastewater / generation (quality of wastewater). • Construction waste / debris generation. Approve the Construction Plan Activity 6: The mitigation measures are part of the Health Impact Assessment (HIA) A specific monitoring procedure for the construction works shall be presented to the Project Board. Activity 11 - 12 - 13 - 14 - 15 - 19: The study to identify the location must analyze different places based on a criteria matrix, such as: accessibility, security, no disturb landscape or other telecom instruments among others. The project coordinator will ensure that the government has technician in the area and train them to used and maintain the radar. This condition is mandatory to guarantee the sustainability of the action. | Monitoring plan for pollution prevention and resource efficiency developed | 0 Monitoring plan for pollution prevention and resource efficiency | In this reporting period, no safeguard measures have been required. In the next year the plans for the implementation of grey infrastructure will be updated and meteorological equipment and early warning systems will be installed | Not identified | Not identified
13 – Public health |  |  | Risk: The project designed and implemented in a way that produces potentially significant negative impacts on public health. Like any common infrastructure work, there is a low probability risk of collapse, especially during the period of construction and if a hazard materialized during this period, hazards such as: heavy rains, earthquake. Impact: Community – public health affected in noise or air pollutants. | This risk is activated once the grey infrastructure works are carried out in Esmeraldas and Antofagasta. In this reporting period, no safeguard measures have been required Safeguard measures identified in the PRODOC: Activity 5 - 6: A Health Impact Assessment shall be presented to the Project Board. Approval of the HIA. The operational contractor team in Chile and Ecuador shall be formed responsible for the control of all project related to Public Health and will: • Develop an Occupational Health and Safety Management Protocol. • Consider the routine and non-routine activities of the organization to be sure all of them are coordinated. • Beware how all persons accessing the work place including contractors and visitors (clothing, signals, helmets, etc.). • Bear in mind the human behavior, capabilities and other human factors that could increment the potential failure of structural elements of the Project. • Take into consideration how the operational contractor control threats created near the workplace during work -related activities. • Keep in mind how the infrastructure, equipment and materials at the workplace affects construction works. • Consider how the organization identifies changes or proposed changes to its activities or materials it uses. • Consider how modifications to the OH&S protocol / system, whether they be temporary or not, impact on the operations, processes and activities of the organization. • Consider how the project identified legal requirements for health and safety of persons beyond the immediate workplace, including those who are exposed to the workplace activities. • Consider the effects of the design of work areas, processes, installations, machinery/equipment, operating procedures and work project, including their adaptation to human capabilities. | Occupational Health and Safety Management Protocol developed | 0 Occupational Health and Safety Management Protocol developed | In this reporting period, no safeguard measures have been required. In the next year the plans for the implementation of grey infrastructure will be updated. | Not identified | Not identified
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | CAF has formally informed all Responsible Parties about the ESMP and potential risks to Environmental and Social Safeguards.
Have the implementation arrangements been effective during the reporting period? |  | Yes. As this is the first year of implementation, the CAF has ensured that the Responsible Parties are aware of the identified safeguards and mitigation measures, as well as targeted assessments identified in the ESMF.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | UNDP has regularly monitored the risks identified and the safeguard measures in the reporting period. UNDP has promoted events to socialize with the beneficiaries the developed activities. In addition, it has ensured the equitable participation of men and women in all events.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes. All of this year's safeguard measures were successfully implemented. The events carried out by the project considered a gender approach
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8] |  | After a technical-financial analysis carried out by the project, with support from the DMC, the project will contract the storm detection service instead of acquiring a storm detection system as indicated in PRODOC. This activity was analyzed under the 15 environmental and social principles of the Adaptation Fund. The other USP implementation agreements will be made in the following year once the document updates for the gray infrastructure works and the exact locations of the radar, and weather stations are in place
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | All positions required for the fulfillment of the ESMP are clearly identified and responsibilities are assigned. At the moment, the only position pending recruitment is the social specialist in Ecuador. Due to the COVID-19 pandemic, this position will be hired the following year
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | The ESMP has been updated considering the activity of contracting the service of a storm detection system
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: Hiring the service of a storm detection system in Antofagasta . | Yes | There is a risk that the beneficiaries of the project do not aware of the benefits of the activity Men or women do not have the same opportunities to participate in events and activities planned because their work schedules or lifestyles are not considered | Yes | Appropriate consultations have been carried out during the identification of risks and impacts for this activity with the respective technical institutions in Chile. The grievance mechanism has not been socialized in Chile as expected due to the COVID-19 pandemic | Yes | Promotion of the storm detection service, in the territorial committees in accordance with the established in the Communication and Community Relations Strategy of Antofagasta and Taltal Promotion of the storm detection service, in the territorial committees and women's committees, in accordance with the provisions of the Communication and Community Relations Strategy of Antofagasta and Taltal | Communication and Participatory Strategies developed Percentage of women's participation in events held by the project
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
You should not include only two neighborhoods, you should include the neighborhoods where there are hills like the Cocoy |  | The beneficiary does not include any means of communication to receive a response. However, the project gave a large explanation to the workshop assistance about the project and the area at high risk.
Install a first aid area, provide protective supplies and waste control in the rivers |  | An answer was provided and the person raising the complaint was satisfied with the feedback provided.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Men and women protected by improved risk-reduction measures | Objective | Number of men and women protected by improved risk-reduction measures in Antofagasta, Taltal and Esmeraldas. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | End of project Antofagasta = 380,000 (ca., 50% women) Taltal = 10,000 (ca., 50% women) Esmeraldas = 161,000 (ca., 50% women) | Good. Due to COVID-19's restrictive measures, few workshops have been held to help improve climate risk adaptation measures; however, in the inception workshops in Ecuador and Chile, there has been excellent participation by women
Plans that incorporate provisions for adaptation to climate change with gender perspective. | Outcome | Number of plans that incorporate provisions for adaptation to climate change with gender perspective. | Stormwater management plan Antofagasta = 0 Green infrastructure plan Esmeraldas = 0 | Mid-term: 1 End of project: 2 | Satisfactory In Chile, during the reporting period, the contracting process for the elaboration of the Plan has been initiated. In Ecuador, the Green Infrastructure Plan is already being developed. Both plans incorporate a gender approach
Men and women protected by improved infrastructure | Outcome | Number of men and women protected by improved infrastructure | Antofagasta = 0 Esmeraldas = 0 | End of project: 12,840 Antofagasta = (ca., 50% women) Esmeraldas = 500 (ca., 50% women) | This activity does not apply to the reporting period
Men and women covered by alert and evacuation route signs to respond to floods (Esmeraldas), landslides (Esmeraldas) and mudflows (Antofagasta and Taltal) | Outcome | Number of men and women covered by alert and evacuation route signs to respond to floods (Esmeraldas), landslides (Esmeraldas) and mudflows (Antofagasta and Taltal) | Antofagasta = 0 Taltal = 0 Esmeraldas (floods) = 0 Esmeraldas (landslides) = 0 | Antofagasta = 380,000 people (ca., 50% women) Taltal = 10,000 people (ca., 50% women) Esmeraldas (floods) = 161,000 people (ca., 50% women) Esmeraldas (landslides) = 161,000 people (ca., 50% women) | Good. In Ecuador, the early warning system is in the design phase and incorporates a gender approach. In Chile, EWS will be held the following year
The early warning systems in Antofagasta, Taltal, Cerro Gatazo and Isla Luis Vargas Torres are gender and culturally sensitive and consider the special needs of persons with disabilities. | Outcome | Number of early warning systems | Number of early warning systems Antofagasta = 0 Taltal = 0 Cerro Gatazo = 0 Isla Luis Vargas Torres = 0 | Four early warning systems are gender and culturally sensitive and consider the special needs of persons with disabilities. | Good. In Ecuador, the early warning system is in the design phase and incorporates a gender approach. In Chile, EWS will be held the following year
Staff (men and women) of local governments and pertinent entities trained on risk-based adaptation with a gender perspective in coastal cities. | Outcome | Number of staff (men and women) of local governments and pertinent entities trained on risk-based adaptation with a gender perspective in coastal cities. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 Other coastal cities Chile = 0 Other coastal cities Ecuador = 0 | Antofagasta = >50 Taltal = >10 Esmeraldas = >20 Other coastal cities Chile = >10 Other coastal cities Ecuador = >10 About 40% will be women | This activity does not apply to the reporting period
Men and women who have participated in awareness activities and events. | Outcome | Number of men and women who have participated in awareness activities and events. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = >30,000 (ca., 50% women) Taltal = >1,000 (ca., 50% women) Esmeraldas = >16,000 (ca., 50% women) | Satisfactory Due to COVID-19's restrictive measures, few workshops have been held to help improve climate risk adaptation measures; however, in the inception workshops in Ecuador and Chile, there has been excellent participation by women
Narrators (men and women) trained to maintain cultural memory of climate-related disaster and risks. | Outcome | Number of narrators (men and women) trained to maintain cultural memory of climate-related disaster and risks. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = 10 (ca., 50% women) Taltal = 5 (ca., 50% women) Esmeraldas = 10 (ca., 50% women) | This activity does not apply to the reporting period
Men and women who have participated in events for dissemination of lessons and best practice (e.g., workshops, exchange visits, seminars) | Outcome | Number of men and women who have participated in events for dissemination of lessons and best practice | 0 | Mid-term >100 people > 50% women End of project: >200 people > 40% women | Satisfactory Due to COVID-19's restrictive measures, few workshops have been held to help improve climate risk adaptation measures; however, in the inception workshops in Ecuador and Chile, there has been excellent participation by women In addition, the project organized three webinars on: "Use of green infrastructure and nature-based solutions as climate risk reduction measures", "Policies and economic benefits of green infrastructure in urban environments" and "Green infrastructure at the service of the community", in which national and international experiences on the subject were shared. A total of 359 people participated in the events, with 41% women's participation
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | During the reporting period, CAF ensured socialice the importance of compliance the gender policy.
Have the implementation arrangements at the IE been effective during the reporting period? |  | All activities implemented by the project have a strong gender approach.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | UNDP has ensured the equitable participation of men and women in all events carried out. Training to the project team on its policy of Prevention of Sexual Exploitation and Abuse
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes. All the events carried out by the project considered a gender approach
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No complaints related to gender equity and women's empowerment have been received
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | C1 / Outcome 1. Enhanced plans and green infrastructure reduces vulnerability to floods, landslides and mudflows in three coastal cities |  | Outcome 4 | - Engineer company contract to update stormwater management plan for Antofagasta. - Prepare and implement a training event on green infrastructure planning in coastal cities. Three-day workshop (ca., 30 people) in Esmeraldas. Participants will be technical staff from GADM and relevant entities - Situation analysis of climate-related risks and options to enhance green infrastructure in the city of Esmeraldas |  | Regarding the Outcome 1. The activities planned for the first year have been 90% completed. UNDP Chile has indicated that a company has been selected to update the Antofagasta Stormwater Management Plan and that the contracting process is progressing. The Green Infrastructure Plan for Esmeraldas is under development, this consultancy includes the analysis of the climate risk. It was developed a virtual three-day workshop on green infrastructure, which increased exponentially the number of participants. Three webinars where held on green infrastructure with national and international lecturers and more than 200 participants. | S
| Outcome 2. Reduced vulnerability to floods, landslides and mudflows in two coastal cities |  | Outcome 4 | - Purchase of AQUAVEO WMS software and network server to model and analyse watersheds. | - Purchase of AQUAVEO WMS software and network server to model and analyse watersheds. | Regarding the Outcome 2. A 100% of the outcome has been achieved for the first year of implementation. Chile government counts with the software AQUAVEO WMS for the Meteorological Directorate of Chile (DMC) to model and analyse watersheds. | HS
| Outcome 3. Improved climate monitoring and means to alert the local population |  | Outcome 1 | - Study to identify best location for weather radar and design supporting infrastructure and facilities in Antofagasta - Study to identify best location for weather radar and design supporting infrastructure and facilities in Esmeraldas - Purchase of meteorological stations, including installation in Antofagasta and Taltal - Purchase of two meteorological stations and one hydrological station in Esmeraldas |  | Regarding the Outcome 3. Chile works with national entities in the identification of meteorological equipment needed. The pandemic prevented field visits, which are expected to be carried out in 2021. Ecuador is soon to finalize the Climate Monitoring Design for Esmeraldas. It is expected to have it finalized for Febrerury 2021, which has to be validated by the INHAMI. The project works to guarantee a clear local management model and maintenance commitments of the INHAMI and Esmeraldas Prefectura prior to purchasing the equipment.. | MS
| Outcome 4. Improved means to respond to floods, landslides and mudflows |  | Outcome 1 | - Design of an early warning system on Luis Vargas Torres Island - Purchase and installation of equipment for pilot flood early warning system. - Meetings and workshops socialize and train local groups on flooding alert and emergency procedures. - Update mudflows evacuation maps for Antofagasta and Taltal. - Prepare flooding evacuation map and landslide risk evacuation map for Esmeraldas. |  | Regarding the Outcome 4. Ecuador, with the support of the Risk Management Service and the Escuela Politécnica del Litoral - ESPOL, carries out a flood risk analysis on Luis Vargas Torres island that will allow the design of the Early Warning System (EWS). EWS equipment will be installed in 2021. In Chile, with the support of ONEMI, the evacuation maps for the city of Antofagasta have been updated and the maps for the city of Taltal are being updated. | S
| Outcome 5. Local governments with improved capacity to design and implement adaptation measures |  | Outcome 2 | - Two consultants to coordinate and prepare course on risk-based adaptation in coastal cities. - Joint workshop to delineate training contents and structure, and agree working procedures |  | Regarding the Outcome 5. A capacity / knowledge situational diagnosis is carried out at the regional level with local officials of Antofagasta, Taltal, Esmeraldas for the initial preparation of the course on risk-based adaptation in coastal cities. In 2021, progress will be made in the development of content and virtualization of the regional course. | S
| Outcome 6. Local population and government personnel with increased awareness of climate-related risks (floods, landslides, mudflows) |  | Outcome 3 | - Prepare needs assessment and communication and public education strategy for Antofagasta - Prepare needs assessment and communication and public education strategy for Taltal - Prepare needs assessment and communication and public education strategy for Esmeraldas - Joint workshop to share national and international experience and convene work strategy. |  | Regarding the Outcome 6. The communication and education strategies of Antofagasta, Taltal and Esmeraldas are under development. In Chile it is developed by the Social Specialist, which is already hired. In Ecuador, a consultant was hired to develop the education and communication strategy for Esmeraldas, including the Implementation Plan and Monitoring and Evaluation Plan. | S
| Outcome 7. Lessons and best practice on reducing vulnerability to climate related flooding, landslides and mudflows in coastal cities have been shared in the region. |  | Outcome 8 | - Equipment for web-based communication platform. - Web-based communication service - Production videos, images and other communication media for the project´s web platform and news. |  | Regarding the Outcome 7. The project has the hardware and software tools necessary for the team to be permanently communicated, the executing entity has guaranteed a fluid communication of all the actors, through digital means of communication. Three videos of the project have been produced. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Carolina Cortes
| Email: | acortes@caf.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
As the implementing agency, the actions of the project have been followed up through periodic meetings with the ministerial teams of Ecuador and Chile as well as with UNDP Ecuador and Chile and the respective project teams. Likewise, and according to the implementation mechanisms, two meetings were held with the National Technical Committees, where the programming for each semester and the Procurement Plan and the progress to date were shared. The first meetings were face-to-face on February 10th 2020 in Ecuador and on January 22nd, 2020 in Chile. The second meetings were held both virtually, due to the health emergency in Ecuador and Chile that restricted face-to-face meetings that were held on September 15, 2020 in Ecuador and June 30th, 2020 in Chile It is worth mentioning that the project was developed 5 years ago, so it has been required to collect updated information and join new national environmental authorities and different local teams. The implementation of certain activities required new analysis of the best solution and technical feasibility, this is how the acquisition of a storm detection system was changed for the contracting of the service with a company, which will allow to achieve the initially proposed results in a better way . In this period, and despite the presence of the pandemic, the implementation of the project has been satisfactory. The objectives established in the proyect have been successfully met, obtaining the expected results for the first year despite de different problems. The presence of the global pandemic due to COVID-19 changed the mechanisms under which a project is implemented, making many activities virtual throughout the year. Only in the last quarter of the year, there have been face-to-face approaches through workshops and field activities, always following the guidelines established by the national government and under strict biosecurity measures that guarantee the health of the participants. (Estas reuniones cuales fueron ?? )
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 1. Enhanced plans and green infrastructure reduces vulnerability to floods, landslides and mudflows in three coastal cities |  | Outcome 4 | - Prepare and implement a training event on green infrastructure planning in coastal cities. Three-day workshop (ca., 30 people) in Esmeraldas. Participants will be technical staff from GADM and relevant entities - Situation analysis of climate-related risks and options to enhance green infrastructure in the city of Esmeraldas - Engineer company contract to update stormwater management plan for Antofagasta. |  | - Three webinars on green infrastructure were conducted with the support of national and international experts as part of training for local technicians. A virtual course on green infrastructure has been designed, which will be available in early 2021. As a result of the restrictions in Ecuador due to the health emergency by COVID-19, it was not possible to develop the face-to-face green infrastructure training event in the city of Esmeraldas. However, a virtual course was carried out to meet the training objective. - The Green Infrastructure Plan for the city of Esmeraldas is advancing as planned and will be ready in the first quarter of 2021. At the moment, there is a diagnosis that includes a climate-related risk analysis. - To update the Master Plan, internal meetings were held with the project's partner institutions. It is expected that the activities of the consultant will start in the first semester of 2021 | S
| Outcome 2. Reduced vulnerability to floods, landslides and mudflows in two coastal cities |  | Outcome 4 | - Purchase of AQUAVEO WMS software and network server to model and analyse watersheds. |  | - Chile is provided with AQUAVEO WMS software that will allow modeling and analysis studies of watersheds in Chile, with an emphasis on the cities of Antofagasta and Taltal. - Esmeraldas provides technical assistance to the development of Land Use and Management Plan (PUGS) to incorporate the Green Infrastructure Plan through this instrument. In addition, a Partial Plan of the intervention polygon in Cerro Gatazo (PP) advances. These two, PUGS and PP, plans are instruments established in the Land Use Planning Law. The PP aims to order the study area and identify the land tenure situation in the sector, a step prior to the design and construction of planned green (grey) slip control and reforestation infrastructure works. | HS
| Outcome 3. Improved climate monitoring and means to alert the local population |  | Outcome 1 | - Study to identify best location for weather radar and design supporting infrastructure and facilities in Antofagasta - Study to identify best location for weather radar and design supporting infrastructure and facilities in Esmeraldas - Purchase of meteorological stations, including installation in Antofagasta and Taltal - Purchase of two meteorological stations and one hydrological station in Esmeraldas |  | - In relation to the storm detection system for Antofagasta, a technical and financial analysis was carried out with support from the Chilean Meteorological Directorate on the feasibility of acquiring a system as mentioned in the PRODOC. As a result of the analysis, it was determined that it is not feasible to make this purchase because the project budget is much lower than that required for the acquisition. As an alternative to this activity and with the certainty of obtaining the same results, storm detection services are contracted. In addition, as this activity is considered USP, the process of reviewing compliance with the 15 environmental and social principles of the Adaptation Fund has been carried out. - Talks are progressing to determine the locations of the weather stations for Antofagasta and Taltal, with the Directorate General of Waters of the Ministry of Public Works and the Chilean Meteorological Directorate . Technical and financial feasibility for installation is analyzed. Locations will be held by the beginning of 2021. - In Esmeraldas, a diagnosis of climate monitoring was made, as an indispensable pre-step to station or radar acquisitions. As a result of this consultancy, it will be possible to get the best alternative to perform efficient climate monitoring in Esmeraldas, including the equipment to be purchased, the maintenance or relocation of existing ones and their exact location. | S
| Outcome 4. Improved means to respond to floods, landslides and mudflows |  | Outcome 1 | - Design of an early warning system on Luis Vargas Torres Island - Purchase and installation of equipment for pilot flood early warning system. - Meetings and workshops socialize and train local groups on flooding alert and emergency procedures. - Update mudflows evacuation maps for Antofagasta and Taltal. - Prepare flooding evacuation map and landslide risk evacuation map for Esmeraldas. |  | - Advance the design of the ILVT Early Warning System in Esmeraldas; there is a diagnosis of the risk of flooding in the island, the design of the early warning system, flood risk maps and evacuation routes, formation of the community risk management committee and the imparting of workshops to beneficiaries. In 2021 the final design will allow the purchase of SAT equipment. The process has been built in a participatory way with the community and with the support of the National Risk Service and the Municipality of Esmeraldas. - In the case of updating evacuation maps for Antofagasta and Taltal, work has been carried out conjointly with ONEMI, an institution that has already updated the maps for Antofagasta and is in the final stage of drawing up the Taltal maps. The final versions will be socialized again with the beneficiaries at the beginning of next year. | S
| Outcome 5. Local governments with improved capacity to design and implement adaptation measures |  | Outcome 2 | - Two consultants to coordinate and prepare course on risk-based adaptation in coastal cities. - Joint workshop to delineate training contents and structure, and agree working procedures |  | Prior to the completion of the regional course, it was considered necessary to carry out a situational diagnosis of existing capacities, competences, and courses on risk-based adaptation in coastal cities, in local, subnational, and national governments of the Latin American and Caribbean region. This analysis is currently in the completion stage. With the results obtained, a course will be designed to suit the needs of coastal cities in Latin America and the Caribbean. | S
| Outcome 6. Local population and government personnel with increased awareness of climate-related risks (floods, landslides, mudflows) |  | Outcome 3 | - Prepare needs assessment and communication and public education strategy for Antofagasta - Prepare needs assessment and communication and public education strategy for Taltal - Prepare needs assessment and communication and public education strategy for Esmeraldas - Joint workshop to share national and international experience and convene work strategy. |  | The communication and public education strategy for Antofagasta and Taltal is developed by the Social Specialist. It is structured in 4 pillars: territorial tables, public education, women's bureau, narrator initiative. In the case of Esmeraldas, a consultant was hired, who developed the education and communication strategy for Esmeraldas, including the implementation plan and the monitoring and evaluation plan of that strategy. Mobility restrictions due to Covid-19 in Chile and Ecuador prevented face-to-face workshops, instead 3 webinars were made on "Use of green infrastructure and nature-based solutions as climate risk reduction measures", "Policies and economic benefits of green infrastructure in urban environments" and "Green infrastructure at the service of the community". In addition, a virtual workshop was organized with the participation of environmental education professionals from the Ministry of the Environment and professionals from Valdivia, who implemented the initiative of narrators in that city, sharing their experience with the project unit of Chile and Ecuador. | HS
| Outcome 7. Lessons and best practice on reducing vulnerability to climate related flooding, landslides and mudflows in coastal cities have been shared in the region. |  | Outcome 8 | - Equipment for web-based communication platform. - Web-based communication service - Production videos, images and other communication media for the project´s web platform and news. |  | - Project staff have been equipped with the necessary equipment to enable them to maintain efficient communication. - The development of a project communication strategy that defines the project's communication guidelines, including the development of a web platform, is under way. - 3 communication videos of the project were produced. 1. Information about the project in general, its objectives and components in such a way that the population knows the activities to be developed. 2. A video in Ecuador about the Early Warning System of Luis Vargas Torres Island, and 3. A video about the experiences of the flood that occurred in Antofagasta, in order to raise awareness and maintain in the collective memory of the population, the climatic risks existing in the city. | MS
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Nury Bermudez
| Email: | nury.bermudez@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project has been successfully implemented, reaching 80% programmatic execution and 38% financial execution according to the activities and products planned for the first year of implementation. This has been possible, thanks to the sustained work of the entire project team, both in Chile and Ecuador, the ongoing supervision of CAF and UNDP offices in the respective countries and, of course, the accompaniment of the Ministry of the Environment. Other key players in achieving the results are, at the national level, the Secretariat of Risk Management and INAMHI in Ecuador. In Chile, ONEMI and the DMC. At the local level, the commitment of the technicians of the municipalities of Esmeraldas, Antofagasta and Taltal, help the intervention to move forward as planned despite the difficulties caused by the health pandemic of the Covid-19. One of the aspects that requires a greater focus relates to participatory activities with the people of the neighborhoods, which is due to the difficulties of mobilization, restrictions on holding meetings and the low internet connectivity or economic difficulties that the population undergoes to access it. During 2021, the project plans to incorporate communication actions, through information leaflets, flyers, parakeet, and posters that bring us closer to the neighborhoods and areas of direct influence of the project. Among the most relevant milestones are the following: In Esmeraldas – Ecuador the following are in place: Diagnosis and design of climate monitoring for Esmeraldas; the Green Infrastructure Plan for Esmeraldas is under way; the early warning system for ILVT is being developed; the Partial Plan at Cerro Gatazo is being developed; a virtual course on Green Infrastructure and SBN has been designed to enable local coastal government officials to be trained and launched in the first half of 2021. In Chile: Contracting of Storm Detection Services for Antofagasta, acquisition of AQUAVEO WMS software for watershed modeling and analysis studies, the updating of Antofagasta and Taltal evacuation maps is under way. At the regional level: 3 webinars were conducted on solutions based on nature and green infrastructure; advances a diagnosis of capacities on climate change adaptation issues in 10 coastal cities in order to provide a more adequate focus to the Regional Course on CC Adaptation; and the project's communication strategy. The Covid-19 pandemic, which is still present in the countries, involved different priorities for national and local governments, which has made it somewhat difficult to implement joint activities. Nonetheless, the necessary mechanisms have been devised to continue on with the support of all partner institutions in both countries. Finally, it is worth mentioning that PRODOC was developed in 2015-2016, so an initial time period was required to resume contact with new authorities and technicians of government entities for a better understanding of expected scopes and outcomes. In terms of implementation, together with the new governance teams, alternatives are discussed to achieve the objectives set out in the project, in different political, financial, and social contexts.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective | Number of men and women protected by improved risk-reduction measures in Antofagasta, Taltal and Esmeraldas. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | End of project Antofagasta = 380,000 (ca., 50% women) Taltal = 10,000 (ca., 50% women) Esmeraldas = 161,000 (ca., 50% women)
Outcome 1 | Number of plans that incorporate provisions for adaptation to climate change with gender perspective. | Stormwater management plan Antofagasta = 0 Green infrastructure plan Esmeraldas = 0 | Stormwater management plan Antofagasta = 0 Green infrastructure plan Esmeraldas = 20% | 2
Outcome 2 | Number of physical assets constructed to withstand conditions resulting from climate variability and change. | Antofagasta = 0 Esmeraldas = 0 | Antofagasta = 0 Esmeraldas = 0 | 2
Outcome 2 | Number of men and women protected by improved infrastructure to withstand climate change and variability-induced stress. | Antofagasta = 0 Esmeraldas = 0 | Antofagasta = 0 Esmeraldas = 0 | 12,840 Antofagasta = (ca., 50% women) Esmeraldas = 500 (ca., 50% women)
Outcome 3 | Number of weather radar in Esmeraldas and Storm detection system in Antofagasta to monitor precipitation, linked to gender-sensitive early warning systems. | Antofagasta = 0 Esmeraldas = 0 | Antofagasta = 0 Esmeraldas = 0 | Antofagasta = 1 Esmeraldas = 1
Outcome 3 | Number of meteorological stations to monitor precipitation which affect the cities, linked to gender-sensitive early warning systems. | Antofagasta = 4 Taltal = 1 Esmeraldas = 5 | Antofagasta = 4 Taltal = 1 Esmeraldas = 5 | Antofagasta = 6 Taltal = 2 Esmeraldas = 7
Outcome 4 | Number of men and women covered by alert and evacuation route signs to respond to floods (Esmeraldas), landslides (Esmeraldas) and mudflows (Antofagasta and Taltal) | Number of people Antofagasta = 0 Taltal = 0 Esmeraldas (floods) = 0 Esmeraldas (landslides) = 0 | Number of people Antofagasta = 0 Taltal = 0 Esmeraldas (floods) = 0 Esmeraldas (landslides) = 0 | Antofagasta = 380,000 people (ca., 50% women) Taltal = 10,000 people (ca., 50% women) Esmeraldas (floods) = 161,000 people (ca., 50% women) Esmeraldas (landslides) = 161,000 people (ca., 50% women)
Outcome 4 | The early warning systems in Antofagasta, Taltal, Cerro Gatazo and Isla Luis Vargas Torres are gender and culturally sensitive and consider the special needs of persons with disabilities. | Number of early warning systems Antofagasta = 0 Taltal = 0 Cerro Gatazo = 0 Isla Luis Vargas Torres = 0 | Number of early warning systems Antofagasta = 0 Taltal = 0 Cerro Gatazo = 0 Isla Luis Vargas Torres = 0 | Four early warning systems are gender and culturally sensitive and consider the special needs of persons with disabilities.
Outcome 5 | Number of staff (men and women) of local governments and pertinent entities trained on risk-based adaptation with a gender perspective in coastal cities. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 Other coastal cities Chile = 0 Other coastal cities Ecuador = 0 | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 Other coastal cities Chile = 0 Other coastal cities Ecuador = 0 | Antofagasta = >50 Taltal = >10 Esmeraldas = >20 Other coastal cities Chile = >10 Other coastal cities Ecuador = >10 About 40% will be women
Outcome 6 | Number of men and women who have participated in awareness activities and events. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = 0 Taltal = 0 Esmeraldas = 359 (41% women) | Antofagasta = >30,000 (ca., 50% women) Taltal = >1,000 (ca., 50% women) Esmeraldas = >16,000 (ca., 50% women)
Outcome 6 | Number of narrators (men and women) trained to maintain cultural memory of climate-related disaster and risks. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = 10 (ca., 50% women) Taltal = 5 (ca., 50% women) Esmeraldas = 10 (ca., 50% women)
Outcome 7 | Number of men and women (by nationality) who have participated in events for dissemination of lessons and best practice (e.g., workshops, exchange visits, seminars) | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | >200 people > 40% women
Outcome 7 | Number of visitors per month (annual average) recorded in the network of electronic channels of the regional on-line platform used to disseminate project´ learnings and best practice | Visits 0 Unique visits 0 | Visits 0 Unique visits 0 | Visits >4000 Unique visits >3200

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | During the first semester, meetings were held with the different project´s partner institutions in both countries and several processes were initiated as planned. However, due to the arrival of COVID-19 (March, 2020) national governments enforced strong restrictive measures, causing delays in some processes, mainly in field activities with final beneficiaries.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The arrival of Covid-19 in both country cause some delays in the workshops and participatory meetings to face this situation, workshops and events have been carried out virtually as far as possible. In Chile, after several months of analysis related with the Storm Detection System, the government decided to hire a consultant instead of buying the radar and implement directly. There are more benefits to used this modality, especially related with the ESMP. The estimated budget for this activity is the same as that considered in the project design This change in the strategy cause a delay in the implementation. The process to hire the Storm Detection System is just about to be completed. In Ecuador, the Climate Monitoring System was a first step to complet before acquired the radar and the meteo stations.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | Output 4.2, Act. 19. An early warning system for the island Luis Vargas Torres in Esmeraldas, was the first step to do it, before implementing any megaphones or syrens installation. In this first year the project is working on this EWS and based on the analysis the implementation will take place. Output 1.2 Act. 2 As part of the Green Infrastructure Plan a training event of three-day workshop was developed, due to the pandemic. The project implemented three webinar and produced a online course related to green infrastructure. The materials will allow the project to expand the benefits in a more wide number of public officials.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes. The project implement effective measures to avoid unwanted negative environmental and social impacts. Such as: 1. A communication and participatory strategy is now in place and will be presented to the Project Board. 2. The Green Infrastructure Plan has a biologist in the team to choose the best vegetal species for the reforestation process. 3. A grievance mechanism is now in place and the communities and beneficiaries has been informed about the process to follow.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Yes, gender considerations has been put in place, such as: 1. Participatory and inclusive approach in all the workshops, events and trainings has been incorporate incorporate in the project execution. 2. The project team is gender balance 3. The public communication strategy to empower and engage local communities is now under design.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A at this stage
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A at this stage
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A at this stage
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A at this stage
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | This is the first year of this project, the implementation is preparing all the studies and conditions to implement the adaptation measures. Lessons learned about the concrete adaptation interventions will be possibe to share in next year.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | It is quite premature to answer this question, because this is the first year of this project under particular circumstances (Covid-19 presence).
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Communities are visible thanks to the project and they have a lot of expectation about this process. Even though this first year, was really complicated to implement the community participatory workshosp due to the Covid-19 pandemic and the restriction and social distance imposse by the governments.
What measures are/have been put in place to ensure sustainability of the project/program results? | Close coordination with national and local level, with an important involvement in all the project´ decisions, through a National Technical Board and also bilateral meetings.
What measures are being/could have been put in place to improve project/program results? | Incorporate the Local Social Especialist in Ecuador need to be done for this second year. This first year and due to the pandemic and the restrictions the process fell twice in Ecuador.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Official climate information were used for the Climate Monitoring Analysis for Esmeraldas. Previous studies related to the geology and geomorphology of the Cerro Gatazo Area were compiled also. Local Development and Land Used Planned (PDOT by its acronym in Spanish) and all the cartography need in Ecuador and Chile were used and incorporated as information for the different consultants. Also some information through community workshops related with the knowledge of its territory related with flooding for the Island Luis Vargas Torres were compiled.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Relevant stakeholders are involved during all the implementation. The project share with them each consultant product. The final results of the consultants will be share through the project webpage (now under design)
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | • Virtual course on green infrastructure for coastal cities • Partial Land Use Plan for a specific area located in Cerro Gatazo- Esmeraldas • Technical Report: Conceptualization of the Early Warning System against floods for the LVT Island in Esmeraldas • Study: Diagnosis and proposal for improving climate monitoring in Esmeraldas • Updating of evacuation maps for Antofagasta and Taltal • Handbook with the project communication strategy • Video de socialización de las actividades a realizarse en el proyecto • Videos vivenciales sobre inundaciones en Esmeraldas y flujos de lodo en Antofagasta
If learning objectives have been established, have they been met? Please describe. | The project has as an initial activity a training course related with green infrastructure, due to the pandemic, the project transform into a online course. The process to built the materials and lessons will finish in december and the first group following the learning process would start in December and January.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Big difficulties related to the status of land tenure in Esmeraldas. There is a relevant information for the project, especially to declare part of Cerro Gatazo as protective natural area and start the green and gray infraestructure and also de revegetation. The project scale up the need of this relevant info to the Esmeraldas Major and some mitigation measures are now in place.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes, all the learning objectives of the project will contribute to the Outcome of the project and allow to scale-up the thematics in the region, thanks to the Component 3 Outcome 7. Lessons and best practice on reducing vulnerability to climate related flooding, landslides and mudflows in coastal cities have been shared in the region.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | The satelite storm detection system for Antofagasta is a new way to monitore the weather and seems to is the near future in detections.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization. | N/A
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | Development Bank of Latin America (CAF)
Type of implementing entity | RIE
Country | Ecuador
Region | Latin America and Caribbean
Sector | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 551000 | 47000 | 504000 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Coastal flooding | 2: Partially effective | Total | 47000 | Coastal flooding | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 3 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 3 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Disaster risk reduction | 2: Low capacity | Total | 100 | Disaster risk reduction | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 40% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 100 | 40% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Disaster risk reduction |  | 50 |  | Disaster risk reduction
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 50% | 2: Partially not aware |  | 551000 | 50% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Disaster risk reduction | Local | 2: Partially responsive (Lacks most elements) |  | Disaster risk reduction | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
Note on J21: Juan Monteros: Revisar cifra. Corresponde al número de personas que han participado en eventos de concienciación. CONFIRMAR