## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | July 2019 to June 2020
| Project Title: | Adapting to Climate Change in Lake Victoria Basin (ACC-LVB Project)
| Project Summary: | Climate change in the Lake Victoria Basin (LVB) – a water catchment in Burundi, Kenya, Rwanda, Tanzania and Uganda – has resulted in increased mean annual temperatures and increased variability in rainfall patterns. Climate change projections predict that mean annual temperatures will continue to increase and that variability in rainfall patterns will be exacerbated. Projected climate change will result in several negative effects within the LVB, including a decrease in water quality and availability for a number of uses, including inter alia: i) domestic; ii) agricultural; iii) industrial and commercial; and iv) cultural. The negative effects of climate change disproportionately affect marginalised and rural communities within the LVB by reducing the productivity of agriculture and wetlands and the abundance of fish in Lake Victoria and its tributaries. In addition, the projected effects of climate change are likely to negatively impact economic sectors within the LVB that depend on water resources, such as hydropower facilities and commercial fisheries. Therefore, to reduce the impact of climate change on local communities and water dependent economic sectors within the LVB, the Project will increase climate resilience in the LVB at both a regional and local level by implementing both regional and community-based climate change adaptation interventions. The Project objective will be achieved through five outcomes, namely: i) strengthened institutional and technical capacity to integrate climate resilience into transboundary water catchment management; ii) improved delivery of accurate and timely climate information to regional and national policy makers, technical officers and local communities; iii) climate change adaptation technologies, including water harvesting techniques, climate-smart agriculture and Ecosystem based Adaptation (EbA), transferred to communities to reduce their vulnerability to climate change; iv) regional resilience to climate change promoted through innovative, community based projects; and v) improved knowledge management frameworks for the collection and maintenance of regional knowledge in transboundary water catchment management and climate change adaptation practices.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | UNEP:S1-32AFB-00009 / SB-008892 AF ID: AFR/MIE/Water/2015/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Environment Programme (UNEP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity (MIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Burundi, Kenya, Rwanda, Tanzania and Uganda | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The LVB is contained within the southern section of the Nile River Basin (NRB), between the Eastern and Western Rift Valleys. The LVB catchment area is ~195,000 km2 and contains Lake Victoria, the world’s second largest freshwater lake, which has a surface area of ~69,000 km2, a mean depth of ~40 m and contains ~2,750 km3 of water . Lake Victoria extends into three countries, namely Kenya, Tanzania and Uganda, while the LVB extends further to include Burundi and Rwanda. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2017-07-05
IE-AFB Agreement Signature Date: |  | 2017-10-01 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2018-06-28 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
| Original Completion Date: | June, 2021
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception report - 11th September, 2019 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://www.unenvironment.org/explore-topics/climate-change/what-we-do/climate-adaptation/ecosystem-based-adaptation/ecosystem-7 | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Dr. Masinde K.Bwire | Dominican Republic
| Email: | bwirejoseph@gmail.com; Bwire@lvbcom.org | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: |  | Equatoral Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | United Nations Environment Programme (UNEP) | Fiji
| Email: | essey.daniel@un.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Lake Victoria Basin Commission | Georgia
| Email: | matano@lvbcom.org | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Dr. Masinde K.Bwire | Grenada
| Email: | bwirejoseph@gmail.com; Bwire@lvbcom.org | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [30th June 2019] |  |  |  | Financial information PPR 2: cumulative from project start to [30th June 2020] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [30th June 2020] | 674201 |  |  | Estimated cumulative total disbursement as of [30th June 2020] | 1138308 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 29983 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List outputs and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List outputs and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
OUTPUTS | ITEM / ACTIVITY / ACTION | AMOUNT |  | OUTPUTS | ITEM / ACTIVITY / ACTION | AMOUNT
Output 1.1: Strengthened institutional coordination mechanism to sustain a climate resilient approach to transboundary water catchment management. | Regional Platform - CCTWG meeting, communication | 4900 |  | Output 1.1: Strengthened institutional coordination mechanism to sustain a climate resilient approach to transboundary water catchment management. | Regional Platform - CCTWG meeting, communication | 0
Output 1.2. Training provided to government ministries and agencies, civil society and the private sector to address climate change related challenges in transboundary water catchment management | International Consultant (Water Catchment Management and Adaptation Expert) | 19450 |  | Output 1.2. Training provided to government ministries and agencies, civil society and the private sector to address climate change related challenges in transboundary water catchment management | International Consultant (Water Catchment Management and Adaptation Expert) | 0
| Regional Training Workshops | 0 |  |  | Regional Training Workshops | 28155
| National Training workshops | 69137 |  |  | National Training workshops | 0
Output 2.1. Tailored climate information packages to guide both operational and long term strategic planning. | Regional/National Training Workshops | 68097 |  | Output 2.1. Tailored climate information packages to guide both operational and long term strategic planning. | Regional/National Training Workshops | 2450
| Downscaling software | 0 |  |  | Downscaling software | 0
Output 2.2. Climate information dissemination mechanism strengthened to deliver climate information to national policymakers, LVBC technical officers and local communities. | Regional workshops, Materials & goods, Travel, Communication costs & Community information sharing | 0 |  | Output 2.2. Climate information dissemination mechanism strengthened to deliver climate information to national policymakers, LVBC technical officers and local communities. | Regional workshops, Materials & goods, Travel, Communication costs & Community information sharing | 73426
Output 3.1. Project intervention sites and appropriate adaptation technologies identified. | Identification of demonstration sites for adaptation technologies | 20000 |  | Output 3.1. Project intervention sites and appropriate adaptation technologies identified. | Identification of demonstration sites for adaptation technologies | 11486
| Stocktaking exercise | 20000 |  |  | Stocktaking exercise | 45870
Output 3.2. Extension officers and local communities trained on climate change adaptation technologies including water conservation practices, climate-smart agricultural techniques and EbA activities. | National community training workshops - including facilitation of training, travel, communication, traning materials | 0 |  | Output 3.2. Extension officers and local communities trained on climate change adaptation technologies including water conservation practices, climate-smart agricultural techniques and EbA activities. | National community training workshops - including facilitation of training, travel, communication, traning materials | 0
| Establishment of adaptation technologies demonstration sites | 47114 |  |  | Establishment of adaptation technologies demonstration sites | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
| Exchange visits | 0 |  |  | Exchange visits | 0
Output 3.3. Climate change adaptation technologies demonstrated at selected project intervention sites. | Climate change adaptation technologies – Burundi, Kenya, Tanzania, Rwanda & Uganda | 312400 |  | Output 3.3. Climate change adaptation technologies demonstrated at selected project intervention sites. | Climate change adaptation technologies – Burundi, Kenya, Tanzania, Rwanda & Uganda | 235041 |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
Output 4.1. Small-scale projects funded to promote innovative approaches to climate change adaptation. | Community Workshops & Training | 0 |  | Output 4.1. Small-scale projects funded to promote innovative approaches to climate change adaptation. | Community Workshops & Training | 0 |  | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| small grants to small scale community-based adaptation subprojects - Burundi, Kenya, Tanzania, Rwanda and Uganda | 0 |  |  | small grants to small scale community-based adaptation subprojects - Burundi, Kenya, Tanzania, Rwanda and Uganda | 0
| M&E of small scale community-based adaptation subprojects | 0 |  |  | M&E of small scale community-based adaptation subprojects | 0
Output 5.1. A forum established to promote the collaboration of research initiatives across the Lake Victoria Basin, with a focus on adaptation to climate change. | Regional Research Forum/workshop and communication materials | 25591 |  | Output 5.1. A forum established to promote the collaboration of research initiatives across the Lake Victoria Basin, with a focus on adaptation to climate change. | Regional Research Forum/workshop and communication materials | 0
Output 5.2. Awareness-raising campaign to share lessons learned with stakeholders, ranging from policy and decision makers to vulnerable communities in the Lake Victoria Basin. | Communication Materials | 4512.43 |  | Output 5.2. Awareness-raising campaign to share lessons learned with stakeholders, ranging from policy and decision makers to vulnerable communities in the Lake Victoria Basin. | Communication Materials | 12552
| awareness raising campaigns | 0 |  |  | awareness raising campaigns | 0
| Exhibitions | 0 |  |  | Exhibitions | 0
6. Project/Programme Execution cost (9.5%) | Office Supplies | 1730 |  | 6. Project/Programme Execution cost (9.5%) | Office Supplies | 3406
| Project steering committee meetings | 63217.22 |  |  | Project steering committee meetings | -10911
| Personnel | 4000 |  |  | Personnel | 66700
| Consultants Recruitment | 6825 |  |  | Consultants Recruitment | 5030.91
| Audit | 0 |  |  | Audit | 0
| Telephone Printing and Internet | 7227.29 |  |  | Telephone Printing and Internet | 2234.02
| TOTAL | 674200.94 |  |  | TOTAL | 475439.93
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
Output 1.1: Strengthened institutional coordination mechanism to sustain a climate resilient approach to transboundary water catchment management. | 1.1.1. Strengthen – building on the stakeholder engagement strategy prepared by the CCTWG – and sustain the flow of information between the following: i) projects and organisations collecting climate data within the LVB; ii) regional climate information platforms; iii) experts and technical staff responsible for water catchment management and climate change adaptation; and iv) regional policy and decision makers. | 0 |  | Output 1.1: Strengthened institutional coordination mechanism to sustain a climate resilient approach to transboundary water catchment management. | 1.1.1. Strengthen – building on the stakeholder engagement strategy prepared by the CCTWG – and sustain the flow of information between the following: i) projects and organisations collecting climate data within the LVB; ii) regional climate information platforms; iii) experts and technical staff responsible for water catchment management and climate change adaptation; and iv) regional policy and decision makers. | 20000 | By April 2021
| 1.1.2. Support one meeting of the CCTWG to plan and implement climate-resilient approaches to transboundary water catchment management. | 80000 | By Feb 2020 |  | 1.1.2. Support one meeting of the CCTWG to plan and implement climate-resilient approaches to transboundary water catchment management. | 40000 | By April 2021
| 1.1.3. To undertake one regional capacity building training in water catchment management in the context of climate change in organisations such as inter alia: i) LVBC; ii) CCTWG; iii) LVBC project Unit; and iv) ICPAC, FEWSNET, RCMRD and DHI | 10000 | By Janaury 2020 |  | 1.1.3. To undertake one regional capacity building training in water catchment management in the context of climate change in organisations such as inter alia: i) LVBC; ii) CCTWG; iii) LVBC project Unit; and iv) ICPAC, FEWSNET, RCMRD and DHI | 25000 | By May 2021
Output 1.2. Training provided to government ministries and agencies, civil society and the private sector to address climate change related challenges in transboundary water catchment management | 1.2.1. Develop/revise training material on climate change adaptation and transboundary water catchment management. | 0 |  | Output 1.2. Training provided to government ministries and agencies, civil society and the private sector to address climate change related challenges in transboundary water catchment management | 1.2.1. Develop/revise training material on climate change adaptation and transboundary water catchment management | - | By June 2021
| 1.2.2. Provide training on climate change, climate change adaptation and water management at the regional level to national government representatives from the climate change, environment, and water and local government sectors in each of the five Partner States. | 45000 | By January 2020 |  | 1.2.2. Provide training on climate change, climate change adaptation and water management at the regional level to national government representatives from the climate change, environment, and water and local government sectors in each of the five Partner States.
| 1.2.3. Provide training on climate change, climate change adaptation and water management at national workshops which will include 50 civil society, non-governmental organisation (NGOs) and the private sector. | 45000 | By January 2020 |  | 1.2.3. Provide training on climate change, climate change adaptation and water management at national workshops which will include 50 civil society, non-governmental organisation (NGOs) and the private sector. | 80000 | By April 2021
Output 2.1. Tailored climate information packages to guide both operational and long term strategic planning | 2.1.1. To train 25 representatives from the national meteorological agencies in each of the five Partner States on downscaling regional climate information on the national level. | 60000 | By September 2019 | Output 2.1. Tailored climate information packages to guide both operational and long term strategic planning | 2.1.1. To train 25 representatives from the national meteorological agencies in each of the five Partner States on downscaling regional climate information on the national level. | 62000 | By June 2021
| 2.1.2. To develop 10 national tailored climate information packages for: i) policy and decision-makers; and ii) local communities. | 20000 | By September 2019 |  | 2.1.2. To develop 10 national tailored climate information packages for: i) policy and decision-makers; and ii) local communities. | - | By June 2021
2.2. Climate information dissemination mechanism strengthened to deliver climate information to national policymakers, LVBC technical officers and local communities. | 2.2.1. Identify cost-effective means of strengthening existing climate information dissemination mechanisms, including ICPAC, FEWSNET, RCMRD and DHI. | 20000 | By September 2019 | Output 3.3. Climate change adaptation technologies demonstrated at selected project intervention sites | 3.3.1 to 3.3.5. Implement climate change adaptation technologies including water conservation practices, climate-smart agricultural techniques and EbA at the selected intervention sites in Burundi, Kenya, Rwanda, Tanzania and Uganda. | 427000 | By June 2021
| 2.2.2. Strengthen existing climate information dissemination mechanisms – including the LVBC information hub – to develop an LVB specific platform for climate information. | 20000 | By February 2020 | Output 4.1. Small scale projects funded to promote innovative approaches to climate change adaptation. | 4.1.2. To provide training to 1000 local communities or relevant local-level government sectors or NGOs on how to develop a project proposal and the necessary financial, administrative and monitoring procedures for a small-scale project. | 20000 | By February 2021
| 2.2.3. Deliver climate information for long term strategic planning to policy and decision makers in regional organisations as well as technical staff in national ministries within the LVB | 10000 | By February 2020 |  | 4.1.3. Review project proposals and select successful project proponents. | 30000 | By April 2021
| 2.2.4. Pilot innovative information-sharing mechanisms – such as the provision of climate information through mobile networks – to deliver climate information to communities in a locally relevant and accessible format. | 40000 | By March 2020 |  | 4.1.4 to 4.1.8 Provide small grants to project proponents to implement small-scale, community-based adaptation projects in Burundi, Kenya, Rwanda, Tanzania and Uganda. | 101250 | By June 2021
3.1. Project intervention sites and appropriate adaptation technologies identified. | 3.1.1. Apply findings/lessons learned from past and current LVBC programmes (LVWATSAN, LVEMP II, PREPARED Vulnerability Assessment) to identify potential project intervention sites. | 10000 | By December 2019 |  | 4.1.9. Undertake monitoring and evaluation of small scale projects to provide information for Outcome 5. | 15000 | By June 2021
| 3.1.2. Conduct a stocktake of adaptation interventions detailed in existing national strategies and action plans, recommendations from other regional projects and findings of scientific research in the LVB to identify appropriate adaptation technologies to be implemented regionally. | 15000 | By March 2020 | Output 5.2. Awareness raising campaign to share lessons learned with stakeholders, ranging from policy- and decision-makers to vulnerable communities in the Lake Victoria Basin. | 5.2.1. To develop a detailed communication plan for ACC-LVB project building on the communication and outreach strategy prepared by the CCTWG to share lessons learned from the proposed project with relevant national and regional stakeholders through appropriate media. | 5000 | By April 2021
3.2. Extension officers and local communities trained on climate change adaptation technologies including water conservation practices, climate-smart agricultural techniques and EbA activities. | 3.2.1. Train extension officers and local community members at selected intervention sites on climate change adaptation technologies including water conservation practices, climate-smart agricultural techniques and EbA activities. | 40000 | By January 2020 |  | 5.2.2. To produce awareness raising materials on water management and climate change adaptation. | 5000 | By June 2021
| 3.2.2. Establish demonstration sites for climate change adaptation technologies at selected intervention sites. | 10000 | By December 2019 |  | 5.2.3. To undertake awareness raising campaigns for vulnerable communities to share lessons on water management and climate change adaptation. | 8000 | By June 2021
| 3.2.3. Organise information exchange visits where people from communities surrounding the project intervention sites are exposed to the climate change adaptation technologies. | 25000 | By February 2020 |  | 5.2.4.To distribute awareness raising materials translated into local languages where proper – to policy- and decision-makers in national ministries and regional organisations to raise awareness on transboundary water management in the context of climate change and lessons learned from adaptation interventions demonstrated through Component 3 and 4. | 5000 | By June 2021
Output 3.3. Climate change adaptation technologies demonstrated at selected project intervention sites | 3.3.1 to 3.3.5. Implement climate change adaptation technologies including water conservation practices, climate-smart agricultural techniques and EbA at the selected intervention sites in Burundi, Kenya, Rwanda, Tanzania and Uganda. | 500000 | By March 2020 |  | 5.2.5 Host exhibitions to showcase the successful regional and community-based approaches to climate change adaptation demonstrated through Component 3 and 4. | 15000 | By June 2021
Output 4.1. Small scale projects funded to promote innovative approaches to climate change adaptation. | 4.1.1. Host workshops with communities at intervention sites selected in Component 3 to identify specific climate change impacts and appropriate community-based adaptation interventions. | 5000 | By December 2019 | Project Operational costs at regional level (include paying salaries) | Project Operational costs at regional level (include paying salaries) | 141400 | By June 2021
| 4.1.2. To provide training to 1000 local communities or relevant local-level government sectors or NGOs on how to develop a project proposal and the necessary financial, administrative and monitoring procedures for a small-scale project. | 10000 | By January 2020 |  | Total | 999650
| 4.1.3. Review project proposals and select successful project proponents. | 5000 | By February 2020
| 4.1.4 to 4.1.8 Provide small grants to project proponents to implement small-scale, community-based adaptation projects in Burundi, Kenya, Rwanda, Tanzania and Uganda. | 500000 | By March 2020
| 4.1.9. Undertake monitoring and evaluation of small scale projects to provide information for Outcome 5. | 35000 | By December 2019
5.1. A forum established to promote the collaboration of research initiatives across the Lake Victoria Basin, with a focus on adaptation to climate change. | 5.1.1. Hold regional workshops with researchers and technical experts to plan interdisciplinary research projects on climate change adaptation and water catchment management. | 10000 | By April 2020
| 5.1.2. Establish a forum of researchers and technical experts working on climate change adaptation to coordinate climate change research initiatives across the LVB. | 0
| 5.1.3. Promote knowledge sharing through the Global Adaptation Network (GAN), Africa Adaptation Knowledge Network (AAKnet) and Africa Adaptation Initiative. | 15000 | By March 2020
Output 5.2. Awareness raising campaign to share lessons learned with stakeholders, ranging from policy- and decision-makers to vulnerable communities in the Lake Victoria Basin. | 5.2.1. To develop a detailed communication plan for ACC-LVB project building on the communication and outreach strategy prepared by the CCTWG to share lessons learned from the proposed project with relevant national and regional stakeholders through appropriate media. | 20000 | By February 2020 | [5 empty] | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
| 5.2.2. To produce awareness raising materials on water management and climate change adaptation. | 0
| 5.2.3. To undertake awareness raising campaigns for vulnerable communities to share lessons on water management and climate change adaptation. | 17000 | By February 2020 |  |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
| 5.2.4.To distribute awareness raising materials translated into local languages where proper – to policy- and decision-makers in national ministries and regional organisations to raise awareness on transboundary water management in the context of climate change and lessons learned from adaptation interventions demonstrated through Component 3 and 4. | 16000 | By April 2020 |  |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
| 5.2.5 Host exhibitions to showcase the successful regional and community-based approaches to climate change adaptation demonstrated through Component 3 and 4. | 0
Project Operational costs at regional level (include paying salaries) | Project Operational costs at regional level (include paying salaries) | 200000 | By June 2020 |  |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
| TOTAL | 1783000
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
High turnover of staff members in implementing agencies and within different countries may negatively impact on project deliverables. | Low | The Lake Victoria Basin Commission (executing entity of the project) has established strong partnership with government institutions of partner states (Burundi, Kenya, Rwanda, Tanzania and Uganda) with the aim of utilizing the capacities of relevant institutions to support implementation of project activities. This is expected to ensure continuity of the project beyond individual staff and therefore cushion the project against high staff turnover. Among the key government institutions that the project has built partnership with include: National Focal Point ministries responsible for climate change, environment and water resources management; National meteorology directorates; as well as relevant regional institutions dealing with climate including IGAD Climate Prediction and Application Centre (ICPAC), Famine Early Warning Systems Network (FEWSNET) and Regional Centre for Mapping of Resources for Development (RCMRD).
Disagreement amongst stakeholders with regards to demonstration of site selection. | Low | Through a consultative process, selection of intervention sites has been done using an agreed upon list of criteria to ensure that the selection process was transparent and equitable. The selection process was conducted through a thorough participatory approach, with multiple meetings being held between national project coordination teams of each partner state, local authorities in the intervention areas and local communities. This approach helped to alleviate disagreement amongst stakeholders with regard to selection of intervention sites.
Loss of government support may result in lack of prioritisation of Project activities. | Low | LVBC is actively engaging senior government officials that are members of the Regional Policy Steering Committee-RPSC (Permanent Secretaries of responsible ministries) in providing strategic guidance of the project and promoting political buy-in for the project. As a show of commitment, all partner states have now signed MoUs with LVBC that guide the implementation of project interventions in the respective countries. Additionally, project national coordinators have been appointed by their respective focal ministries in each of the partner states thus ensuring that partner states aspirations and priority agenda are well captured during project planning and execution of activities.
Institutional capacities and relationships are not sufficient to provide effective solutions to climate problems that are complex and multi-sectoral. | Low | Capacity development of institutions and communities on transboundary water catchment management and climate change adaptation continues to be an integral part of the project. Training sessions have been facilitated (e.g. the regional training on downscaling of climate information that was conducted in October 2019) as well as local community training sessions in project sites is expected to contribute in putting in place appropriate institutional frameworks to effectively provide solutions to complex and multi-sectoral climate related problems. Additionally, the project is working with experts from specialized national and regional institutions that have adequate capacity to support implementation of project activities e.g. national meteorology directorates; focal ministries responsible for climate change, environment and water resources management; IGAD Climate Prediction and Application Centre (ICPAC); Famine Early Warning Systems Network (FEWSNET); and Regional Centre for Mapping of sources for Development (RCMRD) among others.
Capacity constraints of local institutions may limit the ability to undertake the research and interventions. | Low | To address capacity constraints of local institutions, a research and technical forum plans to be established to support collaboration, knowledge and information exchange between local and international research institutes. This will ensure that capacity constraints of local institutions that limit the ability to undertake research and implementation of interventions are addressed. Furthermore, a Chief Technical Advisor, Administration Finance, Project Manager and consultants have been hired to support timely delivery of project outputs.
Priority interventions implemented are not found to be cost-effective. | Low | The selection process of priority adaptation measures to be implemented has been done with cost-effectiveness being one of the core principles guiding the process. Measures have also been put in place to ensure that detailed information regarding cost-effectiveness of implemented adaptation measures is documented, widely disseminated and used to inform future adaptation initiatives in the Lake Victoria Basin. Moreover, adaptation interventions to be implemented have been designed to ensure steady flow of water of good quality at reasonable cost, thus encouraging payment by consumers.
Lack of commitment/buy-in from local communities may result in failure of intervention sites | Low | Consultation with community and local leadership/authority on selection and prioritization of adaptation technologies in selected project sites has greatly contributed in ensuring ownership and buy-in from local communities. Community consultation through a bottom-up approach during ACC-LVB implementation phases has ensured that local community transboundary water catchment management and climate change adaptation aspirations and needs are addressed by the project.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Novel Corona virus (COVID-19) pandemic that has resulted to national and partial lockdowns, travel restrictions and cancellation of meetings across countries including partner states in LVB. This has negatively affected implementation of project activities. | High | The project is adopting adaptive management e.g. use of virtual meetings to ensure progress in project implementation is achieved albeit in a scaled down manner. Deliberations are also ongoing to assess the possibilities of holding online training sessions. Postponement and rescheduling of activities that require traveling has also been done. For studies e.g. stock take exercise of adaptation technologies use of desktop review of existing literature and online consultations was used for gathering data in Uganda and Kenya where field visits were affected by COVID-19 pandemic.
Seasonal variability such as the recent high and intense precipitation in the East African region since August 2019 has resulted to a rapid rise in the Lake Victoria’s water levels by 13.4metres, mark last recorded in 1964. Similarly, the rains have caused the waters of major rivers draining into Lake Victoria to reach peak levels thus breaking the banks and causing major flooding in the region. This has had devastating impacts which include displacement of a large number of people, destruction of the properties, infrastructure, agricultural lands, crops, and in extreme cases resulted in fatalities of humans and livestock. As a result, the livelihoods and resilience of the local communities and the regional, national and subnational economies in LVB has negatively been affected. This has resulted to a push by key stakeholders/authorities for the project to help respond to the extreme weather event that are mainly occurring outside the selected project sites thus exposing the project to a risk of scope creep. | Medium | Lake Victoria Basin Commission (Executing Entity) is working very closely with East Africa Partner States in the LVB to ensure that the project continue to be implemented in line with its objective and scope as agreed upon in the project document. Additionally, LVBC is fundraising resources from various sources in order to contribute to the current emergency caused by rising water levels of Lake Victoria and the flooding of major rivers.
Disagreement in recruitment processes between partner countries and executing agency leading to delays in hiring of project staff/consultants which negatively affects overall project implementation | Low | Lake Victoria Basin Commission (Executing Entity) has already finalized the recruitment of project team (Project Manager, Finance Assistant and Chief Technical Advisor). Similarly, the recruitment of international consultants to support implementation of various project activities is going on well without interference from partner states.
Lengthy administrative process of formalizing partnership (development and signing of Memorandum of Understanding) between Lake Victoria basin Commission (Executing Entity) and Focal Ministries responsible for spearheading the implementation of project activities in respective partner states. | Low | To fast-track the administrative process of putting in place Memorandum of Understanding between Lake Victoria Basin Commission and institutions responsible for the spearheading implementation of project activities in each partner state, consultative meetings were held that also tasked the national project coordinators to follow up with authorities responsible for approving and signing the MoUs in their respective countries. This contributed immensely to hasten the process of having all partner states sign the MoUs.
Disagreement among stakeholders with regard to roles in the Project. | Low | Stakeholder roles which are detailed clearly in the stakeholder involvement plan were discussed and agreed upon during the project's inception workshop that was held 28th June 2018. This has ensured that there is clarity on the roles and responsibilities of key stakeholders such as Lake Victoria Basin Commission (LVBC), United Nations Environment Programme (UNEP), National Executing Entities etc. Furthermore, a virtual meeting between LVBC and UN Environment was held on 7th April 2020 to discuss and clarify emerging issues related to the roles of executing entity and implementing entity during implementation of the project.
Current climate and seasonal variability and/or hazard events result in poor results for the EbA and conservation agriculture activities. | Medium | The project engaged ICPAC to facilitate a training downscaling regional climate information to the national, sub nation and local levels targeting national experts in the partner states of LVB. Furthermore, LVBC will continue to engage ICPAC to support in downscaling regional climate information to the national and local level to ensure availability of accurately and timely climate data and information. This will ensure that current climate and seasonal variability and/or hazards events are taken into account during planning of the Ecosystem-based Adaptation (EbA) and conservation agriculture interventions. Additionally, the project is also recruiting an Adaptation Expert technical guidance on adaptation activities such as: introduction of drought- and flood-resilient species; crop diversification; conservation agriculture; ecosystem-based adaptation among others.
Trees planted by the project are cut down by the communities. | Low | Community training and awareness raising sessions are being undertaken to sensitize local communities on the importance of sustainable management of tree resources. Additionally, formation of local structures manage forest resources including planted trees is being promoted.
Some infrastructure put in place by the project, for instance communal dams as water harvest strategy, could lead to conflicts associated with different user access. | Low | To minimize instances of conflict, extensive consultations with community members is a core element during selection of adaptation technologies to be implemented with support of ACC-LVB project in every community. This helps to build consensus and ownership to the project activities. Additionally, establishment and training of community management structures (such as village water committees, micro-irrigation system committee, modern fish drying kiln committee etc.) in management and conflict resolutions is an integral part of the project. This will mitigate the risk of conflicts associated with competition for constructed infrastructural developments e.g. communal dams.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Overall the project risk rating is Low. Risk mitigation measures continued to be employed to address existing and emerging risks affecting the project. As a result some of the risks that had a rating of high and medium in the previous reporting period are now rated as low. For instance, the risk associated with high turnover of staff members in implementing agencies was mitigated through enhancement of strong partnership and linkages with government institutions of partner states which has allowed the utilization of the capacities of relevant institutions to support implementation of project activities. This is has ensured continuity of the project beyond individual staff and therefore cushion the project against high staff turnover. Similarly, the risk of loss of government support resulting in lack of prioritization of project activities has been mitigated through active engagement of senior government officials that are members of the Regional Policy Steering Committee responsible for providing strategic guidance and promoting political buy-in of the project. Additionally, project national coordinators have been appointed by their respective focal ministries in each of the partner states thus ensuring that partner states priority agenda are well captured during project planning and execution of activities. As a show of commitment, all partner states have now signed MoUs with LVBC. Notably, during the reporting period, two new risks emerged that are rated high and medium. These are (i) novel corona virus (COVID-19) pandemic that forced partner states to impose measures (e.g. lockdowns, travel restrictions, curfew, meeting ban etc); (ii) seasonal variability - recent high and intense precipitation that occurred since August 2019 in the East African region resulting to a rapid rise in the Lake Victoria’s water levels by 13.4metres, mark last recorded in 1964. The rains caused the waters of major rivers draining into Lake Victoria to also reach peak levels thus breaking the banks and causing major flooding in the region. This has had devastating impacts which include displacement of a large number of people, destruction of properties, infrastructure, agricultural lands, crops, and in extreme cases resulted in fatalities of humans and livestock. As a result, the livelihoods and resilience of the local communities and the regional, national and subnational economies in LVB has negatively been affected. To mitigate the corona virus (COVID-19) pandemic, adoption of adaptive management e.g. use of virtual meetings and training sessions, postponement and rescheduling of project activities, use of desktop review of existing literature and online digital platforms to consult with stakeholders is helping to mitigate the impacts of this risk. On the issue of the seasonal variability in rainfall that caused rising water levels and flooding in the LVB region, LVBC (Executing Entity) is working very closely with East Africa Partner States in finding short- medium- and long term solutions which include fundraising resources from various sources in order to contribute to the current emergency caused by rising water levels of Lake Victoria and the flooding of major rivers. This has greatly ensured that ACC-LVB project continue to be implemented in line with its objective and scope as agreed upon in the project document. Moving forward, all risks will continue to be regularly assessed and reported on at Regional Policy Steering Committee meetings and at Sectoral Council of Ministers meetings for guidance and direction.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Unidentified sub-projects (USPs) may require an EIA to comply with national environmental laws. | At the moment, none of the proposed project activities require detailed EIA. However, the requirement for an EIA are continuously being verified by each National Project Team before the implementation of on-the-ground activities at the targeted intervention sites. | Project well aligned and complies with regional, national and sub-national policies, laws, plans and priorities for sustainable development and adapting to climate change. | The Project is well aligned and complies with regional, national and sub-national policies, laws, plans and priorities for sustainable development and adapting to climate change | During the design and implementation of the sub-projects, the national project teams of each partner states have continuously screened for probable environmental and social impacts of the proposed adaptation technologies/interventions in order to ensure compliance with relevant national and regional legal requirements. This process has been guided by the ACC-LVB project Environmental and Social management Plan (ESMP) which was developed during the project inception phase. So far, none of the proposed project activities require detailed EIA to be conducted before implementation. | No
2 - Access and equity |  |  | Given that the beneficiaries are poor people who are not often integrated in the decision-making process, there could be risk of insufficient access of the project resources by these persons. | Clear and transparent criteria has been used by the National Project Teams to select sub-projects and project beneficiaries to ensure gender equity and inclusion of marginalized and vulnerable communities. This include the selection of participants in the training sessions. | Vulnerable and marginalized groups have sufficient access and benefits to project activities, particularly the water conservation practices, climate smart agricultural techniques and EbA interventions under Component 3. | The World Bank funded project developed a criteria to guide the National Project Teams during selection of sub-projects and project beneficiaries. However the criteria had gaps which had to be filled by this project. The selection of vulnerable areas was done through a fair and transparent process using the EAC-approved PREPARED VIA. | Priority project interventions are currently being implemented in selected vulnerable sites that were identified through extensive consultations with stakeholders including beneficiary communities and guided by the results of the Vulnerability and Adaptation Assessment (VIA) of the PREPARED project. Design and implementation of adaptation technologies and community-based subprojects that address the underlying causes of vulnerabilities has been done through a highly participatory, flexible and pragmatic process. This has ensured inclusion of all stakeholders in decision-making processes in a culturally appropriate and gender and inter-generationally inclusive manner. | No
3 – Marginalized and vulnerable Groups |  |  | Vulnerable and marginalised groups at project intervention sites will have insufficient access to project activities, particularly the water conservation practices, climate‑smart agricultural techniques and EbA interventions under Component 3. | Project activities have been specifically designed to take vulnerable and marginalised groups into account, particularly women. An ESMP will be followed throughout project intervention to ensure vulnerable and marginalised groups have adequate access to and benefit from project interventions. | Vulnerable and marginalised groups are involved in the selection of project beneficiaries and small scale projects; and have sufficient access and benefits to project activities, particularly the water conservation practices, climate smart agricultural techniques and EbA interventions under Component 2. | The LVBC through PREPARED has identified climate change hotspots; and marginalized and vulnerable groups. | So far, measures have been put in place in order to support inclusion of vulnerable and marginalized groups (e.g. women, elderly, youth, people living with disabilities etc.) as part of the direct beneficiaries of the project interventions. These measures include targeted project interventions and capacity building initiatives that address specific vulnerabilities affecting various community members. | No
4 – Human rights |  |  | No appreciable risk | No | Number of human rights reported and action taken | No | Project has included Community Development Officers as key extension officers to ensure compliance. So far, no human rights violation as a result of implementation of project activities has be reported. | No
5 – Gender equality and women’s empowerment |  |  | Project interventions do not benefit men and women equally. | The Project has included a 50% proportionate gender consideration in all project interventions, with a specific focus on the ground activities (Component 3 and 4). Therefore, the Project is designed to promote gender equity. The PCU and local government authorities at the Project intervention sites will need to ensure that these gender considerations are adhered to during project implementation. Fair and equitable selection of beneficiaries will be done for capacity building and training sessions. A list of all the participants will be maintained and gender ratio will be monitored by the PCU on a quarterly basis. | Number women and men involved and benefiting from project activities and outcome | 30% women and 70% men used to participate and benefits from other projects | National project teams have agreed to put in place measures that will ensure gender equality and women's empowerment is a core consideration during implementation of project activities. For instance, while at the moment the project has achieved 36% as the overall participation of women, it is expected that partner states will strive to achieve 50% women participation as beneficiaries as well as in project planning, implementation and decision-making processes. | No
6 – Core labour rights |  |  | Local community members may be exposed to the risk of accidents while implementing the Project’s climate change adaptation interventions | During implementation, the PMU and National Project Teams will ensure compliance with national and international labour laws and will provide adequate protection equipment for workers. | Number of cases reported on international labour and action taken | No case reported | Project has included Community Development Officers as key extension officers to ensure compliance. So far, no case of violation of labor rights has been reported. | No
7 – Indigenous peoples |  |  | Indigenous communities at project intervention sites are not identified and are therefore not included in the relevant stakeholder consultations and decision-making processes. Inequitable access of indigenous peoples to the project's resources | Comprehensive stakeholder mapping will take place through Output 3.1 as project intervention sites are identified. This will allow for the identification of indigenous peoples. The Project will not contravene the rights of indigenous people. Indigenous peoples will be included in the participatory planning of project interventions and the design of CBAPs to ensure equitable access to project resources. | Number of indigenous communities identified action taken | No indigenous communities identified and reported | During stakeholder mapping exercise in the selected intervention sites, rigorous community engagement processes included a criteria to safeguard indigenous communities. However so far no indigenous communities were identified in the selected project sites/beneficiary communities. | No
8 – Involuntary resettlement |  |  | No appreciable risk | During project development involuntary resettlement was addressed and included in selection criteria. Project intervention site selection included item of identifying involuntary resettlement | Number of involuntary resettlement issued identified action taken | No case reported | None of the project activities being implemented across the five partner states has resulted to displacement or resettlement of local communities. However, subnational project teams have included Community Development Officers as key extension officers to ensure that involuntary resettlement safeguards are put in place incase where future project activities will require resettlement of local communities. | No
9 – Protection of natural habitats |  |  | Construction of adaptation interventions (for example boreholes or gabions) identified in the community based adaptation plans could result in the destruction of small areas of natural habitat. | Technical feasibility studies will be conducted for physical infrastructure identified as sub-projects in the community based adaptation plans to ensure that they will not result in significant adverse impacts on natural habitat. All activities will adhere to the EIA regulations of the relevant Partner State. | number of Construction of adaptation interventions identified and appropriate action taken | No case reported | With support of project teams, assessments of likely impacts of project interventions on natural habitats have been carried out. So far, no negative impacts on natural habitats have been reported as a result of project activities. | No
10 – Conservation of biological diversity |  |  | Construction of adaptation interventions (for example boreholes or gabions) identified in the community‑based adaptation plans could result in negative impacts on biodiversity. | Technical feasibility studies will be conducted for physical infrastructure identified as sub-projects in the community based adaptation plans to ensure that they will not result in significant adverse impacts on biodiversity. | number of Construction of adaptation interventions identified and appropriate action taken | No case reported | So far, no negative impacts on biological diversity as a result of project intervention has been detected. However, project teams in respective partner states are actively monitoring probable negative impacts in order to ensure that appropriate mitigation measures are implemented. | No
11 – Climate change |  |  | No appreciable risk |  |  |  | All project activities are intended to enhance climate resilience in LVB at both regional, national and subnational/local levels.
12 – Pollution prevention and resource efficiency |  |  | No appreciable risk |  |  |  | No project activities has resulted to pollution. Resource efficiency is a core consideration where some adaptation technologies e.g. micro irrigations subprojects are being designed to tap into renewable solar energy.
13 – Public health |  |  | Water-related diseases (such as Malaria) may increase in frequency with the construction of water storage infrastructure. | The construction of water storage infrastructure will be accompanied with training and technical support to communities on how to mitigate the risks of water-related diseases. | Number of trainings conducted to avoid and treat Water-related diseases | No case reported | Health officers at the project sites are being involved in the monitoring of water-related diseases that may occur due to water storage infrastructure. | No
14 – Physical and cultural heritage |  |  | Without specific site selection, it is possible that the interventions identified in sub-projects will negatively affect physical and cultural heritage. | Participatory mapping – which will include local communities and district level authorities – will be undertaken during the development of CBAPs to identify areas of physical and cultural significance and ensure that sub-projects will not negatively impact upon those. | number of physical and cultural heritage identified and appropriate action taken | No case reported | So far, national project teams responsible in the five EAC partner states have not reported any project intervention that will negatively affect physical and cultural heritage in the project sites | No
15 – Lands and soil conservation |  |  | No appreciable risk
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes. National Project Teams in all partner states (Kenya, Uganda, Tanzania, Rwanda and Burundi) have been provided with an updated ESMP monitoring template in order to record unanticipated ESP risks of on the ground activities that have been initiated/proposed.
Have unanticipated ESP risks been identified during the reporting period? |  | Unanticipated ESP risks will continuously be monitored as countries submit reports detailing progress of implementation of on the ground project activities. Next PPR will give details.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | The ESMP that was developed during inception phase of the project has been updated to incorporate unanticipated ESP risk section. Next PPR will give details.
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The safeguard risks were identified during the project development phase and an ESMP developed. UNEP will manage and monitor and report on the ESMP and adapt/adjust the ESMP if and when needed. An ESP was developed and presented to the Regional project coordination team. United Nations Environment Programme (UNEP) held meeting with Executing Entity (LVBC) and Partner States (Burundi, Kenya, Rwanda, Tanzania and Uganda). One of agenda of the meeting was ESP safeguard measures. In the meeting UNEP, LVBC and Partner States agreed and put mechanisms to implement required ESP safeguard measures. The mechanisms includes (a) Project Management Unity has obligation to ensure ESP safeguard measures are implemented as per signed project document and revised ESP and reported (b) Project has established National Coordination teams with Coordinators. The teams include relevant project sectors such as Agriculture, Livestock, Forestry, climate/ Meteorology, Water, Environmental Management Authorities/ agencies; and particularly Community development officers whose mandate is to ensure ESP safeguard measures are implemented and adjusted accordingly and reported to project management (c) Project has established districts/county project coordination teams with the same structure in (b) and play the same role (d) UNEP has issued guidelines that for all activity LVBC has to ensure ESP measures are coordinated and reported to RPSC and Council of Ministers for actions. In the meeting it was agreed to identify issues which were not included in the ESP to ensure they are captured and addressed.
Have the implementation arrangements been effective during the reporting period? |  | So far, there has been no reported shortcomings on the implementation arrangements. However, the effectiveness of the implementation arrangements will be measured during the upcoming Mid-Term review of the project. This will be reported in the next PPR.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | National Environment Councils/ Authorities are regulatory bodies and are involved in the project implementation. The established RPSC and PMU at regional level; and national and Districts Coordination teams are responsible for implementation and reporting of ESP
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Effective. An ESP was developed and presented to the Regional project coordination team for the Lake Victoria Basin. A training on the implementation and monitoring of ESP has been conducted to national teams of Rwanda, Burundi and Tanzania.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | An updated ESMP for the ACC-LVB project has been developed and shared with all EAC partner states that are implementing the project. The ESMP include the following components: (a) Subproject activity; (b) Potential adverse effects/impacts; (c) Proposed mitigation measures; (d) Institutional responsibility for mitigation (including enforcement and coordination); (e) Monitoring requirements; (f) Responsibility for monitoring and supervision; Implementation schedule; and (g) Cost estimates. National institutions and staff to support ESMP implementation are present. Roles and responsibilities are adequately assigned to national, Districts and County institutions including established coordination teams. To enhance effective implementation of the ESMP, the regional project team recently facilitated a training targeting National Project Teams in Tanzania, Rwanda and Burundi. Plans to facilitate a similar training on ESMP implementation targeting National Project Teams of Uganda and Kenya were disrupted by travel restrictions due to COVID-19 pandemic. However, the regional project team is exploring the options of facilitating a virtual training for Kenya and Uganda teams.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | During the reporting period, the project ESMP has been updated to include a section of unanticipated risks in USPs. The Project team will continuously update the ESMP together with its monitoring framework once the identified interventions in the USPs are assessed. The ongoing exercise on identification of intervention activities include gathering information to guide in the identification of USPs will inform regular updates of ESMP.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
Proposed USPs concepts for Burundi, Rwanda, Tanzania and Uganda have been agreed upon between communities, subnational, national and LVBC regional project teams. Currently, detailed proposals for the agreed upon USPs concepts are being developed. Identified environmental and social risks for each USPs proposal will be reported in the next reporting period. | The exercise of identifying ESMP for proposed USPs for Burundi, Rwanda, Tanzania and Uganda is currently ongoing.
For Kenya, USPs are yet to be identified but will be reported during the next reporting period. | This exercise is on-going and related risks will be reported in the next PPR, as specified by the IE. In kenya there is a delay in the USPs' identification
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
So far, no grievances regarding environmental and social impacts of project activities has been reported. |  | So far, no grievances regarding environmental and social impacts of project activities has been reported.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal?
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)?
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | UNEP has a comprehensive Policy and Strategy on Gender Equality and the Environment which sets in place the use of a gender marker. Essentially the gender marker serves as a monitoring tool that ensures that at the point of project development and implementation gender perspectives are integrated at all stages including the budget. The gender marker has a four point scale against which the project is assessed. Each project is required to meet a rating of 2a which means that gender is fully mainstreamed and the project will make a significant contribution to meeting gender equality. Should a project not meet the 2a rating, the project officer is required to revise the project and ensure gender perspectives are fully mainstreamed and thereafter resubmit the project for project review.
Have the implementation arrangements at the IE been effective during the reporting period? |  | As a follow up to the 4 day training organized by UN Environment’s Climate Change Adaptation Unit (CCAU) for the project manager and chief technical advisor for the project, UNEP carried out two missions in October 2019 and January 2020 to provide additional training for the project management unit to strengthen capacities in climate change adaptation and project management best practices. The trainings refreshed on how integrate gender across the project including developing terms of reference for trainings and need for gender equity in beneficiaries of project activities as well as how to record and report on gender markers.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The proposed project has included proportionate gender consideration on all project interventions, with a specific focus on on-the-ground activities (Component 3 and 4). Provisions for equitable selection of beneficiaries have been included for all capacity building and training activities and gender ratio will be monitored by quarterly basis. The PCU and partner countries' government authorities at the proposed project intervention sites are continuously being monitored to ensure that these gender considerations are adhered to during project implementation.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | 3 out of 5 National Project Coordinators nominated by the partner countries to the project are women (60%). However, more efforts are required to ensure equitable representation among national experts in partner countries is achieved through continuous discussions with governments as well as assistance in drafting gender responsive TORs.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Partner countries have lower ratio of women employed in offices and units relevant to the project which in turn affect the GP compliance in project deliverables. Project has ensured TORs and invitation letters include gender component and gender considerations and provide opportunities and ensure Community Development Officers give women equal opportunities and enable participation of women in decision making processes in intervention areas.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievance received during the reporting period
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Outcome 1: Strengthened institutional and technical capacity to integrate climate resilience into transboundary water catchment management. |  | Outcome 2 | By the end of the project, at least 20 staff (of which at least 50% are women) trained on climate change adaptation and water catchment management during regional workshops. By the end of the project, at least 100 staff (of which at least 50% are women) trained on climate change adaptation and water catchment management during national workshops. |  | So far, a total of 666 (52% male and 48% female) community's, extension officers and non-government representatives have been trained during national/sub-national training sessions on climate change, climate change adaptation and water management that have been held in partner states (Burundi, Rwanda, Tanzania and Uganda). Plans are also underway to provide advanced training on transboundary water management and climate change adaptation at regional and national levels to be facilitated by Water Catchment Management and Adaptation Expert that is currently being recruited and expected to be on board by September 2020. The expert will be responsible for spearheading regional and national capacity building training exercise to strengthen institutional and technical capacity to integrate climate resilience into transboundary water catchment management. A project stakeholder engagement strategy has been drafted through a consultative process between LVBC, UN Environment and partner states. The approval of the strategy was part of the agenda of the CCTWG meeting that was scheduled for April 2020. However, due to restrictions imposed by partner states and East Africa Community (EAC) to control the spread of the novel corona virus (COVID-19), the CCTWG meeting was postponed to a future date. The project team is currently liaising with CCTWG members to explore the possibility of holding a virtual meeting that will approve strategy before the end of 2020. | Marginally Satisfactory
| Outcome 2: Improved delivery of accurate and timely climate information to regional and national policymakers, technical officers and local communities. |  | Outcome 1 | By the end of the project, policy- and decision-makers in each pilot country receive down-scaled national climate information every quarter. By the end of the project, local communities in the project interventions sites receive tailored climate information packages. |  | A regional Training of Trainers (ToTs) faciliated by IGAD Climate Prediction and Application Centre (ICPAC) was held in September 2019 and attended by 32 experts drawn from all the partner states (Burundi, Kenya, Tanzania, Rwanda and Burundi) During the training, modules on strengthening of existing climate information dissemination mechanisms in LVB were delivered while at the same time participants were provided with climate modelling software to support the downscaling of climate information to respective national and subnational levels. Additionally, strategies and tools for strengthening existing climate information dissemination mechanisms were developed with guidance from ICPAC trainers. To promote downscaling of regional climate information at national and subnational levels, a national training was held in Rwanda where 35 weather forecasters (27men and 8 women) were trained by Meteo Rwanda. National training workshops in Burundi, Kenya, Tanzania and Uganda that were scheduled to take place in Q2 & Q3 of 2020 were postponed to 2021 due to restrictions imposed by partner states after the emergency of novel COVID-19. Plans are at an advanced stage for ICPAC to spearhead the development of tailored climate information packages to be shared with communities, decision and policy makers across the partner states. | Satisfactory
| Outcome 3: Climate change adaptation technologies transferred to communities to reduce their vulnerability to climate change. |  | Outcome 8 | At least 1000 hectares of agricultural land rehabilitated through climate-smart agriculture (200 ha at project intervention sites in each of the five Partner States) and at least 500 hectares of hectares of woodland rehabilitated using an EbA approach (100 ha at project intervention sites in each of the five Partner States). At least 500 people (100 per intervention site) are practicing climate change adaptation technologies. |  | A stock take of adaptation technologies/interventions detailed in existing national strategies and action plans, recommendations from other regional projects and findings of scientific research in the LVB has been conducted and a draft report produced. The report provides a representative overview of the wide diversity of existing adaptation technological options in water conservation, ecosystem based adaptation and climate smart agriculture that are being applied in the LVB. Reference to the report is being used by partner states to promote transfer, adoption and diffusion of innovative adaptation technologies in the region. The report is also expected circulated widely through various communication channels including GAN. Adaptation technologies to be demonstrated in Burundi, Rwanda, Tanzania and Uganda have been agreed upon between National and Subnational teams in each partner state and LVBC. In Burundi, approximately 240 hectares of agricultural land has been rehabilitated through construction of contour lines, bio-engineering and planting of 548,000 multipurpose agroforestry and fruit trees in Gatete and Rwabikara communes in Busoni district as well as Nzove-Kayove and Rukusha -Kijumbura communes in Giteranyi district of Burundi. In Rwanda, Uganda and Tanzania, Community engagement and sensitization workshops have been held to lay the ground work for the implementation adaptation technologies. For instance, in Rwanda, community training sessions have been held where 143 community animators, extension officers and community members were trained in February 2020. In Uganda, 108 local community members and extension workers (50% women) were trained while 295 community members located in the 7 villages of Kashenyi, Kyagungu, Kitoma, Bugere, Mijjunju, kyakasa and Kalungu were sensitized on the role of water conservation, EbA and CSA in enhancing local resilience to the impacts of climate change. Currently, partner states with technical support from LVBC are developing concepts detailing adaptation technologies to be piloted in selected demonstration sites. In Kenya, there has been no progress in the implementation of adaptation technologies due to the delay in the signing of MoU between Kenya and LVBC which restricted funds transfer to Kenya. However, the MoU was signed in May 2020 and therefore Kenya is expected to initiate implementation of on the ground activities starting Q3 of 2020. Upon signing, field visits to project sites have been conducted while National and Subnational Project Teams are currently selecting project intervention sites. To fasttrack project implementation, Kenya has requested local authorities to support beneficiary communities in order to ensure simultenous implementation of adaptation technologies (Outcome 3) and community-based adaptation interventions (Outcome 4). This is expected to address the lag in the implementation of activities in Kenya | Marginally Satisfactory
| Outcome 4: Regional resilience to climate change promoted through innovative, community-based projects. |  | Outcome 8 | At least 1000 people (200 per intervention site) benefit from small-scale community-based projects. |  | Significant progress has been achieved in Uganda and Rwanda where training targeting community groups and selected local NGOs in project sites on development of small-scale proposals, administrative and financial management of community-based small-scale projects, as well as self-monitoring and evaluation by communities have been conducted. A template has been developed to guide community-based organizations in partner states to develop project proposals related to promotion of climate change adaptation. In Uganda, 20 community-based organizations have developed proposals after they were trained on proposal development. Upon completion of the review of community-based adaptation subprojects partner states, selected subprojects that promote innovative approaches to community-based climate change adaptation will be financed through grants from ACC-LVB project grants starting from Q1 of 2021. | Marginally Satisfactory
| Outcome 5: Improved knowledge management frameworks for the collection and maintenance of regional knowledge in transboundary water catchment management and climate change adaptation practices. |  | Outcome 3 | At least 15 news outlets in the local press and media that have covered climate change adaptation in relation to transboundary water catchment management in the LVB. |  | A detailed communication plan and its implementation plan has been drafted through a consultative process between LVBC, UN Environment and partner states. Approval of the plan by the CCTWG was scheduled for June 2020 but CCTWG meeting was postponed until further notice due to corona virus (COVID-19) pandemic. National Project teams have developed communication materials on water management and climate change adaptation and utilized them during community mobilization and awareness raising sessions in respective partner states (Rwanda, Tanzania, Burundi and Uganda). Project newsletters for Tanzania, Burundi and Rwanda have also been produced. National awareness campaigns that were scheduled to take place since March 2020 have been postponed until further notice due to restrictions imposed by partner states to curb the spread of the novel corona virus (COVID-19). | Marginally Satisfactory
[6 empty] | Overall Rating | Marginally Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Essey Daniel
| Email: | essey.daniel@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project took a number of steps to Fastrack implementation in the countries and to make up the time lost during the first year of execution. Building on the preparatory work conducted during the first year, the project has made good progress towards the achievement of expected outcomes during the second year of implementation. The recruitment of the project team was finalised by June 2019 and has worked with the focal points in the 5 partner countries to develop working relationships. A draft stock take of the draft stock take report detailing existing adaptation technologies in the LVB was produced to capture existing adaptation technologies and guide the community based adaptation approaches in the region. This was followed by training on climate change adaptation and water management for over 600 participants in the 4 partner countries. Burundi are ahead in starting implementation of adaptation technologies in the sites that were selected, and have gone ahead with activities including agroforestry as well as submitting proposals for fish drying technologies and micro-irrigation system, Rwanda and Tanzania have submitted their proposals for adaptation options and have started recruitment of firms for on ground implementation. The project however suffered substantial delays on activities due to a number of reasons - The Memorandum of Understanding between the executing entity LVBC and the Government of Kenya was not delayed due to a request from Government of Kenya that fiduciary responsibility for Kenya's portion of funds rested with LVBC due to complications with procurement and financial reporting at the local government level. After interventions by senior management of LVBC, EAC secretariat and the project steering committee the MOU was signed in May 2020. This however meant that no funds could be transferred to Kenya until the MOU was finalised and activities touching on component 3 and component 4 could not commence - High and intense precipitation that occurred since August 2019 in the East African region resulting to a rapid rise in the Lake Victoria’s water levels by 13.4metres.This has had devastating impacts which include displacement of a large number of people, destruction of properties, infrastructure, agricultural lands, crops, and in extreme cases resulted in fatalities of humans and livestock. A number of the project areas were affected and local governments were overwhelmed with implementing short term measures to support the vulnerable communities around the LVB and this resulted in postponement of a number of project activities such as stakeholder consultations and prioritization of adaptation options with the communities. -The novel corona virus (COVID-19) pandemic forced partner states to impose measures (e.g. lockdowns, travel restrictions, curfew, meeting ban) that severely affected activities including regional forums and trainings, validation workshops for communication and stakeholder engagement strategy for the region as well as general slow down of implementation in the countries due to government shutdown and restrictions around mobility in the country. Despite the challenges above the project team has been able to continue it's engagement with the countries through extensive use of IT, virtual meetings and training sessions and with the softening of COVID-19 related restrictions in 4 partner countries, the signed MOU in Kenya and the various measures of fast racking implementation of component 3 and 4, the next reporting period plans to achieve the majority the milestones that were planned for Q1 and Q2 of 2020. In light of the progress achieved on adaptation stock take exercise, template for adaption options, setting up country teams, identifying project sites, setting up training events on climate change adaptation and in a number of countries identifying adaptation priorities and setting up framework for execution I rate the project progress Marginally Satisfactory.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 1: Strengthened institutional and technical capacity to integrate climate resilience into transboundary water catchment management. |  | Outcome 2 | By the end of the project, at least 20 staff (of which at least 50% are women) trained on climate change adaptation and water catchment management during regional workshops. By the end of the project, at least 100 staff (of which at least 50% are women) trained on climate change adaptation and water catchment management during national workshops. |  | National training sessions on climate change, climate change adaptation and water management have been held in Rwanda where 143 (50% male and 50% female) community animators, extension officers and community members were trained in February 2020. Similarly in Uganda, 295 (55% male and 45% female) community members located in the 7 villages of Kashenyi, Kyagungu, Kitoma, Bugere, Mijjunju, kyakasa and Kalungu were trained on the role of water conservation, ecosystem-based adaptation and climate-smart agriculture in enhancing local resilience to the impacts of climate change. In Tanzania, awareness raising training sessions were conducted in Magu District and attended by 16 District technical staff and 228 (51% female and 49% male) Ng'haya village community group members. In Burundi, orientation trainings on climate change targeting National Project Steering Committee team and community members were conducted during the reporting period. Plans are also underway to provide advanced training on regional management of transboundary water catchment in the context of climate change and adaptation in the Lake Victoria Basin facilitated by Water Catchment Management and Adaptation Expert that is currently being recruited by LVBC and will be onboard in September 2020. A draft project stakeholder engagement strategy has been developed. However, due to corona virus (COVID-19) pandemic the CCTWG meeting that was scheduled for April 2020 to approve the stakeholder engagement strategy was postponed until further notice. | Marginally Satisfactory
| Outcome 2: Improved delivery of accurate and timely climate information to regional and national policymakers, technical officers and local communities. |  | Outcome 1 | By the end of the project, policy- and decision-makers in each pilot country receive down-scaled national climate information every quarter. By the end of the project, local communities in the project interventions sites receive tailored climate information packages. |  | A regional Training of Trainers (ToTs) workshop was facilitated by IGAD Climate Prediction and Application Centre (ICPAC) and attended by 32 experts from the five partner states in September 2019. During the training, modules on strengthening of existing climate information dissemination mechanisms in LVB were delivered while at the same time participants were provided with climate modelling software to support the downscaling of climate information to respective national and subnational levels. Additionally, strategies and tools for strengthening existing climate information dissemination mechanisms were developed with guidance from ICPAC trainers. Similarly, one national training was held in Rwanda where Meteo Rwanda trained 35 weather forecasters (8 women and 27men) on downscaling regional climate information to national level. National training workshops in Burundi, Kenya, Tanzania and Uganda that were scheduled to take place in Q2 & Q3 of 2020 were postponed to 2021 due to restrictions imposed by partner states after the emergency of novel COVID-19. Consultative meetings have been held between LVBC and IGAD Climate Prediction and Application Centre (ICPAC) with a view to engaging ICPAC experts to support national meteorological agencies in partners states in the development of tailored climate information packages. However, due to restrictions to curb the spread of COVID-19 that do not allow meetings to be held and slowed down project activities, this activity has been rescheduled for 2021. | Satisfactory
| Outcome 3: Climate change adaptation technologies transferred to communities to reduce their vulnerability to climate change. |  | Outcome 8 | At least 1000 hectares of agricultural land rehabilitated through climate-smart agriculture (200 ha at project intervention sites in each of the five Partner States) and at least 500 hectares of hectares of woodland rehabilitated using an EbA approach (100 ha at project intervention sites in each of the five Partner States). At least 500 people (100 per intervention site) are practicing climate change adaptation technologies. |  | A draft stock take report detailing existing adaptation technologies in water conservation, CSA and EbA in LVB was produced in May 2020. The results contained in the stock take report is currently being used to promote transfer, adoption and diffusion of innovative adaptation technologies in the project sites. The report is also expected to be reviewed and approved by CCTWG and thereafter circulated widely through various communication channels including GAN. In Burundi, Rwanda, Tanzania and Uganda, project demonstration sites as well as CSA, water conservation and EbA practices to be implemented in these countries have jointly been agreed upon between national and subnational teams, communities and LVBC project team. In Burundi, approximately 240 hectares of agricultural land has been rehabilitated through construction of contour lines, bio-engineering and planting of 548,000 multipurpose agroforestry and fruit trees in Gatete and Rwabikara communes in Busoni district as well as Nzove-Kayove and Rukusha -Kijumbura communes in Giteranyi district of Burundi. In Rwanda, Uganda and Tanzania, Community engagement and sensitization workshops have been held to lay the ground work for the implementation adaptation technologies. For instance, in Rwanda, community training sessions have been held where 143 community animators, extension officers and community members were trained in February 2020. In Uganda, 108 local community members and extension workers (50% women) were trained while 295 community members located in the 7 villages of Kashenyi, Kyagungu, Kitoma, Bugere, Mijjunju, kyakasa and Kalungu were sensitized on the role of water conservation, EbA and CSA in enhancing local resilience to the impacts of climate change. Currenlty, partner states are in the process of developing concepts detailing adaptation technologies to be implemented in respective desmonstration sites. In Kenya, there has been no progress in the implementation of adaptation technologies due to the delay in the signing of MoU between Kenya and LVBC which restricted funds transfer to Kenya. However, the MoU was signed in May 2020 and therefore Kenya is expected to initiate implementation of on the ground activities starting Q3 of 2020. Upon signing, field visits to project sites have been conducted while National and Subnational Project Teams are currently selecting project intervention sites. To fasttrack project implementation, Kenya has requested local authorities to support beneficiary communities in order to ensure simultenous implementation of adaptation technologies (Outcome 3) and community-based adaptation interventions (Outcome 4). This is expected to address the lag in the implementation of activities in Kenya. | Satisfactory
| Outcome 4: Regional resilience to climate change promoted through innovative, community-based projects. |  | Outcome 8 | At least 1000 people (200 per intervention site) benefit from small-scale community-based projects. |  | So far, in Uganda and Rwanda training targeting community groups and selected local NGOs in project sites on development of small-scale proposals, administrative and financial management of community-based small-scale projects, as well as self-monitoring and evaluation by communities have been conducted. Training in Burundi, Kenya and Tanzania are scheduled to take place in Q3 & Q4 of 2020. A template to guide the development of small scale community based adaptation projects has been developed and shared with national project teams. In Burundi, Tanzania, Rwanda and Uganda, preliminary meetings have been held between local communities, National and Subnational Project Teams as well as LVBC in order to agree on the probable community based adaptation interventions. Upon completion of training on proposal development, community-based organizations working in ACC-LVB project sites are therefore expected to develop proposals that promote climate change adaptation interventions. These proposals will be reviewed in Q4 2020 and those that promote innovative approaches to climate change adaptation will be funded starting Q1 of 2021. | Marginally Satisfactory
| Outcome 5: Improved knowledge management frameworks for the collection and maintenance of regional knowledge in transboundary water catchment management and climate change adaptation practices. |  | Outcome 3 | At least 15 news outlets in the local press and media that have covered climate change adaptation in relation to transboundary water catchment management in the LVB. |  | A communication plan and its implementation plan has been drafted. The CCTWG meeting that was to review and approve the draft communication plan was scheduled to take place in April 2020 but was postponed until further notice due to corona virus (COVID-2019). Local communities awareness raising materials have been produced in Rwanda, Tanzania, Burundi and Uganda. These materials were extensively used during the community training sessions facilitated by respective national project coordination teams. Project newsletters for Tanzania, Rwanda and Burundi have also been produced. | Marginally Satisfactory
[6 empty] | Overall Rating | Marginally Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dr. Masinde K. Bwire
| Email: | Bwire@lvbcom.org; bwirejoseph@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The overall rating of the progress of project implementation is Marginally Satisfactory. The project had a prolonged inception phase occasioned by delays in the signing of MoUs between LVBC and partner states which delayed funds disbursement to the partner states. A good example is the MoU between Kenya and LVBC which was signed in May 2020 despite the process being initiated in 2018. This therefore means that very minimal progress towards implementation of on the ground activities has taken place in Kenya. Similarly, bureaucratic procedures in EAC delayed the setting up of the Regional Coordination Team (Project Manager, Chief Technical Advisor and Finance Assistant) further stifling project implementation. The recent corona virus (COVID -19) pandemic has further affected the pace of project implementation. While the aforementioned issues have resulted to delays in project implementation, this has allowed extensive consultations and consensus that have contributed to a strong sense of ownership and engagement of various stakeholders at regional, national and subnational levels. Furthermore, key milestones that have been achieved include completion of the inception phase (inception workshop held on 28th June 2018); establishment of national and subnational project coordination teams for each partner states; laying the groundwork for the implementation of project activities in Tanzania, Rwanda, Burundi and Uganda; piloting of on the ground project activities in Burundi; capacity building initiatives on adaptation and downscaling of regional climate information at national and subnational/local levels; engagement and stakeholder sensitization forums that have achieve high level political support from senior government officials of partner states that play a critical role during the implementation of the project. Through engagement with regional institutions e.g. IGAD Climate Prediction and Application Centre (ICPAC) and other institutions at national levels, the project is able to create partnerships and cross-sectoral collaborations that have enabled it to tap into existing expertise of these institutions to support implementation of project activities thus increasing project efficiency. Furth more, partnerships are contributing towards increasing knowledge sharing and improve working relationships in the process of trickling the impacts of climate change in the East Africa Region. Moving forward, measures to fast track implementation of project activities have been put in place e.g. simultaneous implementation of project activities as well as regular strategic meetings between LVBC, National Coordination Teams of partner states and UN Environment in order address challenges/bottlenecks facing the project. Additionally, maximizing use of digital platforms (e.g. virtual meeting) to ensure business continuity during the COVID-19 pandemic that has restricted travelling and one on one meeting while at the same time updating and seeking regular guidance from Regional Policy Steering Committee to help in unlocking bureaucratic administrative processes to hasten the process of implementation of activities.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1. Indicator | No. of staff trained to respond to, and mitigate impacts of, climate-related events (gender disaggregated). | Staff involved in regional institutions have been trained through the PREPARED project on climate change adaptation. | 2018/2019 reporting period: one (1) man trained . 2019/2020 reporting period: LVBC is currently finalizing the recruitment of an International consultant (Water Catchment Management and Adaptation Expert) to provide technical guidance and support capacity building initiatives on trans-boundary water catchment management and climate change adaptation in the LVB. | By the end of the project, at least 20 staff (of which at least 50% are women) trained on climate change adaptation and water catchment management during regional workshops; and By the end of the project, at least 100 staff (of which at least 50% are women) trained on climate change adaptation and water catchment management during national workshops.
Output 1.1. Indicator | Number of meetings of the CCTWG. | 2 meetings during the project period | 2018/2019 reporting period: 1 meeting of regional climate and national situations held to share experiences of data collection, analysis and dissemination. 2019/2020 reporting period: CCTWG meeting that was scheduled for April 2020 was cancelled due to travel restrictions associated with COVID-19 pandemic. The meeting has now been rescheduled to Q4 of 2020 if the situation of COVID-19 allows. | 6 meetings of the CCTWG are held
Output 1.2 Indicator | No. of staff trained to respond to, and mitigate impacts of, climate-related events (gender disaggregated). | Staff involved in regional institutions have been trained through the PREPARED project on climate change adaptation. | 2018/2019 reporting period: One LVBC (man) Trained on UN Environment training of Climate Change Adaptation. 2019/2020 reporting period: LVBC is currently finalizing the recruitment of an International consultant (Water Catchment Management and Adaptation Expert) to provide technical guidance and support capacity building initiatives on trans-boundary water catchment management and climate change adaptation in the LVB. | at least 20 staff (of which at least 50% are women) trained on climate change
Outcome 2. Indicator | Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis. | Policy- and decision-makers in the five Partner States received project implementation status and provided directives. | 2018/2019 reporting period: This project was used to disseminate the identified climate threat and hazard information generated by PREPARED project to decision makers 14 (6 women and 8 men) Permanent Secretaries and 7 (3 women and 4 men) Sectoral Council of Ministers 2019/2020 reporting period: LVBC is currently engaging IGAD Climate Prediction and Application Centre (ICPAC), with a view of producing regional climate information which will be analysed and tailored to the requirements of end-users in the LVB, including regional and national policy- and decision-makers, technical staff in national and local government agencies as well as local communities. | By the end of the project, policy- and decision-makers in each pilot country receive down-scaled national climate information every quarter. By the end of the project, local communities in the project interventions sites receive tailored climate information packages.
Output 2.1. Indicator | Delivery of climate information to local communities at selected project intervention sites. | National hydro meteorological agencies in each of the Partner States receive regional climate information from institutions such as ICPAC and FEWSNet through regional forums such as the CIN. However, this information is not transmitted to local communities to allow them to plan seasonally. | 2018/2019 reporting period: 4 capacity building workshops were held for the established project National Coordination team in Burundi, Kenya, Rwanda and Uganda for climate, agriculture, water, community development technical experts (38 participants (12 women and 16men) to understand project management; and delivery of climate information to local communities at selected project intervention sites. 2019/2020 reporting period: 32 national hydro meteorological experts were trained by ICPAC on downscaling regional climate information to national, subnational and local levels in September 2019. The trained experts are expected to support in the delivery of climate information to the local communities in their respective countries. | All communities at the selected project intervention sites receive relevant climate information at least twice a year.
Output 2.2. Indicator | Number of staff members trained on downscaling regional climate information to the national level. | Staff from national meteorological agencies have been trained to produce regional climate information with GEOCLIMA software | 2018/2019 reporting period: Project has agreed with IGAD Climate Prediction and Application Centre (ICPAC), Famine Early Warning Systems Network (FEWSNET), Regional Centre for Mapping of Resources for Development (RCMRD) to conduct training at ICPAC training Centre. Training will be in August 2019. 2019/2020 reporting period: During the month of September 2019, ICPAC facilitated a training of 32 national experts (5 from each of the 5 partner states and 7 from LVBC) on downscaling regional climate information to national, subnational and local levels. | At least 25 (5 per Partner State) staff members trained on downscaling regional climate information to the national level
Outcome 3. indicator | Natural assets protected or rehabilitated | Areas of forest and agricultural land and being degraded through overexploitation for fuelwood and unsustainable agricultural practices. | Project has identified and validated intervention sites. Actual activities has not started due to the delay of approved ToR for procurement of Adaption expert. It will start by October 2019. 2019/2020 reporting period: Approximately 240 hectares of agricultural land has been rehabilitated through construction of contour lines, bio-engineering and planting of 548,000 multipurpose agroforestry and fruit trees in Gatete and Rwabikara communes in Busoni district as well as Nzove-Kayove and Rukusha -Kijumbura communes in Giteranyi district of Burundi. However, on ground activities in Rwanda, Kenya, Tanzania and Uganda implemented activities include community mobilization and trainings on adaptation technologies as part of laying the ground work for on the ground activities. A draft report of the stock take of existing adaptation technologies for water conservation practices, climate-smart agricultural techniques and ecosystem-based adaptation (EbA) in LVB that are detailed in national strategies and action plans.in the LVB has also been produced. | At least 1000 hectares of agricultural land rehabilitated through climate-smart agriculture (200 ha at project intervention sites in each of the five Partner States) and at least 500 hectares of hectares of woodland rehabilitated using an EbA approach (100 ha at project intervention sites in each of the five Partner States).
| Number of people practicing climate change adaptation technologies. | 0 | Adaptation technologies are planned to be implemented in Q3 & Q4 of 2020. | At least 500 people (100 per intervention site) are practicing climate change adaptation technologies.
Output 3.1. Indicator | Number of project intervention sites identified. | The VIA being finalised by PREPARED has identified vulnerability hotspots. Specific sites will be chosen within these hotspots. | 2018/2019 reporting period: 9 intervention sites have been identified using agreed regional criteria. Burundi selected Kirundo and Muyinga as intervention sites, Government of Kenya selected Busia and siaya as interventions sites, Government of Rwanda selected Kihere District within Akagera river basin and names of sites are Gahara and Musaza; Government of Tanzania selected Magu; and government of Uganda selected Masaka and Mubende as intervention sites. 2019/2020 reporting period: Selected project site in Uganda, Rwanda, Tanzania and Burundi have been validated by national project teams in collaboration with LVBC project team. Additionally, national and subnational teams have engaged local communities to lay the ground work in the preparation for the implementation of project activities. Local communities in Burundi, Rwanda, Tanzania and Uganda have further selected sites within their localities where various project activities (e.g. Water Conservation, Climate-Smart Agriculture and EbA interventions) will be implemented. | At least 1 intervention site identified in each Partner State.
Output 3.2. Indicator | Number of community members at project intervention sites in each state trained on climate change adaptation technologies (gender disaggregated). | 0 | 2018/2019 reporting period: Project has identified and validated intervention sites. Actual activities has not started due to the delay of approved ToR for procurement of Adaption expert. It will start by October 2019. 2019/2020 reporting period: In Burundi, Tanzania, Rwanda and Uganda, preliminary meetings have been held between local communities, National and Subnational Project Teams as well as LVBC in order to agree on the probable community based adaptation interventions. Additionally, in Uganda and Rwanda training targeting community groups and selected local NGOs in project sites on development of small-scale proposals, administrative and financial management of community-based small-scale projects, as well as self-monitoring and evaluation by communities have been conducted. So far, a total of 523 community members of which 228 (118 female and 110 male) are from Tanzania and 295 (165male and 130 female) are from Uganda have been trained. In Rwanda, 143 community animators, extension officers and community members were trained in February 2020. | At least 100 community members in each Partner State (of which 50% are women) trained on climate change adaptation technologies (500 people in total).
Output 3.3. Indicator | Number of households at project intervention sites in each Partner State benefitting from water conservation practices. | 0 | 2018/2019 reporting period: Regional training on how to facilitate, approve project proposals for funding has been scheduled by September and training at community level will be starting by October 2019. Funds have been transferred to Countries to implement this activity. 2019/2020 reporting period: Water conservation practices have been documented in the draft stock take report of adaptation technologies that was produced in May 2020. Similarly, communities in Uganda, Tanzania, Rwanda and Burundi have identified water harvesting technologies e.g. micro-dams and water tanks as some of the water conservation practices to be implemented in their localities. These technologies have jointly been agreed upon between national and subnational teams, communities and LVBC project team. However, these technologies are scheduled to to be implemented starting Q3 of 2020 after they are assessed/reviewed using a criteria that was developed during the stocktaking exercise. | At least 100 households in each Partner State benefitting from water conservation practices (500 households in total).
| Number of hectares of climate-smart agriculture at project intervention sites in each Partner State. | 0 | 2018/2019 reporting period: Regional training on how to facilitate project proposals has been scheduled by September and training at community level will be starting by October 2019. Funds have been transferred to Countries to implement this activity. 2019/2020 reporting period: Climate-smart agriculture practices have been documented in the draft stock take report of adaptation technologies that was produced in May 2020. Similarly, communities in Uganda, Tanzania, Rwanda and Burundi have identified climate-smart technologies to be implemented in their localities. These technologies have jointly been agreed upon between national and subnational teams, communities and LVBC project team. However, no climate smart agriculture have been implemented in any of the project sites. These activities are scheduled to to be implemented starting Q3 of 2020 after they are assessed/reviewed using a criteria that was developed during the stocktaking exercise. | At least 200 hectares of climate-smart agriculture at project intervention sites in each Partner State (1000 hectares in total).
| Number of hectares of land restored using an EbA approach at project intervention sites in each Partner State. | 0 | 2018/2019 reporting period: Regional training on how to facilitate, approve project proposals for funding has been scheduled by September and training at community level will be starting by October 2019. Funds have been transferred to Countries to implement this activity. 2019/2020 reporting period: EbA practices have been documented in the draft stocktake report of adaptation technologies that was produced in May 2020. Similarly, communities in Uganda, Tanzania, Rwanda and Burundi have identified EbA technologies to be implemented in their localities. These technologies have jointly been agreed upon between national and subnational teams, communities and LVBC project team. However, these technologies are scheduled to be implemented starting Q3 of 2020 after they are assessed/reviewed using a criteria that was developed during the stocktaking exercise. | At least 100 hectares of hectares of land restored using an EbA approach at project intervention sites in each Partner State (500 hectares in total).
Outcome 4. Indicator | Number of beneficiaries of small-scale community-based projects. | 0 | 2018/2019 reporting period: Regional training on how to facilitate, approve project proposals for funding has been scheduled by September and training at community level will be starting by October 2019. Funds will be transferred to Countries to implement this activity by December 2019. 2019/2020 reporting period: In Burundi, Rwanda, Tanzania and Uganda communities that will implement small-scale community based projects have been agreed upon. In Tanzania, 200 (108 women and 92 men) beneficiaries of the small scale community based projects have been selected. | At least 1000 people (200 per intervention site) benefit from small-scale community-based projects
Output 4.1. Indicator | Number of small-scale projects that promote innovative approaches to climate change sites funded at intervention in each Partner State. | 0 | 2018/2019 reporting period: Regional training on how to facilitate, approve project proposals for funding has been scheduled by September and training at community level will be starting by October 2019. Funds will be transferred to Countries to implement this activity by December 2019. 2019/2020 reporting period: In Burundi, Tanzania, Rwanda and Uganda, preliminary meetings have been held between local communities, National and Subnational Project Teams as well as LVBC in order to agree on the probable community based adaptation interventions. Additionally, in Uganda and Rwanda training targeting community groups and selected local NGOs in project sites on development of small-scale proposals, administrative and financial management of community-based small-scale projects, as well as self-monitoring and evaluation by communities have been conducted. In Tanzania and Uganda, 228 community members (118 female and 110 male) and 295 community members (165male and 130 female) participated in the training respectively. A template to guide in the development of small scale community based adaptation projects has also been developed and shared with national project teams for onward transmission to the community based groups in project sites interested in applying for project grants. | At least 4 small-scale projects Number of small-scale projects that promote innovative approaches to climate change sites funded at intervention in each Partner State.
Outcome 5. Indicator | No. of news outlets in the local press and media that have covered climate change adaptation in relation to transboundary water catchment management in the LVB. | 0 | 2018/2019 reporting period: 3 regional TV stations covered project implementation (climate change adaptation) 2019/2020 reporting period: A video documenting the baseline status of selected project sites in Burundi was produced in Q3 of 2019. This video has been widely circulated in the social media channels. | At least 15 news outlets in the local press and media that have covered climate change adaptation in relation to transboundary water catchment management in the LVB.
Output 5.1. Indicator | Establishment of a research forum for the LVB. | Climate change research is not coordinated across the LVB and takes place in isolation | 2018/2019 reporting period: 1 established for regional and national climate institutions 2019/2020 reporting period: Efforts to establish a research forum for the LVB have been initiated with Burundi and Tanzania having selected one research institution in each country to lead in knowledge management and learning. Tanzania has selected Tanzania Agricultural Research Institute Ukiriguru, Mwanza while Burundi has selected Burundian Office in Charge of Environmental Protection (OBPE). Kenya, Rwanda and Uganda are yet to select research institutions to spearhead knowledge management and learning. Selected institutions will form a research forum for the LVB. | One research forum for the LVB established.
Output 5.2. Indicator | Number of exhibitions to showcase the successful regional and community-based approaches to climate change adaptation demonstrated through the project. | Several projects, including PREPARED, have undertaken awareness-raising activities within the LVB. However, none of these awareness raising activities have included exhibitions to showcase regional and community-based climate change adaptation interventions. | 2018/2019 reporting period: 3 (One through International Environment day, two (2) UN and two (2) universities) exhibitions showcased regionally identified climate change issues, vulnerable areas and communities; and project intervention areas and expected activities and outcomes. 2019/2020 reporting period: LVBC staff participated in two exhibitions to showcase the successful regional and community-based approaches to climate change adaptation. These exhibitions are Mara River Day which was held in Mara Region of Tanzania and UNFCCC COP 25 meeting which was held in Mara region of Tanzania on 15th September 2019 as well as UNFCCC COP 25 which was held in Madrid Spain during the month of December 2019. | At least 2 exhibitions to showcase the successful regional and community-based approaches to climate change adaptation demonstrated through the project.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Joint planning and regular consultations between LVBC and national project teams is an important ingredient in ensuring realistic planning and implementation of project activities. Close collaboration and extensive engagement with key decision - and policy makers of partner states has also helped to unlock key challenges/bottlenecks affecting project implementation. In view of the corona virus (COVID-19) pandemic that has forced countries to impose travel restrictions, lockdowns and social distancing measures, majority of project activities scheduled for part of Q1 and Q2 of 2020 had to be postponed/ delayed. To mitigate this emerging issue, project teams at LVBC and partner states have put in place measures that help to facilitate implementation of project activities. These measures include leveraging on technology to hold virtual meetings, undertaking activities that do not necessarily require extensive traveling e.g. finalization of stocktaking of existing adaptation technologies through desktop review of existing literature and virtual interviews. During the reporting period, seasonal variability such as the recent high and intense precipitation in the East African region since August 2019 has resulted to a rapid rise in the Lake Victoria’s water levels by 13.4metres, mark last recorded in 1964. The heavy rains have also caused the waters of major rivers draining into Lake Victoria to reach peak levels thus breaking the banks and causing major flooding in the region. This has had devastating impacts which include displacement of a large number of people, destruction of the properties, infrastructure, agricultural lands, crops, and in extreme cases resulted in fatalities of humans and livestock. Due to this some of the project sites were inaccessible e.g. along river Simiyu in Ng'haya village of Magu District. To address this, the project is working closely with local communities and subnational and national stakeholders during the selection of project sites. Additionally, the project is working closely with meteorological institutions of partners’ states and IGAD Climate Prediction and Applications Centre (ICPAC) to deliver subnational climate information that can inform planning and implementation of project activities. A lessons learnt in the process of conceptualization and development of unidentified sub-projects (USPs), was the importance community training on future climate projections and actively engaged in the entire process in order to ensure that proposed interventions are aligned to their aspitations and adaptation needs in the face of current and future/projected changes in climate. As a result, targeted beneciaries are able to propose practical adaptation solutions that balance between short-, medium- and long-term adaptation needs. A training on the proposal development, financial management as well as monitoring was important. Similarly, allowing subnational project teams to spearhead development of USPs was important in order to ensure inclusivity and equal accessibility to the call for proposals to all local CBOs and NGOs. Going forward, LVBC intends to develop a project contingency plan in consultation with UNEP and partner states in the LVB in order to put in place robust measures that will mitigate the aforementioned issues affecting project implementation.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Aligning project planning (workplan & budget) to UNEP, regional (EAC) and National (partner states) planning processes: Aligning ACC-LVB project planning to UNEP, regional (EAC) and National (respective partner states) planning processes is a complex affair that at times results to lengthy delays in workplan and budget approval processes before financial resources can be utilized. For example, In Rwanda and Tanzania, LVBC disbursed project funds to them when their 2019/2020 national budgets had already been approved. Due to this, the national project teams in Rwanda and Tanzania couldn’t access and utilize the funds until ACC-LVB project funds were included and approved for utilization in national supplementary budgets that took place in January/February 2020. This caused delays in execution of project activities for almost 3-4 months in these countries. Going forward, the national project teams agreed to submit the financial projections of this project on time to their ministry of finance for the project funds to be included during the national budget making processes of their respective countries. To address the delays, strategic meetings were also held between LVBC and UN Environment in November 2019 and in January 2020 in order to develop strategies for fast-tracking implementation of project activities.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | During the reporting period of 2018/2019, the project established coordination team in each countries and build capacity on the same. The project also facilitated the countries to come up with strategies to project is successfully implemented. These strategies included: (a) regional criteria for site selection were developed and agreed with all countries (b) Memorandum of Understanding which stipulate how project will be implemented Between Lake Victoria Basin Commission and Countries were developed and signed before disbursing project funds (c) ToRs for Adaption, Watershed, Modeling and Communication consultants were developed and approved to ensure good quality consultants to support project activities (d) In each project site team of extension officers were identified to support project implementation. Capacity building will be provided by aforesaid Consultants; and (e) to compensate the time lost, now component three and four are implemented together. In addition to the above strategies, LVBC project team has actively provided capacity building initiatives to the national and subnational project teams to enhance the planning and implementation processes during this reporting period. This was coupled by frequent field visits and virtual meetings in order monitor progress in the implementation of project activities, discuss on strategies for fast-tracking implementation of project activities and for addressing bottlenecks facing the project. As a result, project teams in Rwanda, Uganda and Tanzania have laid the ground work for the implementation of on the ground activities that are due to start in Q3 of 2020. In Burundi, on the ground activities have been implemented with significant milestones/targets having been achieved. Additionally, instead of hiring a climate modelling consultant, LVBC will now engage IGAD Climate Prediction and Application Center (ICPAC) which is an institution responsible for delivering climate services to Eastern Africa. ICPAC will therefore support in climate modelling and downscaling of regional climate information to the national and local levels in order to ensure availability of accurately and timely climate data and information in the Lake Victoria Basin. Similarly, instead of hiring a communication expert, LVBC and UNEP communication experts will henceforth support project communication needs.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | An updated ESMP monitoring template was recently shared with National Project teams in partners states in order to monitor ESP safeguard measures during implementation of on the ground activities that have been initiated. Similarly, National Project Teams have been tasked to identify and propose mitigation measures for all USPs. So far, no major ESP risks have been reported.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender considerations were taken into account where strategies were put in place in order to ensure active participation of both women and men during the implementation of the project activities. So far, an increase in the number of women participating in decision making processes and capacity building initiatives supported by the project has been recorded.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A
What measures are being/could have been put in place to improve project/program results? | N/A
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | N/A
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | N/A
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | N/A
If learning objectives have been established, have they been met? Please describe. | N/A
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | N/A
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization. | N/A
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | UN Environment
Type of implementing entity | MIE
Country
Region | Africa
Sector | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total |  | 1780 |  | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 2: Partially effective | Total | 25 | Drought | 5: Very effective | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Water management | Regional | 3: Risk and vulnterability assessments completed or updated | 3 | Water management | Regional | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Regional | 1 | 1: Risk knowledge | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 9 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Regional | 1 | 3: Dissemination and communication | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 9 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 4: Response capability | Geographical coverage | Regional | 1 | 4: Response capability | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 9 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | National | 1 | 2: Monitoring and warning service | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 9 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 20 | Water management | 2: Low capacity | Total | 125 | Water management | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 40% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 25 | 50% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Water management | 2: Low capacity | Public | Regional | Water management | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Water management |  | 100% |  | Water management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 1500 | 50% | 2: Partially not aware |  | 1500 | 50% | 5: Fully aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Regional | 3: Moderately responsive (Some defined elements) |  | Water management | Regional | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Water management | 3 | Community |  | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Water management | land | 5: Very effective |  | Water management | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 50 | ha rehabilitated | 2: Partially effective | Cultivated land/Agricultural land | 1000 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 100 | ha rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 500 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 1500 |  | 2: Limited improvement |  | 1500 | 50% | 5: Very high improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 3 | Adaptation strategies | Multi-sector | Capacity development | 3 | Adaptation strategies | Water management | Capacity development
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 1500 | Agricultural-related |  | 400 | 1500 | Agricultural-related |  | 500
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Nature-based solutions | Regional | Innovation replicated |  | Nature-based solutions | Regional | Innovation replicated
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness