## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 24 October 2021 - 23 October 2022
| Project Title: | Increasing the climate change resilience of communities in Eastern Ghouta in rural Damascus to water scarcity challenges through Integrated Natural Resource Management and immediate adaptation interventions
| Project Summary: | The Syrian Arab Republic is highly vulnerable to the effects of global warming and climate change in its various dimensions. This is manifested in various climatic phenomena, but alarming are the increasing temperatures and droughts, already in the short term, and projected reduction of precipitation, mainly in the long term. The effects of these climatic phenomena impact all social and economic sectors and represent a threat to livelihoods, agricultural productivity, water availability and community health. The crisis has exacerbated these threats, since it led to a weak and deteriorating adaptive capacity resulted from damaged infrastructure, limited institutional capacity, rapid resettlement of displaced people, returnees and high level of poverty. This project aims to reduce vulnerabilities to water availability challenges in one of the most vulnerable areas in Syria: Eastern Ghouta. To manage water and land resources efficiently, also considering future climate change risks and population trends in this area, an integrated natural resource management strategy will be developed. Complementing the strategy, the proposed project will directly build the resilience of selected communities though the implementation of concrete no-regret adaptation activities including the treatment of wastewater which is currently polluting water resources in the area and the establishment of water efficient irrigation systems Project Component 1: Integrated natural Resource Management to cope with climate change and crisis related water challenges Project Component 2: Establishment of efficient, sustainable and climate change resilient water supply systems for urban and agriculture purposes Project Component 3: Establishment of efficient, sustainable and climate change resilient irrigation systems and agriculture practices and security of income
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | SYR/MIE/Water/2019/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Human Settlements Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Syria | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Eastern Ghouta (Maliha, Zibdeen , Deir Alasafie and Marj Alsultan) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 02-Jun-21 (Board Decision Decision B.36/8)
IE-AFB Agreement Signature Date: |  | 2021-07-14 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2021-10-24 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
| Original Completion Date: | 2025-04-23
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | 1) Inception report submitted on 23 Nov 2021, Within one month after the inception workshop on 24 October 2021, an Inception Report. Reports will included: (i) agreement on organizational structure of the project, including roles and responsibilities (i.e. ToR PSC and PAC); (ii) 1st year work plan; (iii) project baseline and monitoring and reporting framework; (iv) project risks management framework; (v) Environmental and social Risks Management Framework / Plan; (vi) knowledge management, advocay & communication framework and work plan; | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Hiroshi Takabayashi | Dominican Republic
| Email: | hiroshi.takabayashi@un.org | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Rawan Alazem | Equatoral Guinea
| Email: | rawanalazem@hotmail.com | Eritrea
| Date: |  | Estonia
| Name: | Rouida Nahar
| Email: | rouidanahar@gmail.com
Date:
| Implementing Entity |  | Ethiopia
| Name: | Hiroshi Tabayashi | Fiji
| Email: | hiroshi.takabayashi@un.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | UNHabitat - Tamara Tamzok | Georgia
| Email: | tamara.tamzok@un.org | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | UNDP - Abir Zeno | Grenada
| Email: | abir.zeno@undp.org | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | FAO - Mohamad Amer Jnedan | Guyana
| Email: | Mohamad.Jnedan@fao.org | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 23 October 2022 |  |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 23 October 2022 |  | 1130522.96 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) |  | The above amount represents the first instalment of AF fund, that includes the implementing partners parts and the relative PSC |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME |  | 33.68 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| ` | 1.1. Inception workshop and coordination mechanism | 135802.76
|  | 1.2. Capacity strengthening package | 66645.08
|  | 1.3. Detailed hydrogeological study, CC VA and future outlook for the region | 261787.44
|  | 1.4. Gaps analyses and recommendations for managing water and land | 0
|  | 1.5. INRM Strategy and action plan (with CC mainstreamed) | 0
|  | 1.6. M & E plan for above + replication mechanism | 16998.35
|  | 1.7. Formal adoption of strategy document | 0
|  | 2.1 Assessment and verification / technical specification and engineering studies, including surveys required for detailed design of below interventions | 27233.36
|  | 2.2 Rehabilitated sewage network to divert wastewater towards the WWTPs (concrete intervention) | 301444.55
|  | 2.3 Installed mobile wastewater treatment plants to use non-conventional water resources identified (concrete intervention) | 0
|  | 2.4 Rehabilitated irrigation canals to divert treated water for irrigation purposed (concrete intervention) | 101.75
|  | 3.1. Studies and assessments to detail the proposed interventions | 59176
|  | 3.2. Introduction of water efficient agricultural technology | 31032
|  | 3.3. Adoption of climate-smart agriculture practices for improved soil fertility and enhanced water use efficiency | 9822
|  | 3.4. Promote sustainable livelihood opportunity through crop residuals management and support to rural women | 4911
|  | Project execution | 153056.8
|  | Project cycle management | 62511.87
|  | TOTAL | 1130522.96 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
|  | 1.1. Inception workshop and coordination mechanism | 40261.24 | 2023-10-23
|  | 1.2. Capacity strengthening package | 59418.92 | 2023-10-23
|  | 1.3. Detailed hydrogeological study, CC VA and future outlook for the region | 355576.56 | 2023-10-23
|  | 1.4. Gaps analyses and recommendations for managing water and land | 81000 | 2023-10-23
|  | 1.5. INRM Strategy and action plan (with CC mainstreamed) | 227564 | 2023-10-23
|  | 1.6. M & E plan for above + replication mechanism | 102341.65 | 2023-10-23
|  | 1.7. Formal adoption of strategy document | 93400 | 2023-10-23
|  | 2.1 Assessment and verification / technical specification and engineering studies, including surveys required for detailed design of below interventions | 76766.64 | 2023-10-23
|  | 2.2 Rehabilitated sewage network to divert wastewater towards the WWTPs (concrete intervention) | 13571.9533 | 2023-10-23
|  | 2.3 Installed mobile wastewater treatment plants to use non-conventional water resources identified (concrete intervention) | 3655921.2105 | 2023-10-23
|  | 2.4 Rehabilitated irrigation canals to divert treated water for irrigation purposed (concrete intervention) | 106952.243 | 2023-10-23
|  | 3.1. Studies and assessments to detail the proposed interventions | 75177 | 2023-10-23
|  | 3.2. Introduction of water efficient agricultural technology | 799646 | 2023-10-23
|  | 3.3. Adoption of climate-smart agriculture practices for improved soil fertility and enhanced water use efficiency | 670151 | 2023-10-23
|  | 3.4. Promote sustainable livelihood opportunity through crop residuals management and support to rural women | 139420 | 2023-10-23
|  | Project execution | 137649.2 | 2023-10-23
|  | Project cycle management | 470688.8047 | 2023-10-23
|  | TOTAL | 7105506.4215 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[9 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[9 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[9 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[9 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
1. Delay of project start-up because critical staff is not in place and / or lengthy contracting process, incl. negotiations with execution entities | Likelihood (1) X Impact (3): very low risk The project has been initiated immediately after organizing the inception workshop in 24 Oct 2021. Contracting both EE has been finalized timely (i.e. UNH/UNDP on March 2022 and UNH/FAO on Dec 2021). | 1.1. UN-Habitat appointed critical staff at UN-H ROAS and Syria CO immediately after signing the project agreement between UN-Habitat and the AF secretary. The process of contracting EE was initiated immediately after the inception workshop; - a dedicated focal point from each EE and IE was appointed to prioritize this task as very urgent and important - the 3 UN HoAs provided direct support to expedite negotiations and obtain due clearances from HQs and regional offices.
2. Loss of government support (at ministerial and municipal level) for the project and activities because of elections and related functions of the project steering committee, which may result in lack of prioritization of AF project activities or different pace of execution of activities | Likelihood (1) X Impact (3): Low risk PSC and PAC members from three keyline ministries, heads of municipalities and EEs and their roles/responsibilities identified and approved within inception workshop and report. Positions of national stakeholders for PSC and PAC membership are also identified in case of changing names and employees. The project coordinator from the national side is appointed i.e. directorate of ESCC at MoLAE. | 2.1. MoLAE released a decree for naming PSC and PAC members as per the agreed roles and responsibilities. 2.2. MoLAE appointed head of PSC, head of PAC, Head of ESCCU and coordinator. 2.3. Detailed ToRs for PSC and PAC and the coordinator were prepared/discussed with keyline ministries and then approved duly 2.4. High-level representatives (e.g. ministers, deputy ministers and directors) from keyline ministries were invited and participated in major events and workshops with local communities.
3. A lack of coordination between and within national government Ministries and Departments and municipalities | Likelihood (2) X Impact (3): Medium risk some coordination issues appeared owing to unintentional misunderstanding of the roles/responsibilities causing some delays until got solved. | In addition to above, 3.1. IE jointly with EEs re-illustrated and discussed the project governing structure in depth with relevant PSC and PAC members. Some minor updates and major clarifications were made/shared accordingly with all stakeholders to ensure smooth implementation and engagement and to avoid any potential conflict of interest. Clarified project governance structure were prepared to ensure that roles and responsibilities are well addressed and clarified Please see annex #02 3.2. Regular meetings with PAC and PSC members took place to ensure better coordination and information sharing.
4. Capacity constraints of executing entities, local institutions, communities and the private sector may limit the effective implementation of interventions | Likelihood (1) X Impact (3): Low risk The 3 EEs have appointed qualified technical teams and project managers to ensure effective implementation. UN-Habitat as IE has assigned special project staff with various expertise in natural resource management, climate change, technical design, M&E, ESMP and safeguards (i.e. SVN) to ensure quality control at for all component in coordination with UNDP and FAO. | 4.1. As for local institutions and communities, EEs are developing concrete-training programs with a clear timeframe for all relevant topics and aspects are tailored for proper capacity and resilience building, to ensure the sustainability of the interventions (such as proper operation, monitoring and maintenance), and to disseminate/replicate the activities at the community and national levels. Examples are available upon request.
5. Communities may not adopt activities during or after the AF project, including infrastructure maintenance | Likelihood (2) X Impact (4): High risk Field Implementation in term of inputs and assets distribution and operation has not been initiated yet. | 5.1. A complete participatory approach with target communities (e.g. focus-group discussion and technical working group) was applied during fine-tuning interventions’ designs to ensure the suitability of interventions at various levels i.e. economic, social, environmental, and operational. Moreover, project stakeholders were involved in the preparation of assessment tools and conducting the assessment to ensure better understating and as part of capacity-building programs. 5.2. For the sustainability of the interventions, please see above the training and capacity building programs, which will include practical training sessions and demonstrations and FFS (learning by doing)
6. Complexity of financial management and procurement. Certain administrative processes could delay the project execution or could lack integrity or needed capacity | Likelihood (2) X Impact (2): Low risk Heavy procurement and financials (PO issuance, service providers contracting) not yet started. | 6.1. Financial management based on the UNCT and individual UN EE procurement policies and procedures will be strictly applied and documented so that timely evidence can be reported duly.
7. Inflation and instability of the national currency leading to budget issues and increased prices for infrastructure delivery | Likelihood (3) X Impact (2): Medium risk costs of different material increased since the startup of the project locally and internationally At the local level the difference between the official and the market SYP to USD rates increased during project Year-1 (Official rate increased only from 2500 to 3000 SYP per USD whereas the market rate increased from 3400 to 5200 SYP per USD). At the international level, the cost of material and shipment increased too especially after the Ukraine crises. | 7.1. All budget lines of the contracts and procurements will be in US$, however, for local procurement the costs increased moderately due to big differences between official and market rates. In additional, local fuel price significantly increases. An adjustment was made to the implementation methodology of some activities to overcome the high cost of fuel and ensure meeting the target. 7.2. Some targets may need to be adjusted due to cost increments by shipment and price hikes of items.
8. Political instability in the target localities inhibits movement and access to target areas | Likelihood (1) X Impact (3): Medium risk As per the UNDSS, the target area is categorized as stable and far away from other unstable areas. | 8.1. field staff were sub-contracted by 3 EEs for daily works in target areas during Year-1, 8.2. Some of the field staff are from the target areas which facilitates accessibility, 8.3. The 3 EEs monitor the situation in the target areas continuously with UNDSS and GoS entities for any potential risk or security event.
9. Poor weather conditions (especially in winter) affect implementation of activities | Likelihood (2) X Impact (1): Low risk So far, there has been no abnormal weather conditions hence, no effect on implementation. | 9.1. Work plans designed to avoid conducting critical field works during winter pick time when severe weather conditions are expected.
10. Covid-19 spread, leading to inaccessibility of target area and / or delays of project activities | Likelihood (2) X Impact (2): Low risk The COVID protective measures applied by GoS were removed gradually in coincident with the project inception phase. | 10.1 The 3 EEs are continuously monitoring the status of COVID and guidelines of GoS and WHO and UNDSS. 10.2 When needed, emergence plan for online or remote monitoring of the activities implementation and follow up can be activated.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Delays in contracting for some project activities because of long procurement process might affect the implementation timeframe and schedule of activities. | Likelihood (1) X Impact (3): Low risk | EEs ensured continuous follow-up on all procurement process steps and workplan adjusted to ensure the delivery of project activities before the end date. Please check the updated workplan under the annex #05
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Potential low risk of non-compliance with laws/standards | Include standard clause in MoU / all contract with reference to laws / standards | Review MoUs, all contracts | All signed MoUs/ contracts were reviewed and standard clauses inserted with reference to relevant laws and standards | As low potential risk exists with project-based subcontractors meeting project requirements during project execution including primarily meeting worker health and safety requirements. Executing entities ensured to include all necessary legal clauses and requirements in project-based contracts and agreements with monitoring of performance during execution. | No residual impact remain as of October 2022 regarding this risk | NA
2 - Access and equity |  |  | NA | NA | NA | NA | NA | NA | NA
3 – Marginalized and vulnerable Groups |  |  | Specific needs, limitation and constraints of target groups may not be fully identified / up to date when project commences | All beneficiary groups consulted again during the inception phase to verify and further identify all specific needs, limitations and constraints. Related to that the ESMF/P will be updated. | Check consultation reports with latest data on identified specific needs, limitation and constraints of beneficiary groups; updated ESMF/P | No specific needs, constraints identified for Target population: T: 81,700 W: 50-60% Y: 32-37 % F: 30-95% | Community consultations workshop, area-based assessment workshops and focus group discussions have been conducted to identify specific needs, limitations, constraints/concerns | Not all specific needs, limitations, constraints/concerns may have been captured specificly at regional level | To conduct more consultations/ and regional workshops focusing on each activity to identify more specific needs, limitations, constraints/concerns
4 – Human rights |  |  | NA | NA | NA | NA | NA | NA | NA
5 – Gender equality and women’s empowerment |  |  | Potential low risk related to limited awareness of gender approach and baseline | Share information on gender policies and approach and baseline with project actors | Keep minutes of consultation meetings and review of grievance register Number of grievances | Target number for the participation of women/youth in workshops | To ensure gender equity both men and women participated in the project Inception workshops and the IE encouraged and followed up the project executing entities to hold gender consultations and assessments. women were involved in the workshops/training and consultation meetings to participate in the assessments and highlight their needs in light of climate change. Minutes of the meeting prepared also, A gender-disaggregated database for workshops and consultations was developed and has been regularly updated to monitor the participation and gender disparity during the project implementation. Please check the stakeholder engagement database under annex #06 | lack of women/youth participation | To conduct more focus group discussions with women and youth, and ensure inviting more women to the workshops.
6 – Core labour rights |  |  | Potential low risk of non-involvement of local employment, non-local procurement, non-compliance worker rights and limited facilities | Include measures to maximise local employment and procurement, include standard clauses in all MoUs and contracts on worker rights and have Contractor provide or facilitate access to facilities | Review of local procurement and employment records; workers grievance mechanism in place, review of grievance register; and appropriate H&S and sanitary facilities provided Number of worker grievances” which can be monitored throughout the project lifecycle | NA | Standard clauses were included in initiated implementation contract | NA | NA
7 – Indigenous peoples |  |  | NA | NA | NA | NA | NA | NA | NA
8 – Involuntary resettlement |  |  | NA | NA | NA | NA | NA | NA | NA
9 – Protection of natural habitats |  |  | NA | NA | NA | NA | NA | NA | NA
10 – Conservation of biological diversity |  |  | NA | NA | NA | NA | NA | NA | NA
11 – Climate change |  |  | Potential low risk of increased GHG Emissions due to Project Emissions (such as from WWTP and pumping) | Exact project-related energy use to be determined during project inception phase and where feasible, ‘extra’ energy use to be compensated through installation of solar PV | Recording, monitoring and review of energy use | Not applicable at this stage of the project measurement of energy use that can be used will be calculated when the WWTP is functional | One rehabilitation work started ( sewerage system) and machinery energy use is being monitored, noting that this is a temporary impact and just for rehabilitation, and the system will be functioning depending on gravity with no need for energy. MOLAE also participated to mitigate the risk of increased GHG Emissions by installing solar lightning in project target are (25 lightening systems in each municipality) | likelihood of increased GHG Emissions due to Project Emissions (such as operating WWTP) | Exact project-related energy use to be determined. Extra’ energy use is to be compensated through the installation of solar systems for boreholes.
12 – Pollution prevention and resource efficiency |  |  | Potential low risk of lack of waste management procedure | A Waste Management Procedure / plan will be developed | Regular site inspections | Not applicable at this stage of the project | Appropriate waste management practices were applied were possible such as recycling / reusing excavation results to refill the trenches during the rehabilitation of the sewerage system. | very low risk of lack of waste management procedure | A waste and residual management plan will be developed to ensure the safe disposal of all residuals that will be generated during the implementation and will be included as a requirement in the general condition of the contract. The supervisory team will monitor and submit a regular report on the action taken to ensure compliance.
13 – Public health |  |  | Potential low risks related to Security incidents; Occupational Health and Safety Increase in Social Tension due to Contractor-Community Interactions and Security Increase in Vector Borne and Communicable Diseases Limited emergency Response Local Capacity and Equipment Workplace health and safety incidents Interaction with security actors Stolen Items; Covid-19 | Mitigations include ensure health and safety procedure prior to construction that establishes procedures and development of: • Occupational Health and safety Plan • Worker Code of Conduct/Training • Vector Borne and Communicable Diseases Procedure • Stakeholder Engagement Plan and Grievance Management System • Emergency Preparedness and Response Procedure • Security and Human Rights Management Procedure • Covid-19 Protocol | Occupational Health and Safety Plan reviewed and in place - Regular monitoring and random site inspection to ensure OHSP and other procedures are being implemented - Review of Code of Conduct induction records (signed) - Review of meeting minutes, grievance register, and number of grievances | Monitoring indicators can include: -Occupational Health and Safety Plan reviewed and in place - Regular monitoring and random site inspection to ensure OHSP and other procedures are being implemented - Review of Code of Conduct induction records (signed) - Review of meeting minutes, grievance register, and number of grievances | Health and safety procedures prior to construction are ensured by such as UXO clearance and transportation of goods clearance from security agencies. Worker code of conduct was included in all signed contracts during the reporting period. All staff involved in project implementation carried out SSAFE training Health and safety procedures were considered during regular monitoring field visits Stakeholder engagement monitoring tools and grievance management mechanisms were developed and applied during the reporting period. COVID-19 mitigation measures were applied in meetings and workshops: distribution of PPEs ( masks and sanitizers), and ensuring workplaces and surfaces are clean and hygienic) When contracts are signed, all contractors are ensured to follow the UN Code of Conduct which includes principles health and safety (such as: (a) the workplaces, machinery, equipment and processes under their control are safe and without risk to health; (b) the chemical, physical and biological substances and agents under their control are without risk to health when the appropriate measures of protection are taken; and (c) where necessary, adequate protective clothing and protective equipment are provided to prevent, so far as is reasonably practicable, risk of accidents or of adverse effects to health.) | There might be residual UXOs not detected standard Claude for Human rights and | Awareness-raising sessions on unexploded ordnance procedures will be conducted for all workers. Awareness raising on Vector Borne and Communicable Diseases Procedures to b carried out
14 – Physical and cultural heritage |  |  | Potential low risk of chance finds | A Chance Finds Procedure must be developed and requires: • Stop work in the event of a find and cordon off until next steps are agreed • Identify relevant national authority for communication in the event of a chance find • In the event of a find, prepare Next-step Action Plan (if required) • Liaise with Competent Authority to arrange oversight of the excavation works and storage and transportation of any finds | Site inspection | NA | Chance find procedures were considered to be applied if any chance was found. | the potencial risk remains | relevant procedures will be applied
15 – Lands and soil conservation |  |  | NA | NA | NA | NA | NA | NA | NA
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | IE conducted the required arrangements to supervise executing entities for the implementation of ESMF/P Regular monitoring of the progress of activities is carried out to ensure that all activities during the implementation will comply with the ESMP in addition to the above the IE conducted awareness on requirements and shared guidelines with execution entities to comply and to ensure ‘opportunities’ are identified and exploited. The project managers and focal points' phone numbers and email addresses were shared to receive any additional comments or grievances.
Have the implementation arrangements been effective during the reporting period? |  | The implementation arrangements have been effective
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Ensure that all activities for implementation are compliant with the ESMF/P Executing Entity (UNDP) ensured to implement of the ESMF/P during the reporting period: the design of the activity of sewerage system rehabilitation was done with respect to stakeholder engagement, Also, the design of WWTP is being prepared in consultation with project stakeholders in the targeted municipalities. In addition to ensuring project grievance management and monitoring of implemented activities, the project management/ focal point phone number and email address were shared with project stakeholders to receive any additional comments. Executing Entity (FAO) ensured the implementation of the ESMF/P during the reporting period: the selection process of the Ground Wells to be rehabilitated was done with full respect to stakeholder and local communities engagement and after several consultation meetings and field visits. Also, identification of what type of Quality/quantity water monitoring systems and climate station was made in organizing Technical Working Groups with relevant technicians from related ministries. The project management/ focal point phone number and email address were shared with project stakeholders to receive any additional comments. Similarly, the identification of Mother fruit trees for the saplings production as well as the crop' varieties for crop rotation and intercropping systems were made taking in account farmers' preference and opinions in addition to the outcomes of the TWG with GCSAR experts interm of the most drought-tolerant, most-adaptive, high-yielding varieties.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The implementation arrangements have been effective
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8] |  | NA
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
To date no grievances have been received.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No
Yes
No
Yes
No

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Capacity building for women to develop, implement and update INRM strategy in which climate change is mainstreamed | Outcome 1 | No. of women national-level staff with capacity increased No of municipal-level staff with capacity increased | 0 | 40% of 20 20% od 40 | N/A - to be completed in the mid-term as per project results framework
Women awarness raising | Outcome 1 | Percentage of women from directly targeted population aware of predicted adverse impacts of climate change, and of appropriate responses | 0 | Mid-20%; end 50% Mid-20%; end 50% Mid-10%; end 20% | N/A - to be completed in the mid-term as per project results framework
Women training, participation in workshops | Output 1.1 | No. of women staff trained / participated in workshops | 0 | 40 % of 40 | N/A - to be completed in the mid-term as per project results framework
Women training, participation in workshops | Output 1.2 | No. of women staff trained / participated in workshops | 0 | 40% of 200 | N/A - to be completed in the mid-term as per project results framework
Capacity building for women national and municipal government staff to operate, maintain and sustain the WWTP and related sewerage and irrigation network. | Outcome 2 | No. of women national-level staff with capacity increased No of Women municipal-level staff with capacity increased | 0 | 30 % of 15 30% of 15 | N/ A to be completed for the third year PPR
Awarness raising of predicted adverse impacts of climate change, and of appropriate responses under component 2 | Outcome 2 | Percentage of women from directly targeted population aware of predicted adverse impacts of climate change, and of appropriate responses under this component | 0 | Mid-20%; end 50% Mid-15%; end 30% Mid-05%; end 15% | N/ A to be completed in the Mid term Review as per result framework
Women training to operate, maintain and sustain the WWTPs | Output 2.3 | No. of women staff trained to operate, maintain and sustain the WWTPs | 0 | 30% of 30 | N/ A to be completed for the third year PPR
Women capacity building to o operate, maintain and sustain/replicate the agriculture technology, smart applications and alternative livelihoods straightened | Outcome 3 | No. of women national-level staff with capacity increased No of women municipal-level staff with capacity increased | 0 | 30% of 20 20% of 40 | N/A for 1st PPR. To be reported on the 3rd PPR
Women awareness raising to of predicted adverse impacts of climate change, and of appropriate adaptive responses under component 3 | Outcome 3 | Percentage of women from population aware of predicted adverse impacts of climate change, and of appropriate adaptive responses under this component | 0 | Mid-20%; end 50% Mid-20%; end 50% Mid-10%; end 20% | N/A for 1st PPR. To be reported on the Mid term Review as per result framework
Women have more secure through access to climate change smart agriculture practices | Outcome 3 | Percentage of women-headed households and communities having more secure (i.e. increased income) through access to climate-smart agriculture practices/livelihoods | 0 | Mid-5%; end 15% Mid-5%; end 15% Mid-2%; end 8% | N/A for 1st PPR. To be reported on the Mid term Review as per result framework
Women training to operate, maintain and sustain / replicate the water efficient agriculture technology | Output 3.2 | No. of women staff and people trained to operate, maintain and sustain / replicate the water efficient agriculture technology | 0 | 30% (of 100) | N/A for 1st PPR. To be reported on the 2nd PPR
Women training to operate, maintain and sustain / replicate alternative livelihood opportunities | Output 3.3 | No. of women staff and people trained to operate, maintain and sustain / replicate climate smart agriculture practices | 0 | 30% (of 240) | N/A for 1st PPR. To be reported on the 2nd PPR
Women training to operate, maintain and sustain / replicate alternative livelihood opportunities | Output 3.4 | No. of women staff and people trained to operate, maintain and sustain / replicate alternative livelihood opportunities | 0 | 30% (of 900) | N/A for 1st PPR. To be reported on the 2nd PPR
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
N/A - to be completed for final PPR as per guidance. |  | N/A - to be completed for final PPR as per guidance.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Implementing Entity has made all necessary efforts to comply with the AF GP and with UN-Habitat M & E policies and guidelines. Project activities are monitored by the IE Syria project manager and dedicated monitoring staff, which have the expertise of M & E compliance to the AF Gender Policy, including gender equity, gender mainstreaming, gender responsiveness, gender sensitivity and women's empowerment. To ensure gender equity both men and women participated in the project Inception workshops and the IE encouraged and followed up the project executing entities to hold gender consultations and assessments.
Have the implementation arrangements at the IE been effective during the reporting period? |  | The arrangements made by the IE/EE have been effective. IE made sure to have all the arrangements in place during the preparation phase. furthermore, during the implementation, all necessary arrangements were carried out like tracking the gender indicators in all activities and ensuring women's involvement in the planning and design of project activities and aiming for equal participation of women in project activities.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | Component 1: To ensure gender considerations have been taken into account during the reporting period, the EE (UnHabitat) made sure that women were involved in the workshops/training and consultation meetings to participate in the assessments and highlight their needs in light of climate change. Allowing women's views to be better captured without being overshadowed by men is one of the reasons why IE held women's focus group consultations and assessments. Furthermore the EE (UNHabitat) carried out arrangements to comply with GP such as having focus group discussions for women, allowing women's views to be better captured without being overshadowed by men to highlight their needs in light of climate change. Please see the report under annex #01 Component 2: During the design of detailed interventions and assessments, UNDP ensured women's involvement in the consultation, technical thematic meetings, and assessments. Priorities, needs, and concerns of local women in the targeted area, regarding climate change impact, were discussed during the community consultation workshop and in the focus group discussion meeting organized in the interactive area-based asssessment workshop jointly with UN-Habitat and FAO. Component#3 by FAO: FAO is committed to its global policy for Gender equality. As Women, particularly in rural, have lower access to productive assets, tools, inputs, and resources and less opportunity to information, they are more vulnerable than other groups and much CC-affected especially in times of crisis. Therefore, FAO to ensure gender equality and empower women properly, certain arrangements have been taken at onset of the implementation phase such as 1) the composition of FAO Project Task Force is well represented by Women. 2) the sub-contracted field experts for field assessments conduction and communities consultations are also very well gender balanced. 3) Prioritize women with certain allocation/percentage out of the total number of beneficiaries for each activity and training course, 4) Women-headed households are top priority in all beneficiaries selection criteria, 5) design and implement specific activities for women empowerment through organizing special focus-group discussion for women.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Component #1 by UNHabitat: The implementation arrangements made by the EES have been effective during the reporting period. Component #2 by UNDP: The arrangement undertaken during the reporting period has been effective. Component#3 by FAO: Yes, so far the aforementioned arrangements are effective. FAO commit to taking additional arrangements whenever deem necessary at any implementation phase as Gender equality and mainstreaming is one of FAO’s key mandate to achieve food security, and adapt to and/or mitigate CC impacts.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented?
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances relating to gender matters have been received in the reporting period. |  | No grievances relating to gender matters have been received in the reporting period.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Integrated natural Resource Management to cope with climate change and crisis-related water challenges |  | Outcome 2 | Capacities and commitment of national and sub-national government institutions, communities and vulnerable groups to assess, plan and manage climate change-induced and post-crises water and land challenges have been strengthened and knowledge and lessons learned for replication collected and shared and integrated into strategies and regulations |  | During the reporting phase, good progress was achieved in the establishment of a horizontal and vertical coordination mechanism on water, land, climate change, and recovery supporting the operation of the Environment Safety and Climate Change technical Unit (ESCCU) in Eastern Ghoutato. To ensure the capacities and commitment of national and sub-national government institutions, communities, and vulnerable groups are increased, a detailed technical assessment for WASH-related infrastructure was conducted in a participatory manner with national municipal staff and the local communities. Furthermore, community consultation workshops and focus group discussions, and technical meetings are carried out to raise awareness, determine the gaps, identify the needs and prioritize interventions. Some delay was experienced in contracting the firm to develop the INRM strategy. The tender was announced and since one sole offer was received, the evaluation process needed specific approvals it is still under the evaluation phase. | MS
| Establishment of efficient, sustainable and climate change resilient water supply systems for urban and agriculture purposes |  | Outcome 4 | 2. Access to municipal and community-level efficient, sustainable and climate change resilient water supply systems for urban and agriculture purposes, using innovative and replicable techniques has increased trough: - Use of non-conventional water resources - Reduction of losses / leakages of wastewater and from canals / irrigation systems And capacities to operate, maintain and sustain these systems have been strengthened |  | A thorough consultation with relevant stakeholders and local communities were done to verify agree on the selected lines of sewage network, irrigation canals and the distribution canals for treated water. A detailed technical assessment and technical specification we prepared for the work of sewage rehabilitation and canal irrigation, procurement cases were advertised , contract for the sewage rehabilitation was signed and the work is initiated , the procurenmnet case related to the rehabilitation of irrigation canals is under evaluation. TOR for the preparation of the detailed technical specification of the wastewater treatment plant prepared and agreed on with relevant stakeholders, contract with technical consultancy signed , the preparation of the detailed technical specification and tender document for the installation of the mobile treatment plan is in progress. | MS
| Establishment of efficient, sustainable and climate change resilient irrigation systems and agriculture practices and security of income |  | Outcome 6 | Resilience of water-dependent livelihoods and security of income (through reduced water demand), especially for vulnerable groups has increased through: - Protection of water resources (and prevention of contamination of surface and groundwater resources / wells) - Raising water use efficiency, using high efficiency irrigation methods - Improved agricultural practices / climate-smart agriculture practices such as crop rotation, introduce drought tolerant crops and trees - Alternative or diversified livelihoods; And capacities to operate, maintain and sustain these systems/practices have been strengthened |  | During Project Year-1, the following has been achieved under Component#3 by FAO: Output1: By April 2022, All ToRs required for both field experts and the 9 assessments/studies have been prepared by project Task Force-PTF in coordination with national stakeholders then cleared by FAO regional office (RNE). Conduction of all assessments finalized within Sep 2022. However, assessments' data analysis/fine-tuning, and obtaining due clearances from RNE and PAC as well as reporting finalization will be all done in Nov-Dec 2022. Output2: TSs and BoQs for Qnt/Qlt water monitoring systems finalized in July 2022. Relevant ITB announced in July and offers’ technical evaluation then awarding for some devices were made in Sep 2022, whereas the rest items will be re-announced duly by Nov 2022, as the competitiveness criterion has not been met properly – only few offers received for some items. Land Laser Leveling Unit-LLLU: all requirements for assembling, types of training courses, selection criteria and other implementation arrangements are identified within Year-1. Accordingly, the Letter of Agreement-LoA with GCSAR (as FAO Implementing Partner) will be signing in Nov 2022. The participatory process for Ground Wells selection is on-going, extensive consultation with local communities and technical authorities were made in the last quarter of Year-1. Final list of GWs to be endorsed during Nov 2022 so that field designing and preparation of TSs can be finalized within 1st quarter of Year-2. In parallel with bids advertising, the establishment of Water Use Association-WUAs will take place. Output3: upon finalizing the Nursery rehabilitation assessment, the main rehabilitation requirements (including Mother fruit trees identification) were prioritized, reviewed and endorsed by PAC early in Nov 2022. Accordingly, FAO has initiated the designing and TSs preparation immediately. The plan to finalize nursery rehabilitation works is by Sep 2023. Similarly, for extension support and training program all have been pinpointed to be implemented in due course within 2023. Output4: As per Year-1 workplan, there is no implementation in the field for this output activities. However, TSs for Crushers and requirements of Farmer Field School-FFS identified within Year-1 and to be implemented starting Feb 2023. | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Hiroshi Tabayashi
| Email: | hiroshi.takabayashi@un.org
| Name: | UNHabitat - Tamara Tamzok
| Email: | tamara.tamzok@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project has made good progress in assigning dedicated project staff and in the areas of coordination and capacity building, in addition to the preparation of technical assessments, ToRs and technical specifications for project activities. On the other hand, some activities are being delayed due to: - A lot of consultation with project stakeholders was conducted to ensure the suitability and sustainability of the interventions. - Challenges related to procurement include a long procurement process and inflation rate increment.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Establishment of efficient, sustainable and climate change resilient water supply systems for urban and agriculture purposes |  | Outcome 4 | Access to municipal and community-level efficient, sustainable and climate change resilient water supply systems for urban and agriculture purposes, using innovative and replicable techniques has increased trough: - Use of non-conventional water resources - Reduction of losses / leakages of wastewater and from canals / irrigation systems And capacities to operate, maintain and sustain these systems have been strengthened |  | A thorough consultation with relevant stakeholders and local communities were done to verify agree on the selected lines of sewage network, irrigation canals and the distribution canals for treated water. A detailed technical assessment and technical specification we prepared for the work of sewage rehabilitation and canal irrigation, procurement cases were advertised , contract for the sewage rehabilitation was signed and the work is initiated , the procurenmnet case related to the rehabilitation of irrigation cans is under evaluation. TOR for the preparation of the detailed technical specification of the wastewater treatment plant prepared and agreed on with relevant stakeholders, contract with technical consultancy signed , the preparation of the detailed technical specification and tender document for the installation of the mobile treatment plan is in progress. | MS
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | UNDP - Abir Zeno
| Email: | abir.zeno@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
During the reporting year, the planned project activities under the three outputs are progressing on track to achieve most major relevant outputs with modest shortcoming despite of the delay of the startup of the activities and the followed long consultation and coordination process .
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | Establishment of efficient, sustainable and climate change resilient irrigation systems and agriculture practices and security of income |  | Outcome 6 | Resilience of water-dependent livelihoods and security of income (through reduced water demand), especially for vulnerable groups has increased through: - Protection of water resources (and prevention of contamination of surface and groundwater resources / wells) - Raising water use efficiency, using high efficiency irrigation methods - Improved agricultural practices / climate-smart agriculture practices such as crop rotation, introduce drought tolerant crops and trees - Alternative or diversified livelihoods; And capacities to operate, maintain and sustain these systems/practices have been strengthened |  | During Project Year-1, the following has been achieved under Component#3 by FAO: Output1: By April 2022, All ToRs required for both field experts and the 9 assessments/studies have been prepared by project Task Force-PTF in coordination with national stakeholders then cleared by FAO regional office (RNE). Conduction of all assessments finalized within Sep 2022. However, assessments' data analysis/fine-tuning, and obtaining due clearances from RNE and PAC as well as reporting finalization will be all done in Nov-Dec 2022. Output2: TSs and BoQs for Qnt/Qlt water monitoring systems finalized in July 2022. Relevant ITB announced in July and offers’ technical evaluation then awarding for some devices were made in Sep 2022, whereas the rest items will be re-announced duly by Nov 2022, as the competitiveness criterion has not been met properly – only few offers received for some items. Land Laser Leveling Unit-LLLU: all requirements for assembling, types of training courses, selection criteria and other implementation arrangements are identified within Year-1. Accordingly, the Letter of Agreement-LoA with GCSAR (as FAO Implementing Partner) will be signing in Nov 2022. The participatory process for Ground Wells selection is on-going, extensive consultation with local communities and technical authorities were made in the last quarter of Year-1. Final list of GWs to be endorsed during Nov 2022 so that field designing and preparation of TSs can be finalized within 1st quarter of Year-2. In parallel with bids advertising, the establishment of Water Use Association-WUAs will take place. Output3: upon finalizing the Nursery rehabilitation assessment, the main rehabilitation requirements (including Mother fruit trees identification) were prioritized, reviewed and endorsed by PAC early in Nov 2022. Accordingly, FAO has initiated the designing and TSs preparation immediately. The plan to finalize nursery rehabilitation works is by Sep 2023. Similarly, for extension support and training program all have been pinpointed to be implemented in due course within 2023. Output4: As per Year-1 workplan, there is no implementation in the field for this output activities. However, TSs for Crushers and requirements of Farmer Field School-FFS identified within Year-1 and to be implemented starting Feb 2023. | MS
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | FAO - Mohamad Amer Jnedan
| Email: | Mohamad.Jnedan@fao.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | During the project Year-1, the vast majority of implementation arrangements in term of field assessments and studies conduction, Technical consultations with relevant stakeholders and target communities, preparation of required technical specification and fine-tuning intervention designs have been made properly so that the project second year is for conduction and execution.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1 Capacities and commitment of national and sub-national government institutions, communities and vulnerable groups to assess, plan and manage climate change-induced and post-crises water and land challenges haveCbeen strengthened and knowledge and lessons learned for replication collected and shared and integrated into strategies and regulations | Capacity of national and municipal government staff to develop, implement and update INRM strategy in which climate change is mainstreamed increased: No. of national-level staff - Total - Women No of municipal-level staff - Total - Women | 0 0 0 0 | National and local government officials have limited capacity to develop, implement and update the INRM strategy in which climate change is mainstreamed. Therefore, this project is aiming to raise the capacity by providing the needed technical support through a series of coordination and consultation meetings/workshops. The project team ensured women were included in the process of identifying stakeholders and also emphasized women participants take part in project workshops and training. Related activities are still ongoing and final results figures will be shared once finalized. A gender-disaggregated database for workshops and consultations was developed and has been regularly updated to monitor the participation and gender disparity during the project implementation. Please check the stakeholder engagement database under annex #06 | 20 40% 40 20%
Outcome 1 | Percentage of direct targeted population aware of predicted adverse impacts of climate change, and of appropriate responses - Total - Women - Youth | 0 0 0 | N/A | Mid-20%; end 50% Mid-20%; end 50% Mid-10%; end 20%
Outcome 1 | Climate change priorities are integrated into INRM strategy and related regulations - INRM with CC mainstreamed - Regulations updated - Number of partner cities that integrate the conservation of land, water and biodiversity in their urban planning processes (Institutional outcome) - Number of human settlements (UN-H DoC 3 -CC- outcome 3.2) - Number of partner cities implementing integrated policies and plans towards mitigation and adaptation to climate change (Institutional outcome) - Number of human settlements with regional or district plans UN-H DoC 3 -CC- outcome 3.3) | 0 0 0 0 | This is early to be assessed and to be identified through AF Syria Framework INRM strategy for KPIs and gaps assessment | 1 1 4 4
Outcome 1 | Innovations adaptation practices are encouraged and / or accelerated at regional, national and / or subnational level through: - Replication guidelines at national level - Workshop to replicate approach - GoS number of participants in international knowledge sharing events - UN system in Syria – disseminated through decentralised hubs – KM documents disseminated - UN-Habitat CoP – KM document shared | 0 0 0 0 0 |  | 1 2 4 1 1
Output 1.1. Inception workshop and coordination mechanism | No. of staff trained / participated in workshops - Total - Women Coordination mechanism established | 0 0 0 | During the reporting period, the awareness of project activities was raised through multi-stakeholders dialogue and coordination workshops/meetings: An inception workshop was conducted on 24 Oct 2022 and the inception report was submitted on 23 Nov 2022 and included: (i) agreement on the organizational structure of the project, including roles and responsibilities (i.e. ToR PSC and PAC); (ii) 1st-year work plan; (iii) project baseline and monitoring and reporting framework; (iv) project risks management framework; (v) Environmental and social Risks Management Framework / Plan; (vi) knowledge management, advocacy & communication framework and work plan. The inception workshop was followed by the PSC meetings and a series of PAC meetings. A community consultation workshop was conducted on 17 Feb 2022 to make the community fully aware of the project objective, activities, target locations, and approved work plan and to explain how to involve the community in project activities of 3 components. Please see the Community consultation workshop report under annex #03 To ensure the establishment of horizontal and vertical coordination mechanisms on water, land, climate change, and recovery, the project team provided the needed technical support to the Environment Safety and Climate Change technical Unit (ES - CCU) in Eastern Ghouta and a series of coordination meetings took place to plan and monitor project activities. ESCCU equipment and materials needs were identified in line with the proposed budget and technical specifications were prepared, procurement is to start in Nov 2022. To ensure gender considerations have been taken into account during the reporting period, the project team made sure that women were involved in the workshops/training and consultation meetings to highlight their needs in light of climate change. A sex-disaggregated database for workshops and consultations was developed and has been regularly updated to monitor the participation and gender disparity during the project implementation. | 40 % 40 % 1
Output 1.2. Capacity strengthening package | No. of staff trained / participated in workshops - Total - Women | 0 0 | This activity is still ongoing. During the reporting period, the project team identified data and capacity gaps and needs for developing and implementing the INRM strategy. Workshops and field assessment studies took place to develop area-based assessments and to feed into the adaptation plan for the target area in eastern Ghouta. the workshop and damage assessment was implemented in participatory manner with local goverment staff, municipal staff and local community. Please see the workshop/training report under annex #03 For the next step, the project team will continue with the implementation of a series of training on the above and below, incl. - Data collection - Data analysis and mapping / GIS - Monitoring of data and implementation of INRM strategy A sex-disaggregated database for workshops and consultations was developed and has been regularly updated to monitor the participation and gender disparity during the project implementation. | 200 40 %
Output 1.3 Establish baseline and targets (data gathering and assessments) + Assess future outlook for the region | No of tools and guidelines developed and shared with relevant stakeholders and - Detailed Hydrogeological study - CC VA - Future outlook for the region | 0 0 0 | This activity is still ongoing, project team developed detailed technical assessment tools in consultation with PAC and ESCCU. Furthermore, field studies/assessments were conducted to determine the Hydrology/water balance - volumes and qualities (groundwater, surface water, drinking water, wastewater, etc.) A report of the technical assessment and the methodology followed is available under the annex#04 Although there was good progress in this activity, there was a delay in finalizing its deliverables due to the need to conduct more consultations with the various stakeholder groups during the design phase to ensure that the results are focused on addressing the needs of the local community Also there was a delay in contracting the Internation firm who should be responsible for the detailed Hydrogeological study, CC VA, and future outlook for the region. Since this service is considered high value, according to UN procedures, the procurement will follow a long procurement and approval process ( through UNON). consequently, a long time is taken to finalize the following steps: EOI advert (launch/close); Finalization of the SSP /TOR; Finalization of Solicitation Document; Launch solicitation (RFP); Site visit and Pre-Bid Conference; Opening of technical proposals; Receipt of bids after clearance by TOC, PS due diligence and send proposals to TEC; Technical Evaluation and draft report; Due Diligence on TER and seeking clarification from bidders; Technical Evaluation final report. | 1 1 1
Output 1.4 Gaps analyses and recommendations for managing water and land | No of tools and guidelines developed and shared with relevant stakeholders: -Gaps analyses and recommendations for managing water and land | 0 | This activity is planned to start in the second year of the project. | 1
Output 1.5 INRM Strategy and action plan (with CC mainstreamed) | No of tools and guidelines developed and shared with relevant stakeholders and municipalities covered - INRM Strategy and action plan (with CC mainstreamed - Regulations updated (based on recommendations above) - Municipalities covered (Also in line with UN-H DoC 3 - CC - outcome area 3.3) | 0 0 0 | It is still early to assess | 1 1 4
Output 1.6 M & E plan for above + replication mechanism | No. of key findings on effective, efficient adaptation practices, products and technologies generated: - Replication mechanism - Project results video online | 0 0 | It is still early to assess | 1 1
Output 1.7 Formal adoption of strategy document | See output 1.5 |  | It is still early to assess
Outcome 2 | Capacity of national and municipal government staff to operate, maintain and sustain the WWTP and related sewerage and irrigation network: No. of national-level staff - Total - Women No of municipal-level staff - Total - Women | 0 0 0 0 | This activity will start after the installation and operation of the mobile WWT plant by the end of 2023 | 15 30 % 15 30%
Outcome 2 | Percentage of direct targeted population aware of predicted adverse impacts of climate change, and of appropriate responses under this component - Total - Women - Youth | 0 0 0 | It is still early to assess | Mid-20%; end 50% Mid-15%; end 30% Mid-05%; end 15%
Outcome 2 | Type of physical infrastructure improved to withstand climate change and variability-induced stress: - Sewerage network - Mobile WWTP - Irrigation canals | 0 0 0 | The rehabilitation of the sewage networks initiated and will be completed in Feb 2023 Preparation of detailed technical study for WWT is in progress The rehabilitation of the irrigation canal will be completed in in April 2023 | 1 1 1
Outcome 2 | Innovations adaptation practices are rolled-out and encouraged at national and / or subnational level through: - Replication guidelines at national level - Workshop to replicate approach | 0 0 | It is still early to assess | 1 2
Output 2.1. | No of tools and guidelines developed and shared with relevant stakeholders and: - Detailed engineering studies and designs of below interventions | 0 | Detailed technical assessment and specification for the rehabilitation of the sewage networks prepared | 1
Output 2.2. | No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change: - Meter of rehabilitated sewerage network | 0 | A thorough assessment and consultation with communities and related departments were undertaken, selected lines of networks were verified and the detailed technical studies prepared. Case was advertised and contract was signed. The rehabilitation of the sewage networks initiated and will be finalized in March 2023 | 1600m
Output 2.3. | No. of staff trained to operate, maintain and sustain the WWTPs - Total - Women No of tools and guidelines developed and shared with relevant stakeholders: - O & M and exit strategy plan, No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change: - No of mobile WWTP - Quantity of water treated No. of key findings on effective, efficient adaptation practices, products and technologies generated - Replication guidelines on mobile WWTP | 0 0 0 0 0 0 | This activity will start after the installation and operation of the mobile WWT plant by the end of 2023 | 30 30% 1 1 3,840 m3/day 1
Output 2.4. | No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change: - Meter of rehabilitated irrigation canals | 0 | A thorough assessment and consultation with communities and related departments were undertaken, the detailed technical studies prepared and case was advertised, the contract is expected to be signed in November and the rehabilitation of the irrigation canal will be initiated and finalized by April 2023 | 48,000m
Outcome 3 Resilience of water-dependent livelihoods and security of income (through reduced water demand), especially for vulnerable groups has increased through: - Protection of water resources (and prevention of contamination of surface and groundwater resources / wells) - Raising water use efficiency, using high efficiency irrigation methods - Improved agricultural practices / climate smart agriculture practices such as crop rotation, introduce drought tolerant crops and trees - Alternative or diversified livelihoods; And capacities to operate, maintain and sustain these systems/practices have been strengthened (in line with AF outcomes 2, 3 and 6 and 8). | Capacity of national and municipal and local extension/water engineers staff and farmers to operate, maintain and sustain / replicate the agriculture technology, smart applications and alternative livelihoods straightened: No. of national-level staff - Total - Women No of municipal-level staff - Total - Women | 0 0 0 0 | It is still early to assess | 20 30% 40 20%
Outcome 3 | Percentage of population aware of predicted adverse impacts of climate change, and of appropriate adaptive responses under this component - Total - Women - Youth Percentage of households and communities having more secure (i.e. increased income) through access to climate smart agriculture practices / livelihoods - Total - Women - Youth | 0 0 0 0 0 0 | It is still early to assess | Mid-20%; end 50% Mid-20%; end 50% Mid-10%; end 20% Mid-5%; end 15% Mid-5%; end 15% Mid-2%; end 8%
Outcome 3 | Innovations adaptation practices are rolled-out and encouraged at national and / or subnational level through: - Workshop to replicate approach | 0 | Capitalization workshop for exit strategy and lessons learnt is scheduled within the project’ Year-3 i.e. end of 2024. | 2
Output 3.1. Studies and assessments to detail the proposed interventions *In line with AF output 3.2.2. and 8.2 | No of tools and guidelines developed and shared with relevant stakeholders: - Inception report - Report of assessments - Report on technical specifications No. of key findings on effective, efficient adaptation practices, products and technologies generated - Capitalization exercise on replication of below interventions at the end of the project | 0 0 0 0 | Workshops to disseminate results will be organized within the project Year-3. Inception workshop organized in 23 Oct 2021. (Achieved by PPR1: 1 out of 1) All field assessments reports will be finalized and cleared from RNE by end of 2022. (Achieved by PPR1: 3 out of 8 studies) Technical specification of Crushers, climate station and Qnt/Qlt water monitoring systems are enclosed. (Achieved by PPR1: 3 out of 3 TSs) Capitalization workshop for exit strategy and lessons learnt is scheduled within the project’ Year-3 i.e. end of 2024. (Achieved by PPR1: 0 out of 1) | 1 1 3 1
Output 3.2. Introduction of water efficient agricultural technology *In line with AF output 2.1.1 and 3.2.2. and 6.1. | No. of staff and people trained to operate, maintain and sustain / replicate the water efficient agriculture technology - Total - Women No of tools and guidelines developed and shared with relevant stakeholders: - O & M and exit strategy plan for output 3.2. No. and type of adaptation assets (tangible and intangible) created or strengthened in support of individual or community livelihood strategies - Ha irrigated by efficient irrigation systems of treated water and wells - Ha of agriculture land levelled by laser - No of ground water wells rehabilitated and equipped with solar pumps - No of climate stations installed - No of stream flow gauge stations installed - No of groundwater monitoring systems installed - No of laser levelling device operated | 0 0 0 0 0 0 0 0 0 0 | Comprehensive Training programme for various topics/scopes is identified; and will be sequentially implemented in relation with conducting relevant interventions during 2023. (Achieved by PPR1: 0 out of 100) Capitalization workshop for exit strategy and lessons learnt is scheduled within the project’ Year-3 i.e. end of 2024. (Achieved by PPR1: 0 out of 1) -Efficient irrigation systems related to treated water is associated to installing and operating WWTP by UNDP whereas for wells is pending finalization of rehabilitation works. (Achieved by PPR1: 0 out of 90Ha) -Land laser leveling operation will start during 3rd quarter of 2023. (Achieved by PPR1: 0 out of 200Ha) -The selection process of Ground wells to be rehabilitated will be finalized soon by end Nov 2022 so that the required designs and Technical specifications can be finalized within 1st quarter of 2023. (Achieved by PPR1: 0 out of 6) -Technical specification of Climate station is cleared and will be re-announced again as only few offers received by first advertisement in July 2022. (Achieved by PPR1: 0 out of 1) -As above for the flow gauge station. (Achieved by PPR1: 0 out of 1) -Some Qnt/Qlt water monitoring system are procured and the rest will be re-announced for. (Achieved by PPR1: 0 out of 1) -Assembling land laser leveling device/s will start earliest in 2023. (Achieved by PPR1: 0 out of 1) | 100 30 % 1 90 Ha 200 Ha 6 1 1 1 1
Output 3.3. Adoption of climate-smart agriculture practices for improved soil fertility and enhanced water use efficiency *In line with AF output 2.1.1 and 3.2.2. and 6.1.1 | No. of staff and people trained to operate, maintain and sustain / replicate climate smart agriculture practices - Total, of which: - Farmers - Technicians - Women - Youth No of tools and guidelines developed and shared with relevant stakeholders: - O & M, and exit strategy plan (capitalisation exercise) for output 3.3. - No of famers applying climate smart agriculture adaptation practices such as crop rotation - No of nurseries to produce drought tolerant crops | 0 0 0 0 0 0 0 0 | Comprehensive Training programme for various topics/scopes is identified; and will be sequentially implemented in relation with conducting relevant interventions during 2023. (Achieved by PPR1: 0 out of 240) Capitalization workshop for exit strategy and lessons learnt is scheduled within the project’ Year-3 i.e. end of 2024. (Achieved by PPR1: 0 out of 1) Optimized crop rotations and intercropping practices are identified with all required seed and inputs. (Achieved by PPR1: 0 out of 2600) Main requirements for Sapling nursery rehabilitation including tools and mother fruit trees are identified then prioritized for cost-effectiveness and sustainability. Detailed Technical specification and designs initiated; and will be announced duly within the 1st quarter of 2023. (Achieved by PPR1: 0 out of 1) | 240 80 % 20 % 30 % 15 % 1 2600 1
Output 3.4. Promote sustainable livelihood opportunity through crop residuals management and support to rural women *In line with AF output 2.1.1 and 3.2.2. and 6.1.1. | No. of staff and people trained to operate, maintain and sustain / replicate alternative livelihood opportunities - Total - Women No of tools and guidelines developed and shared with relevant stakeholders: - O & M and exit strategy plan (capitalisation exercise) for output 3.4 No. and type of adaptation assets (tangible and intangible) created or strengthened in support of individual or community livelihood strategies - Number of alternative / sustainable / climate change resilient livelihoods created through crop residuals management and rural women empowerment | 0 0 0 0 | Comprehensive Training programme for various topics/scopes is identified; and will be sequentially implemented in relation with conducting relevant interventions during 2023. (Achieved by PPR1: 0 out of 900) Capitalization workshop for exit strategy and lessons learnt is scheduled within the project’ Year-3 i.e. end of 2024. (Achieved by PPR1: 0 out of 1) Technical Specification for crushers is identified and cleared and will be announced earlier in 2023. (Achieved by PPR1: 0 out of 6) Required tools for farm’ residuals management for composting and fodder making are identified; and will be cleared and announced during first half of 2023. Inputs for Empowering rural women are still under development. | 900 30 % 1 6 crushers 200 sets of tools 1 sell point for marketing women products

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1) The inception workshop and community consultation workshop were inaugurated by the Minister and deputy Minter of Local Administration and Environment. Their presence mobilised many participants (local communities, policy makers and related stakeholders) and their commitment to the project is expected to facilitate the involvement of stakeholders at all levels and provide the support to collect data required for the project. 2) As the project was disseminated at the local level in the inception workshops and in order to avoid the high expectation of the project to cover all project stakeholder's needs, the IE and EEs tried to mitigate this by conducting a community consultation workshop and regular meetings with project stakeholders to explain the detailed project activities and next steps. 3) Working closely with project stakeholders, technical training, and field surveys helped to strengthen the capacities of national and Eastern Ghouta government institutions, communities, and vulnerable groups to be able to assess, plan and identify needs and provide solutions to manage scarce natural resources (especially water and land) in an efficient, coordinated, sustainable and climate resilient way, also to be prepared and trained to replicate the approach in other areas, Furthermore, this allowed the project team to capture and share lessons and to mainstream these in strategies. 4) Continuous consultation with the other technical entities participating in this project, ensured active participation in the steering committee of the project to ensure in turn involvement and commitment of all concerned stakeholders at all levels.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | 1) There was a delay in finalizing the UN-to-UN agreements with EEs for Components 2 and 3 as UN agencies envisaged in the proposal that the administrative process will go smoothly and fast. However, the administrative negotiations took longer than expected. The Agreement with UNDP for Component 3 was signed in March 2022 The Agreement with FAO for Component 3 was signed in Dec 2021 2) Some of the project activities were delayed due to the need to conduct more consultations with the various stakeholder groups during the design phase to ensure that the project's technical specifications are focused on addressing the needs of the community. These active consultations with stakeholders enabled us to solve the problem and move forward. It also enabled active communication between different stakeholders and accelerated response for any future issue that might arize. The project workplan is adjusted to consider the delay and corrective actions were taken to finalize the activities before the project's end date. The updated workplan is available under annex #5 3) within the first two quarters of the project's first year, It was not an easy task for UN teams to practically explain (have mutual understanding with national teams) the specific roles and responsibilities of each stakeholder engaged in the project; some relevant members had some unclarities which have been properly solved out later on through regular consultations. For instance, the UN well structured (and maybe strict) procurement/administrative/organizational procedures as well as the appropriate coordination procedures that should be followed. 4) There was a misunderstanding of project governance structure by national partners, therefore IE and EEs clarified the project organigram and roles and responsibilities of PAC and PSC after consultation with national partners and based on working practices. Please see annex#2
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | There have not been major changes in project outputs that will differ from the initial outputs.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | During the inception phase, to ensure compliance with the AF ESP and GP, all proposed project activities have been screened against the 15 AF principles (i.e. safeguards) to identify potential environmental and social risks and to assess related potential impacts. According to the ESMP, where risks have been identified, impacts have been assessed and where needed, measures to avoid or mitigate risks and impacts were identified. Costs for risk mitigation measures were integrated into the budget, including e.g. PV installation and water quality monitoring. However, it is not yet completely relevant at this stage as most physical activities implementation is envisaged to start in Nov/Dec 2022. However, initial preparation and briefings have taken place for national partners and communities that describe the project's ESMP and the ESP of the Adaptation Fund.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | 1) During the reporting period, gender considerations were taken into account and the project team ensured that women were included in the stakeholder identification process and emphasized participation of women participants in project workshops and training sessions. 2) A gender-disaggregated database for workshops and consultations was developed and regularly updated to monitor participation during project implementation. 3) A focus group discussion was established with women to highlight their needs in light of climate change.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | N/A
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | N/A
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | N/A
If learning objectives have been established, have they been met? Please describe. | N/A
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | N/A
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization. | N/A
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | SYR/MIE/Water/2019/1
Implementing Entity | UN-Habitat
Type of implementing entity | MIE
Country | Syrian Arab Republic
Region | Asia-Pacific
Sector | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 145000 | 81700 | 0 | Total | 145000 | 81700 | 63300 | Total |  |  |  | Total
|  | % of female beneficiaries | 50% |  | 50% | % of female beneficiaries | 50% |  | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 32% |  | 32% | % of Youth beneficiaries | 32% |  | 32% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 200 | Water management | 2: Low capacity | Total | 200 | Water management | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 40% |  |  | % of female targeted | 40% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 40 | 40% | Public |  | 40 | 40% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 20% |  | Water management |  | 20% |  | Water management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 11 | Training manuals | Sub-national |  | 11 | Training manuals | Sub-national
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Regional | 2: Partially responsive (Lacks most elements) |  | Water management | Regional | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 7 | Physical capital | Water management | Strengthening infrastructure | 7 | Physical capital | Water management | Strengthening infrastructure
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 30790 | Agricultural-related |  |  | 30790 | Agricultural-related
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
2: Most not integrated
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Water management | Regional | Environmental policy | 0 | Water management | Regional | Environmental policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Water management | Regional | Innovation accelerated |  | Water management | Regional | Innovation accelerated
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  | 1: Ineffective