## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 08/02/2022-04/30/2023
| Project Title: | “Strengthening of a replicable micro ecosystem for accelerated development of technologies for climate change adaptation of the Dominican Republic through the development of a pilot Thermo Solar Desalination appropriate technology”
| Project Summary: | Taking into account the experience of the Dominican Institute for Integral Development (IDDI) in climate change projects in the Dominican Republic, it was decided to proceed with the development and testing of a pilot system of distributed generation of drinking water based on solar thermal desalination to be implemented in coastal marine communities in the province of Montecristi where the salt activity is developed, contributing not only to the provision of an innovative mechanism for obtaining drinking water through solar thermal desalination, but also to support good practices for the conservation of ecosystems and biodiversity in the area with environmentally friendly measures for adapting to climate change.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | Decision B.35.a-35.b/72 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Dominican Institute of Integral Development, Inc. (IDDI) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | NIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Dominican Republic | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Dominican Republic, coastal-marine zones of Montecristi Province | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2020-09-23
IE-AFB Agreement Signature Date: |  | 2020-12-12 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2021-02-08 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2022-01-04
| Original Completion Date: | 2022-08-07
Revised Completion Date after approval of |  | The extension of the project was requested for a period of 6 months until February 2023, however the final tests of the prototype were received on 04/30/2023.
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | www.iddi.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Rosa Damaris Mejia | Dominican Republic
| Email: | damarisfull@hotmail.com | Ecuador
| Date: | March 2021 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Milagros de Camps (Vice ministerio de Cooperaciòn Internacional - Ministerio del Medio Ambiente) | Equatoral Guinea
| Email: | milagros.decamps@ambiente.gob.do | Eritrea
| Date: | March 2021 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | David Luther ( IDDI´s Executive Director) | Fiji
| Email: | david.luther@iddi.org | Finland
| Date: | 2021-02-01 | France
| Executing Agency |  | Gambia
| Name: | Alvaro Atilano, Tecnologias Termosolares SRL | Georgia
| Email: | atilal@gmail.com | Germany
| Date: | 2021-02-01 | Ghana
| Executing Agency |  | Greece
| Name: | Ing. José Rafael Díaz, M.S, Universidad Tecnologica de Santiago (UTESA) | Grenada
| Email: | investigacion@utesa.edu | Guatemala
| Date: | 2021-09-01 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Carlos Sanlley Instituto Tecnologico de Santo Domingo (INTEC) | Guyana
| Email: | carlos.sanlley@intec.edu.do | Haiti
| Date: | 2022-04-01 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: Cumulative from project february 08th, 2021 to March 15th, 2022 |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
|  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of march 15th, 2022 | 249929 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. | The funds are held in a commercial bank account in Dominican Pesos that does not generate interest. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | Not annual investment income generated from the Adaptation Fund’s grant |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
|  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
COMPONENT 1 - Development of the Technology including the Prototype for Testing at a Dominican Republic University
| Activity 1.1: Design of a prototype to be tested at a Dominican Republic University. Outputs: a) Design of the prototype concluded. | 5450
| Activity 1.2: Construction of a prototype to be tested at a Dominican Republic University. Outputs: a) Prototype built. | 16850
| Activity 1.3: Performing the first prototype test at a Dominican Republic University. Outputs: a) Prototype tested at a Dominican Republic University. | 18500
| Total Component 1 | 40800
| 3. Executing cost fee by IDDI | 3404
| 4. Total cost of the Project | 44204
| 5. Implementation fee | 16580
| TOTAL | 60784 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
COMPONENT 2 - Pilot test of prioritized adaptation technology in a selected community in Dominican Republic
| Activity 2.1: Selection of the coastal community to test the new pilot adaptation technology. Outputs: a) Community to test theprototitpe (Minimum Viable Product) selected | 14515 | April 2022
| Activity 2.2: Consultation and awareness and training of the coastal community where new pilot adaptation technology will be tested. Outputs: a) Community selected for testing the minimum viable product of the technology consulted and sensitized; b) Community selected trained; and c) A disruptive mechanism to transfer a % of royalties generated by the sales of the technology worlwide to a women led organization established. | 12270 | April 2022
| Activity 2.3: Selection of the site in the coastal community where the new pilot adaptation technology will be tested. Outputs: a) Site selected; b) Agreements with the owners of the site to carry out the test established. | 7650 | April 2022
| Activity 2.4: Design of the modified prototype to be tested at the coastal community. Outputs: a) Prototype/minimum viable product (MVP) designed. | 5200 | June 2022
| Activity 2.5: Construction of the modified prototype to be tested at the coastal community. Outputs: a) Prototype/minimum viable product (MVP) built | 80680 | June 2022
| Activity 2.6: Performing all the necessary tests of the prototype in the selected community, including the operational procedures of technology placement. Outputs: a) MVP transported, placed at the specific site and put into operation; b) Report of the results of the test developed. | 22610 | August 2022
| Activity 2.7: Development of a preliminary operating manual. Outputs: a) Manual developed | 6000 | August 2022
| Activity 2.8: Development of final research and development reports. Outputs: a) Final reports developed | 10270 | August 2022
| Total Component 2 | 159195
COMPONENT 3 - Knowledge management to capture and disseminate lessons learned
| Activity 3.1: Workshop to disseminate lessons learned for NIEs and focal points of the Adaptation Fund in the Caribbean Islands. Outputs: a) At least 15 National Implementation Entities and Focal Points of the Adaptation Fund in 15 Caribbean island countries sensitized and trained on the results of the adaptation project; b) Partnerships established for Phase II of the project; c) Possible request for funds for Phase II of the project developed for the Adaptation Fund and / or request for Full Size Regional Project for the GEF. | 26250 | August 2022
| Total Component 3 | 26250
| 4. Total cost of the Project | 185445
| 5. Implementation fee | 3000 | August 2022
| TOTAL | 188445 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESSMENT
IDENTIFIED RISKS
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The products developed by the project could take more time to provide tangible results than their duration. | MEDIUM | • Prioritization of activities that can be designed and implemented within the useful life of the Program. • Inclusion of long-term research in institutional work plans. • Sensitization with the contractors and universities that will support the studies and evaluations so that the results are delivered within a period that ensures a sufficient schedule for the piloting on site.
Prioritize economic benefits over social and/or environmental benefits. | LOW | • The project activities explicitly integrate the needs of social, economic and environmental development in an integrating framework of climate resilient. • The project will give priority to low-cost resistance strategies that demonstrate the impact on revenues.
The lack of information at the local (and reduced) level on the use of alternative and innovative technologies that provide solutions to CC | MEDIUM | • Prepare specific studies on specific areas and/or at the community level with respect to climate change threats. • The project foresees the need to carry out preliminary studies in the target communities with the participation of all stakeholders.
Delays in the development of the project phases due to the measures taken by governments due to the Covid 19 pandemic have an impact on the achievement of products and results and reduce the scope to deliver the program as described. | HIGH | • Develop a detailed work plan with alternatives to avoid delays in the development of the project phases.
A poor understanding of the objectives by the Program team. | LOW | • Strong participation of technical project team • Support of national experts. • Training adapted for target groups.
Low mobilization of the target group due to a poor understanding of the problems of climate change. | LOW | • Greater collaboration with target com munities. • A participatory approach. • Sensitization to the effects of climate change at different levels.
Lack of capacity to obtain funds, for the follow-up and sustainability of the initiative | MEDIUM | • A continuous dialogue will be established before and after the signing of the contracts between the program partners. • Sufficient allocation within the detailed proposal and cooperation agreements made to develop teams with sufficient capacity (both in size and technical capabilities). • Set realistic goals for future partners' contributions in the first instance
The lack of sufficiently qualified partners and stakeholders | LOW | • Capacity building. • Selection and evaluation of partners, needs assessment. • Collaboration with the communities for their training and awareness on the use of new technologies.
Critical Risks Affecting Progress (Not identified at project design)
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Health problems, and social and economic impacts from the Covid-19 pandemic | HIGH | Monitoring of the protocols issued by the Ministry of Health and PAHO for the prevention of virus transmission and search for alternatives for the development of project activities, taking into account existing restrictions.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
No other risks, in addition to those reported, that have been identified that affect the performance of the project, are foreseen. Through the established monitoring system we will be constantly evaluating the situations that may arise that have not been previously contemplated in the initial risk analysis and through the complaints system we will be attentive to seek the necessary corrective measures to ensure the mitigation of both the expected risks and others not contemplated. The components of the PMU were trained to detect and develop appropriate mitigation measures in the face of risk situations that arise. At the time of writing the PPR, the Covid-19 pandemic, although controlled, has caused delays due to the fact that face-to-face academic activity is suspended, so access to laboratories is restricted. It is expected that in the month of March 2022, presential activity will resume in the Dominican Universities.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | The program complies with the relevant national laws, regulations and policies; and complies with the country's relevant legal framework for water management and use, environmental protection and local rural development. | Monitoring compliance with laws and establish the grievance mechanism. | Number of complaints received for non-compilance of Dominican Law. | All activities under this project are compliant with the Dominican Laws and applicable international laws and regulations. | Ensures that results and actions are aligned with laws and public policies related to Climate Change | N/A | N/A
2 - Access and equity |  |  | The intervention logic of the project is to provide benefits in the most vulnerable communities, with fair and equitable access to activities, equipment, resources and training throughout the planning and execution phases. | All individuals or groups that request participation will have the same opportunity to benefit from the adaptation activities proposed by the project. | Number of people who have received training on adaptation measures for climate resilience. | Project interventions guarantee access and equity to sensitive groups, especially women (heads of household or single mothers) and young people. | The participation of women is ensured in each workshop, meeting or consultation held in the communities. | N/A | N/A
3 – Marginalized and vulnerable Groups |  |  | The program focuses on marginalized and vulnerable groups (poorest rural communities) and aims to help them improve their living conditions and quality of life, whhick area already compromised by poor local development, poverty, lack of access to opportunities, deficit infrastructure and Climate change. | The project will include all members of the community and will be careful not to exclude (by action or omission) Dominicans of Haitian descent and Haitian immigrants (especially those with questionable immigration status) and their families. The program does not have a negative impact on these groups. | Number of vulnerable people / families who participate in the Project activities. | Open, free and informed consultations with key stakeholder groups. It is considered to prepare a contingency plan if applicable. | N/A | N/A | N/A
4 – Human rights |  |  | The Program respects the fundamental rights of people in the areas subject to intervention | Participation in the program will be voluntary and free for all people. | N/A | N/A | N/A | N/A | N/A
5 – Gender equality and women’s empowerment |  |  | Women with low or little participation in decision-making and planning in the activities to be carried out by the project | Provide facilities and ensure the participation of women, in training and decision-making of project activities | Percentage of women participating in training and decision-making activities. | The target groups are predominantly dominated by men due to their activity (salt workers). | The participation of women is ensured in each workshop, meeting or consultation held in the communities. | N/A | N/A
6 – Core labour rights |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 – Indigenous peoples |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 – Involuntary resettlement |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 – Protection of natural habitats |  |  | Low potential risk to natural habitats occurs during prototype testing. The natural habitats will be assumed by the Program and the appropriate measures will be activated in accordance with the EIA/ESP. | Measures will be taken so that the tests of the prototype do not generate an impact and emphasis will be placed on compliance with the EIA. | Number of mesasures taken for protection of natural habitats. | All activities will be monitored to avoid impacts at the level of natural habitats, with the participation of technicians and specialists from the Ministry of the Environment. | It is established in the terms of reference that the activities to test the prototype must be carried out while protecting the environment and natural habitats | Measures are established to ensure the collection of waste (brine) resulting from desalination in appropriate containers. | N/A
10 – Conservation of biological diversity |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 – Climate change |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 – Pollution prevention and resource efficiency |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 – Public health |  |  | Quality of the water obtained does not meet the standards | Control tests carried out by laboratories to check the feasibility of consumption |  |  | N/A | N/A | N/A
14 – Physical and cultural heritage |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 – Lands and soil conservation |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | IDDI has trained the PMU staff to be able to monitor compliance with AF ESPs. Workshops have been held to train communities on ESP and an Information and Accountability System was implemented with the aim of managing complaints and addressing situations in which corrective action should be taken in respect of ESP compliance.
Have the implementation arrangements been effective during the reporting period? |  | During this period, the activities that have been developed are in line with compliance with the ESP.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | IDDI in this project is the implementing and executing entity
Have the implementation arrangements at the EEs been effective during the reporting period?
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No complaints have been submitted by the stakeholders or beneficiaries. |  | N/A
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, gender equity has been taken into account for the development of solar thermal technology, emphasizing the participation of women in training and leadership
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Ensure Acsses Equality | COMPONENT 2 . Pilot test of prioritized adaptation technology in a selected community in Dominican Republic | Percentage of women participating in training and decision-making activities. | 0 | 50% | A participation of 43% of women was achieve, the result its Good
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
During the implementation of the project, there were no problems regarding the equal participation of men and women, even though the target audience was salt workers from the communities of the San Fernando de Montecristi Municipality, a profession that is carried out mostly by men. To ensure the participation of women, the inhabitants of the target communities were included and, of their own volition, 13 women leaders of the communities participated, ensuring a participation of close to 43%. |  | Considering that the project was based on the construction of the solar thermal desalination prototype and that the community activities were complementary to involve the target public in the process, both in terms of training with innovative technologies and in strengthening their capacities to increase climate resilience, in Especially since the target population is vulnerable to the effects of CC, we consider that the participation of women leaders of the communities was an important achievement and we rate this result as good, taking into account the level of participation and appropriation that was carried out throughout throughout the duration of the activities implemented on the ground.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The IDDI is implementing its Gender Policy that is aligned to the GP of the AF. For community activities, the empowerment of women for decision-making and training to be able to use solar thermal desalination technology has been set as a goal.
Have the implementation arrangements at the IE been effective during the reporting period? |  | At the time of this report, community activities have not been carried out on the ground, but it is contemplated in the action plan for the empowerment of women and gender equality.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | IDDI is the implementing and executing entity
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5]
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | NO
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No complaints have been submitted by the stakeholders or beneficiaries. |  | N/A
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | COMPONENT 1. Development of the Technology including the Prototype for Testing at Dominican Republic University |  | Outcome 8 | Preparation of preliminary designs and initial prototype with termo-solar technology |  | Prototype 100% complited and tested by the Technological University of Santiago (UTESA). | S
| COMPONENT 2 . Pilot test of prioritized adaptation technology in a selected community in Dominican Republic |  | Outcome 8 | Final prototype built and tested Prepared technical and operating manuals. Target communities (2) trained and strengthened to increase climate resilience. |  | Final prototype built and tested in two locations: National Aquarium (Santo Domingo) and Montecristi Province (Salina Richetti) by Intec and the IDDI technical team Technical operating manuals and designs prepared and delivered. In total, 6 Workshops were given: 1: "Implementation of technologies for access to drinking water with the desalination of seawater" and 2: "Good practices for the care of coastal ecosystems and adaptation to CC with the participation of 86 people (49 men and 37 women). | HS
| COMPONENT 3 . Knowledge management to capture and disseminate lessons learned |  | Outcome 8 | Presentation of lessons learned and data from the innovation process to public and private entities, NGOs and NIE's in the region |  | Lessons learned presented to public and private institutions in the Dominican Republic The IDDI is committed to monitoring and taking the next steps for the improvement and application of solar thermal technology for desalination through new financing of innovation projects, private companies and the national government. | HS
[6 empty] | Overall Rating | HS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | David Luther (Ejecutive Director)
| Email: | david.luther@iddi.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The results obtained through the tests carried out on the prototype indicate that solar thermal technology for seawater desalination can give important results and be applicable in coastal communities that require drinking water and do not have natural sources for obtaining fresh water. . The effort made by INTEC to redesign and launch the prototype and carry out field tests gave results, allowing it to have a functional and operational team that can be improved in other phases of implementation. The IDDI is committed to monitoring so that this technology can be used, not only to be able to provide water for human consumption to vulnerable communities, especially those affected by climate variability. It is also important to highlight that this type of technology requires time and budgets to be able to implement it, since it is based on trial and error, where the material used requires investments, apart from the time and man-hours invested for calculations, studies and tests. However, the support of the project's technical team was essential for its success. The communities that joined the process, both to train them in the use of new technologies and to strengthen their capacities to increase resilience to CC, were very collaborative and consistent, especially the women community leaders and salt farmers who participated in the process. The participation of more than 35 representatives of public, private institutions and NGOs showed the interest in this type of technology and the need to continue investing for its improvement and implementation.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | COMPONENT 1. Development of the Technology including the Prototype for Testing at Dominican Republic University |  | Outcome 8 | Preparation of preliminary designs and initial prototype with termo-solar technology |  | Prototype Designs (Elaborated) Construction of the first prototype (Completed) Prototype tests (Preliminary report ready, waiting for the final report) | HS
| COMPONENT 2 . Pilot test of prioritized adaptation technology in a selected community in Dominican Republic |  | Outcome 8 | Final prototype built and tested Prepared technical and operating manuals. Target communities (2) trained and strengthened to increase climate resilience. |  | Final prototype built and tested in two locations: National Aquarium (Santo Domingo) and Montecristi Province (Salina Richetti) by Intec and the IDDI technical team Technical operating manuals and designs prepared and delivered. In total, 6 Workshops were given: 1: "Implementation of technologies for access to drinking water with the desalination of seawater" and 2: "Good practices for the care of coastal ecosystems and adaptation to CC with the participation of 86 people (49 men and 37 women). | HS
| COMPONENT 3 . Knowledge management to capture and disseminate lessons learned |  | Outcome 8 | Presentation of lessons learned and data from the innovation process to public and private entities, NGOs and NIE's in the region |  | Lessons learned from the process were presented to public and private institutions in the closing workshop at the National Aquarium - Santo Domingo Presentation at the Adaptation Futures event and dissemination of the step-by-step implementation to NIE's of the AF and other organizations. | HS
[6 empty] | Overall Rating | HS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Rosa Damaris Mejia
| Email: | damarisfull@hotmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Despite the expectations and being an innovation project, we can affirm that the result of the project has been Highly Satisfactory. (HS) Despite the delays caused by the closure of universities due to the Covid 19 pandemic that affected the execution schedule. Thanks to the support of INTEC, the construction and testing of the prototype could be carried out within the expected work ranges. Being an innovative technology, it requires more tests and improvements that will be established with new proposals to enter a second phase and ensure its scaling. Being a modular equipment, it can grow based on the needs of the coastal communities that require it and can be of great help in climate emergency situations or situations where water is required for human consumption in isolated coastal areas. The participation of the communities and local partners in the Province of Montecristi was of great help, especially with the work with the salineros and community leaders of the selected sectors and they provided support for holding workshops and raising community awareness. The closing ceremony and the workshop to disseminate the lessons learned from the project had the participation of more than 35 representatives of public organizations, NGOs and private companies, showing special interest in this type of technologies and offered support to follow up on the process of scallin-up.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
COMPONENT 1. Development of the Technology including the Prototype for Testing at Dominican Republic University
Activity1.1: Design of a prototype to be tested at a Dominican Republic University | At least one thermo solar desalinator prototype designed, built and tested by a Dominican University | Opportunity to develop new modular technologies for the adaptation and mitigation of climate change, of appropriate sizes and costs for coastal communities in the small island countries of the Caribbean and around the world. | Designs made and prototype built. Prototype in testing period in Dominican university | Prototype of thermo solar desalination technology designed, built, tested and endorsed by a Dominican University Laboratory
Activity1.2: Construction of a prototype to be tested at a Dominican Republic University
Activity1.3: Performing the first prototype test at a Dominican University
COMPONENT 2 . Pilot test of prioritized adaptation technology in a selected community in Dominican Republic
Activity 2.1: Selection of the coastal community to test the new pilot adaptation technology | Technical and feasibility studies in the field developed and endorsed by a Dominican University for testing the thermo solar desalination prototype. | Need to develop alternative mechanisms for adaptation to CC based on innovation, with the participation of vulnerable communities for the development of appropriate technologies to improve access to drinking water, with the incorporation of women for the management and operation of adaptive technologies (thermo solar desalination) and the establishment of a disruptive mechanism to transfer the rights generated by technology sales worldwide to a women-led organization. | 2 communities were selected with the support of the City Council of the Municipality of San Fernando de Montecristi, Agrofrontera and INTEC | Technical and feasibility studies developed and endorsed by a Dominican University for the testing of the thermo solar desalination prototype.
Activity 2.2: Consultation and awareness and training of the coastal community where new pilot adaptation technology will be tested | At least two communities in the province of Montecristi awarness and trained in the use of thermo solar desalinisation technology. |  | Two sectors of the Municipality were selected: Las Flores and Aviación, where part of Las Salinas is concentrated. In total, 6 Workshops were given: 1: "Implementation of technologies for access to drinking water with the desalination of seawater" and 2: "Best practices for the care of coastal ecosystems and adaptation to CC with the participation of 86 people ( 49 men and 37 women). | Selection of two coastal sites in Montecristi, sensitization and training of communities (with significant participation of women) in the use of solar thermal desalination technology.
Activity 2.3: Selection of the site in the coastal community where the new pilot adaptation technology will be tested |  |  |  | Prototype of solar thermal desalination technology adapted, built, put into operation, tested and endorsed in a coastal community in Montecristi, Dominican Republic
Activity 2.4: Design of the modified prototype to be tested at the coastal community | A final version of the thermo solar desalination prototype built and in operation in a coastal community in the province of Montecristi. |  | 2 tests were carried out, one at the National Aquarium and the other in San Fernando de Montecristi (Salina Richetti) and the validation and testing processes of the prototype by INTEC were concluded, it is estimated that by the end of April 2023. | Operational manuals and technical reports of research prepared for the implementation of desalinisation thermo solar technology
Activity 2.5: Construction of the modified prototype to be tested at the coastal community
Activity2.6: Performing all the necessary tests of the prototype in the selected
Activity 2.7: Development of a preliminary operating manual | Technical and operation manuals for the prototype developed and endorsed |  | It was delivered by INTEC the: Technical Manual and, Operation Manual and Instructions for Use of the Thermo-solar Desalination System
Activity 2.8: Development of final research Process and development reports | Operational manuals and technical research reports prepared
COMPONENT 3 . Knowledge management to capture and disseminate lessons learned
Activity 3.1: Workshop to disseminate lessons learned for NIEs and focal points of the Adaptation Fund in the Caribbean Islands | Lesson Learned disseminated at least 15 NIE's and AF focal points of the Caribbean Islands | Need to implement innovative technologies that contribute to adaptation to climate change and provide tools to improve the quality of life of marginalized populations in coastal marine areas, especially small islands | The closing workshop was held with the participation of 35 representatives of public institutions of the National Government, NGOs and private companies in the Auditorium of the National Aquarium. The technical information and process will be presented at the Innovation Futures meeting to be held in Montrael - Canada from October 2 to 6. | Lessons learned disseminated among the NIE's and FF focal points in the Caribbean Islands and established the criteria for requesting funds for the implementation of a second phase of the project

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Being an innovation initiative, the development of new technologies is a commitment to achievement, which is why IDDI, in order to achieve the objectives set, has sought alternatives with the design and construction of two prototypes in order to ensure the expected products. The experience in thermo solar technology proposals, especially in the case of desalinators, although it has been put into practice in different countries with prototypes and experiments, the approach as a solution to the problem that many coastal communities present for access to drinking water is still a necessity, which is why all efforts are being made and taking as a reference the lessons learned from other initiatives to achieve the success of the proposal. The support of the universities (INTEC/UTESA) in the Dominican Republic and Riverside in California, USA, will be an important support for the endorsement of solar thermal desalination technology and technical and research contribution to successfully carry out the project's objectives.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The Covid 19 pandemic and the preventive measures adopted by the governments have been a factor that has influenced the development of the activities planned in the project. Although the phase implemented at the time of this report is the design and construction of the thermo solar desalination prototype, the technical accompaniment by the universities and the tests have been delayed, as it was not until September 2021 that activities began in the Dominican Republic and only in February 2022 were the presential activities resumed, meaning that the laboratories were closed and the teaching and research staff were only available virtually. In February 2022, a revision of the work plan was carried out to clarify the dates and establish the necessary times to be able to carry out the tests both in the laboratory and in the field, and we have had the support of INTEC, which has been conducting research on thermo solar technology in order to have alternatives in case the proposal of the company Tecnologías Termosolares SRL is delayed in the validation process of its prototype. This will ensure compliance with the objectives and try to meet the deadlines set in the project. However, the possibility of requesting an extension will be evaluated in case more time is needed to ensure the quality and viability of the prototype.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | To ensure the presentation of the expected product, alternatives have been sought and two prototypes will be worked on, the one initially developed by the company Tecnologias Termosolares SRL and another one presented by the Instituto Tecnologico de Santo Domingo (INTEC), both following the same development vision set out in the proposal. This does not affect the initial proposal presented, but rather strengthens the possibility of having a viable product that meets the proposed objectives.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Laboratory work was carried out in which emphasis was placed on applying safety measures in the use of tools and equipment. For field tests, the previously selected sites took into account the care of the ecosystems and biodiversity of the environment. Due to the type of project, it is not expected to cause any social or environmental impact and mitigation measures have been taken into consideration for the field implementation phase.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Regarding gender policies, the equal participation of men and women in workshops, meetings and consultations was ensured.In order for participation to be equal, local partners were asked to ensure the presence of women in workshops, even though the target audience (salineros) is mostly men. To this end, the leaders of the communities and sectors within the prototype testing area were identified to participate, ensuring that of the 86 people participating in the training and capacity-building process, 43% were women.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The use of clean energies such as solar energy is an important aspect to highlight because combined with techniques such as in this case desalination, they can bring important changes in communities, for obtaining fresh water from sea water, which apart from improve living conditions, it can serve to implement alternative livelihoods in places that, due to climatic effects (desertification and drought), limit the production of crops or livestock to ensure the sustenance of the population.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Use of innovation through the use of clean energy to ensure the supply of drinking water or for irrigation through the desalination of seawater in vulnerable communities due to their geographical location (coasts)
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Advantages of termo-solar desalinization system. Reliable water supply: Desalination helps alleviate water scarcity by providing a steady, sustainable source of drinking water, especially for coastal communities. Independence from traditional sources: Desalination reduces dependence on rainwater, rivers and groundwater, which may be insufficient or contaminated. Remote Accessibility: Desalination plants can be established in remote areas, allowing access to drinking water in regions that previously relied on long-distance transportation or a limited water supply. Industrial Applications: Desalinated water is essential for industries such as agriculture, manufacturing, and energy production. Thermo-solar desalination: a winning combination By integrating solar energy into the desalination process, communities can benefit from a sustainable and eco-friendly solution. Solar-powered desalination systems effectively combine the advantages of both technologies, creating a synergy that leads to greater water security. Key takeaways from solar-powered desalination: Energy efficiency: Solar energy reduces dependence on the electrical grid, making desalination more energy efficient and cost-effective. Environmentally friendly: Solar-powered desalination plants have a smaller carbon footprint, reducing their impact on the environment. Scalability: Solar-powered desalination can be implemented at various scales, from small community systems to large-scale industrial plants. Remote Applications: Solar energy facilitates the deployment of desalination systems in remote areas that lack access to electrical grids. Empower communities with clean wáter The combination of solar energy and desalination technologies has immense potential to bring clean water to communities around the world. By adopting these innovations, we can empower communities, particularly those in water-scarce regions, with access to a reliable and sustainable source of clean water. The benefits of solar-powered desalination go beyond immediate water needs: Improved health and sanitation: Access to safe water significantly reduces the risk of waterborne diseases and improves overall sanitation conditions. Economic Growth and Development: Reliable access to clean water creates opportunities for agricultural development, industrial growth, and a better quality of life. Climate resilience: Solar-powered desalination helps communities adapt to the challenges of climate change, ensuring a constant supply of water
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The coastal areas of the island regions have as a common factor that access to drinking water is limited, either due to few natural sources or due to the effects of climate and geography. In this aspect, the solar thermal desalination plant can be an alternative to obtain drinking water in isolated coastal areas or areas that do not have natural sources for obtaining drinking water.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The achievement of equal participation of men and women in training and capacity-building processes. The demonstrated interest in seeking solutions to the need for drinking water with the use of low-cost technologies and clean energy such as solar energy. The empowerment and desire to improve their capabilities to apply good practices that increase climate resilience.
What measures are/have been put in place to ensure sustainability of the project/program results? | What measures are/have been put in place to ensure sustainability of the project/program results? The dissemination of the lessons learned and the practical applicability of solar thermal systems for the desalination of seawater at low cost and without the use of membranes or high-maintenance and high-cost processes has served as a reference to ensure the interest of different institutions, However, the limitation is the financial capacity to implement this type of initiatives unless they are through financing or subsidies. The IDDI has committed to monitoring and searching for financing sources within the projects it implements with the Adaptation Fund or other initiatives.
What measures are being/could have been put in place to improve project/program results? | Greater participation by private companies and interest from the national government would be necessary to finance and encourage this type of initiatives.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Workshops have been given to public and private institutions and NGOs on the lessons learned from the process.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Workshops have been given to public and private institutions and NGOs on the lessons learned from the process. There is material for distribution, infographics and technical sheets are disponible in the web page of IDDI.
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | They will be available on the website: www.iddi.org a) The design of the thermo-solar desalination system b) The operating manual and technical aspects of the system c) Infographic and technical sheet of the thermosolar desalination prototype d) Presentations of the workshops and courses given
If learning objectives have been established, have they been met? Please describe. | This is divided into two aspects: 1) The use of solar thermal technology for desalination as a viable, economical and scalable process, which can be implemented with the use of clean energy and that contributes to the reduction of the carbon footprint was successful and the experience was replicable. 2) Community participation and interest in having alternatives to reduce their freshwater needs in coastal communities made it possible to raise awareness among them to take care of ecosystems and look for alternatives for the best use of ecosystem services, which in the long run results in climate resilience.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | No problems were identified for data management and the technical team has the necessary experience for the implementation of this type of initiatives.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | The process itself was one of continuous learning since, being an innovation project, each step of progress requires experimentation to obtain results.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | Solar energy, combined with desalination technology, presents an incredible opportunity to address the water scarcity crisis in a sustainable way. Adopting solar desalination not only ensures water security, but also contributes to a sustainable future for generations to come.Desalination is a process that removes excess salt and minerals from seawater, making it safe to drink. This technique has gained importance as a viable solution to address water scarcity. The use of the process through MSF (Multistage Flash Evaporation.) is a practical and economical method.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | Decision B.35.a-35.b/72
Implementing Entity | Instituto Dominicano de Desarrollo Integral
Type of implementing entity | NIE
Country | Dominican Republic
Region | Latin America and Caribbean
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Innovative adaptation financing | Regional | Innovation accelerated |  | Innovative adaptation financing | Regional | Innovation scaled-up |  | Innovative adaptation financing | Regional | Innovation scaled-up
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 0 | Innovative adaptation financing | No innovative practices | 1: Ineffective | 1 | Innovative adaptation financing | Completed innovation practices | 4: Effective | 1 | Innovative adaptation financing | Undertaking innovative practices | 2: Partially effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative technology |  | 1: Ineffective | 1 | Innovative technology |  | 4: Effective