## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | July 01 2023-June 30 2024
| Project Title: | “Building Adaptive Capacity through Innovative Management of Pests/Disease and Invasive Alien Species (IAS) in Bhutan to Enhance Sustainable Agro-Biodiversity and Livelihoods” for Bhutan
| Project Summary: | The project objective is to promote agro-biodiversity activities through efficient and effective management of pests/diseases and invasive alien species (IAS) and has three key components as follows; i. Validate trapping systems as tools adapted to eradicate pests in Bhutan (specifically Giant African Land Snails) ii. Develop strategies and models for sustainable management of pest/diseases and IAS. iii. Awareness generation, capacity building of farmers and other stakeholders on the problems and management of pests/diseases and IAS. The total project budget of USD 243,000 or BTN 18,091,350 (Ngultrum Eighteen million ninety-one thousand three hundred fifty only) is a five-year project implemented by the National Implementing Entity, Bhutan Trust Fund for Environmental Conservation(BTFEC). The Bhutan Food and Drug Authority (BFDA), Ministry of Health (erstwhile BAFRA under MoAF) and Department of Environment and Climate Change (DECC), Ministry of Energy and Natural Resources (erstwhile NECS) are the Executing Agencies. The DECC is the project coordinator and implement the activities that are targeted towards development of national strategy, awareness and advocacy programs, and knowledge products in collaboration with all stakeholders. The BFDA is implementing the core activities of validating traps, reducing pests and IAS, developing diagnostic and response protocol and generating data and models. The executing agencies coordinated by DECC are reporting physical and financial reports to the NIE as per the requirements. The project will benefit farmers who are challenged with the pest (GALS) affecting their livelihood and strengthen the current measures to control or eradicate the pest and IAS through proper strategies, capacity development and generation of information and assessments. The five year project begun it's implementation from 1 July 2022 and is due for completion on 30 June 2027.
| Database Number: | AFRDG00056 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Bhutan Trust Fund for Environmental Conservation | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Bhutan | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Gyelpozhing, Mongar, Bhutan | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2021-10-21
IE-AFB Agreement Signature Date: |  | 2022-02-07 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2022-05-18 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2026-08-01
| Original Completion Date: | 2026-01-01
Revised Completion Date after approval of extension request (if applic) |  | NA
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception workshop for the project was conducted on 18 May 2022 among relevant stakeholders. The final outcome and project inception report was submitted to the Adaptation Fund Board Secretariat. | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://www.bhutantrustfund.bt/public_page/newsdetails | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Dr. Karma Tshering | Dominican Republic
| Email: | karma@bhutantrustfund.bt | Ecuador
| Date: | 2023-01-17 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Mr. Tshering Dorji | Equatoral Guinea
| Email: | tsheringdorji@mof.gov.bt | Eritrea
| Date: | 2024-02-02 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Mr. Kinley Tshering | Fiji
| Email: | kinley@bhutantrustfund.bt | Finland
| Date: | 2023-01-17 | France
| Executing Agency |  | Gambia
| Name: | Mr. Chimi Dorji, Department of Environment and Climate Change | Georgia
| Email: | chimidorji@moenr.gov.bt | Germany
| Date: | 2023-01-17 | Ghana
| Executing Agency |  | Greece
| Name: | Mr. Sonam Dorji N, Bhutan Food and Drug Authority | Grenada
| Email: | sdorjin@bfda.gov.bt | Guatemala
| Date: | 2023-01-17 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 30th June 2024 |  |  |  | Financial information PPR 2: cumulative from project start to 30th June 2024 |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 30th June 2024 | 53012 |  |  | Estimated cumulative total disbursement as of [30 June 2024] | 98499.8 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | A total grant amount for this project Grant No MB214Y22 is USD 217,970.24 of which BTN USD 53,012.04 has been disbursed since 30th June 2023. |  |  | Add any comments on AF Grant Funds. (word limit=200) | A total grant amount for this project (Grant No MB214Y22) is USD 217,970.24 of which BTN USD 98,500 has been disbursed since 30th June 2024. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
*Refer Financial Report
INVESTMENT INCOME | Adaptation Fund account operates as Current Account |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Activity 1.1.2: Collaboration meeting with technical departments | 3548.19
| Activity 1.1.1: Field visits and Stakeholders meeting | 5421.69 |  |  | Activity 1.1.2: Collaboration meeting with technical departments | 2439
| Activity 2.1.4: Field Verification | 581.54 |  |  | Activity 1.1.1: Field visits and Stakeholders meeting | 1829
| Activity 1.2.1: Contractual services(Local) | 5435.05 |  |  | Activity 1.1.3: Tools and equipment(Traps)
| Activity 1.2.2: Stakeholders Consultation | 3012.05 |  |  | Activity 2.1.4: Field Verification
| Activity 1.2.3: Sensitization/Training Workshop | 5421.69 |  |  | Activity 1.2.1: Contractual services(Local) | 6097
| Activity 2.2.1: Contractual services | 4819.28 |  |  | Activity 1.2.3: Sensitization/training workshop | 4878
| Activity 2.1.3: Institutional capacity building | 3452.11 |  |  | Activity 1.2.5: Print and publication | 487
| Activity 1.1.4: Plants and equipments (traps) | 5060.24 |  |  | Activity 1.3.1: Tools and equipment | 1829
| Activity 2.1.1: Contractual services | 8072.89 |  |  | Activity 1.3.2: Sensitization/training | 2072
| Activity 2.2.2: Stakeholders workshops | 1807.23 |  |  | Activity 2.1.3: Institutional capacity building | 3342.28
| PMU: IT equipments | 1204.82 |  |  | Activity 2.2.1: Contractual Services
| PMU: Field gear and equipments | 951.81 |  |  | Activity 2.2.2: Information Technology Equipments | 3653.05
| TOTAL | 48788.58 |  |  | TOTAL | 26626.33
*Refer Semi-Annual Financial Reports (1/7/2022-31/12/2022 & 1/1/2023-30/6/2023)
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Activity 1.1.1: Collaboration meeting with technical depart,ent (NPPC, BNC, etc) | 2409.64 | 2023-12-31 |  | Activity 1.1.1: Collaboration meeting with technical departments | 2439.0244 | 2025-06-30
| Activity 1.1.2: Field visit and stakeholders consultation | 1807.23 | 2023-12-31 |  | Activity 1.1.2: Field visits and Stakeholders meeting | 1585.3659 | 2025-06-30
| Activity 1.1.3: Tools and equipment (Traps) | 9638.55 | 2024-06-30 |  | Activity 1.1.3: Tools and equipment(Traps) | 9756.0976 | 2025-06-30
| Activity 1.2.1: Contractual services | 8554.22 | 2024-02-28 |  | Activity 1.2.1: Contractual services(Local) | 3048.7805 | 2024-12-31
| Activity 1.3.1: Sensitization/trraining workshops | 4819.28 | 2023-12-31 |  | Activity 1.2.3: Sensitization/training workshop | 2560.9756 | 2024-12-31
| Activity 1.2.4: Print and publication | 481.93 | 2023-12-31 |  | Activity 1.2.4: Print and publication | 609.7561 | 2024-12-31
| Activity 1.3.1: Tools and equipments | 1807.23 | 2023-12-31 |  | Activity 1.3.1: Sensitization training workshops | 10134.7 | 2024-12-31
| Activity 1.3.2: Sensitization/training | 240.96 | 2023-12-31 |  | Activity 2.2.1: Workshops/Meetings | 5487.8049 | 2024-03-30
| Activity 2.2.1: Contractual services | 5421.69 | 2024-03-31
| Activity 2.2.2: Information Technology Equipments | 2530.12 | 2023-12-31
| TOTAL | 37710.84 |  |  | TOTAL | 35622.5049
USD conversion rate for BTN was at 82.00 | [7 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Environmental sustainability | The application of commercial traps will need to further undergo impact assessment on the surrounding environment and native species. An initial assessment of existing native species will be carried out to generate a baseline of existing flora and fauna. The selection of traps will consider all environmental safeguards. | Rapid inventory of existing native flora and fauna at the project area has been completed
Mismatch of overall project goals and activities supporting the goal will affect achivement | With the current size of funding, erradication of GALS will be a challanging task. | Stock-taking of the progress and identification of risk, challenges, gaps and opportunities was convened in Year II, second semi-reporting period.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Lack of provisions on the diversification of ideas | Current engagement primarily involves the testing of different trapping systems but do not acknowledge the role of handpicking methods to erradicate the GALS. While trapping systems are important, this alone may not be able to erradicate the pest. | Set of recommendations were outlined in the ideation workshop as a part of diversification of the idea to support project in achieving the objectives
Spread of pest outside project area | While we implement the project at Gyelposhing, Mongar Dzongkhag, we are now confronted with the outbreak of GALS at Autsho, Lhuntsi Dzongkhag which needs equal atention as project area. | We have considered new infested area under the scope of this project as a part of overall erradication plan.
Public and participation in the project is minimal. | Efforts have been made to onboard local communities in the project implementation. However, no significant participation has been seen to date. | Following decisions were made in our recent meeting with Local Government (LG) and communities; - Executing entities to bring on board the LG Administration (Saling, Monga, Tsenkhar and Chali) and strengthen public participation in the project implementation. - The PMU to liases/communicate/request Mongar Dzongkhag Administration for the support including administrative support such as issuance of Notifications/Circulars as required. (BFDA to apprise/follow-up with dzongkhag Administration for the issuance of notification/circular). - Gewog Administrations to liaise with BFDA field office and identify a day in a month akin to Zero Wast Hour, as appropriate for the collection and disposal of the GALS. This will go a long way in our effort to achieve our collective goals. - BFDA in close coordination with the field office and LG to try different trapping system including size and baits of the system, using best available sciences and past interventions made elsewhere. - LG through Dzongkhag Administration to apprise Ministry of Finance to consider annual budget to prevent recurrence of the GALS.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
There was risks but minimal within control like spread of spread of pest outside of project area and lack of provision of diversification of ideas for eradication of GALS . However, collective approach to address and mitigate risks with relevant stakholders were taken through workshop, proper planning and design and inclusion and management of adaptative innovative ideas. Proper management plan for other infected areas are kept in place through constant monitoring, collection and installation of traps by local communities in coordination with technical working group and community leaders.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  |  | Compliance with environmental standards and policies |  |  | Ensured that project meets the highest fudiciary standards and abide by the Food and Nutrition Security Policy of the Kingdom of Bhutan (2014), Plant Quarantine Act of Bhutan, 1993, Bio-security policy of the kingdom of Bhutan and Bhutan's nationally determined contribution
2 - Access and equity |  |  |  | Access to project tools, technologies, training and resources to affected farmers |  |  | Since inception 60 affected households had access to traps use, knowledge and resources.
3 – Marginalized and vulnerable Groups |  |  |  | Targeted Program designed for children in Project site |  |  | Advocacy programs for children in school. Hence, during TWG consultation public schools are chosen as main stakeholder a program targetted for children to understand implication of GALS
4 – Human rights |  |  | NA | NA | NA | NA | NA | NA | NA
5 – Gender equality and women’s empowerment |  |  |  | Ensured participation of women in training and access to Technology . Use expertise of Tarayana foundation experience in women empowerment |  |  | Equal representation of male and female encouraged in programs, access to techonlogy and tools. Due to constant guidance from local leaders project achieved more than 60 women beneficiary of which 40 were men.
6 – Core labour rights |  |  | NA | NA | NA | NA | NA | NA | NA
7 – Indigenous peoples |  |  | NA | NA | NA | NA | NA | NA | NA
8 – Involuntary resettlement |  |  | NA | NA | NA | NA | NA | NA | NA
9 – Protection of natural habitats |  |  |  | Removing of GALS to ensure protection of natural habitats as they are known to infest the forest and farm lands |  |  | Installation of traps, collection, monitoring and disposal of trapped GALS during its lean season to further stop infesting by local communities, clusters region, forest communities and Technical Working Group
10 – Conservation of biological diversity |  |  |  | Generate baseline of existing flora and fauna | NA | NA | Rapid biodiversity assessment is completed | NA | NA
11 – Climate change |  |  | NA | The project will not emit any greenhouse gas emissions | NA | NA | NA | NA | NA
12 – Pollution prevention and resource efficiency |  |  | NA | NA | NA | NA | NA | NA | NA
13 – Public health |  |  | GALS carry pathogens including parastic nematode capable of causing meningitis | Removal of the GALs will ensure positive impact on human health of the people living in the community |  |  | Collection, removal and disposal of GALs during peak season especailly during wet season. Advocacy program by health officials to practice hygiene to avoid negative impact on human health.
14 – Physical and cultural heritage |  |  | NA | NA | NA | NA | NA | NA | NA
15 – Lands and soil conservation |  |  | Baits and chemicals in traps | Use of traps free of baits and chemicals |  |  | Choosing of baits and chemicals is done wisely to ensure that there is no impacts on land and soil. Also minimal use of salt is encouraged.
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | Yes
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | Risks identified, discussed and decisions taken to mitigate the risks
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The BTFEC in coordination with EE's formed a Technical Working Group(TWG) to technically guide project implementation and ensure each sectors monitor and ensure compliance with ESP. Furthermore, monitoring officer and team from BTFEC conducted semi-annual monitoring 31 December 2023 and 30 June 2024 monitoring. The team monitoried and advised on to ensure full compliance.
Have the implementation arrangements been effective during the reporting period? |  | Yes, although every year implementation phase offers different lessons. Proper consultation and engagement with right stakeholders have been effective during each reporting period.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The TWG with members from BFDA, NPPS (National Plant Protection Center) and UWIFoRT (Ugyen Wangchuck Institute for Forestry Research and Training, erstwhile UWICER) has conducted regular monitoring at project site in coordination with Agriculture Research and Development Center, Mongar.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The TWG guided and conducted rapid assessment of flora and fauna site to generate baseline data and to reduce risk to native species from snail traps.
*Refer Technical Progress Reports
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP] | NA
USP 2: [name the USP] | NA
USP 3: [name the USP] | NA
USP 4: [name the USP] | NA
USP 5: [name the USP] | NA
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | No
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes. Out of 250 target community members to be engaged for the outreach program, 60% is targeted at female/women and 40% at male. Implementation of outreach program is ongoing and will be conducted until management of GALS is achieved.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Outreach and awareness on impact of pests/diseases and IAS on agriculture and environment |  | Communities engaged in outreach programs | 0 | 250 (60% female and 40% male) | Good
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
Compared to the start of project female participation has dramatically increased. Although they are reluctant to participant and forthcoming. Many women and female participants are encouraged due to constant awarness program from project implementers |  | Good
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The BTFEC has advised the EE's to ensure that gender representation be ensured in all project activities. A gender focal at the BTFEC sends constant reminder to ensure GP compliance
Have the implementation arrangements at the IE been effective during the reporting period? |  | The inclusion of both male and female participants in project activities and meetings have ensured good representation.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The DECC and BFDA has ensured gender representation in all project activities.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Till date there has been 2 training and consultative events and out of a total of 84 participants, 60 male and 24 females have been engaged. In the 2nd year of the FY 2023-2024, conducted one consultative meeting and one workshop 46 participants (14 female participated)
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | NA
* Refer Tehnical Progress Reports
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
NA |  | NA

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Reduce and eradicate pest and invasive alien species to save crops and biodiversity |  | Outcome 8 | 1. Collaborative meeting with technical department. 2. Field visit and stakeholders' consultation. 3. Procurement of tools and equipment (Traps). |  | Field visit and stakeholders consultation workshops conducted. They are :1. Import Risk Analysis Training Program - Gelephu, October 26th to 30th, 2023 (Report attached) 2. TWG Review Meeting, Field Traps Monitoring, and GALS Eradication Program Implementation-September 20-22, 2023 (Report attached) | HS
|  |  | Outcome 7 | Protocols and response guides developed |  | 1.IdeationWorkshop to build adaptative capacity of people through InnovativeManagement of GAL conducted 11-13 May 2024 (Report attached) | HS
|  |  | Outcome 2 | Upscale to other communities |  | Uupscaled from next GALS emerging season to Autsho, Lhuentse, Sjongkhar and Gelephu. | S
| Develop systems and models for pest management |  | Outcome 7 | Strategy for pest/disease and IAS management developed |  | Preminilariy workshop with local communties, Techinical Working Group, NIE, EEs and DAs conducted. The strategy will developed using locally best fit ideas and knowlege using baited with whey and sugar solution. | S
|  |  | Outcome 8 | Data and models generated for pest management |  | A brief story telling by stakeholders of project including communities living with GALS produced. The video highlights experience sharing and benefit occured as a result of awareness, advocacy, workshop, engagements and use of Traps within 2 years since start of the project inculding reduced impact of the GALS to farms and livelihood. | S
| Project management |  | Outcome 4 | Timely Progress Reporting Submission |  | The IE submits reminder a month before deadline for submission of PPR to project management unit(PMU) Department of Environment and Climate Change. Since inception, PMU submitted 2 PPR(s) July 2022- June 2023 & July 2023-June 2024 to the NIE. Each reporting period brings different lessons, hence each lessons will be used to ensure on time and correct submission of PPR from EE to NIE and then finally to the Adaptation Fund. | S
[6 empty] | Overall Rating | S
The National Implementing Entity - Bhutan Trust Fund for Environmental Conservation in consultation with the Designated Authority - Department of Marco fiscal and Development Finance and Executing Entities- Department of Environment and Climate Change, Bhutan Food and Drug Authority conducts timely joint document review and physical verification of the project progress every end of six months ( 30 June & 31 December). The positive progress made in the last during reporting periof ( July 2023-30 June 2023) inculde : 1) Key stakeholders inculding more than 60 Households/communities living with GALs in the community trained are thoroughly used to using traps, collection and monitoring methods. Led by clusters team , dessungs are engaged in collection and disposal of collected GALs in proper disposal area. As result of this timely intervention, communities report experiencing reduced in number of GALs since start of this project ( Detailed video/story telling from local communities attached with the report). There has been no major negative progress however, there is a lack of community participation and engagment in the project despite constant awarness and advoacy. Therefore, led by National Implementing Entity, Technical working group and local leaders advises for timely intervention and directives in completing activities and meeting the targets within deadline. Possible reason that could contribute to negative progress GALS and other invasive species are through porous transboundary border is possible. Transboundary pest/disease and IAS management plan needs to be strategized and explored through this project.
| Name: | Kinley Tshering
| Email: | kinley@bhutantrustfund.bt
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The National Implementing Entity - Bhutan Trust Fund for Environmental Conservation in consultation with the Designated Authority - Department of Marco fiscal and Development Finance and Executing Entities- Department of Environment and Climate Change, Bhutan Food and Drug Authority conducts timely joint document review and physical verification of the project progress every end of six months ( 30 June & 31 December). The positive progress made in the last during reporting period ( July 2023-30 June 2023) inculde : 1) Key stakeholders inculding more than 60 Households/communities living with GALs in the community trained are thoroughly adapted to using traps, collection and monitoring methods. 2) Led by clusters team , dessungs are engaged in collection and disposal of collected GALs in proper disposal area. As result of this timely intervention, communities report experiencing reduced in number of GALs since start of this project ( Detailed video/story telling from local communities attached with the report). 3) Women being first contact person coming from agriculture household are benefitting from this project having reported higher percentage of participation in GALs management programs and access to tools and traps(Photographic evidence in the attached report). Overall the trap validation and model assesment is on track. 4) There has been no major negative progress however, there is a lack of community participation and engagment in the project despite constant awarness and adovacy. Therefore, led by National Implementing Entity, Technical working group and local leaders advises for timely intervention and directives in completing activities and meeting the targets within deadline. Possible reason that could contribute to negative progress is increased in GALS population even through adaptative innovative practices through porous transboundary border. Transboundary pest/disease and IAS management plan will be strategized and explored through this project.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Reduce and eradicate pests and invasive alien species to save crops and biodiversity. |  | Outcome 8 | 1. Collaborative meeting with technical departments (NPPC,NBC) and field visit and consultations. 2. Tools and equipment (Traps). 3. Stakeholder consultation conducted for development of protocols and response guide. 4. Print and publication for awareness creation among communities. |  | 1. Virtual Meeting of TWG for AF project smooth implementation 2. Conducted field visit and stakeholders consultation at Gyalposhing and Lingmethang, Mongar. 3. Awareness and collection campaing at Autsho, Lhuentse, Sjongkhar and Gelephu. 4. The procurement of traps for the trials was initiated for next trap set up. 5. Capacity building for 30 households in clusters 15 each from Gyalpozhing and Limethang implemented. 6. Stakeholders Awareness and campaign on Giant African Land Snails (GALS) was organized for Gyalpozhing and Lingmethang. | HS
| Develop systems and models for Pest management |  | Outcome 7 | 1. Stakeholder workshop and field verification for strategy and framework development. 2. Data and tools generated for pest management. |  | 1. Implemented GALS TWG review meeting and capacity building of relevant officials (18 Sept to 1 Oct 2023) at Mongar, Sjongkhar and Gelephu. 3. Implemented “ Consultation meeting on draft development of protocol and response guidelines for GALS outbreak and management” at Gelephu 26-30 Oct 2023. 4. Printed materials to aid eradication program. 5. Implemented mass awareness on invasive plant species 6. Workshop on development of models and assessment and protocols and response guide on GALS, w.e.f 15-16 May 2024 at Druk Zhongar Hotel in Mongar | HS
| Project Management |  | Outcome 4 | Project progress reporting meetings and procurement of equipment. |  | 1. The project focals meet periodically to discuss the progress report and prepare the next work plan. Procured office equipment, field gear and laptops. | HS
[6 empty] | Overall Rating | HS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Sonam Dorji N
| Email: | sdorjin@bfda.gov.bt
3.8 million
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500) | [7 empty] | 7 lakh
Despite some field issues from the household engaged in trapping process, we are able to install and collect data from the 1st installation of GALS trap. Mass capaing at Gyalposhing was carried and proved to be effective in the eradication program along with trappings. All the information and data will be useful for developement of protocol and response guide and development of system and models for pest management.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | Reduce and eradicate pests and invasive alien species to save crops and biodiversity. |  | Outcome 8 | 1. Collaborative meeting with Technical Department(NPPC & NBC) 2. Field visit and stakeholders consultations. 3.Tools & equipment |  | 1. Technical working group formed through consultation meeting with technical agencies. 2. Technical group members visited field at Gyelpozhing and Limithang area and familiarized project stakeholders of GALs outbreak areas and updated on the current status of snails and educated on upcoming innvovative GALS interventions and technology. 3. Tools, Traps, equipment and materials procured, capacity building for household and communities conducted.4. Conducted stakeholder consultation for initiating development of protocol and response guidelines for GALS outbreak and management, attended by 21 participants from various agencies. This workshop created awarness and sentized stakeholders on plant biodiversity and phyosanitary requirements. | HS
| Develop systems and models for Pest management |  | Outcome 7 | 1. Stakeholder Workshops. 2. Information Technology equipment. |  | 1.Conducted project stakeholders meeting to prepare data collection. 2. Conducted training workshop on Ecological Niche Modeling of GALS: adopting best practices for predicting occurences and outbreak uder different future climate scenarios. 3. Visited project field completed to conduct situational update and carry rapid inventory of exisiting flora and fauna. | HS
| Project Management |  | Outcome 8 | 1. Field gear/equipment. 2. Progress reporting |  | 1. The project focals of executing agencies met periodically to update and prepare project performance report. 2. For smooth and effective management of project, a set of laptop procured. 3. Field gear an equipment procured. 4. Project performance submitted to National Implementing Entity semi-annually i.e every 15 July for 30 June and 15 January for December end. | HS
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Chimi Dorji
| Email: | chimidorji@moenr.gov.bt
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | For the reporting period, numbers of risks and implementation gaps identified. However the Technical Working Group conducts periodic monitoring and advise the Cluster Coordinators at project site to ensure smooth implementation of project activities. The executing entities' project focal's met towards the begining of every 1st week of July and 1st week of Janaury and discussed progress report for the project, compiled and submitted to National Implementing Entity.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Reduce and eradicate pests and invasive alien species to save crops and biodiversity. | Types of trapping systems adapted and used. | 0 | Two traps baited with whey and sugar solution and a total of 60 traps used. 2 Traps and equipment procured for set up for data collection from August to September 2024. Two type of bait traps will be deployed to study the effectiveness. | 2
| Protocols and response guide developed | 0 | On Track (Final Draft) | 1
| Farmers and communities with access to traps. | 0 | 30 Households for the second year of implementation. Total 60 -40 female and 20 male accessed traps since inception. | 150 farmers (90 Female and 60 male) with access to traps
Develop strategy and models for pest management | Strategy/framework developed. | 0 | Consultation conducted and draft plan drawn | 1
| No. of officials trained to respond to pest & IAS management (gender disaggregated) | 18 | 60 | 15
| Models and assessments on climate change impacts on pests | 0 | On Track ( Data Collection) | 1
Outreach and awareness on the impact of pests/diseases and IAS on the agriculture and environment | Number of innovative solutions on pest/diseases and IAS management received | 0 | Begin from 3 year | 3
| Opportunity given to youth through universities for innovative solutions competition. | 0 | Begin from 3 year | 100
| Number of awareness programs | 0 | Begin from 3 year | 2
| Communities engaged in outreach progam | 0 | Begin from 3 year | 250 (60% female and 40% male)

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | There were complaints from Household engaged in GALS Trapping of decayed and foul smells from trapped snails. However TWG reviewed the monitoring procedure and will be trained from the next season so that insect can be collected during short period. Identified cluster coordinators and assigned roles for trap installation and data collection. Traps reviewed and implementation plan has been revised.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Activities are on track and implemented timely according to the project document.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | Project outputs were implemented as planned in orginal document without deviation and no changes were made in the project design. Sub-activities were added to contribute to the output level achievement.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Environmental and social safeguards played instrumental in directly guiding project interventions to avoid and mitigate unwanted negative impacts.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | During implementation of project activities, strong emphasis was placed on engagement of both gender. The trainings, meetings, awareness programs and field implementation activities had adequate gender representation. The inclusion of women in the above activities greatly facilitated on-ground effectiveness of measures undertaken for GALS trapping since the impact was directly on agriculture, where women were more involved. For the capacity building of household engaged for trapings system from Gyalposhing and Lingmethang, 30 participants trained (16 female, male 14). Implemented stakeholders meeting and workshop on development of protocol and response guide and assessment model (14 female participants involved) inthe second year 2023-2024.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | AFRDG00056;
Implementing Entity | Bhutan Trust Fund for Environmental Conservation
Type of implementing entity | NIE
Country | Bhutan
Region | Asia-Pacific
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female beneficiaries | 60% |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 100% |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness