{"text_format":"1","workbook":"xlsx","n_sheets":12,"sheets":["Survey tool_comp 1","Survey tool_comp 2 ","Survey tool_Comp 3","Survey tool_Comp 4","Survey tool_Comp 5","Component 1.","Component 2","Component 3","Component 4 ","Component 5","Stakeholder Mapping","Tables"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":5,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Survey tool_comp 1","index":0,"n_rows":27,"n_cols":7,"rows_kept":27,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[]
[null,"NO","Component 1 ","Survey Question","Interviewee","Beneficiary ","Data Collection Method "]
[null,1,"Safeguarding forest and water resources through\n strategic protection and restoration solutions ",null,"Belize Forest Department, National Biodiversity Office (NBIO), Protected Areas Conservation Trust (PACT), National Hydrological Service, Department of Environment (DOE), Agriculture Department (AG), Lands Department, Project Managment Unit","Communities "]
[null,1.1000000000000001,"Expected Outcomes ",null,null,"Communities "]
[null,"1.1.1","Water quality improved for watersheds ",null,null,"Women's Group "]
[null," ","Number of rivers with improved climate adaptive management systems ",null,"Belize Forest Department, National Hydrological Service, National Biodiversity Office (NBIO)","Communities ","Kobotool box"]
[null,"1.1.2","Increased understanding of climate change impacts visible in communities ",null,null,"Elderly "]
[null,"1.1.2.1","Acreage of Riparian forests in rivers restored ",null,"Belize Forest Department, National Biodiversity Office (NBIO)","Women's Group ","Kobotool box"]
[null,"1.1.2.2.","Biodiversity Conservation and Ecosystems Management report Completed Riparian ",null,"Belize Forest Department, National Biodiversity Office (NBIO)",null,"Kobotool box"]
[null,1.2,"Expected concrete Outputs ",null,null,"Women's Group "]
[null,"1.2.1","Restoration strategies developed "]
[null,"1.2.1.1","Number of males vs. females participating in rstoration activites",null,"Belize Forest Department, National Biodiversity Office (NBIO)",null,"Kobotool box"]
[null,"1.2.1.2","Forest restoration strategy and Implementation Plan Completed \n",null,"Belize Forest Department, National Biodiversity Office (NBIO), Department of Environment (DOE)",null,"Kobotool box"]
[null,"1.2.1.3","Impact on Land Use Change on Micro and Macro Invertebrates Research Report completed ",null,"Belize Forest Department, National Biodiversity Office (NBIO), Department of Environment (DOE)",null,"Kobotool box"]
[null,"1.2.2","Pilot water quality restoration activities in watershed"]
[null,"1.2.2.1","Number of capacity development activities for project beneficiaries in watershed restoration and water quality management and monitoring","Baseline has to be Zero","Belize Forest Department, National Biodiversity Office (NBIO)","Communites , Women's Group ","Kobotool box"]
[null,"1.2.2.2","Community based water quality sub projects approved for Funding\n","Baseline has to be Zero ","National Hydrological Service, Belize Forest Department, National Biodiversity Office (NBIO), Village Council",null,"Kobotool box"]
[null,"1.2.2.3","Focus group consultation per beneficiary Community on the respective approved subprojects ","Baseline has to be Zero","Belize Forest Department, National Biodiversity Office (NBIO), Protected Areas Conservation Trust (PACT)",null,"Kobotool box"]
[null,"1.2.2.3","Number of reports, strategies and plans developed and disseminated through various social media platforms ","Belizeline has to be Zero ","Belize Forest Department, National Biodiversity Office (NBIO)",null,"Kobotool box"]
[null,"1.3.3","No. direct beneficiaries "]
[null,"1.3.3.1","No of women who participate in watershed management exchange programs ","Baseline has to be Zero","Belize Forest Department, National Biodiversity Office (NBIO), Protected Areas Conservation Trust (PACT)",null,"Kobotool box"]
[null,"1.3.3.2","No of Schools who participate in outreach programs","Baseline has to be Zero","Protected Areas Conservation Trust (PACT), National Biodiversity Office (NBIO)",null,"Kobotool box"]
[null,"1.3.3.3","No of women's organization that participate in education and outreach programs ","Baseline has to be Zero","Belize Forest Department, National Biodiversity Office (NBIO)",null,"Kobotool box"]
[null,"1.3.3.4","No of women with project roles in implementing agencies","Baseline has to be Zero","Belize Forest Department, National Biodiversity Office (NBIO)",null,"Kobotool box"]

{"sheet":"Survey tool_comp 2 ","index":1,"n_rows":28,"n_cols":8,"rows_kept":28,"cut":false,"hidden":false,"merged":[]}
[]
[null,2,"Component 2: Combating wildfires through adaptive management",null,null,"Belize Forest Department, Agriculture Department (AG), National Fire Service","Communities "]
[null,2.1,"Expected Outcomes",null,null,null,"Communities "]
[null,"2.1.1","Enhanced protection from fires"]
[null,"2.1.1.1","Number of communities with increased capacity to address wildfires",null,"Name the communities that now have an increased capacity to address \nwildfires due to adaptive management efforts?","Belize Forest Department, Protected Areas Conservation Trust (PACT)",null,"Kobotool box"]
[null,"2.1.1.2","Number of community fire brigades established",null,"How many community fire brigades have been established? ","Belize Forest Department, Project Manager (PACT)"]
[null,"2.1.1.3","Number of trained males vs. females in community fire brigades established",null,"Have both males and females been trained in your community fire brigades? If so, how many of each gender?","Belize Forest Department, Sarteneja Village Council , Ladyville Village, Hattieville Village",null,"Kobotool box"]
[null,"2.1.1.4","No. of women and men who participate in wildfire preparedness and response training\n",null,"How many women and men in your community have participated in wildfire preparedness and response training?","Belize Forest Department, Village Council",null,"Kobotool box"]
[null,"2.1.1.5","No. of women targeted in communication and fire prevention messages",null,"Have you observed specific efforts to target women in communication and fire prevention messages? How\n many women have been reached through these efforts?","Belize Forest Department, Village Council",null,"Kobotool box"]
[null,"2.1.1.6","Number of NGOs, CBOs and Regulatory Agencies with Increased Capacity to address\n wildfires",null,"How many NGOs, community-based organizations (CBOs), and regulatory  have an increased \ncapacity to address wildfires?","Belize Forest Department, Village Council",null,"Kobotool box"]
[null,"2.1.1.7","Wildfire Management Entities Registry developed ",null,"Is there a registry of wildfire management entities developed for your region or community?","Belize Forest Department",null,"Kobotool box"]
[null,"2.1.1.8","Fire Management - Network Institutional framework completed",null,"Has a Fire Management Network Institutional Framework been completed in your area?","Belize Forest Department",null,"Kobotool box"]
[null,"2.1.1.9","Contract signed for procurement of fire tool kits ",null,"Do you know if a contract for the procurement of fire tool kits has been signed for your community?","Protected Areas Conservation Trust (PACT)",null,"Kobotool box"]
[null,"2.1.1.10","Fire toolkits, gears and equipment procured",null,"Has your community received fire toolkits, gears, and other equipment for wildfire management?","Protected Areas Conservation Trust (PACT)",null,"Kobotool box"]
[null,2.2000000000000002,"Expected concrete Outputs"]
[null,"2.2.1","Fire management strategy developed and implemented"]
[null,"2.1.1.1","Number of Fire brigades in pilot communities",null,"How many fire brigades have been established in the pilot communities in your area?","Belize Forest Department, Sarteneja Village Council, Ladyville Village, Hattieville Village",null,"Kobotool box"]
[null,"2.1.1.2","No. of women and girls who are members of pilot fire brigades",null,"How many women and girls are members of the pilot fire brigades in your community?","Belize Forest Department, Sarteneja Village Council, Ladyville Village, Hattieville Village",null,"Kobotool box"]
[null,"2.1.1.3","Community Fire Brigade training manual and guide completed",null,"Has a community fire brigade training manual and guide been completed for your area?","Belize Forest Department"]
[null,"2.1.1.4","Number of contracts signed for installation of elevated water storage ",null,"How many contracts have been signed for the installation of elevated water storage systems in your community?","Protected Areas Conservation Trust (PACT)",null,"Kobotool box"]
[null,"2.1.1.5","Number of water storage reports submitted",null,"How many reports regarding water storage have been submitted in your area?","Sarteneja Village Council , Hattieville Village",null,"Kobotool box"]
[null,"2.1.1.6","Number of capacity development consultation with targeted communities on improved fire management practices",null,"Have there been capacity development consultations with your community on improved fire management practices? \nIf so, how many?","Belize Forest Department, Sarteneja Village Council , Ladyville Village, Hattieville Village",null,"Kobotool box"]
[null,"2.1.1.7","Focus groups consultation with the targeted community by the PMU and relevant stakeholders in subproject design ",null,"Have there been focus group consultations between your community and relevant stakeholders on subproject design?","Belize Forest Department, Project Manager (PACT), Sarteneja Village Council , Ladyville Village, Hattieville Village",null,"Kobotool box"]
[null,"2.1.1.8","Assessment report of fire response region in the BNPAS completed ",null,"Has an assessment report of the fire response region in the BNPAS been completed in your area"]
[null,"2.1.1.9","Community based wildfire management sub-projects approved for funding ",null,"Have any community-based wildfire management sub-projects been approved for funding in your area?","Protected Areas Conservation Trust (PACT), Village Council",null,"Kobotool box"]
[null,"2.1.1.10","Number of Reports/strategies/plans and communication tools developed and disseminated to increase awareness on fire management",null,"How many reports, strategies, plans, or communication tools have been developed and shared  to \nincrease awareness of fire management?","Belize Forest Department",null,"Kobotool box"]
[null,"2.1.1.11","National wildfire strategy and Action Plan for Brigades Completed",null,"Has the National Wildfire Strategy and Action Plan for Brigades been completed for your community or region?","Belize Forest Department",null,"Kobotool box"]
[null,"2.1.1.13","Training manual for BNPA firefighter completed ",null,"Has a training manual for BNPA firefighters been completed in your area?"]

{"sheet":"Survey tool_Comp 3","index":2,"n_rows":24,"n_cols":7,"rows_kept":24,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[]
[null,"NO","Description of Indicators","Survey Question ","Executing Agencies","Beneficiary","Data Collection Method"]
[null,3,"Component 3: Creating Opportunities to Support Alternative Livelihoods",null,"Inter-American Institute for Cooperation on Agriculture (IICA), Agriculture Department (AG), Beltraide MOE","Communities ","Interview"]
[null,3.1,"Expected Outcomes"]
[null,"3.1.1","Increased number of livelihoods"]
[null,"3.1.1.1","Number of persons with an alternative form of financial income","How many individuals have gained an alternative form of financial income through your agency’s interventions?","Inter-American Institute for Cooperation on Agriculture (IICA), Agriculture Department (AG), Beltraide MOE , Human Development , National Women's Commission",null,"Kobotool box"]
[null,"3.1.1.2","Number of males vs. females with an alternative livelihood","How many males and females have secured alternative livelihoods through your programs? Please provide the numbers for each gender.","Inter-American Institute for Cooperation on Agriculture (IICA), Agriculture Department (AG), Beltraide MOE",null,"Kobotool box"]
[null,"3.1.1.3","Number of persons trainned to operate businesses","How many individuals have been trained to operate businesses as part of your agency's programs?",null,null,"Kobotool box"]
[null,"3.1.1.4","Number of males vs. females trained","How many males and females have been trained to operate businesses through your programs? Please provide the numbers for each gender.",null,null,"Kobotool box"]
[null,"3.1.1.5","No of male and female rural farmers aware of ecological dynamics and\ntechnological innovations ","How many rural farmers (male and female) have become aware of ecological dynamics and technological innovations due to your agency’s efforts?",null,null,"Kobotool box"]
[null,"3.1.1.6","Percentage of rural women participating in agroforestry ","What percentage of rural women  are now participating in agroforestry initiatives supported by your agency?",null,null,"Kobotool box"]
[null,"3.1.2","Increased number of climate smart food production systems"]
[null,"3.1.2.1","Number of functional climate smart food production systems established","How many functional climate-smart food production systems have been established as part of your programs?",null,null,"Kobotool box"]
[null,"3.1.2.2","Number of functional climate smart systems managed by male vs. female","How many of the established climate-smart food production systems are managed by males vs. females?",null,null,"Kobotool box"]
[null,"3.1.2.3","Number of capacity development consultation with targeted communities on improved food production strategies","How many capacity development consultations has your agency held with targeted communities on improved food production strategies?",null,null,"Kobotool box"]
[null,3.2,"Expected concrete Outputs"]
[null,"3.2.1","Climate smart food production system successfully piloted","Has your agency successfully piloted a climate-smart food production system? If yes, please describe its status and outcomes.",null,null,"Kobotool box"]
[null,"3.2.2","Nature-based business operational"]
[null,"3.2.2.1","Nature based businesses identified and selected in communities \n","How many nature-based businesses have been identified and selected in the communities your agency works with?","Belize Forest Department, MAFSE",null,"Kobotool box"]
[null,"3.2.2.2","Number of reports/strategies/plans and communication tools developed disseminated to increase awareness of nature-based and climate smart food production","How many reports, strategies, plans, and communication tools has your agency developed and disseminated to raise awareness of nature-based and climate-smart food production systems?",null,null,"Kobotool box"]
[null,"3.2.2.3","No of men and women receiving technical assistance and support\n for nature based businesses","How many men and women have received technical assistance and support from your agency to operate nature-based businesses?",null,null,"Kobotool box"]

{"sheet":"Survey tool_Comp 4","index":3,"n_rows":22,"n_cols":8,"rows_kept":22,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[]
[null,"NO","Description of Indicators ","Survey Question ","Executing Entities ","Baseline ","Beneficiary ","Data Collection Method "]
[null,4,"Component 4: Building National Capacity to access adaptation finance ",null,"University of Belize (UB)",null,"Elderly "]
[null,4.0999999999999996,"Expected Outcomes "]
[null,"4.1.1","Increased technical capacity to better access climate finance ","Has your agency observed an increase in technical capacity among stakeholders to better access climate finance? If yes, how is this reflected in your work?",null,null,null,"Kobotool box"]
[null,"4.1.1.1","Number of persons trained to access climate finance ","How many individuals have been trained by your agency to access climate finance?",null,null,null,"Kobotool box"]
[null,"4.1.1.2","No. of vulnerable women and women’s groups and organizations\n accessing climate finance ","How many vulnerable women, women’s groups, or women-led organizations have accessed climate finance through your agency’s efforts?",null,null,null,"Kobotool box"]
[null,"4.1.1.3","Number of males vs. females trained ","How many males and females have been trained by your agency to access climate finance? Please provide the numbers for each gender.",null,null,null,"Kobotool box"]
[null,"4.1.1.4","No of women's group receiving technical support in financial mgt. \n","How many women’s groups have received technical support in financial management from your agency?",null,null,null,"Kobotool box"]
[null,"4.1.1.5","Number of NGOs, CBOs and Regulatory agencies with increased awareness of climate change","How many NGOs, community-based organizations (CBOs), and regulatory agencies have increased their awareness of climate change as a result of your agency’s interventions?",null,null,null,"Kobotool box"]
[null,"4.1.1.6","Contract signed for capacity building using earth observation to monitor adaptation finance impact ","Has your agency signed a contract for capacity building using earth observation tools to monitor the impact of adaptation finance? If so, what is the expected outcome?",null,null,null,"Kobotool box"]
[null,"4.1.1.7","Number of financial mechanisms to support climate change adaptation for women producers ","How many financial mechanisms has your agency developed or supported to help women producers adapt to climate change?",null,null,null,"Kobotool box"]
[null,4.2,"Expected concrete Outputs "]
[null,"4.2.1","Establish a Technical Assistance Program to strengthen CSO capacity for project development and implementation","Has your agency established a technical assistance program to strengthen the capacity of civil society organizations (CSOs) for project development and implementation? If so, what are the key outcomes?",null,null,null,"Kobotool box"]
[null,"4.2.1.1","Number of capacity development sessions in accessing climate financing for targeted communities and organizations","How many capacity development sessions has your agency conducted to help targeted communities and organizations access climate finance?",null,null,null,"Kobotool box"]
[null,"4.2.1.2"," Pilot awareness raising program developed and implemented by UB \nand Civil Society Organizations.","Has your agency, in collaboration with UB and Civil Society Organizations, developed and implemented a pilot awareness-raising program? If yes, please describe the program’s status and impact.",null,null,null,"Kobotool box"]
[null,"4.2.2","Develop and pilot an awareness raising and knowledge sharing\nprogram",null,null,null,null,"Kobotool box"]
[null,"4.2.2.1","Number of communication tools developed and disseminated on \naccessing adaptive climate financing","How many communication tools has your agency developed and disseminated to raise awareness about accessing adaptive climate financing?",null,null,null,"Kobotool box"]
[null,"4.2.2.2","Contract signed to develop and pilot awareness raising and \nknowledge sharing program ","Has your agency signed a contract to develop and pilot an awareness-raising and knowledge-sharing program on climate finance? If so, what is the current progress?","National Women's Commission",null,null,"Kobotool box"]

{"sheet":"Survey tool_Comp 5","index":4,"n_rows":25,"n_cols":8,"rows_kept":25,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[]
[]
[]
[null,"NO","Description of Indicators","Survey Question ","Executing Entities","Baseline","Beneficiary","Data Collection Method"]
[null,5,"Component 5: Community Disaster Risk Management",null,"National Emergency Management Organization (NEMO), \"Ministry of Infrastructure, Development and Housing (MIDH)\", Village Council, Belmopan City Council (BCC), \"Ministry of Rural Transformation, Community Development, Local Government and Labour\", Department of Environment (DOE)",null,"Communities "]
[null,5.0999999999999996,"Expected Outcomes"]
[null,"5.1.1","Increased technical capacity to address flooding"]
[null,"5.1.1.1","Number of communities with increased ability to recover post disaster","How many communities have shown an increased ability to recover from disasters, particularly flooding, due to your agency’s efforts?",null,null,null,"Kobotool box"]
[null,"5.1.1.2","Number of male vs. females in communities with increased ability to recover post disaster","How many males and females in the communities your agency works with have demonstrated an increased ability to recover from flooding? Please provide numbers for each gender.",null,null,null,"Kobotool box"]
[null,"5.1.1.3","No. of women who receive disaster management training ","How many women have received disaster management training through your agency’s programs?",null,null,null,"Kobotool box"]
[null,5.2,"Expected concrete Outputs",null,null,null,null,"Kobotool box"]
[null,"5.2.1","Drainage system in flooding prone areas installed"]
[null,"5.2.1.1","Number of drainage systems installed and maintained","How many drainage systems have been installed and maintained in flooding-prone areas by your agency?",null,null,null,"Kobotool box"]
[null,"5.2.1.2","Contract signed for drainage system","Has your agency signed a contract for the installation of drainage systems in flooding-prone areas? If yes, how many contracts have been signed?",null,null,null,"Kobotool box"]
[null,"5.2.1.3","Flooding pattern assessment report  ","Has your agency completed a flooding pattern assessment report for the targeted areas? If yes, what are the key findings?",null,null,null,"Kobotool box"]
[null,"5.2.1.4","Number of communication tools developed and disseminated on improving community resilience from flooding, with consideration of climate change and its impacts","How many communication tools has your agency developed and disseminated to improve community resilience to flooding, taking into account the impacts of climate change?",null,null,null,"Kobotool box"]
[null,"5.2.1.5","Equipment for drainage system and maintenance","Has your agency procured the necessary equipment for the construction and maintenance of drainage systems?",null,null,"Communities ","Kobotool box"]
[null,"5.2.1.6","drainage system constructed and maintained per targeted community (within budget) ","Has your agency successfully constructed and maintained drainage systems in targeted communities within the allocated budget?",null,null,null,"Kobotool box"]
[null,"5.2.1.7","No. of drainage systems projects implemented ","How many drainage system projects have been implemented by your agency in flooding-prone areas?",null,null,null,"Kobotool box"]
[null,"5.2.1.8","No. of communites involved in drainage system projects","How many communities have been involved in drainage system projects facilitated by your agency?",null,null,null,"Kobotool box"]
[null,"5.2.1.9","No of men and women employed in the construction of natural and man-made drainage system ","How many men and women have been employed in the construction of natural and man-made drainage systems in your projects? Please provide the numbers for each gender.",null,null,null,"Kobotool box"]
[null,"5.2.1.10","1 focus group consultation with each of the targeted communities in determining the best suited location of drainage system.","Has your agency conducted focus group consultations with each of the targeted communities to determine the best-suited locations for the drainage systems?","Belmopan City Council (BCC)",null,null,"Kobotool box"]

{"sheet":"Component 1.","index":5,"n_rows":25,"n_cols":15,"rows_kept":25,"cut":false,"hidden":false,"merged":[]}
[]
[]
[null,"NO","Component 1 ","Executing Entities ","Baseline ","Target ","Year 1","Year 2","Year 3","Year 4","Cumulative ","Frequency ","Beneficiary ","Data Collection Method ","Data Collection Period "]
[null,1,"Safeguarding forest and water resources through\n strategic protection and restoration solutions ","Belize Forest Department, National Biodiversity Office (NBIO), Protected Areas Conservation Trust (PACT), National Hydrological Service, Department of Environment (DOE), Agriculture Department (AG), Lands Department, Project Managment Unit",null,null,null,null,null,null,null,null,"Communities "]
[null,1.1000000000000001,"Expected Outcomes ",null,null,null,null,null,null,null,null,null,"Communities "]
[null,"1.1.1","Water quality improved for watersheds ",null,null,null,null,null,null,null,null,null,"Women's Group ","Focus Group","Aug"]
[null,"1.1.1.1","Number of rivers with improved climate adaptive management systems ","Belize Forest Department, National Hydrological Service, National Biodiversity Office (NBIO)",0,2,null,1,1,null,2,null,"Communities ","Focus Group"]
[null,"1.1.2","Increased understanding of climate change impacts visible in communities ",null,null,null,null,null,null,null,null,null,"Elderly ","Survey "]
[null,"1.1.2.1","Acreage of Riparian forests in rivers restored ","Belize Forest Department, National Biodiversity Office (NBIO)",null,10,null,null,10,null,10,null,"Women's Group ","Survey "]
[null,null,"Biodiversity Conservation and Ecosystems Management report Completed Riparian (moved from target to indicator)","Belize Forest Department, National Biodiversity Office (NBIO)",0,1,null,null,1,null,1,null,null,"Interview"]
[null,1.2,"Expected concrete Outputs ",null,null,null,null,null,null,null,null,null,"Women's Group "]
[null,"1.2.1","Restoration strategies developed "]
[null,"1.2.1.1","250 males vs. 50 females participating in rstoration activites","Belize Forest Department, National Biodiversity Office (NBIO)",0,300,null,100,100,100,300,null,null,"Survey "]
[null,"1.2.1.2","Forest restoration strategy and Implementation Plan Completed \n(moved from target to indicator)","Belize Forest Department, National Biodiversity Office (NBIO), Department of Environment (DOE)",0,1,null,null,1,null,1,null,null,"Interview"]
[null,"1.2.1.3","Impact on Land Use Change on Micro and Macro Invertebrates Research Report completed (moved from target to indicator)","Belize Forest Department, National Biodiversity Office (NBIO), Department of Environment (DOE)",0,2,null,1,1,null,2]
[null,"1.2.2","Pilot water quality restoration activities in watershed"]
[null,"1.2.2.1","Number of capacity development activities for project beneficiaries in watershed restoration and water quality management and monitoring","Belize Forest Department, National Biodiversity Office (NBIO)",0,4,null,2,2,null,4,null,"Communites , Women's Group ",null,"Feb, Mar"]
[null,"1.2.2.2","Community based water quality sub projects approved for Funding\n(moved from target to indicator)","National Hydrological Service, Belize Forest Department, National Biodiversity Office (NBIO), Village Council",0,3,null,1,1,1,3]
[null,"1.2.2.3","Focus group consultation per beneficiary Community on the respective approved subprojects (moved from target to indicator)","Belize Forest Department, National Biodiversity Office (NBIO), Protected Areas Conservation Trust (PACT)",0,5,null,2,3,null,5]
[null,"1.2.2.3","Number of reports, strategies and plans developed and disseminated through various social media platforms ","Belize Forest Department, National Biodiversity Office (NBIO)",0,1,null,null,null,1,1]
[null,"1.3.3","No. direct beneficiaries "]
[null,"1.3.3.1","No of women who participate in watershed management exchange programs ","Belize Forest Department, National Biodiversity Office (NBIO), Protected Areas Conservation Trust (PACT)",0,100,null,35,35,40,100]
[null,"1.3.3.2","No of Schools who participate in outreach programs","Protected Areas Conservation Trust (PACT), National Biodiversity Office (NBIO)",0,15,null,5,5,5,15]
[null,"1.3.3.3","No of women's organization that participate in education and outreach programs ","Belize Forest Department, National Biodiversity Office (NBIO)",0,10,null,4,3,3,10]
[null,"1.3.3.4","No of women with project roles in implementing agencies","Belize Forest Department, National Biodiversity Office (NBIO)",0,5,null,2,3,null,5]

{"sheet":"Component 2","index":6,"n_rows":34,"n_cols":15,"rows_kept":34,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[null,"NO","Description of Indicators","Executing Entities","Baseline","Target","Year 1","Year 2","Year 3","Year 4","Cumulative","Frequency","Beneficiary","Data Collection Method","Data Collection Period"]
[null,2,"Component 2: Combating wildfires through adaptive management","Belize Forest Department, Agriculture Department (AG), National Fire Service",null,null,null,null,null,null,null,null,"Communities "]
[null,2.1,"Expected Outcomes",null,null,null,null,null,null,null,null,null,"Communities "]
[null,"2.1.1","Enhanced protection from fires",null,null,null,null,null,null,null,null,null,"Communities "]
[null,"2.1.1.1","Number of communities with increased capacity to address wildfires","Belize Forest Department, Protected Areas Conservation Trust (PACT)",0,5,null,3,2,null,5,"Annually ","Communities "]
[null,"2.1.1.2","Number of community fire brigades established","Belize Forest Department, Project Manager (PACT)",0,5,null,2,2,1,5,null,"Communities "]
[null,"2.1.1.3","Number of trained males (60) vs. females (30) in community fire brigades established","Belize Forest Department, Sarteneja Village Council , Ladyville Village, Hattieville Village",0,90,null,null,null,null,90,null,"Communities "]
[null,"2.1.1.4","No. of women (30) and men (60) who participate in wildfire preparedness and response training\n (moved from target to indicator)","Belize Forest Department, Village Council",0,90,null,null,null,null,90,null,"Communities "]
[null,"2.1.1.5","No. of women targeted in communication and fire prevention messages","Belize Forest Department, Village Council",0,208814,null,null,null,null,208814,null,"Communities "]
[null,"2.1.1.6","Number of NGOs, CBOs and Regulatory Agencies with Increased Capacity to address\n wildfires","Belize Forest Department, Village Council",0,10,null,3,4,3,10,null,"Communities "]
[null,"2.1.1.7","Wildfire Management Entities Registry developed (moved from target to indicator)","Belize Forest Department",0,1,null,1,null,null,1,null,"Communities "]
[null,"2.1.1.8","Fire Management - Network Institutional framework completed (moved from target to indicator)","Belize Forest Department",0,1,null,1,null,null,1,null,"Communities "]
[null,"2.1.1.9","Contract signed for procurement of fire tool kits (moved from target to indicator)","Protected Areas Conservation Trust (PACT)",0,1,null,1,null,null,1,null,"Communities "]
[null,"2.1.1.10","Fire toolkits, gears and equipment procured (moved from target to indicator)","Protected Areas Conservation Trust (PACT)",0,5,null,null,null,null,5,null,"Communities "]
[null,2.2000000000000002,"Expected concrete Outputs",null,null,null,null,null,null,null,null,null,"Communities "]
[null,"2.2.1","Fire management strategy developed and implemented",null,null,null,null,null,null,null,null,null,"Communities "]
[null,"2.1.1.1","Number of Fire brigades in pilot communities","Belize Forest Department, Sarteneja Village Council, Ladyville Village, Hattieville Village",0,5,null,2,3,null,5,null,"Communities "]
[null,"2.1.1.2","No. of women and girls who are members of pilot fire brigades","Belize Forest Department, Sarteneja Village Council, Ladyville Village, Hattieville Village",0,60,null,45,15,null,60,null,"Communities "]
[null,"2.1.1.3","Community Fire Brigade training manual and guide completed (moved from target to indicator)","Belize Forest Department",0,1,null,null,null,null,1,null,"Communities "]
[null,"2.1.1.4","Number of contracts signed for installation of elevated water storage (moved from target to indicator))","Protected Areas Conservation Trust (PACT)",0,3,null,null,null,null,3,null,"Communities "]
[null,"2.1.1.5","Number of water storage reports submitted (added by the consultant)","Sarteneja Village Council , Hattieville Village",0,5,null,null,null,null,5,null,"Communities "]
[null,"2.1.1.6","Number of capacity development consultation with targeted communities on improved fire management practices","Belize Forest Department, Sarteneja Village Council , Ladyville Village, Hattieville Village",0,10,null,null,null,null,10,null,"Communities "]
[null,"2.1.1.7","Focus groups consultation with the targeted community by the PMU and relevant stakeholders in subproject design (moved from target to indicator)","Belize Forest Department, Project Manager (PACT), Sarteneja Village Council , Ladyville Village, Hattieville Village",0,9,null,3,3,3,9,null,"Communities "]
[null,"2.1.1.8","Assessment report of fire response region in the BNPAS completed (moved from target to indicator)",null,0,1,null,1,null,null,1,null,"Communities "]
[null,"2.1.1.9","Community based wildfire management sub-projects approved for funding (moved from target to indicator)","Protected Areas Conservation Trust (PACT), Village Council",0,3,null,1,2,null,3,null,"Communities "]
[null,"2.1.1.10","Number of Reports/strategies/plans and communication tools developed and disseminated to increase awareness on fire management","Belize Forest Department",0,15,null,5,5,5,15,null,"Communities "]
[null,"2.1.1.11","National wildfire strategy and Action Plan for Brigades Completed (moved from target to indicator)","Belize Forest Department",0,1,null,null,1,null,1,null,"Communities "]
[null,"2.1.1.13","Training manual for BNPA firefighter completed (moved from target to indicator)",null,0,1,null,null,1,null,1,null,"Communities "]
[]
[]
[null,null,"Bi annual status reports on project with focus on component 2 during its implementation using Pact's IMS"]

{"sheet":"Component 3","index":7,"n_rows":26,"n_cols":16,"rows_kept":26,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[null,"NO","Description of Indicators","Executing Agencies","Baseline","Target","Year 1","Year 2","Year 3","Year 4","Cumulative","Frequency","Beneficiary","Data Collection Method","Data Collection Period","means of verification , Column1"]
[null,3,"Component 3: Creating Opportunities to Support Alternative Livelihoods","Inter-American Institute for Cooperation on Agriculture (IICA), Agriculture Department (AG), Beltraide MOE",null,null,null,null,null,null,null,null,"Communities ","Interview"]
[null,3.1,"Expected Outcomes"]
[null,"3.1.1","Increased number of livelihoods"]
[null,"3.1.1.1","Number of persons with an alternative form of financial income","Inter-American Institute for Cooperation on Agriculture (IICA), Agriculture Department (AG), Beltraide MOE , Human Development , National Women's Commission",0,5,null,3,2,null,5,null,"Communities "]
[null,"3.1.1.2","Number of males (30) vs. females (20) with an alternative livelihood","Inter-American Institute for Cooperation on Agriculture (IICA), Agriculture Department (AG), Beltraide MOE",0,50,null,25,25,null,50,null,"Communities "]
[null,"3.1.1.3","Number of persons trainned to operate businesses",null,0,50,null,25,25,null,50,null,"Communities "]
[null,"3.1.1.4","Number of males (1000) vs. females (1000) trained",null,0,2000,null,1000,1000,null,2000,null,"Communities "]
[null,"3.1.1.5","No of male (500) and female (500) rural farmers aware of ecological dynamics and technological innovations (added by the consultant)",null,0,1000,null,500,500,null,1000,null,"Communities "]
[null,"3.1.1.6","Percentage of rural women participating in agroforestry (moved from target to indicator)",null,0,0.5,null,25,25,null,0.5,null,"Communities "]
[null,"3.1.3","Increased number of climate smart food production systems",null,null,null,null,null,null,null,null,null,"Communities "]
[null,"3.1.3.1","Number of functional climate smart food production systems established",null,0,5,null,2,3,null,5,null,"Communities "]
[null,"3.1.3.2","Number of functional climate smart systems managed by male vs. female",null,0,3,null,2,3,null,3,null,"Communities "]
[null,"3.1.3.3","Number of capacity development consultation with targeted communities on improved food production strategies",null,0,20,null,10,10,null,20,null,"Communities "]
[null,3.2,"Expected concrete Outputs",null,null,null,null,null,null,null,null,null,"Communities "]
[null,"3.2.1","Climate smart food production system successfully piloted",null,0,null,null,1,4,null,5,null,"Communities "]
[null,"3.2.2","Nature-based business operational",null,0,null,null,1,4,null,5,null,"Communities "]
[null,"3.2.2.1","Nature based businesses identified and selected in communities \n(moved from target to indicator)","Belize Forest Department, MAFSE",0,5,null,3,2,null,5,null,"Communities "]
[null,"3.2.2.2","Number of reports/strategies/plans and communication tools developed disseminated to increase awareness of nature-based and climate smart food production",null,0,9,null,4,5,null,9,null,"Communities "]
[null,"3.2.2.3","No of men (60) and women (40) receiving technical assistance and support\n for nature based businesses (moved from target to indicator)",null,0,100,null,50,50,null,100,null,"Communities "]
[]
[null,null,"5 community awareness and training sessions implemented"]
[null,null,"bi-annual status reports on project with focus on component 3 during\nits implementation using PACTS's IMS"]

{"sheet":"Component 4 ","index":8,"n_rows":24,"n_cols":15,"rows_kept":24,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[null,"NO","Description of Indicators ","Executing Entities ","Baseline ","Target ","Year 1","Year 2","Year 3","Year 4","Frequency"," Cumulative","Beneficiary ","Data Collection Method ","Data Collection Period "]
[null,4,"Component 4: Building National Capacity to access adaptation finance ",null,null,null,null,null,null,null,null,null,"Elderly "]
[null,4.0999999999999996,"Expected Outcomes "]
[null,"4.1.1","Increased technical capacity to better access climate finance "]
[null,"4.1.1.1","Number of persons trained to access climate finance ",null,0,100,null,50,50,null,null,100]
[null,"4.1.1.2","No. of vulnerable women and women’s groups and organizations\n accessing climate finance (moved from target to indicator)",null,0,20,null,10,10,null,null,20]
[null,"4.1.1.3","Number of (50) males vs. females (50) trained ",null,0,100,null,50,50,null,null,100]
[null,"4.1.1.4","No of women's group receiving technical support in financial mgt. \n(moved from target to indicator)",null,0,5,null,3,2,null,null,5]
[null,"4.1.1.5","Number of NGOs, CBOs and Regulatory agencies with increased awareness of climate change",null,0,20,null,10,10,null,null,20]
[null,"4.1.1.6","Number of capacity building using earth observation to monitor adaptation finance impact (moved from target to indicator)",null,0,4,null,2,2,null,null,4]
[null,"4.1.1.7","Number of financial mechanisms to support climate change adaptation for women producers ",null,0,20,null,10,10,null,null,20]
[null,4.2,"Expected concrete Outputs "]
[null,"4.2.1","Establish a Technical Assistance Program to strengthen CSO capacity for project development and implementation"]
[null,"4.2.1.1","Number of capacity development sessions in accessing climate financing for targeted communities and organizations",null,0,20,null,10,10,null,null,20]
[null,"4.2.1.2"," Pilot awareness raising program developed and implemented by UB \nand Civil Society Organizations.",null,null,1,null,null,1,null,"Annually ",1]
[null,"4.2.2","Develop and pilot an awareness raising and knowledge sharing\nprogram"]
[null,"4.2.2.1","Number of communication tools developed and disseminated on \naccessing adaptive climate financing",null,0,5,null,3,2,null,null,5]
[null,"4.2.2.2","Contract signed to develop and pilot awareness raising and \nknowledge sharing program (moved from target to indicator)","National Women's Commission",0,1,null,null,1,null,null,1]
[]
[]
[null,null,"Bi-annual status reports on project with focus on component 4 during its implementation using PACT’s IMS"]

{"sheet":"Component 5","index":9,"n_rows":25,"n_cols":15,"rows_kept":25,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[null,"NO","Description of Indicators","Executing Entities","Baseline","Target","Year 1","Year 2","Year 3","Year 4","Cumulative","Frequency","Beneficiary","Data Collection Method","Data Collection Period"]
[null,5,"Component 5: Community Disaster Risk Management","National Emergency Management Organization (NEMO), \"Ministry of Infrastructure, Development and Housing (MIDH)\", Village Council, Belmopan City Council (BCC), \"Ministry of Rural Transformation, Community Development, Local Government and Labour\", Department of Environment (DOE)",null,null,null,null,null,null,null,null,"Communities "]
[null,5.0999999999999996,"Expected Outcomes"]
[null,"5.1.1","Increased technical capacity to address flooding"]
[null,"5.1.1.1","Number of communities with increased ability to recover post disaster",null,0,4,null,2,2,null,4]
[null,"5.1.1.2","Number of male (35) vs. females (15) in communities with increased ability to recover post disaster",null,0,50,null,25,25,null,50]
[null,"5.1.1.3","No. of women who receive disaster management training (moved from target to indicator)",null,0,10,null,5,5,null,10]
[null,5.2,"Expected concrete Outputs"]
[null,"5.2.1","Drainage system in flooding prone areas installed"]
[null,"5.2.1.1","Number of drainage systems installed and maintained",null,0,4,null,2,2,null,4]
[null,"5.2.1.2","Contract signed for drainage system (moved from target to indicator)",null,0,2,null,2,null,null,2]
[null,"5.2.1.3","Flooding pattern assessment report  (moved from target to indicator)",null,0,1,null,1,null,null,1]
[null,"5.2.1.4","Number of communication tools developed and disseminated on improving community resilience from flooding, with consideration of climate change and its impacts",null,0,4,null,2,2,null,4]
[null,"5.2.1.5","Equipment for drainage system and maintenance (added by the consultant)",null,0,1,null,1,null,null,1,null,"Communities ","Focus Group","Feb, Apr"]
[null,"5.2.1.6","drainage system constructed and maintained per targeted community (within budget) (moved from target to indicator)",null,0,4,null,2,2,null,4]
[null,"5.2.1.7","No. of drainage systems projects implemented (moved from target to indicator)",null,0,5,null,3,2,null,5]
[null,"5.2.1.8","No. of communites involved in drainage system projects",null,0,5,null,2,3,null,5]
[null,"5.2.1.9","No of men (40) and women (10) employed in the construction of natural and man-made drainage system (moved from target to indicator)",null,0,50,null,25,25,null,50]
[null,"5.2.1.10","5 focus group consultation with each of the targeted communities in determining the best suited location of drainage system.(moved from traget to indicator)","Belmopan City Council (BCC)",0,5,null,2,3,null,5]
[]
[]
[null,null,"Bi-annual status reports on project with focus on component 5 during\n its implementation using PACT’s IMS"]

{"sheet":"Stakeholder Mapping","index":10,"n_rows":38,"n_cols":11,"rows_kept":38,"cut":false,"hidden":false,"merged":[[1,1,1,3],[2,1,2,6],[2,7,2,10]]}
[]
[null,"Stakeholder Mapping and Engagement"]
[null,"General Information ",null,null,null,null,null,"Engagement Strategy "]
[null,"Executing Agencies ","Name of Contact ","Sex ","Position/Title ","Email Contact ","Phone Contact ","Stakeholder Group","Interest/Influence ","Engagement Method","Frequency "]
[null,"Project Management Unit (PACT/PMU)","Dr. Juanita Garcia-Saqui ","Woman ","Project Manager ","edapm@pactbelize.org ","822-3637","Donors/Investors ","High Interest ","Interview"]
[null,"Protected Areas Conservation Trust (PACT)","Eli Romero ","Man ","Climate Finance Manager ","cfm@pactbelize.org","822-3637",null,null,"Interview"]
[null,"Protected Areas Conservation Trust (PACT)","Judith Usher ","Woman ","Monitoring and Evaluation Officer ","monitoring officer@pactbelize.org","822-3637",null,null,"Interview"]
[null,"Belize Forest Department","Wilber Sabido ","Man ","Chief Forest Officer ","cfo@forest.gov.bz","822-1524","Government Agencies ",null,"Interview"]
[null,"Belize Forest Department","Raul Chun","Man ","Forest Officer ","gonzalezmi@gobmail.gov.bz","822-1524","Government Agencies ",null,"Interview"]
[null,"Belize Forest Department","Minerva Gonzalez ","Woman ","Forest Officer ","chunr@gobmail.gov.bz","822-1524","Government Agencies ",null,"Interview"]
[null,"Lands Department"]
[null,"Ministry of Infrastructure, Development and Housing (MIDH)","Rahim Thimbriel","Man ","Executive Engineer","rahim.thimbriel@midh.gov.bz",null,"Government Agencies ",null,"Interview"]
[null,"Ministry of Rural Transformation, Community Development, Local Government and Labour","Juan G. Marin Jr.","Man ","Rural Water Service Manager ","ruralwatermgr@labour.gov.bz","802-2663","Government Agencies ",null,"Interview"]
[null,"Ministry of Rural Transformation, Community Development, Local Government and Labour","Cindy Chan-Noble ","Woman ","Policy Coordinator ","policy.coord@labour.gov.bz","802-2663","Government Agencies ",null,"Interview"]
[null,"National Climate Change Office (NCCO)","Johanna Pacheco ","Woman ","Climate Change Officer - Adaptation","adaptationofficer.cc@environment.gov.bz","828-5960","Government Agencies ",null,"Interview"]
[null,"National Emergency Management Organization (NEMO)","Patricia Tzib ","Woman ","Operation Officer ","nemooperation@nemo.gov.bz","614-4080","Government Agencies ",null,"Interview"]
[null,"National Emergency Management Organization (NEMO)","Daniel Mendez ","Man ","National Coordinator ","coordnem@nemo.org.bz","822-2054","Government Agencies ",null,"Interview"]
[null,"Ministry of Finance, Economic Development and Investment/ Climate Finance Unit ","Jason Middleton ","Man ","Project Development Officer ","jason.middleton@med.gov.bz","880-4174","Government Agencies ",null,"Interview"]
[null,"National Biodiversity Office (NBIO)","Saul Cruz","Man ","Acting Director ","cruzs@gobmail.gov.bz","828-9056","Government Agencies ",null,"Interview"]
[null,"University of Belize (UB)","Egbert Irving","Man ","Director, Institutional Advancement Office","egbert.irving@ub.edu.bz","822 1000 EXT 1360","Academia/researchers ",null,"Interview"]
[null,"University of Belize (UB)","Joaquin Magana","Man ","Lecturer","jmagana@ub.edu.bz","822-1000","Academia/researchers ",null,"Interview"]
[null,"Belmopan City Council (BCC)","Kiah Pastor ","Woman ","Development and Environmental Officer","kiahlisani17@gmail.com","822-2271","Town Council",null,"Interview"]
[null,"Inter-American Institute for Cooperation on Agriculture (IICA)","Stephen Williams ","Man ","Technical Specialist ","stephen.williams@iica.int","822-0222/1087","Technical Cooperation Agency ",null,"Interview"]
[null,"Agriculture Department (AG)","Clifford Martinez ","Man ","Agriculture Officer ","clifford.martinez@agriculture.gov.bz","822-2144","Government Agencies ",null,"Interview"]
[null,"MAFSE","Belarmino Esquivel","Man ","Principal Agriculture Officer ","belarmino.esquivel@agriculture.gov.bz","626-9174","Government Agencies ",null,"Focus Group"]
[null,"Department of Environment (DOE)","Anthony Mai ","Man ","Senior Environmental Officer ","maiam@gobmail.gov.bz",null,"Government Agencies ",null,"Interview"]
[null,"National Hydrological Service","Tennielle Williams ","Woman ","Director","principal.hydrologist@naturalresources.gov.bz",null,"Government Agencies ",null,"Interview"]
[null,"National Fire Service ","Colin Gillett ","Man ","Chief Fire Officer ","chief@fire.gov.bz",null,"Government Agencies ",null,"Interview"]
[null,"Beltraide MOE ","Ishmael Quiroz ","Man ","Executive Director ","executive.director@beltraide.bz ",null,"Government Agencies ",null,"Interview"]
[null,"National Association of Village\n Council (NAVCO) ","Delory Valerio ","Man ","President ","delroyvalerio22@gmail.com","664-9092","CSO",null,"Focus Group"]
[null,"Human Development ","Gabriela Escobar ","Woman ","Officer ","eeo.north.wfsd@humandev.gov.bz ","613 7388","Government Agencies ",null,"Interview"]
[null,"National Women's Commission","Eli Rancharan ","Woman ","Programme Officer ","mnay31@gmail.com ",6213109,"CSO",null,"Interview"]
[null,"Sarteneja Village Council ","Mr. Paulino Guerrero","Man ","Chairman ",null,"501 660-5725",null,null,"Focus Group"]
[null,"Ladyville Village","Ms. Mirna Paul","Woman ","Council member focal point ","mirnapaulbelize@gmail.com","501 673-3187",null,null,"Focus Group"]
[null,"Hattieville Village ",null,null,null,null,null,null,null,"Focus Group"]
[null,"Village Council",null,null,null,null,null,null,null,"Focus Group"]
[null,"Project Managment Unit ",null,null,null,null,null,null,null,"Interview"]
[null,"Town Council",null,null,null,null,null,null,null,"Interview"]

{"sheet":"Tables","index":11,"n_rows":21,"n_cols":14,"rows_kept":21,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[]
[]
[null,"Sex",null,"Interest/Influence",null,"Stakeholder Group ",null,"Engagement Method",null,"Frequency ",null,"Beneficiaries",null,"Months"]
[null,"Man ",null,"High Interest ",null,"Government Agencies ",null,"Focus Group",null,"Monthly ",null,"Women's Group ",null,"Jan"]
[null,"Woman ",null,"High Influence",null,"Local Communities ",null,"Interview",null,"Bi- monthly ",null,"Communities ",null,"Feb"]
[null,null,null,null,null,null,null,"Kobotool box"]
[null,"Other",null,"Medium Influence ",null,"NGOs",null,"Survey ",null,"Quarterly ",null,"Elderly ",null,"Mar"]
[null,"Prefer not to say",null,null,null,"Private Sector ",null,null,null,"Semi- annual ",null,"Disable People ",null,"Apr"]
[null,null,null,null,null,"Technical Cooperation Agency "]
[null,null,null,null,null,"Academia/researchers ",null,null,null,"Annually ",null,null,null,"May"]
[null,null,null,null,null,"Town Council"]
[null,null,null,null,null,"CSO",null,null,null,null,null,null,null,"Jun"]
[null,null,null,null,null,"NAVCO ",null,null,null,null,null,null,null,"Jul"]
[null,null,null,null,null,"Donors/Investors ",null,null,null,null,null,null,null,"Aug"]
[null,null,null,null,null,"CSO",null,null,null,null,null,null,null,"Sep"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"Oct "]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"Nov"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"Dec"]