## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 01 August 2016-31 July 2017
| Project Title: | Climate Change Adaptation Programme in the Coastal Zone of Mauritius
| Project Summary: | The objective of the project is “to increase climate resilience of communities and livelihoods in coastal areas of Mauritius”. The project comprises of five key outcomes as follows: 1. Increased adaptive capacity within relevant development and natural resources sectors. It comprises of the application of adaptation measures to protect currently vulnerable coastal ecosystem and community at three priority sites: Mon Choisy, Quatre Soeurs and Rivière des Galets. 2. Reduced exposure at national level to climate-related hazards and threats. This component will focus on development of an Early Warning System for incoming Storm Surge manned on 24/7 basis such that the coastal communities in the Republic of Mauritius are able to safely evacuate prior to future storm surge events. 3. Strengthened institutional capacity to reduce risks associated with climate-induced socio-economic losses. This component is targeted to build capacity for ongoing replication of effective coastal adaptive measures by both the Government and private sector. Capacity development will cover a range of Ministries, NGOs, the private sector and the community at large. Short courses on Coastal Engineering, Cost Benefit Analysis of Coastal Adaptation Measures will be developed and delivered in the Republic of Mauritius. A Handbook on coastal adaptation for coastal communities will packaged as training modules for the coastal communities. 4. Improved Policies and Regulations that promote and enforce resilience measures A National Coastal Zone Adaptation Strategy (NCZAS) for the Republic of Mauritius that addresses all perceived climate change risks in the coastal zone of Mauritius and Rodrigues to promote and enhance resilience measures over the next 20 years, with recommendations for supporting policies and regulations, best technical and institutional adaptation practices and new economic instruments. The NCZAS will be developed following (i) Review of relevant strategies, policies, laws, regulations and projects pertaining to the coastal zone in the ROM (ii) Vulnerability assessment, identification of gaps, and development of a map that identifies the most vulnerable coastal areas and systems with development capacity limit and formulate options for adaptation policies. 5. Effective capturing and dissemination of lessons from the applied activities in the programme. Public awareness campaigns on climate change in the coastal zone of Mauritius will be developed and broadcasted in the media. The project will also have a regional dimension whereby the lessons learned from this Adaptation Project will be disseminated to other countries in the Southern Indian Ocean.
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme (UNDP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Mauritius | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Port Louis | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2011-09-15
IE-AFB Agreement Signature Date: |  | 2012-07-19 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-08-30 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2014-10-27
| Terminal Evaluation Date: | 2019-05-31
|  | List documents/ reports/ brochures / articles that have been prepared about the project. Project Reports to Donor: • Quarterly Reports submitted to the UNDP CO (Progress Reports/Financial Reports/Quarterly Work Plans) • AF Project Audit Report for the period 01 January 2016 to 31 December 2016 • Project Performance Report (01 August 2016-31 July 2017) | Cyprus
|  | Reports/documents produced by Project Outcomes Outcome 1 : Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs (Works) Reports • 24 Progress Reports received from contractor as at 31 July 2017 | Czech Republic
Consultancy Services for Coastal Adaptation works at Mon Choisy and Riviere des Galets Reports/drawings/contract for Riviere des Galets • Design Report for Riviere des Galets • Final Bid Document for Construction of Rock Revetment Structure with Parapet Wall at Riviere des Galets • Bid Drawings • Contract Agreement between Ministry and Super Builders Co Ltd for Construction of Rock Revetment Structure with Parapet Wall at Riviere des Galets-03 May 2017 Reports/Drawings/contract for Mon Choisy • Design Report for Mon Choisy • Bid Document for Coastal Adaptation Measures at Mon Choisy-Part I: Beach Works (Tree and Stump Removal, Sand Procurement, Delivery and Placement, Mechanical Grading, Beach Fencing), Dune Planting, Rock Groyne Removal and Installation of an Artificial Reef Part II: Installation of Fixed Mooring Buoys, Establishment of a Voluntary Marine Conservation Area and Seagrass Rehabilitation Pilot • Final Bid Drawings Environment Impact Assessment (EIA) for Mon Choisy & Riviere des Galets EIA Mon Choisy (Offshore Breakwater Structure) • Final EIA Report-Coastal Adaptation Works Programme for Proposed Offshore Breakwater Structure and Beach Upgrading at Mon Choisy • Final Social Impact Assessment Report (SIA) for Coastal Adaptation Works Programme for Proposed Offshore Breakwater Structure and Beach Upgrading at Mon Choisy Revised EIA for Mon Choisy-Beach Rehabilition including installation of artifical reef units (2017) • Final EIA Report for Mon Choisy • Final SIA Report for Mon Choisy
Outcome 3-Training Training Manuals/Handbooks/Contracts signed • Training Manual on Cost Benefit Analysis for Coastal Zone Management and Adaptation Options to Climate Change in Mauritius • Training Manual on Integrated Coastal Zone Management • Handbook on Coastal Adaptation for coastal communities
Consultancy Services for Development of a National Coastal Zone Strategy for the Republic of Mauritius • Inception Workshop Report • Final Report on TASK 1 - Review relevant strategies, policies, laws, regulations and projects pertaining to the coastal zone in ROM and relevant international best technical and institutional adaptation practices in coastal zone management. • Consultative Workshop Report for Mauritius & Rodrigues (23 & 28 June 2017) • Draft Report on options for adaptation policies and measures, and vulnerability assessment result and map that identifies the most vulnerable coastal areas and systems with development capacity limit Press/media/Weblinks: Outcome 3: Website link: http://lcms.uom.ac.mu/lms/course/view.php?id=585 Website link: http://lcms.uom.ac.mu/lms/course/search.php?search=coastal+engineering Above link to access to course materials for Short Courses (listed hereunder) completed under the AF Project: •Short Course on Cost Benefit Analysis Applied to Climate Change Initiatives Outcome 4: Consultancy Services for the preparation of a National Coastal Zone Adaptation Strategy for the Republic of Mauritius • http://environment.govmu.org/English/Pages/Procurement-Notice.aspx • http://www.comesa.int/consultancy-services-for-the-preparation-of-a-national-coastal-zone-adaptation-strategy-for-the-republic-of-mauritius/ •http://www.mu.undp.org/content/dam/mauritius_and_seychelles/docs/Procurement/12AUG16/RFP%20National%20Coastal%20Zone%20Adaptation%20%20Strategy_08.08.16.pdf •https://www.tendersontime.com/tender/consultancy-services-preparation-national-coastal-zone-adaptation-strategy-75c86e.php •https://opportunities.export.great.gov.uk/opportunities/mauritius-consultancy-services-for-preparation-of-a-national-coastal-zone-adaptation-strategy
Articles on the Adaptation Fund Project Quatre Soeurs Refuge Centre • Le Defi Quotidien-30 March 2017 (Q. Soeurs: Le centre de Refuge operationnel en aout) Mon Choisy • Le Mauricien dated 24 July 2017- Notice for Public Inspection of EIA Report for Proposed artifical reef and beach upgrading at Mon Choisy under the coastal adaptation works programme • L'Express 31 July 2017-Environnement: L'Erosion commence a se faire voir
Partnerships: Banners produced under AF Project: • 1 Banner on Mangroves Plantation & Sensitisation Project in the region of Grand Sable/Quatre Soeurs • 1 Banner on Riviere des Galets Project Site (vulnerability to storm surges) • 2 Banners on Training and Capacity Building Programme • 1 Banner on Problem statement of Mon Choisy & Riviere des Galets Project site • 2 Banner on Coastal Adaptation Options for Mon Choisy & Riviere des Galets project site • 1 Banner on Sensitisation Campaigns conducted under AF Project • 1 Banner on Early Warning System for Storm Surge
List of Cabinet/Information Papers: Parliamentary Questions • PQ B/353-Whether, in regard to the inhabitants of the EDC at Riviere des Galets who are at risk during bad weather conditions, he will state if any decision has been taken for the relocation thereof? (http://mauritiusassembly.govmu.org/English/questions/Documents/PQ2017/pq25april2017.pdf)
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.adaptation-fund.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mrs. D. Lan Ng | Dominican Republic
| Email: | dirdoe@govmu.org | Ecuador
| Date: | 2017-07-31 | Egypt
| Government DA |  | El Salvador
| Name: |  | Equatoral Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | United Nations Development Programme (UNDP) | Fiji
| Email: | christine.umutoni@one.un.org/satyajeet.ramchurn@undp.org | Finland
| Date: | 2017-07-31 | France
| Executing Agency |  | Gambia
| Name: | Ministry of Environment, Sustainable Development, and Disaster and Beach Management | Georgia
| Email: | ngoorah@govmu.org | Germany
| Date: | 2017-07-31 | Ghana
| Executing Agency |  | Greece
| Name: | Ministry of Environment, Sustainable Development, and Disaster and Beach Management (Project Manager) | Grenada
| Email: | mnkhedah@yahoo.com | Guatemala
| Date: | 2017-07-31 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31 July 2017
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [31 July 2017] | 2511977
Add any comments on AF Grant Funds. (word limit=200) | The disbursement up to the reporting period ending 31 July 2017 amounted to USD 2,511,977 (exclusive of management fee) which represent 29.8 % of the total budget. Remarks (i) No VAT has been paid from the AF Grant (ii) Actual Bid Price received for Works was below the earmarked value (ii) Estimated Savings of up USD 1.5 Million Estimated Costs Actual Costs Actual Savings Riviere des Galets USD 2,000,000 USD 765,000 USD 1,235,000 Early Warning System USD 310,365 USD 265,365 USD 45,000 Training USD 394,025 USD 294,025 USD 100,000 Knowledge Dissemination USD 320,000 USD 200,000 USD 120,000 Total USD 1,500,000 Proposals (i) Extension of Early Warning System to include the wave component (ii) Phase II of Refuge Centre (iii) AF Project Extension by 1 Year (iv) Re-allocation of budget for Execution costs The Project budget was revised and approved by the Adaptation Fund Board on 22 May 2014 (Board decision B.23-24/5) as follows; Outcome Prodoc Revised Budget (USD) (USD) 1 6,465,700 6,680,440 2 133,705 310,365 3 394,025 394,025 4 350,000 200,000 5 561,350 320,000 The Procurement of the following Consultancy Services and Contractor for Works were completed during the reporting period and contracts awarded; Contracts Awarded for Consultancy Services during the reporting period • The Contract for Consultancy Services for Supervision of Coastal Protection and Landscaping Works at Riviere des Galets Works was awarded to Luxconsult (Mtius) Ltd for the contract amount of Rs 2,510,000 (Incl. of VAT)-20 April 2017 • Contract signed between Ministry and The University of Western Australia for Design and Delivery of a Short Course on Cost-benefit Analysis applied to Climate Change Initiative for the contract amount of AUD 33,076-17 August 2016. • The Contract for Preparation of a National Coastal Zone Adaptation Strategy for the Republic of Mauritius was signed between Ministry of Social Security, National Solidarity and Environment and Sustainable Development and AGRER S.A.-N.V for the contract amount of Rs 5,752,300 (Incl. of VAT)-06 February 2017 Contracts for Works • The Contract for Construction of a Rock Revetment Structure with Parapet Wall was awarded to Super Builders Co Ltd for a contract amount of Rs 28,977,556.25, incl. of VAT-03 May 2017
INVESTMENT INCOME | 14489.29
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1, 1.2, 1.4, 1.5, 1.6 (Outputs merged under 1 Consultancy Services) | 123896.01
| Output 1.3 (Works) | 676511.51
| Outcome 1 subtotal | 800407.52
| Output 2.1, 2.2 (Outputs merged under 1 Consultancy Services) | 2025.53
| Outcome 2 subtotal | 2025.53
Output 3.1 (Hdbk)
| Output 3.2 (SC on Ceng) | 1562.54
| Output 3.3 (CBA) | 48468.91
| Outcome 3 subtotal | 50031.45
| Output 4.1, 4.2, 4.3, 4.4 (Outputs merged under 1 Consultancy Services) | 14586.38
| Outcome 4 subtotal | 14586.38
| Output 5.1 (Hd Bk) | 12488.32
| Output 5.2 (Diss Ind Ocean) | 7490.51
| Output 5.3 (Scale scale models) | 21485.12
| Output 5.4 (Awareness) | 2836.88
Output 5.5 (Ranking)
| Outcome 5 subtotal | 44300.83
| Outcome 6 (Execution Costs) | 93030.48
| TOTAL | 1004382.19
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | Est. Completion Date | PROJECTED COST
| 1.1 Detailed technical assessment of each site, with chronology of previous flood and erosion events and collection of nearshore oceanographic data, during “quiet” periods and “active” periods (one month each) to inform the design of the technical interventions at each of the three sites-Completed | Riviere des Galets • Design of Coastal Adaptation Measures for Riviere des Galets-Completed (August 2016) Mon Choisy • Design of Coastal Adaptation Measures for Mon Choisy-Completed-November 2016 | -
1.2 Technical design of coastal protection measures at each of three sites, with detailed costing, carried out in a gender sensitive way-Completed
| 1.3 Successful construction of physical interventions at each of the three sites.-Ongoing | Quatre Soeurs (USD 700,000) • Construction Works-Ongoing • Expected Completion-November 2017 Riviere des Galets (USD 652,000) • Bid Document launched-Completed • Contract for Works awarded-Completed • Construction Works-Ongoing • Expected Completion-April 2018 Mon Choisy (USD 1,900,000) • Bid Document for works-Completed July 2017 • Expected Award of contract-November 2017 • Start of Works-January 2018 • Completion of Works-December 2018 | 3252000
| 1.4 Analysis of data and development of recommendations on how the interventions can be adjusted for other vulnerable coastal locations in ROM. | Ongoing | 320000
| 1.5 Monitoring programme designed, to include scoping of suitable parameters, including beach width and slope; depth of adjacent lagoonal sediments; wave height, period, and run-up; direction of nearshore currents, etc. | Ongoing
| 1.6 A targeted coastal process/weather event monitoring system in place | Ongoing
| 2.1 Assessment of the current sea state monitoring systems (Mauritius Meteorological Services and Mauritius Oceanography Institute) and definition of required critical parameters and operational requirements for an . early warning system-Completed | Project Completed The Republic of Mauritius is the first Small Island Developing State to have a fully operational Warning System for Storm and Tidal Surge
2.2 The early warning system installed and implemented (with links to early warning system for cyclones), with communication linkages established from level of National Coast Guard at Headquarters down to the level of coastal communities.-Completed
| 3.1 “Handbook on Coastal Adaptation” packaged as training modules for coastal communities, relevant Government agencies, and private sector stakeholders (such as hotel operators); training sessions delivered on a regular basis over the course of the project (at least twice annually).-Completed | Completed 4 Training Manuals developed: (i) Training Manual on Coastal and Marine Environment for Engineers (ii) Training Manual Coastal Engineering (recognized by The Council of Registered Profession Engineers of Mauritius) (iii) Training Manual on Cost and Benefit Analysis for Coastal Management and Adaptation Options to Climate Change in Mauritius (iv) Training Manual on Integrated Coastal Zone Management | -
| 3.2 Short course on Coastal Engineering designed and delivered (twice during programme period).-Completed | Completed 9 Short Courses on Coastal Engineering (i) Short Course on Coastal and Marine Environment for Engineers (ii) Short Course on Coastal Engineering (iii) Short Course on Coastal Adaptation Structures (soft measures) including a case study of Mon Choisy (iv) Short Course on Coastal and Marine Environment for Engineers (Rodrigues) (v) Short Course on Ocean Data Collection and Analysis 26 -29 January 2015 29 (vi) Short Course on Climate Change and Coastal Zone Management (vii) Short Course on Open Geospatial tools (viii) Short Course on Disaster Risk Reduction (ix) Short Course on Integrated Coastal Zone Management | -
| 3.3 Specialized course on Cost-Benefit Analysis of coastal adaptation measures designed and delivered (annually, over four years).-Completed | Completed 4 Short Courses on Cost-Benefit Analysis (i) Short Course on Cost and Benefit Analysis of Coastal Adaptation Measures (ii) Short Course on Cost Benefit Analysis/Climate Change Economics (iii) Short Course on Cost and Benefit Analysis of Coastal Management and Adaptation Options to Climate Change (Rodrigues) (iv) Short Course on Cost Benefit Analysis on Climate Change Initiatives | -
| 4.1 A National Coastal Zone Adaptation that addresses all perceived climate change risks in the coastal zone of ROM over at least the next 20 years, with recommendations for supporting policies and regulations.-Ongoing | • Procurement of Consultancy Services-Completed • Contract awarded to 'AGRER S.A-N.V' from Belgium-Completed • Contract Signed-06 February 2017 • Inception Workshop Completed-02 March 2017 • Inception Workshop Report-Completed • Report on TASK 1 ‘Review relevant strategies, policies, laws, regulations and projects pertaining to the coastal zone in ROM and relevant international best technical and institutional adaptation practices in coastal zone management’-Completed •Final Report on options for adaptation policies and measures, and vulnerability assessment result and map that identifies the most vulnerable coastal areas and systems with development capacity limit-September 2017 • Final EIA Guidelines-September 2017 • National Coastal Zone Adaptation Strategy Report-December 2017 •Expected Completion Date: December 2017 | 133000
4.2 A set of recommendations on best technical and institutional adaptation practices suitable for the coastal zone of ROM.-Ongoing
4.3 Definition of the required structure and processes for one “clearinghouse” for climate change oversight in the coastal zone of ROM (a unit or institution, or collection of individuals from various agencies, which is able to make final decisions on the climate appropriateness of future development projects; also having a follow-up enforcement capacity).-Ongoing
4.4 Recommendations for new economic instruments-Ongoing
| 5.1 Handbook, training modules, and website content capturing best coastal adaptation practices for the Mauritius context.-Completed | • 1 Handbook for Coastal Communities-Completed | 3000
| 5.2 Dissemination of lessons learned from the programme with coastal stakeholders in other locations in the southern Indian Ocean. -Completed | International Collaborations • Worley Parsons of South Africa • Indian Institute of Technology Madras, India • University of Western Australia • Global Water Partnership Southern Africa and the University of Pretoria • Centre of Environmental Economics and Policy in Africa (CEEPA) South Africa. • The University of Mauritius • Boomerang Geospatial
| 5.3 Interpretive signs and small-scale models of coastal processes designed and installed at each site, explaining the science of climate change and coastal processes (in lay terms), so that the linkages between weather, stability of coastal features, and adaptation measures are clear.-Completed | 7 (3D) small scale ecosystem models deveoped • coral reefs • seagrass beds • mangroves • wetlands 3 interactive climate change models • Depicting Mon Choisy Project Site • Riviere des Galets Project Site • Marine Park (Rodrigues Islands) • 1 climate change game electronic game
| 5.4 Public awareness campaigns on climate change in the coastal zone designed and delivered, involving the Mauritian media (TV, radio, Internet).-Completed | • 31 Public awareness campaigns using Marine Mobile Education Unit • 15,000 people sensitised including school children, NGO’s, private sector and women association
| 5.5 Priority ranking of vulnerable coastal sites established, to guide the order of future investment by the Government of Mauritius and the private sector.-Ongoing | • A Map is being developed under Component 4 that identifies the most vulnerable coastal areas and systems in the Republic of Mauritius with development capacity limit.
| Execution Costs | Project Manager/Project Assistant/Project Technical Assistant | 118000
| TOTAL |  | 3826000
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | No co-financing committed in the Project Document
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 320645
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | 320,645 USD as Government of Mauritius in-kind contribution for purchase of land of an extent of 12,850 m2 at Quatre Soeurs for construction of the Refuge Centre.

## Procurement (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 0
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date | Remaining Balance
local | Contract signed between the Ministry of Environment, Sustainable Development, and Disaster and Beach Management and Scene-Ries Ltd for the consultancy services for Preparation of Environmental Impact Asssemment reports for Mon Choisy and Riviere des Galets | MUR 302,250 (USD 8513) | 2017-02-08 | MUR 137,175 (3863) | USD 4650
Local | Contract signed between Ministry of Social Security, National Solidarity and Environment and Sustainable Development and Luxconsult (Mtius) Ltd for Consultancy Services for Supervision of Coastal Protection and Landscaping Works at Riviere des Galets | MUR 2,182,609 USD 61,472 | 2017-04-20
local | Contract signed between Ministry of Social Security, National Solidarity and Environment and Sustainable Development and Super Builders Co Ltd for Construction of Rock Revetment Structure with Parapet Wall at Riviere des Galets | MUR 25,197,875 USD 709,680 | 2017-10-18 | MUR 3,779,681 USD 106,452 | USD 603,228
International | Contract signed between Ministry of Social Security, National Solidarity and Environment and Sustainable Development and AGRER S.A.-N.V for Development of a National Coastal Zone Adaptation Strategy for the Republic of Mauritius | MUR 5,002,000 USD 140,878 | 2017-02-06 | USD 14,816 | USD 126,062
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Third Round of Procurement RFP for Consultancy Services for Preparation of a National Coastal Zone Adaptation Strategy for the Republic of Mauritius Open International Bidding 08 August 2016 | 1. Agrer S.A.-N.V (Belgium) 2. ESIA Consult Pty Limited (Australia) 3.Dfractals Advisors for Development (India), EML Consultants (Private) Ltd (Sri Lanka) 4. SRK Consulting (South Africa) (PTY) Ltd, Bluepebble Sustainability Solutions (South Africa), University of Cape Town Institute of Marine and Environmental Law (South Africa), Anchor Environmental (South Africa), Strategic Networking Partners and Consulting Ltd (Local) 5. Hatch Africa (Pty) Ltd (South Africa). Enviro Consults Ltd (Local), C-Core (Canada), Gaia Consulting Ltd (U.S.A), Zeta Consultants T/A Prime Africa Consultants (South Africa) | USD 161,946 MUR 5,752,300 | 1. Agrer S.A.-N.V (Belgium) USD 161,946 MUR 5,752,300 | Best Evaluated Bidder based on Technical & Financial Proposal
Procurement of Construction of Rock Revetment structure with Parapet wall at Riviere des Galets Open National Bidding 09 December 2016 | 1. Super Builders Co Ltd 2. Sotravic Limitee 3. Square Deal Multipurpose Cooperative Society Ltd | MUR 28,977,556.25 MUR 41,395,128.60 MUR 35,116,400 | 1. Super Builders Co Ltd MUR 28,977,556.25 USD 815,814 | Best Evaluated Bidder based on Technical & Financial Proposal
Request for Proposal for Consultancy Services for Supervision of Coastal Protection and Landscaping Works at Riviere des Galets 01 December 2016 | 1. Servansing Jadav & Partners Consulting Engineers Ltd 2. GIBB (Mauritius) Ltd 3. Scene-Ries Consult Ltd 4. Mega Design Ltd 5. Luxconsult (Mtius) Ltd | MUR 5,312,000 MUR 4,700,000 MUR 3,890,000 MUR 3,265,000 MUR 2,510,000 | Luxconsult (Mtius) Ltd MUR 2,510,000 USD 70,665 | Best Evaluated Bidder based on Technical & Financial Proposal

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
High level endorsement of proposed policy and regulatory changes to support coastal adaptation may be lacking (enabling legislation may be delayed); there may also be concerns about creating a new climate change oversight function within the Ministry of Environment, Sustainable Development, Disaster and Beach Management (MESDDBM) (degree: moderate) | Coastal adaptation projects and initiatives are fully supported by the Ministry (degree: low) | • The various programme activities and progress are discussed at the Project Steering Committee chaired by the Ministry and is held once every 3 Months. • 18 Project Steering Committee Meetings have been held since start of the project and decisions on proposed policies and regulatory changes with respect to coastal adaptation have been discussed and endorsed. • All Technical issues are discussed at the Technical Committee level under the chair of the Ministry on a regular basis. 26 Technical Committees have been held under the Project since start of the project. | It is assumed here that the Steering Committee meetings are led by the Ministry? This is what makes the "Steps taken" relevant to the risk. | Addressed
Government of Mauritius commitment to climate change management could wane as development priorities become more prominent and compete, especially in the run-up to elections. (degree: moderate) | Up to now the change in Government has not affected the climate change priorities and management in Mauritius (degree: low) | • Mauritius has witnessed in the recent past some of the impacts of climate change including flash floods, variability in rainfall distribution amongst others. The Government is thus well aware of climate change impacts and it is one of the national priority to build climate resilience. • Constant reiteration of the risks of climate change and the positive net benefits of adaptation investments are being disseminated. | Text highlighted in green should be moved to next column | Addressed
Delays in fund transfers and procurement of technical services and equipment. (degree: moderate) | The procurement process in line with the current Public Procurement Act is lengthy. The procurement of highly technical expertise required the project to undertake international bidding No bids were received in some highly technical and scarcity areas. In some cases the bid price were beyond the budgeted amount in the AF Project Document (degree: low) | • Programme activities were initially designed and paced to ensure completion over five years. Following the first round of procurement and lessons learnt, a budget reallocation (USD 391,400) from the Component ‘Policy Mainstreaming’ and ‘Knowledge Dissemination’ to Coastal Adaptation Works at Mon Choisy & Riviere des Galets and Early Warning System was effected in consultation with the UNDP CO. • The Revised Budget allocation was endorsed by the Financial Secretary, the Designated National Authority and subsequently approved by the Adaptation Fund Board (AFB) in March 2014. • The support of the UNDP in Preparation of Terms of Reference for International Consultant for Policy Mainstreaming and procurement of consultancy servicecs for Coastal Adaptation Works at Mon Choisy and Riviere des Galets were undertaken • The Programme Board will also provide required oversight for management of programme inputs. • Where there was delay in fund transfer from the donor to the UNDP CO, the Ministry negotiated with the Ministry of Finance and Economic Developement to meet the project expenditure from the Government funds in the meantime | Text marked in green is a mitigation measure; take to next column | Addressed
MESDBM may have limited management capacity for programme activities, and for the eventual assumption of climate change management oversight and enforcement; conflicts between the CC Cell and the ICZM Division may arise. (degree: moderate) | A new climate change bill at the level of the Ministry has been prepared which clearly defines the roles of each division. (degree: low) | • UNDP will maintain a strong link with the programme, and the various programme activities that address institutional aspects will be guided by consultants, who will bring international expertise and experience from other countries, which should inform the situation in the Republic of Mauritius.
Climate variability accelerates and coastal degradation occurs at a faster pace than anticipated. (degree: moderate) | Climate variability is still a concern, and is complicated by uncertainty. However, the project has undertaken various studies prior to coming up with the best adaptation solution for each coastal sites (degree: low) | • Modelling of different scenarios of the climate change variability and impacts thereof has been included in the scope of the services of the international consultants. The design has taken into consideration the above risk factor where required • The climate change modelling, as part of the deliverables under the component 1 has addressed this potential risk to the satisfaction of the Technical Committee and Project Steering Committee
There may be a misunderstanding about the jurisdictional area of an agency that has climate change management oversight and right of enforcement. (degree: moderate) | The component on Policy Mainstreaming (Development of a National Coastal Zone Adaptation Stratgey) will clearly define the responsibilities of each Ministry, as a specific deliverable. (degree: low) | It is precisely the analysis of overlapping jurisdictions and conflicting regulations that will sort out respective roles and improve the situation for all Ministries/agencies, so that coastal adaptation can proceed accordingly. The consultant for Policy Maintreaming will come up with a National Coastal Zone Adaptation Strategy for the Republic of Mauritius
Districts (local government) may perceive themselves in a peripheral role, with their development put aside for the sake of climate change adaptation. (degree: moderate) | • The officials of all Local authorities in RoM have been trained in the field of coastal engineering/climate change adaptation/CBA as part of the capacity building programme under the project. • The delivery of the Short Courses started since September 2013. To date 13 Short Courses in the field of Coastal Engineering, Coastal and Marine Environment for Engineers, Cost and Benefit Analysis, amongst others have been delivered under the Project in Mauritius and Rodrigues. (degree: low) • Consultations have been with local authorities during the Environment Impact Assessment phase of each projects | The District Councils are represented in the Programme Board (Project Steering & Technical Committee) and in programme activities. The positive results of the coastal protection measures are disseminated and well understood by the District Councils.
Varying, possibly conflicting, perceptions of the climate change risks and coastal adaptation approaches may become apparent, based on previous experiences and technical expertise. (degree: moderate) | • The most feasible option for the climate change adaptation is being looked at based on its own merits to achieve a sustainable solution. For example, at one of the project coastal site, Riviere des Galets, the option of relocation of the vulnerable communities exposed to storm surge had also been explored in consultation with the local community. However, due to project time constraints, a rock revetment with parapet wall, and landscaping works is being constructed under the prroject. • Regular stakeholders meetings and sensitisation are held under the project to reduce conflicting issues amongst the local community/fishers/NGO's/Government/Private sector and the local authorities (degree: low) | • Frequent dialogue with programme partners on reinforcement of principles of climate change management and appropriate adaptation measures has been taken. • Regular stakeholders meetings and sensitisation are held under the project to reduce conflicting issues amongst the local community/fishers/NGO's/Government/Private sector and the local authorities • To date, sensitisation campaigns have been conducted using a mobile education unit and some 15000 people have been sensitised. • Consultative meetings have been held with local community/fishers/NGO's/Government/Private sector/hotel operators/beach hawkers and the local authorities • A grievance mechanism to consider any possible conflicts and public perception on all our sites (Mon Choisy & Riviere des Galets) •A constant public relation is also being conducted with the target group on the 3 sites to inform the progress and the objectives to be met in the context of the AF Project implementation
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The bid prices substantially higher than the amounts earmarked in the budget in the Project Document, for component 1 and component 2. (degree: high) | • The financial offer for Component 1 (Consultancy Services for Mon Choisy & Riviere des Galets) was 275% higher • The financial offer forComponent 2 (Consultancy Services for Early Warning System) was higher than 400% than the budgeted amount in the AF Project document. (degree: moderate) | • Following the 1st round of procurement, the scope of the works had to be reviewed to focus on the key deliverables and implementation within the project budget. A budget revision and extension of time was approved by the Adaptation Fund Board
The process of land availability and acquisition for the construction of the Refuge Centre at Quatre Soeurs under the Component 1 was an issue. (degree: high) | • A Site located on higher grounds, of an extent of 3A04P owned by the private sector was identified for the construction of Refuge Centre at Quatre Soeurs. • The land acquisition procedures was completed by the Ministry of Housing and Lands in June 2015 and land vested to the MESDDBM. (degree: low) | • The land acquisition process was successfully completed in June 2015 by the Mnistry of Housing and Lands. • The project targets as set in the project document will be met under component 1. The scope of works for the respective sites are hereunder listed: Mon Choisy- Wave dissipating structures, beach nourishment, ecosystem based adaptation including seagrass regeneration, plantation of coastal vegetation for dune stabilisation Riviere des Galets - construction of rock revetment, implementation of wave overtopping wall. Quatre Soeurs-The original project scope has been upscaled to provide a newly designed Refuge Centre, which will be a first in its kind in the RoM and in the Indian Ocean to be used as a dedicated Refuge Centre The original scope to retrofit an existing building (approximately 1000 sq ft) has been reviewed to construct a full fledge Refuge centre (10000 sq ft) at more appropriate site acquired by the government of Mauritius and located at 25m above mean sea level as a sustainable solution against storm surge. The original site was not appropriate to house a Refuge Centre against storm surges. Accordingly, the Government of Mauritius was approached and an appropriate site was identified by the Technical Committee based on an agreed site selection matrix and which represented a co-contribution from the Government of Mauritius The output targets have not been affected following the budget reallocation under Component 1. Instead, the targets are being enhanced to achieve a long term and sustainable adaptation measures Mangroves Plantation Project Under component 1, the mangroves plantation project was succesfully completed. Some 20,000 mangroves had been planted along the coastline of Q. Soeurs & region compared with 10,000 as prescribed in the project document. The project has also been replicated to other coastal sites in the Republic of Mauritius with the collaboration of the private sector/NGO's/fishermen & women associations
Poor Performance of Consultant | Poor performance of consultant i.r.t. to the consultancy services for coastal adaptation measures at Mon Choisy & Riviere des Galets under Outcome 1 | The client (UNDP) upon recommendation of Ministry has requested replacement of non performing key personnel for the drafting of the bid document and supervision of works
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
UNDP CO procured the consultancy services for Mon Choisy & Riviere des Galets upon request of the Ministry and approval of the National Designated Authority . The AFB facilitated faster procurement and therefore reduced the risks of delays in delivery. The Mon Choisy Project had to undergo two independent design reviews (1 under the EIA and 1 by the UNDP) to minimise the risks of outcry from the relevant stakeholders (fisher/beach users/hotels operators etc.)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/ Coordinator: | Detailed technical assessment of each site |  | Mon Choisy and Rivière des Galets Procurement of consultancy services for the preparation of feasibility studies, Environmental Impact Assessment Reports, Design, Preparation of Bid Documents and Supervision of Works for the implementation of coastal adaptation measures at Mon Choisy and Rivière des Galets, Mauritius-Completed. Quatre Soeurs Land acquisition procedures for Quatre Soeurs-Completed. Procurement for consultancy services for the design, preparation of tender documents and supervision of works for the construction of Refuge Centre, drainage system and Ancillary works at Quatre Soeurs-Completed Invitation to Bid for the construction of Refuge Centre, drainage system and Ancillary works at Quatre Soeurs-Completed Bid Evaluation for works for the construction of Refuge Centre, drainage system and Ancillary works at Quatre Soeurs-Completed Mangroves Plantation Project completed. |  | COMPONENT 1 STATUS OF IMPLEMENTATION Construction of a Refuge Centre at Quatre Soeurs The construction of Refuge Centre at Quatre Soeurs comprises of highly technical works components including piling works. The major component of the project has been completed and the % completion is at 90%. Some offsite works inter-alia construction of drainage system which were warranted in the context of making the site and building resilient to swells and storm surges are currently being conducted. - The acquisition of land of an extent of 3A04P for construction of Refuge Centre at Quatre Soeurs was completed in June 2015 and land vested to the Ministry. Procurement of Consultancy Services for Quatre Soeurs - The Request for Proposal for Consultancy Services for Design, Preparation of Tender Document and Supervision of Works for Construction of the Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs was launched on 16 February 2015. - The opening of bids was on 25 March 2015 and a Prebid Conference was held on 10 March 2015 at the seat of the Ministry - A Bid Evaluation Committee was constituted by the Departmental Bid Committee of this Ministry for bid evaluation - The contract (local) for consultancy services was awarded on 06 July 2015 to the Consortium: Mega Design Ltd, SEE Engineering Consultants, Steget, Chuttur & Partners Ltd for the price of USD 137,258 (incl. of VAT). Reports submitted by the consultant - As per scope of services, the following deliverables have been completed: a) Inception Workshop report b) Detailed Technical Assessment including survey report c) Geotechnical investigation report and climate change risk assessment reports d) Environmental Impact Assessment Report for construction of Refuge Centre at Quatre Soeurs e) Building maintenance and evacuation plan for the vulnerable communities exposed to storm surges and coastal inundation at Quatre Soeurs f) The architectural design of Refuge Centre and detailed design reports for works including detailed cost estimates g) Maintenance plan of the proposed building h) Bidding document for the construction works of the Refuge Centre The supervision of works are presently being carried out on site. Procurement of contractor for Works for Quatre Soeurs Prebid Conference and Site Visit -A Prebid Conference was held on 13 April 2016 at the seat of the Ministry. -A site visit was conducted following the Prebid Conference at the Quatre Sœurs project site on 15 April 2016 in the presence of representatives from the UNDP, AF Project team and the bidders. The potential bidders took cognizance of the site. Deadline for Submission of bids - The deadline for submission of bids for the Construction of the Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs was on 4 May 2016. - 5 bids were received at the opening of bids on 4 May 2016 - A Bid Evaluation Committee was constituted by the Departmental Bid Committee of this Ministry to conduct the bid evaluation Award of Contract for works - The bid evaluation was completed and the contract for works for the Construction of the Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs was awarded on 24 June 2016 to the best evaluated bidder 'Best Construct Co. ltd' for a price of MUR 43,563,951.62 inclusive of VAT. -The contract for construction of works was signed on 22 July 2016. Mon Choisy & Riviere des Galets Procurement of Consultancy Services We have been confronted to poor performance of the consultant appointed under a UNDP Contract under Component 1 for Consultancy Services for Coastal Adaptation Measures at Mon Choisy and Riviere des Galets. The limitations noted were as follows: 1. Bid document - Quality assurance/external review required 2. Underestimated ‘supervision of works - Replacement of staff required 3. Loose consortium – no better coordination among the team This has led to a delay in delivery of the reports and even various technical aspects were unsatistisfactory both to the client and the Ministry. Furthermore, serious discrepancies in the bid document were found: The bid document was not compliant to the requirements of the Procurement Policy Office. Many inconsistencies were also noted in the Bill of Quantities and technical specifications. The poor technical performance coupled with the protracted delays in submission of documents have adversely impacted in the timeline for implementation of of coastal adaptation measures at Mon Choisy & Riviere des Galets The Contract for Consultancy Services for Coastal Adaptation Measures at Mon Choisy and Riviere des Galets was awarded to Indufor Oy in consortium with eCoast and C.L.A.M.S ltd for a contract amount of USD 817,850 excluding VAT in September 2014 under a UNDP Contract. Stages Completed - To date the following stages have been completed: (i) Inception workshop (ii) Detailed technical assessment (iii) Options for Coastal Adaptation Measures including Cost Benefit Analysis (iv) Feasibility Study (v) Baseline for a managed retreat project at Riviere des Galets (vi) An Economic Valuation and Cost Benefit Analysis of Adaptation and Enhanced Ecosystem Resilience for Mon Choisy Beach (vii) Design for both sites (viii) Bid Document for Works for both sites - Several discussions, Working Sessions (detailed below) and design review activities by (Ministry & UNDP) were held before the final design and bid document were issued. Bidding Document for Construction of Rock Revetment Structure with Parapet Wall at Rivière Des Galets • The first draft bidding document for Construction of Rock Revetment Structure with Parapet Wall at Rivière Des Galets was submitted by Indufor Oy on 19 August 2016 • The bid document was sub-standard and the consultant was advised to consult the website of the Procurement Policy Office and submit the revised bidding document for Riviere des Galets in the proper template • The consultant submitted the revised draft bidding document on 24 August 2016 • The draft bidding document and final design report for Riviere des Galets were circulated to the Technical Committee members on 25 August 2016 for views/comments • Comments were received from The District Council of Pamplemousses, ICZM Division of the Ministry and Ministry of Ocean Economy, Marine Resources, Fisheries, Shipping & Outer Islands • A Correspondence dated 24 August 2016 was received from the consultant ‘eCoast’ in response to letter issued by the Ministry on 26 July 2016 to request clarifications on the following issues; Riviere des Galets • Bidding documents Mon Choisy a. Eco-system based adaptation measures b. Offshore Structures c. Additional hydrodynamic modelling d. No. of Contracts e. Implementation Timeline Meeting held under chair of National Project Director (NPD) • A meeting was held on 30 August 2016 under the chair of the NPD with representatives of the UNDP and the project team to discuss on each of the components of the letter of response dated 24 August 2016 received from Indufor Oy with regards to Coastal Adaptation Works at Mon Choisy and Riviere des Galets and agree on the way forward. • The committee took note that at each stage of deliverables, the consultants came up with arguments with the intention to delay the project. • The committee was of the view that with similar experiences with consultants at the Ministry level, such project delays could follow with claims and variation from the consultants. The committee scrutinized each component of the letter and submitted their views. • The committee agreed that an official correspondence be issued to the consultants on the concerns raised by the committee and on the issues with regards to the draft bidding document for Riviere des Galets. However, it was proposed that the draft letter be vetted by the UNDP CO prior to submission to the consultant. Teleconference with UNDP Regional Technical Adviser • A teleconference was held on 05 September 2016 under chair of the UNDP Regional Technical Adviser whereby the concerns regarding the poor quality of draft bidding document submitted by the consultant ‘Indufor Oy in consortium with eCoast and C.L.A.M.S ltd’ was discussed. • The committee recommended a draft correspondence including the salient comments/issues to be addressed for Mon Choisy and Riviere des Galets be conveyed to the UNDP for vetting prior to submission to the consultant. • The draft letter was sent to the UNDP CO on 07 September 2016 for vetting. The letter included the following amendments on the draft bid document for Riviere des Galets: -Section I (Instructions to Bidders) -Section II (Bid data Sheet) -Bill of Quantities -Preliminary & General Items -Specifications (Material/Revetment/Lighting) • A letter of reminder was sent to the UNDP CO on 13 and 23 September 2016 to request whether the correspondence dated 07 September 2016 had been cleared so that the consultant may be informed accordingly. • The correspondence dated 07 September 2016 was cleared by the UNDP through Dr Peter Wulf, UNDP Consultant on 23 September 2016. • The letter was issued to the consultant on 26 September 2016. • The consultant was instructed in the correspondence dated 26 September 2016 to submit the amended bid documents (Volume 1 – Bidding procedures & conditions of contract and Volume 2- tender drawings (in A3 size) in compliance with ITB 7.1) by 30 September 2016 in electronic format and 3 sets of hard copies, in accordance with the terms of contract agreement. • The UNDP instructed the consultant to submit the bid documents for Riviere des Galets by 06 October 2016. Submission of Final Bidding documents for Construction of Rock Revetment Structure with Parapet Wall at Rivière Des Galets • The consultant submitted the bidding document in (soft copies) for Construction of Rock Revetment Structure with Parapet Wall at Rivière Des Galets on 06 October 2016. •The hard copies of the bidding documents were delivered to the Ministry on 12 October 2016. • The works comprised of Construction a rock revetment of an approximate Length of 430 metres with parapet wall in the coastal frontage at Riviere des Galets. The construction works include: - Demolition of existing gabion revetment - Construction of the rock revetment – transport and delivery of large (up to 2-ton) basalt boulders - Fabrication and installation of a concrete parapet wave-return wall from a combination of pre-cast and cast in place reinforced concrete elements - Installation of concrete pavement/walkway landward of the structure - Installation of specified lighting - Provision of finishing landscaping - Construction of a Parapet extension as per the design specifications near the cemetery boundary going westbound over around 37.5 m • The bid document was approved for launching at the Technical Committee held on 25 October 2016. • The bid document was launched on 09 December 2016 on an Open National Bidding Mode of Procurement • The closing date for submission of bids was 16 January 2016 at 13 30 Hrs (local time). • A Pre-bid Meeting was held under the chair of the Ministry on 20 December 2016. • 3 bidders attended the meeting. On request of the bidders, a site visit was convened on 21 December 2016 at Riviere des Galets to take cognizance of the site and site boundary. 2 bidders attended the site visit at Riviere des Galets. • 3 bids were received at the closing date on 16 January 2017. • A Bid Evaluation Committee (BEC) was constituted by the Ministry and the bid evaluation started on 31 January 2017. • During the bid evaluation some clarifications were sought by the BEC from the Departmental Bid Committee on the Sections ‘Instructions to Bidders’ and ‘Bid Submission Forms’. • A letter was addressed to the Procurement Policy Office (PPO) by the Ministry on 17 March 2017 for advice. • The letter of reply from the PPO was received on 30 March 2017. • The contract for construction works was awarded to ‘Super Builders Co Ltd’ on 03 May 2017 for the contract price of Rs 28,977,556.25 incl. of VAT. 10% completion Consultancy Services for Supervision of Coastal Protection and Landscaping Works at Riviere des Galets (Local) • The bid was launched on 01 December 2016 and the closing date set for 04 January 2017. • Following a request from consultants for an extension of time due to the end of year closure, the closing date for submission of bids was revised to 16 January 2017. • A request for clarifications was received from the consultants on 19 December 2016. • The draft reply was submitted by the project team to the DBC on 22 December 2016. • An addendum was issued by the Ministry on 13 January 2017 • The closing date for submission of bids was further extended by the Ministry to 30 January 2017 at 13 30 Hrs (local time). • 5 bids received were received at the closing date on 30 January 2017. • A Bid Evaluation Committee was constituted by the Ministry and the bid evaluation started on 27 February 2017. • The contract for Consultancy Services for Supervision of Coastal Protection and Landscaping Works at Riviere des Galet was awarded to Luxconsult (Mtius) Ltd on 20 April 2017 for the contract price of Rs 2,510,000.00 incl of VAT. kick off meeting with the consultants • A kick off meeting was held on the 12th May 2017 under the chair of the Ministry with the consultant ‘Luxconsult (Mtius) Ltd’. • The purpose of the meeting was to: (i) introduce the project team members and representative of the Ministry; (ii) to brief the consultant on the overall project including the site constraints, living conditions of the neighboring community at Riviere des Galets; and (iii) to shed light on past projects implemented by the ministry on the project site to showcase the vulnerability of the project site The following items were discussed during the kick off meeting with the consultant: • The consultant was requested to ensure that all works are done in accordance with the scope of work and ensure completion of works within the contractual completion date. • Conformity to EIA conditions and Environmental Monitoring Plan (EMP) • Press issues and any public related grievances to be channelled to the Ministry • Consultant to ensure that the Program of Work (PoW) submitted by the contractor entail realistic construction methodology and disbursement plan • Consultant to process all claims for payment in line with the conditions of contract (i.e) within 28 days to enable the client to effect payments on time. • Submissions of plans/drawings as requested by the Client • Works to be done in phased manner to ensure that the site is safe even during construction works. • No encroachment in the river mouth and the cemetery. A copy of the: (i) Bid submitted by Super Builders Co Ltd; (ii) Bid Drawings; (iii) Company Profile of Super Builders Co Ltd; and (iv) Letter of Award issued to Super Builders Co Ltd was handed over to the consultant. Bidding documents and Revised design for Mon Choisy • The bidding documents for eco-system based adaptation measures at Mon Choisy was expected to be received on 19 August 2016. • The consultant was instructed on 30 September 2016 (i) to submit the aforementioned bidding documents without delay (ii) submit the revised design report for Mon Choisy by 15 October 2016 (iii) submit the bidding document for the implementation of the structural measures by 31 October 2016. • The draft bidding document and drawings for Mon Choisy Public Beach, Part I which includes: Beach Works (Tree and Stump Removal, Sand Procurement, Delivery and Placement, Mechanical Grading, Beach Fencing), Dune Planting, Rock Groyne Removal and Installation of an Artificial Reef was submitted by the consultant on 08 December 2016 • The draft bidding document for Part II which include: Installation of Fixed Mooring Buoys, Establishment of a Voluntary Marine Conservation Area and Seagrass Rehabilitation was submitted on 12 December 2016. • A decision was taken at the level of the UNDP to undergo a quality review of the bid document for Mon Choisy submitted by ‘Indufor Oy’ by a Procurement Expert/Local Engineer) so as to ensure that the document is up to standard and abides by the Laws of Mauritius. • A skype meeting was held under the chair of the UNDP RTA on 16 January 2017. The committee was informed that 2 quotations had been received and the selection of Procurement Expert/Local Engineer) was still under way. • The selection process was completed by ‘Indufor Oy’ on 02 February 2017 and Mr J. Desai appointed as Procurement Expert/Local Engineer) • A meeting was held on 03 February 2017 at the Ministry to introduce Mr J. Desai, local engineer, to the AF Project team. The consultant was informed that the objective was to have a bid document for coastal rehabilitation works at Mon Choisy which is clear and complete with appropriate drawings and detailed specifications so that it could be submitted for approval and launching by the Central Procurement Board (CPB). • The salient points discussed with the consultant on the bid documents for Mon Choisy were as follows: I. Both bid documents shall be based on an admeasurement type of contract in lieu of lump sum contract II. Specific clauses under the Bid Data Sheet (BDS) shall be reviewed III. The Technical Specification is inadequate and shall be re-drafted to respond to the expectation of the undertaking IV. Detailed drawings of the coastal adaptation measures be included V. With respect to the Precast Reef Units, the detailed drawings and specifications of the recommended options shall be provided. The specifications shall also allow for any alternative design by the contractor. The GPS locations of the Reef Units, the anchoring details and the spacing and methodology for placing thereof, including the marker buoys/lights for navigational safety and taking into consideration the existing boat free zone at Mon Choisy VI. The specifications for the walkways and detailed drawings shall be included VII. The BoQ shall be fully detailed and expanded indicating clearly the number of units where applicable. The bill shall be presented in terms of lots for the respective adaptation measures and a clause whereby the client reserves the right to award any one of all the lots be included VIII. To include the GPS location of the Fixed Mooring Buoys and anchoring details thereof IX. Grievance redress mechanism as per the requirements of the UNDP X. The detailed evaluation criteria shall be included under Section IV of the bidding document XI. In compliance to the scope of services of the consultant, Indufor Oy shall be responsible for issuing all approvals, respond to RFIs and RFAs, and issue construction drawings if required. As such, the text in the bid document shall be amended accordingly to reflect the above • A copy of the draft Bill of Quantities was received from the consultant on 25 February 2017. Subsequently, another working session was held with the consultant on 08 March 2017 • The Revised Draft Bid Document for Part I of Mon Choisy was received on 16 March 2017. • Working sessions were held with Mr J. Desai on 03 February 2017, 08 March 2017, 06 April, 02 May, 13 June 2017 to discuss in details the Bid Document (Part I) for Mon Choisy. | S
| Technical design of coastal protection measures at each of three sites-Completed |  | Technical design of coastal protection measures at each of three sites: (i) Quatre Soeurs-Completed (ii) Riviere des Galets-Completed (iii) Mon Choisy-Completed
Joint site visit • A joint site visit was held on 26 April 2017 at Mon Choisy beach in the presence of representatives of the UNDP, Forestry Services, ICZM Division, the local counterpart ‘C.L.A.M.S Ltd’, Desai & Associates and the AF Project Team. The purpose of the site visit was to conduct a ground truthing with the above stakeholders on the (i) Shore Profiles (ii) Tree Removal, in view of finalisation of the bid documents for works • The site survey was led by Mr J. Desai. The following observations were noted during the site visit: Revised Bid Drawings for Mon Choisy • The revised bid drawings was submitted by Mr J. Desai on 13 June 2017. The following comments on the drawings were submitted to the consultant in view of finalization of the bid document: -Drawing No: MC-DRG 01 • The location of the swimming zone and boat free zone demarcation relative to the locus of proposed artificial reefs shall be depicted • The boat passage from the embarkation point No.1 (located near Tarisa Hotel) shall also be indicated in the drawing -Drawing No: MC-DRG 04 • The detailed drawing of the pedestrian access (boardwalk) between the planted areas to be included -Drawing No: MC-DRG 08 • The drawings of the anchoring details, including the clustering of reef balls using stainless steel ropes as proposed by the consultant shall be provided • The X, Y, Z dimensions of the reef units shall be confirmed with respect to the Bill of Quantities-Item 2.1 and the specification Pre-final Bid Document • The Pre-final bid document and drawings for Mon Choisy Public Beach, Part I which includes: Beach Works (Tree and Stump Removal, Sand Procurement, Delivery and Placement, Mechanical Grading, Beach Fencing), Dune Planting, Rock Groyne Removal and Installation of an Artificial Reef was submitted by Desai & Associates Ltd on 16 June 2017. • The bid document was approved ‘in principle’ at the Technical Committee held on 22 June 2017. • The bid specifications was circulated to Technical Committee for views and comments prior to finalization and launching thereof. • The Final bid document and Final drawings for Mon Choisy Public Beach, Part I including all the amendments requested was submitted by Desai & Associates Ltd on 19 July 2017 • The bid document was submitted to the CPB for vetting and launching on 21 July 2017 Procurement of Reef Balls • A request for procurement of the Proprietary Artificial Reef Molds through the RBA Accelerated Delivery form was submitted to the UNDP CO on 08 June 2017. An official letter in view of procurement of the Proprietary Artificial Reef Molds was sent to the UNDP CO on 22 June 2017 including the detailed technical specifications and corresponding drawings. The Revised Draft Bid Document for (Part II) • The Revised Draft Bid Document for Part II which include: Installation of Fixed Mooring Buoys, Establishment of a Voluntary Marine Conservation Area and Seagrass Rehabilitation without the BOQ and Drawings and based on the latest PPO document was submitted by J. Desai on 04 June 2014.
EIA Report for Mon Choisy • The Revised Draft EIA Report (Version 1) was received on 24 March 2017 and Revised Draft SIA Report on 31 March 2017. • The reports were circulated to the main stakeholders for views/comments • The comments of the main stakeholders including the EIA Division was submitted to the consultant on 03 May 2017 • The Revised Draft EIA Report (Version 2) for Mon Choisy was submitted on 23 June 2017 • The EIA Consultant submitted the Final EIA Report for Mon Choisy on 14 July 2017 in (18 sets of hard copies and 2 soft copies in PDF Format) to the Environmental Assessment Division of the Ministry for necessary approval Notice for Public Inspection of EIA Report for Mon Choisy • A notice for Public Inspection of the EIA Report for the 'Coastal Adaptation Works at Mon Choisy' was published in the local press on 19 July 2017. The closing date for submission of public comments was 11 August 2017. Social Impact Assessment (SIA) for Mon Choisy An SIA over and above the EIA was conducted to comply to the requirements of the UNDP. In view of the SIA consultations with the following stakeholders were completed during the reporting period; • Beach goers • Tourists • Hawkers • Boat Operators • Hotels • Registered Fishermen of Pointe aux Cannonier Fish Landing Station • District Council of Riviere du Rempart • Tourism Authority, Beach Authority The Revised SIA Report was received on 31 March 2017. Environment Impact Assessment (EIA) Riviere des Galets • The pre final design review report for Riviere des Galets was submitted on 17 March 2016 • In view of the EIA, several consultations were held with inhabitants of Riviere des Galets, Chemin Grenier Village Councillors, District Council of Savanne on 28th January, 5th February, and from the 2nd to 12th February for informal group discussions. • The draft EIA Report for Riviere des Galets was submitted on 22nd February 2016. The report was discussed at the Technical Committee and the comments received at the committee were transmitted to the consultant. • The Final EIA Report incorporating the views and comments of the Technical Committee was submitted on 31 March 2016 to the EIA Division of the Ministry in 20 copies in compliance with EPA 2002. Notice for Public Inspection of EIA Report for Riviere des Galets • A notice for Public Inspection of the EIA Report for the undertaking ‘Sea Defense Wall at Riviere des Galets’ was published in the local press on 20 April 2016. The closing date for submission of public comments was 06 May 2016. Site Visit by EIA Committee at Riviere des Galets • A Site Visit was conducted at Riviere des Galets on 28 April 2016 by the EIA Committee which comprise of representatives from the EIA Division of the Ministry of Environment, Ministry of Tourism and External Communications, Forestry Services, Ministry of Health and Quality of Life, Wastewater Management Authority, Ministry of Ocean Economy, Marine Resources, Fisheries, Shipping and Outer Island, Road Development Authority, and in the presence AF Project team and Scene-Ries Consult Ltd. • A request for additional information was officially submitted by EIA Committee to the EIA Consultant. • The approval of the EIA Committee was received on 30 August 2016 and EIA Conditions received.
| Successful construction of physical interventions at each of the three sites |  | (i) Quatre Soeurs-Construction Ongoing (ii) Riviere des Galets-Construction Started (iii) Mon Choisy-Expected Start of Works-Janury 2018 (Upon completion of procurement of works) |  | Construction of a Refuge Centre at Quatre Soeurs -The contract for construction of a Refuge Centre was signed on 22 July 2016 with Best Construct Co. Ltd for the contract value of Rs 43,563,951.62 (inclusive of VAT) over a duration of 270 Days -The Handing over of site for Construction of a Refuge Centre at Quatre Soeurs to contractor was held on 25 July 2016, in the presence of the AF Project team, the Consultants, Consortium Mega Design Ltd in association with Design Forum, STEGET, SEE Engineering Consultants Co. Ltd. and Chuttur & Partners Ltd and the Contractor Best Construct Co. Ltd. -A kick off meeting was held on 5 August 2016 at the Ministry in the presence of the Consultants and the Contractor. It was agreed to hold a fortnightly site meeting as from the 25 August 2016 in order to monitor the progress of works and address any issues that may arise. -The contractor started the site mobilization and site establishment as from o8 August 2016 Progress meetings Progress Meetings were held on 25 August, 8 September, 22 September, 6th October, 20th October, 3rd November, 17th November, 1st December, 14th December 2016 and 12th January 2017, 26th January, 8th February, 22nd February, 9th March and 23rd March, 5 April, 20 April, 3rd May, 18th May, 31 May, 14 June, 28th June, 12 July and 26 July 2017 Progress of Works (August 2016-March 2017) -The site establishment was completed with the setting up of the site offices, stores, mess room for workers, toilets, materials storage and a site batching area -The hoarding of the site establishment was completed. -The site clearance for the footprint of the building was completed, as well as the cutting of platforms for the pilling works -The Setting out of the piles started on the 7th September 2016. -The subcontractor Franki piles was appointed for the undertaking of all the piling works -The following works were completed: • Drilling and casting of piles 120 piles • Pile load test on Pile 113 and 11 had been carried out-12th of October 2016 • Trimming of piles • Excavation and Construction of Stepped V-drain, • Excavation for road enlargement at site clearance and for access road to Refuge Centre • Testing of subgrade for road structure • Construction of Stepped V-drain • Excavation of leaching field • Hardcore fill for Access Road • Excavation of Masonry Drain • Construction of RC Drain on alignment I-H • Road Enlargement on alignment I-H • Hardcore fill for Access Road • Construction of energy dissipating pond • Excavation for pile caps and pile capping beams • Trimming of piles • Blinding • Preparation of Sub structure (Pile caps, beams & stub columns) reinforcement • Formworks • Casting of Pile caps and Ground beams • Preparation of reinforcement for building and retaining wall base • The drain under the building-completed • Sewer line under the building-completed with construction of 3 manholes • Reinforcement and casting for septic tank base-completed • The excavation for the sceptic tank-completed • The drain connection and footpath has been done at node ‘H’ • The masonry wall-completed • 5 out of 6 energy dissipating pond-completed. • Shuttering for ground floor slab • Reinforcement for ground floor slab • M & E works on ground floor slab • Construction of drain and manholes under the building • Shuttering and casting of columns and stub columns • Reinforcement, shuttering and casting for Cills and lintel • Retaining wall completed • Construction of ground floor beams and slab • Construction of external staircase Progress of Works (March-June 2017) • The drain under the building-completed • Sewer line under the building-completed with construction of 3 manholes • Reinforcement and casting for septic tank base-completed • The excavation for the sceptic tank-completed • The drain connection and footpath has been done at node ‘H’ • The masonry wall-completed • 6 out of 6 energy dissipating pond-completed. • Construction of septic tank • Construction of water tank base- Completed • Construction of CEB cubicles-completed • Continuation of sewer line and construction of manholes-completed • Casting of Slab for septic tank.-completed • Construction of generator and second water tank base - Ongoing • Cross drain across road access to building Building works completed • Shuttering for ground floor slab • Reinforcement for ground floor slab • M & E works on ground floor slab • Construction of drain and manholes under the building • Casting of ground beams • Shuttering and casting of columns and stub columns • Reinforcement, shuttering and casting for Cills and lintel • Retaining wall completed • Construction of ground floor beams and slab • Construction of external staircase • Reinforcement for ground floor slab • Casting of ground floor slab • M&E works on ground floor slab • Setting out of block walls and columns • Block walls and columns completed in toilet block section • Slab of toilet block • Reinforcement for Columns and Beams of Hall block section • Internal staircase.-Ongoing • Casting of columns and beams of Hall block section • Concealing of electrical pipe in blockwalls • Concealing of plumbing pipe in blockwalls Progress of Works July 2017 Substructure • Boringand casting of 120 no. piles completed Superstructure •Construction of blockworks & ancillary works completed Mechanical & Electrical Works 1. Lighting and switches 2. Speakers for entertainment system 3. PIR for intruders alarm 4. Fire alarm system 5. Data and EWS system 6. Extractor fans in toilet 7. Electrical conduit works for lighting, fire alarm in hall 8. Conduit work in internal staircase for lighting and fire alarm 9. Second fix in hall (electrical) 10. Installation of waste pipe under the ground floor slab 11. Second fix for plumbing in the toilet block 12. Preparation and first fix of pipes for floor drains in toilet block Civil Works 1. Block works for multi-purpose hall 2. Reinforcement for Columns and main beams for multi-purpose hall section 3. Internal Staircase 4th lift 4. Casting of main beams for multi-purpose hall section 5. Construction of table tops 6. Rendering in the toilet block Site works a) Construction of generator and water tank base. b) Construction of footpath and drains. c) Hardcore fill Meeting with Consultant ‘Mega Design Ltd’ -Meetings were held on 20 January, 20 February and 30 March 2017 with the consultant to discuss on the issue of drainage system, leaching field and the overall consultancy services with respect to the Refuge Centre. Meeting with stakeholders w.r.t the drainage system in Quatre Soeurs -A Meeting was held on the 24 October 2016 in presence of the representative of Road Development Authority, Grand Port District Council, Ministry of Health and Quality of life, Traffic Road Management Safety Unit, Mega Design Ltd and AF Project team to discuss on the issue of drainage system with respect to the Refuge Centre. Handing Over of the Refuge Centre in Quatre Soeurs Meeting with National Disaster Risk Reduction Management Centre (NDRRMC) -A meeting was held with the representatives of the NDRRMC on the 16th of May 2017 with respect to the handing over of the refuge centre at Quatre Soeurs. This included the furnishing of the building and the proposal which might be submitted. -A proposal from the NDRRMC has been received which includes the items needed for a functional refuge centre on the 8 June 2017. The procurement of items has been initiated upon approval of the Project Steering Committee Coastal Adaptation Works at Riviere des Galets • The contract for construction works was awarded to ‘Super Builders Co Ltd’ on 03 May 2017 for the contract price of Rs 28,977,556.25 incl. of VAT. • The duration of works will be over a period of 9 months (270 calendar days) from the project start date (order of commence 29 May 2017). Kick Off Meeting with Contractor for construction of Rock Revetment with Parapet Wall at Riviere des Galets •A kick off meeting was held on the 16th May 2017 with the contractor ‘Super Builders Co Ltd’. The purpose was to (i) introduce the project team members and consultant (ii) brief the contractor on the overall project including the site constraints, living conditions of the neighboring community (iii) shed light on past projects implemented by the Ministry to showcase vulnerability of the project site. The following items were also discussed during the kick off meeting with the contractor: • Contractor to adhere to the scope of works and complete the project within the contractual completion date • Conformity to the EIA Conditions and EMP • Safety and security measures at the site • Press issues and any public related grievances to be channelled to the Ministry • Contractor to submit detailed Program of Work, realistic construction methodology and disbursement plan • Works to be done in phased manner to ensure that the site is safe even during construction works • No encroachment in the river mouth and the cemetery. Handing over of Site at Riviere des Galets • A handing over of Riviere des Galets project site was held on 19th May 2017 in the presence of the Contractor ‘Super Builders Co Ltd’, Consultant ‘Luxconsult (Mtius) Ltd’, Local Counterpart ‘C.L.A.M.S Ltd’ AF Project Team, ICZM and EIA Post Monitoring Divisions. The contractor and consultant took cognizance of the existing site conditions and site constraints. The following were also discussed: - The representative from C.L.A.M.S Ltd showed the location of the referral benchmark point. He also indicated the site location at Chainage 0 as indicated in the bid drawings. -A weekly site meeting in the initial stage of the project was agreed Order of Commence • The order of commence was issued by the consultant. The contractual start date was on 29 May 2017 and the contractual completion date on 22 February 2018. Joint Survey • A Joint Survey with the consultant and contractor in the presence of the client ‘Ministry’ was held on 30 May 2017 at the project site. The purpose was to identify the pegs shown on the CAD drawing submitted by CLAMS on the site. Three pegs were clearly marked in red by the surveyor from C.L.A.M.S Ltd on 02 June 2017 and transmitted to Luxconsult (Mtius) ltd, with pictures of the pegs to facilitate their locations. The Joint survey was completed during the reporting period and construction drawings issued to the contractor. Kick Off Meeting with Stakeholders • A stakeholders meeting under the chair of the Ministry was held on Tuesday 06 June 2017. The purpose was to brief the stakeholders on the project so as to ensure facilitation of approvals during implementation of the project. • The meeting was held in the presence of the consultant, contractor and representatives from Ministry of Ocean Economy, National Coast Guard, Ministry of Housing and Land, Road Development Authority, Traffic Management and Road Safety Unit, Police and EIA Post Monitoring Divisions. • The members present agreed to a site visit on 08 June 2017. Site Visit 08 June 2017 • A site visit was held on 8th June 2017 with the relevant authorities; Police, District Council of Savanne, Road Development Authority and Traffic Management and Road Safety Unit. The purpose was to better understand the Contractor’s methodology of work and to take cognizance of the requirements of the different authorities present which were as follows: I. Mauritius Police Force • Road and site safety • Necessary advance warning informing road users of the Works within the proximity of the accesses to the site • Contractor to liaise with the TMRSU for an adequate warning sign scheme. • Contractor to give advance notice to the Police, in case police assistance is required during the Works II. Road Development Authority (RDA) • The route from the rock quarry site up to the site of works was shown • The coastal road shall be used for the transportation of the rocks up to site to which RDA had no further issues. III. District Council of Savanne (DCS) • Use part of the cemetery (extreme edge) as access road by contractor • DCS requested the Contractor to send an official letter requesting approval for wayleave IV. Signboards • The location for the signboards was jointly agreed by the concerned parties • One to be installed just next to the entrance of the cemetery and the second opposite the junction of the Traffic Centre in the road reserve • The Contractor to write to the relevant authorities (DCS and RDA) for necessary wayleaves
[5 empty] | Meeting with Consultant and Contractor -A meeting under the chair of the Ministry on 06 June 2017. The purpose was to discuss on outstanding issues since handing over of site and agree on a time line for upcoming deliverables to enable to proceed. The items discussed were as follows: • Detailed Programme of Works, Works Methodology and Disbursement Schedule • Signboard • Joint Survey • EMP • Site Organigram • Signature of Contract/Client/Contractor • Prediction of Tides for 2017 • Site Visit in view of clearances with the authorities • Insurance Policy • Geotextiles • Site Office and Site Establishment • Rock Test • Permanent Refurbishment necessitating underpinning and Detached Masonry Wall Site visit by Hon. Minister at Riviere des Galets -A site visit in the presence of the Hon. Minister of Social Security, National Solidarity, Environment and Sustainable Development was held on 22 April 2017 at Riviere des Galets. The visit was held in the presence of a delegation comprising of representatives from the Integrated Coastal Zone Division, Adaptation Fund Team, Beach Authority, National Disaster Risk Reduction Management Centre, Living Environment Unit, Project Management Unit to take cognizance of the site. -The AF Project Manager gave an overview of the project area and the works to be implemented at the project site. A detailed geographic description of the area and the difficulties that are faced by the inhabitants were also depicted through a map produced under the AF Project. -Following the site visit, a meeting was held with the inhabitants of Riviere des Galets in the Community Centre of the village. -The Hon. Minister provided a brief on the AF project to the inhabitants on the upcoming works to be carried out most notable the construction of a rock revetment with parapet wall and landscaping works. Contract Agreement -The draft contract agreement for the contractor ‘Super Builders Co Ltd’ was received on 29 May 2017 from the consultant. - The comments of the Ministry were submitted to the consultant on 02 June 2017 for finalization. - The final contract agreement was received on 22 June 2017 and submitted to the contractor for signature on 23 June 2017. Signboard -The drawing of the signboard to be placed at the project site was submitted by the consultant on 07 June 2017. - The comments of the Ministry was submitted to the consultant on 08 June 2017 and drawing approved for finalisation. -Two signboards were produced by the contractor in compliance with the bid specifications and placed in the vicinity of the project site as approved by the authorities. Environmental Monitoring Plan (EMP) -The EMP for Riviere des Galets was submitted to the Ministry on 16 June 2017 by the consultant. Site Meetings Held at Riviere des Galets under the chair of the Consultant ‘Luxconsult (Mtius) Ltd, Contractor ‘Super Builders Co Ltd’ and the Client ‘The Ministry • At the initial stage of the project, weekly site meetings are held with the consultant/contractor and client to monitor progress of work and clear any stumbling bottlenecks. - Site Meeting No. 1-16th June 2017 -Site Meeting No. 2-22 June 2017 -Site Meeting No. 3- 29 June 2017 -Site Meeting No. 4- 04 July 2017 -Site Meeting No. 5- 13 July 2017 -Site Meeting No. 6- 20 July 2017 -Site Meeting No. 7- 27 July 2017 The main items discussed at Site Meeting No. 1 were as follows: • No physical works on site • Documents still not yet submitted by contractor such as PoW, Method Statement etc. • Significant number of correspondences issued by contractor • Insurance Policy • Performance bond • Key Personnel/Site organigram • Contract signature • Programme of works/works methodology and disbursement schedule • Joint Survey & Construction Drawings • Rock tests • Materials approval and procurement • Progress of works • Health & Safety • EMP • Social aspects • Advance Payment (15%) Tidal Predictions for 2017 -A request was submitted to the Mauritius Meteorological Services (MMS) on 09 June 2017 for submission Tidal Predictions for 2017 to the Ministry in the context of the project at Riviere des Galets. The requested information was received from the MMS on 20 June 2017. Payment to Contractor -According to ITB 41 of the Bid Data Sheet, an Advance Payment of 15% of the Contract Price less the provisional and contingencies sums was effected against a bank guarantee issued by a local commercial bank 'SBM Bank (Mauritius) Ltd' amounting to Rs 4,346,633.44 (Rupees Four Million Three Hundred and Forty Six Thousand Six Hundred and Thirty Three and Cents Forty Four only) was paid to the contractor: % Completion • To date it is estimated that 10% of works have been completed | S
S
S
S
| Assessment of the current sea state monitoring systems (Mauritius Meteorological Services and Mauritius Oceanography Institute) and definition of required critical parameters and operational requirements for an early warning system. |  | Procurement of consultancy Services for the implementation of an Early Warning System for incoming storm surge in the Republic of Mauritius-Completed The Early Warning System for incoming Storm Surge for the Republic of Mauritius installed at the Mauritius Meteorological Services and fully operational |  | Component 2: Early Warning System for Storm Surge for the Republic of Mauritius Memorandum of Understanding - A Memorandum of Understanding (MoU) was signed between the MESDDBM and Mauritius Meteorological Services (MMS) for joint implementation of the project component on 13 March 2014. Consultancy Services awarded to Stichting Deltares - The consultancy services for implementation of the Early Warning System for incoming Storm Surge in the Republic of Mauritius was awarded to Stitching Deltares, a leading independent research and internationally operating specialist consultancy institute. -The consultants effected field missions in Mauritius since 2014 until 2015 - In July 2015, hands-on training on Delft-FEWS components and Mauritius EWS was delivered to officials from the MMS, Mauritius Oceanography Institute, NDRRMC. The main goal of the training sessions was to make the participants more comfortable dealing with the Delft-FEWS Early Warning System. In addition, the sessions provided the opportunity to explore the initial version of the EWS. -The Consultants effected their last mission from 03 to 07 August 2015 in Mauritius. - The EWS has been implemented and is already operational at the Mauritius Meteorological Services (MMS). - Some 20 participants from the MMS, Mauritius Oceanography Institute, National Disaster Risk Reduction Management Centre, Ministry of Housing and Lands (Hydrographic unit) and the project team received training on the operation of the EWS and Delft FEWS and Delft 3D model Training Overseas in The Netherlands -3 officials (1 from the National Disaster Risk Reduction Management Centre, 1 from the AF Project team and 1 from MMS received a 2 weeks' training course in The Netherlands from 24 August to 05 September 2015. Mauritius is the first SIDS country to have implemented its own storm surge Early Warning System. - Mission visit of International Consultant from Deltares, Mr D. Vatvani, Project Coordinator of Deltares was on a 1 week mission visit to participate in a working session at the Ministry and to conduct further training organized by the World Meterological Organisation on storm surge, swells and modeling. - The working session was held in the presence of the UN Resident Coordinator and UNDP Resident Representative, Offiials of this Ministry in order to finalize the way forward for the AF Project. Signature of Memorandum of Understanding (MoU) with Stitchting Deltares and UNESCO -IHE -With a view to ensuring the sustainability of the project in relation to capacity building, technical support and technology transfer for a more effective use of the numerical model of the EWS, a MoU between this Ministry through the Adaptation Fund, Stichting Deltares and UNESCO- IHE was signed on 20 January 2016 in the Kingdom of Netherlands in the presence of the Hon Minister R. Dayal and the Project Manager. Purpose -To secure technical assistance in terms of research and capacity building for coastal zone adaptation and operation of the Early Warning System for Storm and Tidal Surge. -The Government of Mauritius (Cabinet office) approved the MoU signed between this Ministry, Stichting Deltares and UNESCO IHE. The main areas of cooperation under the MoU are listed below: • Facilitate scientific and research exchange of scientists, research scholars and specialists, etc. for the purpose of research, training, consultation and exchange of expertise • Ensure Continuous Professional Development for staff of the Mauritius Meteorological Services • Training and capacity building in the field of disaster risk reduction management, coastal engineering and adaptation to climate change • Exchange of scientific and technical information and documentation • Organization of bilateral scientific and technical seminars/ workshops/ conferences and training courses on problems of interest to both countries. • Other forms of scientific and technological cooperation as may be mutually agreed upon by the parties within the scope of this MoU | S
| Handbook on Coastal Adaptation” packaged as training modules for coastal communities, relevant Government agencies, and private sector stakeholders |  | Courses developed and implemented |  | Component 3 : Training Besides the output target 3.1, 3.2, 3.3 and taking into consideration the recommendation of the mid-term review, a continued training following the terminal phase of the project was held. 4 Training Manuals hereunder listed have been produced and are currently being distributed in Universities, Ministries/departments. 4 Handbooks produced under the Adaptation Fund Project • 1 Handbook entitled ‘Training Manual for Coastal Protection Works’-Completed • 1 Handbook entitled ‘Training Manual on Coastal and Marine Environment for Engineers’-Completed • 1 Handbook on 'Cost Benefit Analysis for Coastal Management and Adaptation Options to Climate Change'-Completed • 1 Handbook on Integrated Coastal Zone Management-Completed 13 Short Courses designed and delivered in Mauritius and Rodrigues as follows: 9 Short Courses on Coastal Engineering/Coastal and Marine Environment/ICZM/Disaster Risk Reduction/Open Geospatial tools 1. Short Course on Coastal and Marine Environment for Engineers (CMEE) in Mauritius 2. Short Course on Coastal and Marine Environment for Engineers (CMEE) in Rodrigues 3. Short Course on Coastal Engineering (Specialisation 1) Mauritius 4. Short Course on Coastal Engineering (Specialisation 2) Design of Coastal Adaptation/ Protection Structures including a case study for Mon Choisy (Mauritius) 5. Short Course on Ocean Data Collection and Analysis (Mauritius) 6. Short Course on Climate Change and Coastal Zone Management (Mauritius) 7. Short Course on Open Geospatial tools 8. Short Course on Disaster Risk Reduction 9. Short Course on ICZM 4 Short Courses on Cost Benefit Analysis for Coastal Adaptation Measures 1. Short Course on Cost and Benefit Analysis of Coastal Adaptation Measures 2. Short Course on Cost Benefit Analysis/Climate Change Economics 3. Short Course on Cost and Benefit Analysis of Coastal Management and Adaptation Options to Climate Change (Rodrigues) 4. Short Course on Cost Benefit Analysis Applied to Climate Change Initiatives 494 Engineers and technical staff (both from public and private sector) have been trained under the Adaptation Fund Project Activities during August 2016-July 2017 Activity 3.1: Handbook on Integrated Coastal Zone Management (ICZM) -As per the contract signed with the University of Western Australia (UWA), a draft of the ICZM Handbook was received and circulated to the members of Technical Committee and participants who followed the training course. - The comments received were sent to back to UWA. - The revised handbook was submitted by the UWA on 23 August 2016. - The objective of this handbook is to assist in the delivery of an Integrated Coastal Zone Management for Small Island Developing States short course. This handbook together with the short course delivered, were to connect coastal and climatic changes predominantly observed on small coral reef island nations to an integrated coastal zone management (ICZM) framework. It provides an overview rather than an in-depth reference of the key elements of integrated coastal zone management and the tasks associated with each of these elements. --A meeting was held to discuss on the contents of the ICZM Handbook. It was proposed to add a chapter which contained case studies related to the Mauritian context in the Final Handbook. The representative of the University of Mauritius proposed to draft this chapter and submit to the committee. -The final draft of the ICZM Handbook was received and submitted to the UNDP Country Office for onward transmission to the UNDP Regional Office for a peer review. -The views of the UNDP was incorporated in the final handbook submitted on 11 February 2017. -The printing of the ICZM Handbook is ongoing Short course on Cost-Benefit Analysis applied to climate change initiatives -As per the scope of cooperation under the signed MoU, the procurement for design and delivery of short courses was undertaken by the University of Mauritius for the Ministry. -The short course on cost-benefit analysis applied to climate change initiatives was approved by the Project Steering and Technical Committee. -The University of Mauritius conducted the procurement exercise for recruitment of an international resource person for the design and delivery of the above short course. -The contract for consultancy services for the design and delivery of a short course on cost-benefit analysis applied to climate change initiative was awarded to the University of Western Australia (UWA) for the sum of AUD 33,076. - The short course was delivered from 12-16 September 2016 at the Seat of the University of Mauritius Branch in Ebene, by the Resource Person, Prof D. Pannell from UWA. -36 participants were trained. Visibility Event: Opening Ceremony for the Short course on Integrated Coastal Zone Management and launching of Cost benefit Analysis Training Manual. -An opening ceremony for the Short course on Integrated Coastal Zone Management and launching of Cost benefit Analysis Training Manual was held on 12th September 2016 in the Presence of the Hon. Minister of Environment, Sustainable Development and Disaster and Beach Management, the second secretary of the Australian Commissioner Ms B. Minois, the UNDP representative Mr S. Ramchurn and some other 50 invitees. The opening ceremony was followed by a half day workshop. Courtesy meeting with Director of University of Western Australia (UWA) • A meeting was held on the 10th May 2017 under the chair of the Ministry with the newly appointed Director of the University of Western Australia's Oceans Institute, Prof. Techera on mission in Mauritius from 8 - 12 May on the occasion of the regional Short Course on Oceans which the University of Western Australia will be running in Mauritius in collaboration with the University of Mauritius. • The meeting was held in the presence of the officials from the Ministry. The committee discussed on the way forward and a possible partnership on research and/or providing training and education programs with the Ministry. | S
S
| Short course on Coastal Engineering designed and delivered |  |  |  |  | S
Specialized course on Cost-Benefit Analysis of coastal adaptation measures designed and delivered
| A National Coastal Zone Adaptation that addresses all perceived climate change risks in the coastal zone of ROM over at least the next 20 years, with recommendations for supporting policies and regulations |  | Procurement Procedures for Consultancy Services completed |  | Policy Mainstreaming • Expression of Interest completed • 6 international consultants shortlisted • TOR finalized • List of acts for Republic of Mauritius compiled • Gap analysis undertaken by Technical Committee • List of reports and documents w.r.t. Policy in coastal zone of Mauritius compiled Request for Proposal (RFP) document for Consultancy Services (First Round of Procurement) -The RFP document was launched on 18 December 2015 to the shortlisted firms approved by the Project Steering Committee. -At the closing date on 10 February 2016, no bids were received. RFP document for Consultancy Services (Second Round of Procurement) -The bids were re-launched following a restricted bidding mode of procurement at National Level on the 29th February and the closing date for submission of bids was 31 March 2016. No bids were received. Request for Proposal (RFP) document for above consultancy Services (Third Round of Procurement) -The Terms of Reference was revised by the Project Management Unit in collaboration with the UNDP CO Launching of Request for Proposal Policy Mainstreaming -In line with the deliverables under the Adaptation Fund Project, a National Coastal Zone Adaptation Strategy (NCZAS) for the Republic of Mauritius shall be prepared. The main objective is to prepare a NCZAS that addresses all perceived climate change risks in the coastal zone of Republic of Mauritius. -The NCZAS would include relevant strategies, policies, laws, regulations and projects pertaining to the coastal zone in the Republic of Mauritius, results of map based vulnerability assessment and adaptation options based on assessment, recommendations for new economic instruments and best technical, economically efficient, and institutionally relevant adaptation practices especially in the SIDS context of Mauritius. • The revised RFP document for Consultancy Services for the Preparation of a National Coastal Zone Adaptation Strategy for the Republic of Mauritius was launched on 08 August 2016 on an open international bidding mode. Bid Notice • The bid notice was published in the local press and uploaded on the website of the Ministry, Procurement Policy Office, UNDP and disseminated to all diplomatic missions through the Ministry of Foreign Affairs, Regional Integration and International Trade in view of having a wider international outreach. Addendum No.1 • The initial closing date for submission of bids was 19 September 2016 at 13 30 Hrs (local time). • An addendum was issued by the Ministry on 18 August 2016. • The closing date for submission of bids was extended to 26 September 2016 at 13 30 Hrs (local time). • The addendum was uploaded on the aforementioned websites where the RFP document had been posted. Reply to Clarifications A letter of Reply to Clarifications received from the bidders was issued by the Ministry on 26 August 2016. Pre-bid Meeting A Pre-bid Meeting was held under the chair of the Ministry on 09 September 2016. A presentation was made by the AF Project team on the project overview, objective of the assignment and main requirements under the consultancy services. 4 representatives (local counterparts) of the international consultancy firms attended the Pre-bid meeting. A list of clarifications relevant to the assignment was submitted by the consultant at the Pre-bid meeting. The reply to the clarifications was circulated to the consultants on 15 September 2016. Opening of bids The opening of bids was held at the Ministry on 26 September 2016 at 13 30 Hrs (local time). 5 bids were received. Constitution of the Bid Evaluation Committee • A Bid Evaluation Committee was constituted by the Departmental Bid Committee Award of Contract • 5 bids were received and following bid evaluation • The contract for consultancy services for the preparation of National coastal zone adaptation strategy for the Republic was awarded to ‘AGRER S.A.-N.V.’ from Belgium for a contract amount of Rs 5,752,300 inclusive of VAT on 28 November 2016 • The contract agreement was drafted by the project team and submitted to the Departmental Bid Committee (DBC) on 16 December 2016 for vetting and onwards signature by both parties. • The contract agreement was signed on 6 February 2017 • The consultancy services shall be completed over a duration of 8 Months including missions in Mauritius and Rodrigues. • NCZAS will include: - Review of relevant strategies, policies, laws, regulations and projects pertaining to the coastal zone in the ROM, including international best technical and institutional adaptation practices. - Results map bases vulnerability assessment and adaptation options based on that assessment, including most vulnerable coastal areas and systems with development capacity limit; - Formulation and prioritization of options for adaptation policies and measure and recommendations for new economic instruments and best technical, economically efficient and institutionally relevant adaptation practices, policies and regulations; - Creation of a ‘clearinghouse’ for climate change oversight in the coastal zone of ROM Field Mission for AGRER • The Team Leader J. Mc Cue was on a field mission from 1to 10th March 2017. He conducted the inception workshop on the 2nd of March 2017. • The Legal and Policy expert Chris Hedley was present from 8th to19th March 2017. A series of meetings were scheduled at the offices of this Ministry and several stakeholders. Inception workshop • A full day inception workshop was held on the 2nd of march 2017 in the presence of the Team leader Mr J. Mc Cue from AGRER S.A.- N.V, the Honorable Minister E. Sinatambou, officers of various Ministries, private sector and NGO at the Caudan Waterfront hotel, Port Louis. Consultations/meetings • Following the inception workshop, a series of meetings were scheduled. The purpose of these meetings was to combine available digital and non-digital data sets to help the project, to identify information or data gaps and to clarify the methodology to perform the vulnerability assessment exercise Adaptation Workshop on Adaptation Policies and Vulnerabililty Assessment in Coastal Areas in Mauritius • The second stakeholder workshop for the NCZAS Project was held on 23 June 2017 at the Hennessey Hotel, Cyber City, Ebene, Mauritius • The purpose of the workshop was to: - Explain the findings of the projects latest deliverable (Task 1 Report) on coastal regulations, laws and policies and to present some international best practice examples; - Explain the issues and options that need to be considered at the concept NCZAS design stage; - Provide an update on the coastal vulnerability index work being completed by Mauritius Oceanographic Institute (MOI); - To present early coastal typology maps produced for the coast and hear discussions on how these shall be used within the NCZAS; - To provide an opportunity for participants to ask questions about the NCZAS design, early ideas on adaptation strategic measures, make suggestions for improvements and/or alterations. • Approximately 60 technical staff attended the workshop, including a range of government representatives and District Council officers and local/international consultants. Adaptation Workshop on Adaptation Policies and Vulnerabililty Assessment in Coastal Areas in Rodrigues • The first stakeholder workshop for the NCZAS Project was held on 28 June 2017 at the Cotton Bay Hotel, Rodrigues. The purpose of the workshop was to: - Introduce the purpose of the project; - Relay back to stakeholders some early observations of coastal adaptation challenges based upon and earlier mapping exercise of coastal typologies and ground truthed following a rapid field assessment undertaken on 27 June2017; - Explain the findings of the projects latest deliverable (Task 1 Report) on coastal regulations, laws and policies and to present some international best practice examples; - Explain the issues and options that need to be considered at the concept NCZAS design stage, especially how ecosystem based adaptation (EbA) techniques can be embraced within the NCZAS; - To present early coastal typology maps produced for the coast of Rodrigues and hear discussions on how these shall be used within the NCZAS; - To provide an opportunity for participants to ask questions about the NCZAS design, early ideas on adaptation strategic measures, make suggestions for improvements and/or alterations. - To determine levels of progress regarding the Regional ICZM Committee of Rodrigues (established in 2010) is currently working on the creation of a public ICZM Data Management Office. • Approximately 40 technical staff attended the workshop, including a range of government representatives and District Council officers and local/international consultants. • Reports Submitted by AGRER S.A 1)The Draft inception report was submitted on 9 March 2017 2)The Final inception report was submitted on 27 March 2017 The Inception Report covered the following key areas: a) Section 1: Introduction b) Section 2: Project Understanding – a brief overview of the Adaptation Fund (AF) project and how the objectives and outcomes of this consultancy support the AF project. This section includes preliminary observations, findings and key data gaps identified from the initial desk review. (NB: this review is based on reports/data reviewed prior to, and during the Inception Field Mission 1-9 March 2017). c) Section 3: Technical Approach and Methodology - a review and update of the AGRER approach and methodology as discussed with the client and with key project stakeholders at the Inception Workshop and Inception Mission (2-9 March 2017). Any updates to the scope of the project, based on initial observations identified in Section 1, are clearly outlined in addition to any required alterations to the delivery and approach. d) Section 4: Updated Work Plan - provides updated narrative of the proposed activities and deliverables as agreed during the Inception Mission and as originally defined within the AGRER Work Plan. e) Section 5: Consultation, Workshop and Training Strategy – summary details of the approach towards consultation and (where possible) details of the remaining workshop and training events proposed. 3) The Draft Task 1 relevant strategies, policies, laws, regulations and projects pertaining to the coastal zone in ROM and relevant international best technical and institutional adaptation practices in coastal zone management report was submitted on 11 May 2017 • In support of achieving Outcome 4 of the AF project (entitled “Improved policies and regulations promoting and enforcing resilience measures”), the specific purpose of this report is to provide early commentary on a range of issues set out within the Terms of Reference (ToR). This information shall be used as baseline information, and useful commentary, to help in the production of the NCZAS. • The baseline understanding information being collated within this report includes a review of relevant strategies, policies, laws, regulations and projects pertaining to the coastal zone in ROM. It also includes commentary on past coastal management projects undertaken in Mauritius between 2003 and the present day, a review of land management policies of relevance to the coastal zone, a review of the current coastal adaptation funding options and their appropriateness, a preliminary review of some strategic plans/documents (such as the Hotel Development Strategy) in terms of any coastal adaptation implications for the NCZAS and finally a preliminary review of available international ICZM/coastal adaptation best practices (legal/engineering etc) that may prove of relevance to the Mauritian /Rodrigues situation. Review of the Draft TASK 1 Report • The Draft TASK 1 Report was circulated to the Technical Committee for views and comments on the 19 May 2017. • All the observations/ salient comments were sent to AGRER on 8 June 2017 to amend the draft report accordingly. Submission of Final TASK 1 Report • AGRER submitted the Final TASK 1 Report on 16 June 2017. • A soft copy of the report was circulated to all the members of the Technical Committee. Consultations/meetings Ministry of Housing and Land -The AF team had a meeting with the Min of Housing and Land ( the cartography section )with respect to the information available on the 4 April 2017. Consultation with the UNDP Resident Representative •A meeting was held with Mr Simon Springett, the Consultant Jonathan McCue and the AF Team on the 30 June 2017. •The key points raised during a meeting with the UN Resident Coordinator, Simon Springett, are presented below: - The NCZAS should ensure that risk and hazard maps (produced by the National Disaster Management Centre – NDMC) should be reviewed and considered. - It is acknowledged that tsunami inundation maps are not currently in the public domain and hence may not be used as part of this project. • Consideration of the use of seasonally unused technical equipment (British Antarctic Survey – BAS) such as LiDAR equipped planes etc. The initiation of any new LiDAR survey of the coast will not be possible during the AF project timescales. • More details on the Early Warning System approach is needed for AGRER to review and consider as management approach (intervention options). AF team to provide summary information to AGRER if possible. • World Bank summary report exists on hazard risk mapping for Mauritius, which may be available from NDMC or direct from World Bank. This appears to address climate and disaster related regional insurance aspects and climate finance for countries within South West Indian Ocean and not just Mauritius and Rodrigues. | S
A set of recommendations on best technical and institutional adaptation practices suitable for the coastal zone of ROM.
Definition of the required structure and processes for one “clearinghouse” or climate change oversight in the coastal zone of ROM
S
S
S
S
S
| Handbook, training modules, and website content capturing best coastal adaptation practices for the Mauritius context |  | This component is being implemented in paralell to the implementation of works at the project sites and monitoring of the effectiveness of the adaptation measures through lessons learned. |  | Component 5: knowledge Dissemination Signature of Memorandum of Understanding A first MoU was signed between Reef Conservation and the MESDDBM to kick start the joint implementation of the project on sensitization of the Coastal Communities using a Marine Mobile Unit, development of sensitization materials and 3D Small Scale Models on mangroves ecosystem, coastal zones, coastal adaptation works, as well as, educational tours on mangroves ecosystem, coastal zones and coastal adaptation works. Memorandum of Understanding with Reef Conservation (NGO) and Rogers Foundation ltd (Private Sector) A MoU was signed on 30 March 2016 between Reef Conservation (NGO) , Rogers Foundation Ltd (Private Sector) and this Ministry for the joint undertaking of the activities listed under Component 3: Training and Component 5: Knowledge Dissemination, for a period of 1 year. This initiative provides a platform for public and private partnership to endeavour to adapt in the coastal zone of Mauritius. The areas of cooperation were; • Sensitisation among the Coastal Communities taking into consideration gender and outreach campaigns using the Marine Mobile Educational Unit, also known as ‘Bis Lamer’. • Development of learning/sensitization materials. This will include: 1. A Handbook on coastal Adaptation for the coastal Communities 2. An electronic quiz game 3. 3D small scale Bis Lamer with protective carry case 4. A Do’s and Don’ts sheet at sea with the pouch for boat operators and fishermen. 5. The development of Climate Change community sensitisation game (snakes and Ladder) Current Status • 5 Small Scale Models developed • 2 Display Boards Installed • 3D Small Scale Bis Lamer Model completed • 3D Small Scale Model for South East Marine Protected Area, Marine Park Completed • 3D Climate Change Globe Model • Electronic Quizz Game Electronic Game Application The development of a concept for a game application on climate change targeted for children aged 12 and above has been developed. The purpose is to create an innovative tool to raise awareness about impacts of climate change, targeted for the youth. Public awareness campaigns Development of 1 Marine Mobile Education Unit A Marine Mobile Unit was developed by the Rogers Group (private sector) in collaboration with Reef Conservation (NGO) and the Ministry. The Marine Mobile Education Unit was officially launched on 09 September 2014 at Rogers House, Port Louis. Current Status • 26 sensitization/public awareness campaigns conducted using the Marine Mobile Educational in schools, community centers, social welfare centers and shopping malls. • 2721 students (primary and secondary schools) and coastal communities sensitised as follows; a) Primary School Children of Standard IV, V and VI of St FranXavier RCA on 29 September 2015 b) Elderly Associations and local Communities at Pandit Dayanand Recreational Centre on 30-Sep-15 c) Coastal Communities of Blue Bay Public Beach on 23-Jan-16 d) General Population in the region of Trianon Shopping Mall on 16-Apr-16 e) Secondary School Students of Form 1 to 5 at SSS Swami Vivekananda on 19-Apr-16 f) Secondary School Students of Form 4 & 5 at SSS Rajcoomar Gujadhur on 5-May-16 g) Coastal communities of Bain Boeuf Public Beach on 21-May-16 h) Primary School Students at Quatre Cocos on 26 May 2016 i) Primary School Students at Bois des Amourettes GS 14 June 2016 j) Palmar Community Centre on 18 June 2016 k) Secondary School Students of Form 3 and 4 SSS Pailles on 28 June 2016 l) Secondary School Students of Form 3 and 4 SSS La Gaulette on 30 June 2016 Some 15,000 people have already been sensitized to date on Climate Change Adaptation using the Marine Mobile Educational Unit. A Handbook on coastal Adaptation for the coastal Communities -A handbook targeted to coastal communities, NGOs and private sector stakeholders is currently being developed. -The main objective to explain the effects of climate change in the coastal zone of Mauritius and capture the coastal adaptation practices for the Mauritius. It will be issued in English, French and Mauritian Creole. -The First Chapter of the Handbook was submitted in June 2016 and reviewed at the Level of this Ministry. - A Technical working group chaired under the Deputy Director, of the Ministry was constituted. - Monthly meetings were held since June 2016 to monitor the progress of development of handbook. Working Sessions with Reef Conservation and Ministry -Working sessions were held with representatives of Reef Conservation and the Ministry to discuss the way forward with regards to the development of the remaining Knowledge Disseminating Tools • Final draft of the Handbook reviewed by the working group, with inclusion of comments • The production of the Goose Game • 3000 Waterpoof pouch received in Mauritius Ready for distribution. Meeting with Reef Conservation -A meeting was held on 24 January 2017 with representatives of Reef Conservation and the working group, to provide comments on the Final draft of the Handbook. -The Agenda was as follows: (a) Final Comments for the Coastal Adaptation Handbook (b).Waterproof pouch (c)Comments for illustrations and text for the Flash cards (d)A.O.B A Do’s and Don’ts waterproof pouch for boat operators and fishermen- Ongoing -A waterproof pouch is being developed under the project which will serve as a handy tool for users operating at sea. - The pouch includes a compartment that could hold various important documents such as ‘licences’ which boat operators are legally required to keep handy for inspection by the enforcing agencies. - The waterproof pouch would include messages to sensitise users on the need to protect the marine environment. It would also be used as a practical learning aid. Way Forward -The waterproof pouches have been received and the mode of distribution is being looked into by the Ministry Development of climate change community sensitisation game (Snakes and ladders/ Goose Game) -The concept for the game had been developed by Reef Conservation and approved by the Adaptation Fund Project team. It was named ‘The Giant Goose Game’ instead of Snake and Ladders. -The game has been completed and submitted on the 24 March 2017. -The game has been loaned to Reef Conservation to serve as educational tools during sensitization campaigns. Flash Cards instead of Quiz Game -Validation of the illustrations and final text of the flash cards. Production of the flash cards is expected to be ready by the next quarter. - The printing of the flash cards is under process Training of Coastal Communities and Outreach Campaigns It is also envisaged to develop various learning materials and conduct training through the marine mobile education unit. The main topics included in the trainings are: 1) Effects of Climate Change on Coastal Zones of Mauritius 2) Adaptation measures implemented in Mauritius 3) Importance of Mangroves on the ecosystem This training is also conducted in collaboration with the Private sector and Non-Governmental Organization (Reef Conservation) for broader outreach. Interactive models -The interactive 3D models are being used to enhance the training conducted at schools, to the general public at large and the coastal communities. Marine Mobile Education Unit -1 sensitization/public awareness campaigns using the Marine Mobile Educational Unit has been scheduled for the next quarter. Some 3500 persons have already been sensitized to date on Climate Change Adaptation using the Marine Mobile Educational Unit through conduction of 31 sensitization campaigns, as at date. Resource Centre in Rodrigues • A working session was held with the Office of the Chief Commissioner, Commissioner of Environment and Island Chief Executive of the Rodrigues Regional Assembly (RRA) on 17 and 18 November 2014. Representatives from the UNDP CO, UoM, and the Project Team attended the working session. The signature of a MoU with the RRA was agreed. The construction of a new resource centre within the South East Marine Protected Area (SEMPA) in Rodrigues was approved by the RRA. The progress of activities in Rodrigues were as follows; • A site visit was effected on 23 Dec 2014 by the Rodrigues Cadastral Office, Public Infrastructure Division, Environment Unit and SEMPA team to discuss the project requirements. • A second site visit was effected on 27 Jan 2015 by the Commissioner of Environment, Departmental Head, Commission of Environment, Global Consultants and SEMPA team for finalization of overall project requirements. • An official request was sent by the Commission of Environment (Rodrigues) to the Commission of Public Infrastructure for drafting of Preliminary Design of the Resource Centre. • Vesting of land by the Cadastral Office (Rodrigues) to SEMPA completed • Consultancy Services for Design and Preparation of Tender Docs by Global Consultant (Procurement completed) • Construction and hosting of Resource Centre in 2017 by the Rodrigues Regional Assembly • Development and funding of educational materials under the AF Project, such as, 3D Model of the SEMPA, and other learning materials The construction work for the SEMPA Interpretation Centre started on 10 May 2016 and building nearly completed. | S
Dissemination of lessons learned from the programme with coastal stakeholders in other locations in the southern Indian Ocean
Interpretive signs and smallscale models of coastal processes designed and installed at each site, explaining the science of climate change and coastal processes
Public awareness campaigns on climate change in the coastal zone designed and delivered
S
S
S
S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Nuvin KHEDAH, project manager
| Email: | mnkhedah@yahoo.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The progress made during the reporting period is satisfactory. The AF Project has contributed to bring innovative measures in terms of climate change adaptation in Mauritius. Early Warning System (EWS) for storm and tidal surge The implementation of the EWS for storm and tidal surge has been successfully completed and today Mauritius is the first SIDs to own a fully automated EWS for storm and tidal surges. The system is currently operational at the Mauritius Meteorological Services (MMS) and the output thereof have integrated in the forecasting system of the MMS and is being regularly disseminated to the NDRRMC for decision making for evacuation of the vulnerable communities. Eco-system based adaptation project (EBA) (mangroves plantation) The EBA Project comprising of the establishment of a natural coastal defence against storm surges was implemented under a community based project which has been very successful. The Project was recognised by the UNDP as a best practice as an EBA and an excellent example of climate change adaptation that advances conservation and utilizes innovative solutions to develop economic opportunities to empower communities. The storyline could be accessed on https://undp.exposure.co/20000-mangroves-strong. The project was also awarded the first prize of the Island Bright Spot Award as part of the Global Island Partnership 2013 Solution Search out of 37 countries. This Community Based Adaptation Project was also showcased at the UN SID’s Conference in Samoa in August/September 2014 and at the COP 21 Meeting. Construction of a Refuge Centre at Quatre Soeurs The proposed project for the construction of a Refuge Centre at Quatre Soeurs as stipulated in the project document was re-visited. The initial proposal comprised of implementation of a Refuge Centre (100 M2) in an inundation prone site with limited extent of land available for construction and limited access. This had warranted a land acquisition by the Government of Mauritius (GoM) to the tune of USD 320,000 which was fully financed by the GoM as in-kind contribution to the project. Currently, a Refuge Centre of an extent of 1000 M2 is being constructed over a land extent of 3A04P which is 10 folds bigger and located 25 metres above MSL. The construction of the Refuge Centre has warranted high level of technical expertise for the construction of a sub-structure. The construction is nearing completion and the Refuge Centre is expected to be showcased as a dedicated Refuge Centre for the RoM and an example for replication by the GoM. Training and Capacity Building Thanks to a very robust partnership (MoU) signed with the University of Mauritius, in particular the Faculty of Ocean Studies, the deliverables under Outcome 3 have been completed and is more than satisfactory with an expected high level of durability. Progress under this training component allowed to create a momentum around the project and keep the stakeholders interested and involved during the procurement process which will benefit the whole project in the long term. Delivery of Outcome 3 also links to delivery of Outcome 5 (Knowledge Management and Dissemination) and all training materials/training manuals/ and lessons learned are compiled for future diffusion at national and international levels. Policy Mainstreaming The Contract for development of a National Coastal Zone Adaptation Strategy for the Republic of Mauritius under the Component 4 (Policy Mainstreaming) has already been awarded. The Review relevant strategies, policies, laws, regulations and projects pertaining to the coastal zone in ROM has been completed and currently an analysis of the vulnerable areas are being undertaken both for Mauritius and Rodrigues. This component is expected to be completed by January 2018. Riviere des Galets & Mon Choisy Despite being confronted to poor performing consultants for Mon Choisy & Riviere des Galets under (Outcome 1), thanks to the UNDP colloboration to address the shortcoming. The bid documents for Mon Choisy & Riviere des Galets waere finalised and contract for Coastal Adaptation Works at Riviere des Galets has already been awarded and expected to be completed by mid 2018. Following a robust and transparent procurement exercise for all the components earmarked under the project document, it is expected that an estimated saving to the tune of USD 1.5 Million may be realised while meeting all the output targets set. Estimated Savings of up USD 1.5 Million Estimated Costs Actual Costs Actual Savings Riviere des Galets USD 2,000,000 USD 765,000 USD 1,235,000 Early Warning System USD 310,365 USD 265,365 USD 45,000 Training USD 394,025 USD 294,025 USD 100,000 Knowledge Dissemination USD 320,000 USD 200,000 USD 120,000 Total USD 1,500,000 Proposals (i) Extension of Early Warning System to include the wave component (ii) Phase II of Refuge Centre (iii) AF Project Extension by 1 Year (iv) Re-allocation of budget for Execution costs | [5 empty] | S
S
S
S
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Detailed technical assessment of each site |  | Consultancy services for the preparation of feasability studies, Environmental Impact Assessment reports, Design, preparation of bid documents and supervision of works for the implementation of coastal adaptation measures at Mon Choisy and Riviere de Galets. Consultancy services for design, preparation of tender document and supervision of works for the construction of Refuge Centre, Drainage System and Ancillary works at Quatre Soeurs. |  | Quatre Soeurs • Technical assessment of the site, conceptual/architectural design, EIA, preparation of bid document, bid and bid evaluation are completed and contract for works awarded • Actual construction works started since August 2016 and reached 70% completion Riviere des Galets • Technical assessment of the site, Feasibility study, Cost benefit analysis, design and bid document have been completed. • Contract for works awarded • Contract for Consultancy Services for Supervision of Works awarded • Actual construction works started since June 2017 and reached 5% completion Mon Choisy • Technical assessment of the site, Feasibility study, Cost benefit analysis, design and bid document have been completed. • The bid document for works (Part 1-Structural measures) will be launched in August 2017 • Expected award of contract November 2017 • Start of Works at Mon Choisy-January 2018 Mangroves Plantation • 22000 Mangroves planted and good performance in terms of gender balance. | S
Technical design of coastal protection measures at each of three sites
| Successful construction of physical interventions at each of the three sites |  | Construction of Refuge Centre at Quatre Soeurs:
| Analysis of data and development of recommendations on how the interventions can be adjusted for other vulnerable coastal locations in ROM |  | Analysis of data and development of recommendations on how the interventions can be adjusted for other vulnerable coastal locations in ROM |  | The contract for consultancy services for Mon Choisy & Riviere des Galets included development of baseline for future work at the 2 sites. This is in line with plans to inform 21 more vulnerable sites with methodologies for analysis, modeling, and concrete recommendations for a coastal zone monitoring system. Government of Mauritius have discussed and agreed that the proposed constructions at the two sites are initial steps. The result of the adaptation works at those two sites will be monitored and the results used to implement solutions at other sites. | S
| Monitoring programme designed, to include scoping of suitable parameters, including beach width and slope; depth of adjacent lagoonal sediments; wave height, period, and run-up; direction of nearshore current |  | Monitoring programme designed, to include scoping of suitable parameters, including beach width and slope; depth of adjacent lagoonal sediments; wave height, period, and run-up; direction of nearshore current
| A targeted coastal process/weather event monitoring system in place |  | A targeted coastal process/weather event monitoring system in place
| Assessment of the current sea state monitoring systems (Mauritius Meteorological Services and Mauritius Oceanography Institute) and definition of required critical parameters and operational requirements for an early warning system. |  | Assessment of the current sea state monitoring systems and an Early Warning system-Completed |  | The numerical model and the setting up of a fully automated Early Warning System for Storm and tidal Surge at the Mauritius Meteorological Services was completed and is operational as from September 2015. This project also warranted detail bathymetry data off the coast Mauritius, Rodrigues and Agalega to be retreived from Indian Authorities. | S
| The early warning system installed and implemented |  | The early warning system installed and implemented-Completed |  | A first version of the Early Warning System installed at the Mauritius Meteorological Services on the two high performance computers procured under the project. The hands on training was also delivered to officials from Mauritius Meteorological Services, Mauritius Oceanography Institute and NDRRMC. A Memorandum of Understanding (MoU ) with Stitchting Deltares and UNESCO -IHE was signed to ensuring the sustainability of the project in relation to capacity building, technical support and technology transfer for a more effective use of the numerical model of the Early Warning System. The Ministry of Environment also agreed to monitor the implementation of the MoU. | S
| Handbook on Coastal Adaptation” packaged as training modules for coastal communities, relevant Government agencies, and private sector stakeholders |  | Available-Completed |  | 4 Handbooks have already developed under the Adaptation Fund Project • 1 Handbook entitled ‘Training Manual for Coastal Protection Works’ • 1 Handbook entitled ‘Training Manual on Coastal and Marine Environment for Engineers’ produced under the programme'. • 1 Handbook on Cost Benefit Analysis for Coastal Management and Adaptation Options to Climate Change. • 1 Handbook on INTEGRATED COASTAL ZONE MANAGEMENT FOR SMALL ISLAND DEVELOPING STATES | S
| Short course on Coastal Engineering designed and delivered |  | COMPLETED 9 Short Courses completed (in total) in collaboration with the University of Mauritius. |  | 1. Short Course on Coastal and Marine Environment for Engineers 2. Short Course on Coastal Engineering 3. Short Course on Coastal Adaptation Structures (soft measures) including a case study of Mon Choisy 4. Short Course on Coastal and Marine Environment for Engineers (CMEE) (Rodrigues) 5. Short Course on Ocean Data Collection and Analysis 6. Short Course on Climate Change and Coastal Zone Management 7. Short Course on Open Geospatial tools 8. Short Course on Disaster Risk Reduction 9. Short Course on ICZM
| Specialized course on Cost-Benefit Analysis of coastal adaptation measures designed and delivered |  | COMPLETED 4 Short Courses (CBA) have already delivered before this reporting period. Preparation for another CBA course completed. |  | 1. Short Course on Cost and Benefit Analysis of Coastal Adaptation Measures 2. Short Course on Cost Benefit Analysis/Climate Change Economics 3. Short Course on Cost and Benefit Analysis of Coastal Management and Adaptation Options to Climate Change (Rodrigues) 4. Short Course on Cost and Benefit Analysis Applied to Climate Change Initiatives
| A National Coastal Zone Adaptation that addresses all perceived climate change risks in the coastal zone of ROM over at least the next 20 years, with recommendations for supporting policies and regulations |  | Expected in 2016 /17 • Review of documents pertaining to coastal zone management • Final National Coastal Zone Adaptation Strategy • Creation of ‘clearing house’ for climate change • Recommendation for new economic instruments to fund climate change related projects |  | The procurement of consultancy services was completed and the Development of a National Coastal Zone Adaptation Strategy under way. The following deliverables have been completed to date: • Final Inception Report with Detailed Work Plan-Completed • Final Report on review relevant strategies, policies, laws, regulations and projects pertaining to the coastal zone in Republic of Mauritius-Completed • Final Report on Options for Adaptation Policies & measures, and Vulnerability Assessment result and map that identifies the most vulnerable coastal areas and systems with development capacity limit-Completed • Consultative Workshop in Mauritius and Rodrigues-Completed | S
A set of recommendations on best technical and institutional adaptation practices suitable for the coastal zone of ROM.
Definition of the required structure and processes for one “clearinghouse” or climate change oversight in the coastal zone of ROM
Recommendations for new economic instruments
| Handbook, training modules, and website content capturing best coastal adaptation practices for the Mauritius context |  | COMPLETED |  | • Handbook on integrated Coastal Zone Management for the coastal zone Mauritius-Completed | S
| Dissemination of lessons learned from the programme with coastal stakeholders in other locations in the southern Indian Ocean |  | COMPLETED |  | The project team participated in two regional conferences in collaboration with the Indian Ocean Rim Association (IORA), Global Water Partnership (GWP), and University of Mauritius in October 2015 and June 2016 where 200 participants from the region (SADC countries) were present. The salient issues, lessons learned and best practices were showcased.
| Interpretive signs and smallscale models of coastal processes designed and installed at each site, explaining the science of climate change and coastal processes |  | COMPLETED |  | 7 Small Scale Models developed & 2 Display Board Installed 15,000 People sensitised through marine mobile education unit
| Public awareness campaigns on climate change in the coastal zone designed and delivered |  | 3000 students (primary and secondary schools) and coastal communities sensitised |  | 1 Marine Mobile Education Unit developed jointly with private sector/NGO • 32 sensitization/public awareness campaigns conducted using the Marine Mobile Educational in schools, community centers, social welfare centers and shopping malls completed during the reporting period
| Priority ranking of vulnerable coastal sites established, to guide the order of future investment by the Government of Mauritius and the private sector |  | Currently being undertaken |  | Currently being undertaken
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | S. Ramchurn, Environment Programme Analyst
| Email: | satyajeet.ramchurn@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words | The overall rating is moderate satisfactory because the project actions/activities planned for current reporting period are progressing, but main part has been delayed. There are several positive trend in achievement of outcomes as per the project indicators. Outcome 1 has been the main strategic focus during the reporting period. Indufor in a consortium with eCoast and CLAMS Ltd were engaged to undertake a number of studies in relation to works to be undertaken at Mon Choisy and Riviere des Galets. They conducted community survey at the site as well. The Project Management Unit within the Ministry of Environment, Sustainable Development, and Disaster and Beach Management (Ministry) expressed concerns regarding to the adaptation options and could not come to the conclusion of the Final Design for a couple of months. However, after the Design Review conducted by UNDP consultant, Steering Committe was able to agree on the way forward. Considering the proposed adaptation measures will have long term impacts and has the largest project investment (USD 6,680,440), it was deemed that it was important to take the necessary time to achieve the required designs. Key decisions have now been made and it is expected that the project will achieve a satisfactory rating in the next reporting period. Quite good progress has been achieved with regard to the Quatre Soeurs site. The process of land availability and acquisition for the construction of the Refuge Centre at Quatre Soeurs was one of the main risks at the beginning. However, the land acquisition process was successfully completed in June 2015 by the Ministry of Housing and Lands and the necessary procedures to be able to start the construction of the Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs were finished during this reporting period. The representatives from the community joined the day of the handing over the project site and have been keeping good communication. The construction works started in August 2016. The mangroves project completed successfully. It was an effective community-based adaptation strategy and the mangroves project was replicated in other areas in the Republic of Mauritius in partnership with the private sector and the local community. Outcome 2 has already completed and the EWS is operational at the Mauritius Meteorological Services since 2015. In addition, the Memorandum of Understanding (MoU) is made between Government of Mauritius and Stitchting Deltares and UNESCO -IHE. This will help in the implementation of the EWS and further regional cooperation. Data sharing has been key issue in Mauritius. As suggested by MTR, development of regional partnership agreement on data-sharing during next reporting period will help future effectiveness of this system. Component 3 is in good progress and expected targets are achieved. Capacity development training activities have been organized including site visits to the actual project implementing sites. Events are organized with involvement of the community that have direct impact from the project works and helped their capacity development. Appropriate impact assessment of the training activities will be needed in the next reporting period. Outcome 4 has been delayed since the RFP for Policy Mainstreaming did not receive any proposals. The present policy review and learning activities were conducted during the review of TOR. Then, the third round of invitations to bid launched in August 2016. As suggested by MTR, baseline studies as well as strong support and understanding from line ministries are needed in implementing stage. The implementation of components 5 is in good progress with no major bottlenecks. A memorandum of understanding has been signed with the University of Mauritius (UoM) has produced good results. Several training courses and sensitization activities on climate change and coastal adaptation have been strengthening of climate change adaptation capacity of the future generation.
2. Detail critical risks that have affected progress.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1 | Physical infrastructure improved to withstand climate change and variability-induced stress | The beach at Mon Choisy is eroding at a rate of about 2 metres/year; Riviere des Galets is exposed to storm surges, with a failing seawall, openings in the wave overtopping wall, and an inadequate drainage system in the village; buildings in Quatre Soeurs frequently flood during high tides | 1/3 Mangroves Project completed and replicated to other coastal sites in RoM (see details at output level) Studies completed-(see details at output level) Bid document for Mon Choisy & Riviere des Galets Completed • Contract for Construction works for Quatre Soeurs awarded and construction works Ongoing (see details at output level)-80% Completed • Contract for Construction works for Riviere des Galets awarded and construction works Ongoing (see details at output level)-10% Completed | No further erosion at Mon Choisy (beach accretion of 2 metres over 3 years); no surge flooding and no further shore erosion at Riviere des Galets; and, no flooding of coastal public buildings at Quatre Soeurs. The target for numbers of beneficiaries (as per prodoc) are as follows: Mon Choisy: 1,500-2000 people; Riviere des Galets: 100-150 people; Quatre Soeurs: 1000 people.
Output 1 | Number of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) | No physical asset in place at site 1 (Mon choisy) to withstand conditions resulting from climate change | 1/3 1. Contract awarded to Indufor Oy in September 2014 for Consultancy Services in respect of Coastal Adaptation Measures at Mon Choisy & Riviere des Galets •Technical assessment of site: completed • Feasibility study : completed • Options for Coastal Adaptation including Cost/benefit analysis: completed • Design of adaptation measures: Completed • EIA Study: Completed • Independent Technical Review of Design for Mon Choisy : Completed • Bid document for Mon Choisy-Completed | Physical works properly designed and constructed at Mon choisy 1.1 Clear chronology of coastal process “events” at each site over the last 25 years and oceanographic dataset (2 months of data) for each of the three sites. COMPLETED 1.2 Detailed technical specifications and costs for coastal protection measures at each of the three sites, carried out in a gender sensitive way. COMPLETED 1.3 Physical works properly designed and constructed at each of the three sites, including: detached offshore submerged wave attenuation structures (sloped rock mounds); planting of mangroves; and,planting of beach crest vegetation at Mon Choisy; detached offshore submerged wave attenuation structures (sloped rock mounds); planting of beach crest vegetation; and, development of a drainage scheme for the backshore at Riviere des Galets; planting of mangroves; WORKS ONGOING 1.4 Comprehensive data on the effectiveness of the structures at each of the three sites: ONGOING 1.4 Recommendations for structural adjustments (location, design, materials, etc.) for interventions at other coastal sites in ROM: ONGOING 1.5 Monitoring design report: ONGOING 1.6 A functional monitoring system in place: ONGOING
|  | No physical asset in place at site 2 (Quatre Soeurs) to withstand conditions resulting from climate change 80% Completed | 1/3 1. The Contract for Consultancy Services for Design, Preparation of bid document and Supervision of Works for the Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs was awarded to the Consortium Mega Design in association with Design Forum, STEGET, SEE Engineering Consultants Co Ltd and Chuttur & Partners Ltd on 06 June 2015-COMPLETED 2. Acquisition of freehold land on higher grounds of an extent of 3A04P (1ha2,850 m2) for construction of a Refuge Centre at Quatre Soeurs was completed on 08 June 2015-COMPLETED 3. Construction Works-ONGOING 4. Expected Completion-December 2017 5. Mangrove plantation component (100% completion) with 20,000 mangroves planted and replication of the mangroves project at (6) other sites in the Republic of Mauritius-COMPLETED | Physical works properly designed and constructed at Quatre Soeurs 1.1 Clear chronology of coastal process “events” at each site over the last 25 years and oceanographic dataset (2 months of data) for each of the three sites. NOT RELEVANT (Construction of a Refuge Centre) 1.2 Detailed technical specifications and costs for coastal protection measures at each of the three sites, carried out in a gender sensitive way. COMPLETED 1.3 Physical works properly designed and constructed at each of the three sites, including: detached offshore submerged wave attenuation structures (sloped rock mounds); planting of mangroves; and,planting of beach crest vegetation at Mon Choisy; detached offshore submerged wave attenuation structures (sloped rock mounds); planting of beach crest vegetation; repair and re-sloping of the seawall; sealing the wave- overtopping wall; and, development of a drainage scheme for the backshore at Riviere des Galets; planting of mangroves; re-constructing public buildings at risk on stilts at Quatre Soeurs. WORKS ONGOING FOR CONSTRUCTION OF A REFUGE CENTRE AT QUATRE SOEURS 1.4 Comprehensive data on the effectiveness of the structures at each of the three sites. ONGOING 1.4 Recommendations for structural adjustments (location, design, materials, etc.) for interventions at other coastal sites in ROM. ONGOING 1.5 Monitoring design report: ONGOING 1.6 A functional monitoring system in place. ONGOING
|  | No physical asset in place at site 3 (Riviere des Galets) to withstand conditions resulting from climate change 10% Completion | 1/3 1. Contract awarded to Indufor Oy for Consultancy Services in respect of Coastal Adaptation Measures at Mon Choisy & Riviere des Galets •Technical assessment of site: Completed • Feasibility study : Completed • Options for Coastal Adaptation including Cost/benefit analysis: Completed • Design of adaptation measures: Completed • EIA Study: Completed • Independent Technical Review of Design for Riviere des Galets: Completed • Bid Document-Completed • Contract for Contruction Works-Awarded • Construction Works- Started | Physical works properly designed and constructed at Riviere des Galets 1.1 Clear chronology of coastal process “events” at each site over the last 25 years and oceanographic dataset (2 months of data) for each of the three sites. COMPLETED 1.2 Detailed technical specifications and costs for coastal protection measures at each of the three sites, carried out in a gender sensitive way. COMPLETED 1.3 Physical works properly designed and constructed at each of the three sites, including: detached offshore submerged wave attenuation structures (sloped rock mounds); planting of mangroves; and,planting of beach crest vegetation at Mon Choisy; detached offshore submerged wave attenuation structures (sloped rock mounds); planting of beach crest vegetation; repair and re-sloping of the seawall; sealing the wave- overtopping wall; and, development of a drainage scheme for the backshore at Riviere des Galets; planting of mangroves; re-constructing public buildings at risk on stilts at Quatre Soeurs. ONGOING-WORKS ONGOING FOR RIVIERE DES GALETS 1.4 Comprehensive data on the effectiveness of the structures at each of the three sites. ONGOING 1.4 Recommendations for structural adjustments (location, design, materials, etc.) for interventions at other coastal sites in ROM. ONGOING 1.5 Monitoring design report: ONGOING 1.6 A functional monitoring system in place. ONGOING
Outcome 2 | Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | MMS provides warnings to shipping based on perceived wave climate, and cyclone warnings for the general populace, but this system does not anticipate rogue swell conditions. | 1/1 Project Completed- see details at output level EWS installed at the MMS | By 2018, more than 3,400 people in current surge zones are able to safely evacuate prior to future storm surge events (there are no people left in the surge zone when the surge hits).
Output 2 | Development of early warning systems | No existing EWS for storm surges | 1/1 • Inception Workshop-COMPLETED • Assessment of existing system at the Mauritius Meteorological Services--COMPLETED • National Workshop (Client and End User’s feedbacks)-COMPLETED • Assessment Report-COMPLETED • Design of an optimal Early Warning System for incoming Storm Surge in the Republic of Mauritius-COMPLETED • Setting up of Storm Surge Model-COMPLETED • Design Report-COMPLETED • Initial set up of the Early Warning System at the Mauritius Meteorological Services-COMPLETED • Procurement of Computer Equipments-COMPLETED • Procurement of Hydrographic data from the Indian Hydrographic Office-COMPLETED • Calibration of the Early Warning System model-COMPLETED • Final System Implementation-COMPLETED • Training (Mauritius & Netherlands) & Evaluation-COMPLETED | 2.1 Assessment of the usefulness and practicality of the satellite data and the MMS system: COMPLETED 2.1 Parameters and analytical procedures for the early waning system defined: COMPLETED 2.2 Early warning system set up and running and effective during future storm events, such that no people in vulnerable coastal areas are exposed to storm surges in the future. PROJECT COMPLETED
Outcome 3 | Number and type of targeted institutions with the capacity to minimise exposure to CC. | Public agencies are unclear on their obligations regarding management of climate change effects in the coastal zone, and the private sector and general populace do not know what options there are for coastal adaptation, nor how to initiate such measures in the most practical, cost-effective manner. | 1/1 Partnership with the University of Mauritius set up. Other Collaborations +G21 Worley Parsons • CEEPA (Centre of Environmental Economics and Policy in Africa) • University of Western Australia • India Institute of Technology, Madras, Chennai • University of Southampton, UK • TACSYM LTD training Specialist Involvement of all relevant national institutions secured. 1. Ministry of Environment, Sustainable Development, and Disaster and Beach Management 2. UNDP 3. Mauritius Oceanography Institute 4. Commission for Environment (Rodrigues Regional Assembly) 5. District Council of Pamplemousses 6. District Council of Riviere du Rempart 7. District Council of Savanne 8. Beach Authority 9. Ministry of Tourism and External Communications 10. Mauritius Meteorological Services 11. Ministry of Ocean Economy, Marine Resources, Fisheries, Shipping and Outer Island (AFRC) 12. Ministry of Housing and Lands 13. Ministry of Local Government 14. Outer Islands Development Corporation 15. Municipality of Vacoas/Phoenix 16. Road Development Authority 17. Ministry of Public Infrastructure and Land Transport (Public Infrastructure Division) 18. District Council of Grand Port 19. District Council of Black River 20. Tourism Authority 21. National Development Unit 22. National Coast Guard 23. Prime Minister’s Office 24. National Disaster Risk Reduction and Management Centre 25. Ministry of Social Integration and Economic Empowerment 26. Scene Ries Consult Ltd 27. Vyyaass Consulting Engineer Ltd 28. Luxconsult (Mtius) Ltd 29. GIBB (Mauritius) Ltd 30. Servansingh Jadav and Partners 31. University of Mauritius 32. Universite des Mascareignes 33. MACOSS (Ngos) 500 Participants trained as at 31 July 2017 | By 2018, at least 300 people, at least half of them women, trained. • 494 People (officials from Ministries/departments, local authorities and the private sector in Mauritius & Rodrigues) were trained as at 31 July 2017 & awarded a certificate of attendance (at least half of them women)
Output 3 | No. of staff trained to respond to, and mitigate impacts of, climate-related events | No coastal engineering capacities available at national level | 1/1 Collaboration with the University of Mauritius secured. 13 Short Courses completed in collaboration with the University of Mauritius. 494 Participants trained as at 31 July 2017. 1. Short Course on Coastal and Marine Environment for Engineers delivered in September 2013- 56 Participants trained 2. Short Course on Coastal Engineering delivered in October 2013- 54 Participants trained in the field of Coastal Engineering 3. Short Course on Cost and Benefit Analysis of Coastal Adaptation Measures delivered in December 2013- 41 Participants trained 4. Short Course on Coastal and Marine Environment for Engineers replicated in Rodrigues Islands in July 2014- 28 participants trained in Rodrigues Islands 5. Short Course on Coastal Adaptation Structures (soft measures) including a case study of Mon Choisy delivered in August 2014- 41 Participants trained. 6. Short Course on Cost Benefit Analysis/Climate Change Economics delivered in September 2014- 38 Participants trained 7. Short Course on Ocean Data Collection and Analysis delivered in January 2015- 29 Participants trained 8. Short Course on Climate Change and Coastal Zone Management delivered in June 2015- 33 participants trained 9. Short Course on Cost and Benefit Analysis of Coastal Management and Adaptation Options to Climate Change delivered in Rodrigues Islands delivered in May 2015- 42 Participants trained in Rodrigues Island 10. Short Course on Open Geospatial tools delivered in September 2015- 25 Participants trained 11. Short Course on Disaster Risk Reduction delivered in January 2016- 36 Participants trained 12. Short Course on Integrated Coastal Zone Management delivered in January-February 2016- 35 Participants trained 13. Short Course on Cost Benefit Analysis Applied to Climate Change Initiatives-36 Participants trained | Coastal engineering short course designed and delivered (2x); at least 40 trainees certified. COMPLETED 3.1 Handbook complete, fully relevant to Mauritius coastal context, and used for coastal stakeholder and practitioner training twice per year over three years (at least 300 people, at least half of them women, formally trained). COMPLETED 4 Handbooks COMPLETED 3.2 Coastal engineering short course designed and delivered (2x); at least 40 trainees certified. 337 Engineers and technical staff (both from public and private sector) in Mauritius & Rodrigues trained 3.3 C-B Analysis course designed and delivered (4 x); at least 100 trainees certified.COMPLETED 157 Government officials (Mauritius & Rodrigues) trained. 1 CBA Handbook COMPLETED
Outcome 4 | Climate change priorities are integrated into national development strategy | Current policies and regulations are inconsistent with regard to management of climate change effects in the coastal zone (they do not envision the coastal zone in 2060), and do not provide clear guidance or incentives for practical implementation of adaptive measures. | 1/4 • Contract for Consultancy Services-Awarded • Inception Workshop-Completed • Consultation Workshops in Mauritius & Rodrigues-Completed • Final Report on Reiew of Strategies, Policies-Completed •Final Report on Options for Adaptation Policies-Completed • Draft National Coastal Zone Adaptation Strategy-Received • Final National Coastal Zone Adaptation Strategy-Expected early 2018 | All relevant policies, strategies, plans, and regulations are consistent in a) having a clear vision statement for adaptation in the coastal zone; b) in recognizing climate change impacts in the coastal zone over the next 50 years; and c) in clear Government institutional responsibilities for adaptation in the coastal zone. ONGOING
Output 4 | Number, type and sector of policies introduced or adjusted to address Climate Change Risks. | National ICZM strategy does not fully integrate climate change and is not properly enforced |  | National Coastal Zone Adaptation Strategy in place which addresses all perceived climate change risks in the coastal zone over the next 20 years, with clear recommendations for appropriate policies, regulations, and guidelines for adaptation. ONGOING 4.1 National Coastal Zone Adaptation Strategy in place which addresses all perceived climate change risks in the coastal zone over the next 20 years, with clear recommendations for appropriate policies, regulations, and guidelines for adaptation. ONGOING 4.1 District Outline Schemes (all 9) and the National Tourism Development Plan recognize spatial limitations and capacity limits related to climate change risks, and provide guidance on appropriate locations and designs for infrastructure. ONGOING 4.2 A “toolbox” with the most appropriate technical, institutional regulatory, and economic instruments available for all coastal practitioners in ROM; recommendations feeding into the policy and regulatory review. ONGOING 4.3 Clear recommendations on the structure and processes of an oversight and regulatory body that addresses all climate change issues in the coastal zone with jurisdictional clarity. ONGOING 4.3 Eventual establishment of that body (whether through the ICZM Division in the Ministry or the Climate Change Division). ONGOING 4.4 Clear analysis and recommendations for design and implementation of economic instruments that will facilitate public and private sector compliance with the best coastal adaptation practices. ONGOING
Outcome 5 | Effective capturing and dissemination of lessons from the applied activities in the programme. | There is no consistent awareness nor understanding of the implications of climate change in the coastal zone; households, communities, and Government organizations do not factor into their plans and activities the possible climate change effects 50 years from now. | 2/5 ONGOING | By 2018, effective capturing and dissemination of lessons from the applied activities in the programme. 5.1. Handbook, training modules, and website content produced. COMPLETED 5.2 Mauritian coastal practitioners able to disseminate lessons from the programme to other countries in the southern Indian Ocean and to examine the experiences in those countries. ONGOING 5.3 Interpretive models and signs. These sites marketed and visitor attendance recorded. COMPLETED (7 Small Scale Models developed & 2 Display Board Installed) 5.4 Relevant public awareness campaigns designed and delivered to all coastal villages in the 23% of beaches at risk in Island of Mauritius. ONGOING-15000 People (coastal communities sensitised) 5.5 All vulnerable coastal sites in ROM mapped, scaled, and assessed for importance and degree of risk to climate change in the future. ONGOING 5.5 Replication of coastal adaptation measures initiated, with Government of Mauritius and private sector funding (at least three sites initiated before the end of the project using other sources of funding). ONGOING
Output 5 | Dissemination of lessons learned from the programme with coastal stakeholders in other locations in the southern Indian Ocean. | Mauritian coastal practitioners able to disseminate lessons from the programme to other countries in the southern Indian Ocean and to examine the experiences in those countries | 2/5 ONGOING | Handbook, training modules capturing best coastal adaptation practices in the mauritian context and dissemination of lessons learned in other locations of the Southern Indian Ocean 5.1. Handbook, training modules, and website content produced. COMPLETED 5.2 Mauritian coastal practitioners able to disseminate lessons from the programme to other countries in the southern Indian Ocean and to examine the experiences in those countries. ONGOING 5.3 Interpretive models and signs. These sites marketed and visitor attendance recorded. COMPLETED (7 Small Scale Models developed & 2 Display Board Installed) 5.4 Relevant public awareness campaigns designed and delivered to all coastal villages in the 23% of beaches at risk in Island of Mauritius. ONGOING-15000 People (coastal communities sensitised) 5.5 All vulnerable coastal sites in ROM mapped, scaled, and assessed for importance and degree of risk to climate change in the future. ONGOING 5.5 Replication of coastal adaptation measures initiated, with Government of Mauritius and private sector funding (at least three sites initiated before the end of the project using other sources of funding). ONGOING

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1. The procurement of services and works have to follow lengthy procedures which impact in the project execution. 2. Most of the procurements had to undergo at least 2 rounds of procurement due to budget or scarcity areas & availability of international consultants 3. The land acquisition process for Quatre Soeurs by the Government was a lenghty process (more than 1 yr) 4. The procurement of hydrographic data which was available at the Indian Hydrographic Unit was a lenghthy process (6 months). The Early Warning System for Storm Surge could not be finalised until availability of data. 5. The design for Mon Choisy & Riviere des Galets had to undergo 2 design reviews before finalisation of the most appropriate adaptation measures, thus requiring revision of the initial EIA/SIA Report 6. The involvement and sensitisation of the community is an important factor for a successful implementation of adaptation project at the target site.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | YES. There were delays in implementation as explained above. Measures taken to reduce delays. 1. To reduce procurement timeframe for second round of procurement, the Government sollicited the support of the UNDP. 2. It was noted that for procurements above USD 1,000,000 the UNDP procurement procedures were also lengthy as necessary clearances from the Regional Bureau for Africa were required at various steps. 3. The project team was able to secure a close liaison between the Ministry and UNDP,and between UNDP CO and UNDP RBA. The procurement was successfully completed in 6 month's time.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | 1. The site for Construction of a Refuge centre at Quatre Soeurs was reviewed at the Inception Phase to a more secured and accessible location to be resilient to storm surges and flooding. A suitable site of an extent of 12,850 M2 to the tune of USD 320,645 was identified at Quatre Soeurs and procured by the Government of Mauritius. This represent an in-kind contribution from the Government of Mauritius to the AF Project. 2. A budget reallocation between project components was warranted and approved by the AFB in May 2014
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | 1. The compliance of the project with Equal Opportunity Act is mandatory as per Government legal framework. Focus on Gender has been fully integrated into project activities through involvement of women CSOs and NGOs in activities. Women's association have been actively involved in implementation of coastal adaptation projects, such as: mangrove plantation and sensitisation campaigns conducted by the women associations to coastal stakeholders on importance of mangroves on the coastal eco-system. The participation of women in all consultative meetings and coastal adaptation project was assessed positively at the Mid-Term Review. 2. Out of the 494 People trained under Outcome 3 (40% were Female & 60% Male) 3. Out of the 15000 People sensitised under Outcome 5 (45% were Female & 55% Male)
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The budget allocation of the project at the project development phase for implementation of climate resilient measures need to allow for cost escallation to foresee the actual cost at the implementation phase as a buffer to allow the timelag between the project conception until the execution of the project. To ensure that the impacts of the climate change measures reach to the coastal communities, a community based approach was adopted for implementation of the mangroves project. This has involved the direct participation of the coastal communities and enhanced their livelihoods.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The Adaptation Fund Project has allowed appropriate and indepth studies at the AF Project sites to develop appropriate adaptation measures. Other sites in the Coastal Zone of Republic of Mauritius face the same challenges of beach erosion. The recommended adaptation measures have a great potential to be replicated/adapted to increase climate resilience. The ecosystem adaptation project on 'mangroves plantation' gained international recognition and has aleady been replicated at six other sites in the Republic of Mauritius. The project for implementation of coastal adaptation works at Mon Choisy will consist of an innovative measure (installation of pre-cast reef units in the lagoon). This innovative measure has the potential for future replication at other project sites in Mauritius.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | This project has allowed the introduction of a CBA to enable the appropriate choice of adaptation measures based on lifetime costing. This is a new approach that was introduced to select the most appropriate option for climate resilience projects. For the design of coastal protection works, the selected contractor was a loose consortium whereby the engineer wasn’t from the lead firm. In future, such arrangements will not be accepted where engineering works are concerned.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The mangroves project has been replicated to other vulnerable coastal areas in the Republic of Mauritius. Short Training courses have been replicated to Rodrigues island The Training on the Early Warning System for Storm Surge for the Meteorological Services staff in Rodrigues island and replication of the EWS in Rodrigues is under way.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Mangroves project The involvement of the community in project implementation through community based approach has enhanced a sense of project ownership Sensitisation Campaigns Sensitisation campaigns that have been carried out through innovative means of a mobile education unit has allowed a larger community outreach for the communities Early Warning System Implementation of EWS has allowed coastal communities to be informed on an enhanced forecasting system in the event of storm surges. Following successful implementation , extension of the EWS is envisaged.
What measures are/have been put in place to ensure sustainability of the project/program results? | A Memorandum of Understanding has been signed with the NGO's on community based projects to allow programmes to be continued in future based on the current lessons learnt. The handing over of project to Government authorities for running and maintenance in the long term to ensure project sustainability. The operation and staffing of the Refuge Centre in view of sustainability of the project will be catered under the Government Budget.
What measures are being/could have been put in place to improve project/program results? | Project results on increasing resilience of the coastal communities at Quatre Soeurs increased through the land acquisition on higher grounds as opposed to the initial site which was on lower ground. On this particular output, besides the setting up of the Refuge Centre, alternative routes are also being identified and secured to allow mass evacuation in event of storm surge and calamities The installation of an artificial reef made up of pre-cast reef units will be implemented first time in Mauritius and constitute a technology transfer. This may be as well be used as a showcase.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Project conceived based on assessment of all existing data available from previous works conducted which subsequently feeds in the design of the adaptation measures. In the context of implementation of Early Warning System the availability of bathymetry charts were critical for validation of the model. The data was not in possession at national level and had to be procured at international level. Intervention at highest level was also required to access data retained by the Indian Authorities following survey conducted by the indian navy in the region of Mauritius.
If learning objectives have been established, have they been met? Please describe. | 4 Training courses on Cost Benefit Analysis (CBA) were delivered. The objective is to inculcate the option of having a CBA besides an Environmental Impact Assessment which is legally a mandatory requirement. Mauritius has got no local expertise in coastal engineering and this project delivered Training Courses on Coastal Engineering and this had been a unique opportunity to bring international expertise at local level. A MOU was signed with the University of Mauritius so that award courses on Coastal Engineering may be developed under the support of this project and build capacity at the University of Mauritius level for sustaining the training programme in the longer term. Two post graduate courses on (a) climate change adaptation and disaster risk management and (b) coastal engineering has been mounted with the support of this programme at the University of Mauritius to ensure sustainability of the training programme.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | We need to have appropriate intervention at Government level to access data either through a Memorandum of Understanding. Data is also retained by various authorities (local) in their own format. It is suggested to harmonise all coastal data and data be readily available for future design of coastal adaptation measures.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Climate change impacts thereof were not a common knowledge at the level of the coastal communities. The development of learning materials and tools including the mobile education unit was proven to disseminate the climate change issues and raise awareness among the community and therefore be better prepared to face and adapt at local level The training was extended to practically all institutions concerned with the coastal projects to achieve the objective under outcome 3, e.g. coastal planners from local authorities were involved which build capacity in delivery with a climate change induced risk perspective

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 00062857
Implementing Entity | United Nations Development Programme (UNDP)
Type of implementing entity | MIE
Country | Mauritius
Region | Africa
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 752546 | 6350 | 746196 | Total | 740000 | 75400 | 664000 | Total | 22985 | 5485 | 17500 | Total
|  | % of female beneficiaries | 50% | 30% | 50% | % of female beneficiaries | 50% | 30% | 50% | % of female beneficiaries | 50% | 30% | 50% | % of female beneficiaries
|  | % of Youth beneficiaries | 20% | 20% | 20% | % of Youth beneficiaries | 20% | 20% | 20% | % of Youth beneficiaries | 20% | 20% | 20% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 3400 | Storm surge | 2: Partially effective | Total | 54000 | Storm surge | 4: Effective | Total | 3400 | Storm surge | 3: Moderately effective | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 2 | Coastal management | National | 2: Undertaking or updating of assessments in progress | 2 | Coastal management | National | 3: Risk and vulnterability assessments completed or updated | 2 | Coastal management | National | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 2: Monitoring and warning service | Geographical coverage | National | 3 | 2: Monitoring and warning service | Geographical coverage | National | 1 | 2: Monitoring and warning service | Geographical coverage | National |  |  | Geographical coverage
|  |  |  | Number of municipalities | 7 |  |  | Number of municipalities | 7 |  |  | Number of municipalities | 2 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 300 | Coastal management | 2: Low capacity | Total | 485 | Coastal management | 4: High capacity | Total | 258 | Coastal management | 3: Medium capacity | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 300 | 50% | Public |  | 485 | 50% | Public |  | 258 | 50% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Coastal management | 2: Low capacity | Public | National | Coastal management | 4: High capacity | Public | National | Coastal management | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 20% |  | Coastal management |  | 30% |  | Coastal management |  | 15 |  | Coastal management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 5000 | 50% | 3: Partially aware |  | 50000 | 50% | 4: Mostly aware |  | 4000 | 60% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Coastal management | National | 3: Moderately responsive (Some defined elements) |  | Coastal management | National | 4: Mostly responsive (Most defined elements) |  | Coastal management | National | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 2 | Coastal protection measures |  | Coastal management | 3 | coastal protection measures |  | Coastal management | 1 | coastal protection measures |  | Coastal management
|  | 1 | Construction of refuge centre for communities at risk |  | Disaster risk reduction | 1 | Construction of refuge centre for communities at risk |  | Disaster risk reduction | 1 | Construction of refuge centre for communities at risk |  | Disaster risk reduction
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Coastal management | biological assets | 4: Effective |  | Coastal management | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/ rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 1 | ha protected | 2: Partially effective | Mangroves | 2 | ha protected | 4: Effective | Mangroves | 1 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Coasts | 2 | km protected | 3: Moderately effective | Coasts | 2 | km protected | 4: Effective | Coasts | 1 | km protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 60 | 50% | 2: Limited improvement |  | 115 | 50% | 4: High improvement |  | 115 | 50% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 60 | 10% | From 5% to 10% | Agricultural-related | 60 | 10% | From 5% to 10% | Fishing | 60 | 10% | From 5% to 10% | Fishing
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
[6 empty] | 55 | 100% | From 30% to 40% | Agribusiness | 55 | 100% | From 30% to 40% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 1 | Natural capital | Coastal management | Community-based adaptation | 3 | Natural capital | Coastal management | Community-based adaptation | 0 | Natural capital | Coastal management | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 60 | Fishing |  | 200 | 60 | Fishing |  | 200 | 55 | Handicrafts |  | 100
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
[6 empty] | 55 | Agribusiness |  | 300 | 55 | Agribusiness |  | 300
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 2 | Coastal management | National | Environmental policy | 2 | Coastal management | National | Environmental policy | 0 | Coastal management | National | Environmental policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 3 | 1: Not enforced (No elements implemented) |  | 2: Partially effective | 3 | 4: Enforced (Most elements implemented) |  | 4: Effective | 0 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.