## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 01 August 2017-31 July 2018
| Project Title: | Climate Change Adaptation Programme in the Coastal Zone of Mauritius
| Project Summary: | The objective of the project is “to increase climate resilience of communities and livelihoods in coastal areas of Mauritius”. The project comprises of five key outcomes as follows: 1. Increased adaptive capacity within relevant development and natural resources sectors. It comprises of the application of adaptation measures to protect currently vulnerable coastal ecosystem and community at three priority sites: Mon Choisy, Quatre Soeurs and Rivière des Galets. 2. Reduced exposure at national level to climate-related hazards and threats. This component will focus on development of an Early Warning System for incoming Storm Surge manned on 24/7 basis such that the coastal communities in the Republic of Mauritius are able to safely evacuate prior to future storm surge events. 3. Strengthened institutional capacity to reduce risks associated with climate-induced socio-economic losses. This component is targeted to build capacity for ongoing replication of effective coastal adaptive measures by both the Government and private sector. Capacity development will cover a range of Ministries, NGOs, the private sector and the community at large. Short courses on Coastal Engineering, Cost Benefit Analysis of Coastal Adaptation Measures will be developed and delivered in the Republic of Mauritius. A Handbook on coastal adaptation for coastal communities will packaged as training modules for the coastal communities. 4. Improved Policies and Regulations that promote and enforce resilience measures A National Coastal Zone Adaptation Strategy (NCZAS) for the Republic of Mauritius that addresses all perceived climate change risks in the coastal zone of Mauritius and Rodrigues to promote and enhance resilience measures over the next 20 years, with recommendations for supporting policies and regulations, best technical and institutional adaptation practices and new economic instruments. The NCZAS will be developed following (i) Review of relevant strategies, policies, laws, regulations and projects pertaining to the coastal zone in the ROM (ii) Vulnerability assessment, identification of gaps, and development of a map that identifies the most vulnerable coastal areas and systems with development capacity limit and formulate options for adaptation policies. 5. Effective capturing and dissemination of lessons from the applied activities in the programme. Public awareness campaigns on climate change in the coastal zone of Mauritius will be developed and broadcasted in the media. The project will also have a regional dimension whereby the lessons learned from this Adaptation Project will be disseminated to other countries in the Southern Indian Ocean.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme (UNDP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Mauritius | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Port Louis | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2011-09-15
IE-AFB Agreement Signature Date: |  | 2012-07-19 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-08-30 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2014-10-27
| Terminal Evaluation Date: | 2019-05-31
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | List documents/ reports/ brochures / articles that have been prepared about the project. Project Reports to Donor: • Inception Workshop Report (04 October 2012) • Quarterly Reports submitted to the UNDP CO (Progress Reports/FACE Forms/Quarterly Work Plans) • Mid Term Evaluation Report (26 January 2015) • AF Project Audit Report for the period 01 January 2012 to 31 December 2014 • AF Project Audit Report for the period 01 January 2015 to 31 December 2015 • AF Project Audit Report for the period 01 January 2016 to 31 December 2016 • AF Project Audit Report for the period 01 January 2017 to 31 December 2017 • Project Performance Report (30 August 2012-30 August 2013) • Project Performance Report (30 August 2013-30 August 2014) • Project Performance Report (15 August 2014-15 September 2015) • Project Performance Report (16 September 2015-31 July 2016) • Project Performance Report (01 August 2016 to 31 July 2017 ) • Request for Project Extension by (1 Year) until August 2019 and detailed work plan 2018/19 • Project Performance Report (01 August 2017 to 31 July 2018 ) | Czech Republic
Reports/documents produced by Project Outcomes Outcome 1 : Construction of Refuge Centre at Quatre Soeurs Procurement Stage (EOI) • Expressions of Interest (EOI) document for Consultancy Services for Design, Preparation of Bid Document and Supervision of Works for Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs • Bid Evaluation Report for Expressions of Interest for Consultancy Services for Design, Preparation of Bid Document and Supervision of Works for the Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs • Request for Proposal document for Consultancy Services for Design, Preparation of Bid Document and Supervision of Works for Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs • Bid Evaluation Report (Technical) for Request for Proposal for Consultancy Services for Design, Preparation of Bid Document and Supervision of Works for Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs • Bid Evaluation Report (Financial) for Request for Proposal for Consultancy Services for Design, Preparation of Bid Document and Supervision of Works for Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs Consultancy Services for the Design, Preparation of Bid Document and Supervision of Works for the Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs Reports/contracts signed • Signed Contract Agreement between the Ministry of Environment, Sustainable Development, Disaster and Beach Management and the Consortium Mega Design in association with Design Forum, STEGET, SEE Engineering Consultants Co Ltd and Chuttur & Partners Ltd for Consultancy Services for Design, Preparation of bid document and Supervision of Works for the Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs-06 July 2015 • Inception Workshop Report • Detailed Technical Assessment Reports (including survey reports, geotechnical investigation reports & climate change risk assessment) • Architectural design of Refuge Centre and detailed design reports including detailed cost estimates • Evacuation Plan for the vulnerable community exposed to coastal inundation at Quatre Soeurs • EIA Report • Bid Documents Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs (Works) • Signed Contract Agreement between Ministry of Environment, Sustainable Development, and Disaster and Beach Management and Best Construct Ltd- 22 July 2016 • 30 Progress Reports received from contractor as at 30 June 2018
Consultancy Services for Coastal Adaptation works at Mon Choisy and Riviere des Galets Contract Agreement/Workshop Report • Signed Contract Agreement between UNDP and Indufor Oy in Consortium with eCoast and C.L.A.M.S Ltd-09 September 2014 • Inception Workshop Report • National Validation Workshop Report Reports/drawings for Riviere des Galets • Detailed Technical Assessment Report (Riviere des Galets) • Report on Adapting to Sea Level Rise: A Baseline for Protection and Managed Retreat in Riviere des Galets • Adaptation Options Report (Riviere des Galets) • Cost Benefit Analysis for adaptation to Sea Level Rise: Protection or Managed Retreat in Rivière des Galets • Feasibility Study Report (Riviere des Galets) • Design Report (Riviere des Galets) • UNDP Independent Technical Review Report for Coastal Adaptation Measures at Riviere des Galets (by Dr Peter Wulf) • Final Bid Document for Construction of Rock Revetment Structure with Parapet Wall at Riviere des Galets • Bid Drawings • Signed Contract Agreement between Ministry and Super Builders Co Ltd for Construction of Rock Revetment Structure with Parapet Wall at Riviere des Galets-03 May 2017 • Progress Reports (June, Jul, Aug, Sep, Oct, Nov, Dec 2017) • Progress Reports (Jan, Feb, Mar, Apr, May, June, July 2018) Reports/Drawings for Mon Choisy • Detailed Technical Assessment Report (Mon Choisy) • Report on An Economic Valuation and Cost Benefit Analysis of Adaptation and Enhanced Ecosystem Resilience for Mon Choisy Beach • Adaptation Options Report (Mon Choisy) • Cost Benefit Analysis of Adaptation Options (Mon Choisy) • Feasibility Study Report (Mon Choisy ) • Design Report (Mon Choisy) • UNDP Independent Technical Review Report for Coastal Adaptation Measures at Mon Choisy (by Dr Peter Wulf) • Draft Bid Document for Coastal Adaptation Measures at Mon Choisy-Part I: Beach Works (Tree and Stump Removal, Sand Procurement, Delivery and Placement, Mechanical Grading, Beach Fencing), Dune Planting, Rock Groyne Removal and Installation of an Artificial Reef • Final Bid document and Drawings for Rehabilitation of Mon Choisy Public Beach and Installation of an Artificial Reef (Part 1)-Procurement Reference No.: CPB/03/2018 • Part II: First Draft Bid document-Installation of Fixed Mooring Buoys, Establishment of a Voluntary Marine Conservation Area and Seagrass Rehabilitation Pilot • Second Draft Bid document for Coastal Adaptation Measures for Mon Choisy Public Beach, Republic of Mauritius (Part 2 – A) Lot 1 - Fixed Mooring Buoys Programme and Lot 2 - Pilot Project for Seagrass Rehabilitation Environment Impact Assessment (EIA) for Mon Choisy & Riviere des Galets • Signed Contract Agreement with EIA Consultant (local) Scene-Ries Consult Ltd-15 January 2016 EIA Riviere des Galets • Final EIA Report-Coastal Adaptation Works Programme: Proposed Sea Defense Revetment Wall at Riviere des Galets-March 2016 • Design Review Report of Coastal Adaptation Measures at Riviere des Galets (Prof. Sundar, IIT Madras) conducted under EIA exercise • EIA Conditions for Riviere des Galets-August 2016 • EMP Report for Riviere des Galets EIA Mon Choisy (Offshore Breakwater Structure) • Final EIA Report-Coastal Adaptation Works Programme for Proposed Offshore Breakwater Structure and Beach Upgrading at Mon Choisy • Final Social Impact Assessment Report (SIA) for Coastal Adaptation Works Programme for Proposed Offshore Breakwater Structure and Beach Upgrading at Mon Choisy • Design Review Report of Coastal Adaptation Measures at Mon Choisy (Prof. Sundar, IIT Madras) conducted under EIA Revised EIA for Mon Choisy-Beach Rehabilitation including installation of artifical reef units (2017) • Final EIA Report for Mon Choisy (artificial reefs) • Final SIA Report for Mon Choisy (artificial reefs) • EIA Conditions for Mon Choisy-December 2017 Outcome 2: Early Warning System for incoming Storm Surge in the Republic of Mauritius Reports/contracts Signed • Contract Agreement for Consultancy Services for implementation of an Early Warning System for incoming Storm Surge in the Republic of Mauritius • Inception Workshop Report • Detailed Technical Assessment Report for implementation of an Early Warning System for Storm Surge in the Republic of Mauritius • System Design Report for implementation of an Early Warning System for Storm Surge in the Republic of Mauritius • Project Completion Report Phase 2-Extension of the Early Warning System to include wave component • RFP Document for Consultancy Services for Extension of the existing Early Warning System to include wave, swell and coastal inundation component
Outcome 3-Training Training Manuals/Handbooks/Contracts signed • Request for Proposal (RFP) document for consultancy services for the design and delivery of a CPD course on Disaster Risk Reduction in the Coastal Zone of Mauritius • RFP document for consultancy services for the design and delivery of a CPD course on Integrated Coastal Zone Management • Signed Contract Agreements with International Resource Persons/institutions (Ref. Procurement Sheet) 5 Training Manuals developed • Training Manual on Coastal and Marine Environment for Engineers • Training Manual on Coastal Protection Works • Training Manual on Cost Benefit Analysis for Coastal Zone Management and Adaptation Options to Climate Change in Mauritius • Training Manual on Integrated Coastal Zone Management • Handbook on Coastal Adaptation for coastal communities Outcome 4-Policy Mainstreaming Reports/documents at Procurement Stage • Expressions of Interest document for recruitment of a Consultant/expert for Policy Mainstreaming • Bid Evaluation Report for shortlisting of consultant/experts for Policy Mainstreaming (Expression of Interest stage) • Request for Proposal document for recruitment of a consultant/expert for Policy Mainstreaming (1st & 2nd round of procurement) • Revised Request for Proposal document for Consultancy Services for Preparation of National Coastal Zone Strategy for the Republic of Mauritius • Technical Evaluation Report • Financial Evaluation Report • Contract signed between Ministry and AGRER S.A.-N.V for Development of a National Coastal Zone Adaptation Strategy for the Republic of Mauritius-06 February 2017 • Inception Workshop Report & Detailed Work Plan • Report on review relevant strategies, policies, laws, regulations and projects pertaining to the coastal zone in ROM • Final Report on options for adaptation policies and measures, and vulnerability assessment result and map that identifies the most vulnerable coastal areas and systems with development capacity limit • Consultation Workshop Reports • Draft NCZAS Report including CVI Maps
Press/media/Weblinks: Outcome 1 (Weblinks) •http://environment.govmu.org/English/Documents/AFP-brief.pdf-Adaptation Fund Project 'Climate Change Adaptation Programme in the Coastal Zone of Mauritius' BRIEF •http://environment.govmu.org/English/Documents/photogallery_pdf/june%2015/Anse%20la%20Raie%203.06.15.pdf-Ecosystem Based Adaptation Activities, Public Beach Anse La Raie on 03.06.15 • https://undp.exposure.co/20000-mangroves-strong- access to storyline on mangroves plantation project at Grand Sable • CNN piece on coastal adaptation work at Quatre Soeurs/Grand Sable: http://edition.cnn.com/video/data/2.0/video/international/2014/06/16/spc-inside-africa-mauritius-a.cnn.html • http://www.lemauricien.com/article/face-aux-effets-nefastes-du-changement-climatique-les-villageois-grand-port-s-engagent-prote- Face aux effets néfastes du changement climatique: Les villageois de Grand-Port s’engagent à protéger leur region •http://adaptation-undp.org/resources/highlights/educational-tour-ile-d%E2%80%99ambre-Educational Tour at Ile D’Ambre • http://glispa.org/images/glispa/events/12.4.2013-Solution-Search-Press-Release.pdf: GLISPA!Highlight-Mauritian!NGO!Wins!Island!Bright!Spot!Award • http://allafrica.com/stories/201601182398.html-Government to build a Refuge Centre at Quatre Soeurs to protect coastal communities from storm surges (18.01.16) • https://www.youtube.com/watch?v=d7sOZcExuak-Youtube link to Adaptation Fund Mangrove Video : by Mark Slugg • http://www.maurice-info.mu/decisions-du-conseil-des-ministres-du-29-janvier-2016.html-Cabinet Decision – approval for Mon Choisy and Riviere des Galets • http://m.orange.mu/info/kinews/getnews.php?id=429902&LANG=fr&MCO=OMU-A refuge centre to be built at Quatre Soeur • http://gis.gov.mu-Inception Workshop on Coastal Adaptation Measures at Mon Choisy & Riviere des Galets • http://publicprocurement.govmu.org/Pages/default.aspx-For accessing launching of bid document for Riviere des Galets • www.indufor.fi/coastal-adaptation-measures-climate change-mauritius-Coastal adaptation measures to climate change in Mauritius (2014-2017) • http://www.msmparty.com/lutte-contre-le-changement-climatique-construction-prochaine-dun-centre-de-refuge-quatre-soeurs/ • https://www.eposters.net/pdfs/design-and-assessment-of-climate-change-adaptation-and-erosion-control-measures-for-mon-choisy.pdf • https://www.lexpress.mu/article/328677/mont-choisy-recifs-artificiels-bientot-implantes-dans-lagon • https://defimedia.info/riviere-des-galets-des-vagues-geantes-secrasent-sur-plusieurs-maisons • http://procurement-notices.undp.org/ (Ref No: 45603) • http://procurement-notices.undp.org/ (Ref: 46028) • http://procurement-notices.undp.org (Ref No: 46923) • https://www.ungm.org/Public/Notice (Ref No: 72640)
Outcome 2 (Weblinks) • CNN piece on upcoming Early Warning System- http://edition.cnn.com/video/data/2.0/video/international/2014/06/16/spc-inside-africa- mauritius-c.cnn.html • Signature of MoU with Mauritius Meteorological Services-http://www.gov.mu/English/News/Pages/default.aspx-access to events •Risques de raz-de-maree-L’Express dated 22 January 2015- http://www.lexpress.mu/article/257846/risques-raz-maree •Ce Systeme d’alerte sauvera des vies-Le Mauricien dated 14 March 2015- http://www.lemauricien.com/article/deepak-vatvani- Deepak Vatvani (Conseiller de la firme Deltares) •MoU with Mauritius, Deltares and UNESCO-IHE- https://www.deltares.nl/en/news/mou-with-mauritius-deltares-and-unesco-ihe •Early-Warning System for storm surge and tide in Mauritius- https://www.deltares.nl/en/projects/implementation-of-an-early-warning-system-for-storm-surge-and-tide-in-mauritius • Cyclone Storm Surge Forecasts for Mauritius- https://www.deltares.nl/en/news/cyclone-storm-surge-forecasts-for-mauritius • https://www.unesco-ihe.org/news/minister-mauritius-signs-memorandum-understanding-MoU with Deltares, UNESCO IHE, Ministry of Environment •http://environment.govmu.org/English/PublishingImages/photogallery/29%20Jan%202016.JPG-Signature of Memorandum of Understanding with Stichting Deltares and UNESCO IHE​​ in January 2016
Outcome 3 (Weblinks) University of Mauritius Website link: http://lcms.uom.ac.mu/lms/course/view.php?id=585 Website link: http://lcms.uom.ac.mu/lms/course/search.php?search=coastal+engineering Above link to access to course materials for 13 Short Courses (listed hereunder) completed under the AF Project in Mauritius & Rodrigues: a. Short Course on Coastal and Marine Environment for Engineers (Mauritius) b. Short Course on Coastal and Marine Environment for Engineers (Rodrigues) c. Short Course on Coastal Protection Works (Mauritius) d. Short Course on Cost and Benefit Analysis of Coastal Adaptation Measures e. Short Course on Decision analysis of coastal management and adaptation options to climate change (Mauritius) f. Short Course on Design of Coastal Structures (Soft Measures) (Mauritius) g. Short Course on Cost Benefit Analysis of Coastal Management and Adaptation Options to Climate Change in (Rodrigues) h. Short Course on Ocean Data Collection and Analysis (Mauritius) i. Short Course on Climate Change and Coastal Zone Management (Mauritius) j. Short course on Introduction to Open Source Geospatial Tools (Mauritius) k. Short course on Disaster Risk Reduction in the Coastal Zone of Mauritius l. Short course on Integrated Coastal Zone Management m. Short Course on Cost Benefit Analysis Applied to Climate Change Initiatives http://africa.southsouthworld.org/46-solution/1666/partnership-with-the-indian-institute-of-technology-madras-to-address-climate-change-impacts-in-mauritius-coastline-through-capacity-building-in-the-field-of-coastal-engineering-Partnership with the Indian Institute of Technology, Madras to address climate change impacts in Mauritius coastline through Capacity Building in the Field of Coastal Engineering
Outcome 4 (Weblinks) Consultancy Services for the preparation of a National Coastal Zone Adaptation Strategy for the Republic of Mauritius • http://environment.govmu.org/English/Pages/Procurement-Notice.aspx • http://www.comesa.int/consultancy-services-for-the-preparation-of-a-national-coastal-zone-adaptation-strategy-for-the-republic-of-mauritius/ •http://www.mu.undp.org/content/dam/mauritius_and_seychelles/docs/Procurement/12AUG16/RFP%20National%20Coastal%20Zone%20Adaptation%20%20Strategy_08.08.16.pdf •https://www.tendersontime.com/tender/consultancy-services-preparation-national-coastal-zone-adaptation-strategy-75c86e.php •https://opportunities.export.great.gov.uk/opportunities/mauritius-consultancy-services-for-preparation-of-a-national-coastal-zone-adaptation-strategy • Expressions of interest for recruitment of a consultant/expert for Policy Mainstreaming- https://Jobs-admin.undp.org, http://ppo.govmu.org • Launching of RFP on PPO Website-Weblink:http://publicprocurement.govmu.org/Pages/default.aspx
Outcome 5 (Weblinks) •http://environment.govmu.org/English/Documents/photogallery_pdf/june%2015/Poste%20de%20Flacq%20%204.06.15.pdf-Official sensitization and awareness raising campaign with the Marine Mobile Education Unit "Bis Lamer" and Symbolic Mangrove Plantation, Temple Poste de Flacq - 04.06.15 •http://mbc.intnet.mu/replay/zournal? Website links to access Short video clips on: a. Launching ceremony for Marine Mobile Education Unit b. Educational tour at Ile D’Ambre c. Signature of MoU between Attitude Group and Ministry i.c.w. ‘Greening Mauritius’ campaign including plantation of mangroves • http://www.Facebook.com: Reef Conservation (Sensitisation Campaigns carried out by Bis Lamer under the Adaptation Fund Board) • http://www.rogers.mu/en/news-events/launch-bis-la-mer • http://www.reefconservation.mu/projects/education-and-awareness/bis-la-mer
General Articles on the Adaptation Fund Project • Republic of Mauritius Portal (31 August 2012) • Commission de L’Ocean Indien (ACCLIMATE) 03 September 2012 • GLISPA Highlight: Mauritian NGO Wins Island Bright Spot Award- 4 December 2013 • ADD-GASAT International Conference (17-19 April 2014) • Quarterly Newspaper Vol 1 of the Ministry of Environment, Sustainable Development and Disaster and Beach Management: October to December 2015 • Le Mauricien dated 23.12.14-Erosion Cotiere: Le Ministere de L'Environnement doit avoir le role principal • Le Matinal dated 23.01.15 • Le Mauricien dated 22.01.15 • L’Express dated 22.01.15 • Le Mauricien dated 14.03.15 Outcome 1 (Mangrove Plantation Project at Grand Sable & Construction of Refuge Centre at Quatre Soeurs) • Le Mauricien dated 09 March 2013 • Le Mauricien dated 15 June 2013 • Le Mauricien dated 14 June 2014 • Le Matinal dated 17 June 2014 • Le Mauricien dated 26 July 2015 • Portail Orange Mauritius-19 February 2016-A Refuge Centre to be built at Quatre Soeurs • Samedi Plus 02-08 April 2016 (ONB Construction of Refuge Centre at Quatre Soeurs) • Le Defi Quotidien-30 March 2017 (Q. Soeurs: Le centre de Refuge operationnel en aout) Riviere des Galets • Le Matinal dated 26 March 2013 • Le Defi Quotidien dated 16 June 2014 • LeMauricien dated 27 September 2014-Riviere des Galet et Mon Choisy-Erosion Cotiere: Debut d'une etude au cout de Rs 275 M • L’Express dated 05 May 2016-Exit le relogement, place au mur Mon Choisy • Le Mauricien dated 29 January 2014-Plage de Mon Choisy: L'Erosion accentuee par les intemperies • Le Mauricien dated 27 September 2014-Riviere des Galet et Mon Choisy-Erosion Cotiere: Debut d'une etude au cout de Rs 275 M • L'Express dated 21 January 2016-Érosion côtière- Plages : pas moins de huit «îles-aux-Cerfs» perdues • L'Express dated 17 March 2016-Construction de dunes et recifs artificiels • Le Mauricien dated 24 July 2017- Notice for Public Inspection of EIA Report for Proposed artifical reef and beach upgrading at Mon Choisy under the coastal adaptation works programme • L'Express 31 July 2017-Environnement: L'Erosion commence a se faire voir •L'Express 04 December 2017-Mon Choisy: L'Erosion de plus en plus visible Bid document for ‘Rehabilitation of Mon Choisy Public beach and installation of artificial reef’-Advertised in local press • Le Mauricien dated 8,12 & 15 June 18 • L’Express dated 8,11 & 18 June 18 • Week-end dated 10 June 18 • Business Magazine dated 6 & 13 June 18 Request for Proposals for the Supervision of works ‘Rehabilitation of Mon Choisy Public beach and installation of artificial reef’ • L'Express dated 08 June 2018 • L'Express dated 11 June 2018 • L'Express dated 18 June 2018 • Le Mauricien dated 08 June 2018 • Le Mauricien dated 12 June 2018 • Le Mauricien dated 15 June 2018 • Week-end dated 10 June 2018 Early Warning System • The Economist magazine dated 12 January 2013 • L’Express dated 16 January 2013 • Le Mauricien dated 14 March 2014 • Le Defi Quotidien dated 21 March 2014 • Week End dated 23 March 2014 • Early Warning System for storm surge set up before next cyclonic season (http://www.govmu.org/English/News/Pages/Early-Warning-System-for-storm-surge-set-up-before-next-cyclonic-season.aspx)-21 January 2015 • Early-Warning System for storm surge and tide in Mauritius (https://www.deltares.nl/en/projects/implementation-of-an-early-warning-system-for-storm-surge-and-tide-in-mauritius) • Cyclone Storm Surge Forecasts for Mauritius (https://www.deltares.nl/en/news/cyclone-storm-surge-forecasts-for-mauritius) • MoU with Mauritius, Deltares and UNESCO-IHE (https://www.deltares.nl/en/news/mou-with-mauritius-deltares-and-unesco-ihe) • Le Matinal dated 23 January 2015 • Le Mauricien dated 22 January 2015 • L'Express dated 22 January 2015 • Le Mauricien dated 14 March 2015 • Le Matinal dated 12 August 2015 • Le Mauricien dated 10 August 2015 Training • Le Mauricien dated 10 February 2016
Partnerships: a. Memorandum of Agreement signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and Grand Sable Fishermen Association (NGOs) on 10 April 2013 b. Memorandum of Agreement signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and Grand Sable Women Planters Farmers Entrepreneur Association (NGOs) on 03 July 2013 c. Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and Mauritius Meteorological Services (13 March 2014) d. Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and University of Mauritius (22 May 2014) e. Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and Reef Conservation Mauritius (09 May 2014) f. Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and Rodrigues Regional Assembly (19 November 2015) g. Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, and Disaster and Beach Management and the Attitude Foundation (01 December 2015) h. Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, and Disaster and Beach Management and Stichting Deltares and UNESCO-IHE i. Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, and Disaster and Beach Management and Rogers Foundation, Reef Conservation (30 March 2016) Banners produced under AF Project: • 1 Banner on Mangroves Plantation & Sensitisation Project in the region of Grand Sable/Quatre Soeurs • 1 Banner on Riviere des Galets Project Site (vulnerability to storm surges) • 2 Banners on Training and Capacity Building Programme • 1 Banner on Problem statement of Mon Choisy & Riviere des Galets Project site • 2 Banner on Coastal Adaptation Options for Mon Choisy & Riviere des Galets project site • 1 Banner on Sensitisation Campaigns conducted under AF Project • 1 Banner on Early Warning System for Storm Surge
Short Video Clips produced under AF Project: Short Video Clips-Mangroves Plantation • 1 Short Video Clip on Mangroves plantation at Grand Sable on 09 September 2013 (by Mauritius Broadcasting Corporation) • 1 Short Video Clip on Mangroves sensitization programmes • 1 Short Video Clip on Educational Tour held at Ile D’Ambre on 09 September 2014 • 1 Short Video Clip on Symbolic Mangroves Plantation by the Honourable Minister of Environment, Sustainable Development, Disaster and Beach Management at Anse la Raie on 03 June 2015 • Laying of Foundation Ceremony for the construction of a Refuge Centre at Quatre Soeurs-15 August 2015 • Unveiling of Display Board to commemorate the successful implementation of mangroves project at Grand Sable-25 July 2015 • Unveiling of Display Board to commemorate the successful implementation of mangroves project at Baie du Cap-16 October 2015 • Press Conference and Simulation Evacuation Exercise at Quatre Soeurs Short Video Clips-Early Warning System • 1 Short Video Clip on the occasion of Signature of MoU Ceremony with the Mauritius Meteorological Services held on 13 March 2014 • 1 Short Video Clip on National Validation Workshop on Implementation of an Early Warning System for Storm Surge on 22 January 2015 • National Workshop for implementation of an Early Warning System for incoming Storm Surge in the Republic of Mauritius-22 January 2015 • Press Conference on implementation of an Early Warning System for incoming Storm Surge in the Republic of Mauritius-07 August 2015 • Press Conference on Signature of a Memorandum of Understanding between this Ministry, UNESCO IHE and Stichting Deltares Short Video Clips-Riviere des Galets • 1 Short TV Reportage on Riviere des Galets (23 June 2014) • Inception Workshop for Coastal Adaptation Measures at Mon Choisy & Riviere des Galets- 25 September 2014 • 1 Short Video Clip on National Validation Workshop on Coastal Adaptation Measures at Mon Choisy and Riviere des Galets held on 09 April 2015 Short Video Clips-Mon Choisy • Inception Workshop for Coastal Adaptation Measures at Mon Choisy & Riviere des Galets- 25 September 2014 • 1 Short Video Clip on National Validation Workshop on Coastal Adaptation Measures at Mon Choisy and Riviere des Galets held on 09 April 2015 • 1 short video clip on erosion at Mon Choisy beach Short Video Clips-Training • Short Course on Coastal and Marine Environment for Engineers in Rodrigues-15 July 2015 • Short Course on Cost Benefit Analysis of Coastal Management and Adaptation Options to Climate Change in Rodrigues-25 May 2015 • Award of Certificate Ceremony for the Short course on Integrated Coastal Zone Management Short Video Clips-Policy Mainstreaming • Short video (consultative workshop for development of a National Coastal Zone Adaptation Strategy for the RoM)-23 June 2017 Short Video Clips-Knowledge Disssemination • 1 Short Video Clip on Official Sensitisation and Awareness Raising Campaign with Marine Mobile Education Unit & Symbolic Mangroves Plantation by the Honourable Minister of Environment, Sustainable Development, Disaster and Beach Management at Poste de Flacq on 04 June 2015 • 1 Short Video Clip on exhibition organised under the AF Project in the context of World Environment Day 2015 held on 05 June 2015 • Short Video Clip on Adaptation Fund Project in the context of COP 21 • Short Video Clip on the impacts of climate change in the coastal region of Mauritius List of Cabinet/Information Papers: • The Cabinet Office was informed on 13 November 2013 on forthcoming Coastal Adaptation Works at Riviere des Galets • The Cabinet Office was informed on 09 May 2014 on the participation of the Mangroves Project in the Global Island Partnership 2013 Solution Search Award. This project was recognised as a best practice partnership by the United Nations Commission on Sustainable Development and the GSWPFEA won the first prize, known as the Island Bright Spot Award 2013. • The Cabinet Office was informed on 13 June 2014 that the United Nations, through the UNDP, has showcased the mangroves project at the UN Headquarters in New York in the context of celebrations of the World Environment Day (International) on 5 June 2014. The storyline of the project was also posted on the UNDP website. • The Cabinet took note on 15 January 2016 that the Minister of Environment, Sustainable Development, Disaster and Beach Management would sign a Memorandum of Understanding with Stichting Deltares and UNESCO IHE Institute for Water Education, Netherlands for the development of an Early Warning System for Storm Surge Parliamentary Questions •PQ 692-To ask the Honourable Minister of Environment, Sustainable Development and Disaster and Beach Management – Whether, in regard to the inhabitants of the EDC at Rivière des Galets who are at risk during bad weather conditions, he will state if any decision has been taken in regard to the relocation thereof? (http://mauritiusassembly.govmu.org/English/questions/Documents/PQ2015/pq13october2015.pdf) • PQ B/657-In regard to the inhabitants of Rivère des Galets, where matters stand as to the proposed relocation thereof-(http://mauritiusassembly.govmu.org/English/questions/Documents/PQ2016/pq28june2016.pdf) • PQ B/353-Whether, in regard to the inhabitants of the EDC at Riviere des Galets who are at risk during bad weather conditions, he will state if any decision has been taken for the relocation thereof? (http://mauritiusassembly.govmu.org/English/questions/Documents/PQ2017/pq25april2017.pdf)
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.adaptation-fund.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mrs. D. Lan Ng/Mr S. Mooloo | Dominican Republic
| Email: | smooloo@govmu.org | Ecuador
| Date: | 2018-07-31 | Egypt
| Government DA |  | El Salvador
| Name: |  | Equatoral Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | United Nations Development Programme (UNDP) | Fiji
| Email: | christine.umutoni@one.un.org/satyajeet.ramchurn@undp.org | Finland
| Date: | 2018-07-31 | France
| Executing Agency |  | Gambia
| Name: | Ministry of Social Security, National Solidarity and Environment and Sustainable Development (Environment and Sustainable Development Division) | Georgia
| Email: | ddeenoo@govmu.org | Germany
| Date: | 2018-07-31 | Ghana
| Executing Agency |  | Greece
| Name: | Ministry of Social Security, National Solidarity and Environment and Sustainable Development (Environment and Sustainable Development Division) | Grenada
| Email: | boolkah2000@yahoo.co.uk | Guatemala
| Date: | 2018-07-31 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31 July 2018
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [31 July 2018] | 3705033
Add any comments on AF Grant Funds. (word limit=200) | The disbursement up to the reporting period ending 31 July 2018 amounted to USD 3,705,033 which represent 44 % of the total budget. Note (i) No VAT has been paid from the AF Grant and it is being paid under the Ministry budget
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1, 1.2, 1.4, 1.5, 1.6 (Outputs merged under 1 Consultancy Services) | 152971.33
| Output 1.3 (Works) | 870848.44
| Outcome 1 subtotal | 1023819.77
Output 2.1, 2.2 (Outputs merged under 1 Consultancy Services)
| Outcome 2 subtotal | 0
Output 3.1 (Hdbk)
Output 3.2 (SC on Ceng)
Output 3.3 (CBA)
| Outcome 3 subtotal | 0
| Output 4.1, 4.2, 4.3, 4.4 (Outputs merged under 1 Consultancy Services) | 108413.35
| Outcome 4 subtotal | 108413.35
| Output 5.1 (Hd Bk) | 2888.6039
Output 5.2 (Diss Ind Ocean)
Output 5.3 (Scale scale models)
| Output 5.4 (Awareness) | 3550.2675
| Output 5.5 (Ranking) | 2750
| Outcome 5 subtotal | 9188.8714
| Outcome 6 (Execution Costs) | 93615.01
| TOTAL | 1235037.0014
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1 Detailed technical assessment of each site, with chronology of previous flood and erosion events and collection of nearshore oceanographic data, during “quiet” periods and “active” periods (one month each) to inform the design of the technical interventions at each of the three sites | 0 | COMPLETED
| 1.2 Technical design of coastal protection measures at each of three sites, with detailed costing, carried out in a gender sensitive way | 0 | COMPLETED
| 1.3 Successful construction of physical interventions at each of the three sites: (i) Refuge Centre at Quatre Soeurs Phase I -Completed Phase II (Asphalt Works/fencing/parking) including Supervision (ii) Riviere des Galets (USD 1,000,000) • Contract for Works awarded-03 May 2017 • Construction Works-80% Completed • Expected Completion-November 2018 (iii) Mon Choisy (USD 2,560,000) incl. Supervision • Award of contract-August 2018 • Expected Start of Works-Oct 2018 • Expected Completion of Works-September 2019 | 300,000 600,000 2,560,000 | COMPLETED ONGOING August 2019 ONGOING November 2018 ONGOING August 19
| 1.4 Analysis of data and development of recommendations on how the interventions can be adjusted for other vulnerable coastal locations in ROM. | 0 | ONGOING August 2019
| 1.5 Monitoring programme designed, to include scoping of suitable parameters, including beach width and slope; depth of adjacent lagoonal sediments; wave height, period, and run-up; direction of nearshore currents, etc. | 0 | ONGOING August 2019
| 1.6 A targeted coastal process/weather event monitoring system in place | 0 | ONGOING August 2019
| 2.1 Assessment of the current sea state monitoring systems (Mauritius Meteorological Services and Mauritius Oceanography Institute) and definition of required critical parameters and operational requirements for an early warning system | 200000 | COMPLETED Extension of Early Warning System to include wave run up-Implementation Started August 2019
2.2 The early warning system installed and implemented (with links to early warning system for cyclones), with communication linkages established from level of National Coast Guard at Headquarters down to the level of coastal communities.
| 3.1 “Handbook on Coastal Adaptation” packaged as training modules for coastal communities, relevant Government agencies, and private sector stakeholders (such as hotel operators); training sessions delivered on a regular basis over the course of the project (at least twice annually)-Completed | 0 | COMPLETED
| 3.2 Short course on Coastal Engineering designed and delivered (twice during programme period).-Completed | 0 | COMPLETED
| 3.3 Specialized course on Cost-Benefit Analysis of coastal adaptation measures designed and delivered (annually, over four years).-Completed | 0 | COMPLETED
| 4.1 A National Coastal Zone Adaptation that addresses all perceived climate change risks in the coastal zone of ROM over at least the next 20 years, with recommendations for supporting policies and regulations | 40000 | ONGOING
| 4.2 A set of recommendations on best technical and institutional adaptation practices suitable for the coastal zone of ROM |  | ONGOING
| 4.3 Definition of the required structure and processes for one “clearinghouse” for climate change oversight in the coastal zone of ROM (a unit or institution, or collection of individuals from various agencies, which is able to make final decisions on the climate appropriateness of future development projects; also having a follow-up enforcement capacity) |  | ONGOING December 18
| 4.4 Recommendations for new economic instruments |  | ONGOING
| 5.1 Handbook, training modules, and website content capturing best coastal adaptation practices for the Mauritius context | 0 | COMPLETED
| 5.2 Dissemination of lessons learned from the programme with coastal stakeholders in other locations in the southern Indian Ocean (DRR Workshop NDRRMC) | 200000 | ONGOING December 18
| 5.3 Interpretive signs and small-scale models of coastal processes designed and installed at each site, explaining the science of climate change and coastal processes (in lay terms), so that the linkages between weather, stability of coastal features, and adaptation measures are clear | 0 | COMPLETED
| 5.4 Public awareness campaigns on climate change in the coastal zone designed and delivered, involving the Mauritian media (TV, radio, Internet) | 0 | COMPLETED
| 5.5 Priority ranking of vulnerable coastal sites established, to guide the order of future investment by the Government of Mauritius and the private sector | 0 | COMPLETED
| Execution Costs | 100000
| TOTAL | 4000000
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | No co-financing committed in the Project Document
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 320645
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | No in-kind contribution during the reporting period.

## Procurement (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 0
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date | Remaining Balance
Local | Memorandum of Association signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and Grand Sable Fishermen Association (Mangroves Plantation Project) | 35000 | 2013-04-12 | 35000 | 0
Local | Memorandum of Association signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and Grand Sable Women Planters Farmers Entrepreneur Association (Mangroves Sensitisation Project) | 15000 | 2013-07-03 | 15000 | 0
Local | Memorandum of Association signed with University of Mauritius (Short Course on Coastal and Marine Environment for Engineers) | 22000 | 2013-09-06 | 22000 | 0
Local | Memorandum of Association signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and University of Mauritius (Short Course on Cost and Benefit Analysis of Coastal Adaptation Measures) | 8904.7742 | 2013-11-29 | 8904.7742 | 0
Local | Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and University of Mauritius for a long term collaboration in delivery of Specialised Courses on Coastal Engineering and Cost Benefit Analysis of Coastal Adaptation Measures | na | 2014-05-22 | na | na
Local | Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and Mauritius Meteorological Services for a long term collaboration in implementation of the Early Warning System for Incoming Storm Surge in the Republic of Mauritius | na | 2014-03-13 | na | na
Local | Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and Reef Conservation Mauritius (NGO) for conduct of sensitisation campaigns on Climate Change Adaptation among the coastal communities using a marine mobile education unit, development of learning/sensitisation matters 3D Small Scale Models, Educational tours | 56000 | 2014-09-09 | 56000 | 0
Local | Memorandum of Understanding signed between Ministry of Environment, Sustainable Development,and Disaster and Beach Management and Rodrigues Regional Assembly( RRA) for the broad areas of collaboration comprising of replication of generic designs for coastal adaptation measures develped under the AF project for Rodrigues, development of an Early warning system for storm surge for rodrigues, deilvery of Short courses and learning materials for Resource Centre. | MUR 512900 (USD 16 000) | 2015-11-19 | n/a | n/a
local | Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, and Disaster and Beach Management and Green Attitude Foundation for the replication of mangrove plantation, promotion of alternative livelihood in the northern region, sensitisation campaigns on climate change and environmental protection and video clips. | MUR 500000 (USD 15 600) | 2015-12-01 | na | na
Local | Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, and Disaster and Beach Management, UNESCO-IHE and Stichting Deltares to secure technical assistance in terms of research and capacity building for coastal zone adaptation and operation of the early warning system for storm and tidal surge | na | 2016-01-20 | na | na
Local | Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, and Disaster and Beach Management and Reef Conservation Mauritius (NGO), Rogers Foundation Ltd for conduct of sensitisation campaigns on Climate Change Adaptation among the coastal communities using a marine mobile education unit, development of knowledge dissemination tools : Handbook, electronic quizz game, waterproof pouch | 57545 | 2016-03-30 | 57545 | 0
Local | Contract signed between the Ministry of Environment, Sustainable Development, Disaster and Beach Management and the Consortium Mega Design in association with Design Forum, STEGET, SEE Engineering Consultants Co Ltd and Chuttur & Partners Ltd for Consultancy Services for Design, Preparation of bid document and Supervision of Works for the Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs | 119355 | 2015-07-06 | 100880 | 18475
International | Contract signed between between Ministry of Environment, Sustainable Development, Disaster and Beach Management and the Indian Institute of Technology Madras for the Design and Delivery of a Short Course on Design of Coastal Adaptation Structures (soft measures) including a case study for Mon Choisy | USD 20000 | 2014-07-25 | USD 20000 | 0
International | Contract signed between between Ministry of Environment, Sustainable Development, Disaster and Beach Management and the Indian Institute of Technology Madras for the Design and Delivery of a Short Course on Ocean Data Collection and Analysis | USD 16405 | 2014-12-15 | USD 16405 | 0
International | Contract signed between UNDP and Indufor Oy for services in respect of Coastal Adaptation Measures at: Mon Choisy: Site assessment, identification of adaptation options, cost benefit analysis, preparation of feasibility study, detailed design, preparation of tender documents, supervision of works and recommendation of remedial measures during monitoring period Riviere des Galets: Site assessment, identification of adaptation options, cost benefit analysis, preparation of feasibility study, detailed design, preparation of tender documents Contract Closed | 817850 | 09-09-2014 14-02-2018 | 531607 | 286243
International | Contract signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and Stichting Deltares for Consultancy Services for imlementation of an Early Warning System for incoming Storm Surge in the Republic of Mauritius | 188800 | 2014-11-07 | 188800 | 0
local | Contract signed between the Ministry of Environment, Sustainable Development, and Disaster and Beach Management and Scene-Ries Ltd for the consultancy services for Preparation of Environmental Impact Asssemment reports for Mon Choisy and Riviere des Galets | MUR 930,000 (USD 26,193) USD 12,000 MUR 302,250 (USD 8513) | 15-01-2016 08-Feb-17 | MUR 869,550 (USD 24,490) USD 11,220 MUR 137,175 (3863) | USD 1,703 USD 780 USD 4650
International | Contract signed between the Ministry of Environment, Sustainable Development, and Disaster and Beach Management and TACSYM Ltd for Consultancy services for the design and delivery of a short course on Disaster Risk Reduction in the Coastal Zone of Mauritius | MUR 419,204(USD 13 100) | 2016-01-12 | MUR 419,204 (USD 13100) | 0
International | Contract signed between the Ministry of Environment, Sustainable Development, and Disaster and Beach Management and The University of Western Australia for the Consultancy services for the design and delivery of a short course on Integrated Coastal Zone Management | AUD 55,050 (USD ) | 2016-02-01 | AUD 55,050 (USD ) | 0
International | Contract signed between the Ministry of Environment, Sustainable Development, and Disaster and Beach Management and The University of Western Australia for the Consultancy services for the design and delivery of a short course on Cost Benefit Analysis Applied to Climate Change Initiatives | AUD 33,076 (USD 25,295) | 2016-07-01 | UAD 33,076 (USD 25295) | 0
Local | Contract signed between the Ministry of Environment, Sustainable Development, and Disaster and Beach Management and Best Construct Ltd for Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs | 1281292 | 2016-07-22 | 982073 | 299219
Local | Contract signed between Ministry of Social Security, National Solidarity and Environment and Sustainable Development and Luxconsult (Mtius) Ltd for Consultancy Services for Supervision of Coastal Protection and Landscaping Works at Riviere des Galets | MUR 2,182,609 USD 61,472 | 2017-04-20 | MUR 873,043 USD 25678 | MUR 1,309,566 USD 35,794
local | Contract signed between Ministry of Social Security, National Solidarity and Environment and Sustainable Development and Super Builders Co Ltd for Construction of Rock Revetment Structure with Parapet Wall at Riviere des Galets | MUR 25,197,875 USD 709,680 | 2017-10-18 | MUR 8,941,699 USD 262,991 | MUR 16,256,176 USD 446,689
International | Contract signed between Ministry of Social Security, National Solidarity and Environment and Sustainable Development and AGRER S.A.-N.V for Development of a National Coastal Zone Adaptation Strategy for the Republic of Mauritius | 147110 | 2017-02-06 | 88270 | 58840
BIDS
List all bids for each contract signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Expression of Interest (EOI) for Consultancy Services for the Design, Preparation of Tender Document and Supervision of Works for the Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs/Deux Freres Open Advertised Bidding (local) 22 August 2012 | 1. GIBB (Mtius) Ltd in Association with Spectral 2. Consortium: Mega Design Ltd, SEE Engineering Consultants, Steget, Chuttur & Partners Ltd 3. Lux Consult (Mtius) Ltd in association with Lanka Hydraulic Institute Ltd 4. Daruty De GrandPré & Partners Architects Ltd 5. Pravin Desai Architect 6. Francis Wong Associates Ltd 7. Joint Venture Desai & Associates Ltd & SGI Studio Galli Ingegneria S.p.A 8. Ahmed Rawat Architect in association with Soomah Associates Ltd, Prodesign Ltd, Kim Currun GS | Financial offer not submitted at EOI stage as per National Procurement Procedure | Financial offer not submitted at EOI stage as per National Procurement Procedure | 5 firms were shortlisted (hereunder shortlisted) for future Request for Proposal (RFP) based on the technical capability of the firms. The RFP for Consultancy Services was launched on 16 February 2015. 1. GIBB (Mtius) Ltd in Association with Spectral 2. Consortium: Mega Design Ltd, SEE Engineering Consultants, Steget, Chuttur & Partners Ltd 3. Daruty De GrandPré & Partners Architects Ltd 4. Pravin Desai Architect 5. Francis Wong Associates Ltd
Request for Proposal (RFP) for Consultancy Services for the Design, Preparation of Tender Document and Supervision of Works for the Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs/Deux Freres | 1. Consortium: Mega Design Ltd, SEE Engineering Consultants, Steget, Chuttur & Partners Ltd 2. Francis Wong Associates Ltd 3. Pravin Desai Architect | 1. USD 137,258 2. USD 136,145 3. USD 176,210 | 1. USD 137,258 | Best evaluated bidder based on technical and financial evaluation
Call for Bids for Works for the Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs | 1. Como Construction 2. Best Construct Co. ltd 3.Tayelamay & Sons Enterprise ltd 4.RBRB Construction ltd 5.Square Deal Multipurpose Cooperative Society ltd | 1. MUR 54,970,000 2. MUR 43,629,769.88 3. MUR 49,906,217 4. MUR 56,930,055.40 5. MUR 56,667,616.20 | MUR 43,563,951.62 | Best evaluated bidder based on technical and financial evaluation
First Round of Procurement (EOI) The Expression of Interest for Consultancy Services for the preparation of feasibility studies, Environmental Impact Assessment Reports, Design, Preparation of Bid Documents and Supervision of Works for the implementation of coastal adaptation measures at Mon Choisy and Rivière des Galets, Mauritius Open Advertised Bidding 14 December 2012 | First Round of Procurement (EOI) 1. Arup Sigma Ltd 2. Deltares 3. Indufur Og, Finland in association with Coastal Land & Marine Services Ltd 4. Consulting Consortium DMC – CSIR c/o Delta Marine Consultants 5. Witteveen + BOS 6. Egis International in association with Egis Eau E.Venture Ltd 7. Wapcos Ltd 8. HR Wallingford Ltd (UK) 9. Unique System FZE (UAE) 10. COWI 11. Mukesh and Associates India in Association with Soomah Associates Ltd 12. NIRAS in Association with Mega Design 13. GHD PTY LTD 14. Lux Consult in association with Lanka Hydraulic Institute 15. GIBB (Mtius) Ltd in association with BMT Consultants India & Diospyros Ltd 16. Worley Parsons & Desai and Associates Ltd 17. MED INGEGNERIA 3T PROGETTI ITALIA 18. Mott Macdonald (UK) 19. Indomer Coastal Hydraulics (p) Ltd | Financial offer not submitted at EOI stage as per National Procurement Procedure | Financial offer not submitted at EOI stage as per National Procurement Procedure | First Round of Procurement 1. Deltares 2. Indufor Oy, Finland in association with Coastal Land & Marine Services Ltd 3. Consulting Consortium DMC – CSIR c/o Delta Marine Consultants Pravin Desai Architect 4. NIRAS in Association with Mega Design 5. Lux Consult in association with Lanka Hydraulic Institute 6. GIBB (Mtius) Ltd in association with Association with BMT Consultants India & Diospiros 6 international firms out of 19 received at the Expression of Interests stage were shortlisted for future RFP based on the technical capability of the firms/consortium
First Round of Procurement (EOI) The Expression of Interest (EoI) for Consultancy Services for implementation of an Early Warning System for incoming Storm Surge in the Republic of Mauritius 12 January 2013 | First Round of Procurement (EOI) 1. Worley Parsons/RPS asa/Ctl Consult 2. Met Office/Ctl Consult 3. Sea Systems Engineering Australia Pty ltd 4. Alexander Polonsky 5. Deltares, The Netherlands in association with Delphinium ltd, Mauritius 6. Consortium of ecoast & Mulgur consulting ltd | Financial offer not submitted at EOI stage as per National Procurement Procedure | Financial offer not submitted at EOI stage as per National Procurement Procedure | First Round of Procurement (EOI) 1. Sea Systems Engineering Australia Pty ltd 2. Deltares, The Netherlands in association with Delphinium ltd, Mauritius 3. Met Office/Ctl Consult 4. Worley Parsons/RPS asa/Ctl Consult
First Round of Procurement (RFP) RFP for Consultancy Services for the preparation of feasibility studies, Environmental Impact Assessment Reports, Design, Preparation of Bid Documents and Supervision of Works for the implementation of coastal adaptation measures at Mon Choisy and Rivière des Galets, Mauritius Open Advertised Bidding (International) 26 April 2013 | First Round of Procurement (RFP) 1. NIRAS in Association with Mega Design Ltd and DHI 2. Indufur Og, Finland in association with Coastal Land and Marine Solutions, C.L.A.M.S. Ltd 3. Lux Consult (Mtius) Ltd in association with Lanka Hydraulic Institute Ltd 4. GIBB (Mtius) Ltd in association with BMT Consultants India & Diospyros Ltd 5. Consulting Consortium DMC – CSIR c/o Delta Marine Consultants | USD 1,459,450 1. Consulting Consortium DMC – CSIR c/o Delta Marine Consultants 2. Indufor Oy, Finland in association with Coastal Land and Marine Solutions, C.L.A.M.S. Ltd | No winning bid | Financial offers not responsive (outside outputs budget enveloppe) Bid exercise cancelled
Second Round of Procurement RFP for Consultancy Services for Coastal Adaptation measures at: - Mon Choisy: site assessment, identification of adaptation options, cost-benefit analysis, preparation of feasibility study, detailed design, preparation of tender documents, supervision of works and recommendation of remedial measures during monitoring period. - Rivière des Galets: site assessment, identification of adaptation options, cost-benefit analysis, preparation of feasibility study, detailed design, preparation of tender documents Open international procurement (UNDP) 24 March 2014 | 1. PRDW 2. DMC 3. LuxConsult 4. Worley Parsons 5. Indufor 6. Agrer TYPSA 7. WSP 8. Niras | 2. 1,180,556 USD 5. 817,850 USD 8. 1,120,855 USD | 817,850 USD | Best Evaluated Bidder based on technical and financial evaluation 5. Indufor Oy in association with eCoast and C.L.A.M.S Ltd Following the Bid Evaluation Committee which comprise of members from the AF Project Team, UNDP CO and UNDP Regional Office, the bids were evaluated and the ranking were as follows;
First Round of Procurement RFP for Consultancy Services for the implementation of an Early Warning System for incoming Storm Surge in the Republic of Mauritius Open international procurement 23 May 2013 | 1.Worley Parsons/RPS asa/Ctl Consult 2. Met Office/Ctl Consult 3. Sea Systems Engineering Australia Pty ltd 4. Deltares, The Netherlands in association with Delphinium ltd, Mauritius | Bid technical evaluation completed 1.Worley Parsons/RPS asa/Ctl Consult | Bid Financial evaluation completed (Quoted Price: USD 671,783) | Financial offer not responsive (outside outputs budget enveloppe) Bid exercise cancelled
Second Round of Procurement RFP for Consultancy Services for the implementation of an Early Warning System for incoming Storm Surge in the Republic of Mauritius Open international procurement 09 July 2014 | Shortlist of Consultants 1. Dr Hendrik L. TOLMAN 2. Mr Nadao KOHNO 3. Professor Shishir K. DUBE 4. Dr Wattana KANBUA 5. Dr Pierre DANIEL DPREVI/MAR, Météo- 6. Dr. Paul DAVIES 7. Deepak Vatvani 1 bid submitted 1. Deltares-The Netherlands | USD 249,703 (EUR 188,800) | USD 249,703 (EUR 188,800) | Best Evaluated Bidder based on technical and financial evaluation USD 249,703 (EUR 188,800)
Implementation of mangrove plantation project at Quatre Soeurs/Grand Sable Direct procurement 12 April 2013 | Grand Sable Fishermen Association (Vulnerability Risk Assessment conducted in partership with UNDP/GEF Small Grants Programme) | USD 35000 (as per budget allocation in the AF Project document) | USD 35000 (as per budget allocation in the AF Project document) | Community Based Project involving the vulnerable local communities. NGO selected following Vulnerability Risk Assessment conducted in partnership with UNDP/GEF Small Grants Programme.
Sensitisation campaign in connection with mangrove plantation project at Quatre Soeurs/Grand Sable Direct procurement 3 July 2013 | Grand Sable Women Planters Farmers Entrepreneur Association (Vulnerability Risk Assessment conducted in partnership with UNDP/GEF Small Grants Programme) | USD 15000 (as per budget allocation in the ProDoc) | USD 15000 | Community based project involving the vulnerable local communities. NGO selected following Vulnerability Risk Assessment conducted in partnership with UNDP/GEF Small Grants Programme.
Expression of Interests for Consultancy Services for the Design and Delivery of a Short Course on Coastal Engineering Restricted bidding 10 March 2013 | 1. Worley Parsons (RSA) Ltd-Dr Gary Mocke 2. Dr. Angus Jackson 3. Deltares-Dr Alession Giardino | Financial offer not submitted at EOI stage as per National Procurement Procedure | Financial offer not submitted at EOI stage as per National Procurement Procedure | 3 International firms were shortlisted for future RFP's based on the technical capability of the Experts/firms.
Request for Proposals for Consultancy Services for the Design and Delivery of a Short Course on Coastal Engineering Restricted bidding 3 May 2013 | 1. Worley Parsons (RSA) Ltd 2. Dr. Angus Jackson 3. Deltares | Bid technical evaluation completed 1.Worley Parsons/RPS asa/Ctl Consult-Dr Gary Mocke USD 46,437 | USD 46,437 | Best Evaluated Bidder based on technical and financial evaluation 1. Worley Parsons (RSA) Ltd-Dr Gary Mocke (Bid Evaluation Committee chaired by the University of Mauritius)
Request for Proposals for Consultancy Services for the Design of Coastal Adaptation /Protection Structures Restricted Bidding 26 February 2014 by University of Mauritius | 1. Deltares-Dr Alessio Giardino 2. Consortium: Mr Angus Jackson, Dr Gary Mocke & Pro. R. Tomlison | Bid technical evaluation completed 1.Deltares-Dr Alessio Giardino 65,044 USD | Bid Financial evaluation completed Quoted Price: USD 65,044 | Financial offers not responsive (outside outputs budget enveloppe) Bid Evaluation Committee chaired by the University of Mauritius (UoM) Bid exercise cancelled
Short Course on Design of Coastal Adaptation Structures (Soft Measures) Restricted Bidding 15 June 2014 by University of Mauritius | 1. Indian Institute of Technology Madras | Indian Institute of Technology Madras Prof. V. Sundar, Prof.K. Murali, Prof.S.A.Sannasiraj | Quoted Price USD 20,000 | Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and the University of Mauritius. IIT Madras is the institution collaborating with the UoM in the context of Ocean Economy in the Republic of Mauritius and following failed procurement the team was requested to submit a bid and awarded the contract after technical and financial evaluations as per University of Mauritius procedures.
Short Course on Ocean Data Collection and Analysis Restricted Bidding By University of Mauritius | 1. Indian Institute of Technology Madras | 1. USD 16,405 | 1. USD 16,405 | Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, and Disaster and Beach Management and the University of Mauritius. IIT Madras is the institution collaborating with the UoM in the context of Ocean Economy in the Republic of Mauritius and IIT Madras awarded the contract after technical and financial evaluations as per University of Mauritius procedures.
Short Course on Climate Change and Coastal Zone Management Restricted Bidding University of Mauritius | 1. University of Mauritius | MUR 52,140 | MUR 52,140 | In line with Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, and Disaster and Beach Management and the University of Mauritius.
Short Course on Cost and Benefit Analysis of Coastal Management and Adaptation Options to Climate Change (Rodrigues) Restricted Bidding University of Mauritius | 1. University of Mauritius | MUR 140,000 | MUR 140,000 | In line with Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, and Disaster and Beach Management and the University of Mauritius.
Request for Proposal for consultancy services for the design and delivery of a CPD course on Integrated Coastal Zone Management 27 April 2015 | 1. University of Western Australia 2. Marie Roseline Yardin | 1. USD 52,544 2. USD 26,126 | 1. USD 52,544 | Best evaluated bidder based on training proposal and contents submitted
Request for Proposal for consultancy services for the design and delivery of a CPD course on Disaster Risk Reduction in the coastal zone of Mauritius Restricted Bidding 22 October 2015 By University of Mauritius | 1. TACSYM Specialist Training Facilities 2. Stichting Deltares in association with Asian Disaster Preparedness Centre, Thailand | 1.MUR 419,204 2. EUR 17,890 | MUR 419,204 | Best Evaluated Bidder based on technical and financial evaluation 1. TACSYM Specialist Training Facilities (Bid Evaluation Committee chaired by the University of Mauritius)
Request for Proposal for consultancy services for the Preparation of Environment Impact Assessment Reports for Coastal Adaptation works at Mon Choisy and Rivieve des Galets Restricted Bidding 13 October 2015 | 1.Mega Design ltd 2.Desai & Associates ltd in association with HR Wallingford 3.Scene-Ries Consult Ltd | 1. MUR 1,352,400 2. MUR 1,069,500 | MUR 1,069,500 | Best Evaluated Bidder based on technical and financial evaluation 3. Scene -Ries Consult ltd (Bid Evaluation Committee chaired by the Ministry of Environment, Sustainable Development and Disaster and Beach Management )
Short Course on Introduction to Open Source Geospatial Tools Restricted Bidding University of Mauritius | 1. Boomerang Geospatial |  |  | In line with Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, and Disaster and Beach Management and the University of Mauritius.
Expressions of interest for recruitment of a consultant/expert for Policy Mainstreaming Open Advertised Bidding (International) 18 December 2014 by UNDP CO | 1. Mr. Abu Uddin (BANGLADESH) 2. Mr. Ahmed Yousef (EGYPT) 3. Mr. Aidan Mallamo (UNITED STATES OF AMERICA) 4. Mr. Alan Hooper (UNITED KINGDOM) 5. Mr. Alejandro Moreno Mustieles (SPAIN) 6. Mr. Alexander Dawson Shepherd (UNITED KINGDOM) 7. Mr. Aneel Salman (PAKISTAN) 8. Mr. Avinash Dookia (MAURITIUS) 9. Mr. Bhawan Singh (CANADA) 10. Mr. Christen Wadan (SOUTH AFRICA) 11. Mr. filippo fraschini (ITALY) 12. Mr. Gianluca Ragusa (ITALY) 13. Mr. Gino Sabatini (CANADA) 14. Mr. Guido Corno (ITALY) 15. Mr. jamal Cagoweyne (SOMALIA) 16. Mr. Jonathan McCue (UNITED KINGDOM) 17. Mr. Komlanvi Moglo (UNITED KINGDOM) 18. Mr. miguel trillo (SPAIN) 19. Mokshanand DOWARKASING (MAURITIUS) 20. Mr. Orlando MENDES (GUINEA-BISSAU) 21. Mr. Peter Smith (AUSTRALIA) 22. Mr. thomaskutty AV (INDIA) 23. Mr. Tom Murray (UNITED KINGDOM) 24. Mrs. Stephanie Hodge (CANADA) 25. Ms. BENITHA GOWRAKI (SOUTH AFRICA) 26. Ms. Ephrat Yovel (USA) 27. Ms. Lucinda Fairhurst (SOUTH AFRICA) 28. Ms. Nathalie MAISONNEUVE (FRANCE) 29. Ms. RAJOO VIDUSHI (MAURITIUS) 30. Ms. Saraswatee Jagessur (MAURITIUS) 31. Ms. Sophie van der Meeren (UNITED KINGDOM) | Financial offer not submitted at EOI stage as per National Procurement Procedure | Financial offer not submitted at EOI stage as per National Procurement Procedure | 6 Experts/Consultants were shortlisted (hereunder listed) for future Request for Proposal (RFP) based on the technical capability/expertise 1. Mr. Abu Uddin (BANGLADESH) 2. Mr. Alexander Dawson Shepherd (UNITED KINGDOM) 3. Mr. Bhawan Singh (CANADA) 4. Mr. Guido Corno (ITALY) 5. Mr. miguel trillo (SPAIN) 6. Mr. Peter Smith (AUSTRALIA)
First Round of Procurement RFP for Consultancy Services for the preparation of a National coastal zone adaptation strategy for the Republic of Mauritius Restricted Bidding mode of procurement 18 December 2015 | No bids received
Second Round of Procurement RFP for Consultancy Services for the preparation of a National coastal zone adaptation strategy for the Republic of Mauritius Restricted Bidding mode of procurement 29 February 2016 | No bids received
Third Round of Procurement RFP for Consultancy Services for Preparation of a National Coastal Zone Adaptation Strategy for the Republic of Mauritius Open International Bidding 08 August 2016 | 1. Agrer S.A.-N.V (Belgium) 2. ESIA Consult Pty Limited (Australia) 3.Dfractals Advisors for Development (India), EML Consultants (Private) Ltd (Sri Lanka) 4. SRK Consulting (South Africa) (PTY) Ltd, Bluepebble Sustainability Solutions (South Africa), University of Cape Town Institute of Marine and Environmental Law (South Africa), Anchor Environmental (South Africa), Strategic Networking Partners and Consulting Ltd (Local) 5. Hatch Africa (Pty) Ltd (South Africa). Enviro Consults Ltd (Local), C-Core (Canada), Gaia Consulting Ltd (U.S.A), Zeta Consultants T/A Prime Africa Consultants (South Africa) | USD 161,946 MUR 5,752,300 | 1. Agrer S.A.-N.V (Belgium) USD 161,946 MUR 5,752,300 | Best Evaluated Bidder based on Technical & Financial Proposal
Procurement of Construction of Rock Revetment structure with Parapet wall at Riviere des Galets Open National Bidding 09 December 2016 | 1. Super Builders Co Ltd 2. Sotravic Limitee 3. Square Deal Multipurpose Cooperative Society Ltd | MUR 28,977,556.25 MUR 41,395,128.60 MUR 35,116,400 | 1. Super Builders Co Ltd MUR 28,977,556.25 USD 815,814 | Best Evaluated Bidder based on Technical & Financial Proposal
Request for Proposal for Consultancy Services for Supervision of Coastal Protection and Landscaping Works at Riviere des Galets 01 December 2016 | 1. Servansing Jadav & Partners Consulting Engineers Ltd 2. GIBB (Mauritius) Ltd 3. Scene-Ries Consult Ltd 4. Mega Design Ltd 5. Luxconsult (Mtius) Ltd | MUR 5,312,000 MUR 4,700,000 MUR 3,890,000 MUR 3,265,000 MUR 2,510,000 | Luxconsult (Mtius) Ltd MUR 2,510,000 USD 70,665 | Best Evaluated Bidder based on Technical & Financial Proposal

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
High level endorsement of proposed policy and regulatory changes to support coastal adaptation may be lacking (enabling legislation may be delayed); there may also be concerns about creating a new climate change oversight function within the Ministry of Environment, Sustainable Development, Disaster and Beach Management (degree: moderate) | Coastal adaptation projects and initiatives are fully supported by the Ministry and the Project Steering Committee (degree: low) | High level endorsement of proposed policy and regulatory changes to support coastal adaptation may be lacking (enabling legislation may be delayed) • Programme activities and progress are discussed at the Technical and Project Steering Committees. • 21 Project Steering Committee Meetings and 26 Technical Committee have been held since start of the project and decisions on proposed policies and regulatory changes with respect to coastal adaptation have been endorsed. There may also be concerns about creating a new climate change oversight function within the Ministry of Environment, Sustainable Development, Disaster and Beach Management •A new Climate Change Bill is under preparation at the Ministry at the level of the Ministry which clearly define the roles of each division. The bill will be submitted by the Hon. Minister to the Parliament for approval.
Government of Mauritius commitment to climate change management could wane as development priorities become more prominent and compete, especially in the run-up to elections. (degree: moderate) | Mauritius has witnessed in the recent past some of the impacts of climate change including flash floods, variability in rainfall distribution amongst others. The Government is thus well aware of climate change impacts and it is one of the national priority to build climate resilience. Up to now the change in Government has not affected the climate change management in Mauritius (degree: low) | • Constant reiteration of the risks of climate change and the positive net benefits of adaptation investments are being disseminated.
Delays in fund transfers and procurement of technical services and equipment. (degree: moderate) | The procurement process in the Government is indeed lengthy as it follows the Public Procurement Act procedures. The procurement of highly technical expertise required the project to undertake international bidding No bids were received in some highly technical and scarcity areas. In some cases the bid price were beyond the budgeted amount in the AF Project Document (degree: low) | • Programme activities were initially designed and paced to ensure completion over five years. Following the first round of procurement and lessons learnt, a budget reallocation (USD 391,400) from the Component ‘Policy Mainstreaming’ and ‘Knowledge Dissemination’ to Coastal Adaptation Works at Mon Choisy & Riviere des Galets and Early Warning System was effected in consultation with the UNDP CO. • The Revised Budget allocation was endorsed by the Financial Secretary, the Designated National Authority and subsequently approved by the AFB in March 2014. • The support of the UNDP in Preparation of Terms of Reference for International Consultant for Policy Mainstreaming and procurement of consultancy servicecs for Coastal Adaptation Works at Mon Choisy and Riviere des Galets were undertaken • The Programme Board provide required oversight for management of programme inputs. • Request for last trance from the AFB through the PPR, will be submitted at earliest possible so that there is no shortage of funds to complete the earmarked activities up to end of the project.
Ministry may have limited management capacity for programme activities, and for the eventual assumption of climate change management oversight and enforcement; conflicts between the CC Cell and the ICZM Division may arise. (degree: moderate) | The Adaptation Fund Project has received management support as the chair of the steering committee is the Permanent Secretary and the Director of Environment is the National Project Director who has the technical capacity to the manage the project. Since start of the project all the technical divisions of the Ministry have been involved and provided technical support toward success of the project. Till date there has been no conflicts between the technical division. A new climate change bill at the level of the Ministry has been prepared which will clearly define the roles of each division. This bill has been worked out by the respective technical divisions of the Ministry (degree: low) | Ministry may have limited management capacity for programme activities, and for the eventual assumption of climate change management oversight and enforcement; conflicts between the CC Cell and the ICZM Division may arise. • UNDP has maintained a strong link with the programme, and the various programme activities that address institutional aspects have be guided by international consultants, who have brought in international expertise and experience. • The project has recruited 1 Project Manager, 1 Project Assistant and 1 Project Technical Assistant to support implementation of the project. • The Permanent Secretary has been nominated as the Chair of the Project Steering Committee • The Director of Environment has been nominated National Project Director and also chair of the Technical Committee thus no conflicts have arised till date as the Director of Environment is the Technical Head of the Ministry. • The new climate change bill at the level of the Ministry will clearly define the roles of each division • The climate change management oversight and enforcement is under the same Ministry
Climate variability accelerates and coastal degradation occurs at a faster pace than anticipated. (degree: moderate) | Climate variability is still a concern, and is complicated by uncertainty. However, the project has undertaken various studies prior to coming up with the best adaptation solution for each coastal sites (degree: low) | Modelling of different scenarios of the climate change variability and impacts have been completed under Outcome 1. The final designs have taken into consideration the above risk factor The climate change modelling, as part of the deliverables under the component 1 has addressed this potential risk to the satisfaction of the Technical, Project Steering Committee and the EIA Committee
There may be a misunderstanding about the jurisdictional area of an agency that has climate change management oversight and right of enforcement. (degree: moderate) | The misunderstanding about the jurisdictional area of an agency that has climate change management oversight and right of enforcement is no more an issue as the project has successfully reached its final stage of completion with the colloboration of the Project Steering Committee and Ministry (degree: low) | • The component on Policy Mainstreaming (Development of a National Coastal Zone Adaptation Stratgey) will clearly define the responsibilities of each Ministry, as a specific deliverable. The Final report has been submitted by the international consultants and will be validated by stakeholders from Ministries/departments and EIA Committee in the coming months • It is precisely the analysis of overlapping jurisdictions and conflicting regulations that will sort out respective roles and improve the situation for all Ministries/agencies, so that coastal adaptation can proceed accordingly. The consultant for Policy Mainstreaming has prepared a National Coastal Zone Adaptation Strategy for the Republic of Mauritius including Coastal Vulnerability Maps
Districts (local government) may perceive themselves in a peripheral role, with their development put aside for the sake of climate change adaptation. (degree: moderate) | • The officials of all Local authorities have been trained in the field of coastal engineering/climate change adaptation/Cost Benefit Analysis, as part of the capacity building programme under Outcome 3 • The delivery of t*he Short Courses started since September 2013. To date 13 Short Courses in the field of Coastal Engineering, Coastal and Marine Environment for Engineers, Cost and Benefit Analysis, amongst others have been delivered under the Project in Mauritius and Rodrigues. (degree: low) • Consultations have also been held with local authorities during the Environment Impact Assessment phase of each projects | The District Councils are represented in the Programme Board (Project Steering & Technical Committee and EIA Committee) and in programme activities. The recommendations of the District Councils are integrated in the proposed developments under Outcome 1. The positive results of the coastal protection measures are disseminated and well understood by the District Councils.
Varying, possibly conflicting, perceptions of the climate change risks and coastal adaptation approaches may become apparent, based on previous experiences and technical expertise. (degree: moderate) | • The most feasible option for the climate change adaptation is being looked at based on its own merits to achieve a sustainable solution. For example, at one of the project site, Riviere des Galets, the option of relocation (long term measure) of the vulnerable communities exposed to storm surge had also been explored in consultation with the local community. However, a rock revetment with parapet wall, and landscaping works (short term measure) is being implemented under the project to protect the coastal communities in the meantime. • Regular stakeholders meetings and sensitisation are held under the project to reduce conflicting issues amongst the local community/fishers/NGO's/Government/Private sector and the local authorities (degree: low) | • Frequent dialogue with programme partners on reinforcement of principles of climate change management and appropriate adaptation measures has been taken. • Regular stakeholders meetings and sensitisation are held under the project to reduce conflicting issues amongst the local community/fishers/NGO's/Government/Private sector and the local authorities • To date, sensitisation campaigns have been conducted using a mobile education unit and some 15000 people have been sensitised. • Consultative meetings have been held with local community/fishers/NGO's/Government/Private sector/hotel operators/beach hawkers and the local authorities • A grievance mechanism to consider any possible conflicts and public perception on all our sites (Mon Choisy & Riviere des Galets) •A constant public relation is also being conducted with the target group on the 3 sites to inform the progress and the objectives to be met in the context of the AF Project implementation
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The bid prices substantially higher than the amounts earmarked in the budget in the Project Document, for component 1 and component 2. (degree: high) | • The financial offer for Component 1 (Consultancy Services for Mon Choisy & Riviere des Galets) was 275% higher • The financial offer for Component 2 (Consultancy Services for Early Warning System) was higher than 400% than the budgeted amount in the AF Project document. (degree: moderate) | • Following the 1st round of procurement, the scope of the works was reviewed to focus on the key deliverables and implementation within the project budget. A budget revision and extension of time was approved by the AFB and bids received for construction works are now within the revised budget.
The process of land availability and acquisition for the construction of the Refuge Centre at Quatre Soeurs under the Component 1 was an issue. (degree: high) | This is no longer a risk as land has already been acquired and the Refuge Centre constructed successfully (degree: low) | • The land was identified by the Technical Committee for acquisition under Government Funds • Land acquisition procedures were completed by the Ministry of Housing and Lands in June 2015 • The land was vested to the Ministry for construction of the Refuge Centre which is now completed.
Poor Performance of Consultant | Poor performance of consultant i.r.t. to the consultancy services for coastal adaptation measures at Mon Choisy & Riviere des Galets under Outcome 1 | The contract for the consultant had been foreshortened and a new consultant hired for supervision of works at Mon Choisy Beach and Riviere des Galets Project.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The Mon Choisy Project bid document which constitute installation of an artificial reef made of precast reef units (first time in Mauritius) had been reviewed several times by the consultant and technical committee. The bids were launched by the Ministry following several reviews by the Central Procurement Board (CPB). The bid evaluation was also conducted by the CPB and successfully completed during the reporting period. The contract for works at Mon Choisy (USD 2.7 M) has been awarded and works will be executed in the next reporting period. There is a major risk that project will not be completed at the closing date of 30 August 2019 due the following reasons: a. The project physical implementation on site will start as from November 18 and the project implementation period is 1 year b. The cyclonic season in Mauritius starts from November 18 to end in May 19 which represent a risk for the project as coastal rehabilitation works will have to be stopped if Mauritius is affected by cyclone c. The reef mold for producing the artificial reef units will be imported from Australia by the local contractor. The shipping time constitute a risk in case reef molds do not arrive in Mauritius on time. PROPOSAL It is proposed that the project be extented for a further period of 6 months to allow completion of the Mon Choisy Project which constitue a major part in the project budget

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/ Coordinator: | Detailed technical assessment of each site-Completed Technical design of coastal protection measures at each of three sites-Completed (Output 1.1 , 1.2, 1.4, 1.5, 1.6) were merged into one consultancy for Mon Choisy & Riviere des Galets-Completed |  | Quatre Soeurs • Land acquisition procedures for Quatre Soeurs-Completed • Procurement for consultancy services for the design, preparation of tender documents and supervision of works for the construction of Refuge Centre, drainage system and Ancillary works at Quatre Soeurs-Completed • Invitation to Bid for the construction of Refuge Centre, drainage system and Ancillary works at Quatre Soeurs-Completed • Bid Evaluation for works for the construction of Refuge Centre, drainage system and Ancillary works at Quatre Soeurs-Completed Mon Choisy and Rivière des Galets • Procurement of consultancy services for the preparation of feasibility studies, EIA Reports, Design, Preparation of Bid Documents and Supervision of Works for the implementation of coastal adaptation measures at Mon Choisy and Rivière des Galets, Mauritius-Completed Mangroves Plantation Project-completed |  | COMPONENT 1 STATUS Construction of a Refuge Centre at Quatre Soeurs •The construction of Refuge Centre at Quatre Soeurs comprised of highly technical works components including piling works. The constuction of Refuge Centre has been successfully completed now and the buidlign handed over to the Ministry in June 2018. Land Acquisition by Goverment of Mauritius • The acquisition of land of an extent of 3A04P by the Government of Mauritius for construction of the Refuge Centre at Quatre Soeurs was completed in June 2015 and the land vested to the Ministry. Procurement of Consultancy Services for Quatre Soeurs • The RFP document for Consultancy Services for Design, Preparation of Tender Document and Supervision of Works for Construction of the Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs was launched in 16 February 2015. • The opening of bids was on 25 March 2015 and a Prebid Conference was held on 10 March 2015 • A Bid Evaluation Committee was constituted by the Departmental Bid Committee of the Ministry • The contract (local) for consultancy services was awarded on 06 July 2015 to the Consortium: Mega Design Ltd, SEE Engineering Consultants, Steget, Chuttur & Partners Ltd for the price of USD 137,258 (incl. of VAT). | S
S
[5 empty] | Reports submitted by the consultant a) Inception Workshop report b) Detailed Technical Assessment including site survey report c) Geotechnical investigation report d) Environmental Impact Assessment Report e) Building maintenance Plan f) Evacuation plan for vulnerable communities exposed to storm surges and coastal inundation at Quatre Soeurs g) The architectural design of Refuge Centre and detailed design reports for works including detailed cost estimates h) Bidding document for the construction works of the Refuge Centre i) Progress Reports The supervision of works was successfully completed by the consultants during execution of works. | S
S
[5 empty] | Procurement of contractor for Works at Quatre Soeurs • A Prebid Conference was held on 13 April 2016 at the seat of the Ministry. • A site visit was thereafter conducted at the project site in the presence of representatives from the UNDP, AF Project team and the bidders. The potential bidders took cognizance of the site on that day. Closing of bids • The deadline for submission of bids for the Construction of the Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs was on 4 May 2016. • 5 bids were received at the opening of bids on 4 May 2016 • A Bid Evaluation Committee was constituted by the Departmental Bid Committee of this Ministry to conduct the bid evaluation | S
[5 empty] | Award of Contract for works • The bid evaluation was completed and the contract for works for the Construction of the Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs was awarded on 24 June 2016 to the best evaluated bidder 'Best Construct Co. ltd' for a price of MUR 43,563,951.62, inclusive of VAT. • The contract for construction works was signed on 22 July 2016. | S
[5 empty] | Mon Choisy & Riviere des Galets Site Procurement of Consultancy Services for Mon Choisy & Riviere des Galets Project • The Contract for Consultancy Services for Coastal Adaptation Measures at Mon Choisy and Riviere des Galets was awarded to Indufor Oy in consortium with eCoast and C.L.A.M.S ltd for a contract amount of USD 817,850 excluding VAT in September 2014 under a UNDP Contract. Extension of Contract for Indufor Oy w.r.t. Mon Choisy & Riviere des Galets (UNDP Contract) • The contract for ‘Indufor Oy’ with UNDP expired in February 2017. A no cost extension of contract up to February 2018 was approved by the UNDP CO to allow the consultant to complete the bid document for Part II which comprised of ecosystem based adaptation measures including establishment of a VMCA, Seagrass Restoration and Installation of Fixed Mooring buoys. The amendment to the original contract lapsed on 14 February 2018. | S
S
[5 empty] | The UNDP CO further extended the contract up to 14 June 2018 to allow the consultant to complete the remaining deliverable. As per the contract, the design liability for all the works will remain with Indufor Oy. Stages Completed by Indufor Oy (i) Inception workshop (ii) Detailed technical assessment (iii) Options for Coastal Adaptation Measures including Cost Benefit Analysis (iv) Feasibility Study (v) Baseline for a managed retreat project at Riviere des Galets (vi) An Economic Valuation and Cost Benefit Analysis of Adaptation and Enhanced Ecosystem Resilience for Mon Choisy Beach (vii) Design for both sites (viii) Bid Document for Works for both sites (Mon Choisy & Riviere des Galets) • Several discussions, Working Sessions (detailed below) and design review activities by (Ministry & UNDP) were held before the final design and bid document were issued. | S
S
[5 empty] | Riviere des Galets • The consultant submitted the bidding document for Construction of Rock Revetment Structure with Parapet Wall at Rivière Des Galets on 06 October 2016 Scope of Works • Construction of a rock revetment of an approximate Length of 430 metres with parapet wall in the coastal frontage at Riviere des Galets. The construction works also included: - Demolition of existing gabion revetment - Construction of the rock revetment – transport and delivery of large (up to 2-ton) basalt boulders - Fabrication and installation of a concrete parapet wave-return wall from a combination of pre-cast and cast in place reinforced concrete elements - Installation of concrete pavement/walkway landward of the structure - Installation of specified lighting - Provision of finishing landscaping - Construction of a Parapet extension as per the design specifications near the cemetery boundary going westbound over around 37.5 m Bidding Process • The bid document was approved for launching at the Technical Committee held on 25 October 2016. • The bid document was launched on 09 December 2016 on an Open National Bidding Mode of Procurement • The closing date for submission of bids was 16 January 2016 at 13 30 Hrs (local time). • A Pre-bid Meeting was held under the chair of the Ministry on 20 December 2016. • 3 bidders attended the meeting. A site visit was then convened at the project site at Riviere des Galets • 3 bids were received at the closing date on 16 January 2017. • A Bid Evaluation Committee (BEC) was constituted by the Ministry and the bid evaluation started on 31 January 2017. • During the bid evaluation some clarifications were sought by the BEC from the Departmental Bid Committee on the Sections ‘Instructions to Bidders’ and ‘Bid Submission Forms’. • A letter was addressed to the Procurement Policy Office (PPO) by the Ministry on 17 March 2017 for advice. • The letter of reply from the PPO was received on 30 March 2017. • The bid evaluation was successfully completed Award of Contract for works (Works Riviere des Galets) •The contract for construction works was awarded to ‘Super Builders Co Ltd’ on 03 May 2017 for the contract price of Rs 28,977,556.25 incl. of VAT | S
S
S
S
[5 empty] | Consultancy Services for Supervision of Coastal Protection and Landscaping Works at Riviere des Galets (Local) Bidding Process • The bid was launched on 01 December 2016 and the closing date set for 04 January 2017. • Following a request from consultants for an extension of time due to the end of year closure, the closing date for submission of bids was postponed for 16 January 2017. • A request for clarifications was received from the consultants on 19 December 2016. • The reply was submitted by the project team to the DBC on 22 December 2016. • An addendum was issued by the Ministry on 13 January 2017 • The closing date for submission of bids was further extended by the Ministry to 30 January 2017 at 13 30 Hrs (local time). • 5 bids received were received at the closing date on 30 January 2017. • A Bid Evaluation Committee was constituted by the Ministry and the bid evaluation started on 27 February 2017. • The contract for Consultancy Services for Supervision of Coastal Protection and Landscaping Works at Riviere des Galet was awarded to Luxconsult (Mtius) Ltd on 20 April 2017 for the contract price of Rs 2,510,000.00 incl of VAT. kick off meeting with the consultants • A kick off meeting was held on the 12th May 2017 under the chair of the Ministry with the consultant ‘Luxconsult (Mtius) Ltd’. • A copy of the: (i) Bid submitted by Super Builders Co Ltd; (ii) Bid Drawings; (iii) Company Profile of Super Builders Co Ltd; and (iv) Letter of Award issued to Super Builders Co Ltd was handed over to the consultant. | S
S
S
[5 empty] | Mon Choisy Scope of Works • Construction of artificial reef using pre-cast reef units-900 to 1000 Units • Beach Re-profiling-200 trees and stump removal • Beach Embellishment Works & planting of sand binding plants • Rock Groyne removal 250 m2 Bidding Process •The bid document for Rehabilitation of Mon Choisy Public Beach and Installation of an Artificial Reef was launched by the Ministry on 16 March 2018 • The closing date for submission of bid was on 09 May 2018 at 13.30 Hrs (Local Time) • A Pre-bid Meeting was held under the chair of the Ministry on 12 April 2018 with the prospective bidders • The reply to the clarifications during the Pre-bid Meeting was posted on the website of the Central Procurement Board (CPB) • 3 bids were received at the opening of bids held on 09 May 2018 as follows: i. Onix (119 M excl. of VAT), ii. PADCO (85 M excl. of VAT), iii. JV Sotravic/Subcon (80 M excl. of VAT) Bid evaluation committee • An independent bid evaluation committee was set under the chair of the Central Procurement Board (Government) and comprised of 1 member and 1 Secretary from this Ministry. • The bid evaluation was completed during the reporting period and award of contract expected around mid of August 2018. | S
S
S
[5 empty] | Launching of Request for Proposals for Supervision of works ‘Rehabilitation of Mon Choisy Public beach and installation of artificial reef by UNDP • The above RFP was launched by the UNDP CO on 31 May 2018 • The closing date for submission of bid was on 21 June 2018 at 15 Hrs. • A Pre-proposal conference was held on 08 June 2018 at 15 Hrs at the UNDP CO • 3 bidders attended the pre-proposal conference. • 2 bids were received at the opening of bids on 21 June 2018 as follows; (i) Desai & Associates Ltd, (ii) JV Axis Ingenieria SA de CV and HOV Environment Solutions Pvt Ltd Bid Evaluation Committee (UNDP) • A bid evaluation committee was set up under the chair of the UNDP CO • The bid evaluation was completed during the reporting period and report submitted to RACP for approval | S
S
| Successful construction of physical interventions at each of the three sites |  | (i) Quatre Soeurs-Construction Completed |  | Construction of a Refuge Centre at Quatre Soeurs • The constuction of Refuge Centre has been successfully completed and the building handed over to the Ministry on 08 June 2018. Key Features of the Refuge Centre include; Early Warning System, Standby Generator, Fire Alarm System, Public Address System, Demand Controlled Ventilation via CO2 sensors, LED Luminaires and Accessories, Rainwater Harvesting System, Natural light, Enlarged access roads, improved turning radius of roads and provision of footpath Procurement of furnishing Items for the Refuge Centre include; Foldable beds, Cot for babies, Disposal covers/blankets, Separators/partitioning mounted on wheels-movable type, Foldable tables with 8 foldable chairs, First Aid Kits, Disposable bins, Portable AM/FM Radio Sets, Digital information display screens Site Meetings 36 Site Meetings had been held . The site meetings were held to discuss: (i) The methodology of work; (ii) The Programme of Work ;( iii) The Environmental Monitoring Plan; (iv) The Rock Tests as specified in the BOQ; and (v) The Procurement and Approval of Material. The meetings aimed at ensuring that project is completed in compliance to the contract agreement. Discussions during sites meeting were substantiated by minutes and approved thereafter. | S
[5 empty] | The contract for construction works was awarded to ‘Super Builders Co Ltd’ on 03 May 2017 for the contract price of Rs 28,977,556.25 incl. of VAT Progress of Works • Construction of Revetment Toe- 80% Completed • Construction of Rock Berm – 100% Completed (430 m ) • Construction of Rock Revetment- 400 m Completed out of 430 m • Stacking and sorting of Rock on stack yard – Ongoing • Vehicular Access- Completed • Underpinning works : Completed (26m) • Parapet wall-300 m of 2.2 m high wall out of 400 m Site Meetings •33 Site Meetings held to date Project Completion • The construction works are expected to completed by end of November 2018. | S
S
|  |  | (ii) Riviere des Galets-Construction Ongoing (80% Completion) |  | Award of Contract for works at Riviere des Galets •The contract for construction works was awarded to ‘Super Builders Co Ltd’ on 03 May 2017 for the contract price of Rs 28,977,556.25 incl. of VAT Scope of Works • Construction of a rock revetment of an approximate Length of 430 metres with parapet wall in the coastal frontage at Riviere des Galets. The construction works also included: - Demolition of existing gabion revetment - Construction of the rock revetment – transport and delivery of large (up to 2-ton) basalt boulders - Fabrication and installation of a concrete parapet wave-return wall from a combination of pre-cast and cast in place reinforced concrete elements - Installation of concrete pavement/walkway landward of the structure - Installation of specified lighting - Provision of finishing landscaping - Construction of a Parapet extension as per the design specifications near the cemetery boundary going westbound over around 37.5 m 33 Site Meetings have been held to date at Riviere des Galets under the chair of the consultants: The site meetings are held to discuss: (i) The methodology of work; (ii) The Programme of Work ;( iii) The Environmental Monitoring Plan; (iv) The Rock Tests as specified in the BOQ; and (v) The Procurement and Approval of Material. The meetings aimed at ensuring that project is completed in compliance to the contract agreement. Discussions during sites meeting are substantiated by minutes and approved thereafter. The progress of works on site was as follows: • Construction of Rock Revetment-80 % Completion (out of 430 Metres) • Construction of rock berm-100% Completed • Construction of vehicular access-100% Completed • Construction of Parapet Wall-80% Completed (out of 280 Metres) Completion of Works • Works on site is expected to be completed in the next reporting period by October 2018. | S
S
S
S
|  |  | (iii) Mon Choisy-Start of Works-September 2018 (Procurement of Works completed) |  | Scope of Works to be implemented at Mon Choisy beach • Construction of artificial reef using pre-cast reef units-900 to 1000 Units • Beach Re-profiling-200 trees and stump removal • Beach Embellishment Works & planting of sand binding plants • Rock Groyne removal 250 m2 Bidding Process • The following documents were submitted to the Central Procurement Board (CPB) for vetting and approval prior to launching: (i) Checklist for vetting of bidding documents (ii) Procurement Plan (iii) Detailed Cost Estimate of the project (iv) Soft and hard copy of the bidding document (v) Draft invitation notice. Meeting held at Central Procurement Board • A meeting was held on 04 August 2017 under the chair of the CPB in view of finalising the bid document for Mon Choisy. The meeting was attended by the project team and the local engineer Mr J. Desai. • The CPB recommended to go for an ‘International Bidding’ in lieu of a ‘National Bidding’. • Further amendments to the bid document were received from the CPB on 17 and 23 August 2017. • The Priced Bill of Quantities was received from Mr J. Desai on 23 August 2017. • The amended final bid document was received from Mr J. Desai on 31 August 2017 and submitted to the CPB on 04 September 2017. Approval of the Central Procurement Board • The bid document for Mon Choisy was approved by the CPB for launching on 05 September 2017. • The closing date was set by the CPB was on 08 November 2017 at 13 30 Hrs. • The Ministry was advised to make immediate arrangements to advertise the Invitation for Bids in the press and upload the bidding documents on the website of the Procurement Policy Office. • As at 30 September 2017, the bidding documents had not been launched by the Ministry due to administrative bottlenecks •The bid document for Rehabilitation of Mon Choisy Public Beach and Installation of an Artificial Reef was launched by the Ministry on 16 March 2018 • The closing date for submission of bid was set on 09 May 2018 at 13.30 Hrs (Local Time) • 3 bids were received at the opening of bids held on 09 May 2018 as follows: i. Onix (119 M excl. of VAT), ii. PADCO (85 M excl. of VAT), iii. JV Sotravic/Subcon (80 M excl. of VAT) Bid evaluation committee under chair of Central Procurement Board • An independent bid evaluation committee was set under the chair of the Central Procurement Board (Government) and comprised of 1 member and 1 Secretary from this Ministry. • The bid evaluation was completed during the reporting period Issue of Letter of Acceptance • The letter of acceptance for the contract amount of Rs 79,746,389, excl. VAT was issued by the Ministry to the JV Sotravic/Sub-Con on 10 August 2018. • Construction works on site is expected to start around end of September 2018 | S
S
S
S
S
S
| Assessment of the current sea state monitoring systems (Mauritius Meteorological Services and Mauritius Oceanography Institute) and definition of required critical parameters and operational requirements for an early warning system-Completed EWS installed and implemented -Completed |  | Procurement of consultancy Services for the implementation of an Early Warning System for incoming storm surge in the Republic of Mauritius-Completed The Early Warning System for incoming Storm Surge for the Republic of Mauritius has been installed at the Mauritius Meteorological Services and fully operational-Completed Phase II-Extension of the existing EWS for storm and tidal surge to include wave and swell and the coastal inundation component Procurement of Consultancy Services for extension of EWS (Phase II)-Completed Implementation of Phase II-Extension of the existing EWS for storm and tidal surge to include wave and swell and the coastal inundation component in the AF Project Extension Period approved by the AFB (Aug 18-Aug 19)-Ongoing |  | Component 2: Early Warning System for Storm Surge for the Republic of Mauritius Memorandum of Understanding (local) • A Memorandum of Understanding (MoU) was signed between the MESDDBM and Mauritius Meteorological Services (MMS) for joint implementation of the project component on 13 March 2014. Memorandum of Understanding (International) • With a view to ensuring the sustainability of the project in relation to capacity building, technical support and technology transfer for a more effective use of the numerical model of the EWS, a MoU between this Ministry through the Adaptation Fund, Stichting Deltares and UNESCO- IHE was signed on 20 January 2016 in the Kingdom of Netherlands in the presence of the Hon Minister R. Dayal and the Project Manager. Purpose • To secure technical assistance in terms of research and capacity building for coastal zone adaptation and operation of the Early Warning System for Storm and Tidal Surge. • The Government of Mauritius (Cabinet office) approved the MoU signed between this Ministry, Stichting Deltares and UNESCO IHE. The main areas of cooperation under the MoU are listed below: • Facilitate scientific and research exchange of scientists, research scholars and specialists, etc. for the purpose of research, training, consultation and exchange of expertise • Ensure Continuous Professional Development for staff of the Mauritius Meteorological Services • Training and capacity building in the field of disaster risk reduction management, coastal engineering and adaptation to climate change • Exchange of scientific and technical information and documentation • Organization of bilateral scientific and technical seminars/ workshops/ conferences and training courses on problems of interest to both countries. • Other forms of scientific and technological cooperation as may be mutually agreed upon by the parties within the scope of this MoU Consultancy Services awarded to Stichting Deltares • The consultancy services for implementation of the Early Warning System for incoming Storm Surge in the Republic of Mauritius was awarded to Stitching Deltares, a leading independent research and internationally operating specialist consultancy institute. Training on operation of EWS for Storm Surge (local & overseas) • In July 2015, hands-on training on Delft-FEWS components and Mauritius EWS was delivered to officials from the MMS, Mauritius Oceanography Institute, NDRRMC. The main goal of the training sessions was to make the participants more comfortable dealing with the Delft-FEWS Early Warning System. • Some 20 participants from the MMS, Mauritius Oceanography Institute, National Disaster Risk Reduction Management Centre, Ministry of Housing and Lands (Hydrographic unit) and the project team received training on the operation of the EWS and Delft FEWS and Delft 3D model Training Overseas in The Netherlands • 3 officials (1 from the National Disaster Risk Reduction Management Centre, 1 from the AF Project team and 1 from MMS received a 2 weeks' training course in The Netherlands from 24 August to 05 September 2015. • The EWS has been implemented and is already operational at the Mauritius Meteorological Services (MMS). Phase II-Extension of the existing EWS for storm and tidal surge to include wave and swell and the coastal inundation component Funding • In view of budget savings under the Project, the Phase II-Extension of the existing EWS for storm and tidal surge to include wave and swell and the coastal inundation component was approved by the AFB for implementation during the extension period (Aug 18-Aug 19) Objective • To enable the present EWS to issue better and timely warnings, such that coastal communities in the Republic of Mauritius including Rodrigues and Outer Islands are able to evacuate safely in cases of high waves and swells. Procurement Process • The procurement process was completed by the Mauritius Meteorological Services and contract awarded to Deltares from The Netherlands for a contract amount of EUR 123,000. The implementation process (Extension of EWS) will comprise of the following activities: • Import and Display of NOAA Global WW3 Model • Implementation of Southern Regional Delft-3D Wave Model • Implementation of Detailed Delft-3D WAVE Models • Include Wave Forecast in EWS Reports • Visit by EWS Expert in Mauritius • Support and Maintenance • Wave Modelling for Agalega Island • Flood Forecast for Mauritius, Rodrigues and Agalega Island • Advice on observation locations for forecast validation | S
S
S
S
S
S
S
S
| Handbook on Coastal Adaptation” packaged as training modules for coastal communities, relevant Government agencies, and private sector stakeholders-Completed |  | Handbook on Coastal Adaptation” packaged as training modules for coastal communities, relevant Government agencies, and private sector stakeholders designed and developed-Completed |  | Besides the output target 3.1, 3.2, 3.3 and taking into consideration the recommendation of the mid-term review, 4 Training Manuals hereunder listed have been produced: • 1 Handbook entitled ‘Training Manual for Coastal Protection Works’-Completed • 1 Handbook entitled ‘Training Manual on Coastal and Marine Environment for Engineers’-Completed • 1 Handbook on 'Cost Benefit Analysis for Coastal Management and Adaptation Options to Climate Change'-Completed • 1 Handbook on Integrated Coastal Zone Management-Completed | S
| Short course on Coastal Engineering designed and delivered-Completed |  | Short course on Coastal Engineering designed and delivered-Completed |  | 9 Short Courses on Coastal Engineering/Coastal and Marine Environment/ICZM/Disaster Risk Reduction/Open Geospatial tools were design and delivered in Mauritius & Rodrigues. 337 Participants (70% Male:30% Female) had followed the underlisted courses and received a Certificate of Participation.: 1. Short Course on Coastal and Marine Environment for Engineers (CMEE) in Mauritius 2. Short Course on Coastal and Marine Environment for Engineers (CMEE) in Rodrigues 3. Short Course on Coastal Engineering (Specialisation 1) Mauritius 4. Short Course on Coastal Engineering (Specialisation 2) Design of Coastal Adaptation/ Protection Structures including a case study for Mon Choisy (Mauritius) 5. Short Course on Ocean Data Collection and Analysis (Mauritius) 6. Short Course on Climate Change and Coastal Zone Management (Mauritius) 7. Short Course on Open Geospatial tools 8. Short Course on Disaster Risk Reduction 9. Short Course on ICZM | S
S
| Specialized course on Cost-Benefit Analysis of coastal adaptation measures designed and delivered-Completed |  | Specialized course on Cost-Benefit Analysis of coastal adaptation measures designed and delivered-Completed |  | 4 Short Courses on Cost Benefit Analysis for Coastal Adaptation Measures delivered in Mauritius and Rodrigues. 157 Participants (70% Male:30% Female) had followed the underlisted courses and received a Certificate of Participation.: 1. Short Course on Cost and Benefit Analysis of Coastal Adaptation Measures 2. Short Course on Cost Benefit Analysis/Climate Change Economics 3. Short Course on Cost and Benefit Analysis of Coastal Management and Adaptation Options to Climate Change (Rodrigues) 4. Short Course on Cost Benefit Analysis Applied to Climate Change Initiatives The Collaborations of the following universities/institutions were secured for delivering of the short courses: • Worley Parsons of South Africa • Indian Institute of Technology Madras, India • University of Western Australia • Global Water Partnership Southern Africa and the University of Pretoria • Centre of Environmental Economics and Policy in Africa (CEEPA) South Africa • University of Southampton, UK • The University of Mauritius • Boomerang Geospatial • TACSYM LTD training Specialist | S
S
| A National Coastal Zone Adaptation that addresses all perceived climate change risks in the coastal zone of ROM over at least the next 20 years, with recommendations for supporting policies and regulations |  | The Final National Coastal Zone Adaptation Strategy Report, Report on required structure and process for “clearinghouse” that oversee and regulate climate change issues in the coastal zone of ROM and Recommendation for new economic instruments to fund climate change related projects comleted by August 2018 Output 4.1, 4.2, 4.3, 4.4 merged under one consultancy for Development of a National Coastal Zone Adaptation Strategy for the Republic of Mauritius |  | Award of Contract The contract for consultancy services for the preparation of National coastal zone adaptation strategy for the Republic has been awarded to ‘AGRER S.A.-N.V.’ from Belgium for a contract amount of Rs 5,752,300, inclusive of VAT on 6 February 2017. Objective The objective is to prepare a National Coastal Zone Adaptation Strategy for the Republic of Mauritius (ROM) that addresses all perceived climate change risks in the coastal zone of Mauritius and Rodrigues to promote and enhance resilience measures. Reports completed by the Consultant in line with the contract agreement: • Final inception workshop report including work plan was submitted on 27 March 2017 • Final Report on review relevant strategies, policies, laws, regulations and projects pertaining to the coastal zone in ROM was submitted on 16 June 2016 • Final Report on options for adaptation policies and measures, and vulnerability assessment result and map that identifies the most vulnerable coastal areas and systems with development capacity limit was submitted on 7 September 2017 • Final Consultation report was submitted in November 2017 • Final Report on National Coastal Zone Adaptation Strategy that addresses all perceived climate change risks in the coastal zone of ROM along with recommendations for supporting policies and regulations, best technical and institutional adaptation practices and new economic instruments, including Final EIA Guidelines, and training report, including Coastal Vulnerability Index Map were submitted in May 2018. Workshops Completed • Inception Workshop 2 March 2017 • Options Workshop 23 June 2017 (Mauritius) • Options Workshop 28 June 2017 (Rodrigues) • National Coastal Zone Adaptation Workshop 10 October 2017 EIA Training (Mission visit in September 2018) As per the scope of services, the consultants from Agrer is expected to conduct a 2 day training addressing issues with respect to the EIA procedures and outcomes in September 2018. Way Forward The EIA training is being planned in consultation with the Ministry and consultants to be held in the next reporting period. | S
| A set of recommendations on best technical and institutional adaptation practices suitable for the coastal zone of ROM |  |  |  |  | S
| Definition of the required structure and processes for one “clearinghouse” for climate change oversight in the coastal zone of ROM |  |  |  |  | S
| Recommendations for new economic instruments |  |  |  |  | S
| Handbook, training modules, and website content capturing best coastal adaptation practices for the Mauritius context |  | COMPLETED |  | • Handbook on integrated Coastal Zone Management for the coastal zone Mauritius-Completed • A Handbook on Coastal Adaptation for the coastal Communities-(1300 Copies Printed) | S
| Dissemination of lessons learned from the programme with coastal stakeholders in other locations in the southern Indian Ocean |  | COMPLETED |  | The project team participated in two regional conferences in collaboration with the Indian Ocean Rim Association (IORA), Global Water Partnership (GWP), and University of Mauritius in October 2015 and June 2016 where 200 participants from the region (SADC countries) were present. The salient issues, lessons learned and best practices were showcased. | S
| Interpretive signs and smallscale models of coastal processes designed and installed at each site, explaining the science of climate change and coastal processes |  | COMPLETED |  | 7 (3D) small scale ecosystem models for coral reefs, seagrass beds, mangroves and wetlands, interactive climate change models depicting the region of Mon Choisy, Riviere des Galets and SEMPA marine Park in Rodrigues island • 2 magnetic games to be used in the marine mobile education unit ‘bis lamer’ • A climate change game electronic game application that can be downloaded on androids and tablets • 2 Display Board Installed • 2 magnetic games to be used in the marine mobile education unit ‘bis lamer’ • A climate change game electronic game application that can be downloaded on androids and tablets | S
| Public awareness campaigns on climate change in the coastal zone designed and delivered |  | COMPLETED |  | Memorandum of Understanding • A MoU was signed with Reef Conservation, NGO in September 2014. • The MoU was renewed in March 2016 with Reef Conservation and Rogers Foundation Ltd (Private Sector) for joint implementation of this project. | S
| Priority ranking of vulnerable coastal sites established, to guide the order of future investment by the Government of Mauritius and the private sector |  | ONGOING |  | A Coastal Vulnerability Index Map is being developed under Component 4-Policy Mainstreaming | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | S. Boolkah (AF Project Assistant)
| Email: | boolkah2000@yahoo.co.uk
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The progress made by the project since it started was satisfactory. The AF Project has contributed to bring innovative measures in terms of climate change adaptation in the Republic of Mauritius. Early Warning System (EWS) for storm and tidal surge The implementation of the EWS for storm and tidal surge has been successfully completed and RoM is the first SIDs to own a fully automated EWS for storm and tidal surges. The system is currently operational at the Mauritius Meteorological Services (MMS) and the output thereof have integrated in the forecasting system of the MMS and is being regularly disseminated to the National Disaster Risk Reduction Management Centre (NDRRMC) for decision making for evacuation of the vulnerable communities. Eco-system based adaptation project (EBA) (Mangroves plantation) The EBA Project comprising of establishment of a natural coastal defence against storm surges was implemented under a community based project (fishers and unemployed women) and had been very successful. The Project was recognised by the UNDP as a best practice as an EBA and an excellent example of climate change adaptation that advances conservation and utilizes innovative solutions to develop economic opportunities to empower communities. The storyline could be accessed on https://undp.exposure.co/20000-mangroves-strong. The project was also awarded the first prize of the Island Bright Spot Award as part of the Global Island Partnership 2013 Solution Search out of 37 countries. This Community Based Adaptation Project was also showcased at the UN SID’s Conference in Samoa in August/September 2014 and at the COP 21 Meeting. Construction of a Refuge Centre at Quatre Soeurs The construction of a Refuge Centre at Quatre Soeurs, as stipulated in the project document was re-visited at the inception phase. The initial proposal comprised of implementation of a Refuge Centre (100 M2) in an inundation prone site with limited extent of land available for construction and limited access. The initial project was re-visited and validated at the Inception Workshop. The Government of Mauritius (GoM) acquired land of an extent of 3A04P for (USD 320,000), as in-kind contribution to the project. The Refuge Centre of an extent of 1000 M2 is now completed and is 10 folds bigger than the original project and located 25 metres above mean se level. The construction of the Refuge Centre warranted high level of technical expertise for the construction of a sub-structure. The Refuge Centre has been handed over to the Ministry on 08 June 2018 for operation and management. It is now expected to be showcased as a dedicated Refuge Centre for the RoM and an example for replication by the GoM to other vulnerable areas in the future. Training and Capacity Building Thanks to a very robust partnership (MoU) signed with the University of Mauritius, in particular the Faculty of Ocean Studies, the deliverables under Outcome 3 have been completed and is more than satisfactory with an expected high level of durability. Progress under this training component allowed to create a momentum around the project and keep the stakeholders interested and involved during project implementation. Delivery of Outcome 3 was also linked to delivery of Outcome 5 (Knowledge Management and Dissemination) and all training materials/training manuals/ and lessons learned were compiled for future diffusion at national and international levels. Policy Mainstreaming The Contract for development of a National Coastal Zone Adaptation Strategy for the Republic of Mauritius under the Component 4 (Policy Mainstreaming) had been awarded. The Review of relevant strategies, policies, laws, regulations and projects pertaining to the coastal zone in the ROM was completed. The draft final National Coastal Zone Adaptation Strategy for the Republic of Mauritius ,including a CVI map for Mauritius and Rodrigues has been received and will be validated in December 18. Coastal adaptation works at Riviere des Galets & Mon Choisy beach Despite being confronted to poor performance of design consultants for Mon Choisy & Riviere des Galets under (Outcome 1), thanks to the UNDP colloboration to address the shortcoming. The bid documents for Mon Choisy & Riviere des Galets were finalised and bid launched. The contract for Coastal Adaptation Works at Riviere des Galets and Mon Choisy had been awarded. The coastal adaptation works at Riviere des Galets have reached 80% completion and expected to be completed by November 2018. The works at Mon Choisy (USD 2.4M) is expected to start in October 2018 and expected to be completed in the extension period by September 2019.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Detailed technical assessment of each site |  | Consultancy services for the preparation of feasibility studies, Environmental Impact Assessment reports, Design, preparation of bid documents and supervision of works for the implementation of coastal adaptation measures at Mon Choisy and Riviere de Galets. Consultancy services for design, preparation of tender document and supervision of works for the construction of Refuge Centre, Drainage System and Ancillary works at Quatre Soeurs. |  | Quatre Soeurs • Technical assessment of the site, conceptual/architectural design, EIA, preparation of bid document, bid and bid evaluation are completed and contract for works awarded • Construction works completed and building handed over to Ministry on 08 June 2018. Riviere des Galets • Technical assessment of the site, Feasibility study, Cost benefit analysis, design and bid document have been completed. • Contract for works awarded • Contract for Consultancy Services for Supervision of Works awarded • Construction works started since June 2017 and reached 80% completion Mon Choisy • Technical assessment of the site, Feasibility study, Cost benefit analysis, design and bid document have been completed. • The bid document for works (beach works and installation of artificial reef) launched 16 March 2018 • Contract for Works awarded on 10 August 2018 • Start of Works at Mon Choisy-October 2018 Mangroves Plantation • 22,000 Mangroves planted and good performance in terms of gender balance. | S
Technical design of coastal protection measures at each of three sites
| Successful construction of physical interventions at each of the three sites |  | Construction of Refuge Centre at Quatre Soeurs-Completed Construction of Rock Revetment with Parapet Wall and landscaping works at Riviere des Galets-80% Completion |  |  | S
| Analysis of data and development of recommendations on how the interventions can be adjusted for other vulnerable coastal locations in ROM |  | Analysis of data and development of recommendations on how the interventions can be adjusted for other vulnerable coastal locations in ROM |  | The contract for consultancy services for Mon Choisy & Riviere des Galets included development of baseline for future work at the 2 sites. This is in line with plans to inform 21 more vulnerable sites with methodologies for analysis, modeling, and concrete recommendations for a coastal zone monitoring system. Government of Mauritius have discussed and agreed that the proposed constructions at the two sites are initial steps. The result of the adaptation works at those two sites will be monitored and the results used to implement solutions at other sites. | S
| Monitoring programme designed, to include scoping of suitable parameters, including beach width and slope; depth of adjacent lagoonal sediments; wave height, period, and run-up; direction of nearshore current |  | Monitoring programme designed, to include scoping of suitable parameters, including beach width and slope; depth of adjacent lagoonal sediments; wave height, period, and run-up; direction of nearshore current
| A targeted coastal process/weather event monitoring system in place |  | A targeted coastal process/weather event monitoring system in place
| Assessment of the current sea state monitoring systems (Mauritius Meteorological Services and Mauritius Oceanography Institute) and definition of required critical parameters and operational requirements for an early warning system. |  | Assessment of the current sea state monitoring systems and an Early Warning system-Completed |  | COMPLETED | HS
| The early warning system installed and implemented |  | The early warning system installed and implemented-Completed |  | COMPLETED
| Handbook on Coastal Adaptation” packaged as training modules for coastal communities, relevant Government agencies, and private sector stakeholders |  | Completed |  | COMPLETED | HS
| Short course on Coastal Engineering designed and delivered |  | COMPLETED 9 Short Courses completed (in total) in collaboration with the University of Mauritius. |  | COMPLETED | HS
| Specialized course on Cost-Benefit Analysis of coastal adaptation measures designed and delivered |  | COMPLETED 4 Short Courses (CBA) have already delivered before this reporting period. Preparation for another CBA course completed. |  | COMPLETED | HS
| A National Coastal Zone Adaptation that addresses all perceived climate change risks in the coastal zone of ROM over at least the next 20 years, with recommendations for supporting policies and regulations |  | • Inception workshop Report • Report on Review of Strategies, Policies Consultation Workshop Reports (Mauritius & Rodrigues) • Report on Options for Adaptation Policies • EIA Guidelines • Draft National Coastal Zone Adaptation Strategy |  | Inception workshop Report-COMPLETED Report on Review of Strategies, Policies-COMPLETED Consultation Workshop Reports (Mauritius & Rodrigues)-COMPLETED Report on Options for Adaptation Policies-COMPLETED EIA Guidelines-COMPLETED Draft Final National Coastal Zone Adaptation Strategy including CVI Maps-COMPLETED | s
A set of recommendations on best technical and institutional adaptation practices suitable for the coastal zone of ROM.
Definition of the required structure and processes for one “clearinghouse” or climate change oversight in the coastal zone of ROM
Recommendations for new economic instruments
| Handbook, training modules, and website content capturing best coastal adaptation practices for the Mauritius context |  | COMPLETED |  | COMPLETED | S
| Dissemination of lessons learned from the programme with coastal stakeholders in other locations in the southern Indian Ocean |  | COMPLETED |  | COMPLETED | S
| Interpretive signs and smallscale models of coastal processes designed and installed at each site, explaining the science of climate change and coastal processes |  | COMPLETED |  | COMPLETED | S
| Public awareness campaigns on climate change in the coastal zone designed and delivered |  | COMPLETED 3000 students (primary and secondary schools) and coastal communities sensitised |  | COMPLETED | S
| Priority ranking of vulnerable coastal sites established, to guide the order of future investment by the Government of Mauritius and the private sector |  | Currently being undertaken |  | ONGOING | MS
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | S. Ramchurn, Environment Programme Analyst
| Email: | satyajeet.ramchurn@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The overall rating is satisfactory because the project actions/activities planned for the current reporting period are progressing and now on track. There are several positive trend in achievement of outcomes as per the project indicators. Outcome 1 has been the main strategic focus during the reporting period. Indufor in a consortium with eCoast and CLAMS Ltd were engaged to undertake a number of studies in relation to works to be undertaken at Mon Choisy and Riviere des Galets. They conducted community survey at the site as well. However, the preparation of bid document for coastal adapation works at Mon Choisy beach which also included construction of an artificial reef made of precast reef units tooks some more time than expected. The finalisation of bid document took some 12 months time. Thereafter, the approval for launching of the bid also took some further 6 months time as it had to be vetted and approved by an independent Government body (the Central Procurement Board) for projects exceeding (USD 1.6 M). Quite good progress has been achieved with regard to the Quatre Soeurs site. The process of land availability and acquisition for the construction of the Refuge Centre at Quatre Soeurs was one of the main risks at the beginning. However, the land acquisition process was successfully completed in June 2015 by the Ministry of Housing and Lands and the necessary procedures to be able to completed the construction of the Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs were finished during this reporting period. The representatives from the community have been involved at each stage of the project. The mangroves project was completed successfully using a community-based adaptation strategy. Some 20,000 mangroves plants were planted and the project was also replicated in other areas in the Republic of Mauritius in partnership with the private sector and the local community. Outcome 2 has already been completed and the Early Warning System (EWS) is operational at the Mauritius Meteorological Services since 2015. In addition, a Memorandum of Understanding (MoU) was signed between Government of Mauritius and Stichting Deltares and UNESCO -IHE. This helped in the implementation of the EWS and further regional cooperation. Component 3 has been completed and targets achieved. Capacity development training activities have been organized including site visits to the actual project implementing sites. Events were organized with involvement of the community that have direct impact from the project works and helped their capacity development. Appropriate impact assessment of the training activities will be needed in the next reporting period. Outcome 4 had been delayed since the Request for Proposal document launched for Policy Mainstreaming in the first & second round did not receive any proposals. The present policy review and learning activities were conducted during the review of TOR. Then, the third round of invitations to bid was launched in August 2016. As suggested by MTR, baseline studies as well as strong support and understanding from line ministries are needed in implementing stage. This component achieved satisfactory progress since holding of the Inception Workshop. The National Coastal Zone Adaptation Strategy for the Republic of Mauritius, including a Coastal Vulnerability Map is expected to be completed and validated by December 2018. Outcome 5 implementation made good progress with no major bottlenecks and has been completed. A memorandum of understanding was signed with the NGO's and the private sector and the collaborationproduced good results. Several sensitization and awareness raising activities on climate change adaptation have been held using innovative methods (marine mobile education unit).
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1 | Physical infrastructure improved to withstand climate change and variability-induced stress | The beach at Mon Choisy is eroding at a rate of about 2 metres/year; Riviere des Galets is exposed to storm surges, with a failing seawall, openings in the wave overtopping wall, and an inadequate drainage system in the village; buildings in Quatre Soeurs frequently flood during high tides | 1/3 Mangroves Project completed and replicated to other coastal sites in RoM (see details at output level) Studies completed-(see details at output level) Bid document for Mon Choisy & Riviere des Galets Completed • Contract for Construction works for Quatre Soeurs awarded and construction works Completed (see details at output level)- • Contract for Construction works for Riviere des Galets awarded and construction works Ongoing (see details at output level)-80% Completed •Contract for construction works at Mon Choisy awarded | No further erosion at Mon Choisy (beach accretion of 2 metres over 3 years); no surge flooding and no further shore erosion at Riviere des Galets; and, no flooding of coastal public buildings at Quatre Soeurs. The target for numbers of beneficiaries (as per prodoc) are as follows: Mon Choisy: 1,500-2000 people; Riviere des Galets: 100-150 people; Quatre Soeurs: 1000 people.
Output 1 | Number of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) | No physical asset in place at site 1 (Mon choisy) to withstand conditions resulting from climate change | 1/1 1. Contract awarded to Indufor Oy in September 2014 for Consultancy Services in respect of Coastal Adaptation Measures at Mon Choisy & Riviere des Galets •Technical assessment of site: completed • Feasibility study : completed • Options for Coastal Adaptation including Cost/benefit analysis: completed • Design of adaptation measures: Completed • EIA Study: Completed • Independent Technical Review of Design for Mon Choisy : Completed • Bid document for Mon Choisy-Completed • Contract for Works-Awarded | Physical works properly designed and constructed at Mon choisy 1.1 Clear chronology of coastal process “events” at each site over the last 25 years and oceanographic dataset (2 months of data) for each of the three sites. Completed 1.2 Detailed technical specifications and costs for coastal protection measures at each of the three sites, carried out in a gender sensitive way. COMPLETED 1.3 Physical works properly designed and constructed at each of the three sites, including: detached offshore submerged wave attenuation structures (sloped rock mounds); planting of mangroves; and,planting of beach crest vegetation at Mon Choisy; detached offshore submerged wave attenuation structures (sloped rock mounds); planting of beach crest vegetation; and, development of a drainage scheme for the backshore at Riviere des Galets; planting of mangroves; EXPECTED START DATE FOR WORKS: OCTOBER 18 1.4 Comprehensive data on the effectiveness of the structures at each of the three sites: ONGOING 1.4 Recommendations for structural adjustments (location, design, materials, etc.) for interventions at other coastal sites in ROM: ONGOING 1.5 Monitoring design report: ONGOING 1.6 A functional monitoring system in place: ONGOING
|  | No physical asset in place at site 2 (Quatre Soeurs) to withstand conditions resulting from climate change-Completed | 1/1 1. The Contract for Consultancy Services for Design, Preparation of bid document and Supervision of Works for the Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs was awarded to the Consortium Mega Design in association with Design Forum, STEGET, SEE Engineering Consultants Co Ltd and Chuttur & Partners Ltd on 06 June 2015-COMPLETED 2. Acquisition of freehold land on higher grounds of an extent of 3A04P (1ha2,850 m2) for construction of a Refuge Centre at Quatre Soeurs was completed on 08 June 2015-COMPLETED 3. Construction Works-COMPLETED 4. Building handed over to Ministry on 08 June 2018 5. Mangrove plantation component (100% completion) with 20,000 mangroves planted and replication of the mangroves project at (6) other sites in the Republic of Mauritius-COMPLETED
|  | No physical asset in place at site 3 (Riviere des Galets) to withstand conditions resulting from climate change 80% Completion | 1. Contract awarded to Indufor Oy for Consultancy Services in respect of Coastal Adaptation Measures at Mon Choisy & Riviere des Galets •Technical assessment of site: Completed • Feasibility study : Completed • Options for Coastal Adaptation including Cost/benefit analysis: Completed • Design of adaptation measures: Completed • EIA Study: Completed • Independent Technical Review of Design for Riviere des Galets: Completed • Bid Document-Completed • Contract for Contruction Works-Awarded • Construction Works- 80% Completion | Physical works properly designed and constructed at Riviere des Galets 1.1 Clear chronology of coastal process “events” at each site over the last 25 years and oceanographic dataset (2 months of data) for each of the three sites. COMPLETED 1.2 Detailed technical specifications and costs for coastal protection measures at each of the three sites, carried out in a gender sensitive way. COMPLETED 1.3 Physical works properly designed and constructed at each of the three sites, including: detached offshore submerged wave attenuation structures (sloped rock mounds); planting of mangroves; and,planting of beach crest vegetation at Mon Choisy; detached offshore submerged wave attenuation structures (sloped rock mounds); planting of beach crest vegetation; repair and re-sloping of the seawall; sealing the wave- overtopping wall; and, development of a drainage scheme for the backshore at Riviere des Galets; planting of mangroves; re-constructing public buildings at risk on stilts at Quatre Soeurs. CONSTRUCTION WORKS ONGOING AT RIVIERE DES GALETS-80% COMPLETION REACHED 1.4 Comprehensive data on the effectiveness of the structures at each of the three sites. ONGOING 1.4 Recommendations for structural adjustments (location, design, materials, etc.) for interventions at other coastal sites in ROM. ONGOING 1.5 Monitoring design report: ONGOING 1.6 A functional monitoring system in place. ONGOING
Outcome 2 | Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | MMS provides warnings to shipping based on perceived wave climate, and cyclone warnings for the general populace, but this system does not anticipate rogue swell conditions. | Project Completed- see details at output level EWS installed and operational at the Mauritius Meteorological Services (MMS) | By 2018, more than 3,400 people in current surge zones are able to safely evacuate prior to future storm surge events (there are no people left in the surge zone when the surge hits).
Output 2 | Development of early warning systems | No existing EWS for storm surges | • Inception Workshop-COMPLETED • Assessment of existing system at the Mauritius Meteorological Services--COMPLETED • National Workshop (Client and End User’s feedbacks)-COMPLETED • Assessment Report-COMPLETED • Design of an optimal Early Warning System for incoming Storm Surge in the Republic of Mauritius-COMPLETED • Setting up of Storm Surge Model-COMPLETED • Design Report-COMPLETED • Initial set up of the Early Warning System at the Mauritius Meteorological Services-COMPLETED • Procurement of Computer Equipments-COMPLETED • Procurement of Hydrographic data from the Indian Hydrographic Office-COMPLETED • Calibration of the Early Warning System model-COMPLETED • Final System Implementation-COMPLETED • Training (Mauritius & Netherlands) & Evaluation-COMPLETED | 2.1 Assessment of the usefulness and practicality of the satellite data and the MMS system: COMPLETED 2.1 Parameters and analytical procedures for the early waning system defined: COMPLETED 2.2 Early warning system set up and running and effective during future storm events, such that no people in vulnerable coastal areas are exposed to storm surges in the future. PROJECT COMPLETED
Outcome 3 | Number and type of targeted institutions with the capacity to minimise exposure to CC. | Public agencies are unclear on their obligations regarding management of climate change effects in the coastal zone, and the private sector and general populace do not know what options there are for coastal adaptation, nor how to initiate such measures in the most practical, cost-effective manner. | Partnerships with the University of Mauritius set up. Other Collaborations • Worley Parsons • CEEPA (Centre of Environmental Economics and Policy in Africa) • University of Western Australia • India Institute of Technology, Madras, Chennai • University of Southampton, UK • TACSYM LTD training Specialist Involvement of all relevant national institutions secured. 1. Ministry of Environment, Sustainable Development, and Disaster and Beach Management 2. UNDP 3. Mauritius Oceanography Institute 4. Commission for Environment (Rodrigues Regional Assembly) 5. District Council of Pamplemousses 6. District Council of Riviere du Rempart 7. District Council of Savanne 8. Beach Authority 9. Ministry of Tourism and External Communications 10. Mauritius Meteorological Services 11. Ministry of Ocean Economy, Marine Resources, Fisheries, Shipping and Outer Island (AFRC) 12. Ministry of Housing and Lands 13. Ministry of Local Government 14. Outer Islands Development Corporation 15. Municipality of Vacoas/Phoenix 16. Road Development Authority 17. Ministry of Public Infrastructure and Land Transport (Public Infrastructure Division) 18. District Council of Grand Port 19. District Council of Black River 20. Tourism Authority 21. National Development Unit 22. National Coast Guard 23. Prime Minister’s Office 24. National Disaster Risk Reduction and Management Centre 25. Ministry of Social Integration and Economic Empowerment 26. Scene Ries Consult Ltd 27. Vyyaass Consulting Engineer Ltd 28. Luxconsult (Mtius) Ltd 29. GIBB (Mauritius) Ltd 30. Servansingh Jadav and Partners 31. University of Mauritius 32. Universite des Mascareignes 33. MACOSS (Ngos) 500 Participants trained as at 31 July 2017 | By 2018, at least 300 people, at least half of them women, trained. • 500 People (officials from Ministries/departments, local authorities and the private sector in Mauritius & Rodrigues) were trained as at 31 July 2018 & awarded a certificate of attendance (at least half of them were women)
Output 3 | No. of staff trained to respond to, and mitigate impacts of, climate-related events | No coastal engineering capacities available at national level | Collaboration with the University of Mauritius secured (MOU Signed). 13 Short Courses completed in collaboration with the University of Mauritius. Some 500 Participants trained as at 31 July 2018. 1. Short Course on Coastal and Marine Environment for Engineers delivered in September 2013- 56 Participants trained 2. Short Course on Coastal Engineering delivered in October 2013- 54 Participants trained in the field of Coastal Engineering 3. Short Course on Cost and Benefit Analysis of Coastal Adaptation Measures delivered in December 2013- 41 Participants trained 4. Short Course on Coastal and Marine Environment for Engineers replicated in Rodrigues Islands in July 2014- 28 participants trained in Rodrigues Islands 5. Short Course on Coastal Adaptation Structures (soft measures) including a case study of Mon Choisy delivered in August 2014- 41 Participants trained. 6. Short Course on Cost Benefit Analysis/Climate Change Economics delivered in September 2014- 38 Participants trained 7. Short Course on Ocean Data Collection and Analysis delivered in January 2015- 29 Participants trained 8. Short Course on Climate Change and Coastal Zone Management delivered in June 2015- 33 participants trained 9. Short Course on Cost and Benefit Analysis of Coastal Management and Adaptation Options to Climate Change delivered in Rodrigues Islands delivered in May 2015- 42 Participants trained in Rodrigues Island 10. Short Course on Open Geospatial tools delivered in September 2015- 25 Participants trained 11. Short Course on Disaster Risk Reduction delivered in January 2016- 36 Participants trained 12. Short Course on Integrated Coastal Zone Management delivered in January-February 2016- 35 Participants trained 13. Short Course on Cost Benefit Analysis Applied to Climate Change Initiatives-36 Participants trained | Coastal engineering short course designed and delivered (2x); at least 40 trainees certified. COMPLETED 3.1 Handbook complete, fully relevant to Mauritius coastal context, and used for coastal stakeholder and practitioner training twice per year over three years (at least 300 people, at least half of them women, formally trained). COMPLETED 4 Handbooks COMPLETED 3.2 Coastal engineering short course designed and delivered (2x); at least 40 trainees certified. 337 Engineers and technical staff (both from public and private sector) in Mauritius & Rodrigues trained 3.3 C-B Analysis course designed and delivered (4 x); at least 100 trainees certified.COMPLETED 157 Government officials (Mauritius & Rodrigues) trained. 1 CBA Handbook COMPLETED
Outcome 4 | Climate change priorities are integrated into national development strategy | Current policies and regulations are inconsistent with regard to management of climate change effects in the coastal zone (they do not envision the coastal zone in 2060), and do not provide clear guidance or incentives for practical implementation of adaptive measures. | • Contract for Consultancy Services-Awarded • Inception Workshop-Completed • Consultation Workshops in Mauritius & Rodrigues-Completed • Final Report on Reiew of Strategies, Policies-Completed •Final Report on Options for Adaptation Policies-Completed • Draft National Coastal Zone Adaptation Strategy-Received • Final National Coastal Zone Adaptation Strategy including CVI Maps-COMPLETED and Expected to validated by December 2018 | All relevant policies, strategies, plans, and regulations are consistent in a) having a clear vision statement for adaptation in the coastal zone; b) in recognizing climate change impacts in the coastal zone over the next 50 years; and c) in clear Government institutional responsibilities for adaptation in the coastal zone. ONGOING
Output 4 | Number, type and sector of policies introduced or adjusted to address Climate Change Risks. | National ICZM strategy does not fully integrate climate change and is not properly enforced |  | National Coastal Zone Adaptation Strategy in place which addresses all perceived climate change risks in the coastal zone over the next 20 years, with clear recommendations for appropriate policies, regulations, and guidelines for adaptation. ONGOING 4.1 National Coastal Zone Adaptation Strategy in place which addresses all perceived climate change risks in the coastal zone over the next 20 years, with clear recommendations for appropriate policies, regulations, and guidelines for adaptation. ONGOING 4.1 District Outline Schemes (all 9) and the National Tourism Development Plan recognize spatial limitations and capacity limits related to climate change risks, and provide guidance on appropriate locations and designs for infrastructure. ONGOING 4.2 A “toolbox” with the most appropriate technical, institutional regulatory, and economic instruments available for all coastal practitioners in ROM; recommendations feeding into the policy and regulatory review. ONGOING 4.3 Clear recommendations on the structure and processes of an oversight and regulatory body that addresses all climate change issues in the coastal zone with jurisdictional clarity. ONGOING 4.3 Eventual establishment of that body (whether through the ICZM Division in the Ministry or the Climate Change Division). ONGOING 4.4 Clear analysis and recommendations for design and implementation of economic instruments that will facilitate public and private sector compliance with the best coastal adaptation practices. ONGOING
Outcome 5 | Effective capturing and dissemination of lessons from the applied activities in the programme. Indicator Capturing and dissemination of lessons learned | There is no consistent awareness nor understanding of the implications of climate change in the coastal zone; households, communities, and Government organizations do not factor into their plans and activities the possible climate change effects 50 years from now. | Effective capturing and dissemination of lessons from the applied activities in the programme have been completed through the following activities: • 21 Project Steering Committee have been held till date • 26 Technical Committees held • 50 Sensitisation Campaigns held using a marine mobile education unit and approx. 25,000 people sensitized on Climate Change Adaptation • 20 Websites links and 50 Press Articles where the climate change adaptation programme activities could be accessed • 2 Memorandum of Agreement signed with Grand Sable Fishermen Association (NGOs) and Grand Sable Women Planters Farmers Entrepreneur Association (NGOs) • 7 Memorandum of Understanding signed with Mauritius Meteorological Services, University of Mauritius, Reef Conservation Mauritius (NGO), Rodrigues Regional Assembly, The Attitude Foundation (Private sector), Stichting Deltares and UNESCO-IHE (international), Rogers Foundation (private sector) • 4 Paliamentary Questions replied and submitted to the parliament • 4 Cabinet/information Papers submitted to the parliament REPORTS SHARED WITH ALL STAKEHOLDERS (Per Project Component) COMPONENT 1: Quatre Soeurs Refuge Centre • Inception workshop Report • Detailed technical assessment/Survey of site Report • Environment Impact Assessment Report • Architectural Design • Bid Document • Geo-technical investigation Report • Building maintenance • Evacuation plan • Report on landslide COMPONENT 1: Coastal Adaptation Works at Mon Choisy beach • Detailed Technical Assessment • Options for Coastal Adaptation • Cost/benefit analysis in compliance with UNDP Safeguards • Feasibility Studies • Design for Mon Choisy • Design Review • Environment Impact Assessment Report • Social Impact Assessment Report • Bid document COMPONENT 1: Coastal Adaptation Works at Riviere des Galets • Detailed Technical Assessment • Options for Coastal Adaptation including cost/benefit analysis in compliance with UNDP Safeguards • Feasibility Studies • Design of Rock Revetment with Parapet Wall • Bid Document • Progress Reports-Monthly basis COMPONENT 2: Early Warning System for incoming Storm Surge in Republic of Mauritius • Inception workshop Report • Technical assessment Report • System Design Report • Specifications for hardware/equipment • Service letter agreement-BASE Platform Project • Training materials • Completion Report • 1 Flyer on EWS for Storm Surge COMPONENT 3: Training and Capacity Building • Community Emergency Plan Guidance • Report on Disaster Risk Reduction Course Training Manuals Produced 1. Coastal and Marine Environment for Engineers 2. Coastal Engineering-Recognized by Council of Registered Profession Engineers of Mauritius 3. Cost and Benefit Analysis for Coastal Management and Adaptation Options to Climate Change in Mauritius 4. Integrated Coastal Zone Management COMPONENT 4: Policy Mainstreaming • Inception workshop Report • Report on Review of Strategies, Policies • Consultation Workshop Reports (Mauritius & Rodrigues) • Report on Options for Adaptation Policies • EIA Guidelines • Final National Coastal Zone Adaptation Strategy COMPONENT 5: Knowledge Dissemination and Management Educational Tools/materials developed •7 3D small scale ecosystem models developed for coral reefs, seagrass beds, mangroves and wetlands and 3 interactive climate change models depicting the region of Mon Choisy, Riviere des Galets and SEMPA marine Park. • 2 magnetic games to be used in the marine mobile education unit ‘bis lamer’ • A climate change game electronic game application that can be downloaded on androids and tablets | The project outputs have been completed and the status is as follows: 5.1. Handbook, training modules, and website content produced. COMPLETED 5.2 Mauritian coastal practitioners able to disseminate lessons from the programme to other countries in the southern Indian Ocean and to examine the experiences in those countries. COMPLETED 5.3 Interpretive models and signs. These sites marketed and visitor attendance recorded. COMPLETED (7 Small Scale Models developed & 2 Display Board Installed) 5.4 Relevant public awareness campaigns designed and delivered to all coastal villages in the 23% of beaches at risk in Island of Mauritius. COMPLETED-17000 People (coastal communities sensitised) 5.5 All vulnerable coastal sites in ROM mapped, scaled, and assessed for importance and degree of risk to climate change in the future. COMPLETED 5.5 Replication of coastal adaptation measures initiated, with Government of Mauritius and private sector funding (at least three sites initiated before the end of the project using other sources of funding). ONGOING

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1. The procurement of services and works have to follow Government Procurement Procedures which is lengthy and have an impact in the timeline for project execution. The procurement for works at Mon Choisy had to be undertaken by the Central Procurement Board as it exceeded USD 1.7 M (Major works Projects) and could not be underaken by the Ministry. 2. Most of the procurements had to undergo at least 2 rounds of procurement due to scarcity areas (availability of international consultants) and higher than expected prices received. 3. The land acquisition process for Quatre Soeurs by the Government was a lenghty process and took (more than 1 yr) 4. The procurement of hydrographic data which was available at the Indian Hydrographic Unit was a lenghthy process (6 months). The Early Warning System for Storm Surge could not be finalised until availability of data. 5. The design for Mon Choisy & Riviere des Galets had to undergo 2 design reviews before finalisation of the most appropriate adaptation measures, thus requiring revision of the initial EIA/SIA Report 6. The involvement and sensitisation of the community is an important factor for a successful implementation of adaptation project at the target site.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes, there were delayss in implementation. Measures taken to reduce delays 1. To reduce procurement timeframe for second round of procurement, the Government sollicited the support of the UNDP. However, for procurements above USD 1,000,000 the UNDP procurement procedures are also a lengthy process, as necessary clearances from the Regional Bureau for Africa were required at various steps. Thanks to the close liaison between the Ministry and UNDP and between UNDP CO and UNDP RBA, the actual procurement was completed in 6 month's time. 2. The design for Mon Choisy & Riviere des Galets had to undergo 2 design reviews before finalisation of the most appropriate adaptation measures. The cause for delays was the poor performance of the design consultants and loose consortium. The support of a local engineer was sought by the international consultant to finalise the bid document for Mon Choisy.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | 1. The site for Construction of a Refuge centre at Quatre Soeurs was reviewed at the Inception Phase to a more secured and accessible location to be resilient to storm surges and flooding. A suitable site of an extent of 12,850 M2 to the tune of USD 320,645 was identified at Quatre Soeurs and procured by the Government of Mauritius. This represent an in-kind contribution from the Government of Mauritius to the AF Project. 2. A budget reallocation between project components was warranted and approved by the AFB in May 2014
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | 1. The compliance of the project with Equal Opportunity Act is mandatory as per Government legal framework. Focus on Gender has been fully integrated into project activities through involvement of women CSOs and NGOs in activities. Women's association have been actively involved in implementation of coastal adaptation projects, such as: mangrove plantation and sensitisation campaigns conducted by the women associations to coastal stakeholders on importance of mangroves on the coastal eco-system. The participation of women in all consultative meetings and coastal adaptation project was assessed positively at the Mid-Term Review. 2. Out of the 494 People trained under Outcome 3 (40% were Female & 60% Male) 3. Out of the 17000 People sensitised under Outcome 5 (45% were Female & 55% Male)
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The budget allocation of the project at the project development phase for implementation of climate resilient measures need to allow for cost escallation to foresee the actual cost at the implementation phase as a buffer to allow the timelag between the project conception until the execution of the project. To ensure that the impacts of the climate change measures reach to the coastal communities, a community based approach was adopted for implementation of the mangroves project. This has involved the direct participation of the coastal communities and enhanced their livelihoods.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Yes, there is potential for replication of the Mon Choisy artificial reef project in other countries. The Adaptation Fund Project has allowed appropriate and indepth studies at the AF Project sites to develop appropriate adaptation measures. Other sites in the Coastal Zone of Republic of Mauritius face the same challenges of beach erosion. The recommended adaptation measures have a great potential to be replicated/adapted to increase climate resilience. The ecosystem adaptation project on 'mangroves plantation' gained international recognition and has aleady been replicated at six other sites in the Republic of Mauritius. The project for implementation of coastal adaptation works at Mon Choisy will consist of an innovative measure (installation of pre-cast reef units in the lagoon). This innovative measure has the potential for future replication at other project sites in Mauritius and also in other countries where the coastal zone face acute beach erosion.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | This project has allowed the introduction of a CBA to enable the appropriate choice of adaptation measures based on lifetime costing. This is a new approach that was introduced to select the most appropriate option for climate resilience projects. For the design of coastal protection works, the selected contractor was a loose consortium whereby the engineer wasn’t from the lead firm. In future, such arrangements will not be accepted where engineering works are concerned.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The mangroves project has been replicated to other vulnerable coastal areas in the Republic of Mauritius. Short Training courses have been replicated to Rodrigues island The Training on the Early Warning System for Storm Surge for the Meteorological Services staff was held at the seat of Deltares in The Netherlands
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Mangroves project The involvement of the community in project implementation through community based approach has enhanced a sense of project ownership Sensitisation Campaigns Sensitisation campaigns that have been carried out through innovative means of a mobile education unit has allowed a larger community outreach for the communities Early Warning System Implementation of EWS has allowed coastal communities to be informed on an enhanced forecasting system in the event of storm surges. Following successful implementation an extension of the EWS to include wave component is under way.
What measures are/have been put in place to ensure sustainability of the project/program results? | A Memorandum of Understanding has been signed with the NGO's on community based projects to allow programmes to be continued in future based on the current lessons learnt. The handing over of project to Government authorities for running and maintenance in the long term to ensure project sustainability. The operation and staffing of the Refuge Centre in view of sustainability of the project will be catered under the Government Budget.
What measures are being/could have been put in place to improve project/program results? | Project results on increasing resilience of the coastal communities at Quatre Soeurs increased through the land acquisition on higher grounds as opposed to the initial site which was on lower ground. On this particular output, besides the setting up of the Refuge Centre, alternative routes are also being identified and secured to allow mass evacuation in event of storm surge and calamities The installation of an artificial reef made up of pre-cast reef units will be implemented first time in Mauritius and constitute a technology transfer. This may be as well be used as a showcase.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Project conceived based on assessment of all existing data available from previous works conducted which subsequently feeds in the design of the adaptation measures. In the context of implementation of Early Warning System the availability of bathymetry charts were critical for validation of the model. The data was not in possession at national level and had to be procured at international level. Intervention at highest level was also required to access data retained by the Indian Authorities following survey conducted by the indian navy in the region of Mauritius.
If learning objectives have been established, have they been met? Please describe. | 4 Training courses on Cost Benefit Analysis (CBA) were delivered. The objective is to inculcate the option of having a CBA besides an Environmental Impact Assessment which is legally a mandatory requirement. Mauritius has got no local expertise in coastal engineering and this project delivered Training Courses on Coastal Engineering and this had been a unique opportunity to bring international expertise at local level. A MOU was signed with the University of Mauritius so that award courses on Coastal Engineering may be developed under the support of this project and build capacity at the University of Mauritius level for sustaining the training programme in the longer term. Two post graduate courses on (a) climate change adaptation and disaster risk management and (b) coastal engineering has been mounted with the support of this programme at the University of Mauritius to ensure sustainability of the training programme.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | The difficulty is that data is retained by various authorities (local) in their own format. In one instance, whereby the Early Warning System for storm surge was being implemented we had to request bathymetry data from the Indian Hydrographic office which took us some 6 months time. Proposal We need to have appropriate intervention at Government level to access data either through a Memorandum of Understanding. It is suggested to harmonise all coastal data and data be readily available for future design of coastal adaptation measures.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Learning objectives The Climate change impacts were not a common knowledge at the level of the coastal communities in Mauritius. With the identification of the learning objectives and development of learning materials and tools including the mobile education unit proven to disseminate the climate change issues and raise awareness among the community and therefore be better prepared to face and adapt to climate change at local level helped in achieving the outcomes of the project. A training programme was devised and training extended to practically all institutions concerned with the coastal projects to achieve the objective under outcome 3, e.g. coastal planners from local authorities were involved which build capacity in delivery with a climate change induced risk perspective

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 00062857
Implementing Entity | United Nations Development Programme (UNDP)
Type of implementing entity | MIE
Country | Mauritius
Region | Africa
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 752546 | 6350 | 746196 | Total | 740000 | 75400 | 664000 | Total | 22985 | 5485 | 17500 | Total
|  | % of female beneficiaries | 50% | 30% | 50% | % of female beneficiaries | 50% | 30% | 50% | % of female beneficiaries | 50% | 30% | 50% | % of female beneficiaries
|  | % of Youth beneficiaries | 20% | 20% | 20% | % of Youth beneficiaries | 20% | 20% | 20% | % of Youth beneficiaries | 20% | 20% | 20% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 3400 | Storm surge | 2: Partially effective | Total | 54000 | Storm surge | 4: Effective | Total | 3400 | Storm surge | 3: Moderately effective | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 2 | Coastal management | National | 2: Undertaking or updating of assessments in progress | 2 | Coastal management | National | 3: Risk and vulnterability assessments completed or updated | 2 | Coastal management | National | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 2: Monitoring and warning service | Geographical coverage | National | 3 | 2: Monitoring and warning service | Geographical coverage | National | 1 | 2: Monitoring and warning service | Geographical coverage | National |  |  | Geographical coverage
|  |  |  | Number of municipalities | 7 |  |  | Number of municipalities | 7 |  |  | Number of municipalities | 2 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 300 | Coastal management | 2: Low capacity | Total | 485 | Coastal management | 4: High capacity | Total | 258 | Coastal management | 3: Medium capacity | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 300 | 50% | Public |  | 485 | 50% | Public |  | 258 | 50% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Coastal management | 2: Low capacity | Public | National | Coastal management | 4: High capacity | Public | National | Coastal management | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 20% |  | Coastal management |  | 30% |  | Coastal management |  | 15 |  | Coastal management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 5000 | 50% | 3: Partially aware |  | 50000 | 50% | 4: Mostly aware |  | 4000 | 60% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Coastal management | National | 3: Moderately responsive (Some defined elements) |  | Coastal management | National | 4: Mostly responsive (Most defined elements) |  | Coastal management | National | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 2 | Coastal protection measures |  | Coastal management | 3 | coastal protection measures |  | Coastal management | 1 | coastal protection measures |  | Coastal management
|  | 1 | Construction of refuge centre for communities at risk |  | Disaster risk reduction | 1 | Construction of refuge centre for communities at risk |  | Disaster risk reduction | 1 | Construction of refuge centre for communities at risk |  | Disaster risk reduction
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Coastal management | biological assets | 4: Effective |  | Coastal management | biological assets | 4: Effective |  | Coastal management | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/ rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 1 | ha protected | 2: Partially effective | Mangroves | 2 | ha protected | 4: Effective | Mangroves | 1 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Coasts | 2 | km protected | 3: Moderately effective | Coasts | 2 | km protected | 4: Effective | Coasts | 1 | km protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 60 | 50% | 2: Limited improvement |  | 115 | 50% | 4: High improvement |  | 115 | 50% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 60 | 10% | From 5% to 10% | Agricultural-related | 60 | 10% | From 5% to 10% | Fishing | 60 | 10% | From 5% to 10% | Fishing
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
[6 empty] | 55 | 100% | From 30% to 40% | Agribusiness | 55 | 100% | From 30% to 40% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 1 | Natural capital | Coastal management | Community-based adaptation | 3 | Natural capital | Coastal management | Community-based adaptation | 0 | Natural capital | Coastal management | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 60 | Fishing |  | 200 | 60 | Fishing |  | 200 | 55 | Handicrafts |  | 100
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
[6 empty] | 55 | Agribusiness |  | 300 | 55 | Agribusiness |  | 300
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 2 | Coastal management | National | Environmental policy | 2 | Coastal management | National | Environmental policy | 0 | Coastal management | National | Environmental policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 3 | 1: Not enforced (No elements implemented) |  | 2: Partially effective | 3 | 4: Enforced (Most elements implemented) |  | 4: Effective | 0 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.