## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | From 01/05/2015- 30/04/2016
| Project Title: | Reducing vulnerability to climate change in North Western Rwanda through community based Adaptation
| Project Summary: | The Reducing Vulnerability to Climate Change in North West Rwanda through Community Based Adaptation (RV3CBA) Project is executed under Rwanda Natural Resources Authority (RNRA) and implemented by the Ministry of Natural Resources (MINIRENA). The main objective is to increase the adaptive capacity of natural systems and rural communities living in exposed areas of North Western Rwanda to climate change impacts. To achieve this objective, the project implementation is focusing on the following main components:  Adaptation to climate change (rainfall intensity and duration) through integrated land and water management to support climate-resilient production and post-harvest systems;  Support for the transition from exploitive farming practices to sustainable alternative off-farm livelihoods;  Capacity building of local institutions to improve understanding of climate change impacts and scale up effective adaptation strategies at the local level.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | N/RW/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Ministry of Natural Resources( MINIRENA) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Rwanda | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Rwanda | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2013-12-01
IE-AFB Agreement Signature Date: |  | 2013-11-01 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2014-06-01 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2016-06-01
| Terminal Evaluation Date: | 2018-03-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Project reports have been done on quartely and annual basis. Several articles have been published in local newspapers as well as on RV3CBA project website and other social media links. The following key documents have been prepared: Consultancy services to prepare and to generate multi-hazards adaptation and mitigation measures for long term solution to water logging of mugogo lowland and its surrounding areas; Climate change vulnerability assessment and development of local adaptation plans; Project communication strategy. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.rv3cba.rnra.rw | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | NGABONZIZA Prime | Dominican Republic
| Email: | prime0467@yahoo.fr | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | MUKARUBIBI Fatina | Equatoral Guinea
| Email: | fmukarubibi@minirena.gov.rw | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | HABIMANA Emile | Fiji
| Email: | ehabimana@minirena.gov.rw | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Dr. NKURUNZIZA Emmanuel | Georgia
| Email: | emmanuel.nkurunziza@rnra.rw | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [30/04/2016] | 5380861
Add any comments on AF Grant Funds. (word limit=200) | The planned budget for the two tranches of disbursement already received was so far executed at 78,2% (cumulative spending rate), and this rate is considered to be reasonable because even the remaining rate of 21,8% is committed to contrators and staff salaries.
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1: Community level mobilisation and climate adaptation planning. | 91526
| Output 1.2: Investment in integrated land and water management practices | 2655031
| Output 1.3: Diversification and integration of crop and livestock production systems to minimise the impact of variable rainfall on rural livelihoods (agro-sylvopastoral systems etc.). | 4112 | `
| Output 1.4 Introduction of climate-resilient crop/fodder varieties and agronomic practices (short season crops, seasonal pastures etc.). | 2754
| Output 1.5 Introduction of climate resilient post-harvest processing and storage systems for safe handling and storage of agricultural produce during extreme climate events (floods, rains). | 3250
| 2.1 Identification of viable alternative livelihood opportunities and constraints | 15704
| Output: 2.2 Development of Rural Development hubs within selected imidugudus to promote and facilitate sustainable, market-linked and diversified livelihoods | 11046
| Output 2.3 Resettlement of 200 households living in high-risk zones to Rural Development Hubs. | 2349424
| Output 2.4 Increased investment in market development (infrastructure, transport, storage, market research etc.). | 9419
| Output 2.5 Increased investment in and access to renewable energy (Biogas plants, solar etc.) for enterprise development. | 46243
| Output 3.1 Training of government technical staff on climate risk management and flood and landslide prevention measures for further scaling up. | 14249
| Output 3.2 Sharing project results and lessons learned and mainstreaming new approaches in local and national planning. | 17951.3417
| Compensation of employees | 215452.371
| Office rent and partitioning | 64765.7908
| Phone cards | 6582.9847
| Supplies and services | 15333.9623
| Other Expenses/Bank charges | 71.1297
| TOTAL NEE | 5522915.5802
FOR NIE
| Output1.1: Finance, Budget and Treasury management | 18721
| Output1.2: Project Performance Management | 20694
| Output 1.3: Information and Telecoms Support | 1693
| Output 1.4: legal support | 0
| Output 1.5: Programme Management Support | 39762
| TOTAL NIE | 80870
| TOTAL NEE+NIE | 5603785.5802
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: Community level mobilisation and climate adaptation plans developed and implemented. | 53077 | 2017-06-30
| Output 1.3: Diversification and integration of crop and livestock production systems to minimise the impact of variable rainfall on rural livelihoods (agro-sylvopastoral systems etc.). | 52251 | 2017-06-30
| Output 1.4 Introduction of climate-resilient crop/fodder varieties and agronomic practices (short season crops, seasonal pastures etc.). | 4028 | 2017-06-30
| Output 1.5 Introduction of climate resilient post-harvest processing and storage systems for safe handling and storage of agricultural produce during extreme climate events (floods, rains). | 470737 | 2017-06-30
| 2.1 Identification of viable alternative livelihood opportunities and constraints | 5227 | 2017-06-30
| Output: 2.2 Development of Rural Development hubs within selected imidugudus to promote and facilitate sustainable, market-linked and diversified livelihoods | 675659 | 2017-06-30
| Output 2.4 Increased investment in market development (infrastructure, transport, storage, market research etc.). | 450019 | 2017-06-30
| Output 2.5 Increased investment in and access to renewable energy (Biogas plants, solar etc.) for enterprise development. | 23357 | 2017-06-30
| Output 3.1 Training of government technical staff on climate risk management and flood and landslide prevention measures for further scaling up. | 37909 | 2017-06-30
| Output 3.2 Sharing project results and lessons learned and mainstreaming new approaches in local and national planning. | 28575 | 2017-06-30
| Project Execution costs | 168486 | 2017-06-30
| TOTAL NEE | 1969325
| TOTAL NIE | 150659
| Output1.1: Finance, Budget and Treasury management | 47250 | 2017-06-30
| Output1.2: Project Performance Management | 46716 | 2017-06-30
| Output 1.3: Information and Telecoms Support | 2500 | 2017-06-30
| Output 1.4: legal support | 2250 | 2017-06-30
| Output 1.4: Programme Management Support | 51943.25 | 2017-06-30
| TOTAL NEE+NIE | 2119984
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
1) Low awareness and acceptance of the need to tackle climate change among key practitioners limits the support for action on climate change within key sectors. | Low | In the first year of project implementation (2014-2015), the project has recorded tangible success especially on land and water management activities; this has led key stakeholders and population in the project area to support climate change actions who have been resisting at the beginning of the project. In addition to this, the project kept on conducting meetings, announcements and articles on radio,TV, workshops and trainings with various stakeholders on climate change issues to raise awareness.
2) District administrations lack the resources and capacity to engage fully with the project and integrate project outputs with development plans. | Low | The local government officials starting from the Mayors of Districts, Vice-Mayors, Executive secretaries of sectors, etc. are involved and committed to closely work with the project implementation unit by providing advices and support where necessary. some of the project activities are even included into the District performance contracts.
3) Climatic conditions (destructive rains and unpredictable seasons) hamper project interventions (planting etc.) and could affect adaptation measures being implemented and undermine confidence of local communities in adaptation measures promoted by the project. | Medium | The Project has constructed preventive infrastructures like bench terraces, progressive terraces, protection of river banks and permanent maintainance of Mugogo low land; and the results of these infrastructures have increased the confidence and support of local communities in adptation measures promoted by the project.
4) Limited capacity of partner organisations to deliver project outputs. | Low | The Project has conducted workshops and consultation meetings with different stakeholders in the intervention area to cope the best practices and build capacity.
5) Failure to create ownership of the project at the local level. | Low | The local leaders and community have shown their commitments in participating with the project and ensured their contribution in sustaining its activities. This was made possible by strong and continous mobilization done by the project team and community animators.
6) Price fluctuations which could a) affect the costs of implementation and lead to budgetary constraints b) affect costs and returns from enterprise development activities among project beneficiaries. | Low | Fortunately this kind of risk has not happened, but one it will happen the project will take account of fluctuations in its support functions for enterprise development.
7) Delays in the disbursement of funds, procurement and Institutional inefficiencies (lengthy approval processes etc.) delay the resulting in delayed recruitment of project staff and hence project implementation. | Medium | Delays related to disbursement of funds, procurement and Institutional inefficiencies (lengthy approval processes etc.) have been been minimised at an acceptable level.
8) High costs and insufficient supply of electricity impedes livelihood diversification (Rwanda is expensive compared to other countries in the region at $0.24/kwh compared to Kenya’s $0.15/ kWh, Uganda’s $0.17/kwh, and Tanzania’s $0.05/kwh (EDPRS 2, 2013). | Medium | The project has started to introduce other livelihood diversification source of energies.
9) Failure to adopt a holistic approach necessary for this type of project due to a lack of expertise within the project team or lead agency. | Low | The Project team is made by experienced specialists in different domains and consultations are done for technical advices. The project collaborate with other projects in the intervention area.
10) Lack of co-ordination with other climate change projects in Rwanda limits the capacity of implementing agency to learn from and build on the experiences of related projects. | Low | The PIU consults other similar projects for some activities when needed.
11) Weak capacity of coordination for concerned services in the optional choice of technical solutions and project planning. | Low | The project has experienced staff with coordination and technical skills.
12) Lack of transparency or political interference in allocation of project resources. | Low | To ensure transparency and accountability, the country has put in place financial management measures (like having the Project finance officer, the Project manager and the Chief budget manager) and IFMS (Integrated Financial Management System) for proprer funds management and accountability.
13) Lack of capacity and commitment to project outcomes and resistance to adopting the proposed measures. | Low | To avoid resistance from the project beneficiaries and other stakeholders in owning and implementating project activities, the PIU has formed climate resilient groups as mentioned in the project document ( 100 groups which means 2 groups per Cell in 8 sectors); the members of those groups are the first targeted project beneficiaries who got jobs in terracing and other activities that the project has started. The Project has also organised election of 16 community animators ( 2/sector: Gender balance has been considered) whom works closely with the Project Implementation Unit and the Project beneficiaries for information sharing and sensitization. After all, The local government is fully involved as they are the ones who knows better the attittudes and behaviors of their citizens. Therefore, all the above mentioned organs helps to avoid resistance.
14) Staff turnover in the Project Implementing Unit may hamper progress. | Low | The project has not experienced this risk, and beyond that the governement of Rwanda has initiated the staff retention policy ( work advantages and improved working environment).
15) Local district administrations are unwilling to incorporate climate adaptation into district plans and budgets. | Low | The Project team works closely with the District administrations during the implementation to ensure the local ownership and it is really working.
16) Conflicting interests among stakeholders with respect to land use (e.g. Crop Intensification Programme which is focussed on maximising agricultural production by promoting mono-cropping and the use of chemical inputs) and access to and use of natural resources hampers erosion control and other adaptation measures. | Low | The project started by raising awareness through community mobilization in the selected sites for terraces construction, where the PIU, NIE, NEE and Local leaders explained the objectives of the project to the community, the importance of terraces and use of inputs in increasing the production, and assured them to be facilitated in this process ( construction of bench and progressive terraces and provision of organic manure); it was very fortunate that the community welcomed the project's initiatives and it was realised that they were aware of most of the information as these are included into government initiatives through EDPRS and Umurenge VUP. In addition to this, the project has organs that helps in addressing conficts during its implenentation ( National and Local Steering Committees, and the technical advisory group).
17) Loss of livelihood for resettled families. | Low | The project targeted beneficiaries are the first priority to work with the project in diferrent activities such as erosion control activities, and according to what is observed on the field; people are happy and satisfied with what they get from the project as wages. The project beneficiaries already linked with SACCOs are around15,950(58 % are women). The total amount of money injected directly in beneficiaries as wages is 984,123,000Rwf. Regarding the construction of the model village, the Vulnerable families will be the priority to get employment and support.
18) Resistance to adoption of new livelihood for resettled households. | Low | Families to be resettled do not have where to live by then, so the sensitization was not difficult because they have had that they are going to get the first solution of being given a house which is a very great and important support for them. Together with the Local leaders, the PIU has explained them the importance of living into green model villages as they will have easy access to electicity, water, schools, and other necessary basic infrastructures. they have also been told about the new livelihoods rather than agriculture, and this sensitization shall continue even after having been resettled. the mitigation of this risk could not be difficult because resettlement has been a government initiative for long, and the community is aware for it since long.
19) Delayed compensation to land owners affected by resettlement programme. | Low | The compensation to land owners was fully done.
20) Low awareness of benefits of resettlement results in community resistance. | Low | Most of Rwandans knows very well the benefits of resettlement because this was the preoccupation of the government since long ago. To strenghen this, The project has invested in sensitisation and awareness building by explaining the benefits of resettlement to families to be resettled and those to be expropriated. For families to be expropriated, the project decided that nobody in the site will be expropriated and leave the site, because it would create another problem that the expropriated persons can go also into High risk zones. Therefore, a person living in the site will release only the non constructed land and remain with his/her house. A sub-standard house will be put on the standards of others by the project still. these explanations were welcomed without any objections.
21) Crop destruction during resettlement. | N/A (no risk) | All crops have been harvested prior to commencement of construction activities.
22) Refusal of some households to share their lands for construction of houses. | N/A (no risk) | Land owners have been sensitised and agreed to share their lands with others.
23) Poor targeting of households for resettlement results in less vulnerable households being resettled. | N/A (no risk) | During the project preparation, the vulnerable HH to resettle have been identified in collaboration with Nyabihu district considering their level of vulnerability categorised by Ubudehe. effective targeting of vulnerable households to resettle was ensured.
24) New settlements do not make adequate provisions for human waste management. | Low | During the construction design and constructions now in progress, The aspect proper management of human waste was considered by connecting latrines to biogas digesters to provide a source of gas (for lighting and cooking) and fertiliser.
25) Poor management of solid waste in new settlements results in pollution and disease risk. | Low | After the design of the model village by the consulting company with waste management principles (Rainwater harvesting tanks, biogas and waste management), the project has invited differrent stakeholders experts in resettlement for validation to avoid this risk ( the resettlement task force will be involved, District, Rwanda Energy group/REG, WASAC, Ministry of Disaster Management/MDIMAR, Rwanda Housing Authority,...) and their recommendations have been considered.
26) Continued unplanned settlement and unsustainable farming practices hinder progress. | Low | Project has built and will continue to build awareness on the effects of unplanned settlements and unsustainable farming practices and will introduce advocacy measures to promote the adoption of improved climate resilient farming practices.
27) Lack of incentives for local communities to participate and cooperate in interventions that do not yield immediate financial value or reduce incomes in the short term, but aim at longer-term resilience. This may reduce stakeholder engagement and participation. | Low | The project incorporates activities that yield immediate benefits for commuties in terms of skill development and income generation. The project started building awareness on these benefits. Also affected people got jobs during the project implementation.
28) Religious belief systems (e.g. 7th day Adventism which is prevalent in the project area) preclude certain income generating activities such as raising and eating rabbits, pigs or ducks. | Medium | Intensive consultations with local communities during preparation and implementation of the project. During those consultations the project takes religious belief systems into account.
29) Cultural views of women may impede their ability to take up some of the identified livelihood opportunities especially in construction (e.g. carpentry and bricklaying). | Medium | The project undertook awareness meetings to empower women for carrying out identified livelihoods opportunities including carpentry and bricklaying.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
All identified risks have been managed, they all fall in the range of Low and Medium and the mitigation strategic solutions are promising.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1: Community level mobilisation and climate adaptation plans developed and implemented. |  | The first output was targetting 3 main activities described as follows: Awareness rising of climate change issues by community animators to project beneficiaries. Another targeted was to train project staff and community animators in Value chain management, project cycle management and reporting system, post harvest and handling systems, operationalisation of climate change adaptation plan( the target for this activity was 1000Women/1000Men). Lastly, the project expected to conduct Community meetings and workshops and create 38climate change resilient groups to have a total number of 100 groups by the end of 2015. |  | Awareness raising on climate change issues has become the community animators and project staff's preoccupation, because this is done on monthly basis and due to this awareness raising, climate change issues and project activies are recognized and known by the community in the project area at a very good extent. Project staff, community animators and other key project partners have been trained on Value chain management, reporting system, post harvest and handling systems, operationalisation of climate change adaptation plan. The trainings were successful and they are still on going. 3 community meetings and 2 workshops have been conducted. 38 climate change resilient groups have been created ( composed by 1140 members: 43% are men and 57% are women.) in this reporting year. | Highly satisfactory
| Output 1.2: Investment in integrated land and water management practices |  | This output has under it 4 main activities for this reporting year and most of them are related to watersheds management whereby; 290 Ha of bench terraces were planned to be constructed, 350ha to be installed (progressive terraces and replanting agro forestry trees). other activities were related to Re-planting bamboo on giciye and kinoni river banks on 26ha, Excavation of ponds and Drainage works in Mugogo low land ). another activity was to equip 800hoseholds with rainwater harvesting systems. |  | For bench terraces, the progress is at 200ha, 340ha of progressive terraces, bamboo are planted so far on 22ha, and the drainage works in Mugogo low land are at 87% and regulary done. 800 HH were equiped with rainwater harvesting systems. A Consultancy service to prepare and to generate multi-hazards adaptation and mitigation measures for long term solution to water logging of mugogo lowland and its surrounding areas was carried out. | Highly satisfactory
| Output 1.3: Diversification and integration of crop and livestock production systems to minimise the impact of variable rainfall on rural livelihoods (agro-sylvopastoral systems etc.). |  | This output has 6 activities to perform under it: . Field trials with researchers and farmers (Installation of 16 :2 sites in each sector and Field trials site demonstration with lead farmers) Support for development of 8 tree nurseries for agro-forestry with 960,000 seedlings (One nursery of 120.000 seedlings in each sector). Support for development of 8 tree nurseries for fruits with 80,000 seedlings (One nursery seedlings of 10,000seedlings of each sector) Support for vulnerable farmers' cooperatives to adopt agricultural and small livestock and/or access to finance (at least one cooperative per sector will be supported). Facilitate inputs and extension support (Training for 16 leader farmers :2 by sector on Organic manure making ) Promotion and support for uptake of improved technologies |  | 16Farmer field schools have been grouped in 8 sectors composed by 480 members. Identification of 16 field trials and meetings for awareness have been done. Identification of 8 tree nurseries sites for both agroforestry and fruits was done. Mobilisation and trainings of community who is going to prepare those tree nurseries were done. Regarding support of vulnerable farmers' cooperatives; their identification has been done and the procurement of small livestocks is in process ( MOU between Rwanda Agricultural Board/RAB and RNRA is ready for signature to implement this activity). | Satisfactory
| Output 1.4 Introduction of climate-resilient crop/fodder varieties and agronomic practices (short season crops, seasonal pastures etc.). |  | The following activities were planned under this output: Field trials with researchers and farmers to identify appropriate varieties Establish and build capacity of community seed production groups Promotion and support for uptake of flood resilient varieties by farmers |  | 16Farmer field schools have been grouped in 8 sectors composed by 480 members. Identification of 16 field trials and meetings for awareness have been done. The implementation of other activities under this output is in process and expected to be completed before the end of the year. | Satisfactory
| Output 1.5 Introduction of climate resilient post-harvest processing and storage systems for safe handling and storage of agricultural produce during extreme climate events (floods, rains). |  | Below are activities which were expected to be performed: Technical support for improving processing and storage systems Creation of and capitalisation of a financing facility increase access to existing credit facilities Promotion and support for uptake of credit and technical support |  | Basing on the recommendations from both Technical Advisory Group and Steering Committees, Creation and capitalization of financing facility fund activity has been changed into provision of livestocks to the community which will hepl them to increase their agricultural yields, life improvement in families and creation of alternative job to agriculture. 15,950 beneficiarie have been engaged in project activities and linked with SACCOs, where 984,123,000 Rwf has been disbursed to them. | Highly satisfactory
| 2.1 Identification of viable alternative livelihood opportunities and constraints |  | Raising awareness of potential livelihood opportunities with communities and other stakeholders; and Inclusion and prioritisation of vulnerable groups in re-planting and other work schemes are the expected activities under this output. |  | Self Help Groups have been promoted to formal cooperatives, and some of them engaged in income generation activities like: tailoring, fashion dressing, carpentry and hair cutting. | Satisfactory
| Output: 2.2 Development of Rural Development hubs within selected imidugudus to promote and facilitate sustainable, market-linked and diversified livelihoods |  | The following are activites which were planned in this output: Creation of and capitalization of a credit facility for enterprise development Provision of vocational training and linkages with existing Vocational Training Centers Capacity building of co-operatives and Self Help Groups Facilitate technical support for product and service delivery through value chains ( Handcraft show Center and Carrots Washing Station) Awareness and promotion of available support |  | Basing on the recommendations from both Technical Advisory Group and Steering Committees, Creation and capitalization of financing facility fund activity has been changed into provision of livestocks to the community which will hepl them to increase their agricultural yields, life improvement in families and creation alternative job to agriculture. Concerning Provision of vocational training and linkages with existing Vocational Training Centers; MoU between Workforce Development Authority/WDA and RNRA is ready to be signed by both parties for implementation of this activity, because this is under WDA mandate. Identification of the areas to construct handcraft Show Center and Carrots Washing Station has been done. | Satisfactory
| Output 2.3 Resettlement of 200 households living in high-risk zones to Rural Development Hubs. |  | Extreme poor 200HH from high risk zone resettled in houses constructed in safe zone in compliance with national standards. The construction works are expected to be completed by march 2016. |  | The following construction works progress were observed as of end april 2016: For the house units and access roads: - Houses at finishing level (83%): 165 houses; - Construction of roads is on an average of 76%. - Construction of biogas: 45 biogas out of 45 planned have been constructed and are at 90%. - 45/45 cowsheds are at 82% of completion. - Refurbishment of 35 houses is at 70% of progress. - electrification of the village is at70%. - rainwater harvesting tanks installation are at 87%. | Highly satisfactory
| Output 2.4 Increased investment in market development (infrastructure, transport, storage, market research etc.). |  | Construction of hand craft show center ( Comptoir d`exposition), Promote local products and services to high value markets (support local farmers and producers to afford different exhibitions), Construction of selling point Karago(Kadahenda) Sector, Construction of incinerator(waste treatment) in Busogo (Byangabo) are the project's expectations as far as this output is concerned for this reporting year. |  | The sites for constructions of the mentioned infrastructures have been selected and approved by both national and local steering committee in collaboration with the local government (Districts). Terms of reference were developed, the remaining is the tender process. | Satisfactory
| Output 2.5 Increased investment in access to renewable energy (Biogas plants, solar etc.) for enterprise development. |  | 1000HH using renewable source of energy for cooking and lighting and 16 co-operatives or self help groups accessing a concessional loan for a renewable energy source were the target. |  | Awareness compaign for encouraging the Rwandans to use renewable energy has been done through meetings, televisons and radios. The acual number will be reached in the first quarter of the Next Calendar year. | Satisfactory
| Output 3.1 Training of government technical staff on climate risk management and flood and landslide prevention measures for further scaling up. |  | 70 stakeholders who have received gender sensitization training as part of climate risk management. Another expectation was to see communitee animators facilitated by giving to them bicycles and communication facilities. |  | 118 Persons from Local government, civil society, NGOs, JAF and other project stakeholders attended a workshop on sharing experience with RV3CBA Project. 16 Community animators have got bicycles and communication fees to facilitate them. | Highly satisfactory
| Output 3.2 Sharing project results and lessons learned and mainstreaming new approaches in local and national planning. |  | Participatory videos, Farmer-to-farmer fora, Preparation of guidelines and manuals, Media articles in newspapers, journals, newsletters, radio and Competitions to reward innovative approaches to adaptation were the targets of this output. |  | Climate change adaptation initiatives ( Kabyaza model green village construction, rehablitation of Mugogo lowland, construction and valorization of bench terraces, river bank protection, creation of off farm jobs) have been covered and reported on local press and newspapers like Radio Rwanda, Isango Star Radio, KT Radio, Musanze Community Radio and Rwanda Televion (RTV), The New Times, Imvaho Nshya, Environews.com, www.igihe.com. In addition, RV3CBA project website "www.rv3cba.rnra.rw" and its social media (Twitter"@CCAdaptationRw", Facebook "Rv3cba Project", Flickr "RV3CBA Project" and You Tube "rv3cba") were updated with climate change initiatives and achievments. 3500 people from climate change resilient groups have visited different sites where RV3CBA Project is operating its land and water management (bench terraces, progressive terraces construction and their valorization. Different participatory videos (bamboo production, tree nursery development, good agriculture practices for irish potatoes) were viewed by farmers during meetings and workshops. | Highly satisfactory
[5 empty] | Overall Rating | Highly satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | NGABONZIZA Prime
| Email: | prime0467@yahoo.fr
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Output 1.1: Community level mobilisation and climate adaptation plans developed and implemented. |  | The first output was targetting 3 main activities described as follows: Awareness rising of climate change issues by community animators to project beneficiaries. Anothert targeted was to train trainers (project staff, community animators and key project partners) in Value chain management, project cycle management and reporting system, post harvest and handling systems, operationalisation of climate change adaptation plan( the target for this activity was 1000Women/1000Men). Lastly, the project expected to conduct Community meetings and workshops and create 38climate change resilient groups to have a total number of 100 groups by the end of 2015. |  | The first output related to Community level mobilization and climate change adaptation planning focused on 3 main activities (i) Awareness raising of climate change issues (ii) Training of project staff and community animators and (iii) Community meetings and Planning workshops. In relation to awareness raising of climate change issues , 38 climate change resilient groups comprising 1140 members were created. 57% of the members are women. All 100 climate resilient groups created and now operationalized. Monthly meetings with local communities were conducted. Regarding Training of Project staff and community animators and other stakeholders , this year registered good progress in relation to this activity including but not limited to carry out one training for 1163 out of 1,000 members targeted on value chain management, post harvest and handling systems. In relation to Community meetings : 3 meetings and 2 workshops were conducted. | Highly Satisfactory
| Output 1.2: Investment in integrated land and water management practices |  | This output has under it 4 main activities for this reporting year and most of them are related to watersheds management whereby; 290 Ha of bench terraces were planned to be constructed, 350ha to be installed (progressive terraces and replanting agro forestry trees). other activities were related to Re-planting bamboo on river banks on 26ha, Excavation of ponds and Drainage works in Mugogo low land ). |  | (i) In line with soil erosion control 800 out of 800 households were equipped with rainwater harvesting systems. (ii) The target of rehabilitating 290 Ha with bench terraces was achieved at 68.9% (200) Ha) (iii) Progressive terraces are achieved at 97% (340 Ha /350 Ha) (iv) 26 Ha of bamboo have planted on Giciye and Kinoni river banks. (v) Excavation of Mugogo lowland and construction of 10,748 checkdams were successfully conducted and 7 groups were created to ensure sustainability of the activities done in Mugogo lowland. The Study related to Consultancy services related to Prepare and generate a multi-hasards adaptation and mitigation measures for longterm solution to water logging of Mugogo Lowland and its surrounding areas was conducted. | Highly Satisfactory
| Output 1.3: Diversification and integration of crop and livestock production systems to minimise the impact of variable rainfall on rural livelihoods (agro-sylvopastoral systems etc.). |  | This output has 6 activities to perform under it: (i) Field trials with researchers and farmers (ii) Installation of 16 : 2 sites in each sector and Field trials site demonstration with lead farmers) Support for development of 8 tree nurseries for agro-forestry with 960,000 seedlings (One nursery of 120.000 seedlings in each sector). Support for development of 8 tree nurseries for fruits with 80,000 seedlings (One nursery seedlings of 10,000seedlings of each sector) Support for vulnerable farmers' cooperatives to adopt agricultural and small livestock and/or access to finance (at least one cooperative per sector will be supported). Facilitate inputs and extension support (Training for 16 leader farmers :2 by sector on Organic manure making ) Promotion and support for uptake of improved technologies |  | 8 agroforestry tree and 8 fruits nurseries were installed and around 1 million trees were planted during the planting season. A workshop on capacity building for agro forestry management has been conducted with project stakeholders(Community animators, district and sector forest officers and presidents of cooperatives ), The identification of existing cooperatives was done (130 cooperatives in Nyabihu, and 39 in Busogo/Musanze), and 16 Farmer field schools have been grouped in 8 sectors composed by 480 members. | Highly Satisfactory
| Output 1.4 Introduction of climate-resilient crop/fodder varieties and agronomic practices (short season crops, seasonal pastures etc.). |  | The following activities were planned under this output: Field trials with researchers and farmers to identify appropriate varieties Establish and build capacity of community seed production groups Promotion and support for uptake of flood resilient varieties by farmers |  | Output 1.3 and 1.4 are complementing eachother. The second year of the implementation of the Project Reducing Vulnerability to Climate Change in North West Rwanda trough Community Based Adaptation focused on training community animators, district forest officers and members of the cooperatives on the importance of agroforestry and fruits nuseries. 16 nurseries were created and trees were planted. Introduction of climate resilient crops will be focused on in the 3rd year of the implementation of the Project. | Satisfactory
| Output 1.5 Introduction of climate resilient post-harvest processing and storage systems for safe handling and storage of agricultural produce during extreme climate events (floods, rains). |  | Below are activities which were expected to be performed: Technical support for improving processing and storage systems Creation of and capitalisation of a financing facility increase access to existing credit facilities Promotion and support for uptake of credit and technical support |  | A survey on existing post harvest processing and storage systems in 8 sectors has been done and found out that 4 post harvest storages exists but none of them is used due to the low production and sometimes due to resistance. To incease access to credit facilities; the project beneficiaries already linked with SACCOs are around 3613(2,204 women equivalent to 61%). The total amount of money injected directly in beneficiaries as wages is 143,959,000Rwf. The shares paid by beneficiaries in SACCOs are so far 14,726,000Frw. | Highly Satisfactory
| 2.1 Identification of viable alternative livelihood opportunities and constraints |  | Raising awareness of potential livelihood opportunities with communities and other stakeholders; and Inclusion and prioritisation of vulnerable groups in re-planting and other work schemes are the expected activities under this output. |  | SACCO managers, district cooperatives officers, community animators and cooperative representatives have been trained on saving and credit, financial literacy and self sufficiency and 15,950 jobs were created. | Highly Satisfactory
| Output: 2.2 Development of Rural Development hubs within selected imidugudus to promote and facilitate sustainable, market-linked and diversified livelihoods |  | The following are activites which were planned in this output: Creation of and capitalization of a credit facility for enterprise development Provision of vocational training and linkages with existing Vocational Training Centers Capacity building of co-operatives and Self Help Groups Facilitate technical support for product and service delivery through value chains ( Handcraft show Center and Carrots Washing Station) Awareness and promotion of available support |  | Preliminary activities were done where 15,950 beneficiaries from self help groups have opened accounts in SAACOs; The community enterprise development guidelines document has been developed and shared with Technical Advisory Group members for Advices and Capacity and needs assessment of 4 technical vocational training centers (Kibihekane, Karago, Abacu Tubiteho Rwankeri, and Jenda craft center) was carried out. | Highly Satisfactory
| Output 2.3 Resettlement of 200 households living in high-risk zones to Rural Development Hubs. |  | Extreme poor 200HH from high risk zone resettled in houses constructed in safe zone in compliance with national standards. The construction works are expected to be completed by march 2016. |  | All 165 houses to be constructed now are completed. 35 houses to be refurbished are now at finishing level. 45out of 45 biogas, rainwater harvesting tanks almost completed. Cowsheds completed at 82% and road construction progress is at 73% (Compaction and drainage underway). | Highly Satisfactory
| Output 2.4 Increased investment in market development (infrastructure, transport, storage, market research etc.). |  | Construction of hand craft show center ( Comptoir d`exposition), Promote local products and services to high value markets (support local farmers and producers to afford different exhibitions), Construction of selling point Karago(Kadahenda) Sector, Construction of incinerator(waste treatment) in Busogo (Byangabo) are the project's expectations as far as this output is concerned for this reporting year. |  | 4 meetings were carried out with Local communities on entrerprise development. Needs assessment of the market infrastructures was conducted. Land acquisition for Karago selling point and Waste treatment plant (Incinerator) for Busogo Sector was successfully done. | Satisfactory
| Output 2.5 Increased investment in access to renewable energy (Biogas plants, solar etc.) for enterprise development. |  | 1000HH using renewable source of energy for cooking and lighting and 16 co-operatives or self help groups accessing a concessional loan for a renewable energy source were the target. |  | Awareness compaign for encouraging the Rwandans to use renewable energy has been done through televisons and radios. The acual number will be reached in the first quarter of the Next Calendar year. | Satisfactory
| Output 3.1 Training of government technical staff on climate risk management and flood and landslide prevention measures for further scaling up. |  | 70 stakeholders who have received gender sensitization training as part of climate risk management. Another expectation was to see communitee animators facilitated by giving to them bicycles and communication facilities. |  | Around 120 stakeholders have been trained on Climate risk management. All Animators received bicycles and are being facilitated on monthly basis | Highly Satisfactory
| Output 3.2 Sharing project results and lessons learned and mainstreaming new approaches in local and national planning. |  | Participatory videos, Farmer-to-farmer fora, Preparation of guidelines and manuals, Media articles in newspapers, journals, newsletters, radio and Competitions to reward innovative approaches to adaptation were the targets of this output. |  | Video has been shot, farmer to farmer meetings were conducted, 4 training on meanstreaming climate change management approaches were carried out. Media articles in news papers , journals, news letters and radio were performed. Evaluation of the best and innovative approaches will be carried out in the next year. | Highly Satisfactory
[5 empty] | Overall Rating | Highly Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Emile HABIMANA
| Email: | ehabimana@minirena.gov.rw
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Overall Objective | Consumption levels in target HH | Rwf 118,000 | in relation to indicator concerning the consumption levels in targeted households, a lot of initiatives targeting its increase up to 50% are still ongoing and the current progress is estimated up to 165,200 RWF (to be confirmed by the mid-term evaluation). | 50% increase on baseline
Overall Objective | Percentage of target population adopting risk reduction measures | 10% | The target on this indicator was to increase the percentage of the population adopting risk reduction measures from less than 10% to 60%. Meetimgs, workshops and trainings were carried out to raise awareness of local communities to adopt risk reduction measures. also, specific incentives were discussed and these include local cooperatives producing and selling some climate risk management materials ( agroforestry trees). the current progress on this indicator is estimated at 37%. | 60% practice at least 1 risk reduction measure.
Outcome 1. | Number of victims killed and houses destroyed by flooding and landslides. | 13 people died, 598 households completely destroyed, 748 households partially destroyed | Since the project started operating in its intervention area, the positive impact observed by project stakeholders. Landslides that are the measure cause of the death and destroying economic activities were reduced up to 55% due to flood control investiments. In addition to that no incident related to death and house destroyed in the project area. | 30% decrease on baseline
Outcome 1. | Crop losses due to climate variability (potatoes, beans, maize, wheat, peas, tea, coffee, pyrethrum). | 6114 ha of crop land destroyed. | Due to the project intervention activities mostly soil & water managent activities, the positive impact of the project is gradually visible as described and crop losses have been reduced at a very good extent. | 30% decrease
Output 1.1 | No. of community based adaptation plans being implemented. | 0 | 8 Adaptation plans were developed and being implemented. | 8Plans (1 for each sector)
Output 1.1 | No. of community groups formed and operationalised for adaptation planning. | 0 | up to now 100 community groups were formed and operationalised. | 55 groups
Output 1.1 | Participation of women/men from target HH in adaptation planning processes and mobilised to participate in project activities. | 0 | The total number of participants was 7,992 people (3,704 Male&4,288 Female). Community animators and project staff have been trained on Value chain management, project cycle management and reporting system, post harvest and handling systems, operationalisation of climate change adaptation plan, financial literacy, cooperative management , forestry management, watersheds management, post harvest and storage techniques and land management. They have also been explained their role in the project activities. | 4000 women/4000 men
Output 1.1 | Percentage of committee positions held by women/men from target HH in adaptation planning processes. | 0 | Meetings and workshops with volunteers committees have been conducted to raise awareness.This activity is regularly done by community animators . The focus is put on ownership of RV3CBA activities. Note that Gender consideration is always taken into account. | 50% women/50% men
Output1.2 | Hours per day (or year) women from target HH spend fetching water and collecting water. | 1 hour | Consultancy on rainwater harvesting infrastructures installation was done, and this indicator is going to be measured next year after the construction of those infrastructures. | 30 minutes
Output1.2 | Area (ha) rehabilitated with erosion control measures. | 1. 2,479 Ha of radical terraces. 2. 26,000 ha of progressives terraces 3. 7,800 ha have forest | For bench terraces, the progress is at 363ha, 780,5ha of progressive terraces. | 1. 309 ha increase for radical terraces 2. 550 ha increase for progressives terraces
Output1.2 | Number of water user groups managing ponds and rainwater harvesting tanks with management plans in place. | 0 but 14 underground tanks, 65 ponds with accompanying rope-and washer pumps were constructed. | The consultancy study on rainwater harvesting infrastructures results are available ( the quantity of tanks and areas to install them are known).This indicator will be measured rigth after the construction of the model Green village. | 80
Output1.2 | No. target HH using harvested rainwater for domestic use and irrigation. | 102 HH | The consultancy study on rainwater harvesting infrastructures results are available ( the quantity of tanks and areas to install them are known).This indicator will be measured rigth after the construction of the model Green village. | 2000
Output1.2 | Change in turbidity of rivers. | 0 mg/l to 0.86 mg/L | bamboo are planted on 118ha, and the drainage works in Mugogo low land are regulary done. | 20% reduction
Output 1.3 | No of target HH adopting climate resilient farming practices disaggregated by type (e.g. agro-forestry, agro-sylvopastoral etc). | (24,285women/25,226 men) of farmers at land use consolidated areas adopt good agriculture practices. | 4500 HH beneficiaries of terraces adopted climate resilient farming practices. Workshops on capacity building for agro forestry management have been conducted with project stakeholders(Community animators, district and sector forest officers and presidents of cooperatives ) and these people trains also many others because they are closer to them. | 5000 increase on baseline
Output 1.3 | Area of cultivated land (ha) under diversified cropping and integrated farming systems in target areas. | Maize: 6,356 ha Irish Potatoes: 12,342 ha Beans: 8,703 ha Wheat: 3,234 ha | The area of cultivated land under diversified cropping and integrated farming practices are 213ha of bench terraces and 500,5ha of progressive terraces. | 20%
Output 1.4 | Numbers of HH adopting at least 1 new climate-resilient crop or fodder variety or agronomic practices (disaggregated by male/female headed HH). | 0 | 4500 HH beneficiaries of terraces adopted climate resilient farming practices. 43% of men and 57% of women. | 5000
Output 1.4 | Participation of women/men in farmer field trials. | 1006 Women/704 Men | 223 men and 257 women are participating in farmer field trials all grouped into 16 groups from 8 sectors. | 140 women/140 men increase on baseline
Output 1.5 | Number of post harvest storage systems established; number of HH using these. | 4 Storage established | The post harvest survey was done and realised that 4 storages are already established but not used due to low production and resisitance for some HH. What we are doing is the mobilisation of farmers to use the exixisting ones. | 7 storage facilities used by > 700 HH
Output 1.5 | Percentage of target HH adding value by primary agro processing such as sorting, drying, threshing, grading. | 2 drying ground (Rurembo and Jomba sectors) | Training on value chain has been done. | 40% increase on baseline
Output 1.5 | Percentage of target HH adding value through transformative agro processing such as milling, shelling, grinding or packaging | 5% HHs engaged in 2nd processing | Carrots washing station is planned to be built in Jenda sector in line with agro processing aspect. The plot for construction was identified and the lay out plan is in process. | 20% increase on baseline
Output 1.5 | No of women/men from target HH engaged in post- harvest livelihoods | 50Men/100Women | 70 HH out of 81HH trained on financial literacy and enterpreneurship have been engaged in post-harvest. | 1000W/1000M
Outcome 2. | Share of target HH income from non-farm activities. | 12,4% | The project area activities normally rely on agriculture (98% deliver their income from farming activities). Generating other jobs other than farming activites is a priority in the project document however a good number of interventions are targeted in Year 3. | 50%
Outcome 2. | No. of women/men from target HH adopting alternative livelihood. | 54 women/203 men | 15,950beneficiarie have been engaged in project activities and linked with SACCOs, where 984,123,000Rwf has been disbursed to them through their own savings accounts. The assessment of alternative livelihoods initiated from savings is going to be done in the mid-term evaluation review. | 50% increase on baseline
Output 2.1 | Number of women/men from target HH with a new source of income. | 0 | To raise awarness of potential livelihood opportunities; SACCO managers, district cooperatives officers, community animators and cooperative representatives have been trained on saving and credit, financial literacy and self sufficiency and 15,950 beneficiaries from community have been engaged as manpower. 45 members of CODUMU Cooperative are engaged in off- farm activities such as making baskets from plastic raw materials, solid and liquid soaps). | 4000 w/4000 men
Output 2.2 | % increase in annual HH income from diversified livelihoods (disaggregated by FHH/MHH). | 16%/13.2% generate income in crop farming, 9/5.6% in wages, 2/9.6% in Animal rearing, 13.2/8.3% from Salary, 19/13% in doing Business | 15,950 beneficiarie have been engaged in project activities as manupower and linked with SACCOs, where 984,123,000 Rwf has been disbursed to them. | 30% increase on baseline
Output 2.2 | Number of women/men from target HH in Self-help groups or co-operatives. | 7,354 women/8,990 men | 3000 people have been grouped into 100 self help groups (composed by 47% of men and 53% of women). Members of cooperatives (number of coop and mbers). | 4000W/4000M incease on baseline
Output 2.2 | Number of women/men from target HH graduating from vocational training schemes. | 5 women/ 12 men | Capacity and needs assessment of 4 technical vocational training centers (VTC Kibihekane, MTC karago, DCD Abacu tubiteho Rwankeri, and Jenda craft center) have been done; The senior management has advised to sign an MOU with the Workforce Development Authority (WDA: it is a public institution which has vocational trainings under its mandate) for the implementation of related activities. The MOU is ready waiting for signature. | 50
Output 2.2 | No. of hours spent on domestic duties by women/men aged over 16 years. | 8/4 hrs | 15,950 beneficiarie have been engaged in project activities, among them 59% are women and spent 7 hours out of domestic duties | 3/2 hrs
Output 2.2 | No. of FHH/MHH in receipt of small loans to start an enterprise. | 0 | A Memorendum of Understanding (MOU) with the Ministry of Commerce and Industry through its agency (Rwanda Cooperative Agency: RCA) which has all business related activities under responsibility is going to be signed for the imeplementation of such activities. The role of RNRA through PIU will be to monitor if the implementation is effective. this activity will start immediately after signing the MOU in this reporting year. | 3000
Output 2.2 | No. of women’s associations/savings groups (comprising target HHs) investing in a new and profitable business opportunity. | 0 | 45 members of CODUMU Cooperative are engaged in off- farm activities such as making baskets from plastic raw materials, solid and liquid soaps). | 300
Output 2.2 | No. of target beneficiaries (women/men) in VSLAs | 6 groups (92 women/ 18 men) | 3000 people have been grouped into 100 self help groups (composed by 47% of men and 53% of women). Members of cooperatives (number of coop and mbers). | 3500 w/ 3500 men
Output 2.3 | No. of extreme poor HH from high risk zone resettled in houses constructed in safe zone in compliance with national standards. | 49,024/62,862 (77.9%) household are resettled into villages. | The following construction works progress were observed as of end april 2016: For the house units and access roads: - Houses at finishing level (83%): 165 houses; - Construction of roads is on an average of 76%. - Construction of biogas: 45 biogas out of 45 planned have been constructed and are at 90%. - 45/45 cowsheds are at 82% of completion. - Refurbishment of 35 houses is at 70% of progress. - electrification of the village is at70%. - rainwater harvesting tanks installation are at 87%. | 200
Output 2.4 | Percentage of targeted HH selling produce through new markets. | 4 selling points constructed in Jenda, Rurembo, Kintobo and Jomba sectors used by 5% of targeted HH. | There was an increase of number of cooperatives working in JENDA AGAKIRIRO CENTER from 2 cooperatives to 9 cooperatives and two more selling points are going to be constructed ( plots and designs are available). | 20% increase on baseline
Output 2.4 | Percentage of farmers bulking produce for market and selling collectively. | 0 | Construction of a hand craft show center ( Comptoir d`exposition), Promote local products and services to high value markets (support local farmers and producers to afford different exhibitions), Construction of selling point Karago(Kadahenda) Sector, Construction of incinerator(waste treatment) in Busogo (Byangabo) are strategies taken to effectivelly implement indicators of this output 2.4. The progress is as follows: sites for constructions of the mentioned infrastructures have been selected and approved by both national and local steering committee in collaboration with the local government (Districts). | 60%
Output 2.4 | No of target HH using new market infrastructure. | 3 markets infrastructure in place used by 646 target HH. | Construction of a hand craft show center ( Comptoir d`exposition), Promote local products and services to high value markets (support local farmers and producers to afford different exhibitions), Construction of selling point Karago(Kadahenda) Sector, Construction of incinerator(waste treatment) in Busogo (Byangabo) are strategies taken to effectivelly implement indicators of this output 2.4. The progress is as follows: sites for constructions of the mentioned infrastructures have been selected and approved by both national and local steering committee in collaboration with the local government (Districts). Terms of reference were developed, the remaining is the tender process. | 2000 HH
Output 2.5 | No. of HH using a renewable energy source for lighting or cooking. | 89 HH | Awareness compaign for encouraging the Rwandans to use renewable energy has been done trough televisons and radios. The acual number will be reached in the first quarter of the Next Calendar year. | 1000
Output 2.5 | No. co-operatives or self help groups accessing a concessional loan for a renewable energy source. | 0 | Awareness compaign for encouraging the Rwandans to use renewable energy has been done trough televisons and radios. The real activites under this output are expected to start after the construction of the model green village. | 16
Outcome 3. | No. of sectors outside project area replicating community based adaptation approaches. | 0 | All 19 sectors neigbouring the project area are replicatin the community based adaptation. Intnsive activities and further farmer field schools aiming sustainable land and water management are targeted in Year 3 | 2
Outcome 3. | Gender sensitive climate adaptation approaches incorporated into X local and Y national planning documents. | No adaptation planning currently taking place | The progress will be reported in the project mid-term. | 5 local and 2 national level
Output 3.1 | Budgets and staffing dedicated to climate change adaptation through district development plans. | 0 | Community animators have been elected and equiped with transport facilitations; they have got several trainings to help them in facilitating the project implementation. Project activities are always incorporated into District development plans and annual performance contracts. | Integrated into 2 DDPs
Output 3.1 | No. of stakeholders who have received gender sensitisation training as part of climate risk management. | 0 | 150 representatives of self help groups and 118 people from local authorities and communty initiatives have been trained on Climate Change Management | 150
Output 3.2 | Number of environmental/climate change policy briefs written and communicated to key decision makers. | 0 | Communication strategy was developed and is being implemented. 3 written briefs (RV3CBA official launch, Expropriation of Kabyaza model Green Village and Community participation to Mugogo lowland rehabilitation) were submitted to different senior managers at local and central level. | 8
Output 3.2 | No of farmers making cross visits or viewing participatory videos by other farmers. | 0 | 3500 people from climate change resilient groups have visited different sites where RV3CBA Project is operating its land and water management (bench terraces, progressive terraces construction and their valorization. Different participatory videos (bamboo production, tree nursery development, good agriculture practices for irish potatoes) were viewed by farmers during meetings and workshops. | 8000
Output 3.2 | No. of TV/radio broadcasts with key adaptation messages. | 0 | Project activities and events on community climate change adaptation (Project official launch, Foundation stone laying ceremony of Kabyaza model green village construction, rehablitation of Mugogo lowland, valorization of bench terraces, creation of off farm jobs) have been covered and reported on Radio Rwanda, Isango Star Radio, KT Radio, Musanze Community Radio and Rwanda Televion (RTV). | 10 out of 16
Output 3.2 | No. of news reports in the local press and media that have covered climate adaptation initiatives. | 0 | Climate change adaptation initiatives ( Kabyaza model green village construction, rehablitation of Mugogo lowland, construction and valorization of bench terraces, river bank protection, creation of off farm jobs) have been covered and reported on local press and newspapers like Radio Rwanda, Isango Star Radio, KT Radio, Musanze Community Radio and Rwanda Televion (RTV), The New Times, Imvaho Nshya, Environews.com, www.igihe.com. In addition, RV3CBA project website "www.rv3cba.rnra.rw" and its social media (Twitter"@CCAdaptationRw", Facebook "Rv3cba Project", Flickr "RV3CBA Project" and You Tube "rv3cba") were updated with climate change initiatives and achievments. | 30

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Commitment and ownership of project activities by beneficiaries, Community animators and Local government authorities (Disticts) has contributed very much to the project's progress.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The expropriation process which is always not easy has caused the delay of the construction of the model green village. Intensive awareness with local communities and proper planning for procurement of construction services helped the project to catch up with the current progress.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | For land and water management activities (terraces), the project management has decided to increase the number of hectars to be protected and this was based on the fact that terraces were seen as the most important infastructures to control erosion and landslides in the project area.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The lessons learnt from the reporting process has shown that climate and seggragated data at impact level need considerable investments in conducting specific climate data surveys.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | N/RW/1
Implementing Entity | Ministry of Natural Resources( MINIRENA)
Type of implementing entity | National
Country | Rwanda
Region | Rwanda
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total | 601818 | 164544 | 437274 | Total | 601818 | 15950 |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries |  | 67% |  | % of female beneficiaries |  | 58% |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 601818 | Inland flooding | 2: Partially effective | Total | 601818 | Inland flooding | 5: Very effective | Total | 601818 | Inland flooding | 5: Very effective | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 4 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated | 5 | Disaster risk reduction | Local | 3: Risk and vulnterability assessments completed or updated | 5 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 5 | 2: Monitoring and warning service | Geographical coverage | National | 5 | 2: Monitoring and warning service | Geographical coverage | National | 5 | 2: Monitoring and warning service | Geographical coverage | National |  |  | Geographical coverage
|  |  |  | Number of municipalities | 30 |  |  | Number of municipalities | 30 |  |  | Number of municipalities | 30 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 150 | Multi-sector | 3: Medium capacity | Total | 150 | Multi-sector | 4: High capacity | Total | 118 | Multi-sector | 4: High capacity | Total
|  | % of female targeted | 56% |  |  | % of female targeted | 56% |  |  | % of female targeted | 63% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 45 | 30% | Public |  | 150 | 56% | Public |  | 118 | 63% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 2: Low capacity | Public | National | Multi-sector | 4: High capacity | Public | National | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 10% |  | Disaster risk reduction |  | 60 |  | Disaster risk reduction |  | 37 |  | Disaster risk reduction
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 16454 |  | 3: Partially aware |  | 98226 |  | 5: Fully aware |  | 65818 |  | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Disaster risk reduction | National | 2: Partially responsive (Lacks most elements) |  | Disaster risk reduction | National | 5: Highly responsive (All defined elements ) |  | Disaster risk reduction | National | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Multi-sector | 24 | Community |  | Multi-sector | 56 | Community |  | Multi-sector
|  | 0 | Community |  | Multi-sector | 6 | Community |  | Multi-sector | 3 | Community |  | Multi-sector
|  | 0 | Community |  | Multi-sector | 2 | Community |  | Multi-sector | 4 | Community |  | Multi-sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Water management | water areas | 5: Very effective |  | Water management | water areas | 4: Effective |  | Water management | water areas
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 28479 | ha protected | 3: Moderately effective | Cultivated land/Agricultural land | 29832 | ha protected | 5: Very effective | Cultivated land/Agricultural land | 29622 | ha protected | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 38266 |  | 4: High improvement |  | 16770 | 59% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 10% to 20% | Agribusiness | 19133 |  | Above 50% | Agribusiness | 16770 | 59% | From 20% to 30% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agribusiness |  |  | 8000 | Agribusiness |  |  | 8867 | Agribusiness
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Disaster risk reduction | National | Economic policy | 3 | Disaster risk reduction | National |  | 3 | Disaster risk reduction | National
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.