## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 01 November 2013 to 31 October 2014
| Project Title: | Implementation of Concrete Adaptation Measures to Reduce Vulnerability of Livelihoods and Economy of Coastal Communities of Tanzania
| Project Summary: | Tanzania is impacted by climate change mainly through its effects on rainfall patterns, temperature extremes and sea level rise. The direct impacts of these changes are likely to result in more frequent and intense droughts, the destruction of infrastructures in the coast and inland through flooding, inundation, erosion and storms; if no action is taken, the socio-economic impacts will include agricultural yield decreases, decreased water availability and quality, and losses of lives and livelihoods, as well as the accelerated degradation of ecosystems that form the basis of the Tanzanian economy. To respond to this, the government developed a project proposal to adapt to the climate change in the coast of Dar es salaam. In December 2011 the Adaptation Fund Board considered the proposal and approved a five years project with a total of USD 5,008,564. Implementation of the project started in 1 November 2012. The project consists of the following outcomes, supported by on the ground activities implemented primarily in the vicinity of Dar Es Salaam: 1. Adverse impacts of SLR and floods on coastal infrastructures and settlements are reduced. 2. Coastal ecosystems are rehabilitated and Integrated Coastal Area Management is implemented. 3. Knowledge of climate impacts and adaptation is increased. The project is being implemented by the United Nations Environment Programme (UNEP) and executed by the Vice Presidents Office (Division of Environment) in close cooperation with sectoral ministries as well as Dar es Salaam City Council and Municipalities of Ilala, Temeke and Kinondoni.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AFB-5060-1111-2G48 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNEP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | United Republic of Tanzania | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Dar es Salaam City (Ocean Road; Kigamboni-Mwalimu Nyerere Memorial Institute; Kinondoni Municipality:Tandale street in Tandale ward and Kawe street in Kawe ward; Ilala Municipality:.Bungoni street in Buguruni ward; Temeke Municipality: Miburani-Mtoni Bustani streets in Mtoni ward and Butiama street (Butiama drainage) in Kijichi ward; Kunduchi, Ununio and Mbweni. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2011-12-14
IE-AFB Agreement Signature Date: |  | 2012-11-01 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: | [8 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | May 1, 2015 (MTR), November 1, 2017 (Terminal)
Terminal Evaluation Date:
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Inception Workshop Report 2012; Quarterly Expenditure Reports (Q4,2012, Q1, Q2, Q3&Q4, 2013; Q1,Q2,Q3,2014); Project brief report to the Planning Commission of the United Republic of Tanzania for the Government year 2012/2013; TORs of: Joint Project Steering Committee; National Project Coordinator; Senior Technical Adviser; Finance and Administrative Assistant; Tender Evaluation Repors for supply of the project vehicle; evaluation report for experssion of interest for a position of senior technical adviser; evaluation report for a position of consultancy services for development of a baseline survey and development of indicators and various consultancies. Finalized TORs of: (Feasibility Study, EIA study for the proposed Construction and Rehabilitation of Seawall at Ocean Road and Kigamboni (Mwalimu Nyerere Memorial Institute) and Rehabilitation of Drainage Systems; Climate Change Knowledge Management Specialist; Coastal Zone Management Specialist; Memorandum of Understanding with UNOPS for constrcution and rehabilitation of seawall of Kigamboni and Ocean Road and drainage systems; Reef specialist, Rural energy consultant, mangrove specialist,Coastal Reabilitation specialist, Mangrove specialist, sub-contract env.engineering firm for mangrove rehabilitation, Climate Change Observatory for Tanzania, Task Force to develop EBICAM Action Planand sub-contract NGO reef rehabilitation ); Evaluation Report of Expression of Interest Tender No. ME 002/2012-13/DE/C/07 for Re-advertized Consultancy services for Development of a baseline survey and development of indicators and targets, Procurement plan 2014, Revised Project Budget, Revised Work Plan, Variance of the revised project budget, Report of the development of the Terms of Reference of various consultancies. Baseline study report. PPR (November 2012-October 2013). PPR B (1 November 2013 to 30 October 2014), Audit report 2013, Draft Ecosystem Based Intergrated Coastal Area Management (EBICAM) Action Plan for Dar es Salaam region. Brief report of UNEP task manager and senior technical adviser mission, 2013, Annual physical and financial performance for year 2013. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.unep.org/climatechange/adaptation/AccessToAdaptationFinance/AdaptationFundProjects/Tanzania | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Eng. Ladislaus Kyaruzi | Dominican Republic
| Email: | leoky2009@gmail.com | Ecuador
| Date: | 2014-10-31 | Egypt
| Government DA |  | El Salvador
| Name: | Eng. Ngosi C.X. Mwihava | Equatoral Guinea
| Email: | nmwihava@gmail.com | Eritrea
| Date: | 2014-10-31 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Lars Christiansen, UNEP task manager | Fiji
| Email: | lachr@dtu.dk | Finland
| Date: | 2014-10-31 | France
| Executing Agency |  | Gambia
| Name: | Vice President's Office | Georgia
| Email: | ps@vpo.go.tz | Germany
| Date: | 2014-10-31 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31 October 2014
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31 October 2014(USD)* | 248963
Add any comments on AF Grant Funds. (word limit=200)
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1: Sea wall raised or rehabilitated in areas showing particular damage | 13589.57
| Output 1.2: Effective storm and flood drainage systems in urban areas and near coastal communities | 2659.7
| Output 2.1: Appropriate alternative energy (efficient cookstoves, small solar) technology transferred | 0
| Output 2.2: Mangrove rehabilitation through planting of resilient seedlings, dredging and the creation of no-take buffer zones;degraded coral reefs rehabilitated and protected | 0
| Output 2.3: Shoreline rehabilitated and stabilized using trees and grasses | 0
| Output 3.1: Performance of a baseline study | 15980
| Output 3.2: A climate change coastal observatory for Tanzania for ongoing monitoring of CZM and Coastal environmental status and scientific research | 0
| Output 3.3: Lessons learned from the project outputs documented | 4308.14 |  | 0
| Output 3.4: District level administration have the capacity to adequately manage rehabilitated infrastructure | 0
| Output 3.5: One EBICAM plan for the coastal region approved | 27462.19
| Project Execution | 107949.21
| GRAND TOTAL | 171948.81
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: Sea wall raised or rehabilitated in areas showing particular damage | 3253000 | 2016-12-30
| Output 1.2: Effective storm and flood drainage systems in urban areas and near coastal communities | 200000 | 2016-03-30
| Output 2.1: Appropriate alternative energy (efficient cookstoves, small solar) technology transferred | 68500 | 2015-03-30
| Output 2.2: Mangrove rehabilitation through planting of resilient seedlings, dredging and the creation of no-take buffer zones;degraded coral reefs rehabilitated and protected | 105600 | 2016-12-30
| Output 2.3: Shoreline rehabilitated and stabilized using trees and grasses |  | 2017-06-30
| Output 3.1: Performance of a baseline study |  | 2014-09-30
| Output 3.2: A climate change coastal observatory for Tanzania for ongoing monitoring of CZM and Coastal environmental status and scientific research | 16000 | 2017-10-30
| Output 3.3: Lessons learned from the project outputs documented | 11500 | 2017-12-30
| Output 3.4: District level administration have the capacity to adequately manage rehabilitated infrastructure | 31266 | 2017-12-30
| Output 3.5: One EBICAM plan for the coastal region approved | 25000 | 2015-06-30
| Project Execution | 103591 | 2017-12-30
| GRAND TOTAL | 3814457
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Co-financing is not applicable to the project
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Operational: The multiple ongoing initiatives on climate adaptation in Tanzania could cause operational delays for this project | Low | The appointed National Project Coordinator, Senior Technical Adviser and assistant administrative and financial manager as a dedicated team for project coordination ensure that the project maintains its objectives. In addition the realisation of the Project Steering Committee (PSC) has helped to resolve pending issues allowinh a smooth progress of the planned activities. The Chairperson of the PSC who is the Permanent Secretary of the Vice President's Office ensures that no unnecessary delays of this project. PSC has been able to meet in 3rd March 2014 and 22nd July 2014.
Political: District-level stakeholders and administrations show low engagement for adaptation measures | Low | The Project Steering Committee was established among others, to provide overall guidance with regard to implementation of the project activities. Its members are: Permanent Secretary– Vice President’s Office (Chair); Director of Environment-Vice President’s Office; Director of Environment- First Vice President’s Office –Zanzibar; Director- Dar es Salaam City Council; District Executive Director – Pangani District Council; District Executive Director – Bagamoyo District Council; District Executive Director – Rufiji District Council; Municipal Executive Director – Temeke Municipal Council; Municipal Executive Director – Ilala Municipal Council; Director of Forest – Ministry of Natural Resources and Tourism; Director of Water Resources – Ministry of Water; Director- Ministry of Works; UNEP Task Manager of the Project; and Assistant Director of Environmental Assessment- Vice President’s Office (Secretary). The Steering Committee met on 3rd March 2014 and 22nd July 2014. Also, Dar es Salaam City Council appointed a focal person for this project. The trainings to the district representatives of the coastal communities, fishermen associations, municipal planners, forest officers and environment of the Municipalities of Ilala, Kinondoni and Temeke municipalities and Dar es Salaam City Council enhances their engagement for adaptation measures on the coastal amd marine environment. trainings are scheduled for 18-22 December 2014
Political: the project could experience difficulties in coordination and oversight for activities delivered at various sectors, levels of governments or by multiple partners | Low | The dedicated personnel for project management that has been established through the Vice President‘s Office will coordinate and monitor the project outputs and activities. Close collaboration among various ministries and stakeholders will be provided through among others the project steering committee. With the realisation of the first Project Steering Committee im March 2014, and appointement of the various Institutional Focal Points, a greater cross-intitunional coordination has been achieved.
Environmental: Extreme weather events such as tropical storms, floods or droughts could hinder progress in ecosystem rehabilitation and infrastructure activities | Medium | Protective infrastructure rehabilitation will be designed according to the best available technical standards and using the best available technology. The baseline study has provided appropriate data and information to be used. Scoping and designs to undertaken through the feasibility study will provide more appropriate data and information. In addition all foreseen ecosystem rehabilitation works will be carried out in startight collaboration with NGO's and communities who will be supporting the project in case of extreme weathar event that could equire additional labour input. Finally, working conditions for all key activities of ecosystem and infrastructure rehabilitation will be such to take into consideration and minimize the impacts of any eventual disruption caused by extreme climate/meteorological event.
Financial: market and price fluctuations could cause price variations and variations in costs of certain project activities, leading to budgetary constraints. | Low | The feasibility study will establish the possible costs for the project activities. Environmental Impact Assessment (EIA) will develop a risk management and contingency plans.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Vice President's Office "the executing entity" low executions rate due to internal procurement procedures. | Medium | The experience from the previous period of project implementation have shown severe delays due to slow procurement procedures within VPO. A formal partnership with the VPO procurement unit to create streamlined and dedicated processes for the project (e.g. on-demand meetings of the procurement board) has now been established by including a specific budget in the revised project budget to cover any unforeseen costs during the procurement processes. Furthermore, 2013, 2014 and 2015 project activities were/are included in the annual work plans of the VPO. This has somewhat improved the procurement process by being able to procure many consultancies at a time. Out of 10 consultancies (4 are at the stage of signing the contracts; 2 have signed contracts; feasibility study to be undertaken by UNOPS; 3 consultancies will be advertized in January 2015). Out of 5 sub contracts (1 is being re-advertized in January 2015; seawall and drainage sub contracts will be undertaken by UNOPS; 1 sub contracts to be advertized in January 2015 and 1 sub contract, its acticity of stabilization will start in year 4 of the project). However, measures implemented so far have not been sufficiently effective in mitigating the risk. To minimize further the potential risk with the procurement delays towards the construction/rehabilitation of infrastructures (sea walls and drainage system; the biggest outputs of the project), it is expected that the MoU to be signed with the UNOPS, by which all the procurement and feasibility studies towards the construction/rehabilitation of infrastructures (sea walls and drainage system) will be carried out by this UN unit. Therefore, processes such as (i) The preparation of the feasibility studies and preliminary design requirements, (ii) preparation of the final design requirements; (iii) preparation of the Works design, drawings and other specifications; (iv) preparation of the construction and procurement strategy; (v) procurement of the Works in accordance with the procurement strategy; (vi) undertaking and development of the Works in accordance with the construction strategy, and; (vii) institutional capacity development for maintenance of coastal infrastructure have been included in the UNOPS MoU which establishes that the project will be implemented within a 14 month period, upon the finalisation of the agreement (December 2014).
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Yes. Due to the delays in the procurement processes observed during the past period, a formal partnership with the VPO procurement unit was established by including a specific budget in the revised project budget to cover any unforeseen costs during the procurement processes. Although this measure has enable the VPO Procurement Unit to carry out several procurement processes in simultaneous, unfortunately the risks were not fully reduced and delays persisted. One of the major causes identified was the inabiility of establishing a fasttrack mechanism to hasten the procurement process by reducing the time required by Government Law for public advertisement and contract. Considering that the next major procurements to follow will be related to the construction/rehabilitation of infrastructures (sea walls and drainage systems), a decision was made to partnership with the UNOPS through an MoU so to gurantee speedy implementation.
Note on C11: Timoteo: Ladis, I unable to articulate here. I will leave this for you to have ago first.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Component 1 - Addressing climate change impacts on key infrastructure and settlements
| Rehabilitate, construct and upgrade coastal protection facilities to protect settlements economic and cultural infrastructure |  | Undertake EIA and feasibility study. Contract an engineering firm. Rehabilitate, construct and upgrade 1666 linear meters of seawall along the Ocean Road (Kivukoni-Upanga East) and Kigamboni (Mwalimu Nyerere Memorial Academy-staff quarters) |  | An agreement is being done with UNOPS to upgrade coastal protection (an agreement will be signed in Janaury 2015). TORs of EIA study developed. and TRES Consult (T) Limited has been procured to undertake EIA study from Janaury 2015. TORs of feasibility study developed and submitted to UNOPS. Baseline study has been completed with the new targets (145 meters of seawall upgraded along Kigamboni seawall; 221 meters of seawall constructed in Kigamboni; 800 meters of seawall upgraded along Ocean Road; 500 meters constructed along Ocean Road). Constrcution is expected to start from the second quarter of 2015. A UNOPS Engineer conducted a reconnaissance field mission to establish the overall projects status, scope and key stake holders expectations. UNOPS has also commenced preliminary discussions with specialist design consultancies for their expert inputs on the specialist design requirements for this project. | MU | 1666
| Cleaning up of the drainage channels, rehabilitation of storm drains |  | Develop TORs of the engineering firm. Undertake EIA and feasibility study. Contract an engineering firm for Rehabilitate/Cleaning and maintenance of five storm drains in Dar es salaam city centre. |  | An agreement is being done with UNOPS to clean up the drainage channels and rehabilitation of storm drains (an agreement will be signed in Janaury 2015). TORs of EIA study developed. and TRES Consult (T) Limited has been procured to undertake EIA study from January 2015. TORs of feasibility study developed and submitted to UNOPS. Baseline study has been completed. The new proposed sites are five namely: i) Tandale street in Tandale ward; ii) Kawe street in Kawe ward; iii) Bungoni Street in Buguruni ward; iv) Miburani-Mtoni Bustani streets in Mtoni ward; and v) Butiama Street (Butiama drainage) in Kijichi ward. Works are expected to start from the second quarter of 2015. | MU
Component 2 – Ecosystem-based Integrated Coastal Area Management
| Mangrove rehabilitation |  | Planting of resilient seedlings Dredging and clean-up operations Provision of small solar equipment Distribute fuel efficient cookstoves to 1,500 households Training district officers and community representatives on fuel efficient technologies and sustainable mangroves. |  | TORs of coastal zone management specialist developed. TORs of rural energy consultant developed. The procurement of the consultancies of coastal zone management specialist and rural energy consultancy done.Contracts are being finalized. Consultancies will start right from January 2015. Community training on renewable and efficient energy (through NGO and GreenJobs) scheduled for 18-22 December 2014. Community and user association training on sustainable mangrove management scheduled for 18-22 December 2014. | MS
| Coral reef rehabilitation and protection |  | Coral reefs rehabilitation Training fisheries and local government officers on coral reef conservation |  | TORs of coastal zone management specialist developed. TORs of reef specialist developed. TORs of NGO for reef rehabilitation developed. The procurement of the consultancies of reef specialist, coastal zone management specialist done. Contracts are being finalized. Consultancies will start right from January 2015. | MS
| Shoreline stabilization through reforestation |  | Re-planting of native and resilient trees |  | TORs of coastal zone management specialist developed. Procurement process of coastal zone management specialist done. Contract is being finalized to be signed by January 2015.Consultancy services will start right from January 2015. | MS
Component 3 – Knowledge, coastal monitoring and policy linkages
| Stocktaking |  | Undertake baseline survey and development of indicators and targets. Develop a database of information relevant to adaptation in Tanzania |  | TORs of the consultancy to undertake baseline study developed. Procurement of the firm or individual to undertake baseline study has been done (C4 EcoSolutions). The work of baseline study was completed in September 2014. Subsequent to the baseline study consultancy and as a result of the findings produced a revision of the log-frame was carried out to incorporate and/or adjust new indicators and targets.However, these changes to the Result Framework will have to be endorsed by the Project Steering Comittee at the next meeting scheduled by 30 Janaury 2015 after which the revised log-frame will be shared with the AF Sec. | MS
| Coastal monitoring and assessment |  | Technical assessment of the viability and resilience of proposed actions. Monitoring the key determinants of vulnerability i.e. SLR, water availability and precipitation patterns. Create Climate Change Observatory for Tanzania (CCOT) |  | Members of CCOT established and its TORs developed. The project will support the first meeting of CCOT scheduled for first half of 2015. | MU
| Policy linkages |  | Document lessons learned from project outputs. Review infrastructure maintenance programs of Dar es Salaam City, Temeke, Kinondoni and Ilala Municipalities. Develop an Ecosystem-Based Integrated Coastal Area Management Action Plan (EBICAM). |  | TORs of climate change knowledge management specialist developed. Procurement of climate change knowledge management specialist done. Contract is being finalized to be signed by January 2015.Consultancy services will start right from January 2015. TORs of the task force to develop EBICAM Action Plan of Dar es Salaam region developed. Task force to develop EBICAM formed. The second draft of EBICAM Action Plan of Dar es Salaam region developed. Consultative stakeholders workshop will be held in the first quarter of 2015. | MU
Project operation and management
| Procurement |  | Prepare procurement plans Procure consultancies Procure firms for goods and works services |  | Partnership on procurement process done with the VPO procurement unit, Senior Technical Adviser recruited. Procurement Plan for 2013 and 2014 prepared. Office supplies, computers and assoceries procured. Project car procured (Toyota Hilux Double Cabin registered as DFPA240). C4 EcoSolutions procured to update/develop indicators and targets. Out of 10 consultancies (4 are at the stage of signing the contracts; 2 have signed contracts; feasibility study to be undertaken by UNOPS; 3 consultancies will be advertised in January 2015). Out of 5 sub contracts (1 to be re-advertised in January 2015; UNOPS is being engaged for seawall and drainage sub contracts; 1 sub contracts to be advertised in January 2015). Purchase of 1,500 cookstoves to be done in the January 2015. UNOPS is being engaged for scoping and designs of the seawall and drainage systems and will be engaged for constrcution works. | MU
| Establish project management team |  | Establish the National project management team. Identify the Senior Technical Adviser (STA) of the project. Establish Project Steering Committee |  | The National Project Coordinator appointed. The project finance and administration appointed. The International Senior Technical Adviser recruited. The Project Steering Committee (PSC) formed and carried out the first and second meetings (3rd March 2014 and 22nd July 2014). Third meeting of PSC scheduled on 30 January 2015. The Project Technical Committee established in December 2013. | S
[5 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Eng. Ladislaus Kyaruzi
| Email: | leoky2009@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Recruitment of key personnel of the management team: The National Project Coordinator will be responsible for the overall day to day management of the project; Finance and administration assistant will provide finance and administration support; Senior Technical Adviser will provide overall technical guidance and support; and Focal person at Dar es salaam City Council will support overall implementation of the project activities in his areas. Joint Project Steering Committee of AF and LDCF projects has been formed with members from Vice President's Office, Dar es Salaam City Council and its three municipalities of Ilala, Kinondoni and Temeke, Ministry of Works, Ministry of Natural Resources and Tourism. TORs of all urgent consultancies have been finalized and procurement of almost all the required consultancies has been done and for the remaining positions the procurement process has been initiated. However, the project sustains significant delays primarily due to extensive delays in the national execution of procurement. Establishment of the procurement partnership between the project and the VPO procurement unit has helped to improve the process although not much because we still face some delays. This somehow will not be a big challenge since all the required consultancies for the first four years are being finalized. Out of 10 consultancies (4 are at the stage of signing the contracts in January 2015; 2 have signed contracts; feasibility study to be undertaken by UNOPS; 3 consultancies are being advertised in January 2015). Out of 5 sub contracts (1 which is NGO reef rehabilitation is being re-advertised in January 2015; it has been agreed seawall and drainage systems sub contracts will be undertaken by UNOPS; 1 sub contracts to be advertised in January 2015 and 1 sub contract, its activity of stabilization will start in year 4 of the project). Project work plan and procurement plan has been integrated in Vice President's Office (VPO) plans. The baseline study consultancy procurement has been finalized and the work to establish baseline and targets of the project finalized in September 2014. The challenge is the late start of baseline study (started in April 2014), which has affected a number of project activities such as EIA and feasibility study, seawall and drainage systems rehabilitation and construction. To overcome the delays the revision of the project budget and work plan was made in January 2014. The measure to overcome the delay is to start the activities, which do not depend on each other such as community trainings. Currently the agreement is being finalized between UNOPS and the Government of the United Republic of Tanzania (GoT). It is expected the engagement of UNOPS to lead infrastructure work will improve effectiveness of delivery for infrastructure component. Development of EBICAM Action Plan has started and the second draft is available. Trainings to the district officers and community representatives from Dar es salaam city council, municipalities of Ilala, Temeke and Kinondoni that will ensure the objectives of the project are met is scheduled for 18-22 December 2014.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component 1 - Addressing climate change impacts on key infrastructure and settlements
| Rehabilitate, construct and upgrade coastal protection facilities to protect settlements economic and cultural infrastructure |  | See above. |  | See above. | MU
| Cleaning up of the drainage channels, rehabilitation of storm drains |  | See above. |  | See above. | MU
Component 2 – Ecosystem-based Integrated Coastal Area Management
| Mangrove rehabilitation |  | See above. |  | See above. | MS
| Coral reef rehabilitation and protection |  | See above. |  | See above. | MS
| Shoreline stabilization through reforestation |  | See above. |  | See above. | MS
Component 3 – Knowledge, coastal monitoring and policy linkages
| Stocktaking |  | See above. |  | See above. | MS
| Coastal monitoring and assessment |  | See above. |  | See above. | MU
| Policy linkages |  | See above. |  | See above. | MU
Project operation and management
| Procurement |  | See above. |  | See above. | U
| Establish project management team |  | See above. |  | See above. | S
[5 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Lars Christiansen, UNEP TM
| Email: | lachr@dtu.dk
Please Provide the Name and Contact information of person(s) reponsible for completing the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | The project sustains significant delays primarily due to extensive delays in the national execution of procurement. Procurement of even relatively small national consultancy contracts (e.g. around $20,000) goes through an extensive 3 stage process and has to pass through VPO's procurement board at several points in the process. This policy along with other (to me currently unknown) administrative delays means that (based on experience) TORs can take up to 3 months to approve and advertise, and review/approval/interviews of candidates upwards of 6 months on top of that. A number of mitigating procedures were discussed with VPO and representatives of VPOs procurement unit in December 2013 (at UNEPs last visit), including streamlined processes and allocating budget to faciliation of intersessional sessions for the procurement board and more. Unfortunately, based on experience from the last round of consultancies, no major improvement in effectiveness of procurement has been observed (with consultancy contracts to be signed in December/January, 10 months would have passed from initial agreement between VPO and UNEP on TORs in March 2014). Similarly the baseline study (which has been a major bottleneck for progress on other activities) took a very long time to contract, thus delaying other activities (such as infrastructure works) depending on it. The proposed involvement of UNOPS to lead infrastructure work will hopefully help improve effectiveness of delivery for infrastructure elements (as well as provide high quality technical expertise and supervision of the works) and a number of major technical consultancies have now finally been filled as outlined by the implementing agency above. Procurement process delays remains a major risk and concern for UNEP, however, and will be a major discussion point in our upcoming mission to Tanzania in January.
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Note on F9: Timoteo: Again Ladis. I will leave this for you.
Note on F18: Timoteo: Ladis. I will this to you first.
Note on C28: Timoteo: Ladis. Please do attempt to integrate Lars comments here. I will finalise if necessary.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Component 1 - Addressing climate change impacts on key infrastructure and settlements
| Length of sea walls raised and rehabilitated (m) | Dar es salaam seawall (2.6km) showing signs of severe degradation at Ocean Road and Kingomboni | An agreement is being done with UNOPS to upgrade coastal protection (an agreement will be signed in January 2015). TORs of EIA study developed. and TRES Consult (T) Limited has been procured to undertake EIA study from Janaury 2015. TORs of feasibility study developed and submitted to UNOPS. Baseline study has been completed with the new proposed targets (145 meters of seawall upgraded along Kigamboni seawall; 221 meters of seawall constructed in Kigamboni; 800 meters of seawall upgraded along Ocean Road; 500 meters constructed along Ocean Road). Constrcution is expected to start from the second quarter of 2015. | 1335 linear meters of seawall rehabilitated along Ocean Road and Kingamboni
| Change in number of urban flooding events related to storm and severe rainfall | Average of 5 flooding events in Dar es Salaam city center during rainy seasons over the past 5 years | An agreement is being done with UNOPS to clean up the drainage channels and rehabilitation of strom drains (an agreement will be signed in Janaury 2015). TORs of EIA study developed. and TRES Consult (T) Limited has been procured to undertake EIA study from Janaury 2015. TORs of feasibility study developed and submitted to UNOPS. Baseline study has been completed. The new proposed sites are five namely: i) Tandale street in Tandale ward; ii) Kawe street in Kawe ward; iii) Bungoni Street in Buguruni ward; iv) Miburani-Mtoni Bustani streets in Mtoni ward; and v) Butiama Street (Butiama drainage) in Kijichi ward. Works are expected to start from the second quarter of 2015. | a 50% reduction in the number of flooding events during rainy season.
Component 2 - Ecosystem-Based Integrated Coastal Area Management (EBICAM)
| Number of households provided with efficient cookstoves | Average wood fuel consumption per capita in Tanzania is 1 to 1.3m3; fuelwood efficiency is estimated at less than 10% on average in all sites; estimated mangrove deforestation rate is 2% per year | Scheduled for the the first quarter of 2015. | at least 30% decrease in use of fuelwood; 1500 households have access to alternative and or efficient energy sources
| Area of mangroves under rehabilitation | there are approximately 2,000 ha of mangroves in Dar es Salaam surroundings | TORs of coastal zone management specialist developed. TORs of rural energy consultant developed. The procurement of the consultancies of coastal zone management specialist and rural energy consultancy done.Contracts are being finalized. Consultancies will start right from January 2015. Community training on renewable and efficient energy (through NGO and GreenJobs) scheduled for 18-22 December 2014. Community and user association training on sustainable mangrove management scheduled for 18-22 December 2014. | 40 hectares of mangroves under rehabilitation in severely degraded strands in Dar es Salaam area
| Area of reef rehabilitated | No recent local data available. Latest data sets show low biocover in existing reefs | TORs of coastal zone management specialist developed. TORs of reef specialist developed. TORs of NGO for reef rehabilitation developed. The procurement of the consultancies of reef specialist, coastal zone management specialist done. Contracts are being finalized. Consultancies will start right from January 2015. | 2000 m2 in front of Dar es Salaam, with an increase of 75% annually
| Km of shoreline stabilized using vegetation | rate of coastal erosion estimated between 3 and 8m per year according to recent site specific surveys | TORs of coastal zone management specialist developed. Procurement process of coastal zone management specialist done. Contract is being finalized to be signed by January 2015.Consultancy services will start right from January 2015. | 30,000m2 in Dar es salaam broader area
Component 3 - Knowledge, coastal monitoring and policy linkages
| Availability of a comprehensive baseline study for coastal vulnerability; available knowledge gathered | no such study; there is no recent comprehensive desk review of available knowledge | baseline study completed | 1 baseline study in year 1
| Effective implementation of clearing house function | There is no climate change clearing house mechanism | A clearing house function has been established. | clearing house function is operational by mid-term
| Cost-effective measures are identified for upscaling and policy uptake | ad hoc assessments available but none specific to this project | Associated activities to start from 2015 onwards | measures are identified for upscaling and policy uptake on an ongoing basis
| number of policy briefs provided to key sectors and regulators; number of workshops | While there is a good degree of information on climate change, there is no systematic effort to inform policy makers based on project utcomes | Inception workshop held from 29-30 November 2012.Project brief provided to stakeholders. | 3 briefing notes per year; 2 workshops during the project
| Amount dedicated to infrastructure maintenance from district budgets | infrastructure budgets within district administrations are low | Trainings to district budget and planning officers on district financing and budgeting including how to manage rehabilitated infrastructures and integrating adaptation concerns in local planning scheduled for 18-22 December 2014. | Dar es Salaam Municipal councils earmark appropriate annual allocations for infrastructure maintenance.
| Number of plans approved | no plans yet available but ICZM capacity exists | The second draft EBICAM Action Plan of Dar es Salaam region is available. | 1 plan

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The dedicated management team including Project Steering Committee (PSC), National Project Coordinator, Senior Technical Adviser and assistant administrative and financial manager for project coordination has asured that the project maintains its objectives. The Permanent Secretary of the Vice President's Office as the Chairperson of the PSC has made it possible to reduce unnecessary delays of this project and to take necessary measures. A formal partnership with the VPO procurement unit to create streamlined and dedicated processes for the project (e.g. on-demand meetings of the procurement board) has now been established by including a specific budget in the revised project budget to cover any unforeseen costs during the procurement processes. Furthermore, 2013, 2014 and 2015 project activities were/are included in the annual work plans of the VPO. This has somewhat improved the procurement process by being able to procure many consultancies at a time. To minimize further the potential risk with the procurement delays towards the construction/rehabilitation of infrastructures (sea walls and drainage system; the biggest outputs of the project) UNOPS is engaged by which all the procurement and feasibility studies towards the construction/rehabilitation of infrastructures (sea walls and drainage system) will be carried out by this UN unit.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Delay of the baseline study that was expected to be completed in the first year of the project has caused delays in the implementation of the project. The baseline study was completed in September 2014. EIA and feasibility studies could not be undertaken in 2014. As a measure, the firm to undertake EIA study has been contracted and UNOPS is being contracted to undertake feasibility study. Both studies will start in January 2015.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The baseline study has been completed. The major changes include targets of seawall from 1335m to 1666m to be rehabilitated and constrcuted; five sites of drainage channels to be cleaned and rehabilitated; 1,500 efficient cookstoves will be provided to 1,500 households. This means each household will get one cookstove. As previously mentioned, the full revised results framework will be shared with AFsec after formal approval by the PSC.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Within the national team, a finance and administration assistant is a woman which is equal to 50%. In the national inception workshop, approximately 32% of the participants were women.
Lessons and measures related to coordination with the LDCF project 'Developing core capacity to address adaptation to climate change in Tanzania in productive coastal zones' | The LDCF and AF projects are very closely coordinated, and in practice implemented almost as one. A joint project coordination team has been established at VPO, with one project coordinator handling the AF project and one handling the LDCF project. The two are reporting to, and coordinated through, the assistant director of environment assessment Mr Richard Muyungi. In practice the three are working very closely on a daily basis – i.e. sitting in the same office, having joint meetings etc. Additional examples of the close coordination and collaboration taking place between the two projects include: Joint project steering committee with joint meetings, joint technical committee, joint baseline study, a shared Senior TechnicalAdviser etc. All of this reduces costs, and assures that relevant lessons, outputs and expertise are consistently shared between the two projects. All joint activities and financial contributions are proportionately shared and kept completely separate to avoid co-mingling.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 4 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 4.2 | 5 | 2
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 4 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 4.2 | 2 | 0
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5 | 40 ha mangrove planted, 2000m2 coral reef rehabilitated | 0
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 5 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 5 | 40 ha mangrove planted, 2000m2 coral reef rehabilitated. | 0
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 7 | One (1) Ecosystem Based Integrated Coastal Area Management Plan (EBICAM) with CC adaptation action plan for the coastal region is approved - 5 fully integrated | 1 (none)
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 7.2 | One (1) Ecosystem Based Integrated Coastal Area Management Plan (EBICAM) with CC adaptation action plan for the coastal region is approved | 0 - no
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.