## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 01 November 2015 to 31 Octoberl 2016
| Project Title: | Implementation of Concrete Adaptation Measures to Reduce Vulnerability of Livelihoods and Economy of Coastal Communities of Tanzania
| Project Summary: | Tanzania is impacted by climate change mainly through its effects on rainfall patterns, temperature extremes and sea level rise. The direct impacts of these changes are likely to result in more frequent and intense droughts, the destruction of infrastructures in the coast and inland through flooding, inundation, erosion and storms; if no action is taken, the socio-economic impacts will include agricultural yield decreases, decreased water availability and quality, and losses of lives and livelihoods, as well as the accelerated degradation of ecosystems that form the basis of the Tanzanian economy. To respond to this, the government developed a project proposal to adapt to the climate change in the coast of Dar es salaam. In December 2011 the Adaptation Fund Board considered the proposal and approved a five years project with a total of USD 5,008,564. Implementation of the project started in 1 November 2012. The project consists of the following outcomes, supported by on the ground activities implemented primarily in the vicinity of Dar Es Salaam: 1. Adverse impacts of SLR and floods on coastal infrastructures and settlements are reduced. 2. Coastal ecosystems are rehabilitated and Integrated Coastal Area Management is implemented. 3. Knowledge of climate impacts and adaptation is increased. The project is being implemented by the United Nations Environment Programme (UNEP) and executed by the Vice Presidents Office (Division of Environment) in close cooperation with sectoral ministries as well as Dar es Salaam City Council and Municipalities of Ilala, Temeke and Kinondoni.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AFB-5060-1111-2G48 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNEP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | United Republic of Tanzania | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Dar es Salaam City (Ocean Road; Kigamboni-Mwalimu Nyerere Memorial Institute; Kinondoni Municipality:Tandale street in Tandale ward and Kawe street in Kawe ward; Ilala Municipality: Bungoni street in Buguruni ward; Temeke Municipality: Miburani-Mtoni Bustani streets in Mtoni ward and Butiama street (Butiama drainage) in Kijichi ward;Sarender Bridge, Kunduchi, Ununio and Mbweni. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2011-12-14
IE-AFB Agreement Signature Date: | [8 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-11-01 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned):
| Terminal Evaluation Date: | November, 2015-January 2016 (MTR - Done), November 1, 2017 (Terminal - planned)
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Inception Workshop Report 2012; Quarterly Expenditure Reports (Q4,2012, Q1, Q2, Q3&Q4, 2013; Q1,Q2,Q3,Q4, 2014, Q1, Q2&Q3, 2015); Project brief report to the Planning Commission of the United Republic of Tanzania for the Government; TORs of: Joint Project Steering Committee; National Project Coordinator; Senior Technical Adviser; Finance and Administrative Assistant; Tender Evaluation Repors for supply of the project vehicle; evaluation report for experssion of interest for a position of senior technical adviser; evaluation report for a position of consultancy services for development of a baseline survey and development of indicators and various consultancies. Finalized TORs of: (Feasibility Study, EIA study for the proposed Construction and Rehabilitation of Seawall at Ocean Road and Kigamboni (Mwalimu Nyerere Memorial Institute) and Rehabilitation of Drainage Systems; Climate Change Knowledge Management Specialist; Coastal Zone Management Specialist; Memorandum of Understanding with UNOPS for constrcution and rehabilitation of seawall of Kigamboni and Ocean Road and drainage systems; Reef specialist, Rural energy consultant, mangrove specialist,Coastal Reabilitation specialist, Mangrove specialist, sub-contract env.engineering firm for mangrove rehabilitation, Climate Change Observatory for Tanzania, Task Force to develop EBICAM Action Planand sub-contract NGO reef rehabilitation ); Evaluation Report of Expression of Interest Tender No. ME 002/2012-13/DE/C/07 for Re-advertized Consultancy services for Development of a baseline survey and development of indicators and targets, Procurement plan 2014, Revised Project Budget, Revised Work Plan, Variance of the revised project budget, Report of the development of the Terms of Reference of various consultancies. Baseline study report,2014. PPR (November 2012-October 2013, November 2013 to October 2014). PPR B (1 November 2013 to 30 April 2014, 1 November 2014 to 30 April 2015), Audit reports 2013 and 2014, Final Draft Ecosystem Based Intergrated Coastal Area Management (EBICAM) Action Plan for Dar es Salaam region. Brief report of UNEP task manager and senior technical adviser mission, 2013, Annual physical and financial performance for year 2013 and 2014, draft training materials on on appropriate energy technologies, Criteria of efficient cookstoves, Evaluation and negotiation reports of various consultancies, Bids amount of the consultancies, Procurement Plan 2015, Procurement management reporting, Inception reports of: Reef specialist, Climate change knowledge management specialist, Coastal zone management specilaist, Rural energy consultant, Coastal rehabilitation specialist, Mangrove specialist, NGO for reef rehabilitation, NGO for mangrove reahbilitation, 3rd Revised budget, Revised Work Plan, Agreement between VPO and UNOPS, Management response to baseline study, Revised Results Framework, Action Plan for years 2012,2013,2014,2015,2016&2017, Steering Committee minutes (1st,2nd and 3rd meetings), Training report, Workshop reports, Contracts of consultancies. Second contract of STA, Senior technical Adviser (STA) Work Plans, STA Mission Reports (1-4); STA Quarterly Reports (2013-2014-2015); EIA study Report, Feasibility study and Mid term review reports. Revised budget. Assessment report of the viability and resilience of proposed actions under the project. Training Material On Promotion of Solar Cookers for Inclusive Growth and Environmental Conservation; Training Material On Potential of Urban Forestry in Dar Es Salaam City for Inclusive Growth and Environmental Conservation ; Training Material to Producers and Users of Biomass Stoves; Establishment of Climate Change Observatory for Tanzania (CCOT) | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.unep.org/climatechange/adaptation/AccessToAdaptationFinance/AdaptationFundProjects/Tanzania | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Kanizio Fredrick Manyika | Dominican Republic
| Email: | Freddy_Manyika@hotmail.com | Ecuador
| Date: | 2016-10-31 | Egypt
| Government DA |  | El Salvador
| Name: | Eng. Ngosi C. X. Mwihava | Equatoral Guinea
| Email: | nmwihava@gmail.com | Eritrea
| Date: | 2016-10-31 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Lars Christiansen, UNEP task manager | Fiji
| Email: | lachr@dtu.dk | Finland
| Date: | 2016-10-31 | France
| Executing Agency |  | Gambia
| Name: | Vice President's Office | Georgia
| Email: | ps@vpo.go.tz | Germany
| Date: | 2016-10-31 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31 October 2016
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31st October 2016(USD)* | 3147407
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1: Sea wall raised, rehabilitated and constructed in areas showing particular damage | 1314741
| Output 1.2: Effective storm and flood drainage systems in urban areas and near coastal communities cleaned, rehabilitated | 430000
| Output 1.3: EIA and feasibility study undertaken | 10340.31
| Output 2.1: Mangrove rehabilitated through planting of resilient seedlings, dredging and the creation of no-take buffer zones | 31683
| Output 2.2: Appropriate alternative energy (efficient cook stoves, small solar) technology transferred for avoided deforestation including through training | 16461.28
| Output 2.3: Coral reef rehabilitated and protected in coastal sites | 57500
| Output 2.4: Shoreline rehabilitated and stabilized using indigeneous resilient trees and grasses | 10000
| Output 3.1: Performance of a baseline study based on coastal vulnerability | 0
| Output 3.2: Climate change observatory for Tanzania for ongoing monitoring of CZM and coastal environmental status and scientific research created and operational | 12742
| Output 3.3: Assessment of the economic viability and practical feasibility of adaptation measures (i.e. through undertaking cost-benefit analyses) | 0
| Output 3.4:District level administration have the capacity to adequately manage rehabilitated infrastructure | 21983.24
| Output 3.5: One EBICAM action plan for the coastal region approved | 29543
| Monitoring and Evaluation | 25247.79
| Project Execution | 57637.53
| TOTAL | 2017879.15
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: Sea wall raised, rehabilitated and constructed in areas showing particular damage | 616855.6 | 2017-06-30
| Output 1.2: Effective storm and flood drainage systems in urban areas and near coastal communities cleaned, rehabilitated | 430000 | 2017-06-30
| Output 1.3: EIA and feasibility study undertaken | 16396.08 | 2016-09-30
| Output 2.1: Mangrove rehabilitated through planting of resilient seedlings, dredging and the creation of no-take buffer zones | 13917 | 2017-06-30
| Output 2.2: Appropriate alternative energy (efficient cook stoves, small solar) technology transferred for avoided deforestation including through training | 41923.72 | 2017-03-30
| Output 2.3: Coral reef rehabilitated and protected in coastal sites | 33300 | 2017-05-30
| Output 2.4: Shoreline rehabilitated and stabilized using indigeneous resilient trees and grasses | 40300 | 2017-10-30
| Output 3.1: Performance of a baseline study based on coastal vulnerability | 0 | 2014-09-30
| Output 3.2: Climate change observatory for Tanzania for ongoing monitoring of CZM and coastal environmental status and scientific research created and operational | 50046.49 | 2017-10-30
| Output 3.3: Assessment of the economic viability and practical feasibility of adaptation measures (i.e. through undertaking cost-benefit analyses) | 10000 | 2017-02-28
| Output 3.4:District level administration have the capacity to adequately manage rehabilitated infrastructure | 46284.27 | 2017-10-30
| Output 3.5: One EBICAM action plan for the coastal region approved | 52199.51 | 2017-06-30
| Monitoring and Evaluation | 50272.71 | 2017-10-30
| Project Execution | 67285.62 | 2017-10-30
| TOTAL | 1468781
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Co-financing is not applicable to the project
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Operational: The multiple ongoing initiatives on climate adaptation in Tanzania could cause operational delays for this project | Low | The appointed National Project Coordinator, Senior Technical Adviser and Assistant Administrative and Financial Manager as a dedicated team for project coordination ensure the project maintains its objectives. In addition, the Project Steering Committee (PSC) has helped to resolve pending issues allowing a smooth progress of the planned activities. The Chairperson of the PSC who is the Permanent Secretary of the Vice President's Office ensures that no unnecessary delays of this project. PSC has been able to meet in 3rd March 2014, 22nd July 2014; 16 February 2015 and 11 March 2016. Appointed Focal points have remained the same people in all project sites, that are: Ilala, Temeke and Kinondoni Municipalities and Dar es salaam city council.
Political: District-level stakeholders and administrations show low engagement for adaptation measures | Low | The Project Steering Committee that was established during the commencement of the project continues to provide provide overall guidance with regard to implementation of the project activities. Its members are: Permanent Secretary– Vice President’s Office (Chair); Director of Environment-Vice President’s Office; Director of Environment- First Vice President’s Office –Zanzibar; Director- Dar es Salaam City Council; District Executive Director – Pangani District Council; District Executive Director – Bagamoyo District Council; District Executive Director – Rufiji District Council; Municipal Executive Director – Temeke Municipal Council; Municipal Executive Director – Ilala Municipal Council; Director of Forest – Ministry of Natural Resources and Tourism; Director of Water Resources – Ministry of Water; Director- Ministry of Works; UNEP Task Manager of the Project; and Assistant Director of Environmental Assessment- Vice President’s Office (Secretary). The Steering Committee met on 3rd March 2014, 22nd July 2014, 16th February 2015 and 11 March 2016. In addition, appointed focal points from the project sites, namely: Dar es Salaam City Council, Ilala, Temeke and Kinondoni Municipal Councils have remained the same sinec the inception of the project.The trainings were conducted in December 2014 to the district representatives of the coastal communities, fishermen associations, municipal planners, forest officers and environment of the Municipalities of Ilala, Kinondoni and Temeke municipalities and Dar es Salaam City Council continue to enhance their engagement for adaptation measures on the coastal and marine environment.
Political: the project could experience difficulties in coordination and oversight for activities delivered at various sectors, levels of governments or by multiple partners | Low | The dedicated personnel for project management been established through the Vice President‘s Office coordinates and monitors the project outputs and activities. Close collaboration among various ministries and stakeholders is provided through among others the project steering committee. With the realisation of the first, second and third (and subsequent) Project Steering Committee meetings and appointement of the Focal Points from the project areas, a greater cross-intitunional coordination has been achieved.
Environmental: Extreme weather events such as tropical storms, floods or droughts could hinder progress in ecosystem rehabilitation and infrastructure activities | Medium | The designs of the protective infrastructure rehabilitation are according to the best available technical standards and best available technology. The baseline study provided appropriate data and information to be used. Rehabilitation and infrastructure work has started, and the geotechnical and topographical surveys are completed. Construction of seawall is progressing well.
Financial: market and price fluctuations could cause price variations and variations in costs of certain project activities, leading to budgetary constraints. | Low | The feasibility study established the possible costs for the project activities. Contracts of all costs of consultancies for main project activities such seawall works, drainage works, mangrove and coral reef rehabiltation have been signed with agreed costs. Project activities have commneced and are in good progress as per agreed workplan and budgets. In this regards, price variation and cost variation pose minimal budgerary constraints to the project activities since these was taken into account in the contracts.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Vice President's Office (VPO) "the executing entity" low executions rate due to internal procurement procedures. | Medium | A formal partnership of the project team with the VPO procurement unit continued to create streamlined and dedicated processes for the project. Furthermore, 2013, 2014, 2015 and 2016 project activities were included in the annual work plans of the VPO. This arrangement has improved the procurement process by being able to procure many consultancies at a time. To date, 12 consultancies out of 14 (equivalent to 85.7%) have been procured. Procurement of Coastal climate adaptation consultant and labor costs for shoreline stabilization will be done in the first half of 2017.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Even though procurement remains a risk, formal partnership with the VPO procurement unit that was established in order to create a streamlined and dedicated process for the project continued to serve as measure to address this risk. Most of the procured consultanties are progressing well with close monitoring of the Steering Comittee, project management team, focal points and other stakeholders at both local and national level. Monitoring is likely to intensify as the project activities continue to progress .

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Component 1 - Addressing climate change impacts on key infrastructure and settlements
| Rehabilitate, construct and upgrade coastal protection facilities to protect settlements economic and cultural infrastructure |  | Contract an engineering firm to rehabilitate and construct seawalls. Rehabilitate, construct and upgrade 1400 linear meters of seawall along the Ocean Road and Kigamboni (Mwalimu Nyerere Memorial Academy-staff quarters). Documentation of seawall rehabilitation and construction. |  | Final detailed designs and procurement process approved by VPO on 8 January 2016. Geotechnical and topogreaphgical surveys completed. The target has been comfirmed to be 1400m from 1335m. Dezo Civil Contrators Company Limited was contracted on 13th September 2016 by UNOPS to rehabilitate, upgrade and construct 1400 linear meters of seawalls at Ocean/Obama road (950m) and Kigamboni (Mwalimu Nyerere Memorial Academy (450m).Mobilization and site establishment is at 100 complete.At Ocean Road Seawall site, the coffering is at 12% complete while the demolition of the existing wall is at 3% complete.Construction works of the seawalls is ongoing and expected completion is June 2017. Mhandisi consultancy Ltd was recruited as local supervising engineering firm. | S
| Cleaning up of the drainage channels, rehabilitation of storm drains |  | Contract an engineering firm for Rehabilitate/Cleaning and maintenance of five storm drains in Ilala, Temeke and Kinondoni Municipalities. Rehabilitate/Cleaning and maintenance of five storm drains in Ilala, Temeke and Kinondoni Municipalities. Documentation of drainage systems activities Undertake trainings on ecosystem based coastal adaptation |  | Final detailed designs and procurement process approved by VPO on 8 January 2016. Geotechnical and topogreaphgical surveys completed. Dezo Civil Contrators Company Limited contracted by UNOPS to rehabilitate, upgrade and construct two sites of Bungoni and Mtoni drainages on 13th September 2016. The two sites (i.e., Bunguni, Ilala and Mtoni, Temeke) were approved by Adaptation Fund Board in May 2016. Site clearance at Miburini-Mtoni Bustani Drain and Bungoni Street Drain is complete. The contractor commenced physical works at Miburini-Mtoni Bustani Drain and Bungoni Street Drain. At Ilala Bungoni Street Drain site, the site clearance is at 100% complete while the backfilling is at 25% and the concrete works at 15% complete.Construction of drainage at Bungoni, Ilala has staretd and 200m have been already been rehabilated. At Temeke Mtoni Street Drain site, the site clearance is at 80% complete. Rehabilitataion at Mtoni, Temeke drainage awaits conclusion with respect to the difference in slopes at Kilwa Road culvert and Temeke - Mbagala road culverts | S
| EIA and feasibility study |  | Undertake EIA and feasibility study in areas of seawalls and drainage systems. Establish procurement partnership |  | TRES Consult (T) Limited was procured to undertake EIA study. EIA Report was approved on 13th September 2016 to allow contsruction works works to commence. Feasibility study was undertaken by ARU Company. Final feasibility study Report is available. Partnership on procurement process has been established with the VPO procurement unit and its budget line set in the budget revision. | S
Component 2 – Ecosystem-based Integrated Coastal Area Management
| Mangrove rehabilitation |  | Procure seedlings, saplings and materials for mangrove rehabilitation. Undertake trainings to promote conservation of rehabilitated areas within mangroves. Planting of resilient seedlings. |  | Community Distinguished and Environmental Conservation (CODECO) recruited in September 2015 to rehabilitate mangroves. Community sensitization has been undertaken. Reconnaissance to the sites has been done. Areas to plant mangroves identified (Salender Bridge, Ununio, Kunduchi and Mbweni). Training to the community representatives and municipal officers from Ilala, Temeke and Kinondoni municipalities and user association training on sustainable mangrove management conducted on 18-22 December 2014. The mangrove specialist was procured in August 2015. Suitable mangrove species for each project site identified. i.e. Selander Bridge (Avicennia marina); Kunduchi (A. marina and C. tagal); Ununio (A. marina, C. tagal and B. gymnorrhizha) and Mbweni (A. marina, C. tagal and B. gymnorrhizha). Planting (area of 40ha)will be done during rainy season in March 2017. | MS
| Appropriate alternative energy |  | Distribute fuel efficient cookstoves to 1,500 households. Procure rural energy consultant to prepare to prepare trainings materials on appropriate alternative energy technologies (efficient cookstoves, small solar). Training district officers and community representatives on fuel efficient technologies |  | Rural energy consultant was procured in January 2015. Trainings materials on appropriate alternative energy technologies have been prepared; selection criteria of efficient cooking stove have been established. 3,000 efficient cookstoves were purchased and distribution to 3,000 households, ditribution is ongoing. Community training on appropriate alternative energy was undertaken from 18-22 December 2014. | S
| Coral reef rehabilitation and protection |  | Restore live coverage, using in situ techniques for coral breeding and transplantation. Undertake awareness raising to fisheries and local government officers in order to further reduce unsustainable fishing methods and reef uses. Analyse on lab-agri research. |  | First phase of restoring degraded coral reefs at Sinda and Mwakatumbe islands marine reserve has been done(the area rehabilitated is 2000m2) and is under monitoring.The second phase of coral planting will involve encrusting/massive coral species. Reef specialist consultant was procured in January 2015. The NGO for reef rehabilitation activity was procured in September 2015. Training manuals and materials on conservation of coral reefs as well as sustainable fishing methods prepared. Awareness to fisheries and local government officers from Ilala, Temeke and Kinondoni municipalities and Dar es Salaam city in order to further reduce unsustainable fishing methods and reef uses conducted on 18-22 December 2014. | S
| Shoreline stabilization through reforestation |  | Replant native and resilient trees including bushes and grasses in sufficient density, along the shore with a particular focus on the rehabilitated infrastructures Procure coastal climate adaptation consultant. Shoreline stabilization labour cost. |  | Replant native and resilient trees including bushes and grasses in sufficient density, along the shore with a particular focus on the rehabilitated infrastructures will start in June 2017. Indigenous species have been identified and will be restored after seawalls cosnctruction. | MS
Component 3 – Knowledge, coastal monitoring and policy linkages
| Stocktaking |  | Undertake baseline survey and development of indicators and targets. Develop a database of information relevant to adaptation in Tanzania |  | Baseline study was completed in September 2014. The findings from the baseline report were used to revise the log-frame. The Results Framework and management response were endorsed by the Project Steering Committee on 16th February 2015 and shared with the AF Sec. Development of the database of relevant information of the project is being undetaken by through various consultancies and the project team. | S
| Coastal monitoring and assessment |  | Technical assessment of the viability and resilience of proposed actions. Monitoring the key determinants of vulnerability i.e. SLR, water availability and precipitation patterns. Create Climate Change Observatory for Tanzania (CCOT). Organize meetings of CCOT. |  | The first meeting of CCOT was undertaken in October 2016. TOR's of the coastal rehabilitation specialist developed. Procurement of the coastal rehabilitation specialist to advise on the establishment of CCOT and undertake technical assessment of the viability and resilience of the proposed project actions was done in July 2015. | MS
| Policy linkages |  | Document lessons learned from project outputs. Review infrastructure maintenance programs of Dar es Salaam City, Temeke, Kinondoni and Ilala Municipalities. Develop an Ecosystem-Based Integrated Coastal Area Management Action Plan (EBICAM). Organise an inception workshop. Organize policy briefing workshops.Training district administration on budgetary allocations for rehabilitated infrastructures. |  | A first policy briefing workshop was held from 27 June to 1 July 2016. Training district administration on budgetary allocations for rehabilitated infrastructures was undertaken from 18-22 December 2014. | S
Project operation and management
| Procurement |  | Prepare procurement plans Procure consultancies Procure firms for goods and works services Procure a project vehicle and ensure its maintenance. Purchase computers and accessories. |  | Procurement Plan for 2016 prepared. 3000 Energy Efficient cookstoves were procured in October 2016. UNOPS was engaged for overseing procurement of consultancies for construction and rehabilitation of seawalls and drainage works. Senior Technical Adviser was given a new contract. | S
| Monitoring and evaluation |  | Facilitate auditing. Perform mid-term evaluation and cost-effectiveness assessment. Travel to sites. Undtertake steering committee and technical committee meetings. Bank transfer and statements. Perform final evaluation. |  | Audit report for 2015 is being finalised by the office of the Government Audit and Control General. Mid term review (MTR) was done by Baastel company based in UK. MTR report is available and management response on the recommendation were prepared. The fourth meeting of the Project Steering Committee (PSC) was held on 11 March 2016. The Project Technical Committee was established in December 2013. | S
| Establish project management team |  | Establish the National project management team. Procure the Senior Technical Advisor. |  | The International Senior Technical Adviser was given new contract that was signed in August 2016. In addition, a new National Project Coordinator (NPC) was appointed in October 2016 after the former NPC moved to another office. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: |  |  | Kanizio Fredrick Manyika
| Email: | Freddy_Manyika@hotmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Despite the late commencement of most project activities, the partneship arrangement in procurement process seems to expidite the procurement process and service delivery. Most project seemed to have attained remarkable achievement during the year 2016 as many of the project activities, including cleaning and rehabilitation of the drainage systems, mobilization and construction and rehabilitation of seawalls have been initiated or rather completed. Most project activities are already showing positive progress and are on track. However, Mtoni Bustani street drain levels between Mbagala and Kilwa culverts have presented a design and implementation challenge to the project. This is due to the specialist nature of the works, the varied scope and the geographical spread of the works sites that was unforeseen are likely to affect the completion of the project activities. In addition, rainy season may affect or slow down some site works. However, most of the activities are expected to be completed as planned.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component 1 - Addressing climate change impacts on key infrastructure and settlements
| Rehabilitate, construct and upgrade coastal protection facilities to protect settlements economic and cultural infrastructure |  | See above. |  | See above. | S
| Cleaning up of the drainage channels, rehabilitation of storm drains |  | See above. |  | See above. | S
| EIA and feasibility study |  | See above. |  | See above. | S
Component 2 – Ecosystem-based Integrated Coastal Area Management
| Mangrove rehabilitation |  | See above. |  | See above. | MS
| Appropriate alternative energy |  | See above. |  | See above. | S
| Coral reef rehabilitation and protection |  | See above. |  | See above. | S
| Shoreline stabilization through reforestation |  | See above. |  | See above. | MS
Component 3 – Knowledge, coastal monitoring and policy linkages
| Stocktaking |  | See above. |  | See above. | S
| Coastal monitoring and assessment |  | See above. |  | See above. | MS
| Policy linkages |  | See above. |  | See above. | S
Project operation and management
| Procurement |  | See above. |  | See above. | S
| Monitoring and evaluation |  | See above. |  | See above. | S
| Establish project management team |  | See above. |  | See above. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Lars Christiansen, UNEP TM
| Email: | lachr@dtu.dk
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | UNEP TM: The project has made significant progress on practically all activities during 2016, not least the completion of contracting (through UNOPS) for sea wall and drainage activities, which are now on track for completion by mid 2017. Mangrove and coral reef activities are also progressing well and on target during 2017. It seems likely that the project can close on time and deliver on all or most of expected targets.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Component 1 - Addressing climate change impacts on key infrastructure and settlements
Quantitative | Length of sea walls raised and rehabilitated (m) | Dar es salaam seawall (2.6km) showing signs of severe degradation at Ocean Road and Kingomboni | Mobilization and site establishment is at 100 complete. 86m along Ocean Road and 83m Kigamboni have been reconstructed/rehabilitated.At Obama/Ocean Road Seawall site, the coffering is at 12% complete while the demolition of the existing wall is at 3% complete. At Kigamboni Seawall site, the coffering is at 25% complete while the demolition of the existing wall is at 57% complete and the formwork to base is at 80% complete. | 1400 linear meters of seawall rehabilitated along Ocean Road and Kingamboni
Quantitative | Length of drainage channels contructed, rehabilitated and upgraded (m) | A total length of 6650m showing severe degradation. This is a total length of four sites of Butiama: 1650m, Kawe: 2650m, Bungoni: 1050m and Mtoni: 1300m. | Site clearance on Miburini-Mtoni Bustani Drain is 80% complete and at Bungoni Ilala, the site clearance is at 100% complete while the backfilling is at 25% and the concrete works at 15% complete. Street Drain have been completed.400m of drainage Bungoni and 400m at Mtoni channels have been cleaned. 200m in Ilala Bungoni have been rehabilitated. | By project end-point, at least 2300m of drainage channels cleaned and rehabilitetd
Component 2 - Ecosystem-Based Integrated Coastal Area Management (EBICAM)
Quantitative | Number of households receiving: i) efficient cookstoves; and ii) training on optimal use and maintenance of these stoves (disaggregated by age and gender). | Average wood fuel consumption per capita in Tanzania is 1 to 1.3m3; fuelwood efficiency is estimated at less than 10% on average in all sites; estimated mangrove deforestation rate is 2% per year | 3,000 efficient cookstoves have been purchased and disbribution ongoing | By project end-point, at least 1,500 households from Ilala, Kinondoni and Temeke Municipal Councils
Quantitative | Area of mangroves under rehabilitation | there are approximately 2,000 ha of mangroves in Dar es Salaam surroundings | Community Distinguished and Environmental Conservation (CODECO) recruited in September 2015 to rehabilitated mangroves. Community senstization has been undertaken. Reconnaissance to the sites has been done. Areas to plant mangroves identified (Salender Bridge, Ununio, Kunduchi and Mbweni). Training to the community representatives and municipal officers from Ilala, Temeke and Kinondoni municipalities and user association training on sustainable mangrove management conducted on 18-22 December 2014. The mangrove specialist was procured in August 2015. Suitable mangrove species for each project site identified. i.e. Selander Bridge (Avicennia marina); Kunduchi (A. marina and C. tagal); Ununio (A. marina, C. tagal and B. gymnorrhizha) and Mbweni (A. marina, C. tagal and B. gymnorrhizha). Planting (area of 40ha)will be done during rainy season in March 2017. | 40 ha of mangrove rehabilitated in one or more of the following areas: Salender Bridge, Kunduchi, Mbweni and Ununio. 65% survivorship of mangrove species was confirmed as a target.
Quantitative | Area of reef rehabilitated | No recent local data available. Latest data sets show low biocover in existing reefs | Restoration of 2,000m2 area of coral reefs has been rehabilitated in the first phase. Survivorship is under monitoring. | 2000 m2 under rehabilitation. 1300m2 (65%) survivorship of coral reefs was confirmed as a target.
Quantitative | Km of shoreline stabilized using vegetation | rate of coastal erosion estimated between 3 and 8m per year according to recent site specific surveys | Replant native and resilient trees including bushes and grasses in sufficient density, along the shore with a particular focus on the rehabilitated infrastructures will start in June 2017. Species have been identified. | At least 56,430 m2 of coastal vegetation rehabilitated using three or more fast-growing plant species. 65% survivorship of shoreline vegetation species was confirmed as a target.
Component 3 - Knowledge, coastal monitoring and policy linkages
Quantitative | Availability of a comprehensive baseline study for coastal vulnerability; available knowledge gathered | No baseline data | 1 baseline study was completed in September 2014. | 1 baseline study in year 1
Qualitative | Effective implementation of clearing house function | No baseline data | Members of CCOT established and the TORs were developed. The first meeting of CCOT was conducted in October 2016. | clearing house function is operational by mid-term
Qualitative | Cost-effective measures are identified for upscaling and policy uptake | No baseline data | Coastal rehabilitation specialist procured in July 2015 to identify cost effective measures. The consultant submitted the inception report that was approved in October 2015. | At least 1 report.
Quantitative | number of policy briefs provided to key sectors and regulators; number of workshops | No baseline data 0 workshops | 1 policy workshop held in July 2016. 1 workshop on development of EBICAM Action Plan held in October 2016. To date two documents that could be categorized as 'policy briefs' have been produced: 1. Household Energy Options for Adaptation Measures to Reduce Vulnerability to Impact of Climate Change in Coastal Region and 2. EIA study of the proposed seawall and drainage systems. | Annually, 2 policy briefs (1 on measures to adapt to climate change, 1 on general lessons learned).2 workshops (1 on cost-effective measures to adapt to climate change, 1 on general lessons learned).
Quantitative | Number of reports developed through the AF project on required district budget allocations to maintain infrastructure for adaptation to climate change. | 0 | 1 draft report on district level infrastucture maintainance programme available. | 1 report.
Quantitative | Number of plans approved | no plans yet available but ICZM capacity exists | Inception workshop was held 29-30 October 2012. Procurement of climate change knowledge management specialist was done in January 2015. The draft EBICAM Action Plan of coastal regions of Tanzania (Dar es Salaam, Lindi, Mtwara, Tanga and Coast) and Zaznzibar developed. First consultative stakeholders workshop to validate the draft EBICAM Action Plan was held 23-24 April 2015.A first policy briefing workshop was held from 27 June to 1 July 2016. Training district administration on budgetary allocations for rehabilitated infrastructures was undertaken from 18-22 December 2014. | One EBICAM Action plan of Region approved by end of project.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | It is paramount to fully explore and understand the implications of the institutional arrangements not only regarding the technical capacity to implement and execute project activities, including procurement of goods and services. This issues need to be taken into account in the project design. This can help to avert unforseen delays in the procurement process. Having sufficient and robust baseline data is important for the well designing of the project. It is better to concentrate efforts in a small number of project activities and sites in order to bring more impact of the project. There is need for involvement of multistakeholders (including spacial planning) in project design and implementation so as to be able to take on board future plans of the project site. It is critical that project design recognizes the importance of closely involving local stakeholders in the design and implementation of the project.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Delay of the baseline study that was expected to be completed in the first year of the project has caused delays in the implementation of the project. The baseline study was completed in September 2014. EIA and feasibility studies could not be undertaken in 2014. As a measure, the firm to undertake EIA study has been contracted and UNOPS contracted to work on seawall and drainage rehabilitation and construction and feasibility study. Delays in procurement of consultancies delayed the implementation of the project. As a meausre all necessary consultancies were launched at the same time where currently about 88% of all required consultants have signed contracts. Change of paying system of UNEP to Umoja system caused a bit delay of activities for the period of July-December 2015 since the project lacked funds within this period. The lesson is that it might be of help to request enough funds throughout the year based on the annual work plan. Disbursement of funds was no longer a challenge after Umoja system was sorted out. However, planting of mangroves has delayed awaiting for the rainy season in March 2017. In addition, new councilors following General election in 2015 delayed processing of building permits by the Dar es salaam City Council for Ocean Road and Kigamboni Sea Wall Sites and by Ilala Municipal Council for Bungoni Drainage Site. Presence of focal points in the municipalities helped clarify the matter and buiding permits were issued.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | 145 meters of seawall to be upgraded along Kigamboni seawall, 221 meters of seawall to be constructed in Kigamboni, 800 meters of seawall to be upgraded along Ocean Road and 500 meters to be constructed along Ocean Road. Five sites of drainage channels to be cleaned and rehabilitated. Originally a 50% reduction in the number of flooding events during rainy season in targeted sites was considered as target; Originally on shoreline stabilization, 1500m (20m wide) was a target but now by project end-point, at least 56,430 m2 of coastal vegetation rehabilitated using three or more fastgrowing plant species. The survivorship of species will be 65% survivorship of mangrove species, 65% survivorship of shoreline vegetation species and survivorship of coral reefs will be determined in area. One plan approved by end of project was expected but now its clear is one EBICAM Action plan of Dar es Salaam Region approved by end of project.The full revised results framework was shared with AFsec in February 2015. 3000 cookstoves were bought and distributed to households in the three municipalities. Originally, 1,500 efficient cookstoves were envisaged to be provided to 1,500 households.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Within the national team, a Finance and Administration Assistant is a woman. Project acivities such as training and workshops took into account the issue of gender. Some project activities such as provision of efficient cookstoves which were provided to 1000 households in each district of Ilala, Kinondoni and Temeke municiplatities are likely to benefit more women of each beneficiary household.
Lessons and measures related to coordination with the LDCF project 'Developing core capacity to address adaptation to climate change in Tanzania in productive coastal zones' | A joint project coordination team that was established at VPO that were reporting to the Assistant Director cum Acting Director of Environment helped to establish a close working working reltationship through joint project steering committee with joint meetings, joint technical committee, joint baseline study, a shared Senior Technical Adviser etc, joint baseline study, joint geotechnical and topographical surveys of seawalls works of both projects have been useful interproject learning forum. These considerably helped to reduce operational costs, and assure that relevant lessons, outputs and expertise are consistently shared between the two projects.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Sufficient and robust baseline data is important for the design and scope of the project and assesment of cost-benefits of the project. Such information is crucial for potential replicability of the project activities. It is critical that project design recognizes the importance of closely involving local stakeholders during design and implementation of the project. Underestanding of climatic variations are important factors in implementing some project activities that are geared to enhance resilience to climate change.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Complimentarity of construction of seawalls and drainage systems is expected to increase resilience of seawalls against floods.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | In order to multiply co-benefits and reduce collateral costs, the dynamics and nature of priority sites have to be studied when designing the specific actions that will be conducted in them. Project developers have to understand what people do around the sites, and how the interventions will modify the dynamics around them.The demographic, economic and social trends of a country and its regions have to be analysed together with the climate trends when prioritizing components, activities and sites at project design. Ignoring demographic, economic and social trends can lead to mal-adaptation, in the worst-case scenario, and to missing the opportunity of making strategic investments, in the best-case scenario.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Through EBICAM training there is a high possibility of scaling up of the activities by officials which participated in the training. The interventions arising from the training will really reduce the vulnerability people to climate change in the respective areas. This can result into multiply effect and induce direct adaptation benefits and ensure the provision of significant environmental, social and economic co-benefits. There is increased awareness beyond the target stakeholders and some stakeholders who are members of EBICAM have already started initiative to enable construction of seawall protection structures in other areas such such as Mtwara.Passive designs have been adopted incorporating simple technology, easy to maintain and climate change resilient.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The involvement of the community has been significant through training, decision-making and implementing activities in the field including community members and groups, government stakeholders and other local stakeholder groups (non-government). Adoption of passive designsthat incorporates simple technology, easy to maintain and climate change resilient.
What measures are/have been put in place to ensure sustainability of the project/program results? | Public awareness campaigns through the use of social media at national and local level, and use of PSC and the Technical Committees which will continue to exist beyond the project life. The issue of solid waste management will be taken into workplan of the respective municipalities. Training on piloting on use of efficient cookstoves was was likely to enhance sustainability of the project results.
What measures are being/could have been put in place to improve project/program results? | Policy briefs will improve dessimnination of projects results beyond the project boundaries
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Project activities regarding the rehabilitation of mangroves, coastal vegetation and coral reefs; and provision of efficient cook-stoves used existing data. Development of Dar es Salaam’s Ecosystem-Based Integrated Coastal Area Management (EBICAM) Action Plan, and development of the baseline study used existing reports. The number of sites for seawalls and coral reef rehabilitation, drainage systems and mangrove rehabilitation used existing data from various studies and reports. Reports/studies that were used included Vulnerability Assessment of Coastal Areas to the Impacts of Climate Change that was conducted in 2009.
If learning objectives have been established, have they been met? Please describe. | Learning objectives were met
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Lack of involvement of local staff in the project was a cornerstone in the beginning. Signing an MOU with local stakeholders incerases access to data and information and boosts cooperation among actors
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes, participants of the training workshop that were trained on energy efficience, district financing and budgetting as well as ecosystem management are able to use their knowldege. Sikills obtainaed from those training are being used in planning and identification of beneficiaries for the efficient cook stoves, monitoring of construction works ensures quality of works.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | AFB-5060-1111-2G48
Implementing Entity | UNEP
Type of implementing entity | MIE
Country | Tanzania
Region | Africa
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project | Limited impact | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project | Limited impacts | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 1484942 | 182155 | 1302787 | Total | 1600 | 1600 | 0 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 60.67% | 58.2% | 61.01% | % of female beneficiaries | 90% | 90% | 0% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 |  |  | Total | 0 |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 5 | Multi-sector | National | 3: Risk and vulnterability assessments completed or updated |  | Coastal management | National | 3: Risk and vulnterability assessments completed or updated | 5 | Multi-sector | National | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  | 0 |  | Geographical coverage |  | 0 |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Coastal management | 2: Low capacity | Total | 60 | Coastal management | 4: High capacity | Total | 57 | Coastal management | 3: Medium capacity | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted | 37% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 60 | 50% | Public |  | 57 | 37% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Coastal management | 2: Low capacity | Public | Local | Coastal management | 4: High capacity | Public | Local | Coastal management | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 |  |  |  | 0
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Coastal management | Local | 2: Partially responsive (Lacks most elements) |  | Coastal management | Local | 4: Mostly responsive (Most defined elements) |  | Coastal management | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved
|  | Urban development | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Urban development | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Urban development | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 3: Moderately effective |  | Coastal management | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 4 | ha rehabilitated | 2: Partially effective | Mangroves | 40 | ha rehabilitated | 4: Effective | Mangroves | 1 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 1 | ha rehabilitated | 2: Partially effective | Other | 1 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Coasts | 1 | km rehabilitated | 2: Partially effective | Coasts |  |  | 4: Effective | Coasts | 1 |  | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 |  |  |  | 0 |  |  |  | 0
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Coastal management | National | Environmental policy | 1 | Coastal management | National | Environmental policy/coastal zone | 0 | Coastal management | National | Environmental policy/coastal zone
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective | 1 | 4: Enforced (Most elements implemented) |  | 4: Effective | 1 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on D21: Lars Christiansen: Note: these have been revised based on more detailed inventories conducted during 2016 by local authorities. They are still approximations however and thus represents a best guess based on current information. Information on youth was not possible to obtain at this point. The definition of direct beneficiaries applied is: people directly impacted by project interventions (e.g. protecting their personal property from impacts of coastal erosion or flooding, recepients of cookstoves, people participating in reforestation or coral activities and/or receiving training). The definition of indirect beneficiaries is: broader population living in neighborhoods targeted by interventions (i.e. Ocean/Obama road, Kigamboni, Ilala, Temeke and Kinandoni). Data is from local authorities and as such subject to some uncertainty and could be further revised in the final assessment by project closure. We are happy to share the raw data if this is of interest to AF. A wider definition of indirect beneficiaries could also include a general population of Dar es Salaam (e.g. including daily users of the very busy Ocean/Obama road), but we feel the above interpretation is more objective. We are happy to revise based on advise and further definition of terms from AFsec.
Note on M21: Lars Christiansen: This represents heads of households recepients of cookstoves distributed so far (we do not have information on size of households, so direct impact is significantly higher). As infrastructure work had only just started at time of reporting, neither direct or indirect impact can be claimed here (by far the largest target group of quoted targets)
Note on E89: Lars Christiansen: why can't we provide zero as the baseline here??
Note on D92: Lars Christiansen: Corals are not an option so have left out
Note on E95: Lars Christiansen: see above why can't this be 0?
Note on I95: Lars Christiansen: Cannot provide 1.5, which is the accurate target for shoreline rehabilitation. Very hard to use this template with so many restrictions on format!

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.