Project Completion Summary

In accordance with the project agreement, implementing entities are required to submit a project completion report within six (6) months after Project completion, and the final project progress report (PPR) is considered as a project completion report. While the PPRs meet technical requirements, the information is reported by year and its format is not ideal to convey the overall information and knowledge to wider and more general audiences. To supplement this, implementing entities are requested to prepare a project completion summary.

A project completion summary is intended to cover an entire project life in a reader friendly format by compiling submitted single-year PPRs.  It also gives implementing entities an opportunity to express and share insights from project implementation, findings, challenges etc. which may not be presented by PPRs and captured by a final evaluation report.

A project completion summary consists of narrative information (Section A) and financial information (Section B). Any other information (Section C) can be added to the report as an option. Most of the contents can be filled in by copy-and-paste from the submitted PPRs. The completion report should be no more than 20 pages (excluding annexes).

Project Completion Summary

Section A: Project result and performance

- Basic information

| Title of project/programme | Building Resilience in the Greater uMngeni Catchment |
| --- | --- |
| Project/Programme category | Regular project (ZAF/NIE/Water/2013/1) |
| Project period (if the project was granted an extension, include the original as well as the revised completion date) | - Original: 12 November 2015 – 30 September 2020 - In May 2019, a no-cost extension was approved to extend the end date to 31 March 2022 - In January 2021, a no-cost extension was approved to extend the end date to 31 March 2023 - In November 2022, a no-cost extension was approved to extend the end date to 30 September 2023 - In November 2023, a no-cost extension was approved to extend the end date to 31 March 2024 |
| Country(ies) | South Africa |
| Sector(s) | Water Management |
| Implementing entity name | South African National Biodiversity Institute |
| Type of implementing entity (MIE, NIE or RIE) | NIE |
| Executing entity(ies) | uMgungundlovu District Municipality The University of KwaZulu-Natal played the role of sub-Executing Entity |
| Amount of financing approved (USD) | USD 7,495,055 |
| Project contact(s) | Dr. Mandy Barnett |
| Date of report | - September 2024 |

- Key milestones – Please refer to the overview tab in the latest PPR. For the delay in project implementation and related reasons, refer to the lessons learned tab, section on “implementation and adaptive management”

| Project inception | 12 November 2015 |
| --- | --- |
| Mid-term review (if applicable) | 1 December 2018 to 10 April 2019 |
| Project completion | 31 March 2024 |
| Terminal evaluation | 1 December 2023 to 30 June 2024 |
| If any, delay in implementation and reasons for delay | The project experienced several delays, and it benefited from four no-cost extensions. The primary reason for this slower-than-anticipated progress was related to protracted delays and challenges associated with the procurement of services through the Executing Entity, the uMgungundlovu District Municipality, and in the latter stages of the project through the sub-Executing Entity, the University of KwaZulu-Natal. The procurement delays have been partly due to challenges and changes within the Executing Entity’s and sub-Executing Entity’s internal systems, and partly due to high turnover in high-level staff and political leadership of the Executing Entity. In November 2021, the South African National Biodiversity Institute applied the Direct Project Services methodology to procure services for the Executing Entity. While this procurement was successfully undertaken, it was also delayed. The procurement challenges were further exacerbated by National Treasury regulations, which put a moratorium on all Government-led procurement during Year 7 of the project. This came at a critical time for the project, and resulted in the procurement of service providers for Component 2.1 (Built Environment) through the Executing Entity being stalled. That procurement was shifted to the sub-Executing Entity through a contract amendment. However, this procurement was also delayed for the reasons noted above. The other major delay in the project was related to the COVID-19 pandemic, which prevented community engagement. This severely affected the progress of all aspects of the project. While innovative plans were implemented to maintain momentum and continue engaging communities, and an expedited implementation plan was developed for the post-COVID-19 period, the delays had severe knock-on effects on the project implementation. |

- Project overview and description

The "Building Resilience in the Greater uMngeni Catchment" project, known as the uMngeni Resilience Project (URP), was approved by the Adaptation Fund (AF) in 2014. The South African National Biodiversity Institute (SANBI) submitted the project to the AF as the accredited National Implementing Entity (NIE) for South Africa.

The URP was developed in response to a national call by SANBI for project ideas for submission to the AF, after SANBI was accredited in 2011. It was a combination of two ideas from a pool of 79 applications – the two were from entities who would ultimately go on to be the Executing Entity and sub-Executing Entity for the project. The project was selected because it was deeply embedded in local institutions, and it met principles related to tangible results for vulnerable communities and partnerships and included a range of integrated co-benefits.

In 2014, climate projections indicated that the uMgungundlovu District Municipality (uMDM), in the KwaZulu-Natal Province in South Africa, would experience a warmer future with uncertain changes in mean annual rainfall but with an increased number of flash flood and storm events due to an increase in short duration rainfall. With floods, severe storms and wildland fires already being among the main hazards currently faced by communities in the uMDM at the time, the projections were of concern as they indicated an increased risk of these climate-driven events and did not exclude the potential for an increase in drought events. The projections were of particular concern for the areas and populations in the UMDM as many are already vulnerable to these hazards due to various non-climate related reasons, including: i) low-cost and informal housing located close to river watercourses or on flood plains within catchments; ii) housing of poor standard located on steep hillsides; iii) under-resourced fire stations; iv) high-density informal and formal settlements; v) poor land use management and over-exploitation of natural resources, including grasslands; and vi) small-scale farmers using crops and methods that are not resilient to the impacts of climate change. The predicted increase in frequency and intensity of climate-driven events will significantly increase the vulnerability of affected communities within the uMDM, where adaptive capacity is low.

The overall objective of the URP was to reduce climate vulnerability and increase the resilience and adaptive capacity of vulnerable communities and small-scale farmers in the uMDM that are threatened by climate variability and change, through an integrated adaptation approach. To achieve this, the project adopted a suite of complementary, gender-sensitive project interventions, focussing on:

- Early Warning Systems: to ensure that flood, agrometeorological and fire warnings are supplied timeously in an appropriate format for direct use by communities and relevant disaster response officials;

- Climate-Proof Infrastructure: to strengthen critical settlement infrastructure, community facilities, homes and ecological infrastructure to buffer vulnerable rural communities against anticipated climate-induced stresses;

- Climate-Resilient Agriculture: to promote investments in climate-resilient agricultural practices and physical infrastructure at the farm level to enable small-scale farmers to adapt to the impacts of climate variability and change; and

- Capacity Building and Learning: to generate and share knowledge, and provide policy recommendations to facilitate the scaling up and replication of the project (Components 1-3) in other areas.

The uMDM identified a number of sites as demonstration sites for the project. Four sites were selected, based on the results of a vulnerability assessment, stakeholder consultations, and subsequent shortlisting and ground-truthing through site visits. The sites were:

- Low-lying high-density settlements in the Msunduzi and Richmond Local Municipalities, primarily because of: i) high population densities and the associated potential to benefit many people; ii) the high degree of vulnerability of communities in low-lying areas to flooding rivers, including the Msunduzi, uMngeni and other rivers; iii) low income of residents, increasing vulnerability; and iv) the potential for replication in other informal/formal settlements across the Municipality, as well as other parts of KwaZulu-Natal and the country.

- Ward 8 of Vulindlela in the Msunduzi Local Municipality, primarily because of: i) the high level of poverty and associated vulnerability of rural communities to the predicted impacts of climate variability and change; and ii) the support of traditional authorities who welcomed the project interventions, particularly those related to rehabilitation of degraded grasslands and riparian areas in the ward.

- Ward 8 of Swayimane in the uMshwathi Local Municipality, primarily because of: i) the high level of vulnerability of small-scale farmers to the predicted changes in rainfall for the area; and ii) the potential to scale up the positive results of the University of KwaZulu-Natal (UKZN) School of Agriculture, Earth and  Environment Sciences (SAEES) pilot project working with a limited number of small-scale farmers in the ward.

- Ward 5 of Nhlazuka in Richmond Local Municipality, primarily because of: i) the high level of poverty and associated vulnerability of rural communities to the predicted impacts of climate variability and change; ii) the support of traditional authorities who welcomed the project interventions, particularly those related to the built environment; and iii) the opportunity to implement interventions in an area dominated by degraded bushveld vegetation, in contrast to the grassland-dominated area of Vulindlela.

The project was allocated a total budget of USD 7,495,055. It was implemented through a partnership involving SANBI, in an oversight role as the NIE, the uMDM who were the Executing Entity, and the UKZN who played the role of sub-Executing Entity. Initially planned to run from November 2015 to September 2020, the project received four no-cost extensions, extending until March 2024 without additional funding.

The project was governed through several interlinked governance structures. The National Adaptation Funds Advisory Body (formerly known as the National Implementing Entity Steering Committee) provided overall project governance and promoted linkages with the National policy environment. The National Adaptation Funds Advisory Body membership included the Department of Forestry, Fisheries and the Environment as the National Designated Authority, the National Treasury, the National Disaster Management Centre, the Department of Science and Innovation, the Department of Planning, Monitoring and Evaluation, National Business Initiative and the Adaptation Network, with SANBI as Secretariat. At the project level, a Project Coordinating Committee was established, primarily to provide support, guidance and advice to the Executing Entity and project implementation partners, and to garner support for the project from within the member organisations, decision-makers and other relevant parties. The project Coordinating Committee was chaired by the uMDM. It included members from the Department of Fisheries, Forestry and the Environment, SANBI, relevant technical units within the uMDM, the UKZN, Local Municipalities from within the District, relevant Provincial Departments from KwaZulu-Natal, NGOs and other partners with a role or interest in implementing the project.

- Results and key outcomes (Alignment with the Adaptation Fund core impact indicators – Number of Direct Beneficiaries reached including women; Trainings conducted including women trained, Early Warning Systems (EWS); Assets Produced, Developed, Improved, or Strengthened; Natural Assets Protected or Rehabilitated, i.e. hectares of natural habitats/ meters of coastlines) – Please refer to the “Performance at completion” in the Results Tracker section in the last PPR to extract this information.

The results achieved by the project are included in the table below, using the colour noted in the key below the table to highlight what was achieved against the planned project targets. The main project results are described below the table, per component. A copy of the Results Tracker from the Year 9 Project Performance Report has been included as Appendix 5.

Overall, 39% of the project targets were exceeded, 39% were met, and 22% were partially met. The most significant result is that of the overall objective, where the result achieved (number of people with reduced risk to the impacts of climate change) was exceeded by a factor of four.

Table 1: uMngeni Resilience Project results achieved.

| Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End |
| --- | --- | --- | --- | --- |
| Objective: Reduce climate vulnerability and increase the resilience and adaptive capacity of vulnerable and small-scale farmers in production landscapes in the uMgungundlovu District that are threatened by climate variability and change, through an integrated adaptation approach | Number of people with reduced risk to climate change-driven floods, storms, fires and drought, as a result of project interventions | 0 women and 0 men | TOTAL: 102,855 community members (53,572 women and 49,283 men) *Note - this number is comprised of: Flood Early Warning System: 90,355 community members (46,767 women and 43,588 men in Msunduzi Wards 12, 20, 32, 33 and 35; and Richmond Wards 1 and 2) Fire Early Warning System: 9,000 community members in Nhlazuka (4,950 women and 4,050 men) 3,500 community members in Swayimane (1,855 women and 1,645 men) | 13,414 women and 12,226 men |
| Outcome 1: Number of Early Warning Systems benefiting vulnerable communities and small-scale farmers | Number of Early Warning Systems benefiting vulnerable communities and small-scale farmers | 0 Early Warning Systems in place | 3 Early Warning Systems in place (flood, agro-meteorological and fire) | 3 Early Warning Systems: 1 each for flood/storm, wildland fire and agro-meteorological |
| Output 1.1: Hydro-climatological and fire information and warnings supplied timeously in an appropriate format for direct use by communities and relevant disaster response officials | 1. Flood/storms: Area of the uMDM covered by improved monitoring network, to allow early detection of flooding threats to vulnerable communities | 0% of the uMDM is covered by an improved monitoring network | 100% of the uMDM is covered by an improved monitoring network; Detailed configuration available for 75 km of prioritised rivers in uMDM | High-level/course configuration: 100% of the uMDM; detailed configuration: 75 km of the prioritised rivers in uMDM |
|  | 2. Wildland fire: Number of PPPs in place between the relevant FPAs, the Ingonyama Trust Board and the Local Authorities | 0 PPPs with FPAs, ITB and local authorities | 1 partnership in place | 1 PPP between the relevant FPAs, the Ingonyama Trust Board and the Local Authorities |
| Output 1.2: Early warning systems empower municipal officials and local communities and small-scale farmers to respond timeously to seasonal forecasts and potential disaster | 1. Number of ward-based disaster management systems piloted in project target areas | 0 ward-based disaster management systems have been piloted in the project target areas | 3 ward-based management systems (Flood Early Warning System in low-lying, high-density areas of Msunduzi Wards 12, 20, 32, 33 and 35 and Richmond Wards 1 and 2; Agro-meteorological Early Warning System in Ward 8 of Swayimane; and Fire Early Warning System in Ward 5 of Nhlazuka) | 3 ward-based disaster management systems: one each for the low-lying high-density site, Ward 8 of Vulindlela and Ward 5 of Nhlazuka |
|  | 2. Number of community members benefiting from ward-based disaster management systems | 0 community members (0 women and 0 men) in the low-lying high-density site; ward 8 of Vulindlela and ward 5 of Nhlazuka | Flood Early Warning System: 46,767 women and 43,588 men in low-lying, high-density areas of Msunduzi Wards 12, 20, 32, 33 and 35 and Richmond Wards 1 and 2 Fire Early Warning System: 4,950 women and 4,050 men in Ward 5 of Nhlazuka 1,855 women and 1,645 men in Ward 8 of Swayimane Agro-meteorological Early Warning System: 324 women and 102 men in Ward 8 of Swayimane (*note: these community members are also benefitting from the Fire Early Warning System, hence are not counted separately in the Objective results) Swayimane: 1 855 women and 1 645 men. Total: 3 500 | At least: 500 women and 500 men in the low-lying high-density site 7,962 women and 7,327 men in Ward 8 of Vulindlela 4,852 women and 4,014 men in Ward 5 of Nhlazuka |
|  | 3. Number of community-based fire risk management programmes piloted in project target areas | 0 community-based fire risk management programmes | 1 community-based fire risk management programme in Ward 5 of Nhlazuka | 1 community-based fire risk management programme in Nhlazuka |
|  | 4. Number of trainees directly benefiting community-based fire risk management programme | 0 women and 0 men in Ward 5 of Nhlazuka | 73 community members (42 women and 31 men in Ward 5 of Nhlazuka) | 30 women and 30 men in Ward 5 of Nhlazuka |
| Output 1.3: Access to seasonal weather forecasting improves the resilience of small-scale farmers to climate variability | Number of small-scale farmers in Ward 8 of Swayimane benefitting from improved agro-meteorological forecasts at the farm level | 0 women and 0 men in Ward 8 of Swayimane | 426 community members (324 women and 102 men in Ward 8 of Swayimane) | 300 women and 100 men in Ward 8 of Swayimane |
| Outcome 2: Built and ecological infrastructure enhances resilience and reduces vulnerability to risks associated with climate variability and change | 1. Number of rural physical assets strengthened or constructed to withstand conditions resulting from climate change-driven floods, storms, fires and drought | 0 houses; 0km of stormwater drainage channels; and 0 pedestrian bridge at project start | 263 houses 1.8 km of stormwater drainage channels 5 pedestrian bridges | 300 houses 10 km of stormwater drainage channels 5 pedestrian bridges |
|  | 2. Area and type of natural resource assets maintained and improved to withstand conditions resulting from climate change-driven floods, storms, fires and drought | 0 ha of restored grassland; 0 km of rehabilitated riparian zones; 0 ha of alien vegetation removed to prevent bush encroachment; and 0 km of firebreaks at project start | 206 ha of restored grassland 5.47 km of rehabilitated riparian zones 68 ha (Vulindlela) and 2,688 ha (Nhlazuka) of alien vegetation removed to prevent bush encroachment 106 km of firebreaks | 200 ha of restored grassland 12 km of rehabilitated riparian zones 100 ha of alien vegetation removed to prevent bush encroachment 100 km of firebreaks |
|  | 3. Number of policy revisions and recommendations developed to include adaptation considerations as a result of knowledge gained through the project | 0 policy revision recommendations | 2 policy revision recommendations (included in 1 Climate Sensitive Spatial Planning and Land Use Management policy brief, covering: rural settlement planning processes/SPLUMA; and peri-urban and urban settlement design and upgrade processes/SPLUMA) | At least 3 policy revision recommendations, for the inclusion of adaptation considerations into each of: rural settlement planning processes/SPLUMA South Africa’s Extended Public Works Programme peri-urban and urban settlement design and upgrade processes/SPLUMA |
| Output 2.1: Critical settlement infrastructure, community facilities and homes strengthened and stabilised to buffer vulnerable communities against anticipated climate-induced stresses in rural communities | Number rural structures with strengthened climate resilience in the target area, in direct response to participatory vulnerability mapping of the project | 0 houses; 0 km of stormwater drainage channels; and 0 pedestrian bridges | 263 houses 1.8 km of stormwater drainage channels 5 pedestrian bridges | 300 houses 10 km of stormwater drainage channels 5 pedestrian bridges |
| Output 2.2: Restored and protected critical ecosystems that maintain ecosystem resilience, provide buffering from climate change impacts and provide fresh water to local communities downstream | Area of target ecosystems within target areas with improved climate resilience | 0 ha of restored grassland; 0 km of rehabilitated riparian zones; 0 ha of alien vegetation removed to prevent bush encroachment; and 0 km of firebreaks at project start | 206 ha of restored grassland 5.47 km of rehabilitated riparian zones 68 ha (Vulindlela) and 2,688 a (Nhlazuka) of alien vegetation removed to prevent bush encroachment 106 km of firebreaks | 200 ha of restored grassland 12 km of rehabilitated riparian zones 100 ha of alien vegetation removed to prevent bush encroachment 100 km of firebreaks |
| Output 2.3: Officials empowered to mainstream climate change adaptation into relevant planning and infrastructure development plans and frameworks | 1. Number of tools for mainstreaming climate change adaptation considerations/ standards into informal settlement upgrade planning in the uMDM | 0 climate change adaptation mainstreaming tools | 1 climate change adaptation mainstreaming tool for the uMDM | At least 1 climate change mainstreaming tool, for the uMDM |
|  | 2. Number of training sessions to build the capacity of relevant officials to mainstream climate change adaptation in policies and plans | 0 training sessions | 15 output-driven training and workshops with relevant officials | 15 output-driven training and workshops with relevant officials |
| Outcome 3: Productive landscape resilience increased through the installation of farm-level infrastructure and the integration of climate change responses into agricultural practices | 1. Increase in yield from climate-resilient farms/community home gardens as a result of project interventions | Average of 0.3-1 t/ha for maize and 0.1-0.5 t/ha for dry beans from current farms in target areas | Average of: Maize = 2.9 t/ha Beans = 0.82 t/ha | Average of at least 3-5 t/ha maize and 0.75-1.5 t/ha for dry beans from climate-resilient farms/community home gardens in target areas |
|  | 2. Increase in access to markets for farmers in Ward 8 of Swayimane as a result of project interventions | 0% increase in access | 100% | 50-100 % increase in access to markets for farmers in Ward 8 of Swayimane |
| Output 3.1: Investments in climate-resilient agricultural practices and physical infrastructure at the farm level mitigate impacts of climate variability and change for small-scale farmers | 1. Number of farms/community home gardens in target areas on which climate-resilient project interventions are being implemented | 0 farms/community gardens in target areas | Swayimane: 634 farms Vulindlela: 123 farms Nhlazuka: 98 farms, 5 community gardens | Swayimane Ward 8: 200 farms Vulindlela Ward 8: 200 farms Nhlazuka Ward 5: 5 community home gardens |
|  | 2. Area of farms/community home gardens in target areas in which climate-resilient project interventions are being implemented | 0 ha | 504 ha in Swayimane 30 ha in Vulindlela 18 ha in Nhlazuka | Swayimane Ward 8: 2,000 ha of farmland Vulindlela Ward 8: of 1,000 ha farmland Nhlazuka Ward 5: 2.5 ha of community home gardens |
|  | 3. Number of small-scale farmers in target areas benefitting from climate-resilient agricultural practices introduced through the project | Swayimane Ward 8: 0 women and 0 men farmers; Vulindlela Ward 8: 0 women and 0 men farmers | 688 farmers benefitting in Ward 8 of Swayimane: 540 women and 148 men 123 farmers benefitting in Ward 8 of Vulindlela: 92 women and 31 men 152 farmers benefitting in Ward 5 of Nhlazuka: 113 women and 39 men | Swayimane Ward 8: 300 women and 100 men farmers Vulindlela Ward 8: 300 women and 100 men farmers Nhlazuka Ward 5: 100 women and 50 men community home gardeners |
| Output 3.2: The KZN Provincial Department of Agriculture and Environmental Affairs mainstreams adaptation practices into its extension | 1. Number of trained extension officers placed in project target areas | 0 trained extension officers in target areas | 2 extension officers trained and employed by the URP | 2 trained extension officers (1 in each of Swayimane Ward 8 and Vulindlela Ward 8) |
|  | 2. Number of trained extension officers in uMDM | 0 Extension officers trained in uMDM | 100% of DAEA (now called DARD) extension officers in uMDM undergoing training | 100 % of DAEA extension officers in uMDM trained |
| Outcome 4: Adaptation practices integrated in relevant climate variability and change policies at the municipal level, in targeted sectors and beyond | 1. Percentage of community members in target areas with increased awareness, as a result of the project, of climate change adaptation and options to enhance climate resilience | 0% at project start | 91% of community members in target areas with increased awareness of climate change adaptation and options to enhance climate resilience | 80% (for both women and men) of beneficiaries with increased knowledge of climate change adaptation and options to enhance climate resilience |
|  | 2. Number of development strategies that incorporate adaptation considerations as a result of knowledge generated through the project | 0 at project start | 7 development strategy revision recommendations (5 policy briefs on climate-resilient agriculture; 1 policy brief on Ecological Infrastructure; 1 overarching policy brief on adaptation in South Africa) | 3 development strategy revision recommendations: agriculture human settlements disaster response |
| Output 4.1. Community champions, officials and authorities are empowered to participate in the project's activities | 1. Number of project beneficiaries trained on climate change adaptation and options to enhance climate resilience | 0 at project start | 60 community champions (37 women and 23 men) 5 councillors (2 women and 3 men) 22 officials (14 women and 8 men) | 40 community champions (25 women and 15 men) 4 councillors 8 officials |
|  | 2. Percentage beneficiaries with improved knowledge of climate change adaptation and options to enhance climate resilience | 0% at project start | 67 NQF certificates obtained | 48 NQF certificates |
| Output 4.2: Project outputs and experiences are captured and support integrated learning | Number of platforms to share project outputs and experiences | 0 platforms at project start | 8 reflection workshops 6 learning exchanges 3 conferences | 8 reflection workshops 3 learning exchanges 3 conferences |
| Output 4.3: Policy recommendations support sustaining, scaling up and replicating project successes | Number of national policy conferences and scaling up workshops based on project lessons learned | 0 at project start | 1 national Early Warning System workshop 3 national policy conferences (1 Climate Change Indaba) 3 scaling up workshops | 3 national policy conferences 3 scaling up workshops |

Colour key to note achievement against project targets:

|  | Over-achieved |
| --- | --- |
|  | Achieved |
|  | Partially achieved |
|  | Not achieved |

A description of the main achievements is provided below, per component.

Component 1: Early warning systems (Early warning and response systems improve preparedness and adaptive capacity of local communities and small-scale farmers, drawing on and integrating scientific and local knowledge)

The project's aim for Component 1 was to reduce the vulnerability of community members in the project target areas by providing early warning information related to floods and fires and the factors affecting agriculture. For the Flood Early Warning System, uMngeni-uThukela Water was contracted to develop the system as part of its mandate to provide a functional water resources management and decision support system (WRMDSS) to an area that includes the uMDM. Flood vulnerability mapping was undertaken to identify flooding hotspots. These areas, in Msunduzi and Richmond Local Municipality, were different from those identified in the original Funding Proposal, and the decision was made to re-focus the target areas for the Flood Early Warning System piloting. Hydraulic and hydrological models were setup, and were complemented by real-time water level sensors installed at strategic locations. The system developed included the setting of flood thresholds, which, when forecasted to be exceeded, trigger warnings that are disseminated to the Municipality and other end users via an online dashboard. The information can then be disseminated to end-users via protocols established through the project.

For the Fire Early Warning System, the Richmond Fire Protection Association was contracted to establish a system to allow early detection of wildfires and to allow dissemination of information to support suppression activities. Before the project, the rural target areas were not included in the area covered by a network of fire detection cameras. Through a partnership entered into between the Municipality and the Richmond Fire Protection Association, two additional fire detection cameras were installed overlooking the Nhlazuka and Swayimane project target areas. The cameras can detect smoke from fires, and a command centre then issues information regarding the fire to District and Local Fire Services and directly to communities through protocols established through the project. This early detection and warning service was complemented by the development of a Fire Management Plan for the Nhlazuka area, as well as the training and equipping of community members to be first responders and take action according to the procedures outlined in the plan.

For the Agrometeorology Early Warning System, UKZN led the development of systems to provide information on a range of factors affecting agriculture and human health, to disseminate that information directly to small-scale farmers, and to aid the interpretation of this information through strengthened extension support. This included deep engagement with local small-scale farmers, and the system represents an excellent example of integrating best-practice science with local and indigenous knowledge to increase community resilience. An Automatic Weather Station was installed at a local High School to provide real-time information to complement the climate forecasts used to generate the warning information. The location of the station and an agriculture demonstration plot at the High School was strategic, in that it allowed engagement with youths, which was a focus of the project. Long-term, seasonal and short-term forecasts are tailored to the target area (Swayimane), and this information is disseminated to a user group of small-scale farmers via Short Message Service (SMS), in the local language. Extension Officers, employed at UKZN through the project, then support farmers in interpreting the information to inform better decision-making.

In addition to the planned Early Warning Systems noted above, a lightning detection system was installed on the roof of the Swayimane High School. The school is located on a high ridge at risk from lightning strikes. The hi-tech system detects a build-up of electrical activity in the atmosphere within a 32 km radius of the sensor. When it passes a dangerous threshold, a siren gives an audible warning, and a beacon light gives a visual warning. Communities have been capacitated on how to interpret the warnings, and on how to respond. A prototype of a Rangeland Early Warning System was also developed through the project and piloted in the project target areas to indicate the state of rangelands to support decision-making on, inter alia, grazing management plans.

In Year 8 of project implementation, the operationalisation of the Flood Early Warning System was realised. This, together with the continued functioning of the Fire and Agrometeorological Early Warning Systems, meant that the URP achieved its target of delivering three warning systems for integration into the overall disaster management planning by the Municipality. The systems will assist with effectively building adaptive capacity through: i) providing information on which areas should be evacuated, for example, before a flood event occurs; ii) providing individuals, industries, and commercial enterprises with information which will enable them to respond to potential disasters before they occur; and iii) enabling temporary protection measures to be put in place, where necessary.

The number of people benefitting from these systems is 102,855 (52% of whom are women). This overall number far exceeds the target of 25,640 (52% women) people with reduced risk of climate-driven hazards. The number of people is calculated based on the target areas covered by the Early Warning Systems, using the latest available census data. A more objective assessment would have been required to conduct surveys among these groups to determine the number of people who are more resilient due to the project’s interventions. However, without a quantitative survey, a theoretical method can be applied and is deemed acceptable.

With the operationalisation of the Flood Early Warning System, a number of other project targets were also met or exceeded, e.g. the number of ward-based disaster management systems piloted in project target areas, and the number of community members benefitting from these systems. The targets related to fire warnings and agrometeorological benefits were realised earlier in the project’s implementation. Providing early warning information through systems and protocols established through the project is expected to safeguard lives and livelihoods, and contribute to increased resilience against the impacts of climate change in the project target areas.

Component 2: Climate-proof settlements (A combination of ecological and engineering solutions reduces vulnerability of communities to existing and anticipated impacts of climate variability and change)

The implementation of Component 2 was planned through a set of ecological and engineering solutions to help local communities reduce vulnerability to climate variability and change's existing and anticipated impacts. To support the strengthening of rural built infrastructure to withstand the impacts of climate change, the Built Environment Support Group, supported by additional local partners, undertook an extensive vulnerability of the Nhlazuka project target area. The processes were highly inclusive and participatory, and 300 rural households were identified to be strengthened, 10 km of stormwater drains were identified for construction, and five pedestrian bridges were identified to be constructed or strengthened at strategic locations where community members cross rivers at risk of flash flooding. For the households to be strengthened, a Resilience Design Task Team comprised of engineers and community engagement specialists was established. A range of designs were co-developed that would result in resilient houses, which were also cost-effective and replicable. Construction and engineering firms were then contracted to draw up detailed plans and undertake the construction activities. The activities under this component were plagued with delays, including procurement delays. Once the construction was underway, mid-way through Year 8, the contractors and teams undertaking the construction work encountered challenges related to local business forums, and were forced to stop working.

The contractors then requested to be released from their contracts. Plans were considered for community-based contractors to complete the work; however, it was concluded that there would be insufficient time to complete the work, given the complexity of contracting procedures. A reconciliation of completed works determined that 263 of the target of 300 houses had been strengthened, and 1.8km of the target of 10km stormwater drains had been built. The target of 5 pedestrian bridges was successfully achieved.

However, the project sought other ways to support communities in the Nhlazuka area. After engagement with communities and local and traditional leadership, 22 water tanks, each with a capacity of 5000 litres, were installed in the 11 villages of Nhlazuka. The installation of these tanks, which are capable of being filled by the Municipal water delivery vehicles, is anticipated to alleviate the challenges currently encountered by the community, which necessitates walking considerable distances to fetch water from rivers and streams that dry more frequently than in previous years. The locations of the tanks were strategically selected in collaboration with the local and traditional leadership, and can serve 6-8 households per tank. A hand-over ceremony was held with the local community, to celebrate the installation of the tanks.

For the Ecological Infrastructure activities at the Vulindlela site, the Duzi-uMngeni Conservation Trust was contracted to lead the restoration of grasslands and degraded wetlands. An Environmental Assessment was undertaken, as prescribed by national legislation, and authorization was given to undertake the restoration work. Grasslands were restored through several “soft” interventions, including installing soil blankets and the fencing of springs. This was complemented by “hard” interventions, such as installing several concrete weirs to prevent erosion of wetlands and riparian channels. This provided a good example of how green-grey interventions can complement each other to build resilience, particularly in riparian channels. A rangeland management plan was developed to support the restoration of grasslands.

Furthermore, the rangeland was fenced, a livestock crossing was built, and a borehole was refurbished – these initiatives were not planned and requested by local livestock farmers. In support of this work, Alien Invasive Plants were removed from the Vulindlela site and the Nhlazuka project target area. The targets for grasslands restored and alien vegetation removed were exceeded, while the target for the length of wetland restored was partially achieved, due to budget limitations. The Ecological Infrastructure work focused on capacity development within the local community. Awareness programmes were run parallel to all activities, and community members were hired as Eco-Champs to support the capacity-building interventions.

Mid-way through the project, an Adaptation Toolkit for Rural Planning was developed, which outlines factors to consider by local and traditional decision-makers when making decisions, by adaptation practitioners in implementing responses, and by local communities in safeguarding livelihoods. This was an exciting and innovative product of the project, which will assist both planning officials and rural communities in mainstream adaptation to the planning process and adapt to the impacts of climate change at the community level. A series of training events was held with various stakeholders to build capacity for using the Toolkit.

A policy brief on Climate Sensitive Spatial Planning and Land Use Management was finalized in Year 9, based on lessons learned through the project. The policy brief contains relevant recommendations for including adaptation principles into: i) rural settlement planning processes/the Spatial Planning and Land Use Management Act (SPLUMA); and ii) peri-urban and urban settlement design and upgrade processes/SPLUMA. However, the policy brief lacks recommendations for: iii) South Africa’s Extended Public Works Programme. Engagements with a range of stakeholders have highlighted the opportunity for the policy brief to be further developed – this is beyond the scope of the project, and what has been developed will provide a platform for further engagement.

Component 3: Climate-resilient agriculture (Small-scale farmers have improved resilience and reduced vulnerability to existing and anticipated impacts of climate variability and change)

Component 3 set out to expand on the work already being undertaken in the Swayimane project target area by UKZN to benefit additional farmers and expand the work programme to the Vulindlela project target area. Whilst small-scale farmers were initially supported to set up gardens and grow climate-resilient crops, local circumstances meant that the additional (to Swayimane) focus area shifted to focus more intensively on the Nhlazuka target area.

Across these target areas, over 950 small-scale farmers (77% of whom are women) were supported to grow a variety of climate-resilient (i.e. tolerant to either heat stress or waterlogging, or both) crops using climate-resilient techniques, such as using tunnels and solar-powered drip-irrigation. The focus was on growing climate-resilient crops and those that are nutritious and in demand at markets. Production was realised all year round through the techniques introduced and strengthened through indigenous techniques and the planting calendars generated through the projects. Individual farmers were encouraged to form primary cooperatives and subsequently into secondary cooperatives, which facilitated establishing formal links to the market, including with local supermarkets. Ten such cooperatives, including youth cooperatives, were established through the project across the Swayimane and Nhlazuka target areas. A packhouse and composting station was constructed and equipped through the project in the Swayimane area, which will further enhance the sustainability of the activities and boost the income-generation potential of local small-scale farmers and cooperatives.

The success of the interventions was built on intensive and sustained farmer engagement by UKZN, in both a bottom-up (learning from farmers about indigenous techniques and crops) and top-down (introducing alternative techniques and crops based on best practice science) manner. This engagement resulted in a level of trust that facilitated the uptake and sustainability of project interventions. Regular training events based on farmers' needs were held, and farmer exchanges and field days were held to allow for peer-to-peer learning. Whilst COVID-19 prevented the direct engagement of farmers for a period, the project found innovative ways to continue to provide support, including through the distribution of advice and pamphlets on a range of topics through the SMS channels established through Component 1 of the project.

The project employed and trained two Extension Officers based at UKZN to lead the engagement with farmers. To mainstream the successes to other parts of the District, manuals were developed and training was provided to the Extension Officers employed through the KwaZulu-Natal Department of Agriculture and Rural Development, which facilitated building resilience in farming communities outside of those targeted through the project.

Whilst the majority of project targets for Component 3 were met or exceeded, the target related to the area under improved agricultural techniques was only partially achieved. The target was set in discussion with the traditional leader when the project was designed. Early in the project, the traditional leader passed away and was replaced. Whilst the new leader fully supported the project and plans, the focus shifted to sustainable intensification instead of extensification (i.e., expanding land area), which has trade-offs with land use change.

The success of the Component 3 activities has resulted in the Climate-Resilient Agriculture aspects of the URP (including the Multi-Hazard Early Warning System noted in Component 1) being upscaled into a USD25 million Green Climate Fund project proposal titled “Ecosystem-based Approaches for transforming smallholder farming systems that are vulnerable to the impacts of climate change in South Africa (EbA-Farm)” that is currently under development, with plans to expand the benefits to new areas in KwaZulu-Natal, as well as to three additional provinces.

Component 4: Capacity building and learning (Capacity building and sharing of lessons and policy recommendations facilitates scaling up and replication)

A hallmark of the URP was to continuously engage stakeholders in innovative, participatory and inclusive ways to raise awareness about climate variability and change challenges, as well as the responses to build adaptive capacity. This engagement included awareness events, poster production in the local language, online media campaigns, competitions related to climate change, the distribution of material (e.g. school stationery branded with climate change messages), market days and community exchanges. A highly successful programme of the project was the School’s Climate Change Awareness and Extreme Weather Campaign, implemented in partnership with the Provincial Department of Education. This aligned with the project’s focus on targeting youth, raising awareness and providing practical examples to youths on how to adapt to climate change. Through this and the other engagement programmes mentioned, the project surpassed its awareness-raising targets and benefited 91% of community members in the target areas (against a target of 80%). This achievement reflects the project's effectiveness in raising awareness and educating community members, with a focus on youths, on essential climate-related topics.

The project successfully exceeded its target of training beneficiaries on climate change adaptation and options to enhance climate resilience. A total of 60 community champions, consisting of 37 women and 23 men, were trained, along with 5 councillors (2 women and 3 men) and 22 officials (14 women and 8 men). These training outcomes demonstrated the project's commitment to building knowledge and capacity among a diverse group of beneficiaries. Aligned with this training, the project successfully surpassed its target through 67 people obtaining official (i.e. National Qualifications Framework) certificates. This outcome reflects the project's dedication to enhancing the capacity and expertise of beneficiaries in climate-related matters. Furthermore, the project conducted numerous reflection workshops and learning exchanges, and lessons from the project were presented at numerous conferences. These platforms played a crucial role in sharing project outputs and experiences with relevant stakeholders and fostering learning and collaboration.

The target of 3 policy briefs was exceeded through the finalization of 7 policy briefs in Year 9 of the project on the following topics:

  - Strengthening climate change adaptation and building resilience in South Africa: a Policy Brief

  - Exploring South African Smallholder Farmer’s Adaption to Climate Variability and Change

  - Diversifying The Agrifood System In South Africa: Mainstreaming neglected and underutilised crop species (NUS)

  - Mainstreaming of Neglected and Underutilised Crop Species in South Africa

  - Combatting the El Nino phenomenon in smallholder farmers in Southern Africa

  - Optimizing Decision-Making in the Agricultural Sector using Satellite Technology in South Africa

  - Co-Management of Communal Rangelands In South Africa

Furthermore, over the course of the project:

- 62 articles were written about the project, for sharing via print media or online;

- 7 issues of the URP newsletter were developed and widely circulated, in hard and soft copy;

- 60 papers were published in scientific journals on matters informed by the learnings from the project;

- 23 presentations were given at conferences on the project;

- 72 interviews were conducted, matters informed by the learnings from the project (17 of these occurred between the project closure and the development of this Project Completion Summary);

- 36 leaflets, factsheets and/or guidance documents were developed to share knowledge generated through the project;

- 2 toolkits were developed; and

- 5 videos were produced – one is an overview of the project (26 minutes), while the other 4 are outtakes summarising Component 1 – 4 (each approximately 4 minutes long).

A highlight of Component 4 in Year 8 was the successful hosting of the URP Climate Change Indaba, held in the KwaZulu-Natal Midlands in June 2023. The Indaba was attended by over 100 in-person participants representing communities, civil society organisations, government officials and academics from various institutions across the country. Participants visited a number of the project implementation sites on the first day. They spent the next two days reflecting on the achievements of this national flagship adaptation project, sharing perspectives from the project and related initiatives, and discussing policy recommendations to facilitate scaling solutions. The second and third days of the Indaba were live-streamed to a virtual audience that sometimes exceeded 100 participants. A highlight of the Indaba was a Gala Dinner hosted by SANBI and the Department of Forestry, Fisheries and the Environment (DFFE, the Designated National Authority of the AF in South Africa). Several distinguished guests were in attendance, including DFFE’s Director General, a SANBI Board representative and SANBI’s Chief Executive Officer, the Mayor of the uMDM, the Acting Municipal Manager of the Municipality, Mayors from several local municipalities from within the Municipality and Acting Deputy Vice Chancellor of UKZN, to mention a few. The Manager of the AF (Mr Mikko Ollikainen) provided a pre-recoded opening address, which was appreciated by all in attendance. The Gala Dinner was an opportunity for high-level delegates to celebrate the achievements of the project, receive feedback from local beneficiaries on how the project has supported them to become more resilient to the impacts of climate change and recognise the range of project partners who worked tirelessly to ensure the project’s success.

- Issues, challenges and mitigation measures (Environmental and social risks, gender considerations and other risks) – Please refer to the lessons learned tab in the PPR, specifically the section on “Implementation and Adaptive Management”.

Several challenges were encountered in implementing the URP. Whilst these were mostly successfully mitigated, they did cause delays. This manifested in the project needing to request four no-cost extensions from the AF.

The main challenges were:

- Procurement: The primary reason for this slower-than-anticipated progress was related to protracted delays and challenges associated with the procurement of services through the Executing Entity, the uMDM, and in the latter stages of the project through the sub-Executing Entity, UKZN. The procurement delays have been partly due to challenges and changes within the Executing Entity’s and sub-Executing Entity’s internal systems, and partly due to high turnover in high-level staff and political leadership of the Executing Entity. In November 2021, SANBI applied the Direct Project Services methodology to procure services for the Executing Entity. While this procurement was successfully undertaken, it was also delayed. The procurement challenges were further exacerbated by National Treasury regulations, which put a moratorium on all Government-led procurement for a period during Year 7 of the project. This came at a critical time for the project, and resulted in the procurement of service providers for Component 2.1 (Built Environment) through the Executing Entity being stalled. That procurement was shifted to the sub-Executing Entity through a contract amendment. However, this procurement was also delayed for the reasons noted above.

- COVID-19: The other major delay in the project was related to the COVID-19 pandemic, which prevented community engagement. This severely affected the progress of all aspects of the project. While innovative plans were implemented to maintain momentum and continue engaging communities, and an expedited implementation plan was developed for the post-COVID-19 period, the delays had severe knock-on effects on the project implementation.

Other challenges are noted below. Many of them and the associated mitigation measures are discussed in the Lessons Learned section below, and cross-referenced here:

- Planned technical partners not being involved: Several technical partners contributed to the project's design, but were not involved in its implementation. This was for a variety of reasons, including loss of capacity. This resulted in a slight disconnect between the conceptualisation and implementation of the project, and some activities had to be re-designed – see “Aligning Project Implementation with Conceptualisation” in the Lessons Learned section.

- Lack of leadership: This was most evident in the Municipality because of the high turnover of senior Municipal officials and competing priorities, and in the Project Coordinating Committee, which played a diminishing role in the project over its duration – see “Strong Governance Processes” in the Lessons Learned section.

- Staff turnover: One of the main challenges to efficiently closing out the project was the loss of capacity within the project teams at the Executing Entity and sub- Executing Entity. This loss of capacity is regularly seen in donor-funded projects, where staff are often contracted for a period corresponding to the project's duration. Contract staff's lack of job security past the project end date meant that resignations were anticipated as employees pursued new prospects. Project responsibilities were redistributed among existing staff to address this concern, albeit causing capacity limitations.

- Frustration at the community level: This was most evident in Vulindlela, where expectations of what the project would deliver were unrealistic, and in Nhlazuka, where sustained delays were encountered in initiating the work to strengthen the identified rural built environment – see “Importance of Community Relations” in the Lessons Learned section

- Long turnaround from idea to implementation: The extended period between engaging communities in the design phase and the start of implementation of the responses was a challenge. This was particularly the case where interventions were only initiated from Year 3 onwards. The delays and changing circumstances on the ground, both in how climate impacts affect communities and in the presence of champions who initially drove the ideas forward and garnered support from the community – see “Aligning Project Implementation with Conceptualisation” in the Lessons Learned section.

- Lessons learned (Best practices, adaptive management, what worked during the implementation and what did not, what corrective actions were taken during implementation, what are the ways to improve the intervention) – Please refer to the lessons learned tab in the PPR, specifically the section on “Implementation and Adaptive Management”.

The lessons below can be drawn from the URP. The lessons are derived from the Terminal Evaluation and augmented by the reflections of project stakeholders. By incorporating these lessons into future project designs and implementation, similar initiatives can enhance their effectiveness, sustainability, and impact within their communities.

- Direct Access delivers tangible benefits: The URP demonstrated that Direct Access is an effective modality for building the climate resilience of vulnerable communities and delivering tangible adaptation benefits. SANBI’s familiarity with the implementation landscape and policy environment, as well as its close working relationship with entities at the national and sub-national levels that played a role in the project, demonstrates the value of a national implementing entity overseeing projects of this nature. It should be noted, however, that even though SANBI, as well as many of the other implementation partners, particularly the sub-Executing Entity, have many years of experience in overseeing and implementing multi-million dollar donor-funded projects, the delivery of the URP still proved challenging at times. This highlights the need to build the capacity of fellow NIEs who may have less experience overseeing such projects. These NIEs should be supported to build dedicated, internal and sustained core capacity to perform the roles required by donors such as the AF; this would work as a modality to strengthen climate resilience.

- Realistic Timelines: The project highlighted that project timelines should be realistic, with longer durations necessary for comprehensive implementation. Short project durations may not allow sufficient time for establishing necessary arrangements and achieving project objectives. Projects such as the URP require longer implementation periods, ideally 7 to 8 years, to allow sufficient time for all arrangements and activities. No-cost extensions, while allowing additional time to complete planned interventions, challenge budget availability, particularly for staff assigned to the project. While the project benefitted from four no-cost extensions, a longer initial project timeline would have been advantageous.

- Aligning Project Implementation with Conceptualisation: The project demonstrated the critical importance of aligning project implementation and management with its conceptualisation. For various reasons, many entities identified as leading parts of the components at the proposal stage could not play this role. This caused delays, which meant plans had to be updated and resulted in some of the innovations in conceptualisation being lost. The project also highlighted the urgency of minimising the time between assessment in the funding proposal stage and implementation. Prompt action is essential for addressing community needs effectively. Delays in implementation can render proposed solutions ineffective as circumstances change. Therefore, it's important to expedite the process from identifying solutions to their actual implementation to ensure timely and impactful responses to community needs.

- Institutional capacity: Leading on from the point above, addressing gaps in institutional capacity, both within Executing Entities and sub-Executing Entities, is paramount for future projects. Building and enhancing capabilities within these institutions is essential to implement project responsibilities effectively. The project further revealed the necessity of integrating evidence into decision-making processes at every project stage. The success of the sub-Executing Entity (UKZN) in utilising evidence to inform practice highlights the value of access to high-quality science and information. This enabled adaptive management, facilitating timely updates and adaptations to project strategies. However, such capacity is often lacking in institutions not primarily focused on knowledge generation; hence, future projects should prioritise building institutional capacity for evidence-based decision-making and adaptive management, ensuring access to relevant information and translating it into actionable outcomes. The project demonstrated the importance of assigning technical leads and project managers roles. Collaboration between these roles is vital, with technical expertise guiding project design and management skills ensuring successful implementation. Additionally, it's essential to consider the necessary capacities for project execution carefully. Specialised roles like monitoring and evaluation should be integrated into project designs to ensure robust project management and comprehensive oversight.

- Strong Governance Processes: The project showcased the need for stronger governance processes at the project management level. While the Project Coordination Committee was initially well-defined, changes over time led to a loss of senior-level representation and a shift towards more informational updates rather than decision-making. Strengthening governance structures could enhance accountability and streamline decision-making processes, ultimately reducing delays and improving project efficiency. The project also demonstrated the need to continually engage senior leadership on the objectives, progress and value of externally funded projects like the URP. This was particularly the case in the uMDM, where leadership (e.g. the Municipal Manager and the relevant Head of Department) changed several times throughout the project.

- Agility in Bureaucratic Processes: The project proved that working with entities with the agility to navigate bureaucratic processes efficiently is crucial. This ensures the timely execution of tasks, such as developing terms of reference, securing approvals, and recruiting personnel.

- Working through Partnerships: The URP was always envisioned to be implemented through a partnership between the NIE, the Executing Entity and the sub-Executing Entity. This approach extended to other implementation partners, such as uMngeni-uThukela Water and the Richmond Fire Protection Association, which meant that even when the project faced challenges and delays, progress was still made, which ultimately facilitated the results achieved, for example, in the Early Warning Systems established through the project. The favourable results stemming from UKZN’s engagement in the project, facilitated by access to student research and scientific publications, show how leveraging university partnerships can augment project outcomes and foster knowledge sharing and dissemination. This partnership demonstrated that working across the science-policy-practice interface can yield successful and exciting results. In the case of the URP, the University acted as the technical partner and the Municipality operated in the practitioner and local policy space. At the same time, SANBI held the overall role of guiding the project in alignment with national policies and plans. This relationship extended across many parts of the project and proved successful.

- Importance of Community Relations: The URP showed the value of strong community relationships before and throughout a project. This includes meaningfully interacting with community members, traditional leaders, and gatekeepers to ensure that all parties understand the initiative's objective and that the community buys into its participation. Any inconsistent nature of community interaction can lead to protracted project delays. This was evident in isolated cases in the project, including in Vulindlela, where a misunderstanding of the project plans meant that the built environment work planned to be implemented had to be shifted to Nhlazuka. The project highlighted the importance of managing expectations within communities. It is imperative to manage expectations within communities, especially regarding ambitious project targets. Setting realistic goals and focusing on achievable outcomes can prevent disappointment and ensure communities benefit from tangible results. In response to some of the challenges noted Community Resilience Committees were established in the target areas of the Vulindlela and Nhlazuka projects. Community leaders headed these committees, which included project representation through Community Facilitation Officers, and supported expectation management.

- The transformative impact of capacity building at the local level: The project highlighted the transformative impact of investing in local capacity-building initiatives. Building the skills, knowledge, and leadership capacity of local communities, government agencies, and civil society organisations is essential for achieving sustainable development outcomes. Projects can catalyse positive change beyond their duration by empowering local stakeholders to take ownership of project activities and decision-making processes. An example from the URP is the establishment of community-based Early Warning Systems and building capacity to receive, understand and act on the disseminated information. Moreover, investing in local capacity leads to economic empowerment, social cohesion, and environmental stewardship within communities, contributing to long-term resilience, self-reliance and sustainability. Recognising the value of local expertise and investing in capacity-building initiatives should be a cornerstone of future projects, enabling meaningful participation and empowerment at the grassroots level.

- Adaptive Project Management: The URP demonstrated the importance of adopting an adaptive project management approach. Traditional project management methodologies often rely on rigid plans and timelines, which can be ill-suited for complex, community-driven initiatives. By embracing adaptive management principles, project teams can remain responsive to evolving challenges, opportunities, and stakeholder needs. This involves regularly monitoring project progress, soliciting stakeholder feedback, and making timely adjustments to strategies and activities. Examples of the project adopting such an approach include shifting execution responsibilities to the sub-Executing Entity, who themselves were enabling and adaptive in extending beyond their original mandate to support the delivery of the entire project. Another example is the change in approach to the learning and knowledge management aspects of the project – the partners originally identified to lead this work were unable to do so, meaning that the Executing Entity had to form relations with new collaborators, leverage off ongoing work to amplify benefits and find creative ways to share knowledge, particularly during the COVID-19 enforced lockdown periods. Future projects should prioritise integrating adaptive management practices to enhance resilience and optimise outcomes in dynamic environments.

- Focused, integrated interventions: The project’s findings emphasised the importance of shifting focus from entire wards to individual villages. Concentrating efforts on closely-knit villages rather than broader wards allows for more efficient resource management, reduces logistical challenges associated with site visits, and enables interventions to be more precisely tailored to specific community needs. Additionally, careful consideration of terrain and accessibility is crucial when planning projects in remote areas. Clustering integrated interventions based on geographical proximity and terrain characteristics can enhance efficiency and streamline logistics for contractors and project managers. In this regard, prioritising impact and sustainability over quantity can lead to greater effectiveness. By targeting a smaller number of households with more impactful interventions, projects can significantly improve quality of life while fostering longer-term resilience. The positive effects of uplifting relatively fewer households can reverberate throughout the community, contributing to lasting positive change.

- Innovation: description of any innovative practices or technologies that figured prominently in this project – Please refer to the lessons learned tab in the PPR, specifically the section on “innovation”.

The URP introduced a range of innovative practices and solutions to facilitate the results achieved and build community resilience. These included the established partnerships and the implementation arrangements that were amended throughout the project. The COVID-19 pandemic necessitated innovative ways of reaching communities, such as SMS messages and pamphlets dropped in rural areas. This extended to creative ways of raising awareness through cartoons, online media campaigns in local languages, and school engagement programmes. Another innovation was the integration of Indigenous Knowledge into the planning and implementation of responses. An example was the agrometeorological information sent to farmers – before contextualising the information, the project took time to understand farmers' needs and the local techniques for forecasting weather changes. This was then integrated into the messages disseminated in the local language.

From a technical response perspective, the main three areas of innovation introduced by the project are noted below.

Climate-Smart Agricultural Techniques

The project embraced a range of climate-smart agricultural practices to ensure sustainability and resilience in the face of changing climate conditions. These techniques, including intercropping, crop rotation, and the innovative solar-powered irrigation system, improved soil health, optimised water use, and enhanced agricultural productivity. An outstanding innovation within the climate-smart agricultural practices was implementing solar-powered irrigation systems enhanced with micro-sprinklers. This advanced technology harnessed solar energy to pump and distribute water, while the micro sprinklers delivered water with precision directly to plant roots. This integrated system addressed water scarcity and maximised water efficiency by minimising runoff and evaporation. Incorporating micro sprinklers further enhanced the project's ability to optimise irrigation and adapt to varying crop water requirements.

Weather monitoring and Early Warning Systems

The project installed innovative weather stations that continuously monitored local climate conditions to enhance climate adaptation. Real-time data collected from these stations empowered farmers with timely weather forecasts, enabling them to make informed decisions about planting, harvesting, and other agricultural activities.

A pioneering addition to the project's technological solutions was installing a lightning Early Warning System in the form of robots. This cutting-edge system detects and analyses atmospheric conditions associated with lightning formation. By providing advance warning of lightning strikes, this innovative technology enhanced the safety of farmers and community members working outdoors, preventing accidents and potential damage.

Flood Sensors for Early Detection: Another significant innovation was the installation of flood sensors strategically placed in vulnerable areas. These sensors constantly monitored water levels and rapidly transmitted data to alert systems. This timely flood detection allowed for swift response and evacuation measures, safeguarding lives and minimising property damage. The incorporation of flood sensors further solidifies the project's comprehensive approach to climate resilience, safety, and sustainable practices. This innovative solution strengthens the project's ability to mitigate the impact of floods and protect both lives and livelihoods, aligning with its overarching goals of community well-being.

Fire detection cameras

The project installed fire detection cameras, which play a significant role in enhancing the project's capabilities. These cameras are strategically placed in key locations to detect and monitor fire outbreaks in real time. This technology not only improves the project's ability to detect fires promptly but also enables a swift response to mitigate the impact of wildfires on the environment and communities. Implementing fire detection cameras showcases the project's commitment to effectively leveraging innovative technologies to address environmental challenges.

- Description of the vulnerable communities and social groups affected by the project, and how they have been engaged and empowered – You might want to refer as well to the section on “community/national impact” in the lessons learned tab of the PPR.

The uMDM has a population of approximately one million people, most of whom speak Zulu as their home language. With the highest prevalence of HIV/ AIDS in the country (42%) and a pattern of migratory work outside the District, there is a very high proportion of female-headed households: 46% (125,061) of households (both urban and rural) in the District are headed by women. The predicted increase in frequency and intensity of climate-driven events will significantly increase the vulnerability of affected communities within the District, where adaptive capacity is low. This is inter alia related to low levels of income and education, a significant young (under 19) and old (over 70) population, and a general lack of awareness concerning the impacts of climate change.

There are more than 21,500 informal dwellings and more than 58,000 traditional dwellings in the uMDM. Residents have limited access to basic social, economic, and municipal services. For example, 16% of the population within the District has no access to municipal drinking water, and 19% rely on communal water pumps. Residents have limited access to employment and to land for farming. Census 2011 estimated that the uMDM had an average unemployment rate of 30%. Unemployment is highest in the more remote local municipalities. For instance, the very rural Impendle Municipality has an unemployment rate of 45%.

The areas of the uMDM most vulnerable to climate variability and change are thus characterised by extremely high levels of unemployment and poverty, a significant proportion of female-headed households, large informal settlements prone to flooding, wildland fire and other climate-driven risks, degraded ecosystems, marginal small-scale subsistence farming and often inappropriate farming practices, and an overall lack of resources and capacity by vulnerable groups to undertake successful strategies to adapt to climate variability and change.

The project focused on building the climate resilience of these vulnerable communities in informal/formal settlements and traditional houses, as well as on small-scale subsistence and emerging farmers. Vulnerable groups in these communities, including women, youth, the aged and the unemployed, received particular attention. Climate resilience was achieved through engagement and capacity development, raising awareness of climate change's impacts, and the range of responses demonstrated through the project. In addition to the capacity-building focus, the most successful parts of the URP for the target communities include various meaningful efforts. Using sophisticated agricultural technologies in Swayimane, such as the Agrometeorology system, lightning robots, and solar-powered irrigation, boosted agricultural productivity and resilience, resulting in higher yields and reduced exposure to weather-related hazards. Disaster preparedness initiatives, such as fire detection cameras, flood sensors, and rangeland fencing, are critical in increasing community resilience to natural disasters, leading to earlier detection of wildfires, quicker flood response, and better land management. Furthermore, infrastructure development, as shown in the construction of pedestrian bridges and house retrofitting, represents real improvements in community infrastructure, potentially improving accessibility, housing conditions, and safety for community members.

As noted in Section 3, the project included four main demonstration sites:

- Low-lying high-density settlements in the Msunduzi and Richmond Local Municipalities;

- Ward 8 of Vulindlela in the Msunduzi Local Municipality;

- Ward 8 of Swayimane in the uMshwathi Local Municipality; and

- Ward 5 of Nhlazuka in Richmond Local Municipality.

Below is a brief description of the sites, vulnerable communities, and social groups affected by the project and how they have been engaged and empowered.

Many informal and formal settlements in the uMDM are in low-lying areas with high population densities. The majority are haphazard and unplanned, with no defined roads, established stands or building lines that govern where the household structures may be built. These settlements are mostly located on steep hills (approximately 30% of the UMDM area consists of topography with a gradient steeper than 1 metre in 3 metres, i.e. 1:3) or within low-lying floodplains. The most common building materials include brick, mud, wattle branches, corrugated iron and wooden pallets. These pallets are cheap and easily accessible to residents because they are used and often discarded by factories. Settlements, particularly informal settlements, in the District are typically densely populated, with up to 6 households on one stand and up to 10 people per household. This inhibits services and infrastructure from being provided in the settlements because accessibility to install services in the settlements is limited for municipal vehicles. Settlements are generally located in low-income areas, with limited access to jobs for inhabitants.

Principal climate change-related threats to low-lying, high-density settlements in the uMDM include increased frequency and intensity of rainfall events. Communities in low-lying settlements inappropriately located within river floodplains risk losing assets and lives due to climate change-driven flooding from rivers. In addition, the lack of formal drainage systems means there is an increased likelihood of localised flooding and erosion within the informal and formal settlements, as well as downslope flooding and damage to households. Associated with this erosion and flooding is damage to informal and formal infrastructure and degradation of natural environments, particularly water courses. In informal settlements, this is exacerbated by the lack of formal toilet facilities. Settlements across the District remain at risk due to climate variability and change impacts.

Low-lying, high-density areas of Msunduzi Wards 12, 20, 32, 33 and 35 and Richmond Wards 1 and 2 were selected as the target areas for the Flood Early Warning Systems piloting because of the characteristics and vulnerabilities noted above. Community members and local leadership were engaged in capacity-building efforts to raise awareness of the impacts of climate change and, what that means for people living in low-lying, high-density settlements and the benefits of receiving early warnings through the dissemination protocols established through the project.

Ward 8 of Vulindlela covers an area of 23 km2. In 2011, the population was 15,290 (52% women), which equates to a density of 678 people/km2. In 2011, there were 2,802 households in the ward, with an average of 5.5 people/household. All of the land in Ward 8 of Vulindlela is under communal land ownership. The majority (63%) of dwellings are traditional houses, while 30% are brick-based. Most people (49%) are in the 20-59 year age group, while 44% are under 19. The majority (70%) of people earn a “low” annual income, i.e. < USD 3,638 per year.

The landscape consists of gently to steeply sloping degraded grasslands draining into tributaries of Msunduzi River. The tributaries are incised and generally eroded. The grasslands are used for cattle communal grazing. However, overgrazing and alien tree stands limit the region's carrying capacity. The predicted increase in frequency and intensity of rainfall events will likely result in flash floods, as decreased vegetative cover reduces infiltration into grasslands and encourages downslope runoff. Poor grassland management, including frequent burning to improve grazing for cattle, combined with the predicted higher temperatures and increased likelihood of lightning strikes, presents an increased risk of wildland fires and associated threats to assets and lives. Besides the reduction of grazing for cattle, the loss of vegetative cover in the grasslands and degradation of the riparian environment has resulted in many wetlands losing their functionality. Some of these wetlands provide clay to build informal and traditional houses in the region. As the wetlands become degraded, the consequent reduction in the quality of clay results in homes being more vulnerable to the impacts of climate change-driven extreme storms and associated high winds and rainfall. Whilst fruit orchard planting projects have been successfully implemented in the ward, there is a general lack of improved, climate-resilient crop varieties for farming practices. This presents a food security and nutritional sustenance risk to community members within the ward. Whilst some agricultural and other built environment initiatives have been successfully implemented, such as using tyres to stabilise embankments, institutional and community level capacity is generally low.

Activities in Vulindlela focused on restoring the degraded Ecological Infrastructure (grasslands and wetlands), which improved the resilience of livestock farmers and those dependent on the catchment for water. The development of a grazing management plan and the fencing of the rangeland further supported communities. The area was also a focus for capacity building and awareness-raising activities.

Swayimane is located 40 km outside Pietermaritzburg under the uMshwathi Local Municipality and in Ward 8. Swayimane covers an area of 32km2, and in 2011, the population was 6,857 (53% women), which equates to a density of 213 people/km2 with an average of 5.1 people/household. All of the land in Ward 8 of Swayimane is under communal land ownership. Most (54%) of dwellings are traditional houses (round mud-based structures with thatched roofs), while 44% are brick-based. The majority (49%) of people are under 19, while 41 % are in the 20-59 year age group. The observed age distributions show that Swayimane has a large youth population, which stresses the need for programs that focus on youth employment and capacity development. The majority (84%) of people earn a "low" annual income, i.e. < USD 3,638 per year. Crop production dominates most farming systems, and small-scale farmers mainly grow maize, beans, amadumbe, sweet potato and sugarcane. Animals are used for land preparation, meat and dairy, and during ceremonies. Maize is a staple food in Swayimane, and SC 701 is the most widely used variety. It is sold as green mealies to local traders.

Swayimane was one of the principal focus areas of the URP. Several activities were implemented throughout the project through UKZN and in partnership with various stakeholders, including capacity development, infrastructure development, participatory-type research and on-farm research. In most instances, the activities have worked in a participatory manner, effectively involving vulnerable groups including women, youth, and older people, in planning, implementation and learning from the process.

Farmers within Swayimane were trained on the following topics – forming cooperatives, conflict management, training for transformation, the asset-based community development approach, marketing, value-adding and financial and business management. In addition, farmers and youths have been trained on various climate-smart technologies such as seedling production, crop diversification, use of underutilised crop species, rainwater harvesting and integrated soil fertility management.

A lightning warning system has been installed at Swayimane High School for infrastructure development. There is also an Agrometeorological Instrumentation Mast (AIM) at the High school. Micro irrigation systems have been installed in two community gardens, and water harvesting systems have been fitted at the high school to supply irrigation in tunnels. A total of 8 community members received tunnels where they produce vegetables and seedlings. The seedlings are sold within the community to improve access to healthy planting material. Community gardens have been fenced to improve security and prevent stray animals from damaging crops. Lastly, a packhouse has been constructed to support the sustainability of the project's interventions.

Nhlazuka is in Ward 5 of Richmond Local Municipality. The nearest town to Nhlazuka is Richmond, situated 43.7 km away. The majority (52%) of people are under 19, while 39% are in the 20-59 year age group. Earnings are low, with 86% of people considered as "low annual income” earners, i.e. < USD 3,638 per year. The landscape consists of hilltops and steeply-sided valleys draining into the Umkomazi River and its tributaries. Drainage down steep slopes and valleys results in downstream erosion, while the generally un-terraced agricultural plots are at risk from loss of topsoil and associated negative impacts on production. Nhlazuka communities are highly reliant on ecosystem services. Communities use wetlands as water collection points, fishing grounds and clay collection points (for brick-making). Nhlazuka, like many areas in the province, is experiencing a loss of natural habitat, which has profound ecological consequences for this species-rich area. Similarly, the loss of natural capital and environmental degradation have socio-economic consequences for the inhabitants reliant on natural resources for fuel, fibre, food and medicine. Subsistence farming is a more prevalent form of agriculture, with all households having a direct or indirect role. Timber and sugarcane are the dominant crops, with maize, sorghum, groundnut, taro and cabbage grown in home gardens. Maize is a primary staple food in the area, and when grown by the households, communities mainly consume it as green mealies.

Climate projections indicate that the uMDM, particularly Nhlazuka, will experience a warmer future with uncertain changes in mean annual rainfall but with increased flash floods and storm events due to an increase in short-duration rainfall. Also, the high level of poverty and the associated vulnerability of the community to the predicted impacts of climate variability and change further threaten the potential of agriculture for food and nutrition security and poverty reduction.

Nhlazuka was one of the project's focus areas. Efforts concentrated on building capacity to be resilient against the impacts of changing climate. The built environment aspects of the project were implemented in Nhlazuka, and community members were supported through climate-resilient agriculture interventions. The Fire Early Warning System was centred in the area, and the Alien Invasive Plant clearing activities were partly implemented in this project target area.

Overall, the project laid the groundwork for long-term impact and community resilience by providing empowerment, resources, and awareness across all the intervention areas. The project's people-centred approach recognized the strengths and potential of each group, fostering a more inclusive, empowered, and thriving community. The project's ultimate aim was to create climate change-resilient communities where vulnerable groups were better equipped to adapt and thrive in the face of environmental challenges.

- Description of how long-term institutional and technical capacity for effective adaptation has been strengthened – Please refer to the lessons learned tab, section on “readiness interventions”.

The URP focused on building and strengthening individual, community, and institutional capacity. At the time of project inception, climate change adaptation and mitigation had not become as topical as it has been over the last five years. As such, the URP was a pioneering project.

At an institutional level, the URP established the Project Management Unit (PMU) at the uMDM. This PMU evolved to become the uMDM’s Climate Change Desk at the Municipality, which previously did not have capacity specific to climate change. The URP-PMU staff strengthened the Municipality’s technical capacities in climate change planning, environmental management, disaster risk management and community engagement. Developing Early Warning Systems and trainings provided to uMDM staff, including ward councillors, helped build long-term capacity. The development of protocols also helped build long-term capacity in the uMDM to effectively respond to floods and fires. The Early Warning Systems themselves strengthened the Municipality’s capacity to administer its disaster risk management mandate through access to timely warnings and knowledge of effective response capabilities. The integration of alien invasive plants clearing with the Extended Public Works Programme created capacity in integrated planning and leveraging existing to address climate risks.

UKZN, the sub-Executing Entity, also benefitted from institutional capacity building. Traditionally, the University’s role is in knowledge generation and seldom the translation of science to inform practice. The URP provided an opportunity for UKZN scientists to translate their knowledge and inform practical interventions while also informing policy. For example, the design and deployment of the lightning and Agrometeorological Early Warning System, solar-based irrigation, climate-strengthening infrastructure, and sustainable packhouse solutions. This built an institutional capacity that has made the University a leader in climate change adaptation advisory, with its scientists now highly regarded globally. The University has now entered into long-term partnerships with various government departments to continue to link evidence to inform climate change adaptation.

- An overview of complementarity and/or coherence of with other climate finance sources in the context of this project (synergies with other projects, national plans, etc.) – Please refer to the lessons learned tab, section on “complementarity and coherence”.

The URP was catalytic in that lessons learned through piloting the range of resilience-building interventions were used to leverage numerous grants and resulted in widespread scaling of activities.

Within SANBI, the project was implemented at the same time as the USD2.5 million Community Adaptation Small Grants Facility Project (in full: Taking Adaptation to the Ground: A Small Grants Facility for Enabling Local Level Responses to Climate Change), which was implemented in the Northern Cape and Limpopo Provinces of South Africa. Many lessons learned through the URP informed the adaptive management principles that characterized the implementation of the Community Adaptation Small Grants Facility Project. Similarly, the Global Environment Facility-funded Biodiversity and Land Use Project, for which SANBI was the Executing Entity, was implemented partly in the uMDM, and lessons were shared between the two projects to strengthen the results achieved. Furthermore, there was a strong relationship between the URP and SANBI’s uMngeni Ecological Infrastructure Partnership, which persists even after the former has ended through the people and personal relations developed over time.

At the provincial level, the project's collaboration with the KwaZulu-Natal Department of Economic Development and Environmental Affairs involved parallel efforts, including invasive species clearing in Nhlazuka and employing local community members. This highlighted a comprehensive approach to environmental conservation and community engagement. Both entities efficiently utilized resources empowered communities, and fostered skill development by working in tandem. The partnership amplified the impact of invasive species clearing, enriched knowledge exchange, and laid a foundation for sustained efforts. This joint endeavour also instilled community pride, strengthening the project's commitment to holistic environmental conservation and enhancing ecological restoration and community well-being.

The project's parallel work with the KwaZulu-Natal Department of Agriculture and Rural Development demonstrated its alignment with existing initiatives and its commitment to enhancing the impact of agricultural and environmental efforts. This approach yielded several key benefits. The alignment highlighted a shared dedication to community well-being, strengthening outcomes through mutual reinforcement. Resource sharing between the project and the Department optimized efficiency and effectiveness, and the joint efforts expanded the visibility of initiatives, encouraging positive change. Knowledge exchange and diverse perspectives enhanced community empowerment while integrating conservation and sustainable agriculture underscored a holistic approach. Overall, this parallel effort contributed to long-term sustainability and policy alignment, generating a collective impact beyond individual projects. By embracing similar work, the project exemplified its dedication to community progress, optimizing resources, fostering learning, and contributing to lasting well-being.

A list of grant projects catalysed by the URP is included in Appendix 4.

- Sustainability, scalability and replicability – Please refer to the lessons learned tab, section on “climate resilience measures”.

Already, the Early Warning Systems and climate-resilient agriculture components of the URP are being upscaled through a USD25 million Green Climate Fund project proposal titled “Ecosystem-based Approaches for transforming smallholder farming systems that are vulnerable to the impacts of climate change in South Africa (EbA-Farm)”, which will be implemented in four provinces across South Africa.

The flood forecasting and Early Warning System developed by the project is being upscaled to cover KwaZulu-Natal Province through a partnership between uMngeni-uThukela Water. There is potential for the flood forecasting Early Warning System to be replicated by other water boards across the country and become a national Early Warning System.

The flood forecasting and fire Early Warning Systems were developed in partnership with institutions with a mandate to provide such warnings. The URP’s targeted investments allowed for expedited development and warning system roll-out. However, the relevant institutions will continue to develop and maintain the systems as they form part of their mandate. Hence, these investments will be sustained and replicated across the province. This partnership model is replicable across the country because these institutions are replicated across all provinces. Additionally, the partnerships with key institutions like UKZN and the South African Weather Service facilitate the scaling up and replication of the Early Warning System at a national level. The National Department of Forestry, Fisheries and the Environment is using the URP as a pilot for the National Framework for Climate Services, which provides a platform to share what is learned from developing the Early Warning System on a national scale.

The replication and upscaling of project activities regarding climate-resilient agriculture is already underway. Throughout the URP, lessons from the URP were being actively transferred and shared in other communities in KwaZulu-Natal, such as in Kokstad, Umbumbulu and Tugela Ferry. UKZN has obtained additional funds from various funders to upscale the resilient agrifood systems work nationally and into new countries, such as Zimbabwe, Malawi and Tanzania – see Section 10 and Appendix 4. Through these funds and ongoing projects, the URP has been catalytic in sustaining, replicating and upscaling interventions. For example, the solar-based irrigation and packhouse at Swayimane, together with the cultivation of indigenous crops, is being upscaled to become an Agri-hub, which will serve other districts in KwaZulu-Natal through funding from the Department of Science and Innovation, the Foreign, Commonwealth and Development Office (FCDO) of the United Kingdom and the Biotechnology Industry Research Assistance Council (BIRAC) of India.

Lastly, the URP’s capacity building and strengthening investments at the individual, community and institutional levels have created the capacity to sustain project interventions, grow them (i.e., replicate them) and mainstream them into policy and planning (i.e., upscaling). This is, by far, the greatest investment made by the URP – people. Through these champions, many of the project’s interventions will be sustained and upscaled because capacity exists within rural communities and relevant institutions to undertake such interventions.

Section B: Project expenditure

(The use of spreadsheet is recommended to avoid numerical errors.)

- Project budget

- Actual expenditures

- Variance notes

* Note: This section will be completed once the audit of the NIE’s project account is finalised.

Section C: Appendices

- Appendix 1: Attendance Register from the inception workshop

- Appendix 2: Key project staff list

- Appendix 3: Reports and other publications

- Appendix 4: List of grant projects catalysed through the uMngeni Resilience Project

- Appendix 5: Results reported in the Year 9 Project Performance Report Results Tracker tab

Appendix 1: Attendance Register from the inception workshop

Appendix 2: Key project staff list

Full and part-time staff remunerated through the URP at the National Implementing Entity, Executing Entity and sub-Executing Entity:

| Name | Organisation |
| --- | --- |
| Michael Jennings | South African National Biodiversity Institute |
| Makganthe Maleka | South African National Biodiversity Institute |
| Eleanor Marks | South African National Biodiversity Institute |
| Mpfunzeni Tshindane | South African National Biodiversity Institute |
| Nomalungelo Ndlovu | uMgungundlovu District Municipality |
| Thobile Mhlanga | uMgungundlovu District Municipality |
| Lindokuhle Khanyile | uMgungundlovu District Municipality |
| Manelisi Ndaba | uMgungundlovu District Municipality |
| Khumbuzile Mkhize | uMgungundlovu District Municipality |
| Aphiwe Mfoboza | uMgungundlovu District Municipality |
| Sbu Thisini | uMgungundlovu District Municipality |
| Sanele Ngcobo | uMgungundlovu District Municipality |
| Tholithemba Khoza | uMgungundlovu District Municipality |
| Albert Modi | University of KwaZulu-Natal |
| Tafadzwa Mabhaudhi | University of KwaZulu-Natal |
| Nomthi Maphumulo | University of KwaZulu-Natal |
| Slindile Miya | University of KwaZulu-Natal |
| Vimbayi Chimonyo | University of KwaZulu-Natal |
| Cebile Jobe | University of KwaZulu-Natal |
| Zenande Matinisi | University of KwaZulu-Natal |
| Xola Nqabeni | University of KwaZulu-Natal |
| Khethiwe Mthethwa | University of KwaZulu-Natal |
| Nhlonipho Mbatha | University of KwaZulu-Natal |
| Antonio Blanco-Montero | University of KwaZulu-Natal |
| Nopayi Mkhize | University of KwaZulu-Natal |

Appendix 3: Reports and other publications

The list below includes: i) articles on the project, conference presentation given on the project or matters related to the project by the Executing Entity and sub-Executing Entity; iii) papers published in scientific journal subjects informed by learning from the project; iv) books; v) toolkits; vi) videos on the project; and vii) pamphlets, guidelines and posters to support the knowledge sharing and awareness raising efforts of the project

Articles and reports (print media and online)

- uMDM website articles: International Day for Disaster Reduction, uMDM climate change actions; - SANBI NIE eNews articles: Small-scale farmers observe yield increases due to the uMngeni Resilience Project (URP) interventions: http://www.sanbi.org/sites/default/files/documents/documents/november-2016-linked-enews-article-small-scale-farmers-observe-yield-increases-due-umngeni-resilienc.pdf - Newspaper reports: Adapting to save the future: A district municipality in KwaZulu-Natal is implementing model adaptation practices to deal with climate changeMail & Guardian 20 March 2015, also http://mg.co.za/article/2015-03-20-00-adapting-to-save-the-future), Climate change taught to rural communities (Maritzburg Fever 21 October 2015, also http://www.news24.com/SouthAfrica/Local/Maritzburg-Fever/Climate-change-taught-to-rural-communities-20151021), Swayimane's New Cloud Watcher (Witness Newspaper 10 November 2016), - Newsletters/magazines: UKZN Plays Leading Role in Local Climate Change Project (UKZN Indaba 10 February 2016 V4 I1), Addressing the Impact of Climate Change (UKZN Foundation Annual Report 2015/16), uMngeni Resilience Project off to a great start (UKZN Foundation Magazine, August 2016), - SANBI NIE eNews articles: See http://www.sanbi.org/node/11937. NOTE: The weblink shown is SANBI's "Adaptation this month" portal, which shows eNews articles on all of SANBI's climate related projects and programmes, including the URP. Articles relevant to the URP include: uMngeni Resilience Project Selected As A Finalist in Enviropaedia Eco-Logic Awards (April 2017); Planning for extreme events: uMngeni Resilience Project hosts Early Warning System workshop (April 2017); uMngeni Resilience Project wins silver in Enviropaedia Eco-Logic Awards (June 2017); Food Exchange Day for Swayimane small-scale farmer (July 2017); Field trip to plan the restoration of wetlands in Vulindlela (September 2017). - Newspaper reports: Fighting Fire With Tech (The Witness, 25 August 2017); uMDM wins silver in EcoLogic Awards (uMDM Community Newpaper, Q2 2017/18); Swayimane's New Cloud Watcher (Witness Newspaper, 10 November 2016, https://www.pressreader.com/south-africa/the-witness/20161110/281736974024421); Weather Station Installed at KZN High School (published in the UKZN Ndaba; http://ndaba-online.ukzn.ac.za/UkzndabaStory/1167/weather-station-installed-at-kzn-high-school/#sthash.NKJsp45F.dpbs). - Newsletters: Weather Station installed at Swayimane High (UKZN Ndaba 24 November 2016 V4 53), uMngeni Resilience Project Hosts Workshop on Early Warning Systems (UKZN Ndaba 10 May 2017 V5 25). - Adaptation Fund website: The following "Beneficiary Stories" were published on the AF website: SANBI: Empowering Rural Small Farmers through Localized Projects (https://www.adaptation-fund.org/sanbi-empowering-rural-small-farmers-localized-projects/); South Africa: Helping Smallholders Improve Crop Production (https://www.adaptation-fund.org/south-africa-helping-smallholders-improve-crop-production/); South Africa: Increasing Climate Resilience in Small-Scale Farmers through Integrated Adaptation (https://www.adaptation-fund.org/south-africa-increasing-climate-resilience-small-scale-farmers-integrated-adaptation/). - Flashing for Lightning (Weekend Witness newspaper, 10 February 2018) - uMngeni Resilience Project installs unique lightning warning system at local school (The Mercury Tertiary Times, 27 February 2018) - Adapting to and surviving climate change (Cape Times, 22 June 2018) - R137mill to adapt to climate change (Cape Argus, 19 June 2018) - Need for Climate Resilient Farming Emphasised at UKZN-Hosted Workshop (UKZN Indaba online, December 2017 V5 Issue 63) - UKZN Marks the Launch of MoUs with the South African Weather Service and Umgeni Water (https://www.ukzn.ac.za/news/ukzn-marks-the-launch-of-mous-with-the-south-african-weather-service-and-umgeni-water/) - Msunduzi Municipality Hosts Climate Smart Conversation (Climate Reality Project http://climatereality.co.za/msunduzi-municipality-climate-change-workshop/) - Promoting Early Warning Systems Awareness in a Changing Climate (https://caes.ukzn.ac.za/news/promoting-early-warning-systems-awareness-in-a-changing-climate/) - SANBI Board Visits Swayimane Research Site (ndabaonline.ukzn.ac.za/StoryPrinter.aspx?id=5911) - Successful Farmers’ Day Brings Together International Researchers and Subsistence Farmers (ndabaonline.ukzn.ac.za/StoryPrinter.aspx?id=5912) - SANBI NIE eNews articles: See https://www.sanbi.org/biodiversity/science-into-policy-action/nie-adaptation-fund/adaptation-this-month/. NOTE: The weblink shown is SANBI's "Adaptation this month" portal, which shows eNews articles on all of SANBI's climate related projects and programmes, including the URP. Articles relevant to the URP for Year 3 of the project are: URP facilitates site visit as part of DEA-hosted Ecosystem-based Adaptation workshop; Adaptation Fund 10 Year Anniversary publication showcases South African projects; Umgeni Resilience Project facilitates the signing of MoUs between University of KwaZulu-Natal, South African Weather Service and Umgeni Water; Need for Climate Resilient Farming Emphasised at UKZN-Hosted Workshop; SANBI and Adaptation Fund Project Celebratory Event; and SANBI Board visits the uMngeni Resilience Project (URP) - KZN Farmers Share Ideas at Research Farm: Witness newspaper (23 March 2019) - UKZN Research in Swayimane Profiled, UKZN Indaba Online, March 2019 - Municipal Profile: uMgungundlovu District Municipality, South African Local Government Association (SALGA), March 2019 - Partnerships for Resilience Explored during Ukulinga Howard Davis Memorial Symposium, UKZN Indaba Online, September 2019 - URP Newsletter (Issue 1: April 2019 and Issue 2: September 2019) - SANBI "eSnippets" (see https://www.sanbi.org/biodiversity/science-into-policy-action/nie-adaptation-fund/adaptation-this-month/): - Building local partnerships with municipalities facilitates robust implementation of climate change adaptation projects (November 2018) - uMngeni Resilience Project farmers open a new food garden in Nhlazuka (December 2018) - The South African National Biodiversity Institute hosts the first Community of Practice for Direct Access Entities meeting in Durban (June 2019) - uMngeni Resilience Project develops an Adaptation Toolkit to help decision makers plan and respond to climate change impacts (June 2019) - Agriculture Graduate forges ahead. UKZN Indaba Online Issue 15 May 2020 - A Looming crisis: the impact of COVID-19 on Small-Scale Farmers. UKZN Indaba Online Issue 17 Volume 8, 28 May 2020 - SANBI "eSnippets" (see https://www.sanbi.org/biodiversity/science-into-policy-action/nie-adaptation-fund/adaptation-this-month/): the article noted above was shared in SANBI’s July 2020 eSnippet i.e. A crisis within a crisis: Impact of COVID-19 on food and nutrition security for smallholder farmers - Analysis on the impact of COVID-19 restrictions on small-scale farmers. UKZN URP team - uMngeni Resilience Project Newsletter – Issue 3 December 2019 - uMngeni Resilience Project Newsletter – Issue 4, October 2020 & - uMngeni Resilience Project Newsletter – Issue 5, April 2021 - Promoting new value chain for neglected and underutilized crops - UKZN Indaba Online Issue, June 2021 - uMngeni Resilience Project Newsletter – Issue 6 - https://ndabaonline.ukzn.ac.za/UkzndabaStory/Vol10-Issue9/From%20UKZN%20Project%20Intern%20to%20Hardware%20Store%20Owner - https://ndabaonline.ukzn.ac.za/UkzndabaStory/Vol10-Issue9/COVID-19%20and%20July%20Riots%20Double%20Burden%20for%20Small-Scale%20Farmers - SANBI "eSnippet" on: The uMngeni Resilience Project hosts a farmers market access reflection workshop. - SANBI "eSnippet" on: uMngeni Resilience Project Component 1: Early Warning Systems Reflection Workshop. - SANBI "eSnippets" (see https://www.sanbi.org/biodiversity/science-into-policy-action/nie-adaptation-fund/adaptation-this-month/): - uMngeni Resilience Project hosts Farmers’ Day in celebration of Africa Day (May 2023) - uMDM Mayor launches the commencement of climate-proofing of rural infrastructure activities in the iNhlazuka community, Richmond Local Municipality (November 2022) - SANBI news article: URP partners step out in style to celebrate achievements (June 2023) (see: https://www.sanbi.org/news/urp-partners-step-out-in-style-to-celebrate-achievements/) - SANBI news article: URP Climate Change Indaba: Resilience, lessons and rewards (June 2023) (see: https://www.sanbi.org/news/urp-climate-change-indaba-resilience-lessons-and-rewards/) - uMngeni Resilience Project Newsletter – Issue 6 (October 2022) and Issue 7 (September 2023) - Online UKZNBABA article on Climate Change Indaba: “Climate Change Indaba Celebrates Success of uMngeni Resilience Project” https://ndabaonline.ukzn.ac.za/UkzndabaStory/Vol11-Issue34/Climate%20Change%20Indaba%20Celebrates%20Success%20of%20uMngeni%20Resilience%20Project/

Conference presentations

- Conference Presentations: 2nd Climate Change and Agriculture Conference, Barcelona Spain , March 2017; ICCO Workshop on Climate Change Adaptation, Pretoria South Africa, August 2017. - T. Mabhaudhi, R.P. Kunz, R.E. Schulze and A.T. Modi. Underutilised crops as ‘new’ crops under climate change: a South African perspective. WaterNet17, Swakopmund, Namibia, 24-27 October 2017 - Mabhaudhi, T., and Chibarabada, T.P., Modi, A.T. Adaptation and productivity of selected grain legumes in contrasting environments of KwaZulu-Natal, South Africa. Fountain Hill Estate Research Symposium, Fountain Hill Estate, Wartburg, 11-12 October 2017 - T. Mabhaudhi, S. Mpandeli, L. Nhamo, V.G.P. Chimonyo, A. Madhlopa, G. Backeberg and A.T. Modi. The water-energy-food nexus as an approach for sustainable advancement of food security in South Africa. Cape Town, South Africa, 4-6 October 2017 - Mabhaudhi, T., Chimonyo, V.G.P. and Modi, A.T. Water use and water use efficiency of maize landrace–bambara groundnut–dry bean intercrop system. African Combined Congress, Cape Town South Africa, 15-18 January 2018 - T. Mabhaudhi. An Integrated Approach Using Weather and Climate Applications: Lessons from the uMngeni Resilience Project. 1st annual WeatherSmart Science Symposium, Royal Elephant Hotel And Conference Centre, Pretoria, 15 March 2018 - Mabhaudhi T. Participated in panel discussion on agroecology as a panellist. Seedbeds of Transformation Conference, Port Elizabeth, 9-11 May 2018 - Tafadzwa Mabhaudhi, Cebile Jobe, Zenande Matinisi and Albert T Modi. Lessons from the uMngeni Resilience Project. Ukulinga Howard Davies Memorial Symposium, Ukulinga Research Farm, Pietermaritzburg, 22-23 May 2018 - T. Mabhaudhi, A. Clulow, M.J. Savage and V. Naiken. Improving access to climate information for learners and farmers in rural communities. Adaptation Futures Conference, Cape Town, South Africa, 18-21 June 2018 - -T. Mabhaudhi, R.P. Kunz, R.E. Schulze and A.T. Modi. Forgotten foods may hold key to future food security: mainstreaming underutilised crops into climate change adaptation. Adaptation Futures Conference, Cape Town, South Africa, 18-21 June 2018 - N. Ndlovu. Mainstreaming Climate Change Adaptation into Local Government: lessons from the uMngeni Resilience Project. Adaptation Futures Conference, Cape Town, South Africa, 18-21 June 2018 - Ndlovu N, Building Resilience in the Greater uMngeni Catchment, KZN Climate Change and Sustainable Development Goals Summit, August 2019, Durban, South Africa - Geza, W, Lessons from partnering with youth in agriculture – challenges and opportunities, Ukulinga Howard Davis Memorial Symposium, August 2019, Pietermaritzburg, South Africa - Nqabeni X, Building resilience to climate change in Nhlazuka – Emerging lessons, Ukulinga Howard Davis Memorial Symposium, August 2019, Pietermaritzburg, South Africa - Mthethwa K, Building Resilience to Climate Change in Swayimane – Emerging Lessons,Ukulinga Howard Davis Memorial Symposium, August 2019, Pietermaritzburg, South Africa - Ndlovu M, Increasing access to climate information and services helps farmers to adapt to extreme climatic variability and climate change, Ukulinga Howard Davis Memorial Symposium, August 2019, Pietermaritzburg, South Africa - Mabhaudhi, T., Sobratee, N., Chimonyo, V.G.P., Hlahla, S., Davids, R., Ngidi, M., Gwacela, and M., Geza, W. and Modi, A.T. (2019) Linking agroecology to resilience and sustainable food systems: translating research into policy and practice: Panel discussion. Agroecology for the 21st Century Conference, Centre for the Book, Cape Town, South Africa. 28 – 30 January 2019 - Mabhaudhi, T. and Modi, A.T. (2018). Water-Food-Nutrition-Health Nexus: Linking Water to Improving Food, Nutrition and Health. Keynote presentation at the World Food Day Celebrations, Pretoria, 16 October 2018 - Chimonyo VGP, iCROPM2020 Crop modelling for the Future, February 2020 - Mabhaudhi T. 2020. COVID-19 and beyond: Building resilience through transformative and nexus approaches. Keynote presentation for Dialogue on “COVID-19 and beyond: Building resilience through transformative and nexus approaches”, hosted by the Water Research Commission, 30 April 2020 - Mabhaudhi T. 2020. Research expansion on underutilised indigenous food crops: addressing food insecurity. Keynote Presentation for The Catholic Parliamentary Liaison Office, 03 September 2020 - Mabhaudhi T. 2019. Mainstreaming underutilised crops into South Africa’s food system. Keynote presentation at the World Food Day Celebrations, Pretoria, 16 October 2019 - Mabhaudhi T. 2019. Research agenda and initiatives on the WEF nexus. Keynote presentation at the Global Water Partnership – Southern Africa Special Session on Water-Energy-Food Nexus Policy Dialogue. WaterNet 20 Symposium, Johannesburg, South Africa, 31 October – 1 November 2019 - Mainstreaming underutilized indigenous and traditional crops into food systems for sustainable and healthy diet by Tafadzwa Mabhaudhi 3 September 2020 - Role of Municipalities in Climate Change by Lindokuhle Khanyile 3 September 2021 - Local Government Biodiversity Learning Network by Lindokuhle Mkhize 22 September 2021 - Adaptation Fund interview for podcast and pre-COP26 video: Interview with the AF on the AF’s projects in SA, Enhanced Direct Access, and how the Fund’s support have furthered climate action and country ownership in adaptation in the South Africa, by Mike Jennings, 16 September 2021. - Tafadzwa Mabhaudhi (2021). Africa and its ecologies: people and nature in the age of climate change. Africa and Climate Change Conference. - Tafadzwa Mabhaudhi (2021). Africa and its ecologies: people and nature in the age of climate change. University of Ghent Dialogue. - Tafadzwa Mabhaudhi (2022). Mainstreaming indigenous food crops: building resilient agri-food systems. WRC Science-Policy Dialogue on Underutilized Crops. - Tafadzwa Mabhaudhi (2022). Ensuring food, water and health security and climate resilience through the Just Transition. Presidential Climate Commission. - Tafadzwa Mabhaudhi (2022). Climate and water risks in a changing world. WRC-UKZN Science Policy Dialogue on Flood Risks. - Tafadzwa Mabhaudhi (2022). Developing early warning systems for managing climate risks. KZN PDMC Dialogue.

Journal papers

- Mabhaudhi, T., Chimonyo V.G.P., Hlahla, S., Massawe, F., Mayes, S., Nhamo, L. and Modi A.T. 2019. Prospects of orphan crops in climate change. Planta (2019) 250:695–708 - Chimonyo V.G.P., Modi A.T., and Mabhaudhi, T. 2019. Applying Apsim for Evaluating Intercropping Under Rainfed Conditions: A Preliminary Assessment. 3rd World Irrigation Forum (WIF3). 1-7 September 2019, Bali, Indonesia - Mabhaudhi, T., Mpandeli, S., Nhamo, L., Senzanje, A., Chimonyo V.G.P., and Modi A.T. 2019.Options for Improving Agricultural Water Productivity Under Increasing Water Scarcity in South Africa. 3rd World Irrigation Forum (WIF3). 1-7 September 2019, Bali, Indonesia - Mabhaudhi, T., Chibarabada, T.P., Chimonyo V.G.P., Murugani, V.G., Pereira, L.M., Sobratee, N., Govender, L., Slotow, R. and Modi A.T. 2019. Mainstreaming Underutilized Indigenous and Traditional Crops into Food Systems: A South African Perspective. Sustainability 2019, 11, 172 - Govender, L., Pillay, K. Siweal, M. Modi, A.T., and Mabhaudhi, T. 2019. Consumer Perceptions and Acceptability of Traditional Dishes Prepared with Provitamin A-Biofortified Maize and Sweet Potato. Nutrients 2019, 11, 1577 - Govender, L., Pillay, K. Siweal, M. Modi, A.T., and Mabhaudhi, T. 2019. Improving the Dietary Vitamin A Content of Rural Communities in South Africa by Replacing Non-Biofortified white Maize and Sweet Potato with Biofortified Maize and Sweet Potato in Traditional Dishes. Nutrients 2019, 11, 1198 - Chimonyo, V.G.P., Kunz, R., Modi, A., Mabhaudhi, T., Wimalasiri, E.M. (2020). Optimising traditional cropping systems under climate change: A case of maise landraces and bambara groundnut. Frontiers in Sustainable food systems. doi: 10.3389/fsufs.2020.562568 - Nhamo, L., Magidi, J., Nyamugama, A., Clulow, A.D., Sibanda, M., Chimonyo, V.G.P., Mabhaudhi, T., (2020). Prospects of Improving Agricultural and Water Productivity through Unmanned Aerial Vehicles. Agriculture 10, 256. doi:10.3390/agriculture10070256 - Chimonyo V.G.P, Chivenge P.P., Nhamo L., Mpandeli S., Modi A.T. and Mabhaudhi T. (2020). Yield and water use gaps in cereal multi-crop systems in sub-Saharan Africa under climate change. In: Sareen S, Sharma P, Singh C, Jasrotia P, Singh GP and Sarial AK. Improving Cereal Productivity through Climate Smart Practices. Elsevier, India. Woodhead Publishing, pp. 313–329. https://doi.org/10.1016/B978-0-12-821316-2.00018-2 - Mabhaudhi T., Simpson G., Badenhorst J., Senzanje A., Jewitt G.P.W., Chimonyo V.G.P., Mpandeli S. and Nhamo L. (2020). Developing a framework for the water-energy-food nexus in South Africa. In: E. S. Diop, P. Scheren and A. Niang (Eds.) Water Resources Management in the Climate Change Context in Africa. Springer Nature, Switzerland - Mabhaudhi T., Mpandeli S., Nhamo L., Chimonyo V.G.P., Senzanje A., Naidoo D., Liphadzi S. and Modi A.T. (2020). Emerging water-energy-food nexus lessons, experiences and opportunities in southern Africa In: A. Vasel and D.S-K. Ting (Eds.) Environmental Management of Air, Water, Agriculture, and Energy. Taylor and Francis, Abingdon, United Kingdom. https://doi.org/10.1201/9780429196607 - Mpandeli S, Nhamo L, Moeletsi M, Masuphu T, Magidi M, Tshikolomo K, Liphadzi S, Naidoo D and Mabhaudhi T. 2019. Assessing climate change and adaptive capacity at local scale using observed and remotely sensed data. Weather and Climate Extremes 26, 100240. https://doi.org/10.1016/j.wace.2019.100240 - Akinola R, Pereira L M, Mabhaudhi T, de Bruin F and Rusch L (2020) A Review of Indigenous Food Crops in Africa and the Implications for more Sustainable and Healthy Food Systems. Making KOS, 7 Purley Street, Kenilworth 7708, South Africa. - Barasa P, Botai CM, Botai JL and Mabhaudhi T (2021) A Review of Climate-Smart Agriculture Research and Applications in Africa. https://doi.org/10.3390/agronomy11061255 - Mabhaudhi T, Chimonyo VGP and Kunz R (2021) Developing a guideline for rainfed production of underutilised indigenous crops and estimating green water use of indigenous crops based on available models within selected bio-climatic regions of South Africa. - Mabhaudhi T, Nhamo L, Chibarabada TP, Mabaya G, Mpandeli S, Liphadzi S, Senzanje A, Naidoo D, Modi, AT and Chivenge PP (2021) Assessing Progress towards Sustainable Development Goals through Nexus Planning. https://doi.org/10.3390/w13091321 - Mugiyo H, Chimonyo VGP, Sibanda M, Kunz R, Nhamo L, Masemola CR, Dalin C, Modi AT, Mabhaudhi T (2021) Multi-criteria suitability analysis for neglected and underutilised crop species in South Africa. https://doi.org/10.1371/journal.pone.0244734 - Mustafa MA, Mabhaudhi T, Massawe F (2021) Building a resilient and sustainable food system in a changing world – A case for climate-smart and nutrient dense crops. https://doi.org/10.1016/j.gfs.2020.100477 - Ndlovu M, Clulow AD, Savage MJ, Nhamo L, Magidi J and Mabhaudhi T (2021) An Assessment of the Impacts of Climate Variability and Change in KwaZulu-Natal Province, South Africa. https://doi.org/10.3390/atmos12040427 - Nhamo L, Rwizi L, Mpandeli S, Botai J, Magidi, Tazvinga H, Sobratee, Liphadzi S, Naidoo D, Modi AT, Slotow R, Mabhaudhi T (2021) Urban nexus and transformative pathways towards a resilient Gauteng City-Region, South Africa. https://doi.org/10.1016/j.cities.2021.103266 - Shayanowako AIT, Morrissey O, Tanzi A, Muchuweti M, Mendiondo GM, Mayes S, Modi AT and Mabhaudhi T (2021) African Leafy Vegetables for Improved Human Nutrition and Food System Resilience in Southern Africa: A Scoping Review. https://doi.org/10.3390/su13052896 - Chimonyo VGP, Chibarabada TP, Choruma D, Kunz R, Walker S, Massawe F, Modi AT and Mabhaudhi T. 2022. Modelling neglected and underutilised crops: a systematic review of progress, challenges, and opportunities. Sustainability 14, 13931. https://doi.org/10.3390/su142113931. IF = 3.889: Q2. - Mugiyo H*, Chimonyo VGP, Kunz R, Sibanda M, Nhamo L, Masemola C, Modi AT and Mabhaudhi T. 2022. Mapping the spatial distribution of underutilised crop species under climate change using the MaxEnt model: A case of KwaZulu-Natal, South Africa. Climate Services 28, 100330. https://doi.org/10.1016/j.cliser.2022.100330. IF = 4.381: Q1. - Nhamo L, Paterson G, Van Der Walt M, Moeletsi M, Modi AT, Kunz R, Chimonyo VGP, Masuphu T, Mpandeli S, Liphadzi S, Molwantwa J and Mabhaudhi T. 2022. Optimal production areas of underutilised indigenous crops and their role under climate change: Focus on Bambara groundnut. Frontiers in Sustainable Food Systems 6:990213. https://doi.org/10.3389/fsufs.2022.990213. IF = 5.005: Q1. - Bonetti S, Sutanudjaja EH, Mabhaudhi T, Slotow R and Dalin C. 2022. Climate change impacts on water sustainability of South African crop production. Environmental Research Letters 17 084017. https://doi.org/10.1088/1748-9326/ac80cf. IF = 6.947: Q1. - Hlatshwayo SI*, Ojo T, Modi AT, Mabhaudhi T, Slotow R and Ngidi MSC. 2022. The effect of market participation on food security of the rural smallholder farmers in Limpopo and Mpumalanga provinces, South Africa. Agriculture 12, 1072. https://doi.org/10.3390/agriculture1207107220. IF= 3.408; Q2. - Brewer K*, Clulow A, Sibanda M, Gokool S, Odindi J, Mutanga O, Naiken V, Chimonyo VGP and Mabhaudhi T. 2022. Maize water stress estimation using foliar temperature and stomatal conductance indicators derived from optical and thermal imagery on unmanned aerial vehicle (UAV) platform. Drones 6, 169. https://doi.org/10.3390/drones6070169. IF = 5.532: Q2. - Nhamo L, Mpandeli S, Liphadzi S and Mabhaudhi T. 2022. Securing land and water for food production through sustainable land reform: A nexus planning perspective. Land 11(7), 974. https://doi.org/10.3390/land11070974. IF = 3.905: Q2. - Masenyama A, Mutanga O, Dube T, Bangira T, Sibanda M and Mabhaudhi T. 2022. A systematic review on the use of remote sensing technologies in quantifying grasslands ecosystem services. GIScience and Remote Sensing 59:1, 1000-1025. https://doi.org/10.1080/15481603.2022.2088652. IF = 6.238: Q1. - Mabhaudhi T, Hlahla S, VGP, Henriksson R, Chibarabada TP, Murugani VG, Groner VP, Tadele Z, Sobratee N, Slotow R, Modi AT, Baudron F and Chivenge P. 2022. Diversity and Diversification: Ecosystem Services Derived From Underutilized Crops and Their Co-benefits for Sustainable Agricultural Landscapes and Resilient Food Systems in Africa. Frontiers in Agronomy 4, 859223. https://doi.org/10.3389/fagro.2022.859223. IF = 3.9: Q1. - Geza W*, Ngidi MSC, Slotow R and Mabhaudhi T. 2022. The Dynamics of Youth Employment and Empowerment in Agriculture and Rural Development in South Africa: A Scoping Review. Sustainability 14, 5041. https://doi.org/10.3390/su14095041. IF = 3.889: Q2. - Tomita A, Ncama BP, Moodley Y, Davids R, Burns JK, Mabhaudhi T, Modi AT and Slotow R. 2022. Community disaster exposure and first onset of depression: A panel analysis of nationally representative South African data, 2008-2017. PLOS Climate 1(4): e0000024. https://doi.org/10.1371/journal.pclm.0000024. - Sobratee N, Davids R, Chinzila CB, Mabhaudhi T, Scheelbeek P, Modi AT, Dangour A and Slotow R. 2022. Visioning a food system for equitable transition towards sustainable diets. Sustainability 14(6), 3280. https://doi.org/10.3390/su14063280. IF = 3.889: Q2. - Kushitor SB, Drimie S, Davids R, Delport C, Hawkes C, Mabhaudhi T, Ngidi M, Slotow Rob, and Pereira LM. 2022. The complex challenge of governing food systems: The case of South African food policy. Food Security https://doi.org/10.1007/s12571-022-01258-z. IF = 3.304: Q1. - Hawkins P, Geza W, Mabhaudhi T, Sutherland C, Queenan K, Dangour A and Scheelbeek P. 2022. Dietary and agricultural adaptions to drought among smallholder farmers in South Africa: a qualitative study. Weather and Climate Extremes 35, 100413. https://doi.org/10.1016/j.wace.2022.100413. IF = 5.338: Q1. - Leakey RRB, Avana MT, Awazi NP, Assogbadjo AE, Mabhaudhi T, Hendre PS, Ann Degrande, Hlahla S and Manda L. 2022. The future of food: domestication and commercialization of indigenous food crops in Africa over the third decade (2012-2021). Sustainability 14(4) 2355; https://doi.org/10.3390/su14042355. IF = 3.889: Q2. - Cho MA, Mutanga O. and Mabhaudhi T. 2022. Local actors’ participation in rangeland management systems and the role of participatory GIS: The Case of Vulindlela, South Africa. Journal of Environmental Planning and Management https://doi.org/10.1080/09640568.2021.2017269. IF = 2.735: Q2. - Phoobane P, Masinde M and Mabhaudhi T. 2022. Predicting Infectious Diseases: A Bibliometric Review on Africa. Int. J. Environ. Res. Public Health 2022, 19, 1893. https://doi.org/10.3390/ijerph19031893. IF = 3.364: Q2. - Brewer K*, Clulow A, Sibanda M, Gokool S, Naiken V, Mabhaudhi T. 2022. Predicting the chlorophyll content of maize over phenotyping as a proxy for crop health in smallholder farming systems. Remote Sensing 14(3):518. https://doi.org/10.3390/rs14030518. IF = 5.349: Q2. - Mudau F, Chimonyo VGP, Modi AT and Mabhaudhi T. 2022. Neglected and underutilised crops: A systematic review of their potential as food and herbal medicinal crops in South Africa. Frontiers in Pharmacology 12, 809866. https://doi.org/10.3389/fphar.2021.809866. IF = 5.988: Q1. - Sibanda M, Mutanga O, Chimonyo VGP, Clulow AD, Shoko C, Mazvimavi D, Dube T and Mabhaudhi T. 2021. Application of drone technologies in surface water resources monitoring and assessment: a systematic review of progress, challenges, and opportunities in the global South. Drones, 6, 131. https://doi.org/10.3390/drones6050131. IF = 5.532: Q2. - Ndlovu HS*, Odindi J, Sibanda M, Mutanga O, Clulow AD, Chimonyo VGP and Mabhaudhi T. 2021. A comparative estimation of maize leaf moisture content on smallholder farming systems using Unmanned Aerial Vehicle (UAV) based proximal remote sensing. Remote Sensing. 13(20), 4091; https://doi.org/10.3390/rs13204091. IF = 5.349: Q2. - Govender L*, Pillay K, Siwela M, Modi AT and Mabhaudhi T. 2021. Assessment of the nutritional status of four selected rural communities in KwaZulu-Natal, South Africa. Nutrients 13(9), 2920. https://doi.org/10.3390/nu13092920. IF = 6.706: Q1. - Geza W*, Ngidi M, Ojo T, Adetoro AA, Slotow R and Mabhaudhi T. 2021. Youth participation in agriculture: A scoping review. Sustainability 13(16), 9120. https://doi.org/10.3390/su13169120. IF = 3.889: Q2 - Leakey RRB, Mabhaudhi T and Gurib-Fakim A. 2021. African lives matter: wild food plants matter for livelihoods, justice, and the environment – an agricultural policy brief. Sustainability 13(13), 7252; https://doi.org/10.3390/su13137252. IF = 3.889: Q2. - Barasa PM*, Botai CM, Botai JO and Mabhaudhi T. 2021. A Review of climate-smart agriculture research and applications in Africa. Agronomy 11(6), 1255. https://doi.org/10.3390/agronomy11061255. IF = 3.949: Q1. - Mahomed M*, Clulow AD, Strydom S, Mabhaudhi T and Savage MJ. 2021. Assessment of a ground-based lightning detection and near real-time warning system in the rural community of Swayimane, KwaZulu-Natal, South Africa. Weather, Climate, and Society 13, 605-621. https://doi.org/10.1175/WCAS-D-20-0116.1. IF = 3.019: Q2. - Ndlovu M*, Clulow A, Savage MJ, Nhamo L, Magidi J and Mabhaudhi T. 2021. An assessment of the impacts of climate variability and change in KwaZulu-Natal Province, South Africa. Atmosphere 12(4), 427; https://doi.org/10.3390/atmos12040427. IF = 2.686: Q3. - Matilda Azong Cho, O. Mutanga & T. Mabhaudhi (2023): Understanding local actors’ perspective of threats to the sustainable management of communal rangeland and the role of Participatory GIS (PGIS): the case of Vulindlela, South Africa, South African Geographical Journal, DOI: 10.1080/03736245.2023.2190153 To link to this article: https://doi.org/10.1080/03736245.2023.2190153 - Matilda Azong Cho, Mutanga Onisimo & Tafadzwanashe Mabhaudhi (2023): Using participatory GIS and collaborative management approaches to enhance local actors’ participation in rangeland management: the case of Vulindlela, South Africa, Journal of Environmental Planning and Management, 66:6, 1189-1208, DOI: 10.1080/09640568.2021.2017269 To link to this article: https://doi.org/10.1080/09640568.2021.2017269 - Chimonyo, V.G.P.; Chibarabada, T.P.; Choruma, D.J.; Kunz, R.; Walker, S.; Massawe, F.; Modi, A.T.; Mabhaudhi, T. (2022): Modelling Neglected and Underutilised Crops: A Systematic Review of Progress, Challenges, and Opportunities. Sustainability 2022, 14, 13931. https://doi.org/10.3390/su142113931 - Buthelezi, S.; Mutanga, O.; Sibanda, M.; Odindi, J.; Clulow, A.D.; Chimonyo, V.G.P.; Mabhaudhi, T. Assessing the Prospects of Remote Sensing Maize Leaf Area Index Using UAV-Derived Multi-Spectral Data in Smallholder Farms across the Growing Season. Remote Sens. 2023, 15, 1597. https://doi.org/10.3390/rs15061597 - Bizimana, J.-C.; Yalew, B.B.; Assefa, T.T.; Belay, S.A.; Degu, Y.M.; Mabhaudhi, T.; Reyes, M.R.; Prasad, P.V.V.; Tilahun, S.A. (2023): Simulating Potential Impacts of Solar MajiPump on the Economy and Nutrition of Smallholder Farmers in Sub-Humid Ethiopia. Water 2023, 15, 4003. https://doi.org/10.3390/w15224003 - Bhebhe, Q.N.; Ngidi, M.S.C.; Siwela, M.; Ojo, T.O.; Hlatshwayo, S.I.; Mabhaudhi, T. (2023): The Contribution of Trees and Green Spaces to Household Food Security in eThekwini Metro, KwaZulu-Natal. Sustainability 2023, 15, 4855. https://doi.org/10.3390/su15064855 - Bangira, T.; Mutanga, O.; Sibanda, M.; Dube, T.; Mabhaudhi, T. (2023): Remote Sensing Grassland Productivity Attributes: A Systematic Review. Remote Sens. 2023, 15, 2043. https://doi.org/10.3390/rs15082043 - Agbehadji, I.E.; Mabhaudhi, T.; Botai, J.; Masinde, M. (2023): A Systematic Review of Existing Early Warning Systems’ Challenges and Opportunities in Cloud Computing Early Warning Systems. Climate 2023,11, 188. https://doi.org/10.3390/cli11090188 - Abrahams, M.; Sibanda, M.; Dube, T.; Chimonyo, V.G.P.; Mabhaudhi, T. (2023): A Systematic Review of UAV Applications for Mapping Neglected and Underutilised Crop Species’ Spatial Distribution and Health. Remote Sens. 2023, 15, 4672. https://doi.org/10.3390/rs15194672 - Ndlovu, H.S.*, Odindi, J., Sibanda, M., Mutanga, O., Clulow, A., Chimonyo, V.G. and Mabhaudhi, T., 2024. Use of unmanned aerial vehicle-derived multi-spectral data for the early detection of multi-temporal maize leaf equivalent water thickness and fuel moisture content for the improved resilience of smallholder maize farming. Journal of Applied Remote Sensing, 18(1), pp.014520-014520. https://doi.org/10.1117/1.JRS.18.014520. - Agbehadji, I.E., Schütte, S., Masinde, M., Botai, J. and Mabhaudhi, T. 2023. Climate Risks Resilience Development: A Bibliometric Analysis of Climate-Related Early Warning Systems in Southern Africa. Climate, 12(1), p.3. https://doi.org/10.3390/cli12010003. - Geza, W*., Ngidi, M.S.C., Mudhara, M., Slotow, R. and Mabhaudhi, T., 2023. ‘Is there value for us in agriculture?’ A case study of youth participation in agricultural value chains in KwaZulu-Natal, South Africa. Cogent Food & Agriculture, 9(2), p.2280365. https://doi.org/10.1080/23311932.2023.2280365

Books

- Books: The "Beneficiary Stories" noted above were included in the AF's 10-year anniversary book: Adaptation Fund: 10 Years of Innovation, Action & Learning (https://www.adaptation-fund.org/wp-content/uploads/2017/11/Adaptation-Fund-10-Years-of-Innovation-Action-Learning_WEB.pdf). - Climate Change: a KwaZulu-Natal Agricultural Perspective by Prof Roland Schulze (developed for the URP to assist with training of Department of Agriculture and Rural Development Extension Officers)

Toolkit

- Climate Change Adaptation Toolkit. Produced for the uMngeni Resilience Project through a partnership of Swelihle Agricultural & Environmental Group, Built Environment Support Group (BESG), City Insight, and Partners in Development (PID)

Videos

- URP Full video/short documentary (URP Master Videos - Dropbox) - URP Component 1 summary (URP Master Videos - Dropbox) - URP Component 2 summary (URP Master Videos - Dropbox) - URP Component 3 summary (URP Master Videos - Dropbox) - URP Component 4 summary (URP Master Videos - Dropbox)

Pamphlets, guidelines and posters

- Climate Change Info Sheet (English and isiZulu) (A3 folded to A4); Climate change in the uMDM info booklet (A5); A Changing Climate (A4 info page). - How To Guidelines on: Household risk reduction, environmental awareness, household food security, repairing damaged homes after a storm and household financial management - uMgungundlovu District Municipality Climate Change Adaptation Mainstreaming Leaflet series: Leaflet 1: Understanding Climate Change; Leaflet 2: Reducing the impacts of climate change at a village level; Leaflet 3: Household resilience to climate change; Leaflet 4: Erosion - COVID-19 handbook produced for URP smallholder farmers - Introductory Manual to Food Security for Extension Workers; developed for the uMngeni Resilience Project - Guidelines for Integrating Gender and Social Equity into the URP and other Development Programmes in the uMgungundlovu District Municipality; developed by Dr. Kwame Owusu-Ampomah for the uMngeni Resilience Project - -UKZN - URP Climate Smart Agriculture Brochure series: Part 1: Seasonal Calendar; Part 2: How to plant; Part 3: Manage your garden; Part 4: Tunnel production; Part 5: Climate change adaptability and Part 6: Run your farm as a business - Climate change awareness posters produced for the uMngeni Resilience project - Developing a guideline for rainfed production of underutilized indigenous crops and estimating green water use of indigenous crops based on available models within selected bio-climatic regions of South Africa by T. Mabhaudhi, VGP Chimonyo and R. Kunz - Climate change awareness posters produced for the uMngeni Resilience Project - Climate Change and Extreme Weather: Fire poster, Flood poster, Wind poster, Drought poster, Global Warming poster, Lightning poster - Pamphlets were produced on the following: Ginger Production; Garlic Production; and Packhouse Management - URP leaflet 4_Lightening Early Warning System: Lightning Warning System - URP Booklet 3_component 2 overview: Improved climate resilience of rural communities through investments in built and ecological infrastructure policy mainstreaming - URP leaflet 2 Rangeland management: Rangeland Management Plan (RMP) - URP leaflet 1_Ecological Infrastructure: Restoration of Critical Ecological Infrastructure to Improve its Capacity to Mitigate the Effects of Climate-Induced Disaster

Appendix 4: List of grant projects catalysed through the uMngeni Resilience Project

- Sustainable and Healthy Food Systems for Southern Africa (SHEFS-SA) (2024-2030) (funded by Wellcome Trust GBP5.9 million).

- Shaping food environments in transitioning economies for sustainable and healthy diets (FoodE) (2023-2025) (funded by BMEL Germany Euro 1,300,999; UKZN EURO 261 516).

- Operationalising the water-energy-food nexus (WRC funded project CON2021/2022-00913) (2022-2027) (ZAR5 million).

- Drone applications for determining water quality and quantity in canals for irrigation (WRC funded project CON2021/2022-00914) (2022-2027) (ZAR2 million).

- Commercialisation of nutrient-dense and drought-tolerant traditional and indigenous crops (2021-2024) (funded by the Technology Innovation Agency of South Africa, ZAR6 million) – this is scaling out and up the work on NUS, particularly taro and amadumbe.

- South Africa: Sustainable Agriculture Matrix (SAM Consortium) (2021-2023) (funded by the Belmont Forum, a consortium of eight countries, €50 000).

- Increasing agricultural water productivity for improved food and nutrition security in water-scarce environments (2021-2023) (WRC funded project CON2020/2021-00701, ZAR2 million).

- Managing rangelands for improved water productivity in water-scarce environments of South Africa (2021-2024) (WRC funded project CON2020/2021-00490, ZAR1.5 million) – this is scaling the work done in URP Component 2.2 on rangelands management to the whole of the Umgeni catchment.

- Water use and nutritional water productivity of bush tea (WRC funded project CON2020/2021-00420 (2021-2025) (ZAR2 million) – this is scaling the URP work on NUS to Mpumalanga and Limpopo.

- Building Well-being, sOcial cOhesion, and Dignity by restoring environmental RIGHTS (WoodRIGHTS) A University of KwaZulu-Natal Strategic Flagship Project (2020-2021) (ZAR6 million) – this was a strategic project on scaling integrated approaches that link Ecological Infrastructure to food security and human well being.

- ‘Water use indigenous root and tuber crops’ (WRC funded project C2019/2020-00088) (2020-2023) (US$140 000) – this has been implemented in KZN and supported the evidence on scaling taro/amadumbe.

- ‘Improving resilience and nutrient retention of leafy vegetables for improved health in Southern Africa and Zimbabwe’ (2019-2020) (Global Challenges Research Funding, £249 000) consortium with the University of Nottingham-UK, University of Nottingham-Malaysia and University of Zimbabwe – this expanded the URP work on nutrient-dense leafy vegetables to Zimbabwe.

- ‘Use of drones to monitor crop health, water stress, crop water requirements and improve crop water productivity to enhance precision agriculture and irrigation scheduling’ (2019-2023) (WRC funded project WRCK5/2971//4, US$125 000) – this supported URP Component 1.3 in Swayimane to enhance the link between CIS and CSA and farmer advisory.

- ‘Water-Energy-Food Nexus as a sustainable approach for advancing food and nutrition security and achieving SDGs 2, 6 and 7 with specific attention to efficient energy use food production’ (2019-2023) (WRC funded project WRCK5/2967//4, US$100 000).

- ‘Beacons of Future Food Security’ (2019-2022) (funded by Future Food Beacon, £200 000) in collaboration with the University of Nottingham-UK and the University of Nottingham-Malays.

- ‘Developing guidelines for estimating green water use of indigenous crops in South Africa and estimating water use using available crop models for selected bio-climatic regions of South Africa’ (2017-2022) (WRC funded project WRC K5/2717//4, US$140 000) – this scaled the URP work on NUS to the national level by developing crop suitability maps for the whole of South Africa.

- ‘Water use of crops and nutritional water productivity for food production, nutrition and health in poor rural communities’ (2015–2020) (WRC funded project WRCK5/2493//4, $280 000).

- Shaping food environments in transitioning economies for sustainable and healthy diets (FoodE). (funded by BMEL Germany Euro 1,300,999 ; UKZN EURO 261 516) – this is scaling the focus on NUS, nutrition and food environments in SA, Tanzania, Ghana, Malaysia and Germany.

- Drone applications for determining water quality and quantity in canals for irrigation (WRC funded project CON2021/2022-00914, ZAR2 million) – the is scaling URP Component 1.3, which helped us to develop a portfolio of digital agricultural innovations.

- Sustainable and Healthy Food Systems (SHEFS) programme (funded by the Wellcome Trust, a consortium of 11 institutions, £5.4m) – focused on scaling evidence from the URP into policy outcomes.

Appendix 5: Results reported in the Year 9 Project Performance Report Results Tracker tab

| Indicator |  |  | Target performance at completion |  |  |  |  |  | Performance at completion |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) |  | Direct beneficiaries supported by the project |  | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) |  | Direct beneficiaries supported by the project |  | Indirect beneficiaries supported by the project |  |
|  |  | Total | 25,640 |  | 3,855 |  | 21,785 |  | 102,855 |  | 102,855 |  | 0 |  |
|  |  | % of female beneficiaries | 52% |  | 55% |  | 52% |  | 52% |  | 52% |  | 0.00% |  |
|  |  | % of Youth beneficiaries | 8% |  | 10% |  | 8% |  | - |  | - |  | - |  |
| Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems |  | No. of adopted Early Warning Systems | Category targeted |  | Hazard |  | Inland flooding | No. of adopted Early Warning Systems | Category targeted |  | Hazard |  | Inland flooding |  |  |  |  |
|  |  |  | 3 | 2: Monitoring and warning service |  | Geographical coverage |  | Regional | 3 | 2: Monitoring and warning service |  | Geographical coverage |  | Regional |
|  |  |  |  |  |  | Number of municipalities |  | 2 |  |  |  | Number of municipalities |  | 2 |
|  |  |  | No. of adopted Early Warning Systems | Category targeted |  | Hazard |  | Wind (Fire) | No. of adopted Early Warning Systems | Category targeted |  | Hazard |  | Wind (Fire) |
|  |  |  | 3 | 1: Risk knowledge |  | Geographical coverage |  | Local | 3 | 1: Risk knowledge |  | Geographical coverage |  | Local |
|  |  |  |  |  |  | Number of municipalities |  | 2 |  |  |  | Number of municipalities |  | 2 |
|  |  |  | No. of adopted Early Warning Systems | Category targeted |  | Hazard |  | Drought | No. of adopted Early Warning Systems | Category targeted |  | Hazard |  | Drought |
|  |  |  | 3 | 3: Dissemination and communication |  | Geographical coverage |  | Local | 3 | 3: Dissemination and communication |  | Geographical coverage |  | Local |
|  |  |  |  |  |  | Number of municipalities |  | 2 |  |  |  | Number of municipalities |  | 1 |
| Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses |  | No. of targeted beneficiaries |  | % of female participants targeted |  | Level of awareness |  | No. of targeted beneficiaries |  | % of female participants targeted |  | Level of awareness |  |
|  |  |  | 20,512 |  | 52% |  | 5: Fully aware |  | 23,332 |  | 52% |  | 4: Mostly aware |  |
| Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Core Indicator 4.2: Assets produced, developed, improved or strengthened |  | Sector |  | Targeted asset |  | Changes in asset (quantitative or qualitative) |  | Sector |  | Targeted asset |  | Changes in asset (quantitative or qualitative) |  |
|  |  |  | Multi-sector |  | 2: Physical asset (produced/improved/strengthened) |  | 5: Fully improved |  | Multi-sector |  | 2: Physical asset (produced/improved/strengthened) |  | 3: Moderately improved |  |
|  |  |  | Multi-sector |  | 2: Physical asset (produced/improved/strengthened) |  | 5: Fully improved |  | Multi-sector |  | 2: Physical asset (produced/improved/strengthened) |  | 3: Moderately improved |  |
|  |  |  | Multi-sector |  | 2: Physical asset (produced/improved/strengthened) |  | 5: Fully improved |  | Multi-sector |  | 2: Physical asset (produced/improved/strengthened) |  | 5: Fully improved |  |
| Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated |  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated |  | Unit |  | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated |  | Unit |  | Effectiveness of protection/rehabilitation |
|  |  |  | Rangelands | 200 |  | ha rehabilitated |  | 5: Very effective | Rangelands | 206 |  | ha |  | 5: Very effective |
|  |  |  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated |  | Unit |  | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated |  | Unit |  | Effectiveness of protection/rehabilitation |
|  |  |  | Catchment area/Watershed/Aquifer | 100 |  | ha rehabilitated |  | 5: Very effective | Catchment area/Watershed/Aquifer | 2756 |  | ha |  | 2: Partially effective |
|  |  |  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated |  | Unit |  | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated |  | Unit |  | Effectiveness of protection/rehabilitation |
|  |  |  | Catchment area/Watershed/Aquifer | 12 |  | km rehabilitated |  | 5: Very effective | Catchment area/Watershed/Aquifer | 5 |  | km |  | 5: Very effective |
| Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies |  | Number of Assets | Type of Assets |  | Sector |  | Adaptation strategy | Number of Assets | Type of Assets |  | Sector |  | Adaptation strategy |
|  |  |  | 405 | Natural capital |  | Agriculture |  | Livelihoods | 860 | Natural capital |  | Agriculture |  | Livelihoods |
|  | Core Indicator 6.1.2: Increased income, or avoided decrease in income |  | Number of households (total number in the project area) |  |  | Income source |  | Income level (USD) | Number of households (total number in the project area) |  |  | Income source |  | Income source |
|  |  |  | 200 |  |  | Agriculture |  | 228 | 860 |  |  | 243 |  | Agricultural-related |
| Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks |  | No. of Policies introduced or adjusted | Sector |  | Scale |  | Type | No. of Policies introduced or adjusted | Sector |  | Scale |  | Type |
|  |  |  | 3 | Multi-sector |  | National |  | Other policy | 2 | Multi-sector |  | National |  | Other policy |
|  | Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced |  | No. of Policies introduced or adjusted | Sector |  | Scale |  | Type | No. of Development strategies | Regulation |  |  |  | Effectiveness |
|  |  |  | 3 | Multi-sector |  | National |  | Other policy | 7 | 2: Partially not enforced (Most elements not implemented) |  |  |  | 3: Moderately effective |