## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 01 October 2019 - 30 September 2020
| Project Title: | Taking Adaptation to the Ground: A Small Grants Facility for Enabling Local Level Responses to Climate Change
| Project Summary: | The overall goal of the project is to ensure that local communities in the project focal areas have reduced vulnerability and increased resilience to the anticipated impacts of climate change. The objective is to incorporate climate adaptation response strategies into local practices so that assets, livelihoods and ecosystem services are protected from climate induced risks associated with expected droughts, seasonal shifts and storm-related disaster events. To do so, the project seeks to increase climate resilience in productive landscapes and socio-economic systems in communities in two pilot district municipalities (Mopani, and Namakwa) in South Africa, by working directly with local stakeholders and anticipated beneficiaries through a small grant mechanism.
| Database Number: | ZAF/NIE/Multi/2013/2
Implementing Entity (IE) [name]: |  | South African National Biodiversity Institute (SANBI)
| Type of IE: | National
| Country(ies): | South Africa
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Northern Cape Province - Namakwa District Municipality; Limpopo Province - Mopani District Municipality
Project Milestones
Milestone
AFB Approval Date: |  | 2014-10-10
IE-AFB Agreement Signature Date: |  | 2014-10-28
Start of Project/Programme: |  | 2015-09-16
Mid-term Review Date (if planned): |  | 2018-08-30 (Note: the Mid-term Evaluation has been submitted to the Adaptation Fund)
| Terminal Evaluation Date: | Completed December 2020 and appended to PPR5 along with the management responses.
List documents/ reports/ brochures / articles that have been prepared about the project during this reporting period.
1. Case Studies (awaiting publication)
List the Website address (URL) of project.
Project contacts:
National Project Manager/Coordinator
| Name: | Carl Wesselink
| Email: | carl@southsouthnorth.org
Date:
Government DA
| Name: | Ms Nomfundo Tshabalala
| Email: | dg@environment.gov.za
Date:
Implementing Entity
| Name: | Mandy Barnett
| Email: | m.barnett@sanbi.org.za
Date:
Executing Agency
| Name: | Carl Wesselink
| Email: | carl@southsouthnorth.org
Date:
Facilitating Agency
| Name: | Julia Levin
| Email: | jlevin@conservation.org
Date:
Facilitating Agency
| Name: | Nicola Stuart-Thompson
| Email: | NIKKI@choicetrust.co.za
Date:

## Financial Data
Financial information: cumulative from project start to 30 September 2020
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 30 September 2020 | 2456750
Add any comments on AF Grant Funds. (word limit=200) | The delivery rate of the project in the fifth year of implementation of the Community Adaptation Small Grants Facility (SGF) is 93 % against the planned expenditure schedule. This is an improvement on the 71 % delivery rate achieved in the fourth year. 22% percent of the expenditure for Year 5 was spent by Small Grant Recipients. The balance of the expenditure for the year relates to ongoing support and mentoring provided to the Small Grant Recipients by the Facilitating Agencies, project learning, project execution (administration) and project management fees. Expenditure to date is 95% of the project budget, and 100% of the grant amount was transferred to SANBI. The exchange rate on the funding of the Small Grant Recipient's allocation (Component 1) of the project, in terms of the total grant provided by the AF to date, has been ring-fenced at USD$1= ZAR12.28 on the first disbursement and USD$1= ZAR12.73 on the second disbursement. A request for a 9 month project no-cost extension has been submitted to the Adaptation Fund.
INVESTMENT INCOME | 3136
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1: Adaptation assets strengthened through the implementation of at least 12 small grants (approximately USD 100,000 each) disbursed to at least 12 local institutions in the Mopani and Namakwa District Municipalities | 50178.4187
| Output 2.1: At least 12 local institutions in the Mopani and Namakwa Districts are supported to develop small grant projects for local-level adaptation | 0
| Output 2.2 At least 12 local institutions in the Mopani District and Namakwa District are supported to implement integrated climate adaptation responses | 75100.8432
Output 2.2 Investment Income
| Output 3.1: Training opportunities are provided for Small Grant Recipients | 4543.078
| Output 3.2: Local networks for reducing climate change vulnerability and risk reduction are developed, expanded and strengthened | 4496.1645
| Output 3.3: Case studies and policy recommendations are developed for reflecting on, replicating and scaling up small grant financing approaches | 30154.5891
| Output 3.3 Investment Income | 32580.7928
| Project execution cost | 41108.9749
| Project execution cost Investment Income | 83842
| Implementing Entity project management fee | 16034.37
| Implementing Entity project management fee Investment Income | 25529.1292
| TOTAL | 363568.3604
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: Adaptation assets strengthened through the implementation of at least 12 small grants (approximately USD 100,000 each) disbursed to at least 12 local institutions in the Mopani and Namakwa District Municipalities | 128000 | 2021-12-31
| Output 1.1 Investment Income | 40983.6066 | 2021-12-31
Output 2.1: At least 12 local institutions in the Mopani and Namakwa Districts are supported to develop small grant projects for local-level adaptation
Output 2.2: At least 12 local institutions in the Mopani District and Namakwa District are supported to implement integrated climate adaptation responses
Output 3.1: Training opportunities are provided for Small Grant Recipients
Output 3.2: Local networks for reducing climate change vulnerability and risk reduction are developed, expanded and strengthened
Output 3.3: Case studies and policy recommendations are developed for reflecting on, replicating and scaling up small grant financing approaches
| Output 3.3 Investment Income | 34153 | 2021-12-31
Project execution cost
| Project execution cost Investment Income | 17851.9016 | 2021-12-31
| Implementing Entity project management fee | 9508.4105 | 2021-12-31
Implementing Entity project management fee Investment Income
| TOTAL | 230496.9187
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Not Applicable
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | The SGF project terminal evaluation noted that all project partners reported that they had provided significant co-financing for the project, even though this was not a contractual requirement. The co-financing figures below are based on submissions received from the project IE, EE, and Facilitating Agencies, from project inception to the end of Year 5. The SANBI estimate includes Year 6. FA Mopani: USD 55 366,70 FA Namakwa: USD 232 057,72 EE: USD 465 976,40 National Implementing Entity: USD 1 188 495, 58 This provides a total of USD 48 073 560.00 co-financing contributions. These figures do not include co-financing contributions by the individual Small Grant Recipients involved in the implementation of the project. At the time of commissioning the project Terminal Evaluation, the project end date was June 2020. Due to a range of unforeseen circumstances, including the COVID-19 19 pandemic, the project was extended to December 2021. In practice this has meant that the TE was completed before the project had come to a close. This PPR for Year 5 reports on activities that were largely covered by the TE, but the projected programme of work for Years 6 and 7 was not anticipated or reflected upon..
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | Not Applicable

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Financial | Identified Risk | Current Status | Steps Taken to Mitigate Risk
| Fluctuations in exchange rate (USD - US Dollars : ZAR - South African Rands) which could affect the funding available for implementation and lead to budgetary constraints. | Low | The payments received by the National Implementing Entity from the AF have continued to be received at an exchange rate more favourable than predicted in the project proposal. Despite this, a precautionary approach has been adopted. The Executing Entity (EE) and the National Implementing Entity (NIE) worked together closely on the programming of any exchange gains to support necessary adaptive management going forward. It is for this reason that this risk is rated low, the same rating as for the previous year's report.
| Ineffective management of project funds affects project implementation. | Low | Proactive management of project funds and cascading levels of oversight provided mechanisms through which the complexity of community-based climate change adaptation (CB CCA) projects could be sufficiently managed and facilitated opportunity to discern poor practice, mismanagement and/or malpractice. To further support effect management of funds the FAs delivered or facilitated the delivery of financial management training to build the capacity of SGRs in this regard, which continued into Year 5. Where necessary, an external financial service provider was procured to assist identified SGRs with financial management processes and reporting. The Year 4 audit was completed in January 2021 and can be made available. Procurement for the Year 5 audit is underway. The stringent controls that are in place to ensure financial management, alongside the fact that the project is ending, is the reason that this risk rating remains low.
| Delays in the disbursement of funds, procurement and institutional inefficiencies (e.g. lengthy approval processes) result in delayed recruitment of project staff and hence project implementation. | Low | The EE experienced many challenges in receiving SGRs quarterly reports that were compliant with SGF Standard Operating Procedures (SOPs) and policies. Remediating inadequacies, including inconsistent reporting or lack of requisite supportive documents, involved the Facilitating Agencies and / or the EE working directly with SGRs through iterative versions of reports alongside multiple reviews of copious documents. The rating risk is low for the period under review as there are no further disbursements to SGRs conducted during this reporting period. All SGR projects had completed implementation by the end of the first quarter in Year 5, which resulted in a rating of 'Low'.
| Delayed implementation and completion of small grant projects due to unanticipated events | Low | All SGR projects were complete by the end of this period, resulting in a "low" rating.
Project | Lack of incentives for local communities and Small Grant Recipients to apply for small grants, initially, and failure to create ownership of the projects at the community level once the small grants are awarded. | Low | The facilitation of community ownership and buy-in was a priority throughout the project, and particular attention placed on these activities as projects closed in throughout Year 5. Despite 11 of 12 projects being closed-out by the end of year 4, the Facilitating Agencies provided support and guidance to SGRs to strengthen their capacity to implement their respective Sustainability Plans into Year 5. Particularly relevant was the support provided to the Homu14B community following the suspension and expiry of the Khanimamba SGR contract, which resulted in the inability to complete many project activities and the need for remediation to some structures. During this process the Facilitating Agency facilitated further engaged with the community and it's traditional leadership, conducting a meeting that included the Department of Agriculture and the Mopani District Municipality to design a process that ensured community members benefited - and continued to lead the development of actions - from their participation in the project despite the fact that the SGR contract ended. This approach resulted in the development of adaptation assets and increased resilience in a community that, without SGF intervention, would have not been achieved. This risk is rated as low, as per the previous years.
| Small grant projects under the identified Investment Windows fail to build climate resilience in vulnerable, local communities. | Low | Increased resilience as a result of the adaptation interventions implemented by the Small Grant Recipients was fully visible in this final year of the Small Grants Facility. The Facilitating Agencies and the Executing Entity continued to work closely with Small Grant Recipients to ensure that the projects are implemented as planned, and deliver the adaptation benefits that build local resilience in the target communities. The Facilitating Agencies and Executing Entity provided substantial support to the SGRs and beneficiaries, including several site visits conducted by the FAs during the reporting period, to support SGRs with sustainability planning and implementation to develop and put in place effective sustainability measures to maintain the project activities after close out, and to continue to enhancing climate resilience in the local target communities beyond the SGF. All SGR projects are completed, therefore, this risk is rated "low".
Institutional | Poor coordination with other climate change projects in the focal areas limits the potential to learn from and build on the experiences of related projects. | Low | The knowledge base and connectedness of the Technical Advisory Group, that consisted of local government and local experts, provided a valuable network and support mechanism at grassroots level. A final Project Management Team Reflection and Learning workshop was conducted, which included the PMT and the NIE. WhatsApp groups, facilitated in each district provided an ongoing platform for SGRs to share successes, challenges and information. Furthermore, nine case studies were co-created and finalised during the reporting period as another means through which learnings were captured and could be disseminated. Given the ongoing and well supported programme of work in this area of work, this risk has been rated low, as in previous years.
| Limited capacity of grant recipients to coordinate and deliver project outputs | Low | A range of capacity building activities were implemented to support SGRs at all stages of the process, including two during Year 5. During this reporting period, the capacity building activities were largely informal and focused on strengthening project sustainability, including shelter maintenance training (CLB) and WASH training (KHF) in Namakwa and agro ecology training in Mopani to several SGRs, with particular focus on the Homu14B community. Informal support was delivered to the SGRs to assist in the completion of the financial reporting following close-out. This risk has been rated at "Low" because project outputs have largely been met and all projects closed.
| Project governance structures fail to perform effectively and efficiently | Low | The clear delineation of roles and responsibilities amongst the SGF Project Management Team, which were better understood and articulated in the latter half of the project, improved efficiency. Notwithstanding the above, project governance has been effective and all decisions have been well considered, transparent and inclusive of all actors.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
| Identified Risk | Current Status | Steps Taken to Mitigate Risk
| Delays in the disbursement of funds, procurement and institutional inefficiencies results in delayed project implementation. | Low | Despite a series of adaptive management approaches being applied to shorten delays in the disbursement of funds, including a mechanism for the NIE to make payments outside of the quarterly reporting cycles, these adaptive management measures were only been partially successful and cash flow remained a challenge for project partners. The delays have caused strain for the EE into Year 5, who ultimately shouldered the risk for lack of project performance. The rating risk is low for the period as the project winds up and nearly all disbursements have been completed.
| Rigorous compliance and procurement requirements result in project expenses being disallowed. | Low | Only one SGR project was being implemented in Year 5, and that closed-out in the first quarter, resulting in little expenditure in Year 5 also contributes to the low rating.
| Project sustainability | Low | Despite significant ongoing efforts, and a particular focus on- and resources deployed- towards activities to promote sustainability, risk of projects collapsing at the close of the SGF remain. It is therefore noted that the sustainability of the community based climate change adaptation projects require time and resources beyond the scope of the design of the SGF. Although significant climate change adaptation benefits were achieved, and significant capacity developed towards facilitating increased ability for vulnerable communities to cope and manage adaptation efforts, there is the risk that projects will not be sustained without the support and resources of the SGF. SGF project staff, including the SGRs themselves, have actively sought additional resources to address this shortfall, and some have noted success. Fundraising opportunities were shared with SGRs, including one that resulted in 1 SGR (Ramotshinyadi) receiving funding from the Department of Agriculture for R50,000 to support poultry production. The risk, however, remains a reputational hazard to the SGF Project, as the sustainability of SGR projects is in one way a measure of the SGF Project’s success, as well as undermining the initial Adaptation Fund investment. Although the risk of occurrence is medium, it is rated low as its impact on the SGF Project remains rated as low. SANBI NIE comment: SANBI (NIE) and DEFF (NDA) remain committed to sustaining the gains of the SGF, to supporting the grantees and to creating a long term funding mechanisms that supports local organisations who are vulnerable to climate change. This is a focus of the programme of work for the period to December 2021.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
All risks are “Low” or “Medium” rated and remain subject to continuous monitoring to prevent their escalation. In all cases the measures successfully contained or reduced the risks. The project has not encountered any ‘High’ risks this year.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1]
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law
2 - Access and equity
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency
13 – Public health
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | Yes
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | See USP table below. Additionally the review of the ESP risks against planned and undertaken activities was completed regularly, when projects introduced new activities, each reporting quarter by the EE and an ESP site visits were conducted during last quarter for each project year by the EE and/or NIE.
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The ESP principles were applied to USPs throughout the project, including during the review process, through site visits and during reporting, as per the project ESMP. See Section 6 for hyperlinks to relevant documentation.
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The SGRs in the SGF project were all Unidentified Sub-Projects, therefore, ESP assessments were only conducted after the SGF project was approved. This resulted in considerable effort being undertaken by both the NIE and the EE to ensure ESP compliance, including intensive research on various regulations and procedures and their application. Therefore, the EE, in collaboration with the FAs, provided technical advice and guidance to identify and manage ESPs risks. The EE tracked SGR progress managing ESP risks on a quarterly basis and assisted in identifying risks in the annual ESP risk assessments. Continual support was provided to the SGRs to identify other potential risks and develop mitigating measures that may have arisen in the quarter. This support helped to ensure focus on the ESP risks was maintained and the SGRs continued to address them adequately.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11] |  | No – not required. However the review of the ESP risks against planned and undertaken activities was completed regularly, when projects introduced new activities, each reporting quarter and an ESP site visit was conducted during last quarter for each year.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: Gondwana Alive - “Climate, Biodiversity, and Red Meat – Land & Livestock Adaptation” | Yes | SANBI USP /SGR proposal review process – see SANBI review | Yes | Yes | Yes for Principle 2,3 and 5, in the beneficiary identification process. | See Contract Conditions (Annex B) | See Annex hyperlink to Q4Y4 ESP Report
USP 2: Environmental Monitoring Group Trust-"Two communities adapting together" | Yes | SANBI USP /SGR proposal review process – see SANBI review | Yes | Yes | Yes for Principle 2,3 and 5, in the beneficiary identification process. | See Contract Conditions (Annex B) | See Annex hyperlink to Q4Y4 ESP Report
USP 3: Heiveld Co-operative Limited - "Climate proofing small-scale rooibos production" | Yes | SANBI USP /SGR proposal review process – see SANBI review | Yes | Yes | Yes for Principle 2,3 and 5, in the beneficiary identification process. | See Contract Conditions (Annex B) | See Annex hyperlink to Q4Y4 ESP Report
USP 4: The SaveAct Trust- "Building Resilience to Climate Change by Promoting Savings" | Yes | SANBI USP /SGR proposal review process – see SANBI review | Yes | Yes | Yes for Principle 2,3 and 5, in the beneficiary identification process. | See Contract Conditions (Annex B) | See Annex hyperlink to Q4Y4 ESP Report
USP 5: Kamiesberg Heritage Foundation-"Climate proofing herder shelter to facilitate climate change adaptation" | Yes | SANBI USP /SGR proposal review process – see SANBI review | Yes | Yes | Yes for Principle 2,3 and 5, in the beneficiary identification process. | See Contract Conditions (Annex B) | See Annex hyperlink to Q4Y4 ESP Report
USP 6: Coastal Livelihoods Foundation - "Building Resilience for Northern Cape Small-Scale fisher communities and cooperatives" | Yes | SANBI USP /SGR proposal review process – see SANBI review | Yes | Yes | Yes for Principle 2,3 and 5, in the beneficiary identification process. | See Contract Conditions (Annex B) | See Annex hyperlink to Q4Y4 ESP Report
USP 7: Concordia Lanbou Boerevereniging - "Concordia Farmers Adaptation Project" | Yes | SANBI USP /SGR proposal review process – see SANBI review | Yes | Yes | Yes for Principle 2,3 and 5, in the beneficiary identification process. | See Contract Conditions (Annex B) | See Annex hyperlink to Q1Y5 ESP Report
USP 8: Tsogang Water and Sanitation -"Ga-Ntata Rainwater Harvesting System and Rain Gauge" | Yes | SANBI USP /SGR proposal review process – see SANBI review | Yes | Yes | Yes for Principle 2,3 and 5, in the beneficiary identification process. | See Contract Conditions (Annex B) | See Annex hyperlink to Q4Y4 ESP Report
USP 9: Holani Home Based Care - "Drought Resilient Agriculture Project" | Yes | SANBI USP /SGR proposal review process – see SANBI review | Yes | Yes | Yes for Principle 2,3 and 5, in the beneficiary identification process. | See Contract Conditions (Annex B) | See Annex hyperlink to Q1Y5 ESP Report
USP 10: Exilite 499 cc - "Vuhehli Climate Smart Agricultural Vegetable-Nursery Project" | Yes | SANBI USP /SGR proposal review process – see SANBI review | Yes | Yes | Yes for Principle 2,3 and 5, in the beneficiary identification process. | See Contract Conditions (Annex B) | See Annex hyperlink to Q4Y4 ESP Report
USP 11: Ramotshinyadi HIV/AIDS Youth Guide - "Enhancing Food Security through Climate-Smart Agriculture" | Yes | SANBI USP /SGR proposal review process – see SANBI review | Yes | Yes | Yes for Principle 2,3 and 5, in the beneficiary identification process. | See Contract Conditions (Annex B) | See Annex hyperlink to Q1Y5 ESP Report
USP 12: Khanimamba Training and Resource Centre - "Small Scale Vegetable Gardening Under Controlled Environment for Communal and Family Household Backyards" | Yes | SANBI USP /SGR proposal review process – see SANBI review | Yes | Yes | Yes for Principle 2,3 and 5, in the beneficiary identification process. | See Contract Conditions (Annex B) | See Annex hyperlink to Q1Y5 ESP Report
USP 13: World Vision South Africa - "Hlula Ndlala Project" | Yes | SANBI USP /SGR proposal review process – see SANBI review | Yes | Yes | Yes for Principle 2,3 and 5, in the beneficiary identification process. | See Contract Conditions (Annex B) | See Annex hyperlink to Q4Y4 ESP Report
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts? Yes. A mechanism was developed and endorsed by the relevant governance structures and a dedicated link was created on the homepage of SANBI’s website.
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | No
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Minimum quota | Objective | Number of vulnerable community members in project target areas with reduced risk to extreme weather events (Disaggregated by gender) | 0 | 50% women | Good
Minimum quota | Output | Number of Small Grant Recipients with women within the management structures | 0 | At least 10 out of 12 small grant recipients | Good
Minimum quota | Project selection criteria | Criteria for project selection: Projects must support vulnerable communities especially women | 0 | 100% | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | Gender responsive elements were incorporated in project reporting requirements from inception. This included the application of ESP principle 5 at all stages of the project cycle, annual reporting on project level gender responsive elements, and quarterly reporting for USPs/ SGRs. Gender disaggregation was also requested in tracking of stakeholder participation, beneficiary selection and capacity building processes. Reference to gender responsive grievance mechanism was added to the NIE's website landing page.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | The Adaptation Fund Gender Policy was supported through various design and implementation efforts. All Small Grant Recipient applicants were required to indicate in their proposal document how they would actively include women, prioritising them as direct beneficiaries in the project. A requirement to be considered for successful selection as a grantee of the SGF was that the organisations included women in their management structures. The Small Grants Facility grant application required the disclosure of the number of staff in the management structure of the organisation as well as the number of staff in the management structure of their proposed Small Grants Facility project. Outcome 2 records the number of Small Grant Recipients with women in their management structures as twelve in accordance with their self-report during the application process. It is worth noting that all 12 had women included in their organisational as well as project management structures. As SGR projects were implemented, each was required to submit a beneficiary selection plan with a detailed explanation on how they would ensure women were included in the project. As outlined in the ESP tab, the EE tracked the SGRs approach to managing the ESPs and any potential risks that might rise. This included tracking the SGRs’ approach to adhering to ESP 2: Access and Equity; ESP 3 Marginalised and Vulnerable Groups, ESP 4: Human Rights, and ESP 5: Gender equality and women’s empowerment. This quarterly tracking served as an important reminder to keep women and other marginalised groups as a focus of the project. Furthermore, the EE ensured SGRs monitored and reported the involvement of women in their project on a quarterly basis, and submit beneficiary numbers disaggregated, by age and gender, with their reports. With the project closeout report SGRs were asked to reflect on process of gender inclusion in their project and the outcomes of this process. A Grievance Policy was developed and SGRs informed of procedures to express grievances, including those related to gender.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | Yes.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | The Adaptation Fund's Gender Policy, as applied within the framework established for the SGF, encountered strong compliance. Capacity gaps amongst the SGRs were addressed through support provided by the FA and EE, primarily as part of technical assistance provided on effective Monitoring and Evaluation.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances were received
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
Note: Please note that the Project Manager/ EE has reported on, and rated, cumulative progress as this is the last PPR to which they will contribute. It was not possible to SANBI to disaggregate the reporting.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Component 1 1. Small Grant Recipients are contracted and receive disbursements. 2. Tangible adaptation benefits are delivered. |  | Component 1 1. Contracts are signed for 12 Small Grant Recipients (six in each target area) and disbursements paid. 2. Tangible adaptation benefits are delivered. |  | 1. 13 Small Grant Recipients (SGR) were approved, contracted and ultimately supported to implement community adaptation projects. Eleven Small Grant Recipients included civil society within management structures. The twelfth project was led by a private organisation, but in partnership with a civil society organisation. The majority of these Small Grant Recipients were new to climate change adaptation, and all fall within the three Small Grant Facility Investment Windows. Some of the Small Grant Recipients implemented projects that included more than one Investment Window. At the end of Year 5, 13 Small Grant Recipients had been fully contracted, and all except one, which was terminated before implementation, had been completed. One Small Grant Recipient required an extension to complete their project, therefore the project was completed in Year 5. One of the Small Grant Recipient was unable to complete its activities because the contract ended under suspension, therefore some of the project activities were completed through a close out process that saw the EE supporting activities directly on behalf of the beneficiary community without the assistance of the originally contracted SGR. 2. The delivery of tangible adaptation benefits has been increasingly visible as the projects have proceeded, as evidenced in the indicator tab. However, as implementation took place and the SGRs understanding of context and technical processes evolved it became evident that it was necessary for 5 SGRs alter their initial project targets to be more realistic. Motivations for reductions in certain targets were submitted to, and reviewed and approved by the relevant decision-making bodies. At the end of Year 5, all 12 implemented SGR projects had been closed out. The SGF beneficiary targets exceeded the original project target of 600 direct beneficiaries. | Satisfactory (S)
| Component 2 1. Facilitating Agencies for each target District are contracted to support local communities. 2. Facilitating Agencies identify and support Applicants with proposal development. 3. Facilitating Agencies build the capacity of Small Grant Recipients. |  | Component 2 1. Facilitating Agencies for each target District are contracted to support local communities. 2. Facilitating Agencies identify and support Applicants with proposal development and project implementation. 3. Facilitating Agencies build the capacity of Small Grant Recipients. |  | 1. Through much of Year 5 of the SGF project, the Facilitating Agencies (FAs) continued to provide support to the Small Grant Recipients (SGR) at a level of effort that exceeded the anticipated need. The Facilitating Agencies facilitated the procurement of technical and financial close-out documentation as well as support in a range of technical areas such as agro-ecology and sustainable grazing plans. As the SGF project closed-out, considerable effort was made to instil the knowledge and sense of ownership required to promote the climate adaptation activities to continue as a part of daily practice. In addition, the Mopani District FA contributed significant effort working directly with Homu14 B community during the development and implementation of the Exit Plan, which sought to implement an Exit Plan to address community needs following the expiration of the Khanimamba SGR project contract. 2. Year 5 marked the close-out for the final of the 13 SGRs. By the end of Year 5, the FAs had conducted a combined total of 349 site visits to support local institutions to implement climate adaptation responses. The volume of work within the Small Grants Facility for the Executing Entity and Facilitating Agencies continued into Year 5 due to reporting delays and challenges ascertaining requisite financial and technical close out documents. Additional support was delivered concurrently to improve reporting and monitoring systems as well. 3. Capacity building was a significant and continual focus of the FAs and EE. The experience of the SGF demonstrated that the SGRs required intensive, direct and customised support throughout the project. There were 44 individual capacity building sessions consisting of discrete area or subject matter training / capacity building efforts delivered to SGRs during the project lifespan. This total did not include the preparation time to assess needs, which were conducted through formal needs assessments as well as organically as needs were identified and training programmes and content developed. Capacity building sessions included technical skills training in various adaptation technologies, financial management, reporting, and project management and monitoring as well as less tangible aspects of capacity, including topics such as conflict negotiation. | Satisfactory (S)
| Component 3 1. Small Grant Recipients are trained. 2. Learning platforms are made available to Small Grant Recipients. 3. Case studies and policy recommendations are produced. 4. Project outcomes are presented at fora. |  | Component 3 1. Small Grant Recipients are trained to develop their proposals and have increased capacity to implement climate change adaptation projects. 2. Opportunities for Small Grant Recipients to exchange knowledge and learning are created. 3. Case studies and policy recommendations 4. Project outcomes are presented at district / national / international fora. |  | 1. Small Grant Recipients received capacity building support from the Facilitating Agencies and the Executing Entity from detailed proposal development stage and throughout the project until Close-out. All training conducted after the Small Grant Recipients started implementation was based on training needs assessments conducted by the Facilitating Agencies. There have been 44 training sessions delivered, aspects covered included climate smart agriculture (agro-ecology and conservation agriculture), climate change adaptation, water management, soil conservation, financial management, social dynamics, monitoring and evaluation, and reporting. 2. Learning workshops and exchange visits were convened to facilitate an exchange of experiences and stories amongst Small Grant Recipients, as well as the wider stakeholder community, which included local and national government officials and the local community. In total, five learning workshops were facilitated, including an inter-district learning workshop in Johannesburg and inter-district learning exchanges in each region. The Small Grant Recipients also had an opportunity to share their experiences with the international climate change community through their participation in 2018 Adaptation Futures conference, both as attendees of the conference and as panellists in a session. There are two WhatsApp groups (social media) that have been established to support exchanges between the Small Grant Recipients, at district level. The WhatsApp group was developed as a means through which Small Grant Recipients could connect to discuss challenges and share learnings. In addition to learnings, this platform has been used to disseminate information about potential funding opportunities. Independent learning processes (workshops) focusing on the overall management of the Small Grants Facility were convened in Year 3. This was done to help the National Implementing Entity, Executing Entity and Facilitating Agency reflect on progress being made by the Small Grants Facility, and draw on lessons learned to plan for the next year and work towards a successful project close out. 3. The co-development of case studies continued into Year 5, providing an accessible means through which learnings can be shared. The case studies will also be used to inform the development of policy recommendations and the methodology for enhanced direct access of climate finance that is being developed by the National Implementing Entity. 4. Throughout the SGF project, outcomes were presented at a number of forums convened by local and national government, and local networks, as well as international conference such as the Adaptation Futures and the UNFCCC Conference of Parties sessions. However, none occurred during the Year 5 reporting period. | Satisfactory (S)
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) responsible for completeling the Rating section
| Name: | Carl Wesselink
| Email: | carl@southsouthnorth.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Progress to date is rated as 'Satisfactory' from the Executing Entity's perspective. While there have been challenges, the Small Grants Facility achieved most of its major outcomes and outputs, including: - The target for contracting 12 Small Grant Recipients has been achieved. We have noted earlier that although 13 were in fact contracted, one was terminated prior to implementation. One of the projects was unable to complete implementation due to performance and compliance issues, and the affected beneficiary community was directly supported by the EE to implement some of the identified activities. In summary, twelve of the thirteen Small Grant Recipients have successfully completed and closed out their projects. - The direct beneficiary targets that were set in the original proposal to the Adaptation Fund for the number of vulnerable community members with reduced risk to extreme weather have been significantly exceeded, with the number of women beneficiaries nearly quadruple the target and the number of men triple. - Significant tangible climate adaptation assets have been established through the implementation of the project. There were also 3 additional climate adaptation assets, that were not originally planned, implemented in year 4. These assets were accumulated within a project where 9 SGRs had no prior climate adaptation experience. The communities and local organisations received significantly more capacity building and support than planned, nearly quadruple the target. The site visits are also significantly exceeded. Furthermore, attempts to ensure broad reach of capacity in climate adaptation was exceeded, including the number of women in SGR management and the number of SGRs led by civil society. - Despite delays in the selection, approval and contracting of Small Grant Recipients, as well as challenges associated with Environmental and Social Policy compliance and capacity gaps, and shortened SGR project implementation timeframes, significant adaptation assets as well as climate adaptation achievements were recorded. - Expenditure totalled more than 95% of the budgeted amount by the end of Year 5. - Extensive and significant learning has occurred for all SGF partners through the implementation of this pilot project. Capacity has been enhanced at all levels and adaptive management practices employed, where necessary, to improve the implementation of the SGF, for example having alternative contracting arrangements for SGRs depending on capacity, using a different proposal development approach for the newer SGRs, increasing the level of capacity building and support provided to Small Grant Recipients, and Environmental and Social Policy assessments and adherence has become a collaborative process with guidance and support for the Small Grant Recipients being provided by the Facilitating Agencies and the Executing Entity.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Governance Mechanism: - mechanism established - mechanism operational (quarterly milestone) |  | At the end of Year 5, it was expected that the governance mechanisms of the SGF would continue to be fully functional. |  | During Year 5, the governance mechanisms of the Small Grants Facility continued to be fully functional. During the period under review, the Project Advisory Group met five times, including for two close out sessions and to discuss the findings of the Terminal Evaluation. SANBI's Climate Funds Oversight Committee (CFOC) met three times to reflect on project progress and risk management. The lateness of reporting by the Executing Entity, issues unreported and potentially irregular expenditure and issues of cash flow dominated the discussions. The National Adaptation Funds Advisory Body (NAFAB) also convened 3 times during Year 5 of the project. Over the period under review, it noted overall project progress, considered and approved a request for an additional activity for one of the SGRs (Homu 14B), discussed emerging safeguard issues and noted and discussed the impact that COVID-19 19 was having on the project. It supported the Project Advisory Group’s recommendation that SANBI approach the AF for a project extension to December 2021 and to utilise the funds that were unallocated in Component 1 at the end of Year 5 (USD 128 000) for sustaining the gains through additional investments in the small grant recipients. The NAFAB noted that the project has provided lessons on how to do work that is transformative while providing an understanding of what is required at a community level, and the level of effort that is required to deliver this in a way that is cognisant of the capacity constraints on the ground and across the system. It noted SANBI’s intention to reflect on the emerging lessons and scale up this work. The approved project extension to December 2021 will allow more time for the processes of capturing, documenting and sharing project lessons, and also for augmenting the investments in the small grant recipients. | Satisfactory (S)
| Achievement of targets |  | At the end of Year 5, it was expected that all contracted site based activities would be completed and the project would be drawing to a close |  | At the end of Year 5, all contracted site-based activities were concluded, and the project was drawing to a close. The South African regulations associated with COVID-19 – which included a hard lockdown with travel ban for many months – had a significant impacts on close out activities, but did not materially affect the efforts of the small grant recipient who had largely completed their projects before the onset of the pandemic. The Covid-19 restrictions resulted in the cancellation of the NIE’s annual ESP and close out site visits, and the cancellation of site visits that were due to take place as part of the Terminal Evaluation. They also had a significant impact on the completion of the Year 4 project audit. Notwithstanding these challenges, the project achieved – and exceeded – most of its Component 1 and Component 2 targets. In particular, the original SGF objective target of 600 direct beneficiaries was well exceeded and the range of adaptation measures is extensive. Several Output 3 activities were delayed and will now be completed in Year 6. These include the final design and publication of the case studies, the methodology and the policy brief. SANBI concurs with the ratings of the EE for Components 1 and 2. SANBI notes that the overall project target for beneficiaries, that was set at 600, was exceeded. The targets that are reflected for Outcome 1 are derived from the Small Grant Recipient projects and in some cases were not fully achieved. SANBI is of the view that the overall rating for Component 3 is MS because while the number of events is impressive, the programme itself did not result in the iterative learning and reflection that was envisaged in the project design. A number of early project design assumptions did not hold and resulted in several knock-on effects for implementation. These will need careful analysis so as to inform future iterations of this modality of downscaled climate finance. Four of these are discussed below. Assumption 1: All twelve small grant recipient projects would be contracted in the first year of the project, which would allow for three years of implementation and an integrated learning programme that would involve all grantees. This did not happen, and many of the grantees were only contracted in Year 3. Assumption 2: The learning programme would be designed at project outset, and would support learning and reflection over the duration of the project. The learning programme was not executed as designed, and SANBI concurs with the recommendations of both the MTE and TE that an integrated, strategic and iterative programme is needed for the grantees and beneficiaries themselves to benefit from the process and for peer to peer learning to happen. The lack of a consolidated learning programme and associated products during implementation further hampered the integration of adaptation lessons into national, provincial and local government adaptation processes-especially for engagement with stakeholders outside of the SGF and advisory committees. Assumption 3: Small grant recipients would have the capacity to manage and report on received funds. The challenges that small grant recipients experienced in their management and reporting on received funds persisted throughout the SGF, often resulting in implementation delays, late reporting and shortages of funding. Substantial effort was directed towards addressing this over the course of the project, including focused capacity building and training events, the simplification of reporting, the placement of personnel with the required skills into projects and three-way contracting modalities. In a future iteration, it will be important to provide grants of different sizes that match institutional competence and experience, and to ensure that the due diligence processes that are conducted prior to contracting are improved so as to pick up institutional issues that need attention. A future iteration will also need to pay careful attention to the way in which reporting and compliance processes are designed and supported. Whilst substantial resources were allocated to these functions in the Component 2 budget, the aspiration to create an enabling responsive mechanism does not appear to have been achieved. Assumption 4: The Executing entity and subcontracted parties would have the skills needed to manage the SGF. SANBI was surprised at the extent to which the recommendations for future capacity building focused on the EE and other enabling parties. It was certainly an assumption that the skills needed to mobilise and execute the project were in place, and while the ‘learning as doing’ throughout the project is appreciated, it is a concern that this was at the expense of the small grant recipients. A future iteration will need to clearly identify the skills and systems that need to be in place, and to ensure that these are in place prior to the engagement of the small grant recipients. Particular attention should be given to ensuring that resources are available to provide guidance on regulatory frameworks and associated compliance implications at the outset. | Satisfactory (S)
| Environmental and Social Safeguard and Gender Screening and tracking: - tools and procedures for screening developed - screening process operational (quarterly milestone) |  | At the end of Year 5, it was expected that tools for screening and assessing SGR activities against environmental and social safeguards and gender mainstreaming would be applied to project close out reports, and would confirm that any unintended negative impacts are avoided, or mitigated if necessary |  | During Year 5, and as part of project close out, all SGRs activities continued to be screened for compliance with the safeguards of the Adaptation Fund and completed environmental and social screening dashboards as part of the project close out processes. Specific activities that related to Environmental and Social Safeguard and Gender Screening and tracking were as follows: The site remediation at Homu14B project site, a project site for Khanimamba Resource and Training project were undertaken to address ESP issues along with the scaled-down SGR close-out activities in Homu 14B. CLB conducted the farmer training on monitoring, detecting and managing potential soil erosion around the animal shelters. Through the quarterly reporting process, The issues noted in Y4 reporting and ESP assessments regarding the siting of was noted that two ablution facilities that may not have addressed ESP related contracting conditions risk management measures were addressed in consultation with the community and mitigation actions were agreed and implemented in Y5. The annual NIE ESP site visits were unfortunately cancelled due to restrictions associate with the Covid-19 lockdown. | Satisfactory (S)
| Technical and Financial Risk Management: - reporting and forecasting template developed - funds disbursed based on approved reports (quarterly milestone) |  | At the end of Year 5, it was expected that the revised technical and financial reporting and forecasting templates would be in use, and that the EE would be reporting to the NIE quarterly. |  | The AF will be aware that that Year 4 PPR only submitted to the AF in August 2020, 11 months into Year 5! This was due to range of reporting challenges that the EE experienced in compiling the consolidated report and resulted in several knock-on impacts including on cash flow and the timing of the Year 4 audit and terminal evaluation. This was further compounded by the impacts of the COVID-19 pandemic and associated regulations and restrictions, some of which are still ongoing at the time of compiling this report. Several mitigation measures were put in place and/ or were agreed to address the impacts including: • A no cost extension for the EE, moving EE project closure from March 2020, to June 2020, September 2020 and finally to December 2020. From project outset, the EE had committed to co-finance the project and had commented that their function was under-resourced, and this will need to be examined closely as a critical element of the design of a project scale up. The EE budget was already exhausted at the end of June 2020, and so this no cost extension placed significant pressure on EE capacity. • An extension of the deadline for the submission of the Year 4 audit to December 2020. • The revision of the timelines of the TE, which was designed to evaluate the project at the end of Year 4, based on an assumption that the project would be closing out at that time. The TE could not commence until Year 4 reporting was in place, and the methodology could no longer include site visits to the SGRs due to COVID-19 restrictions on travel. Unanticipated delays in concluding the project also meant that the Year 4 reporting was not aligned with project closure, and that the information that was available to the TE consultants was not inclusive of all elements of project delivery. The TE consultants have noted in their report that they were required to spend more time than planned on the evaluation and were unable to comprehensively address all issues. It is not clear how this situation could have been avoided, but an emerging lesson is that TE processes should not be allowed to commence prior to the closure of the operational elements of projects. • A request for an overall project extension to December 2021 to allow the NIE and facilitating agencies to consolidate the lessons learned through the project and to develop a set of communication products, that will be useful to the global EDA community. The NIE is currently undertaking a comprehensive analysis of the operational system of the SGF, towards understanding how challenges may be addressed in a project scale up. This document will form the basis of the development of the methodology and policy brief, and the design of an enhanced approach to EDA that will inform project development processes. | Satisfactory (S)
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) responsible for completeling the Rating section
| Name: | Dr. Mandy Barnett
| Email: | m.barnett@sanbi.org.za
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | SANBI’s overall rating of the project is S in that it is on track to achieve most, if not all, of its deliverables. Project implementation efforts increased substantially over years 4 and 5, and the small grant receipts achieved an impressive set of results. The period under review faced two main risks – reporting delays and the COVID-19 pandemic. These are discussed above. SANBI’s response to the project Terminal Evaluation is attached.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: Increase climate resilience in production landscapes and socio-economic systems in vulnerable communities in two pilot District Municipalities in South Africa, by working directly with local stakeholders and anticipated beneficiaries through a small granting mechanism | 1. Number of vulnerable community members in project target areas with reduced risk to extreme weather events | 1. 0 women and 0 men | 1. 1083 women and 838 men | 1. 300 women and 300 men
| 2. Number of Small Grant Recipients with increased capacity to implement climate change adaptation projects | 2. 0 small grant recipients | 2. 12 small grant recipients | 2. At least 12 small grant recipients
| 3. Number of policy briefs presented to South African National Treasury and domestic Green Fund reflecting on experiences of the Community Adaptation SGF and informing appropriate actions with a view to creating a climate adaptation finance mechanism that supports local level responses | 3. 0 policy briefs | 3. 0 policy briefs | 3. 1 policy brief
Outcome 1: Small grants support concrete adaptation measures that strengthen livelihood strategies, adaptive capacity and ecosystem resilience in vulnerable communities in two district municipalities in South Africa | Number of vulnerable community members with reduced risk to climate-driven impacts as a result of project interventions | 0 women and 0 men | 1. 1083 women and 838 men | 1334 women and 1126 men
Output 1.1: Adaptation assets strengthened through the implementation of at least 12 small grants (approximately USD 100,000 each) disbursed to at least 12 local institutions in the Mopani and Namakwa District Municipalities | 1. Number of agricultural adaptation assets: • number of livestock shelters • number of poultry houses • number of climate resilient livestock • area (ha) under climate smart grazing • number of livestock farmers with improved access to grazing areas with additional water harvested • number of livestock farmers with improved ability to develop forage / sowing plots with additional water harvested • area (ha) under climate smart farming practises • number of climate resilient food gardens • Number of communal climate resilient food gardens • Number of backyard climate resilient food gardens • number of tanks used for rainwater harvesting for small-scale farming • number of tanks for water storage for small-scale farming • number of reservoirs for water storage • number of nurseries • area (ha) under improved soil management • area (ha) under improved agroforestry • area (ha) of improved drought resistant crops • area (ha) of improved water management • number of biogas digesters | • 0 livestock shelters • 0 poultry houses • 0 climate resilient livestock • 0 ha under climate resilient grazing plans developed • 0 farmers with access to commonage • 0 farmers with shelters containin RWH systems • 0 ha under climate smart farming practises • 0 climate resilient food gardens • 0 ha communal climate resilient food gardens • 0 ha communal climate resilient food gardens • 0 backyard climate resilient backyard food gardens • 0 tanks used for rainwater harvesting for small-scale farming • 0 tanks for water storage for small-scale farming • 0 reservoirs for water storage • 0 nurseries • 0 ha under improved soil management • 0 ha under improved agroforestry • 0 ha of improved drought resistant crops • 0 ha under improved water management • 0 biogas digesters | • 12 livestock shelters • 2 poultry houses • 89 climate resilient livestock • 3 climate resilient grazing plans developed • 23,30 ha under climate smart farming practises • 3 communal climate resilient food garden • 3,97 ha communal climate resilient food gardens • 136 backyard climate resilient food gardens • 37 tanks used for rainwater harvesting for small-scale farming • 26 tanks for water storage for small-scale farming • 2 reservoirs for water storage • 4 nurseries • 3,97 ha under improved soil management • 3,72 ha under improved agroforestry • 3,97 ha of improved drought resistant crops • 3,97 ha under improved water management • 1 biogas digester • 1 solar drier | • 12 livestock shelters • 2 poultry houses • 65 climate resilient livestock • 3 climate resilient grazing plans developed • 100 ha under climate smart farming practises • 7 ha communal climate resilient food gardens • 6 communal climate resilient food garden • 110 backyard climate resilient food gardens • 36 tanks used for rainwater harvesting for small-scale farming • 36 tanks for water storage for small-scale farming • 2 reservoirs for water storage • 4 nurseries • 9,95 ha under improved soil management • 5,8 ha under improved agroforestry • 6,05 ha of improved drought resistant crops • 8,95 ha under improved water management • 1 biogas digester • 1 solar drier
| 2. Number of livelihood adaptation assets: • number of savings groups • number of water committees • number of storage and processing sheds • number of enhanced early warning systems • number of disaster risk response mechanisms • number of disaster risk response mechanisms for fishers • number of capacitated climate resilient small-scale fisher cooperatives • number of shelters for vegetable production • number of communal market facilities • number of cooling facilities for food traders | • 0 savings groups • 0 water committees • 0 storage and processing sheds • 0 enhanced early warning systems • 0 disaster risk response mechanisms • 0 disaster risk response mechanisms • 0 capacitated climate resilient small-scale fisher cooperatives • 0 shelters for vegetable production • 0 communal market facilities • 0 cooling facilities for food traders | • 20 savings groups • 1 water committees • 3 storage and processing sheds • 1 enhanced early warning systems for fishers • 1 disaster risk response mechanisms for fishers • 2 capacitated climate resilient small-scale fisher cooperatives • 3 shelters for vegetable production • 0 communal market facilities • 2 cooling facilities for food traders | • 30 savings groups • 1 water committees • 3 storage and processing sheds • 1 enhanced early warning systems for fishers • 1 disaster risk response mechanisms for fishers • 2 capacitated climate resilient small-scale fisher cooperatives • 4 shelters for vegetable production • 0 communal market facilities • 2 cooling facilities for food traders
| 3. Number of settlement adaptation assets: • number of houses with improved insulation • number of tanks used for domestic rainwater harvesting • number of installed compost toilets • number of mobile herder shelters • number of dams refurbished • area (ha) with improved coastal storm protection • number of improved river crossings • area (ha) of rehabilitated wetlands and riparian systems | • 0 houses with improved insulation • 0 tanks used for domestic rainwater harvesting • 0 installed compost toilets • 0 mobile herder shelters • 0 dams refurbished • 0 ha with improved coastal storm protection • 0 improved river crossings • 0 ha of rehabilitated wetlands and riparian systems | • 15 houses with improved insulation • 154 tanks used for domestic rainwater harvesting • 3 installed compost toilets • 13 mobile herder shelters • 2 earth dams refurbished • 5 donga/gullies rehabilitated • 0 improved river crossings • 0 ha of rehabilitated wetlands and riparian systems. | • 14 houses with improved insulation • 140 tanks used for domestic rainwater harvesting • 4 installed compost toilets • 12 mobile herder shelters • 2 earth dams refurbished • 5 donga/gullies rehabilitated • 0 improved river crossings • 0 ha of rehabilitated wetlands and riparian systems
Outcome 2: Small Grant Recipients and associated institutions are empowered to identify response measures to climate-induced vulnerabilities, and implement relevant climate change adaptation projects | Number of Small Grant Recipients with increased capacity to implement adaptation projects that address risks to extreme weather events | 0 small grant recipients. | 12 small grant recipients. | At least 12 small grant recipients.
Output 2.1: At least 12 local institutions in the Mopani and Namakwa Districts are supported to develop small grant projects for local-level adaptation | 1. Number of Small Grant Recipients with women within the management structures | 1. 0 small grant recipients | 1. 12 small grant recipients | 1. At least 10 small grant recipients | ma
| 2. Number of small grant recipients new to climate change adaptation | 2. 0 small grant recipients | 2. 9 small grant recipients | 2. At least 8 small grant recipients
| 3. Number of small grant recipients lead by civil society | 3. 0 small grant recipients | 3. 11 small grant recipients | 3. At least 8 small grant recipients
| 4. Number of small grant recipients with civil society within the management structures | 4. 0 small grant recipients | 4. 12 small grant recipients | 4. At least 12 small grant recipients
Output 2.2: At least 12 local institutions in the Mopani and Namakwa Districts are supported to implement integrated climate adaptation responses | Number of project site visits by Facilitating Agents | 0 site visits | 349 site visits | 192 site visits
Outcome 3: A methodology for enhancing direct access to climate finance is developed, based on lessons learned, providing recommendations for scaling up and replicating in South Africa and beyond | Number of methodologies for enhanced direct access to climate finance | 0 methodologies | 0 methodologies | 1 methodology
Output 3.1: Training opportunities are provided for Small Grant Recipients Number of training sessions to build local community capacity in inter alia climate change adaptation and financial management skills | Number of training sessions to build local community capacity in inter alia climate change adaptation and financial management skills | 0 training sessions | 44 training sessions | 10 training sessions
Output 3.2: Local networks for reducing climate change vulnerability and risk reduction are developed, expanded and strengthened Number of fora for grant recipients to share experiences at inter- and intra-Municipal levels | Number of fora for grant recipients to share experiences at inter- and intra-Municipal levels | 0 fora | 7 fora | At least 4 fora
Output 3.3: Case studies and policy recommendations are developed for reflecting on, replicating and scaling up small grant financing approaches | 1. Number of fora where project outcomes and relevant policy recommendations are presented | 1. 0 fora | 1. 9 fora (5 local, 1 national and 3 international fora) [derived from reports submitted on a quarterly basis] | 1. At least 6 fora (4 local, 1 national and 1 international fora)
| 2. Number of case studies capturing beneficiary and grantee experiences | 2. 0 case studies | 2. 9 case studies | 2.At least 8 case studies

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Note from the NIE: The EE has responded to the sections below in a cumulative way, as this is the last PPR to which they will contribute. As a result, some of what is reflected and recommeded relates to the project as a whole, and not just to Year 5. It has not been possible for SANBI to disaggregate the reporting.
What implementation issues/lessons, either positive or negative, affected progress? | Results in this section have been collected over time from a variety of sources. Although not exhaustive, it seeks to capture key learnings from perspectives of all stakeholders. Some of the experiences that are reflected here happened earlier than Y5, and are included so as to present a comprehensive picture. Transformational change is hard. Transformation has proven to be challenging, especially for the SGRs, which resulted in slower progress than anticipated. Asking an organization or group to change their systems, transform, adapt, and learn new things, can be intimidating and unsettling and has resulted in resistance and reluctance, even when the change is good. In the context of the SGF, behavioural change is being wrought from all organisations receiving funds, in terms of how to implement an adaptation project and undertake project management, meet increased documentation requirements and standards, comply with Environmental and Social Policy (ESP) requirements, fulfil procurement and travel policies, set up bookkeeping systems etc. These aspects appear to be a good practice, but it’s worth considering the impact on the recipient's operations and social systems and practices as a whole, including the healthiness and sustainability of the project, especially after the end of the SGF project. Compliance requirements should be well articulated, proportionately applied and avoid being overly complex. Rigorous compliance and risk management requirements impacted how the SGR projects were implemented. Compliance activities affected nearly all aspects of the SGF, from the application stage for the grant recipients and throughout each project's implementation. Often requirements were unanticipated and unfamiliar to the SGRs. In order to minimise compliance requirements' negative impact on implementation, while maximising opportunity to minimise and manage project-related risks, several lessons are noted: 1. Up-front investment, alongside transparent due diligence allocated to oversight bodies, committed to identifying minimum capacity required to adhere to compliance requirements anticipated during implementation, and allocating adequate support and resourcing, is required. 2. Capacity should be defined and take into consideration the compliance requirements established by the donor and administering agencies. 3. Proportionality should be applied to all compliance activities, including ESP assessments. Application should focus on the principles most relevant to risk identification and management in a particular project and take the context into consideration. 4. Clear explanation of the reasons for, and the implementation practices related to, the ESPs, including minimum standards for local implementers, is necessary. 5. Essential donor and project compliance requirements should be clearly defined and understood, and appropriate adherence mechanisms agreed upon by all the project implementation partners, prior to the roll out of the SGF. If new activities emerge, compliance requirements should be discussed and fully understood by the SGR during the planning process. 6. Adequate mechanisms (and resources) should be put in place to provide the Small Grant Recipients the means for meeting compliance requirements without compromising their implementation. Continual capacity building for all stakeholders requires resources, including time and money. Understanding and defining capacity within the context of unique and complex interventions in CB-CCA presented a challenge. The original project conceptualisation envisaged that communities would require improved organisational management and that SGR project implementation would require increased understanding of climate change adaptation responses. However, simultaneously most SGRs required additional capacity to meet eligible criteria to receive a grant. Additionally, it was learnt over time that the extent of capacity building necessary was underestimated and, as a result, under-resourced. Finally, given this was a pilot project utilising an untested approach the necessary capacity strengthening of the Project Management Team (NIE, EE and FAs) was not sufficiently considered. Therefore, to ensure appropriate capability is achievable for all stakeholders, the following learnings should be considered: 1. The various levels and types of capacity required for Community-Based Climate Change Adaptation (CB-CCA) should be well understood, including general organisational capacity, administrative and financial capacity, project management alongside specific technical skills and knowledge in relevant adaptation technologies. A flexible approach is necessary, and provision should be made for unanticipated capacity needs. 2. A refined and responsive grant applicant screening mechanism and needs assessment is required to understand the specific strengths, weaknesses and needs of regional and individual grant recipients at the start of their engagement. Based on the outcomes of this screening a two stage capacity building plan should be developed for each applicant. 3. Grant applicants would greatly benefit from a phased and customised approach to capacity building. The first phase would identify grant applicants with adequate concepts notes, who would then receive support to develop their concept alongside requisite organisational skills through a fully resourced and customised capacity development plan. It is unrealistic to expect community based grantees to self-finance their core costs during the proposal fine-tuning and capacity building process. Grant applicants would then be eligible for a second phase of granting that would fund project implementation and the requisite capacity building identified for each grantee. 4. Capacity building should be considered an on-going, evolving and responsive process that continues over the lifetime of the project and must be framed within the requirements established by the donor and administering agencies. The extensive level of support and capacity building required for this project extended to regular, intensive and direct (in-person) training and mentorship in a multitude of areas and required adequate and agile access to expertise and resources. 5. Clear understanding and definition of the multiple capacities is required within the context of donor (and governance) expectations and desired achievements in order to fully assess capacity gaps and address them. A clear assessment of capacity gaps within the Project Management Structure Team and, once identified, the community adaptation project implementers is required. 6. Capacity building efforts should be deployed strategically throughout the project lifecycle for optimal efficiency and effectiveness. Furthermore, as systems are created in response to contexts and needs capacity will need to be built across the whole system, including overall project management. Partnerships at multiple levels and dynamic systems that work alongside communities' existing practices are required. Partnerships that extend beyond transactional relations and build upon shared goals is required. Collaboration and co-created processes are required to manage the diversity and complexity of challenges encountered while ensuring the relevancy - and sustainability- of community-based climate adaptation interventions. This is particularly important within rural communities in which most transactions are based upon relationships of trust. Similarly, systems that support efforts should be dynamic and work alongside communities' existing practices. Networks are an invaluable resource for project implementation and sustainability. Networks opened up opportunities for learning exchanges and allowed the Facilitating Agencies to familiarise themselves with the roles and responsibilities of different stakeholders and the assistance they can offer. Facilitating access to networks within government, relevant sectors and/or climate change adaptation could strengthen sustainability of projects and build greater resilience within communities. This is not only in terms of technical support and guidance that can be offered, but also in terms of accessing potential additional funding for projects to allow them to continue and enhance their impact within the target communities. It is worth noting that relationship building requires sufficient time alongside frequent engagements. Leveraging expertise, impacts and learning to promote increased influence locally, sub-nationally, nationally (or beyond) – should be a strategic goal of the overall Project Management Team, which would be strengthened by being driven at national or regional levels. Strategic oversight should therefore focus on identifying and articulating important linkages and connections which expand impact to strengthen national resilience by connecting local activities with local and national policy, priorities and action. Spearheaded by oversight governance structures, the effort here should be to draw the connections between local projects, national adaptation measures and the policy environs for broad impact. Lengthen the Project Time Frame The learning nature of the SGF, the establishment of new, evolving systems, and the capacity growth required at all levels warranted a longer project time frame to realise the full potential of the SGF. This is particularly pertinent with regards to the Small Grant Recipients and the capacity building required to facilitate effective proposal development and implementation of the climate change adaptation projects. The necessary skills and knowledge needed, both technical and administrative, take significant time to learn and become embedded. More time than originally envisaged is needed to impart and imbed key skills and practices with the beneficiary communities. Therefore a more realistic, appropriate timeframe for the SGF would have been 7-10 years accompanied by a structured legacy plan. Legacy planning beyond project closure. Given the aspirations, and accomplishments, of the SGF a clear legacy plan would have been beneficial. A legacy plan could facilitate on-going support services to communities and expand the valuable work done during the project implementation period, enabling projects to leverage existing momentum to continue working towards their full potential.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Challenges resulting in delays, and actions taken by the PMT to mitigate these delays, as well as recommendations identified in hindsight, are detailed below. Lack of clear policies and procedures and requisite roles and responsibilities within the Project Management Team The SGF sought ambitious achievements on many levels, including developing a financial mechanism and requisite systems to deliver climate finance alongside new and potentially unfamiliar climate adaptation measures lead by organisations with little or no climate change experience. Despite Standing Operating Procefures being developed as an NIE requirement prior to project implementation, delays in implementation were created due to the Project Management Team being required to refine procedures and adjust to various requirements. The inherent uncertainty at the community level required a strong framework of policies and procedures to provide adequate leadership and guidance for the SGRs. Although, as a pilot project, many unknowns prevented a comprehensive understanding of what would be needed to enable SGRs to deliver community-based climate change adaptation projects, a greater focus could have been placed upon the development of policies, procedures and processes that dealt adequately with the complexity of the project operational and risk management requirements at the outset of the project. To manage the uncertainty generated as a result of the evolving policies and procedures during the lifetime of the SGF, the Project Management Team, the FAs in particular, were in close communication with the SGRs and provided continual support to the SGRs. Additionally, with regards to the ESPs to support the SGRs to understand and adhere to these the NIE, EE and FA provided in-field support and guidance. Meeting compliance and ESP requirements Delays were experienced by many SGRs as a result of compliance requirements. These implementation delays occurred as outlined below: - A number of the SGRs were required to obtain proof of legal permissions for certain activities such as Building plan approvals prior to starting construction, obtaining water use rights before drilling a borehole. Waiting for these permissions to be approved was time-consuming, and resulted in delays. To mitigate these delays FAs established relationships with the relevant local partners, which helped facilitate a quicker response. In some cases compliance delays resulted in withholding of disbursement until such compliance was met, which slowed the progression of project implementation. Sourcing and coordination of local service providers and experts -Limited availability of experienced service providers at local level, alongside lack of capacity of local organisations to properly assess providers, resulted in delays due to inadequate provision of services. The project management team was required to provide assistance and work to develop a solution to ensure completion of the project activities within the timeline and, on occasion, provide regular supervision of the service provider. Drawing on the experience of the SGF, it is advisable to develop a list of reliable, proficient service providers in each area to guide local procurement activities. -A key learning from implementing projects of this nature is that they require a range of experts e.g. engineers, designers, architects. Effective coordination is required to facilitate necessary inputs from all disciplines early in the process. This requires adequate identification and vetting of appropriate service providers and adequate budgetary provision. Reporting challenges and subsequent delays in disbursements Late disbursements to the SGRs was another cause of delays in project implementation. Grantees relied on prompt receipts of funds and lacked the means to continue project implementation without them. Therefore, disbursement delays resulted in a loss of project momentum. The different reasons for late disbursements are intertwined. As a result of the varying capacity gaps, many SGRs struggled to meet assigned reporting deadlines, with the knock on effect that submission of a quarterly report to the NIE was late which in turn delays the release of funds. Additionally, the disbursement of funds was contingent on all reports (FA, EE and SGRs) being approved. Therefore if one report was outstanding/in revision it held up the disbursement of funds to all partners. Disbursement delays have been an ongoing and recurring challenge since project inception and the NIE, EE and FA have continued to make efforts to address this issue including: - simplified the reporting templates and requirements; - facilitated report-writing workshops to assist and guide the SGRs; - Continued capacity building provided by the FA and EE with SGRs on an individual level; and, - Provision of additional funds to procure external financial service providers to assist SGRs with financial tracking and reporting. The actions mentioned below were not actions taken in the life time of this project, but are recommended for future iterations of similar grants facility projects: 1. Taking into account the target grantees of the SGF, the size of the grants, and the intention to build capacity adopt a proportionate approach, have a less stringent quarterly reporting process, with less conditions and requirements and allow for reports to be ‘good enough’. 2. Allow for a level of trust between all parties involved within the SGF, including limiting in depth reviews and supporting documentation. 3. As this is a pilot project, with an intention of learning allow for a level of risk and failure. Acknowledge that there is risk involved in such a project and provide for some flexibility in this regard, to support creativity and adaptability. 4. Develop and apply a transparent and systematic report review process. Avoid introducing new conditions and requirements along the way, and if it is necessary, do so in through a co-creative process with grant recipients. 5. Clearly articulate roles and responsibilities in the reporting and review process; avoid duplication of efforts. 6. Reduce of the number of entities responsible for the report ‘review’ process. Allocate the duty of an in depth assessment of each report to just one project partner, with delegated decision-making authority. 7. Take a joint report revisions approach, whereby all the implementing partners meet together and collaboratively address reporting queries immediately. This tactic would facilitate speedier decision-making and a more smooth, regular flow of funding. 8. Increase direct in-person engagement between the grant management structure and the Small Grant Recipients to gain an increased understanding of the Small Grant Recipients' local contexts. 9. Reduce the frequency of reporting and full volume verification (M&E and procurement) through the formal reporting lines. Some reporting can be done in-person or in other forms that do not require an intense amount of paperwork from the SGRs. Motivations for changes to projects The motivations for change were required to be submitted to the FAs, then to the EE and then to the NIE, and in a few cases to the National Adaptation Fund Advisory Body (NAFAB) via the Project Advisory Group (PAG) for final decision. This process was time consuming, in some instances taking up to 5 months to finalise, due to: the numbers of layers in the decision making process; the substantial compliance requirements, the capacity weaknesses of some of the SGRs; changing compliance requirements and the lack of alignment of documentation between the different layers i.e. at the different levels the format for presenting of the motivation was different. The delays in decisions on motivations for change held back Small Grant Recipients project progress related to these motivations until decisions had been made and subsequent conditions met. The extended Project Management Team endeavoured to tackle the delays in decisions relating to motivations for change by: - Circulating motivations by round robin to the PAG and NAFAB for no objection and approval, respectively, instead of waiting for quarterly meetings; - The EE and FA provided extensive hands-on support to the SGRs in developing the motivations for change and meeting the necessary compliance requirements; - Developed a ‘Contract Amendment’ Standard Operating Procedure outlining roles and responsibilities, conditions and approval process relating to project changes and contract amendments.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Additional resources allocated to the Small Grant Recipients and Facilitating Agencies As the Small Grant Recipients started their project implementation, a number of project gaps and additional needs were identified. As additional funds became available, they were made available to the Small Grant Recipients to address these gaps, and enhance the impact and sustainability of the Small Grant Recipients' projects. The Facilitating Agencies were allocated additional funding to provide the extensive ongoing support that was needed for SGRs to be successful. Positioned to manage the multiple and complex challenges presented by local and international expectations, they functioned as interlocutor translating grant requirements into contextualised responses, continually responding to the emerging needs of the SGRs and providing breadth and depth of support that was unanticipated. Addition resources allocated for learning activities It was realised early in the SGF implementation process that explicit learning activities in which full SGR participation was required, demanded adequate resourcing. As a result, each SGR was provided additional resources specifically allocated for learning activities. Alternative contracting approach developed The alternative contracting approach was initiated in Year 3 with 3 SGRs allowing for the SGRs to be contracted through the FAs has proven effective. It made provision for the SGF to adapt to be more inclusive and flexible, and target those organisations on the ground with good project plans and strong adaptation ideas, despite not then meeting the eligibility requirements of the SGF, nor having the capacity to meet the compliance requirements. These SGRs required strong support and internal capacity building, to ensure compliance requirements of the SGF are met and properly adhered to. This approach has worked well with these 3 SGRs benefitting significantly from the FAs oversight and management and learning from this process. Increased number of learning events There was an initial target of two intra-district and two inter-district learning events, but by the end of year 4 there had been 4 intra-district and 3 inter-district learning events. The reason for these variations was to facilitate active learning at the SGR level and to offer opportunity for SGRs to improve their practices by incorporating new learnings from others. These activities facilitated increased learning across projects, thus enhancing the Small Grant Recipients’ capacity, showcasing innovative adaptation responses, building relationships and creating support networks. These exchanges presented the opportunity for technical cross-project learning as well as exposing SGRs and beneficiaries to different parts of the country and contexts. These learning exchanges proved to be effective, building relationships across projects and people from the different districts and backgrounds, and inspiring SGRs in terms of new potential technologies that could be used e.g the charcoal evapotranspiration cooler. SGR Project Changes Some projects had to reduce their targets. Due to the design of specific structures being more complex and resource intensive than anticipated resulting in delays in implementation, ultimately resulting in certain projects being unable to achieve their initial planned targets in the given time frame and project budget. The process of reducing targets was heavily supported by the FA and carefully negotiated with the beneficiary groups to ensure that expectations were managed and the process of selecting beneficiaries remained fair and in line with the ESPs. This experience enhanced the capacity of SGRs in terms of project planning, developing realistic of timeframes and the level of effort necessary to properly adhere to compliance requirements. Project design changes were undertaken in order to take advantage of new opportunities or better utilise information learned throughout the early implementation process. For example, after a participatory processes, it was determined that it was more economically sensible to purchase rams, who are hardier and can breed with local ewes, resulting in changes to the original purchase plan in the Gondwana Project. In the ‘Two Communities Adapting together’ project, engagement with community members in context resulted in a change in the type of technologies preferred. Drought conditions resulted in increased demand for rainwater harvesting tanks and less demand was noted for compost toilets and housing insulation. Reallocation of Budget to meet capacity needs EE and FA staff were required to spend more time than was anticipated to support the SGRS with technical, financial and administrative requirements. The additional time was not fully resourced. This resulted in the request to reallocate unused budget from Component 1 to Components 2 and 3. The cost for implementing a project of this nature are greater than the SGF had catered for, even with the additional investment. In future, financial resources should be adequately provided to ensure the support of SGRs to complete technical (ESP, particularly), financial and administrative requirements. The suspension and expiry of one project prior to completion resulted in an alternative approach to facilitating the beneficiaries needs that didn't involve a grant recipient but saw the EE administer and the local FA facilitate the activities prioritised by the community. Procured additional service providers to support project implementation and sustainability During project implementation some SGRs discovered that additional expertise e.g. engineers were necessary to ensure that it met compliance and health and safety requirements, and to facilitate project sustainability. As a result some projects engaged external service providers to play this role, which was initially unplanned and unbudgeted for and in particular cases impacted on project targets. Subsequent to the SGR projects coming to an end, it was noted that some projects would substantially benefit from continued support and guidance beyond the lifetime of their small grant. Therefore, to further embed the skills and knowledge gained through the project and foster greater sustainability a service provider was engaged to provide additional training and mentorship to the beneficiaries of these small grant projects after their contracts came to an end.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | The design of the SGF placed particular focus on screening for potential environmental and social risks, aiming to mitigate unintended negative impacts on an ongoing basis. Selecting adaptation projects that demonstrated limited negative environmental and social impacts promoted more efficient project delivery given the limited time and funds available for complex assessments and mitigation measures. Establishing criteria that ensured that “no significant risks” were incurred with regard to the ESP and disallowing projects that require a Basic Assessment or full Environmental Impact Assessment potentially minimised costs and delays. Several ESPs promote environmental conservation. ESP principles 9 (protection of natural habitat), 10 (conservation of biological diversity), 12 (pollution prevention and resource efficiency), 13 (public health) and 15 (land and soil conservation) resulted in the delivery of awareness raising and technical assistance and resulted in increased awareness of potentially environmentally harmful activities as well as promoting community health and safety. Knowledge and capacity building to this effect has potential to change local practices over time to promote improved land conservation and biodiversity. Rigorous compliance monitoring, supported by ESP visits, flagged ESP risks early, allowing opportunity to implement remedial actions and support. Quick detection of project management challenges offered opportunities to identify appropriate technical assistance or support required to remediate the problem and capacitate SGRs based on individual needs to promote acceptable performance. Exposure also allowed for remediation actions to be identified and implemented before poor management became project risks. The gains from ESP compliance measures were not achieved without significant effort, however. Many of the challenges resulted from differing interpretations and understanding of the ESPs, and how that was communicated to SGRs, as well as lack clarity of roles and responsibilities due at least in part because formal systems for unidentified sub-projects were not established at the inception of the SGF project. An extensive mapping of the ESP requirements, and what is required to meet these requirements, is necessary prior to any implementation. To improve the practical application of ESPs in communities, proportionality could be applied to ESP assessments, focusing on the principles most relevant to risk identification and management in a particular project The experience was a process of capacity building for all parties in the SGF, resulting in transformed understandings across the system of what it takes to make effective and acceptable use of climate finance, and how best to achieve that understanding. Additionally, the process of interpreting and understanding the ESPs in terms of how they applied to the SGF and projects of the Small Grant Recipients took the project partners, the NIE and EE in particular, a substantial amount of time to unpack. This was demonstrated in the ESP Dashboard that was developed but could not be applied to the SGR projects as it was not within the SGRs capacity to utilise, and it was difficult to apply this tool to these small adaptation projects. Finally, the local context in which the ESPs are applied is an important consideration. In both districts local and provincial government capacity presented a challenge, particularly with regards to ESP 1: Compliance with the law. In complying to ESP 1, specifically obtaining permits, licences, registrations and approvals, the SGRs experience significant project delays as the process of obtaining these was time consuming and in many cases not straight-forward. In future iterations of such a project the following is recommended with regards to ESPs: - At project proposal stage an extensive mapping of potential ESP risks and the real requirements in terms of time and resources of mitigating those risks e.g. water use licence will take 1 year and require extensive follow-up, be conducted by the Project Management Team. Adequate understanding of the time and budget required to conduct this mapping, and requisite planning, is required. - Assessments of ESPs risks in line with project proportionality be conducted collaboratively with Small Grant Recipients, - Substantive and on-going capacity building for SGRs on ESP risk management starting at the proposal development stage
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | The planning and design of the project included provisions for promoting the participation of women. Stakeholder workshops conducted as part of the planning process actively promoted participation of women, targeting a 50:50 ratio, which was largely achieved. Gender sensitive criteria, indicators and targets were included in the project design to promote the inclusion of women. Once the small grants were awarded, SGR projects were required to develop beneficiary selection plans that included outlining the planned process for including women in the project, and to disaggregate beneficiary data by gender, each of which were reported quarterly. These measures were generally effective in ensuring equitable representation of women as beneficiaries as well as within decision-making structures. The Results were that 11 of 12 SGRs included women in their management structures. By the end of Year 5, more than 55% of beneficiaries were women. Nine of the 12 completed projects achieved a minimum of 50 per cent women beneficiaries. The short project time frame limited the impact many projects could have on historical gender bias, which influenced the participation of women. In economic sectors with a long history of male domination, some projects were unable to achieve equitable gender representation. Fisher and livestock farming communities expressed difficulty in achieving equitable gender distribution amongst beneficiaries, despite preferential criteria, as the overwhelming constituency was male. However, the BRK and KHF livestock farmer cooperative and herder community projects were both able to ensure that women were equally represented within the project management structure. In contrast, in sectors or organisations with large female constituencies and/or leadership, the inclusion of women well exceeded fifty per cent. The preferential participation criteria resulted in 85% of the beneficiaries of one climate-smart agricultural project being women, which was also likely influenced by the lead organisation being started and run by women. Projects that involved subsistence farming and household gardens reported participation of mostly women in the project, presumably due to the fact that the managing of household food and nutrition needs were an existing sphere of high influence in the communities. Furthermore, it should be noted that some women will not want to engage in all economic sectors and the right of choice must remain protected at all times. A lesson that can be derived from this information is two fold. In rural vulnerable South African communities women can - and do- have an important role in community adaptation responses. Secondly, context is important. International funding is not going to immediately change social and economic dimensions embedded in cultural practices and the resultant structural barriers encountered by women. Understanding the complex nuances of the beliefs and practices surrounding gender-based inequities is crucial. This required deep engagement with community members over time. The focus on gender during the grant application process and throughout implementation, via quarterly gender disaggregated monitoring and reporting and other compliance tools (such as the beneficiary selection plan), facilitated an ongoing discussion with SGR project management and the communities within which they worked. The fact that 55% of the direct beneficiaries are female is a result of that focus and ongoing conversation.
Please complete the following section at mid-term and project completion
Note from the NIE: The EE has responded to the sections below as this is the last PPR to which they will contribute. SANBI will repeat this information when PPR6 is submitted.
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | This section provides lessons learned by highlighting aspects of the SGF that are broadly believed to have contributed to its success as well as aspects that may be worth considering based upon challenges the project experienced. Capacity building Capacity building is viewed as a central theme of the SGF project; through capacity building efforts climate change adaptation is achieved. Capacity should be understood as a dynamic quality built over time. In addition, the instruments and mechanism used to facilitate community-based climate adaptation should employ adaptive management practices to provide the support required for effective local adaptation interventions as needs emerge. The various levels and types of capacity required for effective community-based climate change adaptation should be well understood prior to the grant application process. Eligibility and Selection of Small Grant Recipients Approach organisational development as a building process and ensure that eligibility criteria do not preclude those organisations that are targeted to implement the projects. Apply granting conditions that promote community organisations' involvement in an effort to increase the numbers and types of SGRs, and as a result the diversity of projects. Offer a phased, and fully funded, proposal development process Nine of the twelve small grant recipients were new to climate change adaptation, therefore significant support and technical capacity building was required at the proposal development and implementation phases of projects. Additionally, to effectively adhere to the compliance requirements accompanying funds provided through a climate finance mechanism to implement climate change adaptation project substantive capacity building and support was required. A fully funded (minimum of 6 month) tailored capacity building programme at the proposal development stage would have greatly benefitted the SGRs and strengthened the outcomes of the SGF project. During this period, the grant recipient would receive technical support related to their climate change adaptation project. This period would also offer opportunity to show (or build) financial reporting capacity, providing an ideal environment in which to test-run and improve capability within targeted local organisations. Such an approach would entail offering applicants that propose approved adaptation project concepts, and who are able to demonstrate an acceptable level of organisational accountability, core funding for operational costs and relevant staff salaries, during a preparation and detailed design phase. Outputs during this phase could include: mentorship to strengthen project concepts; identification of areas of innovation and co-benefits; building climate change adaptation and technical capacity; strengthening of administration, governance and financial capacity; and obtaining familiarity with project management requirements, include ESP tools. Facilitate a holistic systems approach to project interventions Those SGRs that took a systems approach had greater success and enhanced project sustainability. These projects employed a range of complimentary, interconnected interventions that in combination create a self-sustaining system. For example, a food garden with a poultry house that provides manure for the garden, compost heap and biogas digester, the biogas digester provides bio slurry for the garden and gas for a feeding scheme. By addressing the multiple aspects of climate change simultaneously, projects can be strengthened. Make special provision for water management and conservation for community based adaptation projects The most significant challenge faced by all the target communities was extreme water scarcity. This was identified as a key issue in the vulnerability assessments in both districts and recurred throughout the lifetime of the SGF. Each SGR project aimed to address the issue of water scarcity in its own way. However, a more strategic and holistic approach to addressing this issue by each project would have lent itself to enhanced project sustainability and greater environmental protection. Provision for a team of experts in the field of water management and conservation to advise and guide at the project development stage, and provide input during implementation could have strengthened the projects. Customised disbursements based upon individual project achievements To avoid general delays in project progress, a project of this nature should have a flexible funding mechanisms that accommodates for the release of funds to individual SGRs based on each organisations performance and adherence to reporting requirements. Establish robust yet agile structures and systems for effective oversight Agile systems to support responsive action to local needs is required. The system designed to support a technically complex and diverse project requires clear articulation of roles and responsibilities and mechanisms that support flexibility. Decision-making authority should be devolved as close to local implementation as possible, given there is a natural tension between practical delivery needs and the requirement of programme governance (and the requirements of project, government and donor oversight systems). Levels of authority may vary in accordance to theme and may be adjusted throughout the project lifecycle depending on needs. Community-based climate adaptation projects seek to promote local resilience, requiring local solutions to address local problems. Too great a focus on managing delivery though cascading levels of authority, detracts from this strategic objective. Lengthen the project timeframe: The pace of the project meant that there was often not adequate time for the SGRs to adequately focus on capacity building, so that the knowledge and skills were embedded and remain beyond the project. More time is necessary for effective enhancement of capacity and for projects to implement. Therefore if donors want to bring climate finance to the ground, then they should be prepared to allow implementation periods of 7 - 10 years.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Lessons learned from the SGF project identified that scaling up mechanisms should facilitate an enabling environment through the development of increasingly effective and flexible systems and structures delivering project management oversight and climate finance. The goal is not necessarily to scale up local interventions that address specific climate change challenges within each socio-economic and cultural context. The aspiration is rather to scale up the capacity of oversight and governance structures to enable systems that are robust enough to support progress and manage risk, yet flexible enough to facilitate locally-driven adaptation interventions. An enabling environment incorporates mechanisms to promote community engagement and involvement in project management at all levels, building requisite capacity along the way to ensure that interventions are informed and community-led. Furthermore, it provides a structure within which communities have expertise and resources to implement climate adaptation measures that suit their needs and priorities while ensuring that capacity-building efforts are delivered to enhance local and sub-national resilience. In addition to creating more effective project management, this also provides an opportunity to take development challenges further and establishes policy and procedural approaches that represent progress towards effective climate change adaptation. A systems approach to enhancing the capacity of the systems involved to swiftly deliver responsive support services is key. This includes being responsive to specificity and diversity of context as there is no single solution to community-based climate change adaptation. In order to do so, a local presence, facilitation and interlocutor is essential. Decision-making authority must be devolved as close to communities as possible and feedback loops integrated into the highest levels of oversight. The specific structure can not be recommended, and must be based upon various factors, but should its design should include input from all stakeholders and encourage the deep integration of local priorities and learnings while ensuring appropriate oversight mechanisms exist to manage risk. Projects should employ a holistic approach that entails a range of different interventions that complement one another and tackle the multiple different contributing factors to climate change vulnerability. Therefore, community-led project development should take cognisance of the multiple different issues and explore ways to address these. Through the SGF a variety of innovative community based climate change adaptation approaches were demonstrated. Whilst interventions should be context and project specific, the methodologies developed through the SGF could inform and be used in other projects. Therefore these approaches should be shared as potential options to address challenges identified through a participative engagement and project development process. Additionally, this practical learning should be disseminated and shared in other community-based adaptation arenas including communities of practice. NIE contribution: Efforts are underway to complete the methodolgical framework, which is a Component 3 deliverable, as an informant for a future small grant facility that supports climate change adaptation responses at the local level. It will be critical to address some of the governance, reporting, complaince and capacity challenges that were persistent over the AF pilot project, and the experiences and emerging lessons will be important informants of the way foward.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | As reported in Year 2, the AF's climate finance readiness support (in SANBI's case, a Technical Assistance Grant to develop an updated ESP Dashboard) supported SANBI to develop an ESP Dashboard that was applied in project reporting and review processes. The process was instructive in that it illustrated the level of capacity building support that is needed for the effective application of the ESP at all stages and at all levels of the system. The experiences and challenges of working with the ESP is discussed in several responses in PPR5, and is also the subject of one of the project's case studies.
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | SANBI received a Technical Assistance Grant from the AF to develop an updated ESP Risk Dashboard and associated Guideline Document. As part of the development of the Dashboard, training sessions on how to use the tools were held with the EE, Facilitating Agencies and small grant recipients. The Dashboard and associated training initially proved valuable in facilitating compliance with the AF's ESP and ensuring any unintended negative impacts are avoided, or mitigated if necessary, as well as in building the capacity of the small grant recipients to understand and manage environmental and social risk and constantly improve their projects. The Dashboard has also proved valuable in assisting with the review of conditions associated with project approval and implementation, thus is an integrated risk and planning tool. Use of the Dashboard at the local level was, however, problematic. In spite of receiving what was believed to be the necessary training, neither the Executing Entity nor the Facilitating Agencies were able to interpret the tool for the local level. This often resulted in disproportionate responses to the safeguards by small grant recipients. The issue of cascading compliance is noted in the MTE, the TE and is the focus of one of the case studies.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | In addition to the items noted above with regard to lessons learned to enhance climate change resilience, the following is noted by the EE: Adaptation assets should be chosen by local communities in order to ensure they meet their needs and priorities Community-based adaptation interventions should be developed and directed by the communities within which they serve and reside. Whilst the SGRs had a mandate from their community to implement their projects, further increasing participation in the decision-making could better empower communities and support increased buy-in and sustainability. This combined with suggestions and inputs from key experts on technical aspects of the project, and a longer project time frame in which to implement would have enhanced ownership and commitment to the projects. Ascertain SGR capacity at the proposal development stage A comprehensive technical assessment to undertake specific adaptation interventions, potentially through a capacity assessment, could have helped to: - Identify aspects of a proposed project that an SGR is new to or inexperienced with e.g. cooperative dynamics and assist them to build in the necessary support to implement such projects - Identify if the planned activities were realistic or too ambitious for a given timeframe, based on the outcome of the SGR’s capacity assessment and previous experience. Assist SGRs to identify and engage the relevant, trusted experts needed to support the project prior to implementation The application and/or instalation of various adaptation interventions is often very technical and requires input from experts. Supporting SGRs to identify local experts appropriate to the task that offer value for money can reduce time and costs associated with various activities, including managing risk associated with improper or inadequate installation. Make greater provision for infrastructural inputs A valuable and unusual aspect of the SGF was the funding of infrastructural inputs e.g. earth dam refurbishments, construction of buildings etc. Apart from requiring technical range of experts e.g. engineers, designers, architects, resources e.g. TLBs, solar systems, steel components, infrastructural interventions require substantial financial resources. Therefore to effectively facilitate infrastructural developments, alongside identifying appropriate service providers, a greater budgetary provision would be necessary, and included in this should be funding for maintenance of the infrastructure beyond the lifetime of the project.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Adaptation interventions were custom designed by communities to address their specific climate vulnerabilities and local priorities and customs, therefore were all contextually dependent. However, some broad approaches, which could be replicated and scaled in various places to promote an environment ripe for successful implementation of adaptation projects, include: -utilising a holistic approach that leverages co-benefits through integrated interventions that support mutually reinforcing community assets; -adopt and resource capacity building as an integral, but separate, work package to ensure that grant recipients build the requisite organisational, management and technical skills required to manage and implement adaptation projects; -develop a legacy plan and integrate it with project sustainability plans to promote the development of support structures that continue to promote successful adaptation even after the project closes; -nurture, develop and value partnerships at all levels of the project, including local government and private entities; and, -facilitate participatory, inclusive and locally-driven processes throughout every stage of the project to ensure alignment with local priorities and support community buy-in. Concrete adaptation actions that lend themselves to replication and scale include: * the introduction of hardier and drought resistance animal breads into existing livestock * the use of simple, cost effective technologies such as bio slurry from biogass digestion to improve soil quality, garden terracing on slopes to improve water retention, charcoal cool rooms to help store produce, drip irrigation to conserve water, creating access to markets for enhanced income, domestic rain water harvesting and storage.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | During final engagements with the SGRs, including the EE and NIE’s final site visits, project beneficiaries shared their learning, experiences and gratitude for how the SGF grant had changed their lives. Many beneficiaries expressed appreciation for the fact that they could now access food and/or funds for their families, and that they had learned a great deal about climate change and how adaptation techniques would help them to sustain these benefits over the years. These adaptive management skills and adaptation assets brought tangible results to communities. The SGF served as a vehicle to bring climate change to the fore, raising awareness of it and ways to address it, both at the community and municipal level. Importantly, the SGF initiated the process of engaging with issues relating to climate change, and developing adaptation responses for many of the SGRs, who previously had no experience or understanding of the field of climate change, despite suffering it’s effects. This is particularly pertinent in the Mopani district where the level of understanding and engagement with issues of climate change was extremely low, as identified by the vulnerability assessment. The improved capacity to understand, design and implement community-based climate change adaptation is a notable success. Implementing the SGF has enhanced the capacity of all partner organisations in the project in a range of ways, including climate change adaptation, technical project implementation aspects, project management, capacity building, stakeholder engagement, and grant-making and compliance management in the context of climate finance. A national mechanism through which international climate funds can be filtered was developed and refined through this process. This mechanism can inform national architecture to access a variety of climate finance funds that can ultimately strengthen the adaptive capacity and resilience of South African communities. A total of 34 adaptation assets created or strengthened in support of individual or community livelihood strategies in highly vulnerable communities in which, without the SGF, those assets would not have been achievable.
What measures are/have been put in place to ensure sustainability of the project/program results? | The project management team have spent a significant amount of time and effort assisting the SGRs to develop sustainability plans for their projects. These plans, facilitated by the project management team but developed by beneficiaries and SGRs to ensure support and buy-in, take into consideration the cost of proposed sustainability activities and how they will be funded. In addition, the project management team, particularly the FAs, identified and supported applicable SGRs to access additional funding opportunities through grant applications and potential partnerships. The Project Management Team also continues to alert the SGRs to potential funding opportunities when they arise. Both FAs are continuing to engage with the local municipality, district and provincial government, and develop local networks to provide on-going support to the SGR projects and facilitate project sustainability. As part of sustainability activities, fundraising opportunities were shared with the SGR to encourage applications for future funding. As a result of these, 1 SGR (Ramotshinyadi) was able to confirm funding from the Department of Agriculture for R50,000 to support poultry production and 1 SGR (Tsogang) submitted an application for an International Climate Initiative (IKI) grant but have not had confirmation. In Namakwa, the FA has facilitated the inclusion of a number of the SGR projects into the Namakwa District Integrated Development Plan (IDP), allowing the SGRs to potentially benefit from certain funding, resources and support.
What measures are being/could have been put in place to improve project/program results? | Seeking to use climate finance to enable local responses to climate change entails the continuous improvement and development of approaches to community engagement and project management. Some learnings that could be applied to subsequent iterations in an effort to improve results include: -Ensure a balance between robust structures for effective oversight and agile systems to support responsive action to local needs. The system designed will require clear articulation of roles and responsibilities as well as mechanisms that support flexibility to respond to local emerging needs. -Decision-making authority that is devolved as close to local implementation as possible is key to locally-driven interventions. Levels of authority may vary in accordance to theme and may be adjusted throughout the project lifecycle depending on the demands of the project and needs of the community. Default authority should be allocated to those institutions / stakeholders closest to beneficiary community, with levels of authority provided to oversight structures only with suitable motivation. -Advisory support and technical assistance should articulate important linkages and strategic connections to expand impacts and strengthen resilience more broadly. Leveraging high level policy and contextual understanding, national and sub-national project authorities should use learning to promote increased adaptive capacity throughout the nation or region, drawing the connections between local projects, regional adaptation measures and the policy environs for broad impact. -Flexibility to support local entities to identify and implement practical solutions is essential. Community-based climate change adaptation projects seek to promote local resilience, requiring local solutions to address local problems. Too great a focus on managing delivery though cascading levels of authority, detracts from this strategic objective. -It is necessary to develop a clear understanding and definition of the multiple capacities required to implement locally-driven climate adaptation interventions. Capacity should be understood within the context of donor and governance expectations as well as the desired technical achievements. Adopt a strategic approach to capacity building, including: - capacity building should form a separate programme of work/project, apart from the SGR support function. The programme should consist of a team with a range of expertise e.g. financial management, M&E, climate change adaptation to meet the necessary capacity building requirements, and this programme of work should be resourced accordingly. - Conduct a well-structure and extensive capacity assessment, organisational and technical, at the onset of proposal development. On this basis put in place a structured capacity building plan, specific to each applicant. The capacity building plan should be split into two parts one that focuses on proposal development stage and another for during implementation should a grant applicant be successful. - Include the local municipality in the participative project design/proposal development process. This will facilitate buy-in and support from the local municipality, as well as assist in building their capacity from the outset of the project.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Various data and research informed the design of the SGF, including a climate analysis based on the latest climate change projections, prepared under South Africa’s Long Term Adaptation Scenarios (LTAS) Flagship Research Programme Phase 1 process. In order to gain a better understanding of the local scale projections for the two project target areas, a study was commissioned for a spatially specific analysis of data from the downscaled projections produced under the LTAS. A full report, developed by the African Climate and Development Initiative (ACDI) at the University of Cape Town (UCT), including participatory engagement with both communities, further informed local needs and was used to develop the investment windows applied to the grant application process. The collective information was used as a departure point for the project design, providing a detailed and localised understanding of climate change science and local socio-economic and climate-related concerns and priorities from which the project was built. The project implementation included a component that was dedicated to facilitating learning, highlighting training opportunities, the facilitation of local networks and the development of case studies and policy recommendations as outputs. The FAs conducted capacity building assessments with the SGRs to determine areas that required strengthening. Based on the findings, training and mentorship was provided to build SGR capacity. Each SGR had additional funding allocated to ensure their participation was resourced throughout the project lifecycle. Learning workshops were facilitated throughout the projects, ensuring that learnings from all stakeholders and from various perspectives were solicited and shared. This included facilitated learning workshops involving SGR stakeholders, regional workshops as well as inter-district workshops alongside project management learning and reflection sessions. Nine case studies and a case study series introduction were co-developed, focusing on thematic learnings, and will be available for public dissemination.
If learning objectives have been established, have they been met? Please describe. | The learning component outputs included: 1. Training opportunities are provided for SGRs 2. Local networds for reducing climate change vulnerability and risk reduction are developed, expanded and stregnthened 3. Case studies and policy recommendations are develop for reflecting on, replicating and scaling up small grant financing approaches In total 44 discrete subject matter capacity building sessions were delivered to project beneficiaries. A significant effort was made to build local networks as well as facilitate cross-district learning about climate adaptation responses to reduce climate change vulnerability, including: - Facilitating local peer learning exchange visits between SGF projects and those of other organisations e.g. climate smart agriculture exchange visit between Mopani SGRs and small holder farmers supported by the Association for Water and Rural Development (AWARD). - Multiple intra-district learning events to allow SGRs within each district to reflect, learn from and build relationships with one another. - An inter-district learning event, which include participants from national and local government, researchers, SGRs, the FAs, EE and NIE. This event provided a space to reflect on the SGF, draw out key lessons learned and share experience across the 2 landscapes. The inclusion of government and researchers presented an opportunity for further development of networks, and for these participants to learn from the SGF processes and about effective context specific adaptations responses. It also provided an opportunity for the SGRs to engage with and talk directly too decision-makers within the SGF, the National Implementing Entity and National Designated Authority. - Two inter-district learning exchanges whereby SGRs from one district visited projects in the other district and vice-versa. This facilitated cross-learning between the two districts, exposing the SGRs to different kinds of adaptation projects. To strengthen the relationship with the district municipality and continue building knowledge about community based climate change adaptation, local government members were included in SGR visits in their district. - 3 Project Management Team Reflections and Learning workshops. These provided a space for the SGF project management team inclusive of the NIE to reflect, share experiences, cross-learn, exchange ideas and plan for the following year. These in person engagements were important for building relationships across the team, enhancing communication and establishing a shared understanding of the SGF and key activities. - Supporting SGRs to join local groups/networks to support the project and further build skills e.g. in Mopani 3 SGRs supported to become part of a local Agroecology group, where practitioners, and civil society organisations involved in agroecology share lessons and opportunities. NIE comment: Several learning objectives were not met at the time of the EE completing its work and these will be completed and disseminated over the coming months. These include the methodological framework for scaling up the AF pilot project, the policy brief and the publication of the case studies. The case study on capacity building provides several important insights and recommendations in relation to learning that will need to be considered for a future iteration of the project.
Additional to these learning events, local networks were established and strengthened by regularly engaging and sharing lessons with the district and provincial municipality in a range of ways. Activities included: - inclusion of TAG members in the SGR proposal development process - the FAs joining and participating in local government forums and networks and providing regular updates about the SGF. - facilitating regular visits to SGRs sites with the Technical Advisory Group to provide guidance to the project, and to learn from the adaptation approaches being used. - inclusion of local government departments in learning exchanges and capacity building training events. - identify and engaging relevant local government departments to support SGR projects, including local municipality via TAG and PAG in the annual EE and NIE site visits. Nine case studies, focused on providing examples of lessons learned organised thematically, were developed. As a series the case studies span the lifetime of the SGF and draw out lessons learned and recommendations in key areas. The intention of the series is to provide a basis for and inform the development of a ‘Methodology for enhancing direct access to climate finance is developed based on lessons learned providing recommendations for scaling up and replicating in South Africa and Beyond’ The methodology will be developed prior to project close out. The case study series will be shared in early 2021 once SANBI has completed the design process.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Obtaining accurate, verifiable data (evidence) from the SGRs was a continual challenge and involved on-going capacity building and support from the FAs and the EE throughout the project lifespan. However, this is to be expected given the intention and nature of the SGF as a pilot programme. To address this challenge the support and capacity building functions of the SGF required greater resourcing, in particular a larger team with a range of expertise to provide the necessary input. Additionally, a reporting and verification process that focused on a learning process and built capacity over time may be useful. For exampe, initial reports could have been very simple, and as capacity grew the reports and verifications requirements could have increased to align more closely with the donor and project requirements over time. To accommodate for such an approach a longer project timeframe would also be necessary.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | The learning objectives facilitated structured outputs that were then incorporated into the project implementation, promoting continual learning and reflection and the integration of lessons learned throughout the project lifecycle. These aspects could have been strengthened if: - provision was made for more than one exchange visit to each district, allowing visits to take place through out project implementation, facilitating a parallel learning process across both districts; - having exchange events earlier in the project would have helped with relationship building across the SGRs and districts; and, - the approach to capacity building had been more structured and customised to the needs of each SGF. NIE comment: Due to range of unforseen factors, including incorrect assumptions about the level of effort that would be required to manage the project and late contracting of grantees, the learning component of the project was not executed as designed. Several recommendations for how this might be approached in a future iteration are under consideration as part of the development of the methodological framework.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | ZAF/NIE/Multi/2013/2
Implementing Entity | South African National Biodiversity Institute
Type of implementing entity | NIE
Country | South Africa
Region | Africa
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 2340 | 600 | 1740 | Total | 1693 | 433 | 1260 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 51.71% | 50% | 52.29% | % of female beneficiaries | 66% | 60% | 68% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 20.21% | 33.33% | 15.69% | % of Youth beneficiaries | 14% | 17% | 12% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | NGO |  | 36 | 50% | NGO |  | 30 | 60% | NGO
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 2: Partially not aware |  | 600 | 50% | 5: Fully aware |  | 433 | 60% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Multi-sector | Community-based adaptation | 24 | Physical capital | Multi-sector | Community-based adaptation | 8 | Physical capital | Multi-sector | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 2: Most not integrated |  |  |  | 4: Most |  |  |  | 2: Most not integrated
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | Local | Other policy | 3 | Multi-sector | Local | Other policy | 0 | Multi-sector | Local | Other policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.