## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | June 2019 - May 2020
| Project Title: | Adapting To Climate Change Through Integrated Water Management in Panama
INTEGRATED WATER MANAGEMENT IN PANAMA
| Project Summary: | The overall objective of this programme is to establish climate resilience water management to enhance food and energy security at the national level, including an integrated and community based approach in the Chiriqui Viejo and Santa Maria Watersheds. Specifically, the programme will be addressing the following objectives: a) Increasing climate change and variability adaptation capacity in agriculture, livestock and energy production sectors; b) establishing climate resilient water management instruments with integrated and community based approach; c) strengthening local national capacity for monitoring and decision making to reduce and respond to risks associated to climate change; and d) raising awareness and establish a knowledge exchange platform to respond to and to reduce impacts of climate related events.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing
Implementing Entity (IE) [name]: |  | Fundación para la Conservación de los Recursos Naturales (NATURA) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA
| Type of IE: | NIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks
| Country(ies): | Panamá | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Chiriqui Viejo and Santa Maria Watersheds | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS)
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport
AFB Approval Date: |  | octuber, 2016
IE-AFB Agreement Signature Date: |  | June 20, 2017 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | June 5, 2018 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned):
| Terminal Evaluation Date: | June 5, 2021
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Inception workshop report, Inception article "Adapting To Climate Change Through Integrated Water Management in Panama" in Natura Panamá web page: http://www.naturapanama.org/fondo-de-adaptacion/ Adaptation Program Video (Initial) Work plan and budget 2018, 2019 and 2020 Environmental and Social Safeguards workshop report for executing entities Quarterly Program Progress Reports 1st PPR Program Webinar Panama on the Road to Adaptation: Capacity Building | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | https://adaptacion.miambiente.gob.pa | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Vilna Cuéllar | Dominican Republic
| Email: | vcuellar@naturapanama.org | Ecuador
| Date: | June, 2017 | Egypt
| Government DA |  | El Salvador
| Name: | Milciades Concepción | Equatoral Guinea
| Email: | mconcepcion@miambiente.gob.pa | Eritrea
| Date: | Agosto, 2019 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Rosa Montañez / Vilna Cuéllar | Fiji
| Email: | rmontañez@naturapanama.org / vcuellar@naturapanama.org | Finland
| Date: | June, 2017 | France
| Executing Agency |  | Gambia
| Name: | Yanet Sierra / Rodrigo Luque - Ministerio de Desarrollo Agropecuario | Georgia
| Email: | ysierra@mida.gob.pa / rluque@mida.gob.pa | Germany
| Date: | January, 2020 | Ghana
| Executing Agency |  | Greece
| Name: | Gustavo Padilla / Ligia Castro de Doens - Ministerio de Ambiente | Grenada
| Email: | gpadilla@miambiente.gob.pa / lcastrod@miambiente.gob.pa | Guatemala
| Date: | March, 2020 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Luz Graciela Calzadilla / Alcely Lao - Empresa de Transmisión Electrica, S.A. | Guyana
| Email: | lcalzadilla@hidromet.com.pa / alau@hidromet.com.pa | Haiti
| Date: | August, 2019 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1:: cumulative from project start to [may 31,2019] |  |  |  |  | Financial information PPR 2: cumulative from project start to [may 31,2020] |  |  |  | Financial information PPR 3: cumulative from project start to [] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
Estimated cumulative total disbursement as of [2017] | Total: US$867,047.78 Costos Directos: EE: NIE | US$574,290.45 US$126,106.19 US$165,651.14 |  |  | Estimated cumulative total disbursement as of [2017] | Total: US$2,675,584.06 Costos Directos: EE: NIE: | US$2,148,372.9 US$186,315.77 US$340,895.39 |  | Estimated cumulative total disbursement as of [2017] | Total: US$ Costos Directos: US$ EE:US$ |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Add any comments on AF Grant Funds. (word limit=200) | It is currently running with two of the four executing entities |  |  |  | Add any comments on AF Grant Funds. (word limit=200) | It is currently running with three of the four executing entities. During this period, the projects that are being implemented are on track and their scheduled disbursements and acquisitions of goods and services have been made when the executing entities carry out activities directly. Projects are still to be awarded, which means a delay in disbursements. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
[13 empty] | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 24554.47 |  |  |  | INVESTMENT INCOME | 8889.83 |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
[13 empty] | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
| 1.1 Concrete adaptation measures implemented for household water security | 0 |  |  |  | 1.1 Concrete adaptation measures implemented for household water security | 0 |  |  | 1.1 Concrete adaptation measures implemented for household water security
| 1.2 Pilot climate smart farming projects implemented | 0 |  |  |  | 1.2 Pilot climate smart farming projects implemented | 0 |  |  | 1.2 Pilot climate smart farming projects implemented
| 1.3 Pilot diversified financing and income source models implemented in vulnerable population areas | 0 |  |  |  | 1.3 Pilot diversified financing and income source models implemented in vulnerable population areas | 349313.89 |  |  | 1.3 Pilot diversified financing and income source models implemented in vulnerable population areas
| 1.4 Concrete adaptation measures implemented for sustainable cattle ranching | 0 |  |  |  | 1.4 Concrete adaptation measures implemented for sustainable cattle ranching | 377665.8 |  |  | 1.4 Concrete adaptation measures implemented for sustainable cattle ranching
| 1.5 Enhanced sectorial support through climate financing instruments | 0 |  |  |  | 1.5 Enhanced sectorial support through climate financing instruments | 0 |  |  | 1.5 Enhanced sectorial support through climate financing instruments
| 2.1 Analysis for climate change vulnerability done in prioritized areas at the Chiriqui Viejo and Santa Maria River Watersheds | 52000 |  |  |  | 2.1 Analysis for climate change vulnerability done in prioritized areas at the Chiriqui Viejo and Santa Maria River Watersheds | 137999 |  |  | 2.1 Analysis for climate change vulnerability done in prioritized areas at the Chiriqui Viejo and Santa Maria River Watersheds |  |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 2.2 Developed technical criteria for granting water use concessions and permits in order to reduce/avoid conflicts among users and increase ecosystem resilience in response to climate-induced stress | 0 |  |  |  | 2.2 Developed technical criteria for granting water use concessions and permits in order to reduce/avoid conflicts among users and increase ecosystem resilience in response to climate-induced stress | 92400 |  |  | 2.2 Developed technical criteria for granting water use concessions and permits in order to reduce/avoid conflicts among users and increase ecosystem resilience in response to climate-induced stress
| 3.1 Designed and in operation the National System for Climate Data (NSCD), by upgrading ETESA´s existing network for recording climatic information from hydrographic watersheds | 387400 |  |  |  | 3.1 Designed and in operation the National System for Climate Data (NSCD), by upgrading ETESA´s existing network for recording climatic information from hydrographic watersheds | 532675 |  |  | 3.1 Designed and in operation the National System for Climate Data (NSCD), by upgrading ETESA´s existing network for recording climatic information from hydrographic watersheds
| 3.2 Established an early warning system to identify in advance, the necessary measures in case of hydro-climatic events that could affect food production and power generation | 0 |  |  |  | 3.2 Established an early warning system to identify in advance, the necessary measures in case of hydro-climatic events that could affect food production and power generation | 0 |  |  | 3.2 Established an early warning system to identify in advance, the necessary measures in case of hydro-climatic events that could affect food production and power generation
| 3.3 The NSCD interfaced and equiped with a joint node, with the Ministry of Agriculture Development, to generate and manage climatic information | 22375.33 |  |  |  | 3.3 The NSCD interfaced and equiped with a joint node, with the Ministry of Agriculture Development, to generate and manage climatic information | 39781.46 |  |  | 3.3 The NSCD interfaced and equiped with a joint node, with the Ministry of Agriculture Development, to generate and manage climatic information
| 3.4 Designed a monitoring and evaluation tool to assess effectiveness of climate change adaptation measures implemented by the program and national efforts | 0 |  |  |  | 3.4 Designed a monitoring and evaluation tool to assess effectiveness of climate change adaptation measures implemented by the program and national efforts | 0 |  |  | 3.4 Designed a monitoring and evaluation tool to assess effectiveness of climate change adaptation measures implemented by the program and national efforts
| 4.1 Improved awareness of watersheds vulnerability and participation of population groups in adaptation measures | 16731.73 |  |  |  | 4.1 Improved awareness of watersheds vulnerability and participation of population groups in adaptation measures | 0 |  |  | 4.1 Improved awareness of watersheds vulnerability and participation of population groups in adaptation measures
| 4.2 Strengthened professional capacities for the climate data analysis and processing, for different sectors involved | 39007.21 |  |  |  | 4.2 Strengthened professional capacities for the climate data analysis and processing, for different sectors involved | 27577 |  |  | 4.2 Strengthened professional capacities for the climate data analysis and processing, for different sectors involved
| 4.3 Strengthened professional capacities on water resources management by incorporating climate change adaptation approach | 44621.48 |  |  |  | 4.3 Strengthened professional capacities on water resources management by incorporating climate change adaptation approach | 699.4 |  |  | 4.3 Strengthened professional capacities on water resources management by incorporating climate change adaptation approach
| 4.4 Systematized and disseminated experiences on climate changes adaptation, nationwide | 0 |  |  |  | 4.4 Systematized and disseminated experiences on climate changes adaptation, nationwide | 0 |  |  | 4.4 Systematized and disseminated experiences on climate changes adaptation, nationwide
| 4.5 Portal for Climate Change Adaptation in Panama, implemented | 13154.7 |  | 575290.45 |  | 4.5 Portal for Climate Change Adaptation in Panama, implemented | 14970.9 |  |  | 4.5 Portal for Climate Change Adaptation in Panama, implemented
| EE FEE | 126106.19 |  |  |  | EE FEE | 60209.58 |  |  | EE FEE
| NIE FEE | 165651.14 |  |  |  | NIE FEE | 175244.25 |  |  | NIE FEE
| TOTAL | 867047.78 |  |  |  | TOTAL | 1808536.28 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  |  | TOTAL | 0 |  |  | TOTAL | 0
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date |  | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
Enumerar los resultados planificados y los costes proyectados correspondientes para el próximo período de notificación | 1.1 Concrete adaptation measures implemented for household water security | 60750 | 2021-06-01 |  | Enumerar los resultados planificados y los costes proyectados correspondientes para el próximo período de notificación | 1.1 Concrete adaptation measures implemented for household water security | 181496 | 2021-06-01 | Enumerar los resultados planificados y los costes proyectados correspondientes para el próximo período de notificación | 1.1 Concrete adaptation measures implemented for household water security |  | 2021-06-01 | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
| 1.2 Pilot climate smart farming projects implemented | 105907.15 | 2021-06-01 |  |  | 1.2 Pilot climate smart farming projects implemented | 789405.65 | 2021-11-21 |  | 1.2 Pilot climate smart farming projects implemented |  | 2021-06-01 | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.3 Pilot diversified financing and income source models implemented in vulnerable population areas | 345102.4967 | 2021-06-01 |  |  | 1.3 Pilot diversified financing and income source models implemented in vulnerable population areas | 852417.2 | 2021-09-01 |  | 1.3 Pilot diversified financing and income source models implemented in vulnerable population areas |  | 2021-06-01
| 1.4 Concrete adaptation measures implemented for sustainable cattle ranching | 590714.45 | 2021-06-01 |  |  | 1.4 Concrete adaptation measures implemented for sustainable cattle ranching | 1026671.7 | 2021-07-01 |  | 1.4 Concrete adaptation measures implemented for sustainable cattle ranching |  | 2021-06-01
| 1.5 Enhanced sectorial support through climate financing instruments | 34400 | 2021-06-01 |  |  | 1.5 Enhanced sectorial support through climate financing instruments | 172000 | 2021-06-01 |  | 1.5 Enhanced sectorial support through climate financing instruments |  | 2021-06-01
| 2.1 Analysis for climate change vulnerability done in prioritized areas at the Chiriqui Viejo and Santa Maria River Watersheds | 197998.2 | 2020-12-20 |  |  | 2.1 Analysis for climate change vulnerability done in prioritized areas at the Chiriqui Viejo and Santa Maria River Watersheds | 157599 | 2020-12-20 |  | 2.1 Analysis for climate change vulnerability done in prioritized areas at the Chiriqui Viejo and Santa Maria River Watersheds |  | 2020-12-20
| 2.2 Developed technical criteria for granting water use concessions and permits in order to reduce/avoid conflicts among users and increase ecosystem resilience in response to climate-induced stress | 98800 | 2020-07-20 |  |  | 2.2 Developed technical criteria for granting water use concessions and permits in order to reduce/avoid conflicts among users and increase ecosystem resilience in response to climate-induced stress | 0 | 2020-07-20 |  | 2.2 Developed technical criteria for granting water use concessions and permits in order to reduce/avoid conflicts among users and increase ecosystem resilience in response to climate-induced stress |  | 2020-07-20
| 2.3 Increased hydrological security in prioritized areas at the Chiriquí Viejo and Santa María rivers watersheds, in line with advances of the National Plan for Water Security | 1549600 | 2021-06-01 |  |  | 2.3 Increased hydrological security in prioritized areas at the Chiriquí Viejo and Santa María rivers watersheds, in line with advances of the National Plan for Water Security | 75000 | 2021-09-01 |  | 2.3 Increased hydrological security in prioritized areas at the Chiriquí Viejo and Santa María rivers watersheds, in line with advances of the National Plan for Water Security |  | 2021-06-01
| 3.1 Designed and in operation the National System for Climate Data (NSCD), by upgrading ETESA´s existing network for recording climatic information from hydrographic watersheds | 89200 | 2020-03-20 |  |  | 3.1 Designed and in operation the National System for Climate Data (NSCD), by upgrading ETESA´s existing network for recording climatic information from hydrographic watersheds | 1029603.67 | 2020-11-20 |  | 3.1 Designed and in operation the National System for Climate Data (NSCD), by upgrading ETESA´s existing network for recording climatic information from hydrographic watersheds |  | 2020-03-20
| 3.2 Established an early warning system to identify in advance, the necessary measures in case of hydro-climatic events that could affect food production and power generation | 103017.59 | 2020-03-21 |  |  | 3.2 Established an early warning system to identify in advance, the necessary measures in case of hydro-climatic events that could affect food production and power generation | 331000 | 2021-08-21 |  | 3.2 Established an early warning system to identify in advance, the necessary measures in case of hydro-climatic events that could affect food production and power generation |  | 2020-03-21
| 3.3 The NSCD interfaced and equiped with a joint node, with the Ministry of Agriculture Development, to generate and manage climatic information | 44000 | 2020-06-21 |  |  | 3.3 The NSCD interfaced and equiped with a joint node, with the Ministry of Agriculture Development, to generate and manage climatic information | 309236.13 | 2020-06-21 |  | 3.3 The NSCD interfaced and equiped with a joint node, with the Ministry of Agriculture Development, to generate and manage climatic information |  | 2020-06-21
| 3.4 Designed a monitoring and evaluation tool to assess effectiveness of climate change adaptation measures implemented by the program and national efforts | 12710 | 2020-10-20 |  |  | 3.4 Designed a monitoring and evaluation tool to assess effectiveness of climate change adaptation measures implemented by the program and national efforts | 110000 | 2020-10-20 |  | 3.4 Designed a monitoring and evaluation tool to assess effectiveness of climate change adaptation measures implemented by the program and national efforts |  | 2020-10-20
| 4.1 Improved awareness of watersheds vulnerability and participation of population groups in adaptation measures | 67079.62 | 2020-05-20 |  |  | 4.1 Improved awareness of watersheds vulnerability and participation of population groups in adaptation measures | 72268.55 | 2021-05-20 |  | 4.1 Improved awareness of watersheds vulnerability and participation of population groups in adaptation measures |  | 2020-05-20 |  | TOTAL | 0 |  |  | TOTAL | 0
| 4.2 Strengthened professional capacities for the climate data analysis and processing, for different sectors involved | 699.4 | 2020-04-20 |  |  | 4.2 Strengthened professional capacities for the climate data analysis and processing, for different sectors involved | 62420.38 | 2020-04-20 |  | 4.2 Strengthened professional capacities for the climate data analysis and processing, for different sectors involved |  | 2020-04-20
| 4.3 Strengthened professional capacities on water resources management by incorporating climate change adaptation approach | 14285.7143 | febreo 20 |  |  | 4.3 Strengthened professional capacities on water resources management by incorporating climate change adaptation approach | 35000 | 2021-04-20 |  | 4.3 Strengthened professional capacities on water resources management by incorporating climate change adaptation approach |  | febreo 20 | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
| 4.4 Systematized and disseminated experiences on climate changes adaptation, nationwide | 40174.9 | abril 21 |  |  | 4.4 Systematized and disseminated experiences on climate changes adaptation, nationwide | 40000 | abril 21 |  | 4.4 Systematized and disseminated experiences on climate changes adaptation, nationwide |  | abril 21 | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
| 4.5 Portal for Climate Change Adaptation in Panama, implemented | 147000 | 2021-06-21 |  |  | 4.5 Portal for Climate Change Adaptation in Panama, implemented | 154970.7 | 2021-11-21 |  | 4.5 Portal for Climate Change Adaptation in Panama, implemented |  | 2021-06-21
| EE FEE | 170000 | 2020-06-21 |  |  | EE FEE | 220000 | 2021-12-21 |  | EE FEE |  | 2020-06-21 | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
| NIE FEE | 170000 | 2020-06-21 |  |  | NIE FEE | 175244.25 | 2021-12-21 |  | NIE FEE |  | 2020-06-21
| TOTAL | 3841439.521 |  |  |  | TOTAL | 5794333.23 |  |  | TOTAL | 0 |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | No funding was stipulated. However, the executing entities will file in the next period |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? | Total: US$333,384.36 MiAmbiente: US$50,880 ETESA: US$46,463 MIDA: US$120,000 ONGs: US$85,050 (GEMAS) US$30,991.36 (FUDIS) |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
1952893.709
Note on O39: Vilna Cuéllar: Adenda. Reprogramada actividades
Note on O40: Vilna Cuéllar: Adenda. Recprogramada actividades
Note on O41: Vilna Cuéllar: Adenda. Reprogramada actividades
Note on U45: Vilna Cuéllar: pendiente mapa zonificación marzo 21

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
E-1 Could climate variability affect the production cycle of the project (eg. change of season or increased rainfall, extended dry season) and therefore the achievement of the expected quality, quantity and time? For example, would tree species to be planted be suffering an alteration in the project calendar (production of seedlings, planting date, and survival rate after planted?) Would rice crops be suffering for lack of water to allow expected yields? | MIDDLE | * We constantly verify the program’s schedule to avoid negative impacts in the production cycle (dates of planting and quantities). * To speed up the process, the seedlings have been purchased in local nurseries and they have been transferred to a local nursery. This enables us to monitor their growth and subsequently carry out planting when they are already of the required size to guarantee survival in the field and so not adversely affect the production cycle. * The selected species are native and adapted to the area. * To date, there are no risks that hinder the technical execution of the project.
E-2. Could the adverse weather conditions affect the schedule for installing i) water harvest systems, ii) hydro-agro meteorological stations, iii) EWS? | LOW | * There is a delay in the award of the water harvesting project and early warning systems. The schedule is not expected to be affected by weather conditions. * Hydrometeorological stations have not been affected by weather conditions.
E-3. Are infrastructure elements (named in E-2) in zones susceptible to seasonal flooding or landslides, flooding rivers or other environmental phenomena that may affect the works? | MIDDLE | * Technical criteria have been used for the geographical locations identified for installing the agrometereological stations. The main parameters being those areas where there are no inputs to collect these data. They are also being located in áreas that are safe from climatic risks as well as risks of theft and / or vandalism.
E-4. Could the program generate adverse environmental impacts? | LOW | * No negative environmental impacts are expected from the execution of the program. * Follow-up is being carried out with the governing institutions and executing entities to monitor compliance with national specifications and standards.
E-5. Are ​​the program areas susceptible to fire (whether caused by human or natural actions)? | MIDDLE | * Yes. The work plans of the productive projects incorporate educational measures aimed at the key actors and indirect beneficiaries to prevent fire caused by human action.
E-6. Could the presence of pests in the program areas affect the production process? (i.e. agroforestry systems, agro-silvo pastoral systems, rice / orchids crops) | MIDDLE | * For the agroforestry project a specific monitoring component for pests and diseases has been included to support decision making using economic thresholds and agroclimatic variables, based on monitoring and incident rates. * Each farm has, as part of its follow-up, monitoring activities and maintenance of plots. * In addition, the project also contributes to the exchange of knowledge with owners of neighbouring agroforestry farms susceptible to coffee pests. * No pests have been detected in the livestock project area.
E-7. Could changes in the context (ex. large infrastructure projects, changing government policies, etc.) affect the relevance of the project to achieve the environmental goals set? | MIDDLE | * Panama held a presidential election on May 5, 2019 and the new government took office in July of that year. * The program works in line with the environmental priorities of the current national government, such as management plans, watershed management plans, agricultural action plans, among others, and no changes in public policy that could affect the program are foreseen. * Although passive conflicts are found in the areas to be intervened due to the use of water for energy generation, no works have been identified that would represent risks for the program's projects. * In the context of the new government, the management and technical team related to the Project was changed. In February 2020, new focal points of the executing entity MiAmbiente were designated * Work is underway with the newly appointed focal points. In addition, several meetings have been held to present the program and its progress.
E-8. The scale of the program is not appropriate in the context of the level of the threat and the pressure that is intended to address? | MIDDLE | * The scale of the project is appropriate. * The project was designed based on the needs identified by the stakeholders, consequently the selected sites are relevant, the results of the project will benefit the communities: for example it will contribute to solve feeding problems of the producing partners and their families, as well as of their animals; and it will generate them additional income, among others.
Type of Risk: Information
I-1. Is there scarce information that prevents Natura Foundation to mitigate or take the risks to which it is exposed in the program? | LOW | * There is no scarce information that prevents Natura Foundation to mitigate or take the risks to which it is exposed in the program. * The executing entities, the NGOs and the producer partners constantly provide information to Fundación Natura. * Similarly, Fundación Natura obtains information through the Basin Committees. * Additionally, there is permanent communication with government and civil society entities.
I-2. Is there insufficient information that prevents the implementing organizations to mitigate or take the risks to which it is exposed in the program? | LOW | * There is good interaction and communication between implementing organizations, the government sector, civil society and producer partners, so there is sufficient information and communication mechanisms for NGOs not to take major risks in implementing their projects. * The NGOs implementing the projects are staffed with technical personnel with experience in the project's subject matter. * Additionally, personnel from EE-MIDA, MiAmbiente and ETESA are incorporated to facilitate the management in the field.
I-3 Other information risks | LOW | * Budget lines have been designated in the projects, to attend meetings and presentations of progress to the beneficiary population and the watershed Committees. * In the projects or consultancies, accessible sites are chosen for training activities to facilitate the participation of the most vulnerable population.
Type of risk : Social
S-1. Is the program in an area of ​​actual or potential conflicts over natural (land, water) resource use? | HIGH | * There are risks in the Chiriqui Viejo river basin and possible risks in the upper part of the Santa Maria river basin. * The project does not intend to resolve existing potential conflicts between interested parties. The project will influence generating tools and information, creating a science-political interface (technical information) for all participants on an equal access basis. * In the Terms of Reference of the projects, channels of communication with the governmental or local authorities (civil society, municipality, basin committee) have been included to present the progress of the program, coordinate actions and update on changes in the context of the region. * At the farm level, the adaptation measures applied are mainly to reduce the risk of increased vulnerability and contamination.
S-2. Are there tense situations between stakeholders needed to be solved to implement the program? | LOW | *To date, there are no tense situations identified between stakeholders needed to be solved to implement the program.
S-3. Does the local workforce lack the necessary profile to implement the program? | LOW | * The executing non-governmental organizations have staff (technical and professional) at the central and regional levels, depending on the type of work to be done that the project requires. In addition, they have local staff to carry out and supervise work in the field. * The strengthening of the technical capacity of the local workforce required for project implementation has been included in the terms of reference of the outputs related to this aspect. Different courses are conducted with the staff of the executing entities on topics such as environmental, social and gender safeguards, as well as climate change adaptation issues, and other specific technical courses.
S-4. Is there an adequate level of training of involved individuals and communities to implement the program? Consider, skills training and the ability to react proactively to address the problems that can be encountered in implementing the program. | MIDDLE | *The beneficiaries have a knowledge base generated by projects previously developed in the area; they require training in the subject of climate change. * Additionally, each component has capacity building plans for the producing partners as well as for the executing technicians. The beneficiay are chosen through established participation criteria. * Due to the COVID 19 pandemic (March as of the date of this report), the courses have been reprogrammed and their methodology has been adapted, in accordance with the guidelines issued by Ministry of Health (MINSA) for holding public events.A maximum of 10 people are allowed to participate in each event.
S-5. Are key actors or beneficiaries highly unlikely to continue in the process of the program in the short, medium and long term? | LOW | * There are many positive expectations of the benefits that the project will generate. Consequently, it is expected that the majority will continue to be motivated and put into practice the knowledge acquired in the project toward climate change adaptation; as it will generate better living conditions and higher income (thus creating interest to keep on such good practices). * The Project prioritizes knowledge on adaptation to climate change with training and technical assistance, using individual and group methodologies. Adjustments are made to the traditional model of plot management.
S-6. Are there current or potential projects (hydropower, mining, roads, or other) that could transform the land use and thereby affect the participation of direct or indirect beneficiaries of the program? | LOW | * This type of project is not known to exist. Meetings of the watershed committee are held where all government and civil society organizations in the area are represented and report on the existence or not of projects to be implemented in the communities.
S-7. Could there be social or behavioral patterns resulting from the presence of labor introduced through the projects (mentioned in S-6) that could transform land-use and bring problems to communities that may affect the program implementation and the intended transformation? | MIDDLE | * No such social or behavioural patterns have been identified. There are no projects or knowledge of potential projects that could transform land use and bring problems to the communities that could affect the implementation of the program and its expected results.
S-8. Is there a lack of leadership in the program areas, especially amongst the young people, that might affect the program? | MIDDLE | * There has been participation by young people but not at the leadership level and an attempt is being made to have representative participation by women and young people. * In the livestock project, given the requirements for the producer partner to have a title deed, it is the parents who generally comply with this requirement; however, the young people actively participate as part of the family in the activities of the farms. * The youth population segment of both sexes has been migrating to urban cities due to the lack of opportunities in rural areas. Therefore, the projects are being coordinated with the educational centres in the areas to carry out technical-professional practices activities to motivate young people to stay in the area. The livestock project plans to establish field schools, which will allow the exchange of knowledge between technicians and students.
S-9. Are the communities and beneficiaries of the program indifferent to the problems that affect them in order to find solutions? | LOW | No. On the contrary, the beneficiaries are very participative in solving their communities problems.
S-10. Can a lack of partners for the program (that can take a leadership role and mobilize action to create local cohesion and participation to the program and its processes), be possible? | LOW | * No such situation is expected. The producer partners are characterized by their active participation and collaboration in the entire process, which is expected to strengthen local cohesion as the basis for the project´s sustainability.
S-11. Are there no conditions for the empowerment and leadership of communities, organizations and / or key individuals -with gender considerations- after completion of the processes provided from the Natura Foundation? | MIDDLE | * The communities have an organizational base and with the Program supported by executing entities and Fundación Natura, the conditions are being created for the empowerment and leadership of communities, organizations and / or key individuals -with gender considerations- so it is expected that the producer partners will continue with their initiatives and be sustainable in the long term.
S-12. Is there a scarce inclusion of prior, free and informed stakeholders at the various stages of design or implementation of the program? | LOW | * No, on the contrary, there has been significant stakeholder participation, prior, free and informed, both in the design and in the execution phase of the program. In the design phase, the different existing public policies were taken as the basis, as well as recommendations from key actors and different leaders of civil society. * The design involved a wide consultation process in the basins with the beneficiary population, with managers and technicians from the executing entities MIDA, MiAmbiente, ETESA, SINAPROC and with organized civil society. Similarly, in the current implementation phase, these participation and consultation mechanisms are kept in place as part of the project´s development.
S-13. Is there any indigenous population in the area of program implementation that would require further efforts to ensure its proper participation? | LOW | * There are no indigenous communities in the project area. There is a seasonal indigenous population that arrives for the coffee harvest stage. This population has participated in the awareness raising activities, field days and training carried out by the agro-forestry projects. They have also participated by providing information and recommendations for some consultancies that have been carried out.
S-14. Is there a potential lack of receptivity to the information and activities generated by the program due to absence of awareness, among the beneficiary institutions and stakeholders, about the climate related origin of the problem, instead of considering it is a result of deficient management of natural resources? | LOW | * On the contrary, there is receptivity to the information and activities generated by the program in relation to the subject, since the process of sensitization and information to key actors and executing institutions has begun. The process of disclosure of information by Fundación Natura has also begun through the media and social networks.
Type of Risk: Legal
L-1. Is the area of ​​the program suitable and free from conflicts over land tenure? Or it isn´t? | LOW | * There are no land tenure problems. * The key actors participating in projects such as livestock and agroforestry are required to present ownership verification documents. * Additionally the signing of contracts with executing entities define the permits that the key actor must grant to guarantee the use of land surfaces.
L-2. Could the lack of an environmental license to implement the program in any or all phases affect its performance? | LOW | * Coordination and monitoring meetings continue with the Executing Entities and with the partners so that all the commitments regarding environmental licenses can be fulfilled, according to the different types of projects. * Compliance is verified by the EE and the executing organizations in the field. * Disbursements are made to the extent that all local permits and compliance regulations are met. * The monitoring and evaluation system indicates any changes in the situations of licensing and permits, as well as strategies to address the risks that may occur.
L-3. Are permits and / or required licences in the different phases of the program clearly identified? Can these not be obtained or fulfilled on schedule, and within the scope, and budget of the program? | MIDDLE | * Given its nature, none of the projects carried out in the Adaptation Fund Program requires, in accordance with the law, an environmental impact study in order to operate. * The environmental criteria are followed with rigorous observation to avoid possible negative effects. In addition, the country's regulations are reviewed and meetings are held with the basin committees (made up in part by the municipal authorities), to find out if permits (municipal construction permits, water extraction, etc.) or licenses are required. * In the Terms of Reference, where necessary, these legal requirements are included so that the executing agency is aware of the need to comply with them. * Additionally, compliance with each of these requested permits or licenses is monitored.
L-4. Are there inadequate public security conditions for implementing the program? | LOW | * There are no public safety issues in general terms; however in some farms of the silvopastoril project livestock or equipment have been stolen. Meetings are being held with the area authorities and the executing entity MIDA to define risk mitigation.
Type of Risk: Economic
Ec-1. Does the program fail to generate viable economic alternatives or conditions for the participation of key stakeholders, including individuals? | LOW | * No. From the design phase, public consultations were held and viable economic alternatives were defined that would respond to local needs and ensure the participation of key actors. During this period, the implementation of agroforestry and livestock projects has begun and has been confirmed as adequate and attractive to ensure the participation and commitment of local actors. * In addition, on-farm inputs that can represent an economic alternative have been identified. For example: fence posts, instead of being purchased in a store, are purchased directly from producer partners and other producers who are not part of the program but are within the program's impact area.
Ec-2. Does the program lack of a component that provides some economic support to achieve a viable long-term success of the actions, processes and ensures continued environmental impacts from the program? | LOW | * No. The program provides financial support to beneficiaries and executing entities for the acquisition of goods and services (advice, training, payment of wages, technical material, goods, among others) in field projects. Likewise, the monitoring and evaluation process is carried out to supervise the achievement of better economic conditions for the producer partners, as well as to promote capacity building among the program partners so that after the completion of the program their activities can be sustainable (for example, marketing of their products).
Ec-3. Is there a current or potential presence of land speculation arising from improving farms, attracting buyers who could transform land use or reverse the progress and achievements of the program? | LOW | * In the agroforestry and livestock projects, certain criteria suggested by the EE, NIE and MIDA were defined to select the beneficiaries, such as: long-term residence in the place, strong family ties, sense of belonging, in addition to being approved by MIDA, which has experience in working with producers and families in the area of work. Additionally, the EE signed agreements with the associated producers to guarantee the non sale of the farm at least in the medium term. *The selected beneficiaries have been approved by MIDA, which reduces the existing risk of sale, since the Executing Agency has worked with them previously and knows the situation of most of the farms, as well as the level of education of the owners, their opinions about the land, the long-term objectives they have for their farms, etc. * Improvements on beneficiary farms will bring increases in income and socioeconomic benefits, which may result in a decrease in the likelihood that owners will sell their farm.
Ec-4. Is the population of the area influenced by factors of access to service facilities and job offers which makes them less interested in the program? | LOW | * At the upper side of the CHRSM there is no other initiative that makes the producer partners less interested in the program. In the lower and middle part of the Santa María River watershedand the Chiriquí Viejo watershed there are initiatives such as shops, mills, dairies, hydroelectric plants (Chiriquí). * The creation of sources of income, market opportunities, capacity building through project implementation activities (agroforestry, livestock, among others), will have a direct impact on the community which will help the population to stay in the area, and will discourage the search for employment options outside the communities.
Type of Risk: Organizational
O-1. Is there insufficient involvement and coordination among institutions to maintain EWS, hydro stations, as well as the forest cover and ecosystem features that help prevent (among other impacts) floods and erosion? | MIDDLE | * Although there is coordination between all the institutions in the meetings of the watershed Committee, there are, however, limitations to comply with the commitments made. As a mitigation measure, efforts are being made to strengthen both communication and coordination channels, and field operations.
O-2. Do implementing organizations lack the strengths, skills and institutional capabilities in administrative, financial and technical areas to implement the projects? | MIDDLE | * Fundación Natura provides administrative support to institutional executing agencies to facilitate the procurement of goods and services. In addition, technical capacities are strengthened in gender and social issues, environmental policies (safeguards), project monitoring and evaluation, as well as technical issues (forestry, agro-forestry and adaptation to climate change).
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Pandemic | HIGH | As a result of the COVID 19 Pandemic, the following adjustments or changes have had to be made: * Rescheduling the project work plan. * Review and extension of addendas to contracts. * Reprogramming of public calls. * The modality for the delivery of proposals was adapted so that it is virtual. * Review and adaptation of methodology for group activities such as recruitment, technical assistance, monitoring visits, etc. * Review and adaptation of the methodology for working meetings (Selection Committee and others). * Adaptations for teleworking at NIES, EE and NGO level (virtual meetings, virtual work).
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Yes, risk mitigation measures were used during the current reporting period. The NIE has been permanently advising executing entities on situations that could jeopardize the Programme

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Little compliance with the country's environmental legislation and regulations (national laws, regulations and specifications) (L3) | National environmental laws, regulations and specifications that comply with the safeguards for different types of projects were identified, which are included in the terms of reference. | Number of environmental laws included in the terms of reference. | 0 | The program complied with the inclusion of environmental regulations in the technical specifications or TDR of the calls. The consultancies and projects are being executed considering the environmental regulations and other ruling provisions in the country. | N/A | N/A
2 - Access and equity |  |  | * The target population is not fully trained with gender equality. (I1) | * The participation of men and women was guaranteed under the defined criteria of the program activities.. * The participation of the communities of the intervention sites in the activities of the program was guaranteed through calls and person-to-person invitations. * Access and socialization to the information corresponding to the program was facilitated, such as the workshops and progress meetings in the watershed committees and in the Panama's National Climate Change Committee (CONACCP). | * Population trained by sex. * Public calls on sites with easy population access. * # of youth in program activities to develop community leaders | 0 | *The selection criteria (gender, education, socio-economic and environmental) have been included to guarantee the participation of the communities in the calls and events carried out within the program. *Calls for projects and consultancies open to all public were made. *Gender mainstreaming is considered in all stages of the project. | N/A | N/A
|  |  | * Little participation of vulnerable communities in the dissemination and promotion of program activities. (I3) | Public calls | # of public calls per newspaper, web pages | 0 | 10 Public Calls | N/A | N/A
|  |  | * Lack of youth leadership (S8) | Contact with agricultural training centers to incorporate them into Program activities. | # students participating in internships (10 students) | 0 | Within the silvopastoral project, contact has been made with the agricultural and livestock institutes | That the students remain in their area (rural area) and apply the good practices learned. | N/A
3 – Marginalized and vulnerable Groups |  |  | Inequality in access to water for use by human and domestic consumption and productive activities. | *Alternatives for water access are established for farms, such as protection of water sources for productive use through tree planting; *preparation of a diagnosis of farms in critical situation of access to water; *Identification of solutions for the area: watering holes, wells (drilling, restoration or installation of pumps with solar panels); *Training on water issues. | # of farms with water access guaranteed by the program # of diagnoses of farms with a critical water supply situation # of families with water harvest # of watering holes built | 0 | *The purchase and temporary nurseries of native tree seedlings were made to start the planting process to protect water sources. *Consultant is hired to carry out the diagnosis of farms in critical situation of water access *Water supply solutions on farms are identified: water holes, wells (drilling, restoration or installation of pumps with solar panels) | N/A | N/A
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | The local workforce lacks the academic profiles necessary to implement the program activities. (S-3). | *Criteria were developed for the recruitment of the program team that include knowledge and skills to implement the program (technicians, gender, etc.) * Training for technical teams without distinction of gender, race, creed. * Hiring of personnel from the area of influence of the Program. | *Number of executing entities with technical team fulfilling the academic profiles, experience and knowledge in the area of the program *Number of projects with a technical team meeting the academic, experience and knowledge profiles of the area *Number of trainings for technicians and producer partners | 0 0 0 | *A public call is made for hiring program staff and the topic of environmental and social safeguards was included in the TOR. Professional EE-MIDA was hired with the academic profile, experience and the area for the Coordination of the Program. The technical support team has experience in the work area of the Program *MiAmbiente, MIDA and ETESA maintain personnel in their regional offices with technicians with vast experience in the subject and in the area. *Local technicians hired to carry out projects or consultancies meet the profile (academic, experience and knowledge of the project area). * There have been 21 trainings for technicians and program partners in the different projects and consultancies that are being executed. The projects or consultancies have hired local personnel with the academic profile, experience and knowledge of the area. These personnel have contributed to the approach of the program with the communities and the confidence of the producers in the methodologies that are being used. | N/A | N/A
|  |  | There is no adequate level of training for people in communities to facilitate implementing the program (S-4). | *It was verified that in certain areas some beneficiaries have a technical knowledge base generated by projects that have been previously developed in the area; and they need to be strengthened on the subject of adaptation to climate change. *Within the Program, each component has capacity building plans for both beneficiaries and technicians of the executing entities. * The virtual methodology is being used in training in compliance with the country's health regulations by COVID-19. | # of projects with local staff recruitment criteria # of training activities for partners in the projects that are being executed | 0 | 4 projects and consultancies are executed with local contracted personnel. 12 partner trainings held | N/A | N/A
6 – Core labour rights |  |  |  | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply
7 – Indigenous peoples |  |  | *The local workforce lacks the academic profiles necessary to implement program activities. (S-3). *There is no adequate level of training for people in communities that makes it easier to implement the program (S-4). | No mitigation measure had to be implemented in the reporting period | No mitigation measure had to be implemented in the reporting period | 0 | No mitigation measure had to be implemented in the reporting period | No mitigation measure had to be implemented in the reporting period | No mitigation measure had to be implemented in the reporting period
8 – Involuntary resettlement |  |  | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply
9 – Protection of natural habitats |  |  | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply
10 – Conservation of biological diversity |  |  | Environmental laws and regulations are not complied with (L3) | No mitigation measure had to be implemented in the reporting period | No mitigation measure had to be implemented in the reporting period | 0 | No mitigation measure had to be implemented in the reporting period | No mitigation measure had to be implemented in the reporting period | No mitigation measure had to be implemented in the reporting period
11 – Climate change |  |  | Vegetable mass fires caused by anthropogenic factors (E5) | *Training for producer partners *Awareness raising to producer partners and external actors to the project | # of training on vegetable mass fire # Awareness through radial wedges | 0 | No mitigation measure had to be implemented in the reporting period | N/A | N/A
12 – Pollution prevention and resource efficiency |  |  | Environmental laws and regulations are not complied with. (L3) | Elaborate plans for the prevention and management of waste and contamination for projects of component 1 that require it. | Number of waste and pollution prevention and management plans developed | 0 | No mitigation measure had to be implemented in the reporting period | No mitigation measure had to be implemented in the reporting period | No mitigation measure had to be implemented in the reporting period
13 – Public health |  |  | Environmental laws and regulations affecting public health are not complied with (L3) | Does not apply in the period | Does not apply in the period | 0 | Does not apply in the period | does not apply in the period | does not apply in the period
|  |  | Contamination of producer partners when applying fertilizers and weed control | *Compliance with national regulations on use and handling of products for weed control and fertilizers is verified. *Written information is distributed to producer partners on the use of fertilizers and weed control products | # of training carried out on national standards # of guides delivered to producer partners | 0 | No mitigation measure had to be implemented in the reporting period | No mitigation measure had to be implemented in the reporting period | No mitigation measure had to be implemented in the reporting period
14 – Physical and cultural heritage |  |  | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply
15 – Lands and soil conservation |  |  | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | No, in the previous period there were no unforeseen risks.
Have unanticipated ESP risks been identified during the reporting period? |  | Yes, the country has been severely affected by the COVID -19 Pandemic. As of March 25, the national government, through the Ministry of Health, decreed absolute quarantine in Panama. This meant that the team from Fundación NATURA, the executing agencies, NGOs and contractors implementing the Adaptation Fund Program are carrying out the actions in the telework modality..
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | * Adopt new ways of working to address restrictions in the execution of activities with communities. Teleworking and virtual work processes with the communities were adopted. * The executing organizations and contractors reprogrammed group activities, limiting participation to 10 people, complying with the sanitary standards established by the authorities of the Ministry of Health. * Based on the rescheduling of activities, addenda were processed for the delivery of milestone or final products of the contracts. * The communication channels and work methodologies of the program teams were established, which has made it possible to maintain the effectiveness and efficiency of the project monitoring processes. * Administrative processes in Fundación Natura were adapted to make disbursements to project managers and contractors, in an agile way through the electronic platforms of online banking. * Budget analyzes have been carried out to identify the necessary resources to face pandemic contingencies. For example, the acquisition of sanitary equipment (mask, thermometer, alcohol) for use by program monitoring personnel, executing entities, NGO field technicians, and producer partners. The projects that have continued activities with safe-conduct authorized by the competent authority of the country (MINSA) have developed protocols for the management of health risks for the partial opening of activities due to COVID-19. Activities and strict compliance with these protocols are monitored.
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | *Public calls have been made. * The laws and regulations applicable to the program have been included in the Terms of Reference. *We have followed up the application of laws and regulations according to each project and consultancy. The manager and the project coordinators of NIE give permanent follow-up to evaluate the progress in the results and the general execution of the project. Recommendations are given to the executing entities, when required. Meetings are also held with the Fund's Strategic Committee and the Designated National Authority to present the progress of the Program.
Have the implementation arrangements been effective during the reporting period? |  | Yes, they have been effective
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | *A section called Legal and regulatory framework has been included in the Terms of Reference for projects or consultancies, which describes the laws and regulations applicable to the program as well as other applicable national regulations in addition to Social and Environmental Safeguards and gender policy. *The executing entities monitor compliance with the legal and regulatory framework of each project and the Gender Plan.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes, they have been effective.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
So far we haven´t receive any grievances |  | does not apply
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal?
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)?
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Output 1: Enhanced climate change resilience for improved food, water, and energy security in target watersheds. | Output | No. of people with improved access to water from water harvest systems implemented in targeted watersheds | 0 | 125 women in both of the targeted watersheds. | Not started
Output 1.1: Concrete adaptation measures implemented for household water security | Output | Number of people trained on the use and maintenance of the WHS | 0 | 50 women trained on the use and maintenance of the WHS. | Not started
Output 1.2: Pilot climate-smart farming projects implemented | Output | Number of people in targeted communities that benefit from climate-smart agroforestry systems implemented | 0 | At least 50 women, benefit from the climate smart agroforestry systems implemented at the Caisan River Sub-watershed in CVRW | Not started
Output1.3.b Creating capacities for operating orchid and “naranjilla” crops, as well as establishing the correspondent commercialization scheme at the Rio Gallito Sub-Watershed. | Output | i) Number and percentage of women and men who receive training; | TBD | 16 women will receive training | Not started
Output 1.4: Concrete adaptation measures implemented for sustainable cattle ranching | Output | Number of women that benefits from the climate resilient catlle ranching projects | 0 | 90 women | Satisfactory
Output 1.5 Enhanced sectorial support through climate financing instruments | Output | Number of women farmers that receive technical assistance on access financing sources for climate change adaptation activities | 0 | 4 women farmers from each of the two target watersheds | Not started
Output 2.1 Analysis for climate change vulnerability done in prioritized areas at the Chiriquí Viejo and Santa María rivers watersheds | Output | Number of women that participated in the update consultation process | 0 | 100 women participating in the update consultation process. | Satisfactory
Output 3.2 Established an early warning system to identify in advance, the necessary measures in case of hydro-climatic events that could affect food production and power generation | Output | Number of women trained and with built capacitities on the use of the EWS | 0 | At least 50 women trained on how to reduce risks to extreme weather events by understanting/using the EWS | Not started
Output 3.2 Established an early warning system to identify in advance, the necessary measures in case of hydro-climatic events that could affect food production and power generation | Output | Number of women trained and with built capacitities on the use of the EWS | 0 | At least 6 women staff members trained to respond to and mitigate impacts of climate related events must be woman | Not started
Output 4: Awareness raised and a knowledge exchange platform established to mitigate impacts of climate change related events. | Output | No. of people aware of target watersheds´ vulnerability analyses |  | 125 women will receive technical information delivered by the programme | Satisfactory
Output 4.1.c: Socialize the SMRW and CHVRW vulnerability analyses to facilitate the implementation of identified adaptation measures | Output | Number of people that participated during socialization of SMRW and CHVRW vulnerability analyses | 0 | At least 600 women participating | It has not started. Adjustments are made to the methodology of the workshops due to the sanitary restrictions generated by the COVID-19 Pandemic.
4.2.a Offer a Climate Modelling Course with special emphasis on future scenarios impacting food-energy generation activities (at least 45 participants) | Output | Number of people trained on climate modelling and future scenarios impacting food-energy generation activities | 0 | At least 14 women participating in the event | Good (the established goal was exceeded; 42% of the participants in the trainings were women)
4.2.b Offer an international course on Adaptation to Climate Change: Role of Ecosystem Services (45 participants nationwide, including stakeholders in the two prioritized watersheds) | Output | Number of people trained on adaptation to climate change and the role of ecosystem services | 0 | At least 14 women participating in the event | Good (exceeded the established goal; of all the attendees 54% were women) trained in adaptation to climate change and the role of ecosystem services.
4.3.a Offer an international course on participatory and integrated watershed management emphasizing conflict management skills | Output | Number of people trained on participatory and integrated watershed management emphasizing conflict management skills | 0 | At least 12 women trained on participatory and integrated watershed management emphasizing conflict management skills | Good (the established goal was exceeded; 61% of the participants in the events were women.
4.3.b Offer an international course on ecosystem-based adaptation at marine-coastal zones | Output | Number of people trained on ecosystem-based adaptation at marine-coastal zones | 0 | At least 6 women trained on ecosystem-based adaptation at marine-coastal zones | Course was rescheduled by COVID-19
4.4.b 10 workshops will be held at national level -1 per province- to present the document (4.4.a) | Output | Number of people who attended workshops at each province of the country | 0 | At least 150 women | Not started
Output: 4.5.a Communication strategy and systematization of experiences from the program | Output | Number and percentage of women and men who receive technical information delivered by the programme Number of awareness activities providing targeted information to women on climate change adaptation | 0 | number of woman with enhanced capacity in climate change | Poor
Output 4.5.c: Compilation and synthesis of materials for different audiences -farmers, institutions, academia, etc.- on adaptation to climate change (knowledge products) | Output | Number of knowledge products generated and made available to different users by the program Number of people reached by knowledge products from the program | 0 | 600 women and 1400 men will receive specific knowledge products delivered by the programme; ii) 7 knowledge products targeted at women, by content area | Poor
Output 4.5.f Experience exchanges activities at the local level, including at least one international pasantía (guided visit): | Output | Number of people trained from technical exchanges | 0 | 30 women trained in exchange activities at the local level (number of beneficiaries: core impact indicator) | It has not started. Adjustments are made to the methodology due to the sanitary restrictions generated by the COVID-19 Pandemic, which prevents international travel and group events.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
Empowering women through agro-drilling and livestock projects |  | poor
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The projects have the Gender Focus Participation Plan as part of strategies to encourage participation (producers) with gender equality, with an emphasis on family integrality. In order to better comply with the GP, the EE will hire a gender specialist consultant and train the technicians working on the project on gender policies, as well as implement specific actions to improve gender equality for beneficiaries. Dialogues and meetings with key stakeholders and workshops with beneficiary partners have been held in the implementation of these Plans
Have the implementation arrangements at the IE been effective during the reporting period? |  | Until the closure of the report, not all the activities envisaged within the gender participation plans have been fulfilled because some activities have had to be rescheduled by the executing organizations due to the provisions of the Ministry of Health.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | Until the closure of the report, not all the activities envisaged within the gender participation plans have been fulfilled because some activities have had to be rescheduled by the executing organizations due to the provisions of the Ministry of Health.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | In order to better comply with the GP, the EE will hire a gender specialist consultant and train the technicians working on the project on gender policies, as well as implement specific actions to improve gender equality for beneficiaries. Organizations that run directly in the field maintain gender-aware personal work team within the personal work team.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | New technicians have been incorporated into US regionals and agencies, which was scheduled training on the subject by the end of the reporting period. This training has been rescheduled because many of the technicians because of health restrictions have had to stay in their homes and virtual communications has become difficult to coordinate the participants of the technicians and execute them. The Agro-Environmental And Climate Change Unit/MIDA reviews the best methodology for conducting the workshops.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No complaints have been received in the period
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating MIDA
RATING ON IMPLEMENTATION PROGRESS - MIDA
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Component 1. Outcomes: Enhanced climate change resilience for improved food, water, and energy security in target watersheds |  | Outcome 6 |  | Public calls for the allocation of resources to projects. Approvals by the executing entity of 232 farm management plans and start of implementation |  | The implementation of the projects strengthens the capacities of producer partners in good management practices to reduce vulnerability to climate change by contributing to greater resilience. During this period of implementation of the programme, technical training was initiated on two large livestock and agroforestry projects in the Santa Maria River watershed. It began with the implementation of the 232 farm management plans with approach to climate change adaptation and initiated the acquisition and delivery of inputs to the productrs partners (as). Technical card was delivered for the production of organic fertilizer and efficient microorganisms to agroforestry producer partners, good practices of integrated coffee bit management. There were field days of good practices for handling coffee and gaandería. Surveys were conducted on both projects and results presentation on population awareness about impacts and climate change for activity planning. In technical assistance in both projects was carried out through individual visits. | MS
| Component 3. Outcomes: Increased preparedness in target watersheds and reduced risk for disasters among vulnerable communities nationwide Outcomes: Improved access to data for informed, timely decision-making regarding climate variability risks |  | Outcome 1 | Outcome 2 | Rehabilitation of the office for the Agroclimatic Data System, hiring consultants to strengthen technicians in agroclimatic monitoring, strengthening for agroclimatic tables |  | Meetings have been held with the International Centre for Tropical Agriculture (CIAT) for the strengthening of agrometeorology issues and agroclimatic tables of technicians and the methodology of the workshops that will be taught in a virtual way is being reviewed. Agroclimatic tables have been held in the Santa María river watershed (3 provinces), Chiriquí Viejo river watershed (1 province) and the province of Los Santos with the participation of technicians and producers. The office is adapted for the agroclimatic node by the theme of covid-19 | MS
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Vilna Cuéllar
| Email: | vcuellar@naturapanama.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
During the second year of the program we have seen the effort of the team of the executing entity to meet the outstanding objectives that were generated in the previous year, however, we still have to consolidate the team and what the intervention that is carried out in the basins of the Santa María and Chiriquí Viejo rivers. Progress has been made in implementing 120 farm management plans with a focus on climate change adaptation for livestock farms and 112 for agroforestry. The implementation of Agroclimatic Tables in the basins prioritized by the program and in a province that is part of another basin is highlighted. These agroclimatic tables involve agricultural technicians, producers and technicians from ETESA who provide and analyze climate data. Participants analyze the climatic conditions and phenology of the crops and the related part to the bovine part to plan their agricultural and livestock calendar. To strengthen this initiative, the executing entity is in communication with CIAT experts who have experience in the implementation of the tables in the Central American region and South American countries for the strengthening of technicians and producers. The participation of community personnel or knowledgeable areas of intervention in the projects that are implemented has generated greater confidence of the actors in the area and more effective results. On the other hand, the health restrictions by Covid-19 forced the executing organizations of the projects and executing entity to change the methodology of work of face-to-face to adapt to virtual work processes.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
| Component 1. Outcomes: Enhanced climate change resilience for improved food, water, and energy security in target watersheds |  | Outcome 6 |  | Product 1.1 Concrete adaptation measures implemented for household water security |  | The Water Harvest Project is behind schedule. - The technical team of The MIDA Agro-Environmental and Climate Change Unit conducted an analysis to verify The number of systems to be implemented with The assigned and available budget. | Not started
[5 empty] | Product 1.2 The start of implementation of the two projects is contemplated |  | The technical team of the MIDA Agro-Environmental and Climate Change Unit conducted an analysis to verify the number of systems to be implemented with the assigned and available budget. - A previous calls was made, which was deserted - A two call was made, which allocates resources. Donation contract signed on May 26, 2020 | Not started
Executing Entity/Project Coordinator: |  |  | Outcome 6 |  | Producto 1.3 Pilot diversified financing and income source models implemented in vulnerable population areas |  | Agroforestry project (1.3a) in the Santa María river basin: - 112 socio-economic and farm characterization surveys were conducted. - MIDA approved 112 farm management plans covering 200 has under the agroforestry modality. - The results of the soil analyses of each of the 112 farms were obtained. - The georeferencing of 200 hectares was completed, and drone technology was used to obtain updated images of the land use of each farm and to be able to verify the results at the end of the project. - Demonstrations of marking and distancing of sowing, staking, and pH regulation of soils with agricultural lime, have been made in groups of 10 producers. - To reduce the incidence of the coffee berry borer, it was given alcohol attractant and syringes; and demonstrations were made on the use and monitoring of traps for the ethological control of the coffee berry borer. - It began with the delivery of inputs (al alcohol attractant and biological material) for pest control to producers who already had coffee plantations, to prevent the incidence in new plantations. The application of the surveys and presentation of the results on the level of awareness in the population about the impacts and climate change (in year 1) were carried out. - It began with the implementation of farm management plans with climate change adaptation approach. | S
|  |  | Outcome 6 |  |  |  | With the Livestock Project (1.4a) progress has been made in: - The 120 farm management plans were submitted to MIDA for approval. - The Participation Plan with a Gender Focus was prepared and implemented. - The Plan for Technology Transfer with a Gender Perspective, aimed at producers and technicians in the sector, is being implemented - 15% progress in the implementation of the agreed structural adaptation measures in 40% (48 farms) of the farm management plans (FMP) - The contents of the training materials have been prepared (10 cards and 7 data sheets). Due to the health restrictions imposed by the COVID pandemic, group activities have not been carried out. Field days are scheduled with producers in groups of no more than 10 participants in compliance with health protocols. - Module 1: Climate Change and Livestock has been taught to 40 technicians from the agricultural sector. - A survey was conducted in year 1 on the level of awareness among the target population about the problems and impacts caused by climate change. - Fifteen radio spots have been produced and broadcast on radio stations to actors who have limited access to technological tools. | S
|  |  | Outcome 6 |  | 1.4 Concrete adaptation measures implemented for sustainable cattle ranching |  | With the Livestock Project (1.4a) progress has been made in: - The 120 farm management plans were submitted to MIDA for approval. - The Participation Plan with a Gender Focus was prepared and implemented. - The Plan for Technology Transfer with a Gender Perspective, aimed at producers and technicians in the sector, is being implemented - 15% progress in the implementation of the agreed structural adaptation measures in 40% (48 farms) of the farm management plans (FMP) - The contents of the training materials have been prepared (10 cards and 7 data sheets). Due to the health restrictions imposed by the COVID pandemic, group activities have not been carried out. Field days are scheduled with producers in groups of no more than 10 participants in compliance with health protocols. - Module 1: Climate Change and Livestock has been taught to 40 technicians from the agricultural sector. - A survey was conducted in year 1 on the level of awareness among the target population about the problems and impacts caused by climate change. - Fifteen radio spots have been produced and broadcast on radio stations to actors who have limited access to technological tools. With the Livestock Project (1.4a) progress has been made in: - The 120 farm management plans were submitted to MIDA for approval. - The Participation Plan with a Gender Focus was prepared and implemented. - The Plan for Technology Transfer with a Gender Perspective, aimed at producers and technicians in the sector, is being implemented - 15% progress in the implementation of the agreed structural adaptation measures in 40% (48 farms) of the farm management plans (FMP) - The contents of the training materials have been prepared (10 cards and 7 data sheets). Due to the health restrictions imposed by the COVID pandemic, group activities have not been carried out. Field days are scheduled with producers in groups of no more than 10 participants in compliance with health protocols. - Module 1: Climate Change and Livestock has been taught to 40 technicians from the agricultural sector. - A survey was conducted in year 1 on the level of awareness among the target population about the problems and impacts caused by climate change. - Fifteen radio spots have been produced and broadcast on radio stations to actors who have limited access to technological tools. | S
| Component 3. Outcomes: Increased preparedness in target watersheds and reduced risk for disasters among vulnerable communities nationwide Outcomes: Improved access to data for informed, timely decision-making regarding climate variability risks |  | Outcome 1 | Outcome 2 | 3.3 The NSCD interfaced and equiped with a joint node, with the Ministry of Agriculture Development, to generate and manage climatic information. Conditioning of the agroclimatic node office and coordination with CIAT to strengthen agroclimatic technical tables |  | A total of 5 participative agro-climatic tables have been carried out in each region (Chiriquí, Veraguas, Herrera and Chiriquí, Los Santos) with the participation of technicians from the agricultural sector of the region (MIDA, ISA, IDIAP, IMA, BDA, BNP, MiAmbiente, producers unions, etc.); to analyze the climatic information provided by ETESA. | MS
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Rodrigo Luque / Leonel Montes
| Email: | rluque@mida.gob.pa /lmontes@mida.gob.pa
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
• There are no technical personnel from the agricultural extension agencies assigned exclusively to the program activities. Coordination is made with regional directors so that they assign personnel to follow up on projects, to monitor in the field and to prepare the corresponding monitoring and follow-up reports for each of the projects being implemented. • Some projects have not started because the Agro-Environmental and Climate Change Unit has had to review and modify the Terms of Reference they received (which had been returned by the NIE) so that they were in line with the expected outputs; on the other hand, the proponents do not comply with the established requirements. • The COVID 19 pandemic and the health measures imposed by MINSA, including total and partial quarantine, have limited the action of the projects. • Adjustments are being made, depending on the type of project, to the methodology for reducing this impact in the implementation of projects in the field. • MIDA has provided safe conduct for projects to partially restart activities.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Rating MiAmbiente
RATING ON IMPLEMENTATION PROGRESS - MIAMBIENTE
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Component 2. Outcomes: Improved water governance and natural resources management in prioritized watersheds by mainstreaming climate change data |  | Outcome 1 | Outcome 4 | Completion of consultancies for vulnerability analysis in the Old Chiriquí River Watershed. Two studies of water balance and environmental flow of the Caisan (Chiriquí Viejo Watershed) and Gallito (Santa River Watersheds). Two district hydral security plans developed for Tierras Alta and Santa Fé provinces of Chiriquí and Veraguas. Advance of the consultan art for vulnerability analysis in the Santa Maria River Basin |  | The expected progress has been fully fulfilled, where all the activities incorporated in the Annual Operational Plan (POA) were fully developed. Vulnerability analysis document completed for CHVRW and approved, Level Water Concession Permit technical document, It has been suggested that it be a standard to function as a working tool in the Water Safety Directorate. Two district water safety plans designed for Tierras Alta and Sante Fé provinces of Chiriquí and Veraguas. Republic of Panama and two water balance and environmental flow studies for the Caisan River (Chiriquí Viejo Watershed) and Gallito River (Santa María Watershed in Veraguas) . | HS
| Component 3. Outcomes: Increased preparedness in target watersheds and reduced risk for disasters among vulnerable communities nationwide Outcomes: Improved access to data for informed, timely decision-making regarding climate variability risks |  | Outcome 1 | Outcome 2 | Recruitment of consultants to develop the monitoring and evaluation tool to assess the effectiveness of climate change adaptation measures implemented by national efforts. |  | The executing entity developed the project document for the development of the monitoring and evaluation tool and delivered it to the NIE. The terms of reference were presented to make the public call of the team of consultants to be hired for the elaboration of adaptation indicators with their protocols and methodological sheet. | S
| Component 4. Outcomes: Improved institutional capacity, knowledge management, and awareness on climate change adaptation |  | Outcome 2 | Outcome 3 | Training on participatory and integrated watershed management with an emphasis on conflict management skills, Adaptation to climate change: the role of ecosystem services and climate modelling with special emphasis on future scenarios affecting energy and food generation activities and ecosystem-based adaptation activities in marine-coastal areas. Program portal working, mapping of systematization of experiences in adaptation to climate change. Communication strategy implementing itself. Socializing CRChV Vulnerability Analysis. |  | Se realizaron tres de las cuatro capacitaciones: gestión participativa e integrada de cuencas hidrográficas con énfasis en las habilidades de gestión de conflictos, Adaptación al cambio climático: papel de los servicios de los ecosistemas y modelación climática con especial énfasis en escenarios futuros que afecten las actividades de generación de energía alimentaria. la capacitación de escenarios futuros se para actividdaes de generación de energía y adaptación basada en los ecosistemas en las zonas marino-costeras se reprogramó para el 2021 debdio a las restricciones del COVID-19. The portal format has been changed to make it easier to use; and program information is entered. | S
[7 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Vilna Cuéllar
| Email: | vcuellar@naturapanama.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The rating of S is due to the successful implementation in component 2 and 4 where water management instruments have been developed with an integrated approach to the basins prioritized by the program and the adaptation measures prioritized in the Management Plan of the Chiriquí Viejo River basin have been validated. District climate plans were developed to help achieve the SDG #6 on water and sanitation. Capacity building is also being achieved for government agencies, NGOs and producers (as). Another development is the development of the communication strategy that is the guide to what the program discloses in the different spaces at national and community level. In this period, the areas have been defined by the executing entity's team for the monitoring and evaluation system for the effectiveness of climate change adaptation measures; innovative tool that will help visualize the impacts of national adaptation investments with a gender focus.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Component 2. Outcomes: Improved water governance and natural resources management in prioritized watersheds by mainstreaming climate change data |  | Outcome 1 | Outcome 4 | Completion of consultancies for vulnerability analysis in the Old Chiriquí River Basin. Two studies of water balance and environmental flow of the Caisan (Chiriquí Viejo Watershed) and Gallito (Santa River Watersheds). Two district hydral security plans developed for Tierras Alta and Santa Fé provinces of Chiriquí and Veraguas. Advance of the consultan art for vulnerability analysis in the Santa Maria River Basin |  | Vulnerability analysis document completed for CHVRW and approved. - Level Water Concession Permit technical document. It has been suggested that it be a standard to function as a working tool in the Water Safety Directorate. - Two district water safety plans designed for Tierras Alta and Sante Fé provinces of Chiriquí and Veraguas. Republic of Panama. - Two water balance and environmental flow studies for the Caisan River (Chiriquí Viejo Watershed) and Gallito River (Santa María Watershed in Veraguas) (2.2a.b). | HS
| Component 3. Outcomes: Increased preparedness in target watersheds and reduced risk for disasters among vulnerable communities nationwide Outcomes: Improved access to data for informed, timely decision-making regarding climate variability risks |  | Outcome 1 | Outcome 2 | Recruitment of consultants for the development of the monitoring and evaluation system for adaptation measures |  | The public call for proposals for the M&E System for the effectiveness of climate change adaptation measures is in the final phase of coordination. This project will be carried out directly in MiAmbiente with specialist consultants in the field of indicators and climate change. | S
| Component 4. Outcomes: Improved institutional capacity, knowledge management, and awareness on climate change adaptation |  | Outcome 2 | Outcome 3 | Training on participatory and integrated watershed management with an emphasis on conflict management skills, Climate Change Adaptation: the role of ecosystem services and climate modelling with special emphasis on future scenarios affecting food power generation activities. Program portal working, mapping of systematization of experiences in adaptation to climate change. Communication strategy implementing itself. |  | The following international courses have been held: - International course on participatory and integrated watershed management with emphasis on conflict management skills. - International course on adaptation to climate change: role of ecosystem services. - Climate modeling course with special emphasis on future scenarios affecting food power generation activities. | S
[7 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Lorena Vanegas
| Email: | lvanegas@miambiente.gob.pa
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Changes in Program Coordination delayed activities and did not allow diligent progress. The program has advanced in its component No. 2 implemented by the Ministry of Environment of Panama which has allowed to obtain environmental management instruments that strengthens a sustainable management of the hydrograph basin of the Santa María River and the Chiriqui Viejo River. With regard to component 4, courses have been developed to strengthen the technical capacities of government institutions, NGOs, OCB, the program's Web page has been developed and the monitoring and evaluation system for the program has been started, as well as with the systematization of lessons learned from adaptation at the national level. There have been some setbacks in agreeing on administrative aspects, but they are minimal. The other major challenge has been the pandemis by COVID-19, which has caused the restructuring of contracts and work plans.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Rating ETESA
RATING ON IMPLEMENTATION PROGRESS - ETESA
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Component 3. Outcomes: Increased preparedness in target watersheds and reduced risk for disasters among vulnerable communities nationwide Outcomes: Improved access to data for informed, timely decision-making regarding climate variability risks |  | Outcome 1 | Outcome 2 | Acquisition and installation of agrometeorological, satellite hydrological and GOES-R receiving antenna. Technical training in the maintenance of stations and receiving antenna. |  | The GOES-R satellite data receiver antenna was acquired and installed. and is up and running. 27 out of 45 agro-meteorological stations (between new and modified weather stations) and 3 of the 4 hydrological stations that are collecting data at river level have been installed. Field inspections have been carried out and the transmission of the data to the central station of the national climate system has been verified. ETESA technicians were strengthened with training on the GOES-R satellite data receiving antenna and its software, configuration and maintenance of satellite receiving station software and XCONNECT software and the functions and maintenance of agrometeorological stations. The strengthening of the national climate data system to generate data in the country's productive sectors is in progress. The network is consolidated at the national level by providing information and agroclimatic data to public and private actors. | MS
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Vilna Cuéllar
| Email: | vcuellar@naturapanama.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The MS rating is justified because it has not been completed by the installation of the stations that was scheduled to be completed in this period. In 2020, the company's staff and the executing entity carrying out inspections of installed equipment have had mobility restrictions due to COVID-19. The Executing Entity and the NIE have coordinated actions to support the company in issues of safe conduct for mobility to certain areas of the country to continue with the facilities.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Component 3. Outcomes: Increased preparedness in target watersheds and reduced risk for disasters among vulnerable communities nationwide Outcomes: Improved access to data for informed, timely decision-making regarding climate variability risks |  | Outcome 1 | Outcome 2 | Acquisition and installation of agrometeorological, satellite hydrological and GOES-R receiving antenna. Technical training in the maintenance of stations and receiving antenna. |  | -The Adaptation program acquired and installed the GOES-R satellite data-receiving antenna. It is working. -Installed 3 of 4 hydrological stations that are collecting river level data. -Installed 27 of 45 agro-meteorological stations (between new and modified meteorological stations). Some of these stations are in an inspection phase. -Did 2 workshops for ETESA technicians about the GOES-R satellite data-receiving antenna and the functions and maintenances of the agro-meteorological stations. | MS
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Alcely Lao
| Email: | alau@hidromet.com.pa
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Significant delays have been reported during this period due to heavy rains in 2019. In addition, in 2020, the COVID-19 situation and panamanian government restrictions halts field works for contractors and the US (ETESA).
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
Project Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End | NIE Comments
Outputs | Number of households with improved access to water from water harvest systems installed (number of beneficiaries: core impact indicator) | 0 | 0 | 31 households with water harvest systems installed ( 20 SMRW y 11 CHVRW) | * A public call was made, which was left deserted. * The MIDA executing agency analyzed the budget and made the corresponding adjustments to the current costs. * The Terms of Reference were adjusted. * A second public call was taken with the terms of reference adjusted. * A contract was signed on May 24, 2020
Outputs | Number of people trained on the use and maintenance of the WHS | 0 | 0 | 100 people trained on the use and maintenance of the WHS, of which at least 50% will include women. (number of beneficiaries: core impact indicator)
Outputs | Technical document developed and adopted by the Ministry of Environment | 0 | 0 | 1 technical document produced and adopted by the Ministry of Environment for reference for future replication of this WHS model.
Outputs | Number of farms with agroforestry projects established | Number of farms with climate smart production systems (and the number of people that benefits from them) is estimated at 0; nonetheless, to confirm this assumption, an overall initial baseline survey has been programmed at the beginning of the program implelmenteation. | 0 | At least 20 farms with climate smart agroforestry (shaded coffee mainly) projects succesfully established | * Negotiations are currently under way with the proponent who obtained the highest score in the proposal evaluation.
Outputs | Number of people in targeted communities that benefit from climate-smart agroforestry systems implemented | Number of farms with climate smart production systems (and the number of people that benefits from them) is estimated at 0; nonetheless, to confirm this assumption, an overall initial baseline survey has been programmed at the beginning of the program implelmenteation (and for which funds have been requested accordingly in the M&E budget) | 0 | At least 100 people, of which 50% are women, benefit from the climate smart agroforestry systems implemented at the Caisan River Sub-watershed in CVRW
Outputs | Lineal meters of riparian reforestation successfully established | TBD (exact area of existing riparian forest in targeted communities will be determined in the general baseline survey). | 0 | 6000 lineal meters of riparian reforestation successfully established
Outputs | Diagnostic for irrigation needs completed | 0 | 0 | One irrigation needs diagnostic for Cerro Punta and Divalá production areas | * A public call was made, which was left deserted. * A call was made through a short list. * It is currently at the stage of receiving proposals.
Outputs | Number of hectares of climate resilient irrigation systems established | 0 | 0 | At least 75 hectares of climate resilient irriguation systems at Cerro Punta and Divalá
Outputs | Number of farmers that received technical assistance | 0 | 0 | 40 farmers (gender dissagregated target will be determined after baseline survey is completed; it is anticipated that the majority of local rice farmers are men).
Outputs | Document of the analysis of water footprint for rice crops | 0 | 0 | One technical document on rice crop water footprint
Outputs | Number of farms with FMP (farm management plans) | 0 | 112 farms (of approximately 2.5 hectares each with FMP) | 40 farms of approximately 5 hectares each with FMP
Outputs | Number of hectares with climate resilient agroforestry and soil conservation systems established | Number of hectares with climate resilient shaded coffee agroforestry systems (and the number of people that benefit from them) is estimated at 0; nonetheless, to confirm this assumption, an overall initial baseline survey has been programmed at the beginning of the program implementation (and for which funds have been requested accordingly in the M&E budget) | 0 | 200 hectares of agroforestry schemes (mainly shaded coffee with beans) | *Agroforestry systems are currently being established.
Outputs | Number of people that benefits from the climate resilient shaded coffee agroforestry systems established | Number of hectares with climate resilient shaded coffee agroforestry systems (and the number of people that benefit from them) is estimated at 0; nonetheless, to confirm this assumption, an overall initial baseline survey has been programmed at the beginning of the program implementation (and for which funds have been requested accordingly in the M&E budget) | 480 | At least 200 people benefit from the climate reslilient shaded coffee systems (gender dissagreggated figure will be determined once the baseline survey is completed, and in full compliance with Gender Policy of the Adaptation Fund | *Agroforestry systems are being established. *Currently 480 people benefit from the training and technical assistance (producer partners and family members); 388 men and 92 women.
Outputs | Percentage of income increase in targeted population households (40 farms) | TBD in targeted population households (income in targeted beneficiaries will be determined by a specific socioeconomic survey to be conducted as part of the overall initial baseline survey programmed at the beginning of the program implementation -and for which funds have been requested accordingly in the M&E budget) | 0 | Percentage of income increase by source in targeted population households
Outputs | Number of people trained on establishment and management of orchid and naranjilla crops | TBD in the participatory communitty rapid assessment included as part of the project (although currently there are 14 naranjilla producers and 4 orchid producers) | 0 | 14 naranjilla producers and 4 orchid producers (100% women), fully trained on crops management and commercialization | * The project is in the phase of signing contract with the executing agency, which is scheduled for the end of this period.
Outputs | Number of business plans designed | 0 | 0 | 2 business plans designed and in operation (one for naranjilla and one for orchids)
Outputs | Marketing agreements with potential buyers | TBD in the participatory communitty rapid assessment included as part of the project | 0 | At least 2 market agreements established for naranjilla and 2 market agreements for orchids
Outputs | Number of hectares with sustainable catlle ranching models | 0 (during consultation process it was confirmed that there are 1831 hectares of unsustainable cattle ranching farms) | 0 | 600 hectares with sustainable catlle ranching models established and in operation | * 120 management plans with good practices for adaptation to climate change are being implemented (600 hectares under silvopastoral systems -livestock-).
Outputs | Number of FMP developed | 0 | 120 farm management plans | 120 farm management plans (of around 5 hectares each)
Outputs | Number of people that benefits from the climate resilient catlle ranching projects | Number of people that benefit from the sustainable cattle ranching projects is estimated at 0; nonetheless, to confirm this assumption, an overall initial baseline survey has been programmed at the beginning of the program implementation (and for which funds have been requested accordingly in the M&E budget) | 330 | At least 600 people benefit from the climate reslilient and sustainable cattle ranching projects (10% women) | * Currently 330 people (producer partners and their family members) benefit from training and technical assistance from the project.
Outputs | Study and technical recommendations on climate financial products designed | 0 | 0 | 1 study-review on current credit products offered to agriculture and energy sectors; including technical recommendations on climate financing instruments | • Scheduled for the last project period.
Outputs | Number of business plans developed to establish and operate renewable energy projects, including the correspondent FMP | 0 | 0 | 4 business plans for small scale renewable generation projects (hydro, solar, etc
Outputs | Number of farmers that receive technical assistance on access financing sources for climate change adaptation activities | 0 | 0 | 16 farmers, 8 from each of the two target watersheds (gender dissagreggated target will be determined once the baseline survey is completed, ensuring full compliance with Gender Policy of the Adaptation Fund)
Outputs | Number of microfinance institutions mapping document developed | 0 | 0 | 1 document with microfinance institutions mapping on both watersheds
Outputs | Number of microfinance institutions interested/willing to participate in training on MEbA | 0 | 0 | At least 2 microfinance institutions and/or cooperatives
Outputs | Number of microfinance institutions trained to design climate change oriented finance products | 0 | 0 | 2 trained microfinance institutions and/or cooperatives offer two finance products with MEba model
Outputs | Number of microfinance programmes with MFI and cooperatives designed implemented | 0 | 0 | At least 2 microfinance programmes offered by MIFs and/or cooperatives
Outcome | No. of water security instruments developed for implementation by districts and the national level that respond to climate-induced challenges | 0 | 6 | 8 instruments developed and adopted by incumbent regional/national institutions to respond to new conditions resulting from climate variability and change:
An updated SMRW Management Plan, with the addition of the climate change dimension
One vulnerability analysis document completed for the CHVRW
Two technical criteria document developed for granting water use concessions and permits for two watersheds
One technical recommendations document delivered to responsible parties for adjustments needed to improve hydrological cycle at both watersheds
Two water security disctrict plans designed
National map for agriculture and livestock production developed
Outcome | No. of people benefiting from management instruments designed and approved by incumbent authorities, which allow improved and sustainable access to water resources in a changing climate scenario | Number of people that currently benefit from management instruments designed and approved by incumbent authorities, which allow improved and sustainable access to water resources in a changing climate scenario is estimated at 0 | 0 | At least 114,000 people. Include population from target communities, watersheds (combined population of the CHVRW and SMRW)
Outputs | Update of the document of SMRW management plan | 0 | 0 | Updated Santa María River Watershed (SMRW) Management Plan including the climate change’s dimension | * Final document of the "Diagnosis of the Santa María River Hydrographic Watershed " approved by the executing entity. * Document "Climate Change Scenarios and Analysis of Social and Environmental Vulnerability and their Correlations" prepared and in the validation phase with the Santa María River HydrographicWatershed Committee.
Outputs | Number of people that participated in the update consultation process | 0 | 183 | At least 200 people participated in the process, ensuring participation of 50% men and 50% women. | 183 (122 men y 61women)
Outputs | Vulnerability analysis document completed for the CHVRW | 0 | 1 | Updated- improved CHVRW Management Plan, including analysis of the climate change dimension | * Approved the Climatic Vulnerability Study and Design of Adaptation Measures for the Chiriquí Viejo River Watershed.
Outputs | Number of people that participated in the update consultation process | 0 | 120 | At least 200 people participated in the process, ensuring participation of 50% men and 50% women. | * The Chiriquí Viejo River Watershed Committee (made up of government agencies and civil society), was consulted; working groups were held with representatives of civil society with the participation of 104 men and 94 women.
Outputs | Technical criteria document developed for granting water use concessions and permits for both watersheds | 0 | 2 | 2 technical criteria document for granting water use concessions and permits (one for each watershed) developed and validated with the Ministry of Environment and the Ministry of Agriculture | * Two (2) water balance and environmental flow studies were prepared and approved: for the Caisán (Chiriquí Viejo River watershed) and Gallito (Santa María River whatershed).
Outputs | Number of awareness meetings with local population and responsible parties in the process of granting water use permits | 0 | 3 | 10 awareness meetings completed with local population and responsible parties in the process of granting water use permits | * 3 workshops held for the executing agency's regional technicians, responsible for the process of granting water permits. * There are plans to hold workshops to explain and raise awareness about this issue, once the Ministerial Executive Decree for the technical document on Water Concession Permits is in place.
Outputs | Number of people that participated in the process of developing the technical document with criteria for granting water use permits for agriculture and power generation | 0 | 45 | 80 people are consulted between MiAmbiente and MIDA technicians at the national level and the Chiriquí Viejo and Santa María River Basin Committee (made up of government institutions, NGOs, local governments) | * MiAmbiente and MIDA technicians at the national level and the Chiriqui Viejo and Santa Maria River Basin Committee (made up of government agencies and civil society) were consulted; and working groups were held with civil society representatives.
Outputs | Technical recommendations document delivered to responsible parties for adjustments needed to improve hydrological cycle at both watersheds | 0 | 1 | 1 technical document with recommendations for improving or restoring hydrological cycle at both watersheds, delivered to and validated by the Ministry of Environment and the Ministry of Agriculture | • Approved the technical document "Water Concession Permits" at the national level. • Internal coordination among the directorates of the executing entity MI Ambiente to raise the document to a ministerial Executive Decree.
Outputs | Number of water security disctrict plans designed | 0 | 2 | 2 hydrological security district plans designed and adopted by 2 districts of target watersheds | • Two district water safety plans have been approved: Tierras Alta (Chiriquí Viejo River Watershed) and SanteFé (Santa María River Watershed).
Outputs | National map for agriculture and livestock production developed | 0 | 0 | 1 national map for agriculture and livestock production developed, adopted and widely publicated by the Ministry of Agriculture Development (MIDA) | MIDA (Executing Entity) is in charge of setting up the team that will be responsible of achieving this product.
Outputs | A National System for Climate Data designed and in operation | 0 | 0 | 1 National System of 45 stations for Climate Data, with upgraded ETESA´s network for recording hydro-agro meteorological information from hydrographic watersheds | • The national system is being strengthened with the installation of the agro-meteorological and hydrological satellite stations.
Outputs | Number and type of targeted institutions with increased capacity to minimize exposure to climate variability risks | 1 | 0 | 4 institutions (ETESA, MiAmbiente, MIDA, SINAPROC) with access to information for decision making to recuce national exposure to climate variability risks
Outputs | Number of new stations installed | 72 | 30 agrometeorological stations y 3 hydrological stations) | 45 automatic stations installed (34 new and 11 special sensors agrometeorological) | • The number of stations to be installed was reduced because they were more expensive than budgeted. • Thirty-eight new automatic stations will be installed and 11 stations will be upgraded with the installation of special sensors. • Delay in the installation of the automatic agro-meteorological stations by the contractor, due to the closure for total quarantine as result of the COVID 19 Pandemic. • Installation of 22 agro-meteorological stations. 10 were accepted by the Executing Entity ETESA and the transmission to the central station of ETESA was verified, 12 stations pending of verification of ETESA. • Installation of the 4 hydrological stations; 3 stations successfully stations transmit data to the ETESA's central station.
Outputs | Number of EWS for floods/droughts fully operational | One non-operational EWS for floods at the CHVRW and 0 EWS operational at the SMRW | 0 | Two fully operational EWS in target watersheds (one of floods and one for floods-droghts). Core impact indicator | * No Cooperation Agreement has been signed with SINAPROC. * The NIE and the designated national authority have taken steps to expedite this process. * SINAPROP has indicated that the document is under review.
Outputs | Number of communities included in the CHVRW early warning system | Exact number TBD by initial survey | 0 | TBD, but at least 10 communities from CHVRW watershed
Outputs | Number of people trained and with built capacitities on the use of the EWS | 0 | 0 | At least 100 people trained on how to reduce risks to extreme weather events by understanting/using the EWS
Output | Number of staff trained to respond to and mitigate impacts of climate related events | 0 | 0 | At least 20 staff members trained to respond to and mitigate impacts of climate related events
Output | Number of communities included in the SMRW early warning system | Exact number TBD by initial survey |  | At least 10 communities from SMRW watershed | * No Cooperation Agreement has been signed with SINAPROC. * The NIE and the designated national authority have taken steps to expedite this process. * SINAPROP has indicated that the document is under review.
Output | Number of people trained and with built capacitities on the use of the EWS | 0 | 0 | At least 100 people trained on how to reduce risks to extreme weather events by understanting/using the EWS
Output | Number of staff trained to respond to and mitigate impacts of climate related events | 0 | 0 | At least 20 staff members trained to respond to and mitigate impacts of climate related events
Output | Joint node of climatic information established between ETESA and MIDA | 0 | 0 | 1 operational joint node of climate information established between ETESA and MIDA, generating climate change information | * Rehabilitated the office of the National System of Agroclimatic and Statistical Data. * A total of 19 agroclimatic tables have been held with the participation of technicians from the agricultural sector and producers to analyze climate information and its usefulness for decision-making in the face of climate change scenarios in our productive systems. * Agroclimatic bulletins prepared and distributed to disseminate recommendations to producers and decision makers.
Output | Number of people trained and with built capacitities on the management of the joint node | 0 | 0 | At least 20 staff trained and with capacities built to manage joint node and information on climate change | * The training activities have been rescheduled. * Adjustments are being made to the methodology due to the national emergency situation for the COVID Pandemic. * The executing entity selects (based on the established criteria) the technicians who will be trained.
Output | Tool designed to assess efectiveness of climate change adaptation | 0 | 0 | 1 tool designed to assess efectiveness of climate change adaptation measures at national level | * The Executing Entity MiAmbiente presented the terms of reference for this consultancy. * The public call for proposals is coordinated.
Output | Number of workshops with public and nongovernmental stakeholders on the tool design | 0 | 0 | At least 3 workshops with public and nongovernmental stakeholders on the tool design
Output | Number of people from relevant stakeholders trained and with built capacities to use the assessment tool | 0 | 0 | At least 80 people trained and with built capacities to use the assessment tool
Output | Number of training sessions held | 0 | 15 | 2 working sessions with the technical team and key Implementing partners | * 3 training sessions with the technical team * 10 working sessions with key implementing partners.
Output | Pertentage of project staff trained | 0 | 70% | 100% | * From mid 2019, as a result of changes in government, new staff are appointed to the implementing entities. * Induction made to new personnel.
Output | Percentage of key implementing partners trained | 0 | 50% | 100% | • Trainings to key actors of the program have been carried out.
Output | Number of inception workshops with local and national stakeholders to present the approved programme; revisit programme rationale, scope, define shared visions and operational arrangements for programme implementation. | 0 | 4 | At least 2 local workshops, one for each watershed with local stakeholders; and 1 national workshop with government and civil society stakeholders to present the Programme, identify sinergies with other ongoing adaptation efforts/initiatives and define operational and coordination aspects | * 2 local workshops for the presentation of the program held in the priority watershed * 2 national workshops for the presentation of the program held in the priority watershed.
Output | Number of people that participated during socialization of SMRW and CHVRW vulnerability analyses | 0 | 0 | At least 2,000 people in both target watersheds | * The socialization of the Vulnerability Analysis of the Chiriqui Viejo River Basin, through the virtual methodology due to the restrictions generated by the COVID-19 pandemic, is coordinated with the executing entity Mi Ambiente.
Output | Number of people trained on climate modelling and future scenarios impacting food-energy generation activities | 0 | 46 | At least 45 people trained on climate modelling and future scenarios impacting food-energy generation activities | * 46 people (14 women and 32 men).
Output | Number of people trained on adaptation to climate change and the role of ecosystem services | 0 | 42 | At least 45 people trained on adaptation to climate change and the role of ecosystem services | * 42 people (23 women and 19 men).
Output | Number of people trained on participatory and integrated watershed management emphasizing conflict management skills | 0 | 44 | At least 40 people trained on participatory and integrated watershed management emphasizing conflict management skills | * 44 people (27 women and 17 men.
Output | Number of people trained on ecosystem-based adaptation at marine-coastal zones | 0 | 0 | At least 20 people trained on ecosystem-based adaptation at marine-coastal zones | * These trainings were rescheduled for the first months of 2021, due to the health restrictions caused by the COVID pandemic, which prevent carrying out group activities in person. * The training involves practice in coastal areas.
Output | Technical and practical document (mapping and analysis of projects / initiatives undertaken) designed and made avaible in print and digital formats | 0 | 0 | 1 document produced in print (500 units) and digital formats, broadly disseminated nationwide | • In the process of negotiation with the consultant selected to sign the contract.
Output | Number of news outlets in the local press and media that have covered this dissemination of experiences | 0 | 0 | At least 6 news outlets in the local press and media that have covered this dissemination of experiences
Output | Number of people who attended workshops at each province of the country | 0 | 0 | At least 500 people (50 in each province)
Output | Systematization document developed | 0 | 0 | 1 systematization document produced about experiences from the program
Output | Number of people reached by the communication strategy throughout the program | 0 | 1245 41,522 | 2000 direct beneficiaries of the programme 116,281 indirect beneficiaries of the programme | 1245 capacity building 41,522 through social media
Output | Number of visits per month of the portal | 0 | 0 | TBD after the completion of product 4.1.a | * The format of the portal has been changed to make it more user-friendly. * Program information is being entered. * The portal will be launched in August 2020.
Output | Percentage of favorable comments on usefulness of the portal | 0 | 0 | TBD after the completion of product 4.1.a
Output | Number of knowledge products generated and made available to different users by the program | 0 | 0 | Not less than 20 products throughout the complete program execution
Output | Number of people reached by knowledge products from the program | TBD | 0 | TBD after the completion of product 4.1.a
Output | Number of people who benefit from the training on the use of the portal | 0 | 0 | At least 500 people trained on the use of the portal | * Training has not yet taken place, as indicated, the launch is scheduled for August.
Output | Advisory technical committee established to orient the knowledge management process | 0 | 1 | 1 Advisory technical committee established and operational to orient the knowledge management process | * On August 16, 2019, the National Committee on Climate Change created a Knowledge Management Committee,which is composed of members from the Technological University of Panama, the National University of Panama, the Ministry of Education and the National Secretariat of Science and Technology.
Output | Number of decisions made and implemented from advisory technical committee meetings | 0 | 0 | TBD after the completion of product 4.1.a. Rationale.
Output | Number of people trained from technical exchanges | 0 | 0 | At least 100 people trained in exchange activities at the local level (number of beneficiaries: core impact indicator) | * Activities are rescheduled for the next period.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Positive aspects: * Selecting NGOs at the level of project executors, with community personnel or knowledgeable of the areas of intervention, generates greater confidence of the actors in the area and more effective results. *.Selecting NGOs with high experience in the management of agro-environmental projects, allows generating more dynamic and effective work mechanisms in the implementation phase of each intervention. * The active participation of key actors (men, women, and youth) in both planning and execution is decisive for achieving more effective results. * The "learning by doing" methodology is valuable to help reinforce learning and multiply knowledge among producers of both sexes. Negative aspects: * Personnel rotation of the executing entities generates setbacks in activities contemplated in the Work Plan. * The scarce personnel assigned to the different projects of the EE (government institution), and who are not assigned 100% to the program, since they have to share their time with other assignments, prevent them from fulfilling their functions in the program in a timely manner. * Delays in the selection of work teams at the watershed level, slow down plan execution. * The change of Government generated a high degree of rotation in the EE-MIDA staff, which slowed down the implementation phase of the program. * The lack of internal disclosure of the program affected the level of appropriation by EE-MIDA's local technical staff.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | * The low effectiveness of technical staff in charge of the adaptation programme in the EE-MIDA, in the initial period of the programme. * The previous government administration did not comply with the work plan, thus creating an overload of commitments for the current implementation period. * The current measures that have been taken to reduce delays in the EE-MIDA are the training of a qualified and responsible multidisciplinary technical working team; the establishment of strategies for the constant monitoring of the evolution of the programme in the EE-MIDA; the increase of the internal linking of the programme, which translates into a greater collaboration of multiple national directions towards the objectives of the programme. * The establishment of the FA Portal has been affected by the change in design of the website. * Delay in the delivery of information by implementing agencies. This situation is being corrected through written requests to each entity to obtain the information and the participation of the NIE in the process of acquiring the information, as well as the assignment of personnel from the Communications Department of MiAmbiente for the adjustments of the website . * There has been a delay in the delivery of consultancy and project reports by the executing entities, NGOs or consultancy companies generated by the health restrictions and the total quarantine of the country, due to the COVID Pandemic, which implies that adjustments have had to be made in the timetables and methodologies. * The health situation as of COVID 19 has generated a delay in the execution of the group's activities (training, technical assistance, validations with the communities, etc.), which has led to the reinvention of alternative actions to comply virtually with these planned activities. Communication via e-mail, telephone and chat has been implemented, which has contributed to reducing delays. * WhatsApp groups were created (for those who do not have access to the Internet) between the project team and the producer partners, which has made it possible to provide information on the delivery of inputs, tools and equipment, technical assistance (for example, how to make the drill bit*** traps with recycled plastic bottles), how to do good soil conservation practices (construction of dead barriers), organic fertilizer production, farm management consultations, among others, are answered. * Some of the technical personnel provide assistance in the field, strictly following the sanitary protocols established due to the COVID pandemic. *The NIE has increased constant communication with the executing agencies to determine safe and timely actions to achieve the Programme's objective and indicators. *Addenda to contracts have been processed, due to delays generated by the COVID pandemic.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | • Adjustments or modifications to this PPR have been suggested for some indicators of the results framework, allowing the establishment of achievable parameters more in line with the existing budget and the timeframe to achieve them (the modifications have their respective justification in the indicator matrix; for example related to water harvesting projects, agroforestry in the Chiriqui Viejo River Basin and irrigation) • As the budget to cover the salaries of the EE-MIDA coordination team calculated in the project design was very limited, budgetary transfers are being made to increase the amounts for this item..
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | • The projects under implementation are meeting the parameters of social and environmental safeguards, and have not created risks to the programme. For Component 1 projects, the Environmental and Social Management Plan is prepared and followed
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | • Participation Plans with a gender focus have been developed. • The participation of women in the project has been promoted. • Prior to the implementation of project activities, women are consulted about the best options of days and times for them, taking into account their triple role, so that they can organize and participate in the events. The aim is for the participating women to increase their knowledge on the subject of climate change, to understand the importance of good practices in adapting to CC and to put them into practice. • There are women promoters in the projects in the area, who facilitate the work with women. • Women's participation has been promoted in the presentation of proposals to the calls made by the programme. • Strengthening women's technical capacities in the area of climate change facilitates their empowerment in the communities. .
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | We are in the process of implementing climate adaptation measures. When you have more information, you can answer the question.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | We are in the process of implementing climate adaptation measures. When you have more information, you can answer the question.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | We are in the process of implementing climate adaptation measures. When you have more information, you can answer the question.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Projects are beginning to implement good adaptation practices and it is noted that producer partners (as) are concerned about climate change. In this second year, we see the availability of continuing to apply good practices once the project is completed. In addition, producers in the region are waiting to see results to replicate good practices. As for the agroclimatic tables other regions have requested to be included to start with the process of the tables.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | • Program partners are benefiting from the program in several ways: • Capacity building (sensitizing and training producers on the causes and effects of climate change and how they can contribute through the implementation of agroforestry and soil conservation projects for adaptation and mitigation, in order to conserve their water source) • Better management of available natural resources • Reduction of agro-climatic risks, • Supply of production inputs, • Relevant information generated in the technical documents for better decision making. • Similarly, it is expected that income generation for the families of the producer partners will be achieved.
What measures are/have been put in place to ensure sustainability of the project/program results? | • Producers make counterpart contributions either in wages or inputs, which is key factor for project appropriation. • Publicize the project to the main companies and cooperatives in the region in order to achieve the future purchase of coffee, livestock and other items generated by the program. • Mitigate the incidence of pests and diseases through ethological control of the coffee berry borer (broca). • Adequate selection of producers based on objectively verifiable and clearly established beneficiaries' evaluation and selection criteria.
What measures are being/could have been put in place to improve project/program results? | • Support in interinstitutional coordination to expedite procedures required in projects. Reviews in conjunction with the executing entities of the products that are generated in consultancies and projects to guide in the achievement of the results.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | • The information that is being generated by the projects or consultancies (agro-climatic bulletins, good practice guides, and others) makes it possible to determine with greater certainty the parameters of food production, thus reducing the consequences that climatic variations generate on crops. • Agroclimatic bulletins are published, information on the behavior of climate variables by region is shared, technical information is available on websites, telephone messages are posted on social networks (instagram, facebook, you tube) and others. • Information from the Participation Plan with a gender perspective, environmental and social safeguards plan, socio-economic baseline survey, training plan, farm management plans, perception survey on causes and effects of climate change applied at the beginning of the projects has been used. • A periodic photographic record of the project is kept, which includes training; seedling production and planting activities, among others
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | • Existing information/data/knowledge has been made available to stakeholders. • Brochures on the courses offered are given, • Information is shared on social networks and by mobile phone (WhatsApp).
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | • The products generated are being uploaded to the website of the Adaptation Program: https://adaptacion.miambiente.gob.pa. The website is scheduled to launch in August 2020.
If learning objectives have been established, have they been met? Please describe. | • Projects have a knowledge management component that develops as projects or consultancies are carried out. • Knowledge products focusing on climate change adaptation have been developed and serve as a basis for replication in other projects, such as: gender participation plan, environmental and social safeguards plan, training plan, agricultural management plans, socio-economic and agricultural characterization report, population perception report on the effects and causes of climate change, • In addition, courses have been held: climate modelling with a focus on future scenarios affecting food-generation activities, adaptation to climate change, the role of ecosystem services, participatory and integrated watershed management, among others.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | • To date, there have been no problems with accessing or retrieving existing information (data or knowledge) that is relevant to the project. • Once the web page is launched, all the documents generated in the program will be available through such page.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | • Learning goals have contributed to greater impact by enabling local knowledge creation and replication of this impact at other levels. Learning objectives are contributing to capacity building at the local level through organizations implementing Component 1 projects and building capacities in organizations and NGOs in analysis and processing of information for different sectors and strengthening on water resource management by incorporating climate change adaptation approach.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | • The agroclimatic tables involving technicians and producers in the analysis and recommendations for their agricultural and livestock calendar is an innovative practice in Panama
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization. | • The NIE in coordination with the DNA (MiAmbiente) are looking for other initiatives.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | Fundación Natura
Type of implementing entity | NIE
Country | Panama
Region | Latin America and Caribbean
Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 116281 | 2000 | 114281 | Total | 42317 | 795 | 41522 | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries | 30% | 40% | 30% | % of female beneficiaries | 0.5% | 27% |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0% | 0.6% | 0% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Multi-sector | Regional | 1: No plans conducted or updated | 8 | Multi-sector | Regional | 3: Risk and vulnterability assessments completed or updated | 8 | Multi-sector | Regional | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 2 | 2: Monitoring and warning service | Geographical coverage | Local | 2 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 2 |  |  | Number of municipalities | 2 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 1 |  |  | Number of municipalities | 1 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 20 | Multi-sector | 2: Low capacity | Total | 60 | Multi-sector | 3: Medium capacity | Total | 0 | Multi-sector | 1: No capacity | Total
|  | % of female targeted | 30% |  |  | % of female targeted | 20% |  |  | % of female targeted | 0% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 60 | 10% | Public |  | 0 | 0% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 3: Medium capacity | Public | National | Multi-sector | 3: Medium capacity | Public | National | Multi-sector | 1: No capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 1 | National | Other | 3: Medium capacity | 1 | National | Other | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
[6 empty] | 70% |  | Food security |  | 5% |  | Food security
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 2552 | 15% | 4: Mostly aware |  | 5% | 1% | 3: Partially aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
[6 empty] | 8 | Technical guidelines | Regional |  | 6 | Technical guidelines | National
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
[6 empty] | Food security | Local | 3: Moderately responsive (Some defined elements) |  | Food security | Local | 2: Partially responsive (Lacks most elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
[6 empty] | 1 | Community |  | Multi-sector | 1 | Community |  | Multi-sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 50 | 10% | 2: Limited improvement |  | 328 | 24% | 3: Moderate improvement |  | 180 | 2% | 2: Limited improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 40 | 5% | From 0 to 0.5% | Cultivation | 60 | 10% | From 1% to 5% | Cultivation | 0 | 0% | From 0 to 0.5% | Cultivation
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 30 | 0% | From 0 to 0.5% | Livestock production | 120 | 2% | From 5% to 10% | Livestock production | 120 | 2% | From 0 to 0.5% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 34 | 3% | From 0 to 0.5% | Agriculture | 148 | 30% | From 5% to 10% | Agriculture | 60 | 4% | From 0 to 0.5% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Social capital | Food security | Capacity development | 1 | Social capital | Food security | Capacity development | 1 | Social capital | Food security | Capacity development
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 60 | Cultivation |  | 140 | 60 | Cultivation |  | 200 | 60 | Cultivation |  | 140
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 120 | Livestock production |  | 250 | 120 | Livestock production |  | 300 | 120 | Livestock production |  | 250
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 148 | Agriculture |  | 100 | 148 | Agriculture |  | 160 | 148 | Agriculture |  | 100
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
Note on H25: Vilna Cuéllar: meta final
Note on L25: Vilna Cuéllar: progreso o avance a medio termino
Note on L30: Vilna Cuéllar: 6 documentos entregados
Note on I54: Vilna Cuéllar: 280 personas 60 técnico
Note on M54: Vilna Cuéllar: Aún no inician el proyecto
Note on O54: Vilna Cuéllar: No ha iniciado el proyecto
Note on M55: Vilna Cuéllar: no ha iniciado el proyecto
Note on O59: Vilna Cuéllar: No ha iniciado el proyecto
Note on H66: Vilna Cuéllar: directo + indirecto
Note on I71: Vilna Cuéllar: Analisis de vulnerabilidad CHRSM y CHRChV Consecionesde agua Planes distritales Sta. Fé y Tierra Altas Mapa Nal Balances hídricos CHRSM y CHRChV
Note on J71: Vilna Cuéllar: Hay 2 a escala Nal.
Note on O120: Vilna Cuéllar: aún no hay cambios
Note on O122: Vilna Cuéllar: Aún no hay cambios
Note on O124: Vilna Cuéllar: Aún no hay cambios