## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | October, 2017- May, 2019
| Project Title: | Adapting To Climate Change Through Integrated Water Management in Panama
INTEGRATED WATER MANAGEMENT IN PANAMA
| Project Summary: | The overall objective of this programme is to establish climate resilience water management to enhance food and energy security at the national level, including an integrated and community based approach in the Chiriqui Viejo and Santa Maria Watersheds. Specifically, the programme will be addressing the following objectives: a) Increasing climate change and variability adaptation capacity in agriculture, livestock and energy production sectors; b) establishing climate resilient water management instruments with integrated and community based approach; c) strengthening local national capacity for monitoring and decision making to reduce and respond to risks associated to climate change; and d) raising awareness and establish a knowledge exchange platform to respond to and to reduce impacts of climate related events.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Fundación para la Conservación de los Recursos Naturales (NATURA) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | NIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Panamá | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Chiriqui Viejo and Santa Maria Watersheds | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | octuber, 2016
IE-AFB Agreement Signature Date: |  | June 20, 2017 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | June 5, 2018 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned):
| Terminal Evaluation Date: | June 5, 2021
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | In the first year, the documents elaborated for the project are as follows: 1- Inception report about the first workshop 2-Operative plan 3- Inception article "Adapting To Climate Change Through Integrated Water Management in Panama" in Natura Panamá web page: http://www.naturapanama.org/fondo-de-adaptacion/ | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Vilna Cuéllar | Dominican Republic
| Email: | vcuellar@naturapanama.org | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Emilio Sempris | Equatoral Guinea
| Email: | esempris@miambiente.gob.pa | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Rosa Montañez | Fiji
| Email: | rmontañez@naturapanama.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Luis Carles - Ministerio de Desarrollo Agropecuario | Georgia
| Email: | lcarles@mida.gob.pa | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | René López - Ministerio de Ambiente | Grenada
| Email: | rlopez@miambiente.gob.pa | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Diego Gonzalez - Empresa de Transmisión Electrica, S.A. | Guyana
| Email: | dagonzalez@hidromet.com.pa | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
FUNDACIÓN NATURA
FONDO DE ADAPTACIÓN
Financial information: cumulative from project start to [may 31,2019]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
| Estimated cumulative total disbursement as of [2017] | Total: US$701,396.64 Costos Directos: US$575,290.45 EE:US$126,106.19
Add any comments on AF Grant Funds. (word limit=200)
| INVESTMENT INCOME | 24554.47
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
| List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
|  | 1.1 Concrete adaptation measures implemented for household water security | 0
|  | 1.2 Pilot climate smart farming projects implemented | 0
|  | 1.3 Pilot diversified financing and income source models implemented in vulnerable population areas | 0
|  | 1.4 Concrete adaptation measures implemented for sustainable cattle ranching | 0
|  | 1.5 Enhanced sectorial support through climate financing instruments | 0
|  | 2.1 Analysis for climate change vulnerability done in prioritized areas at the Chiriqui Viejo and Santa Maria River Watersheds | 52000
|  | 2.2 Developed technical criteria for granting water use concessions and permits in order to reduce/avoid conflicts among users and increase ecosystem resilience in response to climate-induced stress | 0
|  | 3.1 Designed and in operation the National System for Climate Data (NSCD), by upgrading ETESA´s existing network for recording climatic information from hydrographic watersheds | 387400
|  | 3.2 Established an early warning system to identify in advance, the necessary measures in case of hydro-climatic events that could affect food production and power generation | 0
|  | 3.3 The NSCD interfaced and equiped with a joint node, with the Ministry of Agriculture Development, to generate and manage climatic information | 22375.33
|  | 3.4 Designed a monitoring and evaluation tool to assess effectiveness of climate change adaptation measures implemented by the program and national efforts | 0
|  | 4.1 Improved awareness of watersheds vulnerability and participation of population groups in adaptation measures | 16731.73
|  | 4.2 Strengthened professional capacities for the climate data analysis and processing, for different sectors involved | 39007.21
|  | 4.3 Strengthened professional capacities on water resources management by incorporating climate change adaptation approach | 44621.48
|  | 4.4 Systematized and disseminated experiences on climate changes adaptation, nationwide | 0
|  | 4.5 Portal for Climate Change Adaptation in Panama, implemented | 13154.7
|  | Executing Entities (EE) | 126106.19
|  | NIE - NATURA | 165651.14 |  | 575290.45
|  | TOTAL | 867047.78
PLANNED EXPENDITURE SCHEDULE
| List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Enumerar los resultados planificados y los costes proyectados correspondientes para el próximo período de notificación | 1.1 Concrete adaptation measures implemented for household water security | 60750 | 2021-06-01
|  | 1.2 Pilot climate smart farming projects implemented | 105907.15 | 2021-06-01
|  | 1.3 Pilot diversified financing and income source models implemented in vulnerable population areas | 345102.4967 | 2021-06-01
|  | 1.4 Concrete adaptation measures implemented for sustainable cattle ranching | 590714.45 | 2021-06-01
|  | 1.5 Enhanced sectorial support through climate financing instruments | 34400 | 2021-06-01
|  | 2.1 Analysis for climate change vulnerability done in prioritized areas at the Chiriqui Viejo and Santa Maria River Watersheds | 197998.2 | 2020-12-20
|  | 2.2 Developed technical criteria for granting water use concessions and permits in order to reduce/avoid conflicts among users and increase ecosystem resilience in response to climate-induced stress | 98800 | 2020-07-20
|  | 2.3 Increased hydrological security in prioritized areas at the Chiriquí Viejo and Santa María rivers watersheds, in line with advances of the National Plan for Water Security | 0 | 2021-06-01
|  | 3.1 Designed and in operation the National System for Climate Data (NSCD), by upgrading ETESA´s existing network for recording climatic information from hydrographic watersheds | 1549600 | 2020-03-20
|  | 3.2 Established an early warning system to identify in advance, the necessary measures in case of hydro-climatic events that could affect food production and power generation | 89200 | 2020-03-21
|  | 3.3 The NSCD interfaced and equiped with a joint node, with the Ministry of Agriculture Development, to generate and manage climatic information | 103017.59 | 2020-06-21
|  | 3.4 Designed a monitoring and evaluation tool to assess effectiveness of climate change adaptation measures implemented by the program and national efforts | 44000 | 2020-10-20
|  | 4.1 Improved awareness of watersheds vulnerability and participation of population groups in adaptation measures | 12710 | 2020-05-20
|  | 4.2 Strengthened professional capacities for the climate data analysis and processing, for different sectors involved | 67079.62 | 2020-04-20
|  | 4.3 Strengthened professional capacities on water resources management by incorporating climate change adaptation approach | 699.4 | febreo 20
|  | 4.4 Systematized and disseminated experiences on climate changes adaptation, nationwide | 14285.7143 | abril 21
|  | 4.5 Portal for Climate Change Adaptation in Panama, implemented | 40174.9 | 2021-06-21
|  | EE FEE | 147000 | 2020-06-21
|  | NIE FEE | 170000 | 2020-06-21
|  | TOTAL | 3671439.521
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
| How much of the total co-financing as committed in the Project Document has actually been realized? | No funding was stipulated. However, the executing entities will file in the next period
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Note on E47: Vilna Cuéllar: pendiente mapa zonificación marzo 21

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
E-1 Could climate variability affect the production cycle of the project (eg. change of season or increased rainfall, extended dry season) and therefore the achievement of the expected quality, quantity and time? For example, would tree species to be planted be suffering an alteration in the project calendar (production of seedlings, planting date, and survival rate after planted?) Would rice crops be suffering for lack of water to allow expected yields? | MIDDLE | the projects in field, are starting, therefore we are doing verifications about the schedules of the programs to avoid negative in impacts in the production cycle (planting dates and quantities) (The organization will plant the seedlings as far as weather conditions permit and next year, the rest of the scheduled seedlings will be sown)
E-2. Could the adverse weather conditions affect the schedule for installing i) water harvest systems, ii) hydro-agro meteorological stations, iii) EWS? | LOW | we have choose the most vulnerable areas to start the instalation process , before the rainy temporate began. while the calls for water harvesting projects and early warning systems have not been initiated, so that the terms of reference will take measures not to affect their execution.
E-3. Are infrastructure elements (named in E-2) in zones susceptible to seasonal flooding or landslides, flooding rivers or other environmental phenomena that may affect the works? | MIDDLE | The projects they have initiated do not include activities that can create significant environmental impacts. The call for the Early Warning System has been rescheduled, so that projects can be carried out in the dry season. | MIDDLE
E-4. Could the program generate adverse environmental impacts? | LOW | Follow-up is being carried out with the governing institutions and executing entities to monitor compliance with national specification standards | LOW
E-5. Are ​​the program areas susceptible to fire (whether caused by human or natural actions)? | MIDDLE | In the work plans of the production projects, educational measures aimed at key actors are incorporated to prevent fires caused by human actions.
E-6. Could the presence of pests in the program areas affect the production process? (i.e. agroforestry systems, agro-silvo pastoral systems, rice / orchids crops) | MIDDLE | A specific monitoring component for pests and diseases has been included for decision making using economic thresholds and agroclimatological variables. a, monitoring and percentage of incidents. Each farm will have, for its follow-up, the activities for the implementation of the plot monitoring and maintenance plan.
E-7. Could changes in the context (ex. large infrastructure projects, changing government policies, etc.) affect the relevance of the project to achieve the environmental goals set? | MIDDLE | In the inauguration of the new government is expected, to initiate coordination with the new government officials. In addition to meetings to present the program and its progress and defining new focal points. Technicians appointed to the program with the previous government are following up on projects that are in place but are waiting for the new authorities. The work is being done as best we can. New projects could not be convened because they must be approved by the focal point of executing entities and these have not yet been designated by the ministerial authorities.
E-8. The scale of the program is not appropriate in the context of the level of the threat and the pressure that is intended to address? | MIDDLE | Periodic meetings are held with the executing and charitable entities. to present the progress of the objectives and the relevance of the program
Type of Risk: Information
I-1. Is there scarce information that prevents Natura Foundation to mitigate or take the risks to which it is exposed in the program? | LOW | Progress of the program is presented to the Santamaria River and Chiriquí Viejo River Watershed Committees, which are made up of members of government institutions, municipalities and key actors
I-2. Is there insufficient information that prevents the implementing organizations to mitigate or take the risks to which it is exposed in the program? | MIDDLE | The Fund's website is being prepared, which will include a link with all the Program Executing Entities, in addition to projects, knowledge management section, (program actors, interviews, lessons learned), meetings are being held with the Committee of National Climate Change periodically, to present advances of the Fund.
I-3 Other information risks | LOW | Within the projects, budget lines have been designated for attendance at meetings, workshops, presentations, courses, etc. Of the beneficiary population.
Type of risk : Social
S-1. Is the program in an area of ​​actual or potential conflicts over natural (land, water) resource use? | HIGH | In the Terms of Reference of the projects, channels of communication with the governmental or local authorities (civil society, municipality, basin committee) have been included to present the progress of the program, coordinate actions and update on changes in the context of the region. the project does not intend to resolve existing potential conflicts between interested parties, the project will influate generating tools and information, creating a science-political interface, (technical information) for all participants on an equal access basis.
S-2. Are there tense situations between stakeholders needed to be solved to implement the program? | MIDDLE | The program is not intended to resolve existing or potential conflicts between interested parties.
S-3. Does the local workforce lack the necessary profile to implement the program? | MIDDLE | The technical capacities required for the execution of the projects have been included in the Terms of Reference of the projects and courses have been carried out on the personnel of the Executing Entities with the award of new projects (Environmental, social and gender safeguards, as well as Climate Change adaptation issues, specific Technical courses)
S-4. Is there an adequate level of training of involved individuals and communities to implement the program? Consider, skills training and the ability to react proactively to address the problems that can be encountered in implementing the program. | MIDDLE | Each component has capacity building plans for the beneficiaries as well as for the executing technicians. Courses are being carried out in component four, they are chosen through established participation criteria.
S-5. Are key actors or beneficiaries highly unlikely to continue in the process of the program in the short, medium and long term? | MIDDLE | Behavioral change will be induced throughout implementation of the different projects, toward climate change preparedness; as will generate better living conditions and higher income (thus creating interest to keep on such good practices)
S-6. Are there current or potential projects (hydropower, mining, roads, or other) that could transform the land use and thereby affect the participation of direct or indirect beneficiaries of the program? | LOW | In advance meetings with the basin committee, information is requested on possible projects to be implemented in the area.
S-7. Could there be social or behavioral patterns resulting from the presence of labor introduced through the projects (mentioned in S-6) that could transform land-use and bring problems to communities that may affect the program implementation and the intended transformation? | MIDDLE | No resulting behaviors that could transform land use and bring problems to communities have been detected, because we are starting with the projects in the field.
S-8. Is there a lack of leadership in the program areas, especially amongst the young people, that might affect the program? | MIDDLE | Currently, there has been no lack of leadership in the areas of the program, all projects have had criteria for selecting beneficiaries, to include the different audiences. (men, women, youth)
S-9. Are the communities and beneficiaries of the program indifferent to the problems that affect them in order to find solutions? | LOW | They have been included in the Terms of Reference of the field projects, reference surveys on the level of awareness in the population, on the impacts and climatic causes that affect them. It also includes the generation and distribution of information materials, to fill the gaps.
S-10. Can a lack of partners for the program (that can take a leadership role and mobilize action to create local cohesion and participation to the program and its processes), be possible? | LOW | The terms of reference included that executives' technicians have experience in the areas of the program, 2- the program progress presentations and coordination with the Santamaría and Río Chriquí Viejo river basin committees are being made. and executors have been requested to have staff or local technicians. to leave capacities built in the areas of incidence of the program.
S-11. Are there no conditions for the empowerment and leadership of communities, organizations and / or key individuals -with gender considerations- after completion of the processes provided from the Natura Foundation? | LOW | It is starting with the execution of projects; however, communities have an organizational basis and the program will create conditions for the empowerment and leadership of communities, organizations and/or key individuals - with gender considerations - for producer partners to continue their initiatives.
S-12. Is there a scarce inclusion of prior, free and informed stakeholders at the various stages of design or implementation of the program? | LOW | The program plan was developed based on different public policies and recommendations of key actors and different leaders of civil society, the program design included public calls to obtain opinions from interested groups
S-13. Is there any indigenous population in the area of program implementation that would require further efforts to ensure its proper participation? | LOW | There are no indigenous communities in the area of ​​project implementation.
S-14. Is there a potential lack of receptivity to the information and activities generated by the program due to absence of awareness, among the beneficiary institutions and stakeholders, about the climate related origin of the problem, instead of considering it is a result of deficient management of natural resources? | LOW | Based on the surveys carried out, necessary information will be distributed to key actors, as well as in alternative media such as: Radio, website and brochures
Type of Risk: Legal
L-1. Is the area of ​​the program suitable and free from conflicts over land tenure? Or it isn´t? | LOW | the risk is being mitigated by requesting the key actors participating in projects such as livestock and agroforestry, to present ownership verification documents, as well as the signing of contracts with executing entities that define the permits that the key actor must grant.
L-2. Could the lack of an environmental license to implement the program in any or all phases affect its performance? | MIDDLE | coordination meetings are being held with the Executing Entities, so that we can fulfill all the commitments regarding environmental licenses, and these, which have participated since the design of the program, are willing to collaborate. the payments corresponding to the executing entities will be made to the extent that all local permits and compliance regulations are complied with. The monitoring and evaluation system must include, through the implementation of the projects, any changes in the licensing and permit situations, as well as strategies to address the risks that may occur.
L-3. Are permits and / or required licences in the different phases of the program clearly identified? Can these not be obtained or fulfilled on schedule, and within the scope, and budget of the program? | MIDDLE | Given its nature, none of the activities of the Adaptation Fund require, according to the law, an environmental impact study. The environmental criteria are followed with rigorous observation to prevent possible negative effects. In addition, periodic meetings are held with the basin committees, formed in part by municipal authorities, and these indicate whether permits (municipal building permits, water extraction, etc.) are required, if necessary they will be included in the Terms of Reference, so that the executing agency is aware of the permits that must be requested. in the Terms of Reference, the principles necessary permissions to implement the program in the work area are addressed.
L-4. Are there inadequate public security conditions for implementing the program? | LOW | Actualmente, estamos iniciando con la implementación de proyectos en las comunidades, la comunicación continua con los comité de cuenca y representantes de Entidades Ejecutoras nos facilita obtener información sobre si existe algún peligro de Seguridad Pública en las cuencas, Además de responsabilizar a Entidades Ejecutoras de el sano cumplimiento de los estándares de seguridad en campo, explicados por fundación Natura.
Type of Risk: Economic
Ec-1. Does the program fail to generate viable economic alternatives or conditions for the participation of key stakeholders, including individuals? | LOW | from the design of the program, carried out through constant public consultation, viable economic alternatives were created that ensure the participation of key actors. With the start of implementation of agroforestry and silvopastoral systems projects, we have managed to identify a considerable number of people in the community interested in participating.
Ec-2. Does the program lack of a component that provides some economic support to achieve a viable long-term success of the actions, processes and ensures continued environmental impacts from the program? | MIDDLE | We are currently initiating the projects, the need to support the beneficiaries with (material, technical, advice, training, pay for wages, etc.) from the executing entities, in projects has been taken into consideration for the Terms of Reference as agroforestry and silvopastoral, it was included in the Terms of Reference, that the Monitoring and evaluation process is necessary, to supervise the achievement of better economic conditions for the beneficiaries, as well as, to promote capacity building among the beneficiaries so that after The culmination of the program can respond positively to adverse events.
Ec-3. Is there a current or potential presence of land speculation arising from improving farms, attracting buyers who could transform land use or reverse the progress and achievements of the program? | MIDDLE | Starting with the Agroforestry and livestock projects, it was taken into account to choose the beneficiaries, certain criteria suggested by the EE, NIE and MIDA as: Long-term residence on the site, strong family ties, sense of belonging, in addition to be approved by the Ministry of Agricultural Development, who mostly has experience working with the producers and families of the work area, the executing agency will sign agreements with the partner producers to ensure the non-sale of the farm at least in the short in the medium term. Fundación Natura will function as guarantor of these agreements. Improvements in the beneficiary farms will bring increases in income and socio-economic benefits, which can result in a decrease in the likelihood of owners selling their farm. The Terms of Reference include beneficiaries approved with MIDA, which in any case exponentially reduces the existing risk of sale, since the Executing Entity has worked with them previously and knows the situations of most farms as well as, level education of the owners, opinions about the land, long-term goals for farms, etc.
Ec-4. Is the population of the area influenced by factors of access to service facilities and job offers which makes them less interested in the program? | LOW | the creation of sources of income, market opportunities, capacity building through program implementation activities, have a direct impact on those wishing to remain in the area, and it is not necessary to seek sources of work outside the communities.
Type of Risk: Organizational
O-1. Is there insufficient involvement and coordination among institutions to maintain EWS, hydro stations, as well as the forest cover and ecosystem features that help prevent (among other impacts) floods and erosion? | MIDDLE | The Executing Entities that are currently initiating work, such as MIDA and ETESA, are willing to participate and assume responsibility for the maintenance and monitoring of activities after the end of the program (for example: Agrohydrometeorological stations and agroclimatic node project), the establishment of constant communication measures and donation agreements between Executing Entities, participating NGOs and Fundación natura will allow the results of the projects to be sustained over time. As well as the maintenance and care commitments of the installed projects.
O-2. Do implementing organizations lack the strengths, skills and institutional capabilities in administrative, financial and technical areas to implement the projects? | MIDDLE | Fundación Natura provides administrative support to Institutional Executing Entities, to facilitate the acquisition of goods and services for the implementation of their projects, in addition, technicians are strengthened in gender, social, environmental (Safeguards), monitoring and follow-up policies. projects as well as technical issues such as: Silvopastoral, Agroforestry, Water Harvest and Adaptation to climate change.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1]
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law |  |  | Little compliance with the country's environmental legislation and regulations (national laws, regulations and specifications) | * National environmental laws that comply with safeguards for different types of projects were identified. | Number of environmental laws included in the terms of reference. | 0 | The program complied with the inclusion of environmental regulations in the technical specifications or TDR of the calls. The consultancies and projects are being executed considering the environmental regulations and other ruling provisions in the country. | does not apply | does not apply
2 - Access and equity |  |  | * Target population is not fully trained with gender equality. (I1) * Little participation of vulnerable communities in the dissemination and promotion of program activities. (I3) * Lack of youth leadership (S8) | * The participation of men and women was ensured under the defined criteria of the program activities. * The participation of the communities of the intervention sites in the activities of the program through call and invitations from person to person was guaranteed. * Access and socialization to the information corresponding to the program was facilitated, such as the workshops and progress meetings in the watershed committees and in the CONACCP. | * Population trained by sex. * Vulnerable population that participates in the activities defined by the program. * Include young people in the activities of the program to create community leaders. | 0 | The selection criteria (gender, education, socio-economic and environmental) have been included to guarantee the participation of the communities in the calls and events carried out within the program. | Lack of access to information, due to the lack of adequate communication channels in vulnerable communities. | Promotion through environmental promoters, strategic partners, watershed committees and other key actors.
3 – Marginalized and vulnerable Groups |  |  | Does not apply in the period | Does not apply in the period | Does not apply in the period | Does not apply in the period | Does not apply in the period | Does not apply in the period | Does not apply in the period
4 – Human rights |  |  | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply | No aplica | No aplica
5 – Gender equality and women’s empowerment |  |  | The local workforce lacks the academic profiles necessary to implement program activities. (S-3). There is no adequate level of training for individuals in communities involved in order to implement the program (S-4). | Does not apply in the period The program trained technical personnel of the Executing Entities. | Note: Work with communities begins in the field, so there is no further progress in this period. | does not apply in the period | does not apply in the period | does not apply in the period | does not apply in the period
6 – Core labour rights |  |  | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply
7 – Indigenous peoples |  |  | The local workforce lacks the necessary profiles to implement program activities. (S-3). There is no adequate level of training for individuals in communities involved in order to implement the program (S-4). Does not apply in the period | does not apply in the period | does not apply in the period | does not apply in the period | does not apply in the period | does not apply in the period | does not apply in the period
8 – Involuntary resettlement |  |  | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply
9 – Protection of natural habitats |  |  | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply
10 – Conservation of biological diversity |  |  | The program includes environmental laws and regulations. It does not apply in the period because there is no progress in field work. | does not apply in the period | does not apply in the period | does not apply in the period | does not apply in the period | does not apply in the period | does not apply in the period
11 – Climate change |  |  | The program includes environmental laws and regulations. It does not apply in the period because there is no progress in field work. | does not apply in the period | does not apply in the period | does not apply in the period | does not apply in the period | does not apply in the period | does not apply in the period
12 – Pollution prevention and resource efficiency |  |  | The program includes environmental laws and regulations. It does not apply in the period because there is no progress in field work. | does not apply in the period | does not apply in the period | does not apply in the period | does not apply in the period | does not apply in the period | does not apply in the period
13 – Public health |  |  | The program includes environmental laws and regulations. It does not apply in the period because there is no progress in field work. | does not apply in the period | does not apply in the period | does not apply in the period | does not apply in the period | does not apply in the period | does not apply in the period
14 – Physical and cultural heritage |  |  | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply
15 – Lands and soil conservation |  |  | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply | does not apply
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | No, monitoring for unanticipated ESP risks has not been carried out.
Have unanticipated ESP risks been identified during the reporting period? |  | No, unanticipated risk has not been identified
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | does not apply
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | "(i) public calls have been made. (ii) The laws and laws applicable to the program have been included in the Terms of Reference Additional note: we are starting with the projects. "
Have the implementation arrangements been effective during the reporting period? |  | Calls have been made, including Social and Environmental Safeguards policies.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | They are starting with the calls for projects, so the only measure that has been used is to make the Terms of Reference based on the laws and laws applicable to the program, in addition to Social and Environmental Safeguards.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes, they have been effective. We are starting with the call
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | No, the executing entity that has the highest percentage of products and budget to execute has not defined the roles or responsibilities of the staff that will work directly with the fund. You have only defined the staff at the central level.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11] |  | So far there is no ESMP to update.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
so far we haven´t receive any grievances |  | does not apply
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | No
Does the results framework include gender-responsive indicators broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Output 1: Enhanced climate change resilience for improved food, water, and energy security in target watersheds. | Output | No. of people with improved access to water from water harvest systems implemented in targeted watersheds | 0 | 125 women in both of the targeted watersheds. | Poor (projects in field to be initiated)
Output 1.1: Concrete adaptation measures implemented for household water security | Output | Number of people trained on the use and maintenance of the WHS | 0 | 50 women trained on the use and maintenance of the WHS. | Poor (projects in field to be initiated)
Output 1.2: Pilot climate-smart farming projects implemented | Output | Number of people in targeted communities that benefit from climate-smart agroforestry systems implemented | 0 | At least 50 women, benefit from the climate smart agroforestry systems implemented at the Caisan River Sub-watershed in CVRW | Poor (projects in field to be initiated)
Output1.3.b Creating capacities for operating orchid and “naranjilla” crops, as well as establishing the correspondent commercialization scheme at the Rio Gallito Sub-Watershed. | Output | i) Number and percentage of women and men who receive training; | TBD | 16 women will receive training | Poor (projects in field to be initiated)
Output 1.4: Concrete adaptation measures implemented for sustainable cattle ranching | Output | Number of women that benefits from the climate resilient catlle ranching projects | 0 | 90 women | Poor (projects in field to be initiated)
Output 1.5 Enhanced sectorial support through climate financing instruments | Output | Number of women farmers that receive technical assistance on access financing sources for climate change adaptation activities | 0 | 4 women farmers from each of the two target watersheds | Poor (projects in field to be initiated)
Output 2.1 Analysis for climate change vulnerability done in prioritized areas at the Chiriquí Viejo and Santa María rivers watersheds | Output | Number of women that participated in the update consultation process | 0 | 100 women participating in the update consultation process. | Poor (projects in field to be initiated)
Output 3.2 Established an early warning system to identify in advance, the necessary measures in case of hydro-climatic events that could affect food production and power generation | Output | Number of women trained and with built capacitities on the use of the EWS | 0 | At least 50 women trained on how to reduce risks to extreme weather events by understanting/using the EWS | Poor (projects in field to be initiated)
Output 3.2 Established an early warning system to identify in advance, the necessary measures in case of hydro-climatic events that could affect food production and power generation | Output | Number of women trained and with built capacitities on the use of the EWS | 0 | At least 6 women staff members trained to respond to and mitigate impacts of climate related events must be woman | Poor (projects in field to be initiated)
Output 4: Awareness raised and a knowledge exchange platform established to mitigate impacts of climate change related events. | Output | No. of people aware of target watersheds´ vulnerability analyses | 0 | 125 women will receive technical information delivered by the programme | Poor (projects in field to be initiated)
Output 4.1.c: Socialize the SMRW and CHVRW vulnerability analyses to facilitate the implementation of identified adaptation measures | Output | Number of people that participated during socialization of SMRW and CHVRW vulnerability analyses | 0 | At least 600 women participating | Poor (projects in field to be initiated)
4.2.a Offer a Climate Modelling Course with special emphasis on future scenarios impacting food-energy generation activities (at least 45 participants) | Output | Number of people trained on climate modelling and future scenarios impacting food-energy generation activities | 0 | At least 14 women participating in the event | Scheduled for next term
4.2.b Offer an international course on Adaptation to Climate Change: Role of Ecosystem Services (45 participants nationwide, including stakeholders in the two prioritized watersheds) | Output | Number of people trained on adaptation to climate change and the role of ecosystem services | 0 | At least 14 women participating in the event | Good (23 women accounted. 55% of women trained on adaptation to climate change and the role of ecosystem services of the totality of the attendants)
4.3.a Offer an international course on participatory and integrated watershed management emphasizing conflict management skills | Output | Number of people trained on participatory and integrated watershed management emphasizing conflict management skills | 0 | At least 12 women trained on participatory and integrated watershed management emphasizing conflict management skills | Good (27 women, corresponding to 61% of participants)
4.3.b Offer an international course on ecosystem-based adaptation at marine-coastal zones | Output | Number of people trained on ecosystem-based adaptation at marine-coastal zones | 0 | At least 6 women trained on ecosystem-based adaptation at marine-coastal zones | Scheduled for next term
4.4.b 10 workshops will be held at national level -1 per province- to present the document (4.4.a) | Output | Number of people who attended workshops at each province of the country | 0 | At least 150 women | Scheduled for next term
Output: 4.5.a Communication strategy and systematization of experiences from the program | Output | Number and percentage of women and men who receive technical information delivered by the programme Number of awareness activities providing targeted information to women on climate change adaptation | 0 | number of woman with enhanced capacity in climate change | Poor (projects in field to be initiated)
Output 4.5.c: Compilation and synthesis of materials for different audiences -farmers, institutions, academia, etc.- on adaptation to climate change (knowledge products) | Output | Number of knowledge products generated and made available to different users by the program Number of people reached by knowledge products from the program | 0 | 600 women and 1400 men will receive specific knowledge products delivered by the programme; ii) 7 knowledge products targeted at women, by content area | Poor (projects in field to be initiated)
Output 4.5.f Experience exchanges activities at the local level, including at least one international pasantía (guided visit): | Output | Number of people trained from technical exchanges | 0 | 30 women trained in exchange activities at the local level (number of beneficiaries: core impact indicator) | Starts in the second period
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | (i)The NIE put in place a Workshop about the Gender policies and Environmental and Social Policy Compliance to the Executing Entities Staff and the NIE itself. (ii) it has been indicated to the Executing Entities, that in the events (Workshops, International Courses), there must be selection criteria, as well as those based on gender equality (iii) In the revision of the Terms of Reference delivered by the Executing Entities, it has been verified that they comply with the Gender Policies of the Adaptation Fund.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Arrangements have been implemented to the projects that have been done. For example in workshops and international workshops.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | The projects in field are starting. Therefore, to date, gender policies are being attached to the Terms of Reference, so that they are complied with by the different Executing Entities.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | The projects in field are starting. Therefore, to date, we dont have results to share.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Theres not enough capacity, for the compliance of the gender policies, because in the staff that is working with the Executing Entities, there´s not a Gender Specialist. With the government change, in july, and the news focals points, assigned technicians, its programmed to impart a new Environmental and Social Policy Compliance and Gender policies Workshop , to new assigned staff.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | No complaints were received
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The conditions and requirements related to the ESP refer to all those that relate directly or indirectly to the fulfillment of the ESP. These conditions are generally included in "Annex II of the legal agreement" with the name "requirements and conditions for disbursements and disbursement schedule"
2 | The ESP requires that environmental and social risks be identified for all project / program activities before funding approval. When not all project / program activities have been sufficiently formulated at that time to allow adequate identification of risks, then the identification of ESP risks is not complete
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes a general table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, copy the findings about the presence or absence of risks here by checking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | COMPONENT 1 |  | Enhanced climate change resilience for improved food, water, and energy security in target watersheds |  | Theres have been delays in the delivery of the Terms of Reference from the Executing Entity, because, they havent defined the work group, for the regionals in the provinces. Currently developing the Terms of Reference of the projects programmed for the year. | (MU) (the projects in the in field, have not start yet, we are making arrengements with the Executive Entities, to comply with the results that have been set in the program)
| COMPONENT 2 |  | Established climate-resistant water management instruments with an integrated and community-based approach |  | The projects started with delays however they are running satisfactorily | (MS)
| COMPONENT 3 |  | Increased preparation of hydrographic basins and disaster risk reduction among vulnerable communities across the country - better access to data for informed and timely decision making, in relation to climate variability risks |  | There were delays in the calls for projects scheduled during the period. Currently, they are making satisfactory progress to achieve the adequate results. | (MS)
| COMPONENT 4 |  | Improved institutional capacity, knowledge management and awareness on adaptation to Climate Change |  | knowledge management activities, training courses and workshops are being executed, as scheduled in the period. however, the interinstitutional exchange of information should be strengthened | (MS)
[5 empty] | Overall Rating | (MS)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Elba Cortes
| Email: | ecortess@miambiente.gob.pa
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| COMPONENT 1 |  | Enhanced climate change resilience for improved food, water, and energy security in target watersheds |  | To date, the project is in the call of two projects, Sustainable Livestock and Agroforestry in the Santamaría River basin, the Executing Entity has developed three Terms of Reference: Water collection systems, implementation of Agroforestry Systems and soil conservation systems in rebirth, which will be convened in the month of July. | (MU)
Implementing Agency | COMPONENT 2 |  | Established climate-resistant water management instruments with an integrated and community-based approach |  | The program is in execution of product 2.1a, 2.2a, 2.2b, 2.2c, 2.2d and 2.3a. It begins with the process of calling for the product of analyzing vulnerability in the Santamaría river watershed | (MS)
| COMPONENT 3 |  | Increased preparation of hydrographic basins and disaster risk reduction among vulnerable communities across the country - better access to data for informed and timely decision making, in relation to climate variability risks |  | The project for updating the existing network of the National Climate Data System and the beginning of the national Agroclimatic and Statistical data system are being implemented, this are the projects programmed for the year. | (MS)
| COMPONENT 4 |  | Improved institutional capacity, knowledge management and awareness on adaptation to Climate Change |  | Workshops and trainings have been given which have been publicly announced and the project is currently in the final phase of the Climate Change Adaptation portal in Panama | (MS)
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Vilna Cuéllar
| Email: | vcuellar@naturapanama.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | [6 empty] | más de una entidad ejecutora
minimo una ee y la nie deben llenarlo.
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The project had a slow start, because the executing Entities did not present their annual operational plans and their plan for the acquisition of goods and services, in addition to the formation of equipment in the Executing Entities, had delays, for example, the MIDA Executing Entity conformed its regional team, at the end of the first year period, who must comply with a component that mostly has projects in the field. In the second component, terms of reference were presented that were not consistent with the proposal approved by the fund, so there were delays. Due to the fact that we were in the election year, the possible proponents for project executions and consultancies did not want to present projects to work with the Government Entities that participate in the program as Executing Entities. Up to three calls for the same project / consultancy had to be made to be able to allocate resources.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
consultancies started in June 2019. note progress in implementation
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
1.1 | Number of households with improved access to water from water harvest systems installed (number of beneficiaries: core impact indicator) | 0 | 0 | 50 households with water harvest systems installed (25 in each target watershed)
1.1 | Number of people trained on the use and maintenance of the WHS | 0 | 0 | 100 people trained on the use and maintenance of the WHS, of which at least 50% will include women. (number of beneficiaries: core impact indicator)
1.1 | Technical document developed and adopted by the Ministry of Environment | 0 | 0 | 1 technical document produced and adopted by the Ministry of Environment for reference for future replication of this WHS model.
1.2 | Number of farms with agroforestry projects established | Number of farms with climate smart production systems (and the number of people that benefits from them) is estimated at 0; nonetheless, to confirm this assumption, an overall initial baseline survey has been programmed at the beginning of the program implelmenteation (and for which funds have been requested accordingly in the M&E budget) | 0 | At least 20 farms with climate smart agroforestry (shaded coffee mainly) projects succesfully established
1.2 | Number of people in targeted communities that benefit from climate-smart agroforestry systems implemented | Number of farms with climate smart production systems (and the number of people that benefits from them) is estimated at 0; nonetheless, to confirm this assumption, an overall initial baseline survey has been programmed at the beginning of the program implelmenteation (and for which funds have been requested accordingly in the M&E budget) | 0 | At least 100 people, of which 50% are women, benefit from the climate smart agroforestry systems implemented at the Caisan River Sub-watershed in CVRW
1.2 | Lineal meters of riparian reforestation successfully established | TBD (exact area of existing riparian forest in targeted communities will be determined in the general baseline survey). | 0 | 6000 lineal meters of riparian reforestation successfully established
1.2b | Diagnostic for irrigation needs completed | 0 | 0 | One irrigation needs diagnostic for Cerro Punta and Divalá production areas
1.2b | Number of hectares of climate resilient irrigation systems established | 0 | 0 | At least 150 hectares of climate resilient irriguation systems at Cerro Punta and Divalá
1.2b | Number of farmers that received technical assistance | 0 | 0 | 80 farmers (gender dissagregated target will be determined after baseline survey is completed; it is anticipated that the majority of local rice farmers are men).
1.2b | Document of the analysis of water footprint for rice crops | 0 | 0 | One technical document on rice crop water footprint
1.3a | Number of farms with FMP (farm management plans) | 0 | 0 | 40 farms of approximately 5 hectares each with FMP
1.3a | Number of hectares with climate resilient agroforestry and soil conservation systems established | Number of hectares with climate resilient shaded coffee agroforestry systems (and the number of people that benefit from them) is estimated at 0; nonetheless, to confirm this assumption, an overall initial baseline survey has been programmed at the beginning of the program implementation (and for which funds have been requested accordingly in the M&E budget) | 0 | 200 hectares of agroforestry schemes (mainly shaded coffee with beans)
1.3a | Number of people that benefits from the climate resilient shaded coffee agroforestry systems established | Number of hectares with climate resilient shaded coffee agroforestry systems (and the number of people that benefit from them) is estimated at 0; nonetheless, to confirm this assumption, an overall initial baseline survey has been programmed at the beginning of the program implementation (and for which funds have been requested accordingly in the M&E budget) | 0 | At least 200 people benefit from the climate reslilient shaded coffee systems (gender dissagreggated figure will be determined once the baseline survey is completed, and in full compliance with Gender Policy of the Adaptation Fund
1.3a | Percentage of income increase in targeted population households (40 farms) | TBD in targeted population households (income in targeted beneficiaries will be determined by a specific socioeconomic survey to be conducted as part of the overall initial baseline survey programmed at the beginning of the program implementation -and for which funds have been requested accordingly in the M&E budget) | 0 | Percentage of income increase by source in targeted population households
1.3 b | Number of people trained on establishment and management of orchid and naranjilla crops | TBD in the participatory communitty rapid assessment included as part of the project (although currently there are 14 naranjilla producers and 4 orchid producers) | 0 | TBD, but at least will include current 14 naranjilla producers and 4 orchid producers (currently, all involved producers are women), fully trained on crops management and commercialization TBD, but at least will include current 14 naranjilla producers and 4 orchid producers (currently, all involved producers are women), fully trained on crops management and commercialization To define the specific target we will consider: • The participatory community rapid assessment will include a consultation to identify other inhabitants interested in the production of these products; willingness to participate; potential barriers to participate (working schedules, literacy, etc) • A consultation with MIDA and local cooperatives to identify other extension and/or technical assistance programmes that the Ministry is conducting and that might include a module on the production of orchids and naranjillla. To reflect the gender equality dimension (Human Capital), the indicator will be disaggregated as follows: i) Number and percentage of women and men who receive training; ii) Number of training sessions targeted at women and men, by content area Note: This particular activity and indicator is gender oriented to promote women´s empowerment since preliminary research conducted during the proposal writing process confirmed that the activity is currently developed by women, so women participation will be emphasized.
1.3b | Number of business plans designed | 0 | 0 | 2 business plans designed and in operation (one for naranjilla and one for orchids)
1.3b | Marketing agreements with potential buyers | TBD in the participatory communitty rapid assessment included as part of the project | 0 | At least 2 market agreements established for naranjilla and 2 market agreements for orchids
1.4a | Number of hectares with sustainable catlle ranching models | 0 (during consultation process it was confirmed that there are 1831 hectares of unsustainable cattle ranching farms) | 0 | 600 hectares with sustainable catlle ranching models established and in operation
1.4a | Number of FMP developed | 0 | 0 | 120 farm management plans (of around 5 hectares each)
1.4a | Number of people that benefits from the climate resilient catlle ranching projects | Number of people that benefit from the sustainable cattle ranching projects is estimated at 0; nonetheless, to confirm this assumption, an overall initial baseline survey has been programmed at the beginning of the program implementation (and for which funds have been requested accordingly in the M&E budget) | 0 | At least 600 people benefit from the climate reslilient and sustainable cattle ranching projects (core impact indicator) (gender dissagreggated figure will be determined once the baseline survey is completed, ensuring full compliance with Gender Policy of the Adaptation Fund)
1.5a | Study and technical recommendations on climate financial products designed | 0 | 0 | 1 study-review on current credit products offered to agriculture and energy sectors; including technical recommendations on climate financing instruments
1.5b | Number of business plans developed to establish and operate renewable energy projects, including the correspondent FMP | 0 | 0 | 4 business plans for small scale renewable generation projects (hydro, solar, etc
1.5b | Number of farmers that receive technical assistance on access financing sources for climate change adaptation activities | 0 | 0 | 16 farmers, 8 from each of the two target watersheds (gender dissagreggated target will be determined once the baseline survey is completed, ensuring full compliance with Gender Policy of the Adaptation Fund)
1.5c | Number of microfinance institutions mapping document developed | 0 | 0 | 1 document with microfinance institutions mapping on both watersheds
1.5c | Number of microfinance institutions interested/willing to participate in training on MEbA | 0 | 0 | At least 2 microfinance institutions and/or cooperatives
1.5c | Number of microfinance institutions trained to design climate change oriented finance products | 0 | 0 | 2 trained microfinance institutions and/or cooperatives offer two finance products with MEba model
1.5c | Number of microfinance programmes with MFI and cooperatives designed implemented | 0 | 0 | At least 2 microfinance programmes offered by MIFs and/or cooperatives
2 | No. of water security instruments developed for implementation by districts and the national level that respond to climate-induced challenges | 0 | 0 | 8 instruments developed and adopted by incumbent regional/national institutions to respond to new conditions resulting from climate variability and change:
One updated SMRW Management Plan, incorporating the climate change dimension
One vulnerability analysis document completed for the CHVRW
Two technical criteria document developed for granting water use concessions and permits for two watersheds
One technical recommendations document delivered to responsible parties for adjustments needed to improve hydrological cycle at both watersheds
Two water security disctrict plans designed
National map for agriculture and livestock production developed
2 | No. of people benefiting from management instruments designed and approved by incumbent authorities, which allow improved and sustainable access to water resources in a changing climate scenario | Number of people that currently benefit from management instruments designed and approved by incumbent authorities, which allow improved and sustainable access to water resources in a changing climate scenario is estimated at 0 | 0 | TBD once baseline survey is completed, but will include population from target communities, watersheds (combined population of the CHVRW and SMRW is about 114,000), and the national level (close to 4 million). Gender dissagregated numbers will be determined after the survey, but will incorporate full compliance with Gender Policy of the Adaptation Fund.
The specific target will be based upon:
Population of districts selected for the development of district plans for water security
Socio economic data raised during the VIA analysis (2.1), including identification of communities within the 2 watersheds, emphasizing those affected by drought/flooding events and hydroelectric projects
Communities involved in water conflicts due to hydroelectric projects or other water related issues
Membership of water councils within the project area, disaggregated by gender, including participation of women in the boards and other similar water governance structures
Compliance with gender policy: In response to gender equality requirements, the indicator will be disaggregated to identify:
Number of households with improved access to water for agricultural and household uses (addressing human capital)
Number of community-based agreements and adaptation plans that have input from both women and men (addressing voice and rights)
Changes in water management instruments and initiatives due to consultation with women promoted by the programme
2.1a | Update of the document of SMRW management plan | 0 | 0 | Updated Santa María River Watershed (SMRW) Management Plan including the climate change’s dimension
2.1a | Number of people that participated in the update consultation process | 0 | 0 | At least 200 people participated in the process, ensuring participation of 50% men and 50% women.
2.1b | Vulnerability analysis document completed for the CHVRW | 0 | 0 | Updated- improved CHVRW Management Plan, including analysis of the climate change dimension | 0
2.2.a | Technical criteria document developed for granting water use concessions and permits for both watersheds | 0 | 0 | 2 technical criteria document for granting water use concessions and permits (one for each watershed) developed and validated with the Ministry of Environment and the Ministry of Agriculture
2.2 b | Number of awareness meetings with local population and responsible parties in the process of granting water use permits | 0 | 0 | 10 awareness meetings completed with local population and responsible parties in the process of granting water use permits
2.2 c | Number of people that participated in the process of developing the technical document with criteria for granting water use permits for agriculture and power generation | 0 | 0 | Number of participants TBD at the initial survey of the program, but will observe the Gender Policy of the AF
2.2 d | Technical recommendations document delivered to responsible parties for adjustments needed to improve hydrological cycle at both watersheds | 0 | 0 | 1 technical document with recommendations for improving or restoring hydrological cycle at both watersheds, delivered to and validated by the Ministry of Environment and the Ministry of Agriculture
2.3 a | Number of water security disctrict plans designed | 0 | 0 | 2 hydrological security district plans designed and adopted by 2 districts of target watersheds
2.3 b | National map for agriculture and livestock production developed | 0 | 0 | 1 national map for agriculture and livestock production developed, adopted and widely publicated by the Ministry of Agriculture Development (MIDA)
3.1 a | A National System for Climate Data designed and in operation | 0 | 0 | 1 National System of 142 stations for Climate Data, with upgraded ETESA´s network for recording hydro-agro meteorological information from hydrographic watersheds
3.1 a | Number and type of targeted institutions with increased capacity to minimize exposure to climate variability risks | 1 | 0 | 4 institutions (ETESA, MiAmbiente, MIDA, SINAPROC) with access to information for decision making to recuce national exposure to climate variability risks
3.1 a | Number of new stations installed | 72 | 72 | 70 new automatic stations installed
3.2 a | Number of EWS for floods/droughts fully operational | One non-operational EWS for floods at the CHVRW and 0 EWS operational at the SMRW | One non-operational EWS for floods at the CHVRW and 0 EWS operational at the SMRW | Two fully operational EWS in target watersheds (one of floods and one for floods-droghts). Core impact indicator
3.2 a | Number of communities included in the CHVRW early warning system | Exact number TBD by initial survey |  | TBD, but at least 10 communities from CHVRW watershed
3.2 a | Number of people trained and with built capacitities on the use of the EWS | 0 | 0 | At least 100 people trained on how to reduce risks to extreme weather events by understanting/using the EWS
3.2 a | Number of staff trained to respond to and mitigate impacts of climate related events | 0 | 0 | At least 20 staff members trained to respond to and mitigate impacts of climate related events
3.2 b | Number of communities included in the SMRW early warning system | Exact number TBD by initial survey |  | TBD, but at least 10 communities from SMRW watershed
3.2 b | Number of people trained and with built capacitities on the use of the EWS | 0 | 0 | At least 100 people trained on how to reduce risks to extreme weather events by understanting/using the EWS
3.2 b | Number of staff trained to respond to and mitigate impacts of climate related events | 0 | 0 | At least 20 staff members trained to respond to and mitigate impacts of climate related events
3.3 a | Joint node of climatic information established between ETESA and MIDA | 0 | 0 | 1 operational joint node of climate information established between ETESA and MIDA, generating climate change information
3.3 a | Number of people trained and with built capacitities on the management of the joint node | 0 | 0 | At least 20 staff trained and with capacities built to manage joint node and information on climate change
3.4 a | Tool designed to assess efectiveness of climate change adaptation | 0 | 0 | 1 tool designed to assess efectiveness of climate change adaptation measures at national level
3.4 a | Number of workshops with public and nongovernmental stakeholders on the tool design | 0 | 0 | At least 3 workshops with public and nongovernmental stakeholders on the tool design
3.4 a | Number of people from relevant stakeholders trained and with built capacities to use the assessment tool | 0 | 0 | At least 80 people trained and with built capacities to use the assessment tool
4.1 a | Number of training sessions held | 0 | 0 | 2 working sessions with the technical team and key Implementing partners
4.1a | Pertentage of project staff trained | 0 | 0 | 100%
4.1a | Percentage of key implementing partners trained | 0 | 0 | 100%
4.1b | Number of inception workshops with local and national stakeholders to present the approved programme; revisit programme rationale, scope, define shared visions and operational arrangements for programme implementation. | 0 |  | At least 2 local workshops, one for each watershed with local stakeholders; and 1 national workshop with government and civil society stakeholders to present the Programme, identify sinergies with other ongoing adaptation efforts/initiatives and define operational and coordination aspects
4.1c | Number of people that participated during socialization of SMRW and CHVRW vulnerability analyses | 0 | 0 | At least 2,000 people in both target watersheds
4.2 a | Number of people trained on climate modelling and future scenarios impacting food-energy generation activities | 0 | 0 | At least 45 people trained on climate modelling and future scenarios impacting food-energy generation activities
4.2 b | Number of people trained on adaptation to climate change and the role of ecosystem services | 0 | 0 | At least 45 people trained on adaptation to climate change and the role of ecosystem services
4.2 c | Number of people trained on participatory and integrated watershed management emphasizing conflict management skills | 0 | 45 | At least 40 people trained on participatory and integrated watershed management emphasizing conflict management skills
4.3 b | Number of people trained on ecosystem-based adaptation at marine-coastal zones | 0 | 0 | At least 20 people trained on ecosystem-based adaptation at marine-coastal zones
4.4 a | Technical and practical document (mapping and analysis of projects / initiatives undertaken) designed and made avaible in print and digital formats | 0 | 0 | 1 document produced in print (500 units) and digital formats, broadly disseminated nationwide
4.4 a | Number of news outlets in the local press and media that have covered this dissemination of experiences | 0 | 0 | At least 6 news outlets in the local press and media that have covered this dissemination of experiences
4.4b | Number of people who attended workshops at each province of the country | 0 | 0 | At least 500 people (50 in each province)
4.5a | Systematization document developed | 0 | 0 | 1 systematization document produced about experiences from the program
4.5 a | Number of people reached by the communication strategy throughout the program | TBD |  | TBD after general survey at the beginning of the program implementation
4.5 b | Number of visits per month of the portal | TBD |  | TBD after the completion of product 4.1.a
4.5b | Percentage of favorable comments on usefulness of the portal | TBD |  | TBD after the completion of product 4.1.a
4.5C | Number of knowledge products generated and made available to different users by the program | 0 | 0 | Not less than 20 products throughout the complete program execution
4.5C | Number of people reached by knowledge products from the program | TBD |  | TBD after the completion of product 4.1.a
4.5D | Number of people who benefit from the training on the use of the portal | 0 | 0 | At least 500 people trained on the use of the portal
4.5 e | Advisory technical committee established to orient the knowledge management process | 0 | 0 | 1 Advisory technical committee established and operational to orient the knowledge management process
4.5 e | Number of decisions made and implemented from advisory technical committee meetings | 0 | 0 | TBD after the completion of product 4.1.a. Rationale.
4.5 f | Number of people trained from technical exchanges | 0 | 0 | At least 100 people trained in exchange activities at the local level (number of beneficiaries: core impact indicator)

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | We have had difficulties for the Executing Entities: (i) definition of the focal point of the project in the Executing Entity with greater budget to execute (ii) delays in the selection of work equipment at the level of the areas of the hydrographic basins, so There have been delays in deliveries of the Terms of Reference. Until the EE defined the focal point and the teams of the regional offices the NIE assumed the monitoring in the field of activities already initiated; however, new activities (TDR, calls) were carried out once the focal point and technical teams were defined. In addition, we continue to work with the other executing entities on their work plans
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | (i) in the Executive entity that has more products to deliver, there have been changes at the institutional level, which has caused the current staff to ignore the project, which has had to have permanent coordination meetings, and hiring of consultants to perform the Terms of Reference, which have then been sent to the regionals for review.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Options are being evaluated to establish the best strategy to assist the regional coordination of executing entities in each prioritized basin. For the Santa Maria River basin there are 3 provinces which shows that for a project it must be coordinated with 3 regional agencies of the executing entity and only a coordinator is available at the level of executing entity.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | We are initiating projects for what our Terms of Reference include, Social and environmental safeguard policies and gender, to avoid negative impacts on the projects. They will be followed accordingly.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | At the end of this reporting period we have no lessons learned to contribute based on gender as we are starting with the projects.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | Fundación Natura
Type of implementing entity | NIE
Country | Panama
Region | Latin America and Caribbean
Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 116281 | 2000 | 114281 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries |  | 40% |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % de los beneficiarios de la juventud | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Número de partes interesadas específicas |  | Información sobre peligros generada y difundida | Eficacia general | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 |  |  | Total | 1000 | Inland flooding | 3: Moderately effective | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 20% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Multi-sector | Regional | 1: No plans conducted or updated | 8 | Multi-sector | Regional | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 2 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 1 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 1 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 0 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 4: Response capability | Geographical coverage | Local | 0 | 4: Response capability | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted / Número de personal dirigido |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 20 | Multi-sector | 2: Low capacity | Total | 60 | Multi-sector | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 30% |  |  | % of female targeted | 20% |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | a total of 40 technicians from public institutions were trained, and 55 NGO technicians and community-based organizations
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 30% | Public |  | 60 | 10% | Public | [9 empty] | 60 técnicos 100 personas por cuenca + 80 personas (general): Total 280 personas
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 3: Medium capacity | Public | National | Multi-sector | 3: Medium capacity | [8 empty] | 4 instituciones
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures Porcentaje de población objetivo que aplica medidas de adaptación |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
[6 empty] | 70% |  | Food security
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 2552 | 0% | [10 empty] | 5. Totalmente consciente 4. mayormente conciente 3. Parcialmente consciente 2. Parcialmente no consciente
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
[6 empty] | Food security | Local | 3: Moderately responsive (Some defined elements) | [9 empty] | 4: Mayormente sensible (elementos más definidos) 3: Moderadamente sensible (algunos elementos definidos)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved | [9 empty] | 4: Mayormente mejorado 3: Moderadamente mejorado
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
[6 empty] | 1 | Community |  | Multi-sector | [8 empty] | Adm. pública con doc. que apoyan toma de decisión
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Resultado 5: Aumento de la resiliencia de los ecosistemas en respuesta al cambio climático y al estrés inducido por la variabilidad | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress Indicador 5: Servicios ecosistémicos y activos de recursos naturales mantenidos o mejorados bajo el cambio climático y el estrés inducido por la variabilidad | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability Resultado 5: Servicios ecosistémicos vulnerables y activos de recursos naturales fortaleceron en respuesta a los impactos del cambio climático, incluida la variabilidad | Core Indicator 5.1: Natural Assets protected or rehabilitated Indicador básico 5.1: Activos naturales protegidos o rehabilitados | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha rehabilitated | 1: Ineffective | Forests |  | ha protected | 1: Ineffective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land |  | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land |  | ha rehabilitated | 1: Ineffective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer |  | ha protected | 1: Ineffective | Catchment area/Watershed/Aquifer |  | ha protected | 1: Ineffective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households / No. de los hogares objetivo | % of female headed households / % de hogares encabezados por mujeres | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 50 | 10% | 2: Limited improvement |  | 328 | 24% | 3: Moderate improvement | [9 empty] | 4: Alta mejora 3: Mejora moderada 2: Mejora limitada
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | % de aumento del nivel de ingresos con respecto a la lìnea base // fuente alternativa
|  | 40 | 5% | From 0 to 0.5% | Cultivation | 60 | 10% | From 1% to 5% | Cultivation | [8 empty] | cultivo naranjilla y orquídeas, hortalizas, arroz
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 30 | 0% | From 0 to 0.5% | Livestock production | 120 | 2% | From 5% to 10% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 34 | 3% | From 0 to 0.5% | Agriculture | 148 | 30% | From 5% to 10% | Agriculture | [8 empty] | agroforestería
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets / Número de activos | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Social capital | Food security | Capacity development | 1 | Social capital | Disaster risk reduction | Capacity development
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) / Número de hogares (número total en el área del proyecto) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 60 | Cultivation |  | 120 | 60 | Cultivation |  | 200
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 120 | Livestock production |  | 250 | 120 | Livestock production |  | 300
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 148 | Agriculture |  | 100 | 148 | Agriculture |  | 160
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures Resultado 7: Políticas y regulaciones mejoradas que promuevan y apliquen medidas de resiliencia | Indicator 7: Climate change priorities are integrated into national development strategy Indicador 7: Las prioridades del cambio climático se integran en la estrategia nacional de desarrollo | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans Resultado 7: Mejora de la integración de las estrategias de resiliencia climática en los planes de desarrollo de los países | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks Indicador 7.1: No. políticas introducidas o ajustadas para abordar los riesgos del cambio climático | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced Indicador 7.2: No. estrategias de desarrollo específicas con prioridades incorporadas en materia de cambio climático | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on K21: Vilna Cuéllar: Cuencas Chiriquí Viejo 48,316 y Santa María 65,965 :114,281 )incluye distritos y ctes de cuenca
Note on I23: Vilna Cuéllar: por determinar
Note on J23: Vilna Cuéllar: por determinar
Note on K23: Vilna Cuéllar: por determinar
Note on I55: Vilna Cuéllar: 280 personas 60 técnico
Note on H64: Vilna Cuéllar: Del componente 1. 352 productores, el 80%
Note on I70: Vilna Cuéllar: 2 cuencas

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.