## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 28 February 2018 - 28 February 2019 (MTR)
| Project Title: | Enhancing the climate and disaster resilience of the most vulnerable rural and emerging urban human settlements in Lao PDR
| Project Summary: | The project objective is to “enhance the climate and disaster resilience of the most vulnerable human settlements in Southern Laos by increasing sustainable access to basic infrastructure systems and services, emphasizing resilience to storms, floods, droughts, landslides and disease outbreaks”. It combines a number of horizontally and vertically interrelated policy, planning and capacity development initiatives and has at its core the delivery of resilient infrastructure and services in target settlements that are characterized by a high exposure to climate hazards. It is structured around the following components: Component 1: Institutional level strengthening to reduce vulnerability in human settlements, Component 2: Building capacity at the human settlement and community level for climate resilience, Component 3: Enhance climate and disaster resilient infrastructure systems in human settlement and Component 4: Ensure project compliance with AF and UN-Habitat standards for knowledge Management and Advocacy
|  |  | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | LAO/MIE/DRR/2016/1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UN-Habitat | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Laos | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Attapeu, Sekong and Saravan Provinces |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
|  |  | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones |  | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  |  |  | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 28th AFB Meeting, 6-7 October 2016
IE-AFB Agreement Signature Date: |  | 2016-11-22 |  | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 23 February 2017 (inception workshop) |  | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | February / March 2019
| Terminal Evaluation Date: | June 2021
List documents/ reports/ brochures / articles that have been prepared about the project.
3x Provincial Level Vulnerability Assessment reports (1 each for Attapeu, Sekong and Saravan Provinces) - Final draft. 189 Village level assessment infographics. 1 Project brochure. The web presence has been refreshed and updated. 1x Google Earth model of the implementation area
List the Website address (URL) of project.
Infographics -http://af-189villages.info/. General info (Story map) - https://www.arcgis.com/apps/MapSeries/index.html?appid=2195a7a66b5b4a71a69b51b807e10504
Project contacts:
National Project Manager/Coordinator
| Name: | Buahom Sengkhamyong
| Email: | sbuahom@gmail.com
Date:
Government DA
| Name: | Syamphone Sengchandala
| Email: | syamphone.s@gmail.com
Date:
Implementing Entity
| Name: | Avi Sarkar
| Email: | avi.sarkar@un.org
Date:
Executing Agency
| Name: | Phomma Veovaranh - Ministry of Public Works and Transport
| Email: | pveovaranh@yahoo.com
Date:
Executing Agency
| Name: | Keovixien Sixanon - Director, NPSE Attapeu
| Email: | sxkeovixien@yahoo.com
Date:
Executing Agency
Name:
Email:
Date:

## FinancialData
Financial information: cumulative from project start to 28th February 2019
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 28 Feb 2019 | 281032 |  |  | NOTE | THIS IS THE Y2 TOTAL (to be added to the Y1 - total of USD 443,755)
Add any comments on AF Grant Funds. (word limit=200) | Cumulative total expenditure as at 28/2/2019 was 254,773 and 281,032 is the amount advanced by UN-Habitat to executing partners.
INVESTMENT INCOME | None
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1 - Vulnerability Assessment | 24445
| Output 1.2 - Capacity Building | 46253
| Output 1.3 - Developing Action Plans | 77977
| Output 2.1 Training and community planning | 22425
| Output 3.1 - Vulnerable infrastructure strengthened or new resilient infrastructure constructed | 72487
| Output 4.1 - Project activities and results are captured and disseminated | 11186
| TOTAL | 254773
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1 - Vulnerability Assessment | 38297 | 2020-02-28
| Output 1.2 - Capacity Building | 58617 | 2020-02-28
| Output 1.3 - Developing Action Plans | 165718 | 2020-02-28
| Output 2.1 Training and community planning | 283788.5 | 2020-02-28
| Output 3.1 - Vulnerable infrastructure strengthened or new resilient infrastructure constructed | 841428.57 | 2020-02-28
| Output 4.1 - Project activities and results are captured and disseminated | 21000 | 2020-02-28
| TOTAL | 1408849.07
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
1. Current climate and seasonal variability and/or hazard events result in infrastructure construction delays or undermine confidence in adaptation measures by local communities | The tropical storms and heavy monsoon rains that affected Lao PDR, during the months of July and August 2018, caused immense destruction throughout the country. The subsequent floods (and/or flash floods) and landslides had a devastating impact on different sectors. Despite this several physical infrastructures were completed in six (6) villages with total beneficiaries of 3,508 people and another thirty (30) water infrastructure survey, with an approximate value of 0.5 million USD,technical design and BoQ are completed and the construction to be soon started in Saravane,/Sekong/Attapeu. Medium risk. | Initial construction has primarily taken place in the dry season and in villages that are easy to access. Now that the operational modality for construction is well established, construction will scale up. Construction will only take place in easier to access villages during the rainy season for safety reasons. Some delays have been caused by the July 2018 floods in Attapeu.
2. Loss of government support (at all levels) for the project (activities and outputs) may result in lack of prioritization of AF project activities. | Government has retained healthy support for the project. Low risk | The PMC met early in year 2 and approved the workplan and gave guidance on the major activities. Private briefings took place with Directors General from MPWT and MoNRE. Sub-national staff have been regularly briefed through frequent field visits.
3. Capacity constraints of local institutions may limit the effective implementation of interventions | Capacity constraints have not yet proved a major barrier to project implementation. Low risk | The project has put capacity building at the forefront of its approach to implementation. Training has continued at the provincial and district level to be able to gather data, work with communities and plan and construct adaptation infrastrucutre. Consultants engaged by the project continued to develop 'how-to's - to hep replicate the project's activity and build specific technical capacities. Products were available in draft at the the end of Y2
4. Lack of commitment/buy-in from local communities may result in delay at intervention sites. | This risk will become more prominent as implementation of component 3 excelerates. Medium risk | Community engagement has taken place throughout the construction phase, before, during and after each construction. Several sites were visited during the MTR process, with all villages having functioning committees and/or other mechanisms to manage infrastructure
5. Disagreement amongst stakeholders with regards to adaptation measures (infrastructure) and site selection. | This has not yet occurred. Low risk | A second survey of all villages was conducted to present and rank-order adaptation options in the villages, and agree upon the most suitable option. This survey also completed an environmental and socia safeguards questionnaire in each village
6. Communities may not adopt activities during or after the AF project, including infrastructure maintenance | Construction of six community infrastructure projects completed and 30 are underway. Low risk | The mid-term review visited 3 of the 6 target communities where infrastructure construction is complete and found the uptake of local people to be very positive. No problems have so far been reported through vilage chiefs, to the Provincial NPSE, or to the project team directly
7. Complexity of financial management and procurement. Certain administrative processes could delay the project execution or could lack integrity | Financial commitments have been made as planned, without any delays or serious issues. Medium risk | The overall financial and administrative management of the project are governed by established UN rules and regulations. UN-Habitat undergoes periodic member state audit as per established regulations. The activities implemented by the implementing agency, NPSE Attapeu, are governed by Government of Lao PDR’s established admin and financial regulations, which are subjected to interim and financial audits by external auditors.
8. Delays in project implementation, and particularly in the development of infrastructure interventions | Construction of 6 water infrastructures completed and 30 is underway. Medium risk | There have been no delays in implementation so far. Vigilance is needed to ensure that fund flow continues from UN-Habitat to NPSE Attapeu and that rainy season doesn't hinder construction
9. A lack of coordination between and within national government Ministries and Departments | Ministries have played an active role in supporting the project implementation. Low risk | The MTR mission met with MPWT who demonstrated enthusiasm and continued support for the project. Coordination between MPWT and other relevant government agencies has continued. Coordination with MoNRE and
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Some villages are very remote and hard to access - especially in Sekong Province | A small selection of villages have been changed | 16 villages in Kaleum District (Sekong Province) proved too difficult to access. Reaching these villages would involve up to 12 days' return hike. Because these villages practice shifting cultivation, it was agreed with the PMC that the villages would be replaced, and that the total population of the new villages would be the same or greater. New villages were proposed to the PMC and accepted. The total population of these 16 villages is greater than the replaced 16 villages. Additional risk information has been generated, which generally shows the villages to be lower risk, primarily because they are more accessible
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Guideline for replication of vulnerability and risk assessments for other areas |  | Complete by month 18 |  | Methodology identified, but guideline still to be drafted | MS
| Intrastructure to be constructed selected |  | Complete by month 18 |  | Complete | HS
| Provincial and District level climate change action plans |  | Complete by month 22 |  | Complete | HS
| Updated guidelines for small scale projects |  | Complete by month 22 |  | Complete | S
| Plans for sub-projects |  | Complete by Month 24 |  | Completed 6 Sub-projects complete, 30 more under construction | HS
| Environmental and social risk assessments of sub-projects conducted |  | Complete by month 27 |  | The engineer's survey before each construction further analyses ESS risks. 30 engineer's surveys complete | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Buahom Sengkhamyong
| Email: | sbuahom@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
1) The guideline for replication has been rated as marginally satisfactory. This is because work is still in progress beyond the original time frame. However, the work has attracted the interest of MoNRE, which wants to roll it out in other provinces of Laos, which explains the delays. In the end, the delay is likely to service greater replicability of the guidelines.
2) All infrastructure has been identified and the process of engineer's surveys, detailed design and contruction is beginning
3) Provincial and District level climate change adaptation action plans is rated satisfactory as this activity is still ongoing and not due to be complete until month 22 of the project implementation. Nevertheless, this activity is ongoing and so-far there have been no significant problems, and the activity is on track to be complete on or before schedule.
4) The guidelines have been updated based on the completed sub-projects.
5) The sub-projects have been planned and initial designs have been done, based on action plans. The 189 sub-projects are now at different stages - 6 have been completed, a further 30 are under construction. Some delays have been caused by the flooding in Attapeu in June 2018 and the subsequent flooding in August 2018, the response from which has diverted government staff and resources
6) Building on the surveys undertaken in year 1, an engineer's survey took place before each construction that re-evaluated environmental and social risks and incorporated them into the detailed designs. As construction is underway and scaling up, it is essential to continue monitoring risks going forward
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Guideline for replication of vulnerability and risk assessments for other areas |  | Complete by month 18 |  | Methodology identified, but guideline still to be drafted | MS
| infrastructure to be constructed selected |  | Complete by month 18 |  | Complete | HS
| Provincial and District level climate change action plans |  | Complete by month 22 |  | In progress | S
| Updated guidelines for small scale projects |  | Complete by month 22 |  | In progress | S
| Plans for sub-projects |  | Complete by Month 24 |  | Completed 6 Sub-projects complete, more under construction | S
| Environmental and social risk assessments of sub-projects conducted |  | Complete by month 27 |  | Phase 1 complete, phase 2 underway | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Avi Sarkar
| Email: | avi.sarkar@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1] | N/A
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law |  |  | Risk of non-compliance with Lao PDR IEE procedure (identified despite no risk in the proposal) | Ensure IEE is completed following Lao PDR procedures, where applicable | No monitoring framework was identified in the ESMP developed during the full proposal, which was developed under older ESP operational guidance | N/A | See section 5 of this tab, column entitled 'List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP' | N/A | N/A
2 - Access and equity |  |  | Failure to engage indigenous people and people with vulnerabities in decision-making. Indigenous people not enjoying equal access to resulting service | Ensure continued use of UN-Habitat Project Template and equitable benefits of the project. Ensure all project affected persons have free, prior and informed consent relating to project outcomes
3 – Marginalized and vulnerable Groups |  |  | See access and equity
4 – Human rights |  |  | Rights abuses, including against indigenous people | Ensure HRBA through use of the human rights marker
5 – Gender equality and women’s empowerment |  |  | Failure to engage women in decision-making. Women not enjoying equal access to resulting service | Ensure the continued adherence to the specifications of CEDAW and ILO Conventions.
6 – Core labour rights |  |  | Community contracts that are not implemented according to ILO standards | Ensure the project is accordance with ILO Conventions. Ensure that no underage staff or children are employed in the project.
7 – Indigenous peoples |  |  | Failure to engage indigenous people in decision making. Indigenous people not enjoying equal access to resulting service. See also access and equity. | Ensure that the components of the UNDRIP Declaration and ILO Convention 169 on Indigenous tribes and people, are respected and upheld.
8 – Involuntary resettlement |  |  | Project actions lead to unintended resettlement consequences | Ensure that no (sub-) projects are undertaken that involve forced eviction
9 – Protection of natural habitats |  |  | See conservation of biodiversity
10 – Conservation of biological diversity |  |  | Impacts of local, upstream and downstream biodiversity as a result of project activities | Ensure adherence to the Convention on Biological Diversity and species included within the IUCN Red List.
11 – Climate change |  |  | The project causes maladaptation either in the project sites or upstream or downstream (identified in the proposal anyway, despite low risk) | Ensure VA is completed locally accepted/ endorsed
12 – Pollution prevention and resource efficiency |  |  | See conservation of biodiversity | Include impact monitoring through implementation of the project
13 – Public health |  |  | Communities may use some machinery and/or not have protective equipment. Unexploded ordinance is present in some areas | Ensure Projects are not implemented in areas that have not been demined in accordance with the Lao National Unexploded Ordnance Programmes. Ensure that ICSC international health and safety standards are clearly accessible and understood
14 – Physical and cultural heritage |  |  | N/A
15 – Lands and soil conservation |  |  | See conservation of biodiversity
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes, but no unanticipated ESP risks occurred, aside from those planned for. See monitoring measures below, designed to caputre all risks before and during contruction. None occurred beyond this
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | UN-Habitat conducted a training with NPSE Attapeu, on implementing and environmental and social management plan with a view to compliance with the ESP of the Adaptation Fund. This also included new information derived from the vulnerability assessment
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Village chiefs have been made aware of the ESP and the grievance mechanism. All contractors obliged to follow the ESP as laid out in the project document
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The arrangements have worked, though need to be stepped in scope as the project reaches more villages in coming years
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Yes, at present
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11] |  | No updates were deemed necessary
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12]+A62 | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
AF-Talui-LCB: Supply & Delivery of water pipes/fittings, Local Competition Bidding in Sekong dated 27 Dec 2018 | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk | Yes | The following institutions were present during the Consultation in each village (Village chief, Village deputy, Lao Women Union, Lao Youth Union and People of the village) | Please state the number of persons consulted??? | Principle 3: participatory mechanism established that ensures that any vulnerable group would not be subject of discrimination or have negative impact as a result of the activity. Principle 6: The implementation in compliance with the 2014 Labour Law. Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health/Basic construction safety measures | 1. Engineering survey 2. Water demand 3. Primary design 4. Detail design 5. Monitoring physical work 6. Training on O & M and establish water use group
AF-Lahang-LCB: Supply & Delivery of water pipes/fittings, Local Competition Bidding in Saravane dated 24 Dec 2018 | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk | Yes |  | Please state the number of persons consulted??? | Principle 3: participatory mechanism established that ensures that any vulnerable group would not be subject of discrimination or have negative impact as a result of the activity. Principle 6: The implementation in compliance with the 2014 Labour Law. Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health/Basic construction safety measures
AF-Champao-LCB: Supply & Delivery of water pipes/fittings, Local Competition Bidding in Attapeu dated 15 Dec 2018 | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk | Yes |  | Please state the number of persons consulted??? | Principle 3: participatory mechanism established that ensures that any vulnerable group would not be subject of discrimination or have negative impact as a result of the activity. Principle 6: The implementation in compliance with the 2014 Labour Law. Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health/Basic construction safety measures
AF-Keumsang-LCB: Supply & Delivery of water pipes/fittings, Local Competition Bidding in Attapeu dated 15 Dec 2018 | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk | Yes |  | Please state the number of persons consulted??? | Principle 3: participatory mechanism established that ensures that any vulnerable group would not be subject of discrimination or have negative impact as a result of the activity. Principle 6: The implementation in compliance with the 2014 Labour Law. Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health/Basic construction safety measures
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
N/A
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | A limited assessment was conducted. However, there is no gender annex per se - rather it was included under Gneder Equality and Women's Empowerment in the ESP Annex
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | No
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
Almost all village chiefs and local government staff in Laos are male |  | Satisfactory - some progress has been made at including women, including increasing engagement with Lao Women's Union and ensuring that women have decision-making responsibility at the village level
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | Requesting EE and government partners to promote female representatives and participants at trainings and events
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes, partially, There has been an increase in female representation. However, the baseline is very low and very few women work in government departments, especially at sub-national level. Almost all village chiefs are male. It is difficult to change this
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | NPSE Attapeu has ensured that women are more involved in decision making at the village level. E.g ensuring that maintenance arrangements include women
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | Yes, in the 6 initial villages this has been successful so far. However, in more remote villages where traditional beliefs hold this will be difficult in the future.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | None per se. However, as above, the project is working with a very low baseline of inclusion of women at the sub-national level
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None raised relating to the AF Gender Policy
Yes
No
Partially

## ESP Guidance Notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1.1 | Number of local vulnerability assessments reports that are available/processed to national government agencies for policy making. | 0 | 3 provincial and 8 district reports complete | 3 Provincial, 8 district and 189 village level assessments complete (provincial and district level assessments in draft)
Output 1.1.1 | Number of climate change vulnerability and disaster risk assessments produced at the provincial, district and settlement/community level | 0 | 3 Provincial 8 district (highlighting specific vulnerabilities in 189 settlements | 3 Provincial, 8 district and 189 village level assessments complete (provincial and district level assessments in draft)
Outcome 1.2 | Number of targeted institutions with increased capacity to reduce vulnerability to climate variability risks | 0 | 2 National government agencies (MPWT and MoNRE) have actively participated. All sub-national governments have been involved throughout (3 provinces, 8 districts) | National Government / MPWT (1) can provide guidance to sub-national level on resilient infrastructure development - Provincial governments (3) and district governments (8) actively participate and guide community level adaptation investments
Output 1.2.1 | Number of staff trained to roll-out the project and to improve community-level resilience. |  | 17 Province level staff trained | National-level government (20), Provincial-level (30) District-level (40) National-level government (20) Provincial-level (30) District-level (40) National-level government (20) Provincial-level (30) District-level (40)
17 district level staff trained
Outcome 1.3 | Provincial governments and district authorities are aware of pro-poor, rights-based, gender sensitive, climate change adaptation options | 0 | 3 provincial and 8 district plans under development | Provincial governments and district authorities are aware of pro-poor, rights-based, gender sensitive, climate change adaptation options
Output 1.3.1 | Number of government entities on provincial and district level that developed initial climate change action plans and adaptation options. | 0 | 3 provincial development plans and 8 district development plans under development, at final draft stage | 3 provincial development plans 8 district development plans
Outcome 2.1 | No. of targeted communities with increased capacity, incl. representatives of all ethnicities, women (50%), young people, elderly, people with disabilities and other people with vulnerabilities participate in the planning process | 0 | 8 district development plans | 8 district development plans
Output 2.1.1 | Number of actionable plans developed | 0 | Plans in the 6 villages where construction is underway | 189 (or less if clustering is possible)
Output 3.1 | Number of physical infrastructure improved or newly constructed to withstand climate change and variability- induced stress | 0 | 1,108 beneficiaries from 4 further villages | 47,000 people should be beneficiaries
Output 4.1 | No of materials | 0 | 2 main products online - story map and 189 village level vulnerability assessments (counted as 1 product) | Still to be defined

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Contact with the government has continued to be very smooth. If the working relationship with the government were to deteriorate (and there is no sign that it will) then implementation wwould be much more difficult. Fund flow from UN-Habitat to NPSE Attapeu is critical to timely implementation. While this hasn't been problematic so far in the project's implementation, it is imperative that UN-Habitat ensure that fund flow continues as the project enters the main procurement phase of Component 3, where te bulk of the funds are to be spent. Lesson learned, therefore, is that positive relations with the government is critical throughout the project life-cycle.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | MTR - Spending continues to be in line with original projections as infrastructure construction begins. Component 1 has slightly underspent. However, there will be further costs associated with the publication of the vulnerability assessment reports, which have yet to be incurred
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Component 2 has now been fully aligned with Component 3 in terms of the implementation timeframe. This is because UN-Habitat and NPSEs-Attapeu, Saravane & Sekong have agreed that it is critical to build community capacity based on the specific infrastructure being built in a village and that this capacity building should be concurrent with construction.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Yes gender considerations have been taken into consideration. However, it remains a challenge to engage women at sub-national government level, for example, due to a lack of female staff. In the Programme Management Committees and Project Implementation Units (PIUs) for example, only three of 49 representatives are women. It was not possible to increase female participation in these bodies. Lao Women's Union have now been engaged in the project, and women have been engaged at the village level in the monitoring and management of the infrastructure construction
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Cost planning is of critical importance. The project has done everything it can to keep costs within budget, but the number of villages (189) makes it challenging with the budget available. The activities under component 2 now need to keep pace with construction under Component 3 - as community capacity is essential to guarantee the continued functionality of the infrastructure.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The potential remains substantial, especially now, at MTR, initial results are emerging and lessons learned can be gathered. Publication of the VA reports will happen soon and is critical for raising knowledge and awareness of the work undertaken so far. Finance remains a barrier to further replication of small scale infrastructure in the country. However, additional financial support can be found then we assess there to be a very high chance that the approach can be replicated elsewhere
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Please see above regaridng complementary capacity building. The infrastructure investments are so far working well. However, further consideration needs to be given to ensure that access can't be denied to people in the future. While this problem has not emerged so far, the potential remains, despite capacity building and safeguarding measures.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | See above. There is substatial interest and willingness to scale up, but finance remains the biggest challenge. The Ministry of Public Works and Transport is especially receptive to efforts to upscale infrastructure construction to new villages in the general project area and other provinces in Laos that are highly vulnerable to the impacts of climate change.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Adaptation through water access is evident in the 6 villages where construction has been completed, and according to site visits conducted in the formulation of the MTR, there is universal satisfaction among villagers
What measures are/have been put in place to ensure sustainability of the project/program results? | The training under Component 2 ensures that communities have the capacity to operate, manage and maintain the facilities. In the future, a small fee may be required to ensure financial sustainability of the investments
What measures are being/could have been put in place to improve project/program results? | So far, the project has made very soud progress toward its desired results. The training to communities is being rolled out faster and more emphasis is being placed on organising communities
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The project is very much driven by the date it generates and the information it produces. The vulnerability assessment (at provincial, district and village level gave the local government up to date, evidence to improve decision making relating to infrastructure and socio-economic evelopment. The action plans and associated knowldge, such as the google earth model help to visualise the complex information generated by the project. The project also has a brochure and exhibited a poster at the IPCC Cities and Climate Science conference in Edmonton, Canada, in 2018. The challenge is now to publish the knowledge products more widely - beyond the project's immediate stakeholders, for a wider audience
If learning objectives have been established, have they been met? Please describe. | Learning objectives are incorporated into the activities of Output 2.1.1. Under this, the objective is that a number of people, with as equal balance as possible of men and women, learn the basic techniques required to operate and maintain the infrastructure. At the provincial and national level, knowledge is core to Outcome 4 (and part of Outcome 1). The objective of publishing the vulnerability assessments is that provincial and national level stakeholders learn how to use climate related information in the planning and decision making
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | The vulnerability assessments will soon be published, improving the access of anyone who wishes to see the project's data. Otherwise, some data has been challenging to access because it is not public. The VA process relied heavily on the census data, for example, which is not publicly available and therefore this would be difficult to replicate for other agencies if they were to attempt to replicate the exact approach of this project
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes, because having villagers who can take responsibility for the infrastructure, and conduct basic management, operation and maintennance of it is critical for both the achievement of the project's outcomes and its sustainability
|  | 480000 | 34.2857
2142000

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | LAO/MIE/DRR/2016/1
Implementing Entity | United Nations Human Settlements Programme
Type of implementing entity | MIE
Country | Lao People's Democratic Republic
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total | 47000 | 47000 | 60000 | Total | 3371 | 3371 | 0 | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries | 65% | 65% | 65% | % of female beneficiaries | 52% | 52% | 0% | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 30% | 30% | 30% | % of Youth beneficiaries | 48% | 48% | 0% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total | 200 | Drought | 4: Effective | Total | 200 | Drought | 4: Effective | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted | 15% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 3 | Multi-sector | Regional | 1: No plans conducted or updated | 200 | Water management | Regional | 3: Risk and vulnterability assessments completed or updated | 200 | Water management | Regional | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  | 0 |  | Geographical coverage |  | 0 |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 100 | Multi-sector | 2: Low capacity | Total | 100 | Multi-sector | 4: High capacity | Total | 100 | Multi-sector | 2: Low capacity | Total
|  | % of female targeted |  |  |  | % of female targeted | 25% |  |  | % of female targeted | 25% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% |  |  | 100 | 25% | Public |  | 100 | 15% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Multi-sector | 2: Low capacity | Public | Regional | Multi-sector | 4: High capacity | Public | National | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 100 |  | Multi-sector |  | 7 |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 47000 | 50% | 1: Aware of neither |  | 47000 | 65% | 4: Mostly aware |  | 3371 | 48% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Regional | 2: Partially responsive (Lacks most elements) |  | Water management | National | 4: Mostly responsive (Most defined elements) |  | Water management | Regional | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Multi-sector | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Multi-sector | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved |  | Multi-sector | 1: Health and Social Infrastructure (developed/improved) | 2: Somewhat improved
|  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Water management | 100 | Community |  | Water management | 6 | Community |  | Water management
|  | 0 | Multi-community |  | Water management | 20 | Multi-community |  | Water management | 0 | Multi-community |  | Water management
|  | 0 | Multi-community |  | Health | 10 | Multi-community |  | Health | 0 | Multi-community |  | Health
|  | 0 | Multi-community |  | Multi-sector | 10 | Multi-community |  | Multi-sector | 0 | Multi-community |  | Multi-sector
|  | Baseline information |  |  |  | Target information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Multi-sector | biological assets | 3: Moderately effective |  | Multi-sector | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 3 | ha protected | 2: Partially effective | Forests | 3 | ha protected | 4: Effective | Forests | 1 | ha protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 3 | ha rehabilitated | 2: Partially effective | Forests | 3 | ha rehabilitated | 4: Effective | Forests | 1 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 10 | ha protected | 2: Partially effective | Catchment area/Watershed/Aquifer | 10 | ha protected | 5: Very effective | Catchment area/Watershed/Aquifer | 1 | ha protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 9400 | Agricultural-related |  | 1000 | 9400 | Agricultural-related |  | 1500 | 9400 | Agricultural-related |  | 1100
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 |  |  |  | 2 | Multi-sector | National | Policies or guidance | 0
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 |  |  |  | 3 | 4: Enforced (Most elements implemented) |  | 4: Effective | 3 | 2: Partially not enforced (Most elements not implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.